## General
SECTION 1 – GENERAL DETAILS
Project Name: | SP1 NZTA Ohakea Weigh Right | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | 558020 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi | [5 empty] | B | Report by Breach | CM | Construction Manager | Christopher Colman | CC
Contract Number: | 7456 | [5 empty] | C | Check | CR | Cust. Representative (WSP Engineers) | Mark Frampton & Alex Brown | MF / AB
Area/ Sub-System: | Weigh In Motion - South |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A
ITP Number: | 558020-DOW-ITP-PC-0031_v2 (WIM South) |  |  | Version: | 2 |  | H | Hold Point | OP | Operations Manager | N/A
ITP Description: | Installation of WIM plates, ANPR foundation and camera, Cabinet installation and rebuild the pavement | [5 empty] | I | Inspection | PM | Project Manager | Krishna Marangat | KM
Discipline: | Earthwork, Concrete, Pavement | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Gavin Hosnell | GH
Specification: | NZTA B/2, NZTA M/3, NZTA M/4, NZTA M/6, NZTA M/10, NZTA M/23, NZTA M/27, NZTA P/3, NZTA P/11, NZTA Q/5, NZS 4402, NZS 4407 | [5 empty] | O | Operation | QM | QA Manager | Steve Darby | SD
[7 empty] | R | Review | SE | Site Engineer | Ribin Jose | RJ
Drawings: | Waka Kotahi NZ Transport Agency SH3 & Pukenui Rd Intersection, Ohakea Weigh Right Programme. Civil - For Construction | [5 empty] | S | Subcontractor | SP | Supervisor | Gavin Hosnell (Civil) & Gareth Mclellan (Drainage) | GH / GM
[7 empty] | V | Visual Verification | ST | Superintendent | N/A
Prepared By: | Ribin Jose |  |  | Date: | 2023-11-15 |  | W | Witness Point | SV | Surveyor | Stefan Killian | SK
Quality Specified: | [8 empty] | WS | Welding Supervisor | N/A
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Ribin Jose |  |  | Signature: |  |  |  |  | Date: | 2024-09-06
Downer Approval |  | Name: | Krishna Marangat |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Alex Brown |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS
Item No. | Activity/ Task Description | Standard / Specification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
3.1 | General Preliminary
3.1.1 | Survey Setout | Downer | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Survey Records | Prior to Works | Document review | H | SV
3.1.2 | Service Location | Downer | Complete the on site check to identify, locate and protect all services. | Service location documents | Prior to Works | Document review | R | SE
3.1.3 | Internal Permits | Downer | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Internal Permits | Prior to Excavation | Document review | R | SE
3.1.4 | External Permits | Downer | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | External Permits | Prior to Excavation | Document review | R | SE
3.1.5 | Approved Construction Drawings | Downer | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | IFC Drawings | Prior to works start | Document review | R | SE
3.2 | Receiving Materials/Parts - ANPR + Cabinet Pad Foundation
3.2.1 | Concrete mix design | As per Design Specification 30Mpa | Concrete Mix design for each mix comply with the requirements of the Project Specification | Concrete supplier mix designs | Submitted to Client Engineer for approval before construction | Document review | H | CR
3.2.2 | Reinforcement | As per Design Specification | Reinforcing bars and mesh shall comply with AS/NZS4671:2001. | Mill Certs | Each Lot | Document review | R | SE
3.3 | Receiving Materials/Parts - WIM plates + Ducts + Chamber
3.3.1 | Galvansied Ducts | As per Design Specification | Galvanised steel pipe larger than DN 80 must be Schedule 40 Seamless Line Pipe to ASTM A106 and hot dip galvanised following fabrication | Product data sheet/Docket | Per Delivery/Batch | Visual, Document Review | R | SE
3.3.2 | Concrete Chamber | As per Design Specification | Manholes or Precast Structures to be cast to NZS 3109 with surface finish to NZS 3114 standard | Product data sheet/Docket | Per Item/Batch | Visual, Document Review | R | SE
3.3.3 | Embedment / Bedding | As per Design Specification | Free draining river cobble or similar bedding material | IANZ Test Reports | Prior to Works | Document review | R | SE
3.3.4 | Concrete mix design | As per Design Specification Minimum of 20Mpa | Concrete Mix design for each mix comply with the requirements of the Project Specification | Concrete supplier mix designs | Submitted to Client Engineer for approval before construction | Document review | H | CR
3.4 | Receiving Materials - Pavement Materials
3.4.1 | Mix Design Approval AC20 | NZTA M10:2020 - 3.1 , 3.6 | The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use. | Approved Mix Design | Prior to Use | Document review | H | CR
3.4.2 | Mix Design Approval SMA10/12.5 | NZTA M27:2020 - 3.1 , 3.6 | The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use. | Approved Mix Design | Prior to Use | Document review | H | CR
3.4.2 | Bitumen | NZTA P11: 2007 | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification. | IANZ Lab Reports | Prior to Use | Document review | H | CR
3.5 | Receiving Materials/Parts - Shoulder Widening and Sealing
3.5.1 | AP65 - Source Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 10,000m3 | Document review | H | CR
3.5.2 | AP65 - Production Property Tests and Sampling | TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ | Document review | H | CR
3.5.3 | AP65 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR
3.5.4 | AP40 - Source Property Tests and Sampling | TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio. | IANZ Lab Reports | 10,000m4 | Document review | H | CR
3.5.5 | AP40 - Production Property Tests and Sampling | TNZ M/4: 2006 - 4 NZS 4407 : 1991 | The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control. | IANZ Lab Reports | 3 per source initially, then 1/1000m³ | Document review | H | CR
3.5.6 | AP40 - Testing for Layer Compaction - MDD | TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3 | The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). | IANZ Lab Reports | 5,000m2 | Document review | H | CR
3.5.7 | Sealing Chip - Source Property Tests and Sampling | TNZ M/6: 2019 - 4 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | IANZ Lab Reports | Before Supply and Every 10,000m3 Thereafter | Document review | H | CR
3.5.8 | Sealing Chip - Production Property Test Sampling | TNZ M/6: 2019 - 5 | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | IANZ Lab Reports | Every 500m3 | Document review | H | CR
3.5.9 | Bitumen - Quality Testing | NZTA M01: 2022 - 6 | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01. | IANZ Lab Reports | One test per grade supplied | Document review | H | CR
3.5.10 | Bitumen - Supply Testing | NZTA Q05: 2022 - 6.2 | The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05. | IANZ Lab Reports | Every 200 tonnes supplied. | Document review | H | CR
3.6 | Receiving Materials/Parts - Safety Barrier
3.6.1 | Barrier Mill Certs | NZTA M23 AS/NZS 3845 | Compliance documentation | Mill Certs | Prior to commencement of works | Document review | R | SE
3.6.2 | Concrete mix design | As per Design Specification | Concrete Mix design for each mix comply with the requirements of the Project Specification | Concrete supplier mix designs | Submitted to Client Engineer for approval before construction | Document review | H | CR
3.6.3 | Guard Rail | As per Design Specification, Appendix E, Section 2.1.2 | The Contractor will in advance nominate type of compliant system and manufacturer they propose to use and agree this with the Engineer. | Concrete supplier mix designs | Engineer for approve before construction | Document review | H | CR

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS
Item No. | Activity/ Task Description | Spectification | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Signature | Date
[7 empty] | Key | By (Role Key)
4.1 | ANPR + Cabinet Foundation - Construction
4.1.1 | Construction Location | Design Location | Proposed location of construction to be staked out to the engineer for review prior to construction | Approval letter, Photos | Prior to each foundation build | Survey Setout | V | CR
4.1.2 | Ground Compaction Test | Downer Standard | Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers | Test reults, Location of Test | For each Foundation | Check | C | SE
4.1.3 | Reinforcement and Hold Down Bolt Inspection | As per Design Specification | Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete. | Pre pour, Photos | Prior to each foundation pour | Visual Inspection, Dimensional Inspection | H | CR,SE
4.1.4 | Electrical & Comms Ducts Placement | As per Design Specification | Compliant with the construction drawings | Pre pour, Photos | Prior to each foundation pour | Visual Inspection | H | CR,SE
4.1.5 | Pre-Pour Inspection | Downer Standard | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | Pre pour, Photos | Prior to each foundation pour | Visual Inspection | H | CR,SE
4.1.6 | Delivery Dockets | Downer Standard | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | Dockets | Each Pour | Review | R | SE
4.1.7 | Compression Testing | As per Design Specification | One specimen from each pour shall be tested at 28 days. | Test Results | one test per 50m³/per pour | Review | R | SE
4.1.8 | Post Pour Inspection | Downer Standard | Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings. | Post Pour, Photos | Each Pour | Visual Inspection | R | SE
4.1.9 | Defective Concrete Finishes | Downer Standard | Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer. | NCR | Prior to minor repair | Review | A | SE
4.2 | WIM plates and Ducts Installation
4.2.1 | WIM plate location | Design Location | Set-out to be completed by Surveyor | Approval letter, Photos | Each | Survey Setout | D,W | SV,CR
4.2.2 | WIM plate installation | Design Location | To be completed as per the design and technical requirements, under supervision of PAT NZ | ITP Sign off/Photos | Each | Visual Inspection | V | SE
4.2.3 | Supply and installation galvanised pipe | As per design drawing/notes Sheet No: C 8102 | 100mm Galvansied pipes one each to the line of WIM plate location from concrete chamber one connecting the chamber to cabinet | ITP Sign off, As-built and Photos | Before backfill | Visual Inspection | V | SE
4.2.4 | Supply and installation concrete chamber | As per design drawing/notes Sheet No: C 8103 | To be completed as per the design and technical requirements | Photos, Checkcheet | Each | Visual Inspection | V | SE
4.3 | Pavement Construction
4.3.1 | Preliminary
4.3.1.1 | Service Location | Downer Standard | Complete the on site check to identify, locate and protect all services. | ITP Sign off/Photos | All | Visual Inspection | V | SP
4.3.1.2 | Pre-Construction Test Pits | Scala test as per specification | Minimum CBR 3.5% as per design notes Drawing/Notes Sheet No :C 8103 | Test report | 3 test pits per site | Report review | R | SE
4.3.1.3 | Undercut - If needed | Visual Inspection | Undercut to be treated as per specific Note: Drawing/Notes Sheet No : TD0002 | Undercut need to reproof roll after backfill and NDM comapction Check sheet, DN-QC-05, Photos | Area of undercut needed | Visual Inspection | V | SE
4.3.2 | Pavement and Surfacing
4.3.2.1 | Visual inspection and level check | Depth check as per the design drawing spec | Check the entire length of pavement cut to the height as per design and tie ins are cut as per details | Photos | Each lane | Visual and dimensional | Witness Point | SE
4.3.2.2 | Subgrade scala | minimum CBR 3.5% as per pavement detail | Ensure achieve minimum 2 blows per 100mm which is equivalent to 3.5% CBR | Scala sheet | 1 per 20m alternative wheel tracks | Check | Hold Point | SE
4.3.2.3 | Contingency undercut | additional undercut as per pavement detail | ensure achieved the additional cut of 150mm as per design | Photos | Each lane | Visual and dimensional | Witness Point | SE
4.3.2.4 | geofabric | As per Design Specificationdetailed in Drawing number TD002 Rev 03 | instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. | Photos | whole area | Visual | Witness point | SE
4.3.2.5 | Subbase Placement and compaction | NDM - Dry Density | Mean DD ≥ 95% of MDD Minimum DD ≥ 92% of MDD | NDM Test Results | 5 tests minimum evenly placed alternative wheel tracks each lift | Check | Hold Point | SE
4.3.2.6 | Subbase level check | Survey As-built and Project Specification 3.7.7 | No area of pavement shall pond water. Grade to be set at 2.5%. Subbase layer to be within -15mm / +5mm of design levels | As-built survey | Full width in every 10m | Dimensional | Witness Point D | SV
4.3.2.7 | proof roll | As per project specification, Section 2.10 and NZTA F/1, 10.5.1 | Proof roll the whole area of pavement usign a 8 ton roller to check the defelction which is more than 3mm | Photos, videos | whole area | Visual Inspection | Hold Point | CR, SE
4.3.2.8 | Heavy Tack & Blind | Minimum Residual Bitumen of 1.2 L/m2 as per project pavement specification | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. Minimum 1.2L/m2 residual bitumen spray rate. | Run sheet, QA from Sub, Photos | Entire length of pavement | Visual Inspection | V | SE
4.3.2.9 | Asphaltic Concrete - Base | NZTA M27 | 210mm of AC20 (B60) Lifts of 105/105mm As per project based pavement specification | Run sheet, QA from Sub | Entire length of pavement | Dimensional Inspection | D | SE
4.3.2.10 | Asphaltic Concrete - Surfacing | NZTA M27 | 50mm of SMA10 As per project based pavement specification | Run sheet, QA from Sub | Entire length of pavement | Dimensional Inspection | D | SE
4.3.2.11 | Thickness | Contract Specification, Section 3.7.15 | Thickness as per design lift with +/-10mm (AC20) Thickness of 50mm with +/-5mm (SMA10) | ITP Sign off | Continuous | Visual | C | SE
4.3.2.12 | Finished surface | Contract Specification, Section 3.7.16 | No more than 3 mm variation under a 5 m stright edge | ITP Sign off | Continuous | Visual | C | SE
4.3.2.13 | Air Voids | NZTA M/10 | The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids. | Test results | Continuous | Review | C | SE
4.3.2.14 | Level checks | Survey | Thickness as per design lift with +/-10mm (AC20) Thickness of 50mm with +/-5mm (SMA10) | As-built drawing | 1/20m full width | As-built | D | SV
4.3.2.15 | Line marking | Set out | As per NZTA standard | ITP sign off/ Photos | All | Visual Inspection | V | SE
4.3.3 | Shoulder Extension
4.3.3.1 | Visual inspection and level check | Depth check as per the design drawing spec | Check the entire length of shoulder cut to accommodate 200mm subbase and 50mm SMA | Photos | Each lane | Visual and dimensional | Witness Point | SE
4.3.3.2 | Basecourse Placement and compaction | NDM - Dry Density | Mean DD ≥ 98% of MDD Minimum DD ≥ 95% of MDD | NDM Test Results | 1 per 20m (minimum 5 test) | Check | Hold Point | SE
4.3.3.3 | Degree of saturation | Contract Specification, Section 3.6.7 | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%. | NDM Report | 1 per 20m (minimum 5 test) | Check | C | SE
4.3.3.4 | Basecourse level check | Survey As-built and Project Specification 3.7.7 | No area of pavement shall pond water. Grade to be set at 2.5%. Subbase layer to be within -15mm / +5mm of design levels | As-built survey | Full width in every 10m | Dimensional | Witness Point D | SV
4.3.3.5 | Grade 3/5 two coat Chipseal | As per approved seal design | Ensure the entire length of shoulder sealed as per the approved seal design. Two coat chipseal with Grade 3 and 5 | QA reprot | Entire length | Witness | W | SE
4.3.3.6 | Heavy Tack & Blind | Minimum Residual Bitumen of 1.2 L/m2 as per project pavement specification | Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. Minimum 1.2 L/m2 residual bitumen spray rate. | Run sheet, QA from Sub, Photos | Entire length of pavement | Visual Inspection | V | SE
4.3.3.7 | Asphaltic Concrete - Surfacing | NZTA M27 | 50mm of SMA10 (PG58-V) As per project based pavement specification | Run sheet, QA from Sub | Entire length of pavement | Dimensional Inspection | D | SE
4.4 | Shoulder Widening, Sealing and Surfacing - Construction
4.4.1 | Material Placement | Downer Standard | The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout | Survey / Level Checks | Continuous monitoring. | Check | C | SV, PS
4.4.4 | Basecourse Pavement Layer Compaction | TNZ B/02: 2005 - 7.6 | Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD | NDM Report | 1/10m | Check | H | SE
4.4.5 | Basecourse Layer thickness. | TNZ B/02: 2005 - 5.1 | The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm | Survey / Level Checks | 1/20m Full width | Dimensional Inspection | D | SV or SE
4.4.6 | Surface Shape | TNZ B/02: 2005 - 7.7 | The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.. | Survey / Straight edge Report | 1/20m Full width prior to sealing | Dimensional Inspection | D | SV
4.4.7 | Surface Finish post sweeping | TNZ B/02: 2005 - 7.8 | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept. | Photos | Prior to sealing | Visual Inspection | V | SE
4.4.8 | Preselling Requirements | TNZ B/02: 2005 - 12 | The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%. | NDM Report | 1/10m | Check | C | SE
4.4.9 | PreSeal inspection | TNZ P3 TNZ B02 | The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site. | Hold point Release, ITP Sign off | Prior to sealing | Check | I | SE
4.4.10 | Spray Temperature | TNZ P3 and Project NTC124 | The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC. (Minimum 1.5L/m2 residual bitumen rate.) | Sealing statement | Prior to sealing | Check | I | SE
4.4.11 | Chip Application | TNZ P3 and Project NTC124 | All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying. G3/5 two coat seal. | Sealing statement | For every spray run | Check | I | SE
4.4.12 | Post Seal Inspections | TNZ P3 | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | Engineers Acceptance | Prior to TM Removal and After Final Sweeping | Visual Inspection | H | SE,CR
4.5 | Guardrail - Installation
4.5.1 | Guard rails - Installation | Appendix E, Section 2.1.3 | The Contractor will set out the guardrail location with the Engineer on site. | Hold Point | For each guard rail | Visual Inspection | V | CR & SE
4.5.2 | Guard rails - Checklist | As per the Contract Specification | To complete the check list along with the guard rail installer after the construction | Check Sheet DN-QC-06 Photos | For each guard rail | Visual Inspection | V | SE
4.5.3 | Guard rail completion | NZTA M/23 | All road safety barrier systems (including end treatments and crash cushions): • System checklists to be completed and co-signed by qualified contractor (who has completed the Waka Kotahi IMI workshop) and Waka Kotahi representative. Note: All faults to be rectified before acceptance into network operations (maintenance manual) and network assets register (and RAMM). | Hold Point | For each guard rail | Visual Inspection | V | CR & SE

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type | Inspection |  | Inspection Point/Signature & Date
[7 empty] | Key | By | Downer Signature | Date | Customer Requirements Verification Records/Location
5.1 | Construction Record Compilation | Upon completion of works | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Closed-out NCR/Defects | Post construction | Review | R | SE
5.2 | As-built Survey | Upon completion of works | Ensure all items have been surveyed and records are assembled for asbuilting | As built survey record completed | Post construction | Review | R | SV
5.3 | Red-line As-built Drawings | Upon completion of works | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar | Signed As-built Drawings | Post construction | Review | R | SE,SV
5.4 | Defect, Snag and Punch List | Upon completion of works | Update the project Defect, Snag and Punch List Register | Register | Post construction | Review | R | PE
5.5 | All QA documentation collated & signed-off | Upon completion of works | All signed and closed out | Signed off Documents | Post construction | Review | R | QM