## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 558020-DOW-ITP-PC-0024_v1 Ducting (Open Trench) | itp | 558020-DOW-ITP-PC-0024_v1 Ducting (Open Trench) | 5d35e562-8828-47bf-84f8-b428f69a83e6
| section | Receiving Inspection
| checkpoint | 3.1 - Design
3ee293fc-4ff3-5348-961e-00451218ff5b | note | Inspection Point: Quality Control Activity - Pre-construction
ca4f1ce4-8441-5708-bddf-b92f4d22022a | note | Acceptance Criteria - Ensure that you are working with the latest IFC drawings.
5d0072db-6c67-560f-b7d3-96f70cba06f2 | note | Verifying Document - Drawings
b8b2f7fc-3335-52a0-a3fe-72effe7793e9 | note | Frequency - Continously
db176ef0-76f7-5cde-a95a-e02eee8deaf7 | note | Inspection Type - Document review
7c14bc35-90cb-54a5-bc58-e3d6297b29e0 | note | Inspection: Key - H
9d1e2a69-e3fe-5c0c-9eb7-8387dc094c31 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Permits
5cefd9bc-211b-58f5-8d1c-8afdf8b33609 | note | Inspection Point: Quality Control Activity - Prior to Construction
2cd5f176-4ffa-5ec4-9398-fa1acbacc5fa | note | Acceptance Criteria - Please ensure that the permit to work is the latest and approved, and that Existing Services have been positively identified.
80d640b3-2c40-5351-8079-77603a0da84f | note | Verifying Document - Permit Register
cee4f3e7-d4d6-542e-a684-84b83ca42cfb | note | Frequency - Prior to works.
e8051aa7-4f78-518e-9242-7e1bd6495d59 | note | Inspection Type - Document review
f4b015ed-f7e1-5544-ade1-e83e15d4b767 | note | Inspection: Key - H
ec3854a0-a5a6-5d32-a9bb-10319cfa8481 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - The survey set out of ducting alignment.
f75982b4-fcc8-56cf-a931-cb8a0933ecce | note | Inspection Point: Quality Control Activity - Prior to Construction
c11d68db-7a2f-597c-993c-ff9de0d4239a | note | Acceptance Criteria - Consistent with the IFC construction drawings.
669bf1e5-7066-5376-b337-6836b9609ad9 | note | Note: All positions to be confirmed on site prior to construction
965c22b5-746f-5a2b-ad8c-45e8f76d0fce | note | ○ If trenching needs to intersect or traverse existing services, appropriate temporary protection must be implemented.
1e12108a-407e-5fac-a41a-f91e2f0abaef | note | Verifying Document - Survey set out records
a39dc251-20cb-5870-a5a9-75ee38a641d8 | note | Frequency - Continuous
3e2d7511-759c-5ac9-801a-00f74ac5197e | note | Inspection Type - Document review
82be6313-3da2-5a6d-9dc5-d20157bdbbc7 | note | Inspection: Key - H
05704a25-ab3f-5fbd-a8d0-15364314c798 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Marking out of existing services. Confirm there are no clashes with design and existing services
e2cfe0dd-5b70-550d-99ac-33b9181f24da | note | Inspection Point: Quality Control Activity - Prior to Construction
e061f9ab-0076-5330-b512-6079e8e305ad | note | Acceptance Criteria - Consistent with the IFC construction drawings.
dd779449-945d-5b27-9e19-fbb6b7666341 | note | Verifying Document - Photos
31d5032c-866e-5f62-a2a0-29a2491c9432 | note | Frequency - Continuous
fd551414-e625-5ece-a96b-8338570667fa | note | Inspection Type - Document review
c20c82db-8dec-547f-b04f-4ec5007753ef | note | Inspection: Key - R
a00c549c-a9a0-546f-8520-c073f1d7e25b | note | Inspection: By - SV
| checkpoint | 3.5 - Material Compliance - 50mm or 100mm or 150mm uPVC Ducts
1ef26818-0935-5ea7-97e1-f40358cc479e | note | Inspection Point: Quality Control Activity - Prior to Construction
3a027722-3f6a-5705-9f6b-4fe10dfc161d | note | Acceptance Criteria - Ducts shall comply with AS/NZS 61386:2015 or AS/NZS 2053.2:2001. Orange for Power & Salmon for Fibre, green for telecom. Also required print marking details of the configuration
ebdff09c-6a71-5819-ba87-b461a1dea15b | note | Verifying Document - Product Technical Datasheet, Delivery Dockets
3415da6f-3307-52c1-b9fb-d4f11cf8ca96 | note | Frequency - Prior to work starting on site and upond delivery to site.
dbece926-9eaf-524b-9192-c3e5e0a531c5 | note | Inspection Type - Visual, Document Review
93c607bb-5bdc-581c-aeef-136c236b1b04 | note | Inspection: Key - H
0ac29d95-f358-5df1-91f6-f691bc69def3 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Warning Tape
70cb4e3c-afe3-56da-ace5-826010203dda | note | Inspection Point: Quality Control Activity - Prior to construction.
f0eafab5-29bb-5bbf-a27a-24778e57c665 | note | Acceptance Criteria - Consistent with the ICF drawings
965e7ed2-4c06-5e5c-af7b-c0362f4a9e3b | note | Verifying Document - Photos
5fde0766-4d23-521d-a37c-1cdf01fc6969 | note | Frequency - Prior to work starting on site
4c759eda-9ebe-5cf9-9a28-9abe35211bca | note | Inspection Type - Visual, Document Review
48b34721-b313-567f-889b-b51b9b2695e0 | note | Inspection: Key - V, R
209ed7c9-aaf3-5525-8f95-1c88f3534af5 | note | Inspection: By - PS
| checkpoint | 3.7 - Incoming Material Inspection for all products and good delivered onto the project site
416b00ac-d131-587a-a1cd-eaafa47ab0dc | note | Inspection Point: Quality Control Activity - Material Delivery
ac90355c-badf-516b-b695-08e943542f01 | note | Acceptance Criteria - Material inspected apon arrival for defects, material handling and storage is suitable and follows manufactures guidelines.
af961895-8669-5ee3-8aa5-2e82d1a75b08 | note | Verifying Document - DN-QUA-QC-10
c6a8137c-aee5-55e3-a36a-60a45206b946 | note | Frequency - Prior to works.
6057ce87-9b40-5e16-b9cb-31b54ca9dc79 | note | Inspection Type - Visual, Document Review
085457a9-8117-53c3-8057-82bfaa58db6f | note | Inspection: Key - R, V
1fc64ae2-e44f-5244-81be-94e144dcf1bb | note | Inspection: By - PS
| section | 4.1 Trench Works
| checkpoint | 4.1.1 - Ensure all sevice in conflict with placement of ducting area exposed
5130da16-f2cb-56b0-a428-6680347e83a7 | note | Inspection Point: Quality Control Activity - Potholing
eea2e220-ebb8-53d8-bdcf-375cba581a0b | note | Acceptance Criteria - All existing services have been identified and confirmed. If trenching needs to intersect or traverse existing services, appropriate temporary protection must be implemented.
02aee4a8-15a2-5203-951e-fdc0f1feddba | note | Verifying Document - Visual inspection and documented.
be54f0d4-7c5d-5488-9e9c-e584e37709ba | note | Frequency - Prior to the works starting
505ed06c-52d5-5414-a25b-f779f476885a | note | Inspection Type - Visual
fe761c61-79b3-5eed-8f85-1d172844ec45 | note | Inspection: Key - V
24e9edaf-2acf-596b-8d19-89b80f05395e | note | Inspection: By - PS
| checkpoint | 4.1.2 - Excavations
f1a65b3d-94c8-50b6-9b6d-0e69678bee87 | note | Inspection Point: Quality Control Activity - During construction
0238bd54-213a-51da-bd0a-2b4af71916ef | note | Acceptance Criteria - Alignment and elevation consistent with the IFC drawings. Where excavation depth exceeds 1.5m the trench shields will be used if the excavations exceed 1.5 meters in depth to Work Safe NZ requirements, All works will be undertaken using hydraulic excavators operated by a competent operator, and all waste material will be removed from the site, and taken to a clean fill site
4e6ca3de-a4b6-538a-b89b-1589194a9afb | note | Verifying Document - Photo Records.
7804dbdf-ac3d-549b-8f36-291cd05c33f3 | note | Frequency - Continuous
2e945116-72e7-5483-b1b5-0a7ba86b8ef0 | note | Inspection Type - Visual Inspections, Measure
804ed958-871a-5982-9ca4-bac8ec2ed5dd | note | Inspection: Key - V, M
9153fe57-292d-50d1-bf8b-6ea16d52ba65 | note | Inspection: By - SE
| section | 5.1 ITS Ducts Installation
| checkpoint | 5.1.1 - Placement of Bedding Material
ff564151-4582-52a5-9abc-6f448980ff54 | note | Inspection Point: Quality Control Activity - During construction
dc428d37-5dd0-5c4b-b4e1-2ed48f2c2de9 | note | Acceptance Criteria - 100mm thick or as shown in the IFC drawings
1cc46371-bbb4-5b2b-bb3a-7bb0c78dc54d | note | Verifying Document - Delievry Dockets, Photos
8a42090d-31bd-5cf4-b0dc-c1a39ff95d71 | note | Frequency - Continuous
f5fb9519-54d8-5705-8a2a-2a0a0eb2439c | note | Inspection Type - Visual Inspections, Measure
caf20cf1-8f25-584d-8c4a-b2b588a82688 | note | Inspection: Key - V, M
ad487f8e-266b-56ba-bea7-fa8c94eb7d5f | note | Inspection: By - PS
| checkpoint | 5.1.2 - Laying Ducts for Power and Fibre
36a11a04-8be6-5edf-95e5-fedfc633914c | note | Inspection Point: Quality Control Activity - During construction
92c65cba-9a7e-5392-b4e5-e5348957cbef | note | Acceptance Criteria - As shown in the IFC drawings.
d98530dd-4dd8-52f7-8196-290a3a494bb7 | note | Verifying Document - Photos
01249f78-9780-573d-99d2-d306d2fbb87d | note | Frequency - Continuous
15acd456-e027-565d-b1d4-44fd78197cef | note | Inspection Type - Visual Inspections,
e53834d4-059d-5777-a99e-3005bd5f1601 | note | Inspection: Key - V
2d31e02b-6f7a-5245-b355-38af6e96b035 | note | Inspection: By - SE
| checkpoint | 5.1.3 - Clearances
26614e59-6c4f-582f-ac81-fb6158d308a1 | note | Inspection Point: Quality Control Activity - During construction
df1dba4d-1f01-5a0e-b11c-340fc7a7983c | note | Acceptance Criteria - Check with the as-built data if any services coming close then work to the standard clearance to each services as detailed in project spec
eecb058b-fcf3-502b-8e8b-3e448419b48a | note | Verifying Document - As-built
d7e0c939-28cf-5beb-88ba-14940c6cc3ef | note | Frequency - Continuous
7bc4cc6c-278d-5654-b3d3-f6ec704af83d | note | Inspection Type - Visual Inspection and verification
e5af08d8-28db-5175-8548-4545d3c1f501 | note | Inspection: Key - V, M
a70277b8-0a7d-587c-990a-f7b910515d8c | note | Inspection: By - SE
| checkpoint | 5.1.4 - Placement of Sand Surround Material
48624153-073e-52fb-af64-14f7ae92ed0e | note | Inspection Point: Quality Control Activity - During construction
0a65e3e0-0033-5295-b553-198fc883f6a9 | note | Acceptance Criteria - Dimensions as shown in the IFC drawings
e80921d6-af00-530d-bf6b-5adcdfdceebb | note | Verifying Document - Ducting Installation Checksheet, Photos
db028bda-7e80-56ea-9f6b-4ee03a962566 | note | Frequency - Continuous
411831e5-558a-5ec8-9171-0355ea54e96a | note | Inspection Type - Visual Inspections, Measure
f37995e4-5210-5d52-be33-51a104358623 | note | Inspection: Key - V, M
e59273ab-43a8-5259-a12f-c842d4e77616 | note | Inspection: By - SE
| checkpoint | 5.1.5 - As Built Survey of the laid ducts
b86eb605-f6c4-5eaa-b90b-5e3034de43f5 | note | Inspection Point: Quality Control Activity - During construction
6b8fd851-0297-53d1-b770-18b90c9220aa | note | Acceptance Criteria - Consistent with Issued For Construction drawings
ae101955-5078-56c9-8d3e-2d2471003d1e | note | Verifying Document - As Built Survey Records
a4ee55bf-a5e3-5718-8bbf-e8f68bd8e67c | note | Frequency - After ducts and chambers are installed
038a2383-757e-58a6-97dd-061ead6655c9 | note | Inspection Type - Survey
723e12a5-a8e2-5e24-b83e-afc07a4d9032 | note | Inspection: Key - C
67e3d289-38bd-53a5-983e-c767e4827217 | note | Inspection: By - SV
| checkpoint | 5.1.6 - Backfill ducts with Sand Material or approved material.
e2ebc30d-fba9-528f-9c4c-e5711fdc60f4 | note | Inspection Point: Quality Control Activity - During construction
e6c49902-f36b-5ff8-9845-edd4659b9cfb | note | Acceptance Criteria - Consistent with Issued For Construction drawings
73629d5f-2ef8-5612-95c5-007e2d040b9f | note | Verifying Document - Photos, Delivery Dockets
872dfa5d-e4ae-5e7f-88a4-5ad8c425303d | note | Frequency - After ducts are installed
a99e80af-d755-5354-8082-3ae2c4390086 | note | Inspection Type - Visual Inspections, Measure
9c71ae23-4d90-518b-a07c-d02e57548e1b | note | Inspection: Key - V, M
b2bbe07f-1b85-5c64-ae3c-6415b7ed53b7 | note | Inspection: By - SE
| section | Final Inspection and Handover
| checkpoint | 7.1 - NCR/Defect/RFI Closed out
3615658d-d03e-56a6-8502-3268caf40d40 | note | Inspection Point: Quality Control Activity - Upon completion of works
49decb50-c1b3-5d57-94ad-8c49e0a671b5 | note | Acceptance Criteria - Construction within a tolerance of drawings & specifications
1bd89e91-6ad8-510c-8e09-a2883405a533 | note | Verifying Document - Closed-out NCR/Defects
ca37c90b-e957-5f2f-89d3-92be0f9bbcea | note | Frequency - Review
4dc015d2-164d-5530-a1f0-a1529a9f7cdb | note | Inspection Type - Review
94710f61-d0a7-5e5e-9895-5cf923361d11 | note | Inspection: Key - I/R
8ccb9258-2d85-5f32-b147-2fc3c0de454a | note | Inspection: By - SE
c247559d-02b3-5946-b138-af4139a1dd66 | note | Customer Requirements Verification Records/Location- M-DNZ
| checkpoint | 7.1.1 - As-built Survey
c5dfefb2-1de9-54ff-a247-f649dc188426 | note | Inspection Point: Quality Control Activity - Upon completion of works
dedfcf63-0aa7-529e-adcb-88d03484f2a7 | note | Acceptance Criteria - Comply with the project specification and drawings
95e4258b-8173-5bf1-847c-33df8ac76319 | note | Verifying Document - As built survey record completed
fc2d91f2-a454-5f5a-8c9b-8622c2dff77e | note | Frequency - Review
272c9d69-1331-551f-8cfd-45b1dfa97016 | note | Inspection Type - Review
cf674171-5b83-5c89-887e-2dcc3830042c | note | Inspection: Key - R
1e3711b2-2508-569b-a7cc-74d721e0986a | note | Inspection: By - SE
b0d73ce3-0ba6-5135-ae92-2b48595769d7 | note | Customer Requirements Verification Records/Location- M
| checkpoint | 7.1.2 - Red-line As-built Drawings
3f645d98-7645-5147-9cae-704b0fecfae1 | note | Inspection Point: Quality Control Activity - Upon completion of works
e5b6ca72-a08d-51e6-80b4-13d69d91a0ac | note | Acceptance Criteria - Consistent with the IFC drawings.
4bf69aaf-ed17-5cc7-8a06-29704561aff0 | note | Verifying Document - Signed As-built Drawings
93885447-df27-54b9-a540-0b2ca08d10b0 | note | Frequency - Action
86d697fd-2c53-5b7f-9d84-90707953abf0 | note | Inspection Type - Review
481c4f58-8d85-5868-a71a-70918c66f923 | note | Inspection: Key - R
87fef197-0c84-58bc-a7b5-a84a2d65f0ed | note | Inspection: By - SE/SV
| checkpoint | 7.1.3 - PS3 & Warranties Completed
9bff0822-0276-5dc2-b9f0-8fd71a8a9466 | note | Inspection Point: Quality Control Activity - Upon completion of works
7f64abed-6f86-57aa-8a4d-92c2ec162a31 | note | Acceptance Criteria - Contractual requirement
6347ba60-445d-5336-9d2e-575df35e543d | note | Verifying Document - PS3 & Warranty
0e063d64-4c1a-53b8-af05-ac9a5b6bbdfa | note | Frequency - Review
3c18a04e-c510-523b-ac3c-f77b3cf3b4e1 | note | Inspection Type - Review
7f06655d-87e8-52f4-9494-0af3e1e68b25 | note | Inspection: Key - R
7bbf3fed-33c5-5fd0-a35d-5ae73af57f61 | note | Inspection: By - PE
f0b5bf38-4de5-54d4-948e-ef74bcbb8fda | note | Customer Requirements Verification Records/Location- DNZ
| checkpoint | 7.1.4 - All QA documentation collated & signed-off
59b61387-0927-5656-bce7-398ae42e83a8 | note | Inspection Point: Quality Control Activity - Upon completion of works
3527d0a2-9f56-53af-98f6-c80698fe4b5c | note | Acceptance Criteria - All signed and closed out
c0bc2749-5d36-5fbe-9b0c-1ba27c6806d0 | note | Verifying Document - Signed off Documents
0fa4c507-6916-575f-9669-d2ab16d79def | note | Frequency - Final Internal Review
ae0e7c49-fcad-5c78-991b-ecd2381fc1f0 | note | Inspection Type - Review
a9c3678f-0fdd-5eaf-b10c-f101e78eed1d | note | Inspection: Key - R
5670528e-64e5-5cd1-ad0d-be5246cac3fb | note | Inspection: By - QM
95f5ec61-8295-5807-93dd-dc4e45cfbe29 | note | Customer Requirements Verification Records/Location- M-DNZ
| checklist | 558020-DOW-ITP-PC-0025 (Kerb and Channel Footpath for CVSC) | itp | 558020-DOW-ITP-PC-0025 (Kerb and Channel Footpath for CVSC) | e7fd73ab-c7e4-44e8-9bb2-ce889dce2cc3
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
6ff42663-caba-50a4-86ff-4a3eed7a3384 | note | Standard/Specification - Downer
62a5ae48-0657-5a13-b08a-215a123a3e3f | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
edcec285-6f01-5503-8495-0d5f105068f9 | note | Verifying Document - Survey Records
d1419d39-2e82-55fa-856c-b7d0ce666aaf | note | Frequency - Prior to Works
3897ac41-4f3e-552a-a430-601e5e87db3a | note | Inspection Type (Visual, other) - Document review
5b96450a-36a5-59de-a15c-cea5788be1bd | note | Inspection: Key - H
cc63c634-549b-5196-ab7e-891d9f7bc313 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
1dc7b6db-adf8-5ab8-be50-01bba6cb2cfc | note | Standard/Specification - Downer
dd1ac149-5ebd-5fc6-80fe-df33077797d8 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
946991ee-a4fd-553f-be7b-03ccbf13612c | note | Verifying Document - Service location documents
bf449cde-d8c3-57b6-8fed-e03cf4ca6491 | note | Frequency - Prior to Works
a6dffd43-96ea-5798-aca6-e967c88d8578 | note | Inspection Type (Visual, other) - Document review
919aa612-687d-5c82-bfa7-a2fdb23db6ea | note | Inspection: Key - R
a419d8ad-f983-5c56-840b-cd6ef2e0d40c | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
e6f99df7-8ef5-529c-92e3-0c32a5f445b4 | note | Standard/Specification - Downer
10e84087-d3ab-5c31-b141-540fc8a16ebd | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
6f5f43f8-d040-55ca-af48-8744ebc29f33 | note | Verifying Document - Internal Permits
fe1aa059-30d5-5dac-bfc8-472026e9ded6 | note | Frequency - Prior to Excavation
ca5825f1-f808-502e-b3c0-862c73b6b417 | note | Inspection Type (Visual, other) - Document review
7c4a056c-0eb7-5117-af2f-c3bfc2909161 | note | Inspection: Key - R
faa612d5-d457-5c30-a4d3-5cfe51b34eed | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
34ea12bd-0843-5572-b9e9-e212dd676951 | note | Standard/Specification - Downer
5c384919-4c5a-565f-81a3-fc6a635e7182 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
49a1388d-69ba-53ad-acd4-6c84301a86ee | note | Verifying Document - External Permits
c5fa36ec-3eaa-50de-97fa-d76651c811a2 | note | Frequency - Prior to Excavation
f937e38f-a32b-5add-af00-0def3d76fed9 | note | Inspection Type (Visual, other) - Document review
4d952046-212b-58fe-b780-b8837024ec17 | note | Inspection: Key - R
b97db96d-b824-556f-bb37-86295e3e7d16 | note | Inspection: By - SE
| checkpoint | 3.1.5 - Approved Construction Drawings
a2c105e5-b750-5b4a-9fc9-e831f694194a | note | Standard/Specification - Downer
a5b959e0-b6c9-58b1-a855-0de214b8ec48 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
0a5d5655-c8eb-502c-876e-920bf78e30d6 | note | Verifying Document - IFC Drawings
d07a1501-ee86-5b17-8a72-98d0bd22e02a | note | Frequency - Prior to works start
0103332e-409f-5de2-ba34-edc39f8dc02a | note | Inspection Type (Visual, other) - Document review
0b0b5a9c-c03e-50d2-aa2b-9cabd6e0ed4a | note | Inspection: Key - R
0465cd25-d34d-50a1-85c0-85269fc6c2f7 | note | Inspection: By - SE
| section | 3.2 Receiving Materials/Parts - Kerb & Channel/Nib
| checkpoint | 3.2.1 - Concrete mix design
12e5be53-ff8e-5992-a171-666b13e2448b | note | Standard/Specification - Pre-construction
05abbd38-4f6f-5d85-82dd-15e4ece2beed | note | Acceptance Criteria - 20Mpa concrete as per design notes, Drawing/Notes Sheet No :C 5110
ee058f54-9b17-5558-92f8-6690dca937d2 | note | Verifying Document - Mix design
80603c4e-70b5-5fe3-8f3c-eb4afe040ab8 | note | Frequency - Per type of mix
7856bc3a-2a0e-5d1d-af48-22037e701c04 | note | Inspection Type - Document review
983ee14d-c9c9-5c43-872b-d3dece7a2841 | note | Inspection: Key - H
bce90500-8d63-58ba-b8e2-0e143953a32c | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.3 Receiving Materials/Parts - Footpath
| checkpoint | 3.3.1 - Concrete mix design
74d1af8b-ab40-52a4-9e6d-fde97748570c | note | Standard/Specification - Pre-construction
1b61d322-ad5d-5626-a683-190af5a039ce | note | Acceptance Criteria - 20Mpa concrete as per Civil Technical Spec Section 5.3
499c67d8-2e68-5f9d-9c1b-c60e1c96c525 | note | Verifying Document - Mix design
280b0a34-93ad-5045-ae8b-056484a6d5ad | note | Frequency - Per type of mix
561d5e10-92f2-59ef-adcb-76bd2eb680e7 | note | Inspection Type - Document review
3be9699b-1bd1-5ca1-8956-015d1d5824bd | note | Inspection: Key - H
88df18a3-76d5-548c-8c44-9c23aa169a3b | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - Steel reinforcement
c6a5109c-df73-52c6-9bd8-81c42d1f6637 | note | Standard/Specification - Pre-construction
f4a689a1-922c-5c45-aa4c-4277bd368790 | note | Acceptance Criteria - As per Civil Technical Spec Section 5.3
a2c8a621-e804-5265-b93a-eab4c304a583 | note | Verifying Document - Material Certificate/Docket, Photos
6b0d30da-9791-50d8-b063-cb3021be2c6c | note | Frequency - Per Delivery/Batch
f50335ab-5fd1-5842-a57b-f439d8c83df1 | note | Inspection Type - Visual, Document review
3730c899-42ec-5676-a553-a4e17b872a49 | note | Inspection: Key - R
2f597a11-91f9-5d9e-8685-5bcf7781801f | note | Inspection: By - SE
| section | 4.1 Kerb & Channel/Nib
| checkpoint | 4.1.1 - Service Location
8af0ff9a-45b2-51be-aeb0-4e20c077ba3b | note | Standard/Specification - As per TDS
b9a0304e-f2bc-5620-929d-3716720343d2 | note | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
4695c94e-a592-5abf-8769-2ca8b5a38209 | note | Verifying Document - ITP Sign Off/Photos
e0d7d344-71ed-58f3-bfb4-94a85f3374d4 | note | Frequency - Prior to the works starting
4d9ccd54-b538-588f-9fde-555909621da3 | note | Inspection Type (Visual, other) - Visual Inspection
bdba2f2c-3ad8-5128-a5e8-2a71b3fc74b9 | note | Inspection: Key - V
4c41e75e-bac8-5de0-a14d-6a1172a4988c | note | Inspection: By - SP
| checkpoint | 4.1.2 - Kerb/Nib Location
99cc1b36-d86a-53d0-b305-3d765fd99cf5 | note | Standard/Specification - As per design
fa6b11dc-27e5-5330-859e-f87c55011977 | note | Acceptance Criteria - Surveyor to set-out location of kerb & channel for foundation preparation
58515221-f2ed-57dd-ac1e-cd21678364a4 | note | Verifying Document - ITP Sign off
67c746a0-ff9e-52c5-8004-0cbba5a4a543 | note | Frequency - Prior to constructing foundation
4134a162-643d-59aa-9096-0c501bac000c | note | Inspection Type (Visual, other) - Survey Setout
4367054b-016b-5fd2-8c44-bca54aacd9f4 | note | Inspection: Key - D
fae20c9e-a7c3-5a99-acd1-f33f8f029a09 | note | Inspection: By - SV
| checkpoint | 4.1.3 - Subgrade Testing
31279a18-7755-5528-bdf2-b32231b5dc38 | note | Standard/Specification - Construction Drawings Sheet No: C-5110
7a4c165c-e613-59a9-b831-d48fdfa542b6 | note | Acceptance Criteria - Clegg testing at 10m intervals
b29ff9da-8a86-53c5-a3dc-22c57c482c3f | note | ○ Subgrade CBR ≥ 7%
b0c549f2-c1bf-53f0-a232-fee2a18cbaf2 | note | Verifying Document - Clegg Hammer Result Sheet
fba62a0f-efa2-55af-ba32-af82682304b4 | note | Frequency - 10m Intervals
80c91ec6-d90b-5691-b1c3-b14e72125341 | note | Inspection Type (Visual, other) - Subgrade Compaction Testing
fed3403b-2bb4-5012-b016-62139dc9e55a | note | Inspection: Key - H
40f463a9-195e-55e9-a76b-d44defd16005 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Foundation Preparation and Asbuilt Survey
a05ce3eb-fd8c-52dd-ab2e-8fd79f238ac8 | note | Standard/Specification - Civil Technical Specification Section 4.3
385d9b02-3f6f-57b8-aed4-4ccfb253eaf8 | note | Acceptance Criteria - 300mm of AP65 or cement modified basecourse
782b5587-7df7-5e74-9a8b-06f4b3107f73 | note | Verifying Document - Photos & Asbuilt Survey
43a524fe-28e4-5078-a81b-9e114aacfdbe | note | Frequency - 10m Cross Sections
6d4f81ed-48e8-5c45-a1d8-e4cea833b180 | note | Inspection Type (Visual, other) - Dimension Inspection
68ff6eb3-8ebe-5f45-871e-eec37d7aad39 | note | Inspection: Key - D
b9ce389f-b1f8-56cb-ac7e-124fc1891a6b | note | Inspection: By - SV
| checkpoint | 4.1.5 - Foundation Testing
323582a8-c25d-589e-8770-03dd241c7110 | note | Standard/Specification - Civil Technical Specification Section 4.3
8028371f-e487-59d9-afad-9576d5bb79e0 | note | Acceptance Criteria - Compacted to a minimum dry density of 2100kg/m3
d08d5088-a7da-5614-8283-00cad68c9239 | note | ○ In accordance with NZS 4407: NZ Heavy Compaction
03a4e873-a56a-5c2c-aa0c-46fc64fa2eb6 | note | ○ Results provided to Engineer to proceed
66ee9c98-c224-566a-ab46-73c2c41d4e47 | note | Verifying Document - IANZ Accredited Laboratory Report
59f70903-9b07-54c8-8d6a-ccf412f72ea3 | note | Frequency - 10m Intervals
00d30b5d-cce9-5468-9016-41f6f3d87af7 | note | Inspection Type (Visual, other) - NDM Compaction Testing
690d79ec-9cce-5929-8ec4-94741cbe8618 | note | Inspection: Key - H
b85fe08d-b533-5c33-b09a-6fdaad48384b | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Kerb/Nib Setout
6df41612-d002-53f6-87ff-bbb6b4e0d063 | note | Standard/Specification - As per design & Construction Drawings Sheet No: C-5110
d3175d13-b493-5082-b94b-9b517ecfff65 | note | Acceptance Criteria - Surveyor to set-out stringline of kerb and channel.
4263f1e9-bcb7-5ad2-bb7c-0a3c5f2c48a2 | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No: C-5110
8089a198-6316-5731-92f8-1ef4fce7657e | note | Verifying Document - ITP Sign Off
e5065fdc-e87c-5bf5-b210-7efefd582cad | note | Frequency - Straight: 10m Intervals
c23779f9-66f0-5102-9a86-cdaeb66a66aa | note | ○ Curve: 2m Intervals
5ad2c4e8-8c55-5132-bd47-1189ee493934 | note | ○ Survey every tangent
66794562-0410-516e-9e1f-fcb6e0b3f325 | note | Inspection Type (Visual, other) - Survey Setout
2e840a17-c005-5fe3-ba18-e152905e08fb | note | Inspection: Key - D
ce34bee4-6d41-5912-be7a-179dabdae0ca | note | Inspection: By - SV
| checkpoint | 4.1.7 - Heavy Duty Vehicle Crossing
0e8e8d62-dcad-5421-bf9e-1bbb244b1691 | note | Standard/Specification - Construction Drawings Sheet No: C-5110
b2324616-11a4-5942-a9ff-4802ef7a9957 | note | Acceptance Criteria - Construct heavy duty vehicle crossing including reinforcing steel as per standard detail in Construction Drawings Sheet No: C-5110
1ac15206-bdea-58cd-87cd-3767b03a615b | note | Verifying Document - ITP Sign Off/Photos
b971c8de-4f29-58e0-90c0-092183c047a7 | note | Frequency - Prior to pouring the concrete
5b0a6558-1027-5acb-bf7d-1a2f5dfd9aa0 | note | Inspection Type (Visual, other) - Visual Inspection
6bc27b9c-bfcd-5fb3-a612-67f452a9be60 | note | Inspection: Key - V
876d8281-28fa-5b96-9202-25c0b52ad6e5 | note | Inspection: By - SE
| checkpoint | 4.1.8 - Pre-Pour Inspection
c4a6a03c-2e8f-52ef-9283-e90ab83a8b1a | note | Standard/Specification - As per TDS
a603d4eb-4a0c-50ca-98bf-ab95f6f01ade | note | Acceptance Criteria - Stringline Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
1f15040c-4f7d-5fee-9973-8b59c392ab8d | note | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
79736e46-6f56-5d7f-8c54-f07e13ad04e3 | note | Frequency - Prior to pouring the concrete
1fb11d01-4b08-534a-aa05-aa2ed907f7b1 | note | Inspection Type (Visual, other) - Pre-pour Inspection
95684c29-e246-54c9-93d8-202d41ee3da2 | note | Inspection: Key - H
ddb8673d-ae82-52df-b3eb-5c60abce37ee | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.9 - Supply and Installation of Concrete
f970e691-3109-5b44-813e-3d613704d657 | note | Standard/Specification - Civil Technical Specification Section 4.3
d09cfd36-fe5e-5020-9f5f-901a2736da0e | note | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
d5ea320c-c1c9-5685-a67e-b7f992ae83ab | note | Verifying Document - Mix Design Certificate
a7d43211-a49a-53a7-bbe4-3bbb9828c7e1 | note | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
80cb3321-9863-5d54-adba-c415ee2f1602 | note | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
187be760-da19-575c-b604-446bd960ce52 | note | Inspection: Key - R
fd840937-2dac-550d-9359-5c1864e38858 | note | Inspection: By - SE
| checkpoint | 4.1.10 - Concrete Testing
93f78d77-914a-595c-8fce-1b1d64e86c09 | note | Standard/Specification - Civil Technical Specification Section 4.4.1
158a2bf2-78fb-5a43-aa17-f04b0801f53a | note | Acceptance Criteria - In accordance with NZS 3109 and NZS 3112 Part 2 Section 9
67173606-9827-5bab-bb91-a830db88474b | note | Verifying Document - IANZ Accredited Laboratory Report
57db940a-b474-54c3-8535-7b40bf7915db | note | Frequency - Minimum of 1 every 50m centres
b82e13e6-76d3-50fd-8503-1cb5c15b4029 | note | Inspection Type (Visual, other) - Core Compressive Strength Testing
4c16a00f-f0f6-5ae0-92a6-e82c17eae620 | note | Inspection: Key - R
50528c3a-4653-5c7d-8840-67166e83675e | note | Inspection: By - SE
| checkpoint | 4.1.11 - Concrete Surface Finish
35a3d8dc-546b-5a9e-9309-86073745141b | note | Standard/Specification - Civil Technical Specification Section 4.2
6bbd1497-486d-5894-b9d2-07e2a5e74d8d | note | Acceptance Criteria - In accordance with NZS 3114
2b3401fd-2a58-5119-baa3-59d34ab320e1 | note | Verifying Document - ITP Sign Off/Photos
ff9118f2-e778-5176-bcec-41327383c380 | note | Frequency - Every Pour
db1ef108-1f7a-5774-b28f-3853e2e13459 | note | Inspection Type (Visual, other) - Visual Inspection
2afd3d77-3d8d-5804-a39e-31143b5e4f35 | note | Inspection: Key - V
567a3ce6-f1b4-5d2f-9542-c232070e9010 | note | Inspection: By - SP
| checkpoint | 4.1.12 - Construction Joints
a6216499-c114-5980-aa01-fe6aa2b37388 | note | Standard/Specification - Civil Technical Specification Section 4.3
2e85e9a5-e069-59da-ae0a-77e2ae68b921 | note | Acceptance Criteria - Construction joints shall be installed in all kerbs and channels at 5m centres
51f264ee-2117-5a1f-a99d-0e367330acb4 | note | Verifying Document - ITP Sign Off/Photos
916794bd-a094-528d-9724-c906cbec5825 | note | Frequency - 1 every 5m centres
8be5b3e8-a6b2-5d09-8583-26367541ff4b | note | Inspection Type (Visual, other) - Visual Inspection
0d271255-c5dc-5d9b-9721-68205025dc83 | note | Inspection: Key - V
2bf7cea0-d9d8-58c3-88ba-21fcf5e5af74 | note | Inspection: By - SP
| checkpoint | 4.1.13 - Concrete Docket Tally
39290a26-311f-515d-a973-abd82c35d765 | note | Standard/Specification - As per TDS
86baeae4-ef73-554f-b36c-f361dbd3e18d | note | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
bb7318e8-f601-5ca5-b5f4-ae08a7988d65 | note | Verifying Document - Dockets
801991a6-4e16-50d8-b50f-9611b6748c49 | note | Frequency - Daily
e92ba787-29ff-55b6-a91f-b56c873a10a3 | note | Inspection Type (Visual, other) - Check
a745b431-7257-505f-9e7d-b41acc499941 | note | Inspection: Key - C
dcb5cdbe-79c6-59ee-8903-24b13aa69cae | note | Inspection: By - SE
| checkpoint | 4.1.14 - Asbuilt Survey
436ad5cf-3a71-5bd8-9ae8-7bf7403eea1b | note | Standard/Specification - Civil Technical Specification Section 4.3
4540aac6-5925-527f-b989-8065e58a03a0 | note | Acceptance Criteria - No discrepancies of greater than 6mm in line or level in any 3m length
19818b4d-dc1f-559c-892a-8f1de69f59dc | note | Verifying Document - Asbuilt Drawings
346a6862-1844-5e6f-afed-0fa0e6dc5104 | note | Frequency - Straight: 10m Intervals
122f6450-a6c9-5939-86a4-5235a66a58d8 | note | ○ Curve: 2m Intervals
458f6771-af83-5720-8aa3-69b5bbd3f43e | note | ○ Survey every tangent
937c8b03-26b5-5049-93d2-8ecc8ec68cf7 | note | Inspection Type (Visual, other) - Survey Asbuilt
9b9b5f25-4b75-52fa-aa0e-be96124ff539 | note | Inspection: Key - R
09c4dbf2-ac94-5e12-aebb-8fc50c413129 | note | Inspection: By - SV
| section | 4.2 Footpath
| checkpoint | 4.2.1 - Service Location
0949902f-c73f-57b8-bdf5-4fadf1f131ec | note | Standard/Specification - As per TDS
e1b75eb0-d1b9-554f-be55-1245274691b6 | note | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
a4f09ac4-5cf1-50f2-899f-9a86b2efbb4e | note | Verifying Document - ITP Sign Off/Photos
78f50feb-3a81-5ed8-9b45-68203293671c | note | Frequency - Prior to the works starting
be739caa-41c5-5a28-b6f8-c60a0290aba8 | note | Inspection Type (Visual, other) - Visual Inspection
68067862-6f4d-50f4-bc22-672ab31438f7 | note | Inspection: Key - V
4c538f67-f92a-53f6-a947-91351157cca8 | note | Inspection: By - SP
| checkpoint | 4.2.2 - Footpath Location
97aea7cf-3383-50f7-8bcc-98657690b4a9 | note | Standard/Specification - As per design & Construction Drawings Sheet No: C-5111
2bf66d39-f487-5ef8-9665-6a983dbd128a | note | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
ae4453ee-cf4b-5b18-bec1-6cd1001220c7 | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111: Height 100mm, Width 1.5m, Slope 2%
ad72313c-6472-54a2-8354-7b69d3d4459e | note | Verifying Document - ITP Sign off
ad02fa5a-6f9a-5055-9816-528a51bc2821 | note | Frequency - Prior to constructing foundation
ce7a055e-e27f-5b50-b291-370b218517ee | note | Inspection Type (Visual, other) - Survey Setout
8136cfd3-901c-5a17-84a7-836395fbd604 | note | Inspection: Key - D
c24b5ad3-29e5-5db2-98db-db7eeacbb110 | note | Inspection: By - SV
| checkpoint | 4.2.3 - Accessible Ramp Location
a71159e1-014b-5311-ace7-66f9c35fdcc7 | note | Standard/Specification - Construction Drawings Sheet No: C-5111
346aa825-3661-55cc-80a5-2af05929c196 | note | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
e691d47a-ead1-50af-acf2-52ca04404d5b | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111:Slope 10%
3e9aa421-77ec-55fb-be10-d20896f8fff4 | note | Verifying Document - ITP Sign Off
b15e162c-7e3e-522b-8a0a-9d743689af03 | note | Frequency - Prior to constructing foundation
ea9b3c8f-5f8f-590e-9483-c60c65e3c68b | note | Inspection Type (Visual, other) - Survey Setout
93e9b937-027f-5b5d-9b03-b11d331251c1 | note | Inspection: Key - D
cddef4ee-074d-54e6-9a56-62f22d196673 | note | Inspection: By - SV
| checkpoint | 4.2.4 - Subgrade Testing
8fbaf84d-1f0b-5b34-893e-4057e2061b39 | note | Standard/Specification - Construction Drawings Sheet No: C-5111
074692fe-5663-599f-adad-e0ffd57be3e0 | note | Acceptance Criteria - Clegg testing at 10m intervals
d76fa85b-183e-599a-8064-461f133fdcd7 | note | ○ Subgrade CBR ≥ 6%
e99e80f6-a04d-5774-9f53-7195372a09a7 | note | Verifying Document - Clegg Hammer Result Sheet
033ce658-7810-52e4-8e34-34f9697c1cf1 | note | Frequency - 10m intervals
f131404d-0cbf-5e5f-9b27-5691d52fc6f3 | note | Inspection Type (Visual, other) - Subgrade Compaction Testing
0a554c0d-1edf-53fd-8b46-68e603ab0f4b | note | Inspection: Key - H
eb59516e-e053-5f6c-8a59-5660b8ae8b08 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.5 - Foundation Preparation and Asbuilt Survey
d71876ef-88ae-5b44-8c24-9c7b79202e52 | note | Standard/Specification - As per design & Construction Drawings Sheet No: C-5111
fad6cef0-da92-5b67-8d4c-9fd6bda0b81b | note | Acceptance Criteria - Minimum 100mm of M/4 AP40 Basecourse
331ac36b-4a82-5f3e-95bc-a710f3279b14 | note | Verifying Document - Photos & Asbuilt Survey
d14ef74c-73d6-5ce6-b1a2-093a1a95a5b8 | note | Frequency - 10m Cross Sections
b9024e09-3543-554f-94b8-6914cbd487a1 | note | Inspection Type (Visual, other) - Dimension Inspection
ebdb6010-c84a-51ad-8185-c6ff1b51e509 | note | Inspection: Key - D
db2d7163-fb0f-5244-8d34-0d5026fc59e1 | note | Inspection: By - SV
| checkpoint | 4.2.6 - Foundation Testing
80e87ba2-526d-55b7-b990-fb505516df97 | note | Standard/Specification - Civil Technical Specification Section 5.5.1
a41490e8-40ad-5a80-847f-31f0dd91f5ed | note | Acceptance Criteria - NDM testing to be carried out by IANZ accredited laboratory. Site plan to be provided to Engineer showing every test point. Minimum acceptable result shall be 95% of the suppliers specification as per approved JMF.
971e6f50-13e8-5d6a-aa8f-95634faaba40 | note | Verifying Document - IANZ Accredited Laboratory Report
1dd05491-141c-5055-bfa0-c89295344eef | note | Frequency - 10m intervals
8c3f8744-00f8-5911-8f7b-a122de3ef087 | note | Inspection Type (Visual, other) - NDM Compaction Testing
1017bfc6-3bc0-515f-8dbd-167cdd4ac131 | note | Inspection: Key - H
d53aa383-bdac-5514-ada1-269712d9f391 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.7 - Foundation Testing
957cbc27-7003-50d8-a8ad-6b4abacd352b | note | Standard/Specification - Civil Technical Specification Section 5.5.1
ce513327-a308-558c-9de2-01449bb578c4 | note | Acceptance Criteria - NDM testing carried out by approved user within Downer (with approval from Waka Kotahi) Min. Acceptable Compaction ≥ 95% of Target MDD
028f0b86-f36b-5d60-bc4e-259e03d92d6d | note | Verifying Document - IANZ Accredited Laboratory Report
2ff71784-7074-5c9e-8078-107d429fc8d7 | note | Frequency - 10m intervals with surveyed test point locations
234b7cb8-d2d2-5ec4-b01e-1315c46c35d1 | note | Inspection Type (Visual, other) - NDM Compaction Testing
57d7ee98-6217-5398-b2ba-212b8940adc5 | note | Inspection: Key - H
d8e7e0e0-9820-52c7-a54c-a939e74493ff | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.8 - Foundation Testing
a61083ff-b266-526e-8f40-a8c66de5e577 | note | Standard/Specification - Civil Technical Specification Section 5.5.2, NZTA T/1
7c4808d7-c364-5c42-bdc2-ab70c866106a | note | Acceptance Criteria - Deflection testing shall be carried prior to kerb and channel being formed.
b98ae562-6f4a-58da-a8bd-ee9b422963ba | note | Allowable deflections are as follows:
b6a6aa0a-790f-5a48-bc07-b457ffc4b917 | note | ○ 95% of readings < 2.0mm
e599d4d4-f397-5d46-a468-bbeaf83d7161 | note | ○ Maximum reading of 2.5mm
9e25226d-bd97-5803-b437-adc87ec99653 | note | Verifying Document - IANZ Accredited Laboratory Report
b9951d33-bd90-5e8f-941d-e56485dc74b8 | note | Frequency - 10m intervals with surveyed test point locations
4020d2ab-679c-5285-8e37-a33ab1d87158 | note | Inspection Type (Visual, other) - Benkelman Beaming
92335bb7-60b2-5c6d-892e-fe6eecd1ef20 | note | Inspection: Key - H
097b8f20-c953-5317-9c94-4d29dab739d1 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.9 - Formwork
1b250f87-1068-5803-8cef-688ee170e873 | note | Standard/Specification - Civil Technical Specification Section 5.3
bb3d3ea9-bfef-5c5f-8eee-eea3165115bc | note | Acceptance Criteria - In accordance with NZS 3109. Finished level of formwork shall be within +-10mm of design. The line of the formwork shall be straight with the maximum deviation from a 3m straight edge along the face of 5mm with a cumulative total of all visible gaps of not more than 10mm
d2eb1f7c-43aa-5a95-9e9d-335216083a4e | note | Verifying Document - ITP Sign off
a1418b4c-f472-593a-99bc-43839254d654 | note | Frequency - Prior to pouring the concrete
fd503390-f7f2-548d-8b54-42a95c296af0 | note | Inspection Type (Visual, other) - Survey Setout
a5ab44ec-c683-556e-a055-e37d35a891be | note | Inspection: Key - D
f321cd83-7bf3-577d-81e5-44f3c8fd93ec | note | Inspection: By - SV
| checkpoint | 4.2.10 - Reinforcing Steel
1acd05b9-da8d-5107-bdf6-ca222989d5ce | note | Standard/Specification - Civil Technical Specification Section 5.2
526df5ad-db26-54eb-be65-9bd55056c1e7 | note | Acceptance Criteria - Reinforcing steel in accordance with AS/NZS 4671 Grade 500E Steel Welded wire fabric in accordance with AS/NZS 4671 Class E smooth
cac4abe9-d899-5903-8085-2891c5f0424b | note | Verifying Document - Dockets & Photos
ae40cb81-4d1a-5ada-b238-b2df59189b3b | note | Frequency - Per batch/delivery
8dd1b852-1167-5569-806f-75d2f71c4c42 | note | Inspection Type (Visual, other) - Check
3b3a6d88-e7be-55b3-9178-76eb0e577ee5 | note | Inspection: Key - C
5f9fb94e-128a-5006-acb5-57756b7bea08 | note | Inspection: By - SE
| checkpoint | 4.2.11 - Pre-Pour Inspection
9ccd89a5-5d91-5b4e-b73d-afa1f7d48807 | note | Standard/Specification - As per TDS
b564b9cc-84e7-55db-a3fc-03a144cf746c | note | Acceptance Criteria - Boxing Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
17318a39-332b-55e7-abda-ba67dcd2e785 | note | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
26355c0b-79fc-5f74-9e94-fb4f9f7eef71 | note | Frequency - Prior to pouring the concrete
a11787f8-626a-53cf-9d84-bafb27c729ac | note | Inspection Type (Visual, other) - Pre-pour Inspection
1ab99b03-2225-5cef-8037-e5b9ed000343 | note | Inspection: Key - H
b0b9a90f-1026-59a6-bacd-1a553e530b22 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.12 - Supply and Installation of Concrete
c10ba905-b5ed-5e59-a1c6-4dccf5d95621 | note | Standard/Specification - Civil Technical Specification Section 5.3
7e4ff235-620e-5e17-bc47-b9121026ac75 | note | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
8761a1b9-d028-5035-b74e-8df6490ec13f | note | Verifying Document - Mix Design Certificate
f46a9204-ee38-5d10-85dc-ebd440dd0121 | note | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
5b6628b5-03cb-524d-8500-630089153ac1 | note | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
16b56ae1-6c5b-5ec3-a9ac-8a7881996d10 | note | Inspection: Key - R
009a7d4b-87e2-5608-a066-8ec029f00ec3 | note | Inspection: By - SE
| checkpoint | 4.2.13 - Concrete Surface Finish
712159c3-7158-55ac-af0c-aa546c5ecb79 | note | Standard/Specification - Civil Technical Specification Section 5.3
6e1e7e6e-eef6-5d3b-b2ba-b11b550626c8 | note | Acceptance Criteria - U5 finish in accordance with NZS 3114
00879cc4-2571-5256-a719-5ca951c5fee8 | note | Verifying Document - ITP Sign Off/Photos
e9b183a2-15fb-5932-8b50-2a6d6483f27d | note | Frequency - Every Pour
2225b8bb-9e57-5133-9851-7f94f236229e | note | Inspection Type (Visual, other) - Visual Inspection
1b6ae5c5-25d5-5b25-ae8d-88afe31e6ce1 | note | Inspection: Key - V
a97d0e7f-7901-5d52-a066-5f28bc4fad2b | note | Inspection: By - SP
| checkpoint | 4.2.14 - Saw Cutting
3aada057-8311-54a4-b7f3-a74d20eddb04 | note | Standard/Specification - Civil Technical Specification Section 5.3
12ba5583-cb4f-5544-b1fa-17c548b95143 | note | Acceptance Criteria - Grooves to be between 1/4 and 1/3 of specified depth of slab, and any convenient width greater than 3mm. Max spacing of saw cuts shall be 3m.
cb7217c7-f274-58b3-b8e5-e13510992631 | note | Verifying Document - ITP Sign Off/Photos
ad54f25e-6a59-5b27-b916-cd77c6a28d0c | note | Frequency - No more than 3m Intervals
c1428280-7bd0-5191-aba7-6a405206873a | note | Inspection Type (Visual, other) - Visual Inspection
f5b5b00f-fc77-5fc3-9cf4-14995b87abdf | note | Inspection: Key - V
c5ac2b39-78b8-5399-b798-c20d86cad01e | note | Inspection: By - SP
| checkpoint | 4.2.15 - Concrete Docket Tally
42719b7b-71e3-539e-bc87-5a38cbb934fc | note | Standard/Specification - As per TDS
4bc0b176-87a9-599f-9a62-92e8fcf2c2a9 | note | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
65acf909-cf31-5216-afca-9436a24ddad5 | note | Verifying Document - Dockets
ccb32259-3643-520f-95b7-4b7ee9d8d9c1 | note | Frequency - Daily
bb7f617a-189f-53c4-8977-bfdf8270a268 | note | Inspection Type (Visual, other) - Check
1581feb1-64ed-5835-87f5-786b1c811d14 | note | Inspection: Key - C
b280f5e7-c12d-568e-b397-09107e711318 | note | Inspection: By - SE
| checkpoint | 4.2.16 - Asbuilt Survey
d0ec42dd-62d4-531c-8e0b-8f810f701c2c | note | Standard/Specification - Civil Technical Specification Section 5.1
949ea41d-269b-516b-887a-84b6b0dd0771 | note | Acceptance Criteria - In accordance with requirements of the TA Minimum cossfall of 1%
08cd6732-fe97-5535-a0c6-ba50a91d9b22 | note | Verifying Document - Asbuilt Drawings
300a2ac3-e938-5897-a215-20008a598868 | note | Frequency - Appropriate intervals to represent asbuilt footpath
97aa1287-30c4-5642-a6b0-b26237cddb4d | note | Inspection Type (Visual, other) - Survey Asbuilt
dccf8536-708d-543d-a535-da88048eca1d | note | Inspection: Key - R
6bc01eca-8389-5054-bc12-138d6d086850 | note | Inspection: By - SV
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
bfa97f90-a171-5f93-b2da-e41446d21a68 | note | Inspection Point: Quality Control Activity - Upon completion of works
755443da-0fcd-5d19-b2fd-746dd0d24c66 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
4127f7a8-3e1e-5967-80c2-6ea1e803dd18 | note | Verifying Document - Closed-out NCR/Defects
935bab38-c418-5f5d-bd72-5a192d208e90 | note | Frequency - Post construction
4104e18c-6e8b-5dde-959c-c76588c189d0 | note | Inspection Type - Review
35c3c9eb-14a6-5d52-9791-5fdfdab97eb0 | note | Inspection: Key - R
ccfa35c3-d66a-580e-af12-d993dc82e04c | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
15073744-4f62-582e-be69-dfcaf276c2e2 | note | Inspection Point: Quality Control Activity - Upon completion of works
09651b82-0e28-54df-ba92-3d0bdc68ee33 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
458b36c3-bc7b-561e-ac32-e6bd00e99a5d | note | Verifying Document - As built survey record completed
2dd48249-302f-5556-9850-507b16c35637 | note | Frequency - Post construction
072a6d24-f425-5ddb-835a-ca6781d36b2b | note | Inspection Type - Review
c9468bbd-71fa-5136-953b-0e05feaa9b25 | note | Inspection: Key - R
a2392391-c817-5a59-a8b8-58da62e56183 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
11712059-5889-5c6a-911f-5e26a740d686 | note | Inspection Point: Quality Control Activity - Upon completion of works
710c8d80-d813-52a4-a9ce-daae21cc7d2b | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
5d177294-ea72-5cdf-a84c-2a9ffa3b3873 | note | Verifying Document - Signed As-built Drawings
051ab85f-60ed-5ea1-a3bd-18f163a16162 | note | Frequency - Post construction
9f9ec319-b222-5bec-a9c7-ca2277e8f38f | note | Inspection Type - Review
64969539-7f91-5625-a6cf-bd264753ab51 | note | Inspection: Key - R
fa24bde3-bfb0-5af4-a9b6-f513976ced4f | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
63f80aa0-2d6a-5a73-b387-ce8be8e0aff2 | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
b20e9e1d-3a48-55c1-bfab-44fb762d96bb | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
ee2e170b-474a-5287-9ea5-a5a853a265bb | note | Verifying Document - Register
6a5cc784-c0f6-520d-80ff-0062c03a190b | note | Frequency - Post construction
d803374d-036c-5c20-b5e5-ac977d345c38 | note | Inspection Type - Review
e21b1d3b-5c80-5362-b00f-bd76b3528f95 | note | Inspection: Key - R
8a66190a-ff6e-5bef-9784-52ab2f71e78c | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
9d019520-a6f3-5047-923a-1ce3c58e540e | note | Inspection Point: Quality Control Activity - Upon completion of works
4178df40-98e3-5562-b999-6bf27fae8582 | note | Acceptance Criteria - All signed and closed out
a93c5242-992b-5a86-ae7e-7c2b724c3d96 | note | Verifying Document - Signed off Documents
b79e3931-0378-5088-9168-41bcb76c15a8 | note | Frequency - Post construction
a04c12d2-63a2-57c3-b765-3388c22caa1d | note | Inspection Type - Review
2712c19a-cc9c-52c7-8e1d-bdba0fd46300 | note | Inspection: Key - R
aaa57011-f2aa-5e3b-b084-3c990496c34d | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0026_v2 (Earthworks -CVSC) | itp | 558020-DOW-ITP-PC-0026_v2 (Earthworks -CVSC) | fc74b781-c60d-48a0-a946-6a8357fd97c2
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
75239bbc-82a4-582a-ab40-9514eaeb9a3f | note | Standard/Specification - Downer Standard
b5801411-f761-5c97-b21c-c50eef9517cd | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
171cc87e-5a7d-541c-80bb-4f8b335705d8 | note | Verifying Document - Survey Records
50c631d5-8963-5b70-bd26-5d67de4786cf | note | Frequency - Prior to Works
60e4f041-263f-599c-b547-a4e180fcba40 | note | Inspection Type (Visual, other) - Document review
35fe106a-bfd3-51c2-8d41-89c3b80b699c | note | Inspection: Key - H
abaa431c-a369-5478-8b59-036cf468789c | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
80ab3d02-0ca8-5e58-9aa0-90eb4327ac51 | note | Standard/Specification - Downer Standard
7fafe139-9121-5259-b833-031625bddcfa | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
80c994c7-044d-5ddd-87f1-7b0624cae3d1 | note | Verifying Document - Service location documents
c6a6eac5-44ea-5a02-9550-f07e2723e2cb | note | Frequency - Prior to Works
c4458b4c-2abd-5f73-b208-d9f8e18797a8 | note | Inspection Type (Visual, other) - Document review
249851f6-7bda-52f6-a3f3-72eb43eef0b8 | note | Inspection: Key - R
1898d0a1-d030-5408-8d88-a25b5558eade | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
93d64db4-ee3c-5593-8deb-5afbf271d7fa | note | Standard/Specification - Downer Standard
78cafb96-fe40-5bc9-97b5-89276ab93c46 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
da66ad7f-3f46-5740-8b4a-5acd20724364 | note | Verifying Document - Internal Permits
bc89e52c-c281-5055-b2ff-47e6b762d750 | note | Frequency - Prior to Excavation
0cf26a86-4471-5f96-9d5d-3a29225faf02 | note | Inspection Type (Visual, other) - Document review
1d59932d-cdaa-5188-837b-eb96f8fe897e | note | Inspection: Key - R
8c40e783-9335-5570-b268-20778d91554a | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
8132f8a1-ccdb-5c5f-86bf-9a32229df8d6 | note | Standard/Specification - Downer Standard
e31d2839-ad43-5dfa-bac6-4b0469ca086f | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
eb0e59a4-2ed0-5118-9708-3e98fb302cde | note | Verifying Document - External Permits
0c5e2308-4547-5061-be73-80f87d1c6c84 | note | Frequency - Prior to Excavation
a861e26d-092c-59a4-b92e-0782121ffd75 | note | Inspection Type (Visual, other) - Document review
f0e2b517-0373-54b2-b7ee-97ca69856bbd | note | Inspection: Key - R
b9d5d258-787e-5b40-8f37-5d455842dd9f | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
537034c0-8fde-5e11-823f-fa95d39e89fe | note | Standard/Specification - As per contracts
137088be-c7ef-5c71-8b80-36db18fa9e36 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by council is in place and valid
d7bd786c-b1cb-5052-940c-26c58da06ec6 | note | Verifying Document - Approved ESCP plan
49940650-e470-5474-92bf-60b191ad3e99 | note | Frequency - Prior to Works
022a7534-9705-5978-a97a-93d7ebfac784 | note | Inspection Type (Visual, other) - Document review
df7efc6f-3d53-5782-ac59-c02bb8210a7c | note | Inspection: Key - R
920d6555-efe7-56bf-ab51-0bd38324dc1f | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
4f89c5c8-5869-5a9d-a357-3a5048e3544f | note | Standard/Specification - Issued by Client
09a04ffa-75a8-5f15-b6b2-2840726ef63b | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
b19b35af-0e8e-59e8-a332-cd732ee3da9d | note | Verifying Document - IFC Drawings
8b63af2a-0234-5a53-a67e-189d265da08c | note | Frequency - Prior to works start
e652bd80-c562-5fb0-a224-78f97446e6d3 | note | Inspection Type (Visual, other) - Document review
66785ac7-a421-59b9-9220-2a86bfc24354 | note | Inspection: Key - R
81a2d422-d71d-5edf-bcf8-2673b7815bb3 | note | Inspection: By - SE
| section | 3.2 Earthwork - Incoming Materials
| checkpoint | 3.2.1 - Imported Fill (AP65) and Structural Fill Sources
8c629f09-2825-5b99-8d12-4e7b816a8f39 | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
0919f5a1-ab58-5741-9f1d-430fc0674ef9 | note | Acceptance Criteria - Max Dry Density (Standard) and Optimum Water Content
4e8052ad-e24a-587e-9e53-0c3c1f0f158c | note | ○ Natural moisture content
9c23e7f7-7410-51b2-a0e9-c387ee39bccb | note | ○ Plasticity index
58a2889e-a52c-5219-89d9-506e7729649d | note | ○ Particle size distribution
6bfdeb2a-47fd-5d8a-b1b2-919e479be577 | note | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
b3cb4e2d-c9d4-5c61-b0bb-79f2730b0bb9 | note | Frequency - Porior to works
1c68b4e8-ba8f-5c2d-bafe-35af0d5e0a83 | note | Inspection Type (Visual, other) - Document review
99b66b93-678d-5e0b-a8e3-10f2604038fc | note | Inspection: Key - R
98724bed-44e0-5ffc-8f09-3ce63251261a | note | Inspection: By - CR/SE
| checkpoint | 3.2.2 - Cut to Fill Material
34cdf3fd-8d1e-5e31-b3c0-36f6910a8bd8 | note | Standard/Specification - NZS 4402:1986
e7715e30-b2e4-5300-8795-4743476e2e28 | note | Acceptance Criteria - Max Dry Density (Heavy) and Optimum Water Content
6b796f47-31ea-5361-9f8e-60d01fc4db58 | note | ○ Natural moisture content
677a7028-b5a0-5695-a6e6-a52af2b45170 | note | ○ Plasticity index
08ab34cd-0143-5672-8a9c-f1770c6c6b78 | note | ○ Particle size distribution
31d8e4f4-3ac9-5f08-99f0-17f64dc9272f | note | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
40bad13e-7065-5e93-82cf-6ee0abed84a8 | note | Frequency - Porior to works
79283287-4294-56d1-a69f-3f5ab8af272d | note | Inspection Type (Visual, other) - Document review
c711d78c-d526-5457-898a-988a929a2cf9 | note | Inspection: Key - R
e0187315-e798-55ab-94fc-6e7280630148 | note | Inspection: By - CR/SE
| checkpoint | 3.2.3 - Geotextile
f12f6b27-f6c8-5009-bf31-b97eb5990487 | note | Standard/Specification - NZTA F/7
45463e39-762c-5cb5-9465-2a2806ac2492 | note | Acceptance Criteria - Non-woven filtration class 1 and Geotextile strenght class C.
6af5743e-a53a-5117-9131-0231fad3ccf4 | note | ○ Confirm the above grade from the Manufacturer's Certificate of Compliance with IANZ endorsed or equivalent test documents.
1610d857-2985-586e-ad50-d9883b8a0a39 | note | Verifying Document - Product data sheet, Docket
f18abf5a-fa5a-5d5a-8b1b-6ba4b9491331 | note | Frequency - Each lot
9fe2433f-5dc8-518b-bdc1-2f3a8dab66be | note | Inspection Type (Visual, other) - Document review
5784192f-ef66-5362-aade-441993ccbb9e | note | Inspection: Key - Inspection
972078b2-698f-597a-843e-17bf4eb7df3d | note | Inspection: By - SE
| checkpoint | 3.2.4 - Geogrid
46e58a80-b0a0-5838-bcdc-66aea09dcb90 | note | Standard/Specification - As per project specification, Section 2.15
7e8315ba-946e-5de3-8287-229023135b46 | note | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
52adc72b-a87a-5171-be55-ce5461b73ce0 | note | Verifying Document - Product data sheet, Photos, As-built
d77703d1-787a-570d-84fb-10bb13859c97 | note | Frequency - each application
7522fac0-d055-58e3-ab1d-9169bc04cf6e | note | Inspection Type (Visual, other) - Action
0e659912-9c34-50bd-98a3-061527279c99 | note | Inspection: Key - W
ac5be148-4389-5744-a32f-de0d924aef2d | note | Inspection: By - SE
| section | 4.1 Earthwork - Construction
| checkpoint | 4.1.1 - Site clearance
af1c256a-18da-56a6-8897-6fa87ffede56 | note | Standard/Specification - As per project specification, Section 2.3
707ca86b-4ef6-54af-9776-4d1318c26841 | note | Acceptance Criteria - Clearing shall include the complete removal of stumps, trees, logs, scrub and coarse vegetation and disposal by burning, or dumping and burying in accordance with any particular requirements of the contract documents
067e9c1e-1c28-5e54-9f83-eea65bfc8c72 | note | Verifying Document - Photos, Checklist as per requirements
253cc605-ec2f-543a-8a79-bb990a4d127c | note | Frequency - Prior to topsoil removal
5a2bf4df-726c-5cd1-8348-2b715a91b758 | note | Inspection Type (Visual, other) - Visual
c72e0e88-bf42-5ae6-bf68-fb96f8a7ec36 | note | Inspection: Key - V
841f95be-46c2-540e-91b1-319505458fa0 | note | Inspection: By - SE
| checkpoint | 4.1.2 - Top soil strip
e3044efb-6881-58be-b2d8-37a388d65c9d | note | Standard/Specification - As per project specification (200mm), Section 2.9
c45ad536-f78a-53d2-b4b9-d5c887dd51b3 | note | Acceptance Criteria - Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
dca71a24-d40f-5f37-8697-2fea40075774 | note | Verifying Document - Photos, As-built
9295da12-0880-5ccf-bc11-231143bcddb0 | note | Frequency - All
36ed77ee-4b49-5f04-87f8-470bb82e535d | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
a9cee588-70e5-54d3-a51c-693a2974721a | note | Inspection: Key - D,V
239efd52-3774-51df-9b56-1f4a9c3fa71d | note | Inspection: By - SV, SE
| checkpoint | 4.1.3 - Subgrade Suitability Testing - Scala Penetrometer Testing
37a15032-7c52-5846-b1d9-b11d5a6372cf | note | Standard/Specification - As per project specification, Section 2.18.2
4820a4ce-ae9e-542a-8490-0474811b453f | note | Acceptance Criteria - The Subgrade must be tested by Scala penetrometer or Shear Vane to confrim suitiablity. 3 blows per 100mm.
88726bbd-507c-53c3-8443-53c2f5c03c49 | note | Verifying Document - Shear vane/scala checksheet
2086ec35-3993-56d6-916c-49e38101a0eb | note | Frequency - Whole area by 20x20m Intervals
947f4c5a-82c5-5f2c-9100-513fecfa62c8 | note | Inspection Type (Visual, other) - Inspection
1f69888d-9be5-521b-8b70-930ad35e77a3 | note | Inspection: Key - H
0a6ffb7c-8726-500a-b717-540cc32356a6 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Subgrade Proof Rolling and Suitability Inspection
7c13ef1a-b92c-5591-80d0-541d366bc149 | note | Standard/Specification - As per project specification, Section 2.10 and NZTA F/1, 10.5.1
16813ca4-a16e-576a-bfd9-13eb8142c3c7 | note | Acceptance Criteria - The subgrade shall be proof rolled to verify the subgrade stiffness and consistency. "Indents" left in the compacte layer shoiuld be no more than 7mm for bulk fill and 5mm for subgrade fill.
4cfe1ca7-7025-58a6-aff4-7f87a6321075 | note | ○ The RL and area of proof rolling will be surveyed.
525434e7-e4e4-5b8c-8db7-9abee0216904 | note | Verifying Document - Proof Rolling Sheet, Photos, Survey area
4ac3541e-585d-5d93-8549-bffe21ef83e1 | note | Frequency - Prior to the placement of any filling, Whole area
4934239c-605a-52cf-95e9-b93abd1fbd33 | note | Inspection Type (Visual, other) - Visual Inspection
a841c17d-56ea-500a-a4b4-ebe5071371fd | note | Inspection: Key - H
12aa503a-7b64-5ba0-a956-721a820c5002 | note | Inspection: By - CR, SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.5 - Imported & Onsite Fill (Gap65/AP65) Compaction Testing (NDM)
58181767-8741-5246-805e-5e2e7cecfc22 | note | Standard/Specification - As per project specification, Sections 2.13 & 2.18
e24e05cc-34ef-5151-a21e-19c564f6d435 | note | Acceptance Criteria - Bulk fill shall be tested by NDM with a minimum Dry Density of 95% MDD
7395a479-b73a-53b0-9278-d56ae61063eb | note | Cohesive soils shall be compacted at OWC (moisture limits are 4% below OWC to 2% above OWC)
a151a6f5-cb91-5531-b032-835551885c1b | note | Minimum acceptable dry density for AP65 is 2100 kg/m3 , a minimum dry density of 95% must be achieved (moisture limits are 4% below OWC to 2% below OWC)
54b9ad88-b43d-5e4a-8d43-36e611708f7c | note | Verifying Document - Test Results
57d92153-ccb0-50d1-a2d7-27c8c362ce53 | note | Frequency - 10m x 10m grid
06add4c8-0f0f-5605-86e4-3af6f2933ca4 | note | Inspection Type (Visual, other) - Inspection
1cf61fea-bed0-5ae9-b34d-b11a26f5a838 | note | Inspection: Key - H
19b43954-4fe1-5922-b7bb-7b05af3b7833 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Geotextile Installation and Lap Length
0d168871-f6cf-5550-939f-56e75276439a | note | Standard/Specification - As per project specification, Section 2.15
7f832c87-66ba-5d80-919d-f5a398386ed7 | note | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
12bc4462-f362-5979-80cd-a457b33c3f8d | note | Verifying Document - Photos, As-built
eeb859b0-9ffc-5455-a317-7f3ce17fc72a | note | Frequency - each application
60e4761a-7394-565d-8ae9-492838727055 | note | Inspection Type (Visual, other) - Action
b0177165-76ba-5a57-9ec9-8a2397f087f9 | note | Inspection: Key - W
f652c49e-e800-5572-9ce8-f8a8047231ec | note | Inspection: By - SE
| section | 4.2 Landscaping
| checkpoint | 4.2.1 - General
6f00ebde-d620-5fda-a6ce-1fa59d68ee05 | note | Standard/Specification - NZTA P/39
629401de-8900-5202-8377-0dcc18e9bbb3 | note | Acceptance Criteria - Planting and grassing shall be in accordance with NZTA P/39.
5d148c5e-86d1-56e8-947b-c82bdc6ac50a | note | This includes, but is not necessarily limited to:
b9219ef3-e9fd-5f84-91b1-2125ff70b230 | note | ○ Site preparation for planting
9fb155a3-f36c-5df5-bbe6-eb433024f972 | note | ○ Topsoil placement
d820b9ad-5b38-5cfc-bbe5-81d32dea7669 | note | ○ Planting of grass and trees
beffc691-b658-5472-9c11-4e16ccd6fd40 | note | ○ Trimming existing garden beds
3f36637b-53a1-510a-a939-33b2ee0ed570 | note | ○ Replacing trees
4d4bf500-b716-50b4-adbc-e1f817a5b4d1 | note | ○ Supply and spread mulch
684d4d1b-b879-5729-95ae-7038763cd597 | note | ○ Watering
e0c2fa7c-1fbd-5f4a-ad8d-6b14a9ff0d93 | note | ○ Weed control
e2154a6e-2b40-5760-a443-fcfb95a0259b | note | ○ Maintenance
6d9f2b6b-ecdd-5cac-addd-af9e02fd8558 | note | Verifying Document - Photos, as builts
1e5b23eb-a429-5f2f-bc54-cadb178a64c5 | note | Frequency - All
aa6883fc-7cbd-5756-9477-680b7820655e | note | Inspection Type (Visual, other) - Visual Inspection
46bc7bf6-8570-5160-a981-4ee8cb0e5221 | note | Inspection: Key - V
bca0bc05-85e9-50be-9eb3-d27fd40e5cc8 | note | Inspection: By - SE
| checkpoint | 4.2.2 - Topsoil - Depths
567d3416-1d31-5187-a693-a5f8b18c9565 | note | Standard/Specification - As per project specification, Section 6.3
0ab55ff0-2f7c-56ac-b63e-995c5f0e3fc6 | note | Acceptance Criteria - New grassed areas shall have a minimum of 200mm depth New garden areas shall have a minimum depth of 300mm. Where required top soil areas shall tie into existing levels with a minimum depth of 150mm of topsoil and at a maximum grade of 1V:5H.
b612d7a0-c8cd-50f6-9b87-ede4ecde2e11 | note | Verifying Document - Photos, as builts
a541c999-9535-53b8-b029-59c8320865bc | note | Frequency - All
6696386e-bbc4-5fc8-b344-bc4262cfb591 | note | Inspection Type (Visual, other) - Visual Inspection
a16502c3-1941-51b5-94ff-fc64f0c64bc1 | note | Inspection: Key - V
c7c1647c-9aa8-50da-9b87-c765a4cdc7a0 | note | Inspection: By - SE
| checkpoint | 4.2.3 - Topsoil - Quality
5666c118-685e-5f3b-8a9d-3530ed190cea | note | Standard/Specification - As per project specification, Section 6.3
3e43bb2a-1fd0-5a6c-a52a-adea99780f16 | note | Acceptance Criteria - Topsoil shall contain less than 5% by dry weight of solid detritus and debris and stone content shll be less than 10% by dry mass. The topsoil shall not contain any object larger than 30mm in diameter in the largest direction.
c0b21cbc-27f3-5c05-bcf6-ee95fdf93008 | note | Verifying Document - Photos, as builts
8d3a6798-66d8-53e8-a592-4fe63d8ae36c | note | Frequency - All
dbb8b03a-2c16-5b68-bd46-29ea7617de69 | note | Inspection Type (Visual, other) - Visual Inspection
8e3fe73b-fd1e-5238-b9cb-36af31634c4f | note | Inspection: Key - V
78aab188-fdff-5ae7-a7e8-8c97b63d574c | note | Inspection: By - SE
| checkpoint | 4.2.4 - Grass - Fertilization
6423d1bb-c645-5038-9b4e-c439f0750363 | note | Standard/Specification - As per project specification, Section 6.4
30869cd8-9def-56c8-bc56-c92e7b0f38f6 | note | Acceptance Criteria - Superphosphate fertilizer shall be applied at 20 grams/m2 at grass seeding.
6b0ee617-517a-518b-948e-1457a0e4a526 | note | ○ Three weeks after seeding, slow release fertilizer shall be applied at a rate of 15 grams/m2
d3151e6e-40c4-5020-a7bf-9ed4ef2b2fca | note | ○ The fertilizer shall be 3-2-1 NPK plus trace elements mix. Hydroseeding is acceptable.
5f5c4a2a-0496-5315-992a-d1686d811c8a | note | Verifying Document - Photos, as builts
293d6589-730b-59e9-9381-5ae4ffabe2dc | note | Frequency - All
47d8d951-3c84-5dc5-863a-6ef550ea7985 | note | Inspection Type (Visual, other) - Visual Inspection
5d270d91-4afe-5fdc-a951-ded0f5744ee5 | note | Inspection: Key - V
8b1c1a1e-72e1-5980-b998-1bd2e693801a | note | Inspection: By - SE
| checkpoint | 4.2.5 - Grass - Coverage
0ea0ac31-9e3f-5644-a113-6256027f3e6f | note | Standard/Specification - As per project specification, Section 6.4
d60d19cd-d367-5c08-b36e-12fed98b78ef | note | Acceptance Criteria - At least 90% of the ground surface shall be covered with no bare area greater than 30mm diameter.
2c069889-b8ef-51c8-9da8-9373dc13257a | note | ○ The grass sward shall be maintained at no less than 90% weed free (i.e have less than 10% of it's area in non-specific grasses and weeds).
478b5019-ea62-5fa8-afe0-7faab504ac2b | note | Verifying Document - Photos, as builts
d1fb5ca0-6410-54b7-91dc-b977ef083aba | note | Frequency - All
da2c5e41-2271-53cd-8867-0ddcec43ab7e | note | Inspection Type (Visual, other) - Visual Inspection
b4b26ffc-82c4-581b-bc7d-d9d9a889cedb | note | Inspection: Key - V
7b74d0d1-59b3-5e42-90a3-e3a2302306a8 | note | Inspection: By - SE
| checkpoint | 4.2.6 - Grass - Seeding Conditions
1e410ad8-5f29-5764-989d-18e9fba31af8 | note | Standard/Specification - As per project specification, Section 6.4
62ff5f50-66dd-5e49-a488-442b0271833f | note | Acceptance Criteria - Work shall only be undertaken when the weather is suitable i.e mild, dull and moist, and when the ground is moist and workable. All planting and grassing operations shall be suspended during periods of severe frosts, drought, water logging or persistant drying winds.
9b11d33c-2478-5859-9a7f-56ad19e3955d | note | Verifying Document - Photos, as builts
fe530e2f-a338-5f1f-9fb2-a7f2ed473ec1 | note | Frequency - All
911362de-8efe-5387-b670-5046844b55f6 | note | Inspection Type (Visual, other) - Visual Inspection
a4307c8c-1b31-5f3e-94d0-5800f15a83fd | note | Inspection: Key - V
d3f42920-3868-5f17-bd7d-c7e523322e0e | note | Inspection: By - SE
| checkpoint | 4.2.7 - Mulch to Garden Beds - General
b2203548-c18e-50ee-a68a-18943bfe3ee3 | note | Standard/Specification - As per project specification, Section 6.5
a7253143-ab33-5955-8c3b-af1e05cea9fb | note | Acceptance Criteria - The Contractor is to supply and install organic mulch to all garden bed and planted areas. Mulch shall be clean, dry and weed free.
519c50c6-5535-549d-970f-18069db55be6 | note | Verifying Document - Photos, as builts
aadc2c17-f6f7-582f-bb57-33b6ac9e91cc | note | Frequency - All
239b1a72-0729-5402-8f57-6b9acea404a3 | note | Inspection Type (Visual, other) - Visual Inspection
58186820-f7a7-5adb-80f4-d68236e2229a | note | Inspection: Key - V
8d843eb3-5e73-579b-ba36-13575f0d6d53 | note | Inspection: By - SE
| checkpoint | 4.2.8 - Mulch to Garden Beds - Depth
f3db3289-c9e5-5558-8ff4-d04981e0ad16 | note | Standard/Specification - As per project specification, Section 6.5
2fa092b0-f84a-556d-b02a-e395d0cd3d4b | note | Acceptance Criteria - Ensure mulch is kept a minimum of 50mm clear of plant stems to avoid stem rot.
5ab7583a-1e1c-5908-8bf4-33b13d0309a5 | note | ○ Mulch depth shall be maintained to a minimum consolidated depth of 100mm.
eb910d9e-2345-59b1-baf7-8b5948f10a85 | note | Verifying Document - Photos, as builts
3cc88cb8-daa9-5526-a047-447eee9eb30e | note | Frequency - All
3830feff-b613-5a28-a6df-fb37e75e85a0 | note | Inspection Type (Visual, other) - Visual Inspection
76ee9f04-5edd-5663-b846-bc1df992c011 | note | Inspection: Key - V
ec9300cf-c41b-5ddc-abe7-d4081190fbd3 | note | Inspection: By - SE
| checkpoint | 4.2.9 - Mulch to Garden Beds - Surface Height
ef3504ba-2890-5871-b47d-2d370f3c2035 | note | Standard/Specification - As per project specification, Section 6.5
10c5f48d-929b-50a1-ac61-80f4aa1b1943 | note | Acceptance Criteria - The surface of the mulch shall be flush with or no more than 25mm below the surrounding ground surface, kerb, path or other formed surface and shall be even and free of hollows.
43a9016c-1ca8-5e3b-9399-97677039935a | note | Verifying Document - Photos, as builts
5a027780-9573-5cf1-b7b8-e0c21b508a24 | note | Frequency - All
036a9eab-a437-59a9-a5f1-d7c4930b8e50 | note | Inspection Type (Visual, other) - Visual Inspection
e6a8b4bd-7235-5381-9888-223a4b1ff4c1 | note | Inspection: Key - V
ae78ed26-5345-5e31-bba3-885665fdca7a | note | Inspection: By - SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
01c9624e-6bff-5e52-b9d5-9e8c82533603 | note | Inspection Point: Quality Control Activity - Upon completion of works
649b7111-a175-5b22-88a0-d5024ee8e898 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
a87e5099-d770-5f9e-81b4-abfebf8c2bcd | note | Verifying Document - Closed-out NCR/Defects
5d496a75-6a1a-5e06-b04f-d8868bcea30c | note | Frequency - Post construction
d43acfe9-dc08-52cf-bff7-18ac310f8418 | note | Inspection Type - Review
e05b4507-6aeb-5668-9975-3b5a7a155ec2 | note | Inspection: Key - R
afa91cb9-d1b1-588f-8a97-1671e2db32f7 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
5eedcc55-d342-5d05-84d8-73952b023b67 | note | Inspection Point: Quality Control Activity - Upon completion of works
262e92cd-1588-5b6a-861d-b5967ca36f66 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
eb320148-47fc-5ccb-b7df-cd7d38662a25 | note | Verifying Document - As built survey record completed
e091fc8f-31e5-5190-9b83-4e9776a38ede | note | Frequency - Post construction
8e0633dd-b0aa-558c-bc4d-0c72055c2b86 | note | Inspection Type - Review
a08481fb-6f08-5ab8-afdb-a9e950707aa7 | note | Inspection: Key - R
2a5e4de9-96dc-58c2-8e46-99c9f3062746 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
d01976a9-ed32-55de-9c98-e78d0e90ee43 | note | Inspection Point: Quality Control Activity - Upon completion of works
4c723a10-1043-5d81-8acf-685b6bf480ba | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
7103b937-3b5f-585e-b7ce-f95f86d98293 | note | Verifying Document - Signed As-built Drawings
65955ab2-4387-5c32-b90f-b2315f4de2e9 | note | Frequency - Post construction
f2891d85-2a2d-5fe6-b4a7-c0558d97af0c | note | Inspection Type - Review
87b9032f-05dc-5106-9a0a-834e951c6b8f | note | Inspection: Key - R
856d19ec-7417-5533-bb2c-4d75f6865050 | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
79669ad8-6ea2-56ee-8a51-46e6fc3a04fa | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
c53ff09b-9dd4-5f37-9d66-0aa0395c730a | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
b4079296-16d7-5888-bcde-05142e28ef1b | note | Verifying Document - Register
db6ce604-481d-54d1-9039-3a883bb17070 | note | Frequency - Post construction
14db9971-a9ba-53c7-964b-a85bdd12af19 | note | Inspection Type - Review
8bfd4148-3288-5cae-94c9-6cda64817532 | note | Inspection: Key - R
8fc6e775-ac08-5e1f-ac8b-a9db7eb98209 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
ae9bb30f-7b67-57d1-b4df-312d00d398e4 | note | Inspection Point: Quality Control Activity - Upon completion of works
ff3f9471-bbd7-5fce-8d4f-2b2a0e2fab94 | note | Acceptance Criteria - All signed and closed out
2f8bee37-fbc4-5bb6-84f6-1b84f1eb9ab5 | note | Verifying Document - Signed off Documents
c009d7bd-a845-547b-931c-b1d9da2a61d7 | note | Frequency - Post construction
d2eda39a-d31d-53aa-a09b-45a7944bf66a | note | Inspection Type - Review
0cd86238-8b0a-52ee-956d-059e36402e41 | note | Inspection: Key - R
1e690fbb-f8eb-5930-a10c-8e99ee0c4c00 | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC) | itp | 558020-DOW-ITP-PC-0027_v3 (Pavement - CVSC) | 5b39dd18-42f0-4f6d-858b-a020a6cd46ec
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
847d6c63-150e-5d03-b4c8-572eaa9c1c00 | note | Standard/Specification - Downer Standard
51547b4b-05d0-54f5-ad71-41c99c6c58d5 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
e10acbde-1af1-5d68-86f6-112f57296566 | note | Verifying Document - Survey Records
11ef350a-33e2-547a-a3b0-5c9adaf9493a | note | Frequency - Prior to Works
52dc4ddc-85de-549f-bf65-5490bd367253 | note | Inspection Type (Visual, other) - Document review
a2d1eebd-07f2-57e4-83cf-ff31eefbbfa5 | note | Inspection: Key - H
c9c97a5e-55e7-56da-a495-f79babdd4d85 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
0bc4e475-dc98-54b0-bcdb-80c7dc33ae29 | note | Standard/Specification - Downer Standard
b1c0ce26-ac85-5574-afc9-ff9c58e3f4ef | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
4532d5be-13bb-5093-bb9b-b6e5c046fbe9 | note | Verifying Document - Service location documents
c0de4a0a-e9a7-58a5-8db6-b4faba192ec6 | note | Frequency - Prior to Works
8e5a4fd3-4054-5dfb-8bd2-fab2b30f8af8 | note | Inspection Type (Visual, other) - Document review
7bad0b22-4f5d-5deb-bed4-34724344a3ca | note | Inspection: Key - R
fcfa1ffa-43da-5836-b5de-784c30a37fd6 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
14e8d99c-d3f9-5ce9-af98-2ac2f3ae69c8 | note | Standard/Specification - Downer Standard
11d6d146-3fa6-5f41-8263-1e6d98bd25fe | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
c823e88b-5484-5d5f-b5a7-a0c1acc19b3d | note | Verifying Document - Internal Permits
02bff64a-a626-531a-9080-2e9f2a2be348 | note | Frequency - Prior to Excavation
244db40d-5f54-542f-ba5e-7021bf34ce72 | note | Inspection Type (Visual, other) - Document review
db6d655c-aa25-5d2d-8dc4-8de9f923b4f4 | note | Inspection: Key - R
f6cc6885-0103-5eae-a2d5-5473f2be496c | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
42456ecb-0e2a-5f22-ad51-aac552887127 | note | Standard/Specification - Downer Standard
6b216733-50ad-5ca3-ac72-c23dca4d2717 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
14651cb1-fb48-5fee-98db-5925619faab9 | note | Verifying Document - External Permits
31dfc0f2-62f9-5f4f-876a-4eb683e30b2c | note | Frequency - Prior to Excavation
40cb714b-177b-5f44-9755-fc3fa8ec9802 | note | Inspection Type (Visual, other) - Document review
d7fc50c4-5ee3-5461-9d43-f05413f460e1 | note | Inspection: Key - R
41102a4f-b4aa-5351-b54b-2b10493cf8a5 | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
35bdff83-20c5-5855-a49b-8f06c1603704 | note | Standard/Specification - As per contracts
61e227a6-565a-57a1-9bcf-44b135572481 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
109b32af-0ff8-5ec5-9e2d-339a575e2ef9 | note | Verifying Document - Approved ESCP plan
b6392720-3a3c-58d6-a07f-f6d91116ced7 | note | Frequency - Prior to Works
dc86d3c9-08bc-5f20-8ca3-49d72dabd834 | note | Inspection Type (Visual, other) - Document review
b30b58a7-b818-514e-955d-bdd26ef4bc8e | note | Inspection: Key - R
aee0ae00-3b42-5b1b-89c5-f5f528f244ed | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
269e2b77-aae3-5868-ad5b-8ca0e59fd187 | note | Standard/Specification - Downer Standard
c4a09cf8-c6d2-5abb-b70f-16ea2274c86f | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
13987449-65cc-54a2-b233-8da961001b84 | note | Verifying Document - IFC Drawings
184d7c95-d855-580b-a1fe-6371a3466339 | note | Frequency - Prior to works start
d1058bc4-6a28-5cae-99e3-e4d1db34756c | note | Inspection Type (Visual, other) - Document review
1b3d5950-19ba-5d4d-b4b9-83742f191482 | note | Inspection: Key - R
6aee0706-6471-52c3-9461-c5841f1f745e | note | Inspection: By - SE
| section | 3.2 Pavement Materials
| checkpoint | 3.2.1 - AP65 - Source Property Tests and Sampling
025eb54b-75e5-5455-b5ae-4c8be92ad733 | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
76d9e947-ed83-58ac-8e50-02215aeb145e | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
8c69b5c0-1d01-5ec9-b682-fbd7f6f4b9b7 | note | Verifying Document - IANZ Lab Reports
3e91cc9d-3251-5cab-98fe-59b92b08823a | note | Frequency - 1 per source
f347a7df-9d4a-5bc0-b465-65336b90fd67 | note | Inspection Type (Visual, other) - Document review
13bcfb4e-eadc-5914-b34c-050df92f25ea | note | Inspection: Key - H
fb9f5ae7-e234-5d99-9838-2541c9681cad | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - AP65 - Production Property Tests and Sampling
93eccdd3-5ad9-57aa-ad62-765be2a11acb | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
839306f5-3f07-5f38-8e79-c70dd58a10e0 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
07725c69-f608-5a09-abfc-0a481b1673b4 | note | Verifying Document - IANZ Lab Reports
9928738c-73bc-54c4-8576-0e5834aab9fc | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
dd4ab942-e24c-5ea1-a39c-64a872008b97 | note | Inspection Type (Visual, other) - Document review
ddcd7515-6974-54b9-b5fe-2f0fc3e0828e | note | Inspection: Key - H
fa440b39-c232-5d4b-ab28-c87bf8e0c23a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.3 - AP65 - Testing for Layer Compaction - MDD
2e8614f5-d225-516d-8fe5-a4b2b291f80d | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
12b331b1-9ffc-5c88-842c-ef235f5e9cb4 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
24bbfb73-dfee-5e7d-8f10-5575c44ef0e0 | note | Verifying Document - IANZ Lab Reports
16fc6ebc-6078-5449-b275-282807911f20 | note | Frequency - 1 per material source (stockpile sample)
c0161c16-61b5-50f9-9ff8-dcfd016b6c28 | note | Inspection Type (Visual, other) - Document review
64af2501-0b87-5d34-bcae-4ce1b1ba534f | note | Inspection: Key - H
edf496ed-068e-557c-8df5-be1c6cc0a901 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.4 - AP40 - Source Property Tests and Sampling
462ebc7f-2a48-523a-900a-4eb982f94e14 | note | Standard/Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
3b23ea13-8e6a-5c59-b03e-54919b727d9e | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
76ecc44b-fa67-5391-bcb6-baa5cb70c0b1 | note | Verifying Document - IANZ Lab Reports
2ed6e7d5-c46c-542d-b0d7-74decd39e7bf | note | Frequency - 1 per source initially, then 1/1000m³ (stockpile sample)
cfcc56ee-3a01-56e7-919c-775fe3cf0dbc | note | Inspection Type (Visual, other) - Document review
5b5bea69-1b25-555a-9429-e3f465544653 | note | Inspection: Key - H
cd36a09d-8175-5998-8abc-a099c260a8d3 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.5 - AP40 - Production Property Tests and Sampling
25270210-6672-5907-bf26-856532744f6f | note | Standard/Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
2485bf5e-7d53-58e0-bbbc-02d94c63ec74 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
c1f653f4-a400-5ab6-b396-d659d0e86023 | note | Verifying Document - IANZ Lab Reports
68ee175b-ff47-52cf-bc06-57660bd6e464 | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
d66334d2-ced0-5f79-ba1d-996010f04c33 | note | Inspection Type (Visual, other) - Document review
13f942d4-94f9-5c3d-9162-a6de0df0a791 | note | Inspection: Key - H
4194cd99-5062-5326-904b-dca499d04ba4 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.6 - AP40 - Testing for Layer Compaction - MDD
20277a0e-40ab-56e5-b2cc-2fc3b3aa6ed6 | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
68aeed14-d535-5606-91df-d76b16409ea2 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
e5e5717d-e637-5254-9f8e-353b8bcad44c | note | Verifying Document - IANZ Lab Reports
81b5017e-4ef5-5867-8dac-1cf7a9dbceaa | note | Frequency - 5,000m2
c497769f-8831-5084-8927-732ee5c2864e | note | Inspection Type (Visual, other) - Document review
74fbd330-10aa-57ee-9db9-49d92c65f56b | note | Inspection: Key - H
6e90f090-fc99-5d32-af04-081efc8be709 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Sealing Chip - Source Property Tests and Sampling
cd9b86e7-dec0-5c02-a35e-393d80f8b4fd | note | Standard/Specification - TNZ M/6: 2019 - 4
f1334ba4-95d9-59cf-bdb4-ae9f78e0dff7 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
df6adaab-1aeb-55ae-bcb2-a8bae58440d5 | note | Verifying Document - IANZ Lab Reports
0a9630a5-950f-51e4-98ee-e9ba20ab8c5b | note | Frequency - Before Supply and Every 10,000m3 Thereafter
2c08ccf9-01b8-532e-8874-9b5006366c50 | note | Inspection Type (Visual, other) - Document review
d0e4ef01-e508-5d49-b0b5-2e3388fdf949 | note | Inspection: Key - H
4fd2731c-3475-58c7-a90f-1f4770ebc0eb | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.8 - Sealing Chip - Production Property Test Sampling
ab6cb2a3-5e88-5bce-ac12-db6edcbce305 | note | Standard/Specification - TNZ M/6: 2019 - 5
06ba3dd1-a062-5a53-bee9-d0dedacd9452 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
80940501-b482-5f7e-a04a-2c5aaebd11c1 | note | Verifying Document - IANZ Lab Reports
9600bd9c-d66f-5afa-9dbe-f6f8d5f8cc0a | note | Frequency - Every 500m3
994ceecc-6a9b-530a-9808-5f897d9acc62 | note | Inspection Type (Visual, other) - Document review
a7c3e921-da14-5d9a-b278-84d75a3ed410 | note | Inspection: Key - H
692dfdbc-cf37-5335-aed3-77e35c7c2d2d | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.9 - Bitumen - Quality Testing
5336e6cf-cb52-54a8-a887-cfa3b9d6fad4 | note | Standard/Specification - NZTA M01: 2022 - 6
de21d394-2f36-5454-93fd-f3c7f6876ce5 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
1f83164f-d4c2-566b-ae2a-31a824a921db | note | Verifying Document - IANZ Lab Reports
0426be1e-bef8-557f-896e-a224aa5859d1 | note | Frequency - One test per grade supplied
1b040053-af9b-5fb8-ab87-4f6f89897872 | note | Inspection Type (Visual, other) - Document review
7496179d-3c18-52ab-9a56-dc911bda82e9 | note | Inspection: Key - H
6aa2cb72-192c-5bf4-8efd-28d7bc189775 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.10 - Bitumen - Supply Testing
983377e9-b640-5f14-8123-8b717540c625 | note | Standard/Specification - NZTA Q05: 2022 - 6.2
921baa72-6979-53df-9cca-d4d7225acaaf | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
3008cbbe-83b8-51c0-8829-2820d70f5b8a | note | Verifying Document - IANZ Lab Reports
d27ba970-52ce-5658-8171-aa2e436e158a | note | Frequency - Every 200 tonnes supplied.
cec30357-b157-57d4-9ed6-85fa4b04b211 | note | Inspection Type (Visual, other) - Document review
16ac327b-3792-5cd8-bf17-9a4a341bc182 | note | Inspection: Key - H
52404e03-3df9-5885-881a-93b58a7fe70a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.3 Cement Treated Basecourse
| checkpoint | 3.3.1 - Cement
5d02a1df-ba37-5196-962a-6765e40d7244 | note | Standard/Specification - NZS3112
60c5f12e-e96c-5515-846f-d4a1dc34e291 | note | Acceptance Criteria - General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents.
3f4de7f1-65c5-52a9-b46c-e439e219847c | note | Verifying Document - Datasheet
2342d9cb-619e-5fa6-8e0e-256e231bb9ac | note | Frequency - Prior to use
1c1991c1-7ef2-5313-889e-e31206622f1f | note | Inspection Type (Visual, other) - Document review
0a4bf14e-922e-5a08-b363-20594f23c4d0 | note | Inspection: Key - H
fdcf682b-e586-5b92-b5a1-7b8255f00cee | note | Inspection: By (Role Key) - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Asphalt
| checkpoint | 3.4.1 - AC14
085959e3-473f-5492-898d-c979db790582 | note | Standard/Specification - Pre-construction
1e3fb505-ce28-58b8-ac26-adffdb56f529 | note | Acceptance Criteria - As per NZTA M/10 specification
69785efa-5fb3-5b73-abba-67e76cd183a2 | note | Verifying Document - Mix Design, Production Test report or Volumetric properties
d75b140a-7f69-51e5-9719-c41db3c29d86 | note | Frequency - Per Mix
fb8a6e52-11e0-51f6-b035-e4283ef19cec | note | Inspection Type (Visual, other) - Document review
b371a82b-3d93-5e23-94cf-e3a5f975cd9a | note | Inspection: Key - H
322fbc31-1b06-5ddb-8c67-dfc03eecbd70 | note | Inspection: By (Role Key) - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.5 Geotextile and Geogrid
| checkpoint | 3.5.1 - Geotextile
f4b80b72-7f7e-593a-8cc0-e70257667aee | note | Standard/Specification - Class C as per design spec
3591d190-8c68-5f58-9d4f-15d8b42f6fa1 | note | Acceptance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
54366453-7a09-5ad3-b37d-30b45197b11c | note | Verifying Document - Datasheet
d1c69967-27ff-5995-b9e5-d06a92883690 | note | Frequency - Prior to use
74357906-3520-5e9e-bb6c-e24f10daa5ad | note | Inspection Type (Visual, other) - Document review
ce00c77c-76be-5b98-b78a-2ea5cba254fa | note | Inspection: Key - R
6586a027-ed2c-5c81-acc3-2386685d97ce | note | Inspection: By (Role Key) - SE
| checkpoint | 3.5.2 - Geogrid
9724947a-f3fc-5bb8-aff5-0f1077ffdbd3 | note | Standard/Specification - TENSAR TRIAX TX160 as per desig spec
d197e62e-5452-5a96-9a4f-ac56497689ae | note | Acceptance Criteria - The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001.
c76b9ade-47ac-5e04-b5f2-057bf5f56739 | note | Verifying Document - Datasheet
5b55d26b-51e9-5a6a-9557-d1f7ec92a449 | note | Frequency - Prior to use
477a408d-62f9-5267-a31f-fe8222604904 | note | Inspection Type (Visual, other) - Document review
54348746-9c79-5e47-bb6f-d8a1f99e9c7b | note | Inspection: Key - R
f7bf5415-7b52-56fa-bde5-8de064306b3e | note | Inspection: By (Role Key) - SE
| section | 4.1 Unbound Pavement Construction
| checkpoint | 4.1.1 - Top Subgrade CBR
4fe7f51e-cd23-5e93-a34c-b4f73e92fa6d | note | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
fe7a0bbc-445c-51fe-a7f1-c76b0d0d169a | note | Acceptance Criteria - Minimum CBR 3.5% to be achieved failed to achieve the above need to carry with the contingency details as per Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
121e28f3-f471-579a-8385-c6d474982cc4 | note | Verifying Document - Test Report
65e3cbb6-3d98-579e-8de3-2a48d976cad0 | note | Frequency - Before starting Subbase layer, whole lot in 20x20 centers
393bb36d-eb04-53b9-996c-cd1b70181b03 | note | Inspection Type (Visual, other) - Check
3d03200b-82f0-524e-ad91-cb63f869994f | note | Inspection: Key - H
d7cc96e6-dd64-5b1d-9284-bbf0492e358d | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.2 - Geotextile
d4280938-d187-554d-9391-285439766aa5 | note | Standard/Specification - NZTA F/7
e8a9f971-55f7-5857-9aec-8c5c72204ff9 | note | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
acde397f-2e38-5dc9-9973-add86530d092 | note | Verifying Document - Photos
c9367394-24b0-572c-a7ad-aef5c5223ef3 | note | Frequency - Each roll out and overlaps
290bf472-3f0a-5b45-bea1-761d55905c81 | note | Inspection Type (Visual, other) - Check
1214d1d7-3585-5a64-a30c-be964ebae246 | note | Inspection: Key - C
5a6510ad-abf2-5af8-a572-ff70e77fb79d | note | Inspection: By - SP
| checkpoint | 4.1.3 - Geogrid
da6273fa-3b3c-53b1-8b95-c5b4638ff1a9 | note | Standard/Specification - Project Specification CVSC Pvmt Type C Detail on Bartley Dwg TD002
d735b33e-8e3d-5305-98a3-50970b465a40 | note | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
adc09031-f655-5199-8a31-c8a805107a71 | note | ○ A minimum overlap of 500mm is required between sheets.
53f09362-bc19-5496-a161-d395471a42fc | note | Verifying Document - Photos
a4a3b83b-78ce-5e78-9b6a-03ee40edfeb7 | note | Frequency - Each roll out and overlaps
8b93c68a-be27-5d60-b662-f4d4e948bf30 | note | Inspection Type (Visual, other) - Check
43dc1c06-fcc8-51af-8345-0b8b162e3ca3 | note | Inspection: Key - C
8a99809b-8cab-55f5-961a-f2e7218340b8 | note | Inspection: By - SP
| checkpoint | 4.1.4 - Material Placement
1a4350b4-776f-5696-b146-69c7defcde88 | note | Standard/Specification - Downer Standard
626f7f68-5e8c-57b3-924b-14ad47cf805d | note | Acceptance Criteria - The uniformity, contamination and segregation shall be Continuous monitored thoughout
139f4ff0-39bc-5893-8dd0-cf9958a63ce2 | note | Verifying Document - Photos
902d769d-9815-540f-9a68-60a99c12f9e4 | note | Frequency - Continuous monitoring.
7fd7a35b-d3f0-58bc-b430-1026234e914b | note | Inspection Type (Visual, other) - Check
77b46f8d-bf09-5f55-abe6-c96a744e771a | note | Inspection: Key - C
6a4c4865-858d-59ad-b2ef-3721997ba2f9 | note | Inspection: By - PS
| checkpoint | 4.1.5 - Plateau Density Tests (Sub-basecourse)
f022dfb3-02a9-54d0-a60a-c17266fd33ec | note | Standard/Specification - TNZ B/02: 2005 - 7.5
5b641802-8f10-5e0c-84d6-ff290c839f88 | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
4b47ce51-ff0b-547d-b1ab-9e19f94e6f64 | note | Verifying Document - Plateau test results confirmance
94c362d3-4ca8-57e5-953d-28f206f8354d | note | Frequency - Continuous monitoring.
68877cbe-0e10-5521-8896-51df2bbd7397 | note | Inspection Type (Visual, other) - Check
237483d6-6430-5a77-afc3-0e6d4f9f7378 | note | Inspection: Key - C
89b7d323-726c-5597-af45-97fcb1f6bde6 | note | Inspection: By - SE
| checkpoint | 4.1.6 - Sub-basecourse Pavement Layer Compaction (NDM)
0b317ecc-f599-557e-a9fc-d52b262b6ea9 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
e45e31fd-44f2-595f-9f6c-27535b97a2cd | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
ba2e9f35-1846-5c57-9fdc-6e65e46052f9 | note | Verifying Document - NDM Report
3bb5b311-8fa4-5cea-a040-8a68c36aad38 | note | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
9ad5e5fc-7238-5337-a7b0-2a12291674c8 | note | Inspection Type (Visual, other) - Check
31d91026-8d89-50a9-8ff8-43422c480db2 | note | Inspection: Key - H
a0976e49-e937-5262-ae01-f513f717beed | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.7 - Sub-basecourse Layer thickness
cf82c409-73b6-51cf-a395-d616f1a2e90a | note | Standard/Specification - TNZ B/02: 2005 - 5.1
2bd77f62-23af-56ed-ba63-a1b8882a791a | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
a45c92cf-9185-5fa3-a631-b4e114db4fd3 | note | Verifying Document - Survey / Level Checks
b54c2100-c4d0-55d2-a0cf-240431b6cfef | note | Frequency - 1/20m Full width
7b6fe019-8954-5450-a62b-f6f82cc8c522 | note | Inspection Type (Visual, other) - Dimensional Inspection
320dc52f-fc06-50f7-bc50-5deceb0bcfb8 | note | Inspection: Key - D
7023e306-7b67-5d21-96bc-3db133ef867f | note | Inspection: By - SV or SE
| checkpoint | 4.1.8 - Benkelman Beaming on Subbase
31676058-177e-5367-93e1-4b95f17904d4 | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
0afb38bc-a49a-50d6-9b57-9509acf89c7a | note | Acceptance Criteria - 90th percentile deflection ≤ 1.3mm.
a7c4464f-3fe4-5cbc-a15f-738fd795c723 | note | ○ No single deflection > 1.4mm.
88e475d4-930a-5782-bcc9-6e8e8304d741 | note | Verifying Document - Test report, delivered weekly
5db4fc73-fb40-51eb-820e-e2b6c3bd7237 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
a1f6c029-e61c-5520-bd71-2bf1ec6b0bb1 | note | Inspection Type (Visual, other) - Dimensional Inspection
efdaf6a5-054e-5aae-a941-8d121578972b | note | Inspection: Key - C
ef72d68b-643f-5733-b528-444878b04a1c | note | Inspection: By - SE
| checkpoint | 4.1.9 - Plateau Density Tests (Pre stabilise Basecourse)
2f537b3e-213c-5c32-9698-dea246a9484e | note | Standard/Specification - TNZ B/02: 2005 - 7.5
3848e550-0918-5b21-97bd-b2a70354dd19 | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
6d69fb1c-2b62-5989-8d7e-2d476fbf3b55 | note | Verifying Document - Plateau test results confirmance
8f3b895a-22ef-5724-a7c3-4f25e6694d51 | note | Frequency - Continuous monitoring.
8d59f6e3-c214-5392-a6e7-a57a8894cfc4 | note | Inspection Type (Visual, other) - Check
fd14b396-5b34-52de-a639-b1b7559d47f4 | note | Inspection: Key - C
10375e7b-42c5-525d-97d9-6926ad1ce04b | note | Inspection: By - SE
| checkpoint | 4.1.10 - Basecourse Pavement Layer Compaction (Pre stabilise Basecourse)
e0f3aae0-6af8-5b11-ab3b-2832a9e6fd59 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
326aecfe-2614-573d-b9b3-e3bafc59f011 | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
f9764152-741e-5d47-a18b-bf6d91f2ad80 | note | Verifying Document - NDM Report
491de88f-e6c8-5ae9-9d9a-fa62b2d9e4b5 | note | Frequency - 1/10m each layer not exceeding 200mm. If no clear lanes then 1 test per 50m2.
a46533b7-dea0-52ce-9bc3-321100c8b83c | note | Inspection Type (Visual, other) - Check
598f44bd-3903-5017-8c40-b5f100449c22 | note | Inspection: Key - H
d5414d93-8f3e-5066-b08b-d85f9e918f41 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.11 - Basecourse Layer thickness. (Pre stabilise Basecourse)
05000847-8f1a-54b3-b329-07f0d7e3bdcb | note | Standard/Specification - TNZ B/02: 2005 - 5.1
41e97ab2-6a1e-50b8-9fb9-204cbb73a124 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
d1224440-2053-5ccc-aa77-8e1b0a16bc91 | note | Verifying Document - Survey / Level Checks
69481786-4491-5d91-b755-f9d7eb497a57 | note | Frequency - 1/20m Full width
57f1aa10-14ed-5721-9795-1bf4512e51b0 | note | Inspection Type (Visual, other) - Dimensional Inspection
b359a309-d84e-5d1f-8ca6-709699d86d06 | note | Inspection: Key - D
dbeced11-ee46-52de-b986-4fc17714b892 | note | Inspection: By - SV or SE
| section | 4.2 CTB (Cement Treated Basecourse)
| checkpoint | 4.2.1 - Pre-Stab check
5195348e-f429-5959-a38d-d79ac57c3a7c | note | Standard/Specification - Downer Standard
34c626f4-2d7e-5133-8142-48c484d86589 | note | Acceptance Criteria - Check the temperature (between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs)
c4ff8757-c2d5-5ed5-8708-2f7c07d1cbad | note | Verifying Document - Checklsit
d33b04e3-297e-596a-aee6-b22f63f6d490 | note | Frequency - Befoore the stabilisation
a54d4c6c-866c-553f-bb60-ae362e7b4c54 | note | Inspection Type (Visual, other) - Check
7de51829-eec2-5e35-af0e-d7c8cfa67517 | note | Inspection: Key - C
550cfcd2-2203-5be6-afbd-3e517fbd3eb5 | note | Inspection: By - SE
| checkpoint | 4.2.2 - Mat testing
b1ac9697-e45b-5b33-973e-4b1834094c98 | note | Standard/Specification - NZTA B/5: 2008 - 7.3
708784e8-45d8-5dc0-b55c-ed8da7dd449b | note | Acceptance Criteria - Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate.
f8c7f5f9-2077-5ff0-8abb-fec1176d53b0 | note | Verifying Document - Test Results/Photos
6b02d068-2d94-5800-a42c-38fbb216db92 | note | Frequency - Every 400 m2
49cf340a-c862-5d0d-bbf4-743ede17a0b2 | note | Inspection Type (Visual, other) - Dimensional Inspection
4cee6249-470f-5ad5-8702-53ccba59eabb | note | Inspection: Key - D
de7a40fd-0e68-5876-897d-7e585b4d4c6a | note | Inspection: By - SE
| checkpoint | 4.2.3 - Average usage test
69db5051-878d-5577-8ee2-1ab3615b4d36 | note | Standard/Specification - NZTA B/5: 2008 - 7.3
a67a06a8-5077-51a2-943c-bba07a34cf2a | note | Acceptance Criteria - Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate
12c3edac-159d-5c12-98f2-a583283ca55b | note | Verifying Document - Calculation with Dockets and Weights
b845eff4-4ac8-590b-9961-0e3c159de34d | note | Frequency - Upon emptying the spreader and bulk tanker
09a138af-4d58-5094-9cf2-9400023f0366 | note | Inspection Type (Visual, other) - Dimensional Inspection
89d2c230-3a3e-50a2-ac1e-de1105d38751 | note | Inspection: Key - D
4ebf7371-f59e-5d51-ac17-ae07617c0af4 | note | Inspection: By - SE
| checkpoint | 4.2.4 - Water content during compaction
22fc1983-2698-5f62-9df2-d09ec62d3c72 | note | Standard/Specification - NZTA B/5: 2008 - 7.5
07f74200-c973-5203-a0c8-e07b977afd65 | note | Acceptance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records.
78145596-e2a9-5be2-8236-b8d3c561a78b | note | Verifying Document - NDM Results, delivered weekly
2d7fcdf1-7794-5e98-aaf6-9212f8bcb683 | note | Frequency - 5 tests per 1000m2
e21d4a40-e079-507e-a5b6-55c6f16ef766 | note | Inspection Type (Visual, other) - Check
88753d38-4e80-5169-8077-b36209f6b784 | note | Inspection: Key - C
f6f19f7c-b370-5806-b10b-93190d640459 | note | Inspection: By - SE
| checkpoint | 4.2.5 - Control of cut depth
7be3ea67-180c-5313-8fe3-c5bcc4a833f7 | note | Standard/Specification - NZTA B/5: 2008 - 7.6.1
5cf8ec65-9b6a-5b07-ba03-ddb6bcadbb2c | note | Acceptance Criteria - The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer.
22cfa1b7-74d8-5046-a2d9-b031dfcbbffe | note | Verifying Document - Site Records/Photos
3510c2e5-4ed1-54cb-8296-616f7f6145e6 | note | Frequency - Each Cut
95445630-eeee-5814-b7bb-eb0496b5264a | note | Inspection Type (Visual, other) - Check
83f59a6c-7f7c-53d3-83dd-21a652f2af96 | note | Inspection: Key - C
b3053f1a-a754-5b67-98bc-fbe16bf47d9e | note | Inspection: By - SE
| checkpoint | 4.2.6 - Overlap on longitudinal joints
fedefdc5-6f28-5c70-ad50-419d675eb324 | note | Standard/Specification - NZTA B/5: 2008 - 7.6.2
f7c5051b-8114-5cb5-a3b9-17855536cb59 | note | Acceptance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater.
878e400a-0aa4-51a3-8c7c-b5845bc37a94 | note | Verifying Document - Site Records/Photos
80f0e09a-bbef-589f-8486-f53a96f5c983 | note | Frequency - Each Cut
6f53401b-533b-5360-bee9-a55f30cd9bd4 | note | Inspection Type (Visual, other) - Check
741f4c81-77f5-5478-bf65-01c20113a4d1 | note | Inspection: Key - C
16e03a93-a570-5843-99f0-0f8d28284966 | note | Inspection: By - SE
| checkpoint | 4.2.7 - Continuity of stabilised layer
afffdc2a-bdf9-5244-b6c1-e3e875efdfcc | note | Standard/Specification - NZTA B/5: 2008 - 7.6.3
384de8c8-2324-5713-8579-2d126dff1f93 | note | Acceptance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark.
b7beef9a-3268-5f6d-95a1-cadecbffc524 | note | Verifying Document - Site Records/Photos
0b08f505-1f06-55f2-8ec3-93d2209a524a | note | Frequency - Each Cut
f3b91639-3eb5-546f-bd1f-0af84d527a80 | note | Inspection Type (Visual, other) - Check
e99c7cb7-a0fa-5e66-a981-f45641e84931 | note | Inspection: Key - C
1243b47c-b79a-50d7-9e9a-08f98cfe0cd6 | note | Inspection: By - SE
| checkpoint | 4.2.8 - Plateau Density tests
9c2986e5-9f59-5de6-9183-07ab9ec960a0 | note | Standard/Specification - NZTA B/5: 2008 - 7.7
5894f7ec-b942-54ec-8548-7557c5e07603 | note | Acceptance Criteria - At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted.
0806a46b-8158-587b-899e-a9a957ad1a76 | note | Verifying Document - Plateau Density test
ec246258-a89e-50d0-bfa6-8a0d4194fc45 | note | Frequency - Continuous monitoring.
511fb46a-a29e-55b8-b219-f16ede65111c | note | Inspection Type (Visual, other) - Inspection
4ccc6739-0509-5b52-97cd-d87989858da9 | note | Inspection: Key - I
1be8d6fb-ef20-5da7-9a9c-3d8d0da4b227 | note | Inspection: By - SE
| checkpoint | 4.2.9 - Compaction testing
d5709ae7-458a-5298-8236-0cafbc0fc2cc | note | Standard/Specification - NZTA B/5: 2008 - 7.7.1
a8efca4c-808c-5871-a550-caf6551d7bd7 | note | Acceptance Criteria - The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots.The area of a lot shall not exceed 1000 m2
89dfc105-9dbf-531d-a1b4-7f8c169bf884 | note | Verifying Document - NDM Results
cabbbf80-6dc6-5085-a11a-ee1a3bca2343 | note | Frequency - 5 tests per Lot
efed4098-94e6-556d-a9e6-13263c043992 | note | Inspection Type (Visual, other) - Check
7403241b-4bf6-5611-a069-92ed61354cb4 | note | Inspection: Key - C
ae754a14-12b4-5b10-88b2-9ede924c7104 | note | Inspection: By - SE
| checkpoint | 4.2.10 - ITS Testing
e79f2903-cc64-51ab-98e4-7484ef86faa8 | note | Standard/Specification - NZTA T/19, Contract Specification, Section 3.6.5, Appendix F
ffccd810-7b2b-5110-899c-642e1ccea1f5 | note | Acceptance Criteria - ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows:
7ca30abc-880d-59ab-9e85-8aea916fcc05 | note | ○ Dry: 150kPa - 350 kPa
1cef5fa9-4a43-5a34-81eb-776117c8949c | note | ○ Soaked: 100kPa - 300kPa
2948cf31-f97f-5b95-94b5-b00f01c65801 | note | – The Tensile Strength Retained (TSR) shall be no less than 75%
9ec95b0c-ab9f-5cd9-ae31-5c21bc5bbc64 | note | – If results are below the target strengths then notify the Engineer immediately.
8c6715d4-f3a1-50b1-944e-9a11fe983855 | note | Verifying Document - Test Results, delivered weekly
76fe2990-37f2-56e1-9c98-30e49db41785 | note | Frequency - 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation. Samples are to be taken from seperate locations.
2a204e19-3dc6-5a7a-a5e8-810bf447c3bb | note | Inspection Type (Visual, other) - Check
c85720f8-818c-50c1-92b4-844a978adfe6 | note | Inspection: Key - C
f5c7411b-8ab7-5c66-9927-2f377f984f24 | note | Inspection: By - SE
| checkpoint | 4.2.11 - Benkelman Beaming on Basecourse (cement modified)
0171acd1-0883-5933-930b-d1e308eaf506 | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
7668d6ce-6b2b-5d7d-ac09-80a6c4114479 | note | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
4644cc20-be73-5193-8880-d23ef17ed570 | note | ○ No single deflection > 1.1mm.
097e6e99-b632-5331-bd7c-8bbf7e738d6c | note | Verifying Document - Test report, delivered weekly
b20fe515-d609-5f84-98ef-91fbc8ea5f10 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
7b602984-bcd1-5fb1-9858-018265e59fae | note | Inspection Type (Visual, other) - Dimensional Inspection
2f745f6d-8d3d-5632-81ff-817cd8c4ca4d | note | Inspection: Key - C
193b6086-6afe-57b1-a9dc-3268b080a0d2 | note | Inspection: By - SE
| checkpoint | 4.2.12 - Construction Tolerances
a0f43756-5a3a-5658-a7d9-e1ab844e7804 | note | Standard/Specification - TNZ B/5: 2008 - 7.8
4e594773-20a4-5f31-a707-fe128c64addf | note | Acceptance Criteria - Basecourse where asphalt surfacing with concrete channel
3cdcefd6-9d2f-5139-8f8a-80eafe75644f | note | (i) at or close to the lip of channel –5 +5 mm
8c214878-f448-54b0-afee-d712bf8d8f46 | note | (ii) at other locations on pavement –15 +5 mm
ce03b0e4-a2c5-55db-82fc-4633a85753a7 | note | (iii) at other locations on pavement –5 +15 mm
4424ef15-913f-590a-8c0c-92eb9b7d4193 | note | Verifying Document - Survey Records
c667262c-9d04-5082-80f2-9ab2f7ee4597 | note | Frequency - On final layer
52046d0e-ad7b-58c4-b8b5-ce6fd83dcb18 | note | Inspection Type (Visual, other) - Dimensional Inspection
e9293513-53aa-5d48-a9ed-cc1cc4ccdbb2 | note | Inspection: Key - C
5953f9e7-f075-59be-ba0e-d4e3d95c3701 | note | Inspection: By - SV
| checkpoint | 4.2.13 - Surface Finish post sweeping
fe80ecf6-f991-52c9-b44d-11694ef9451e | note | Standard/Specification - TNZ B/02: 2005 - 7.8
f1ae74c0-2813-567f-8fe0-299f33d7acb0 | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
bd032a49-6016-5ec7-90fc-c9de2b3c6c09 | note | Verifying Document - Photos
7a62b4ab-7cec-5f97-8a7b-e66bf98f78ee | note | Frequency - Prior to sealing
d48b8225-3a4b-5f06-b1a8-a7abe758daa7 | note | Inspection Type (Visual, other) - Visual Inspection
4324aff6-df12-5ae2-98d0-d4d1147e83c9 | note | Inspection: Key - V
dc137125-de92-5b6e-bc2e-508a86d8841b | note | Inspection: By - SE
| section | 4.3 Grade 3/5 Chip Sealing
| checkpoint | 4.3.1 - Presealing Requirements
41393b5c-8e84-5b6d-9530-8cec2e1cfb61 | note | Standard/Specification - TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7
18bd21a3-db49-5431-add5-8d9b58e80448 | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%.
56cbf788-3ebf-5b17-9194-d0b987ad72d4 | note | Verifying Document - NDM Report
a2c743c6-d41c-5ed1-9502-2b3767223f48 | note | Frequency - 1/10m
d0d1b3e4-0905-5246-aa7f-a733c88977bb | note | Inspection Type (Visual, other) - Check
5838e3b6-1f01-56a9-93ae-203396b128f1 | note | Inspection: Key - C
ecd6cd24-c3a1-547f-bfcc-df19bac36b15 | note | Inspection: By - SE
| checkpoint | 4.3.2 - Benkelman Beaming on Basecouse (on AP40 CTB)
eb0fd6d7-206f-59a6-9451-049fc5bacf0a | note | Standard/Specification - Contract Specification, Section 3.5.5 & Appendix F
c2f542ef-1cb4-5fa7-8c30-f18440e993ba | note | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm.
c2f7795a-ee6b-5eb0-8b6b-4e5f3eebd673 | note | ○ No single deflection > 1.1mm.
75e8975a-4131-54a8-8167-88c9eb29d703 | note | Verifying Document - Test report, delivered weekly
a41540db-f185-5400-8c94-83278ff5d6c8 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
c42414e5-7507-5f95-987d-f26d4302ddda | note | Inspection Type (Visual, other) - Inspection
c3fff91d-592e-5a7e-abc7-2c55b291127f | note | Inspection: Key - I
ed7850a2-7b93-5a21-a943-f6059b8218ea | note | Inspection: By - SE
| checkpoint | 4.3.3 - Preseal inspection/ Subbase/Basecourse check
165fb6df-bd43-5614-a694-35f255e77a06 | note | Standard/Specification - TNZ P3 TNZ B02
8b734e14-a67f-5d30-bfe2-5e76d6897e40 | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade.
140c78de-2e3c-59f1-9777-084d50134b4f | note | ○ Visual inspection by engineer's representative
460dfc1b-87b4-5176-a8db-d5c696fb09fe | note | Verifying Document - Hold point Release, ITP Sign off
9541677e-1179-552a-a833-9c55395057f0 | note | Frequency - Prior to sealing
b031aabc-21b0-5c78-ae01-20cd30fa4514 | note | Inspection Type (Visual, other) - Check
f162c79b-e62b-5a74-a32f-f5f1e6abf9df | note | Inspection: Key - I
ba4da028-98f3-5df9-a52c-0fc85840e664 | note | Inspection: By - SE
| checkpoint | 4.3.4 - Spray Temperature
2d6ed30a-76ef-5cc5-9018-463d3e7243fe | note | Standard/Specification - TNZ P3
eead3e59-04bc-541d-bb85-8f1c7d469f70 | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
86d560be-5cbf-5bcd-a8a3-376c5be05cb4 | note | Verifying Document - Sealing statement
a6c1711f-86cc-56f8-af70-73cf05c3b9d0 | note | Frequency - Prior to sealing
3ae4d9d5-a344-533e-a115-8f0a96a6c44d | note | Inspection Type (Visual, other) - Check
dfdfffee-41c7-5203-8366-359567559186 | note | Inspection: Key - I
cef81091-b8dc-53b0-bb11-3fd9b9dd4522 | note | Inspection: By - SE
| checkpoint | 4.3.5 - Chip Application
536dc5d3-6aa8-5d9f-8c4b-51a2a8d4adf4 | note | Standard/Specification - TNZ P3
639d64d7-303d-5408-8112-be9f3b325181 | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
0bab0fab-49a6-5f45-941b-0c7dcb993cc7 | note | Verifying Document - Sealing statement
fd9c69d8-7a59-55ac-90e8-50dbbaa34749 | note | Frequency - For every spray run
1a0beb19-9e6f-5869-9368-e39ec3ac2777 | note | Inspection Type (Visual, other) - Check
227a1f69-99e9-5394-ae82-5b70577094f3 | note | Inspection: Key - I
4078f6fb-0e7b-5e85-bf9a-82956cfe9a3a | note | Inspection: By - SE
| checkpoint | 4.3.6 - Post Seal Inspections
3ad10fb2-a25b-59b0-9a6e-c2dc68479575 | note | Standard/Specification - TNZ P3
6b3612c1-03ff-5750-9abb-db2d83ef77d7 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
3f656ee5-a725-5ae7-a7ed-3c735d83ad98 | note | Verifying Document - Engineers Acceptance
7a11de81-0bc2-5ffe-aca7-a197002ca3da | note | Frequency - After Final Sweeping
e6461434-142d-5d88-8be8-b4f3b945182b | note | Inspection Type (Visual, other) - Visual Inspection
82dc6453-4e7b-5010-bf4c-dbdbb407c0a2 | note | Inspection: Key - H
f0755141-c96d-5bce-9916-3f36876cf1b7 | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3.7 - Chipseal Repairs
a5a948b1-5409-5dc3-9312-f6ca53e4326e | note | Standard/Specification - TNZ P3
3162bf64-cdd6-5d6a-86df-16700739846a | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
992ce976-cf4e-5c82-8e12-6f5cf2cace40 | note | Verifying Document - Approved Repair Methodology
d5a38a4e-a755-5b7a-a5dc-96276eecfb1f | note | Frequency - Prior to Repairs
232f7ebd-711f-5317-85bc-d63af1d1c878 | note | Inspection Type (Visual, other) - Review
83298693-fe30-501e-986c-d124136dd013 | note | Inspection: Key - A
b530ce4d-af38-5b86-899e-285901a41227 | note | Inspection: By - SE
| section | 4.4 Asphaltic Concrete (AC14)
| checkpoint | 4.4.1 - Preparation of Area to be Paved
bd85a623-191b-5286-8082-72c766078535 | note | Standard/Specification - NZTA M27:2020 - 9
ef53f705-d1d6-5ecf-833b-76d18bf402a4 | note | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
26ecfa1d-3534-5a5d-817e-428985ebb7ed | note | Verifying Document - Site Notes/Photos
6c1c75ed-645e-58e0-84db-c4e3489014dd | note | Frequency - Pre Seal
cbabbb51-b5c1-5b80-b2d6-97f59805cd1b | note | Inspection Type (Visual, other) - Visual Inspection
b148d054-b7a8-54cb-aaa3-b4e177a8e9f8 | note | Inspection: Key - V
4d2a6ad2-3d52-511b-b0e0-0ef0a0df0740 | note | Inspection: By - PS
| checkpoint | 4.4.2 - Ambient Conditions for Placing
a0c15321-b6b9-5a04-a8ad-88b9447b4e33 | note | Standard/Specification - NZTA M27:2020 - 9
812e851a-fd8c-5e0a-a867-641d1dc5c719 | note | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
11cb05d8-8e4f-53fc-9b94-9668458b09bd | note | Verifying Document - Site Notes/ Weather report
ff35a444-34ed-5278-b521-2c0d8837c9d2 | note | Frequency - Pre Seal
23a1774e-469d-519a-9d3f-e44502b0fb52 | note | Inspection Type (Visual, other) - Check
c6a645e6-b560-558c-a598-8969a49b447c | note | Inspection: Key - R
9296ff61-23d8-54df-a5ad-7827747c4af7 | note | Inspection: By - PS
| checkpoint | 4.4.3 - Seal surface check prior to asphalt
60fc2819-8492-5ea1-896c-715671d47878 | note | Standard/Specification - as per project specification 3.7.7
0f1565e4-ae16-52a4-963d-993066882831 | note | Acceptance Criteria - Visual inspection by engineer's representative
88b646d8-4a94-5440-ac0d-fe9962edac3c | note | Verifying Document - ITP Sign off
41c52791-4f88-555d-8cff-ecb0e247566b | note | Frequency - All
89d074ee-21ce-5e2f-9121-082d95fc28ef | note | Inspection Type (Visual, other) - Visual
29450f86-5962-5a6d-8e60-ac0fc2975473 | note | Inspection: Key - H
41057b54-95a2-53d9-a902-8465174edb2d | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.4 - Heavy Tack & Blind
27c0e5f2-8df3-5ca9-8aa7-0a730571ad78 | note | Standard/Specification - Minimum Residual Bitumen of 1.2 L/m2 As per project based pavement specification
a7411259-f31c-5910-80c9-cef0f4cc2c23 | note | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
a5d68dc2-1f10-5058-8096-9a15c64fd700 | note | Verifying Document - Run sheet, QA from Sub
378407c3-7dd1-5345-a4f3-e6118d5f9525 | note | Frequency - Entire length of pavement
77f1fa6e-16df-5cba-91a6-099f979f08bf | note | Inspection Type (Visual, other) - Visual Inspection
703f92f9-a510-503c-9e3d-1e326df5b911 | note | Inspection: Key - V
707b6084-65b0-509a-a393-b378500e404f | note | Inspection: By - SE
| checkpoint | 4.4.5 - Asphaltic Concrete - Surfacing
5cb75794-47bf-5e2d-9e02-40bce7dbd5df | note | Standard/Specification - NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15
05210fb0-3576-538f-a551-b9aeb268bf90 | note | Acceptance Criteria - 55mm of AC14
10d3ac04-75a5-5149-bff1-67f2e8dfe4bf | note | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
125ec925-05cb-5ae9-817c-a06ab5290f2b | note | ○ The combined thickness of all asphalt layers should not be less than the specified total asphalt depth.
ee33e08b-5626-5c4b-b6d6-48c1f4b882ab | note | Verifying Document - Run sheet, QA from Sub
b61fc35e-4e57-5f87-966c-1579a62ddede | note | Frequency - Entire length of pavement
66b99dc4-a56b-5919-be51-565b391db8b5 | note | Inspection Type (Visual, other) - Dimensional Inspection
0b9aecbb-8cde-5828-a41b-7112b9c00caf | note | Inspection: Key - D
805208dc-9ee0-55fd-919e-c9939b8e8894 | note | Inspection: By - SE
| checkpoint | 4.4.6 - Thickness
ddd725b5-c542-551c-b774-43144033ac67 | note | Standard/Specification - Contract Specification, Section 3.7.15
ee475d01-30bb-5663-bcf0-4e9b1a6967a3 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
788643ea-c697-59c4-8909-97b92847513f | note | Verifying Document - ITP Sign off
31e85044-96bc-5aa4-82b0-8de0e26017b7 | note | Frequency - Continuos
1fb35878-f5d9-547d-8b27-d6e82e5eecc6 | note | Inspection Type (Visual, other) - Visual
a15a7046-04bf-58e3-b3e9-827f96613996 | note | Inspection: Key - C
b29b0107-bd13-528c-96f1-dde98392d3e1 | note | Inspection: By - SE
| checkpoint | 4.4.7 - Finished surface at joints
d453e75a-95bf-5e45-a238-d1a4771a4eb3 | note | Standard/Specification - Contract Specification, Section 3.7.16
f511aa99-7200-5f61-8864-73b040cab660 | note | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
2db45deb-0a22-5aa0-b62f-ecd68e08c623 | note | Verifying Document - ITP Sign off
66b6a6c6-760a-59ca-a596-27d5c1282422 | note | Frequency - Continuos
43ac59c2-5de5-5a63-8bc7-01b2ca70047b | note | Inspection Type (Visual, other) - Visual
68cbc332-50d0-5e33-9688-00b669123ac3 | note | Inspection: Key - C
e1304afc-2977-5925-8315-8532c633a44d | note | Inspection: By - SE
| checkpoint | 4.4.8 - Air Voids
1d0e2e9c-daaf-56be-aa09-6ad251ad41bf | note | Standard/Specification - NZTA M/10
e98c2842-35bf-58f5-bc90-3827b5267557 | note | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
0834a204-91a9-5ead-8d40-99ac274444c0 | note | Verifying Document - Test results, delivered weekly
0743d953-a02a-54bb-b6e9-fb5da08cb56b | note | Frequency - Continuos
260ea949-84a1-5736-a051-c86822ef1b0a | note | Inspection Type (Visual, other) - Review
0fd2a7cb-2f23-587a-8112-191f084c7b8d | note | Inspection: Key - C
bda919a9-5d68-574b-bc30-0952353bbc82 | note | Inspection: By - SE
| checkpoint | 4.4.9 - Level checks
5115460c-52fb-51b0-a1a7-f6fd3f4b0c0c | note | Standard/Specification - Survey
d1b64206-e67f-579a-a405-efcdd1c8c8fe | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20)
59e160e8-ddb8-5822-af7a-21c2dbdb7de6 | note | ○ Thickness of 40mm with +/-5mm (SMA10)
3b63ed51-b1ad-5803-b03e-545a48411907 | note | Verifying Document - As-built drawing
1f49f846-5296-598b-87fc-bc2ae70fe4f1 | note | Frequency - 1/20m full width
02bc9bf4-0327-56dd-bb82-8ce66c3a41fb | note | Inspection Type (Visual, other) - As-built
255a7dbe-c330-5647-8cb6-181702556665 | note | Inspection: Key - D
5802c83c-35d9-5b7e-9753-9a492de02e24 | note | Inspection: By - SV
| checkpoint | 4.4.10 - Line marking
dff29e4d-e2be-57ef-b547-e77e1a494837 | note | Standard/Specification - Set out
62e647d5-d497-5a32-bf09-672faeb1f142 | note | Acceptance Criteria - As per NZTA standard/ design drawings
b318c8b4-1861-57ef-a8c9-ca8ca02a27a1 | note | Verifying Document - ITP sign off/ Photos
f601fac7-0315-5e57-97ca-7fa6be42d8a7 | note | Frequency - All
f915a790-17e5-5666-b31d-3a7a9559ed85 | note | Inspection Type (Visual, other) - Visual Inspection
f834ad60-a09a-5870-8c5d-304ca401ad27 | note | Inspection: Key - V
2eee8f9d-8fdc-5207-ae35-75d0c7e6af6f | note | Inspection: By - SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
224eba33-b1f3-5285-b628-1d137463422a | note | Inspection Point: Quality Control Activity - Upon completion of works
9ca1824c-2aca-558e-9a32-01afe6c80d1d | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
d65b9a14-165f-5cf1-a859-f080c2df6bbc | note | Verifying Document - Closed-out NCR/Defects
fd687f3f-ece4-59df-8487-21dc4a271855 | note | Frequency - Post construction
de8e509a-a214-5d4d-8d69-3139605f6734 | note | Inspection Type - Review
11edbc9b-5de1-5dd4-81e6-7a010c4eb159 | note | Inspection: Key - R
e17e76b4-ac41-5a28-ba14-352f2fd70ba4 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
8c97c4d4-a052-5433-a72e-e6bd88283243 | note | Inspection Point: Quality Control Activity - Upon completion of works
15be9ba7-4cc8-5c96-960d-a02c6ae69863 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
83b43b10-2063-5c01-a802-c5eda9565a44 | note | Verifying Document - As built survey record completed
af4b6f82-ba4b-50d6-a6dc-bd16367b4b69 | note | Frequency - Post construction
298793b0-2564-579e-b771-dea14e06f749 | note | Inspection Type - Review
bbcd52f1-b5e7-5b96-a7ac-0a32aa389e58 | note | Inspection: Key - R
9b438564-b468-5fc2-b057-7b02dc31ce61 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
5ff6838a-4bba-514d-bfe5-d03a3908c90e | note | Inspection Point: Quality Control Activity - Upon completion of works
1758cdce-a015-58ae-ac1a-cac1696b42c5 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
b4d92f1d-36cb-59a4-a46d-8f5d99a450cc | note | Verifying Document - Signed As-built Drawings
53cf08c3-d86f-5437-b305-ba2c1e3b0d04 | note | Frequency - Post construction
ae43a2b5-4816-5b6d-8646-6cdde6ec9867 | note | Inspection Type - Review
7f97fd26-f6f7-5516-bbe7-284c2bb94604 | note | Inspection: Key - R
41e9a5a2-55ff-5d9f-bf3b-55da1b0d0968 | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
7e80c029-ad45-51ba-a590-1686ada750fb | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
d94b5425-1d07-537d-8e4c-b874deeb553e | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
26d488e2-0b4f-5429-a3a3-fc78d619c13e | note | Verifying Document - Register
9c441c04-b3c2-558a-a2a7-c39eff27ba4f | note | Frequency - Post construction
023c92ad-32ee-5623-942c-3e484ad6f8d8 | note | Inspection Type - Review
110dc694-7086-526a-8208-3697b1ee3784 | note | Inspection: Key - R
4c1974b8-429e-5437-9fc9-79e615fe6f3c | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
89ee3c80-65b5-5152-bd31-a809a665eb38 | note | Inspection Point: Quality Control Activity - Upon completion of works
bf1fa2b2-88a8-5555-94f5-ee905f814d5c | note | Acceptance Criteria - All signed and closed out
a8c58e2e-9149-56cb-9795-bb16edefd768 | note | Verifying Document - Signed off Documents
6c31713d-5163-511f-95fd-bf1e77066d63 | note | Frequency - Post construction
50027f20-f28c-5ad4-8da5-7cf4b3739301 | note | Inspection Type - Review
40047498-83cd-537d-800e-29b0c2ff1296 | note | Inspection: Key - R
b062bedd-1c09-5c92-9d04-0fb074b1ea14 | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0028_v2 (3 Waters - CVSC) | itp | 558020-DOW-ITP-PC-0028_v2 (3 Waters - CVSC) | b07cfa4a-636f-465c-b87a-01b9a11d8535
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
1a07132d-9ece-5cd0-821a-b8273287e595 | note | Standard/Specification - Downer Standard
db4a6912-a94f-537b-8d30-e91d08323267 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
d65bb30e-262e-54e4-9d15-5a0a48f20f55 | note | Verifying Document - Survey Records
2e329a22-359c-5b04-b475-55b25f840d38 | note | Frequency - Prior to Works
513e3657-94d4-575f-94cf-17c045317704 | note | Inspection Type (Visual, other) - Document review
70af3567-076e-5fef-a13a-f7912bc730cc | note | Inspection: Key - H
a203a0fd-9562-5bbf-b236-65fbf5cad9eb | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
97d35606-d466-56ab-97f8-3d28fc3fc922 | note | Standard/Specification - Downer Standard
83a63c45-27de-52ef-aec0-51c1ba1aa38a | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
fbfdb6ba-b29a-516a-8f50-25c492e77330 | note | Verifying Document - Service location documents
b7988e7c-92c1-55db-bcfd-eda7c6711519 | note | Frequency - Prior to Works
3829faf2-5b63-5cb6-90fd-32d1b1b77e0f | note | Inspection Type (Visual, other) - Document review
34ba60b7-2301-53f8-9d4d-236dd54f72b1 | note | Inspection: Key - R
52e9db0a-dc37-5f50-a574-7620c567f682 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
89269fdb-e3dc-5a4d-bb08-913881792a80 | note | Standard/Specification - Downer Standard
5c8c364b-231f-50d1-9a64-34a1777316bd | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
6792afb1-6a84-52b6-919e-d7449f773d28 | note | Verifying Document - Internal Permits
13ce9c61-1291-50d9-b5b6-75cbf26d3700 | note | Frequency - Prior to Excavation
02d21272-5e7d-5929-93f4-55955c4e05e7 | note | Inspection Type (Visual, other) - Document review
93486795-bf16-5bca-ab19-037ae2f8a04e | note | Inspection: Key - R
5d3d1578-b8cc-5395-8740-3a4d67a5484d | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
30f0c348-d010-5ecb-83f3-a372e32910f6 | note | Standard/Specification - Downer Standard
876c9d8d-0c45-555c-b24b-5428af5785ab | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
4c52e74c-eed0-5f35-bd91-452df1104fea | note | Verifying Document - External Permits
3a69c7a9-6f82-5c4a-a061-e175a020d97b | note | Frequency - Prior to Excavation
7ddad0fb-f01b-5434-8a27-e12b56733125 | note | Inspection Type (Visual, other) - Document review
c24471bc-16b4-5229-afa7-531d2a283811 | note | Inspection: Key - R
9abde7b1-4e74-55fa-9981-d32dc03f94e2 | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
aea1b012-db84-5853-b71e-c4405b873c4c | note | Standard/Specification - As per contracts
d634c558-723c-5a7c-96e2-df873d34294d | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
93999857-c86a-5fc3-8298-1d5c963fec94 | note | Verifying Document - Approved ESCP plan
38acdca2-7f2d-56e0-9413-35ad949e3194 | note | Frequency - Prior to Works
c82f20a9-51d5-594f-b226-09c64f872bfd | note | Inspection Type (Visual, other) - Document review
c58b2774-9f50-5fae-849b-51604b27b0eb | note | Inspection: Key - R
60a92a7e-cb60-5c40-8efc-60d0f5ae39ab | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
247f4a5e-5888-5f66-8b83-cc3ac75d1f0f | note | Standard/Specification - Downer Standard
3ae4e0a2-3a79-58fb-901a-a1b0366a2141 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9bae988f-6224-54d7-97c7-90fa22ed8a2b | note | Verifying Document - IFC Drawings
2349142a-7087-548b-afeb-ebb2f1f16982 | note | Frequency - Prior to works start
c9cf611e-dfb6-53cb-a623-44db130d130d | note | Inspection Type (Visual, other) - Document review
500b0e38-fdca-58f3-acee-fddb33ca713c | note | Inspection: Key - R
7f94b0fd-e296-5b35-9a41-bb01f71cd364 | note | Inspection: By - SE
| section | 3.2 Stormwater and Wastewater - Materials
| checkpoint | 3.2.1 - Sand
620020dc-842a-5391-b27c-76e1f3e6a161 | note | Standard/Specification - As per project specification (Stormwater Swales, 3.1.2)
f18a41e0-918f-50c3-a062-5bcf43ec4bb9 | note | Acceptance Criteria - Sieve analysis NZS 4402 Test 4.2.8.2
ce7e530d-4c13-585d-8cb0-7ab0da27380e | note | – – – – – – – – – – – – – –
9eec03e6-f3a8-55d9-8259-eb8f0afc8df5 | note | Grading criteria:
2410a92a-bb4d-5224-976b-101fb5a041c6 | note | – – – – – – – – – – – – – –
9b569c69-73a9-5692-8dd4-ea85e179ef2f | note | Sieve Size ¦¦ % Passing
37c02f31-2277-5d5e-8f65-f15bbbe066bc | note | 9.5mm ¦¦ 100
bf254fc5-20dd-533d-9359-c29a47a3de23 | note | 5.4mm ¦¦ 70 - 100
61b72879-c47b-5149-a205-987e3212f653 | note | 2.36mm ¦¦ 50 - 70
8a551ea4-ea8a-59ec-b013-98ff30e076d1 | note | 0.6mm ¦¦ 15 - 35
ca7e50e6-9326-5218-bd46-f92d7cfddce0 | note | 0.3mm ¦¦ 5 - 15
e3e8833c-0013-5e52-a0e8-d47c4318d78b | note | 0.075mm ¦¦ 2
e24f7281-8251-5cdd-9b43-3001acaf654e | note | – – – – – – – – – – – – – –
e15e81ee-6ee8-50c2-9628-3d5dd029ce0d | note | Verifying Document - Test result
6f5f3bbb-df69-5932-84af-b5ca9d462523 | note | Frequency - 1 per 200m³
f73c2d2c-0710-5e3f-a3db-c3532b88dda2 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
92ebab5e-0e38-5bb3-9875-dc3d30a51343 | note | Inspection: Key - R
a18f986d-cfb4-5c09-aad0-5fbab39d9ed0 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 3.2.2 - Drainage Media
bb73d737-5c2a-54c6-8571-bc70612ba6a6 | note | Standard/Specification - As per project specification (Stormwater Swales, 3.1.3)
de8c3a5c-d0a1-5a5e-93cb-c261ae55d2c5 | note | Acceptance Criteria - Single size angular stone chip no larger than 9.5mm
ee0eb023-490e-56c3-aeeb-dead667af6f3 | note | – – – – – – – – – – – – – –
5d7efd52-8331-5a93-a67b-b7a15ddf6e08 | note | Grading criteria:
26708b09-a40f-5318-909d-0ac206144389 | note | – – – – – – – – – – – – – –
5a33c7f5-4d1c-5c40-a091-279e510976bd | note | Sieve Size ¦¦ % Passing
6c7d1e96-c3aa-567c-ac56-2170e621f205 | note | 9.5mm ¦¦ 80 - 100
5a02786d-ea0b-55f5-8f29-6397e33aa9b2 | note | 2.4mm ¦¦ 0 - 20
d0fd6645-f74e-555a-bdae-6023e141cf22 | note | 0.6mm ¦¦ <2%
266010d2-b10e-5089-a57b-d300b1b7cbcf | note | – – – – – – – – – – – – – –
191509a2-6d39-5f0d-9013-079994db5950 | note | Verifying Document - Test result
985611c3-869b-513c-8da5-5012fc32d77b | note | Frequency - 1 per 200m³
b0eeda95-ee14-52e5-9fe8-2336c7fa4f02 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
10fb9439-6655-5301-a064-160eff58ebd2 | note | Inspection: Key - R
4c09be39-013c-5ce1-a916-ae01aac62d71 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 3.2.3 - Soil Media
b504038f-74f6-5995-aff5-329c0c2992ed | note | Standard/Specification - As per project specification (Stormwater Swales, 3.1.5)
2fc2d265-3c8d-521c-95e3-c5d6c7f01e32 | note | Acceptance Criteria - The media must consist of material that has:
ca27b977-8162-5c8d-b9a5-f9dbda97bb2b | note | ○ 5% clean organic compost from a consistent source. The source of clean organic material must have been provided to the Engineer for acceptance prior to supply.
722a0b46-dc00-5e11-be3d-01be2999aeff | note | ○ Locally sourced topsoil (free of weeds or contamination)
6f07a457-ddc9-5fb5-9733-6a4a7c0cbe3d | note | ○ No obvious seeds, weeds, any contamination and material > 25mm in nominal diameter
e6054bc4-6335-5e05-b223-34c109fe7092 | note | ○ < or = to 50% coarse sand from a consistent source to improve permeability and structure.
69ac8b07-e7ff-5b53-91b2-c2bde8c541d9 | note | ○ < 3% clay (particles < 0.002mm)
4b2e5ae2-5d6c-50cc-a810-d22244d0ed58 | note | ○ < 5% by volume of particles exceeding 4.75mm nominal diameter.
be32f671-2efa-5916-8f5b-8657749d7efb | note | ○ A pH rangeof 7.5 - 5.5
c3a0a753-3076-5fe1-8686-cf40f23969cd | note | ○ Well graded particle size from 0.075mm through to 4.75mm with no gaps in the grading.
b91e7b56-386f-5b15-96dd-f08c5dd62742 | note | ○ Compacted hydraulic conductivity of at least 50mm/hr and nort exceeding 400mm/hr based on the ASTM F1815-069 methodology.
9a8aa306-25bb-59d8-ade1-f706bef71e55 | note | ○ Total Phosphorus < 100mg/kg
3506d8bf-68e6-5512-8b5f-9e99e78dbb01 | note | ○ Total Nitrogen < 1000mg/kg
aa151706-64ed-5f52-9536-784ccd637ca2 | note | Verifying Document - Test result
b9ec8e91-43b2-572a-81ef-b280d024ff0d | note | Frequency - 1 per 200m³
f3c7f69f-a511-5637-84f2-1510cba50b55 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
3fb53d6e-140f-5411-b931-938c699b864a | note | Inspection: Key - R
4cecd5b0-f81b-5a39-ae83-34dd281da4b6 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 3.2.4 - Concrete Pipes
b95579f6-d1d1-5496-95ce-e3a4fd4efee3 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.4.4)
44ffe68a-3d13-5f02-800b-6cc805ab02f9 | note | Acceptance Criteria - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
02cdd201-69c5-5c59-9411-0701a5f4dd69 | note | Verifying Document - Data Sheet
df18a82a-01bb-57ea-95c1-5ef4debb1056 | note | Frequency - Per delivery/Item
c6d21710-2fee-50de-badb-a767f38b657a | note | Inspection Type (Visual, other) - Document review
657b7378-b4fa-5c04-9bf6-dcd6d195d9e6 | note | Inspection: Key - R
76041f60-d7f8-5d92-9c06-93c6f5049e29 | note | Inspection: By - SE/PS
| checkpoint | 3.2.5 - PVC-U Pipes
b7d2e636-6c9f-5546-9c64-c7e67422a26f | note | Standard/Specification - As per project specification (Pipeline Supply, 2.4.2)
9df3b08b-362b-51c7-8032-16c80467b695 | note | Acceptance Criteria - PVC-U pipes and fittings for gravity stormwater must be plain wall construction rubber ring jointed and must comply with AS/NZS 1254.
cc823515-3bf8-5020-a34f-918e23cb25b3 | note | ○ All PVC pipes must have factory fitted, composite rings; loose Z type rings must not be used.
0fd4a5ff-b2fd-5868-87ab-45bd7a8400e6 | note | ○ PVC-U pipe diameters shown on the Drawings are the nominal diameters unless shown otherwise. Pipe classes are to be as shown on the Drawings
01335e04-b902-5cc0-b2f0-a02441798a58 | note | Verifying Document - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
7df65f22-8dda-5524-b1bb-186ba8e916c0 | note | Frequency - Per delivery/Item
725c7edb-0aa4-5fb0-89c0-1782b8569efb | note | Inspection Type (Visual, other) - Document review
63bce602-b8f9-57a3-86fd-b10450f825bc | note | Inspection: Key - R
5de6f13e-027e-5f4d-bf5b-a1d165315e35 | note | Inspection: By - SE/PS
| checkpoint | 3.2.6 - PE & PP Pipes
3e24baeb-dd6d-5848-bd43-ec373e50757c | note | Standard/Specification - As per project specification (Pipeline Supply, 2.4.3)
85b7833c-9eec-59b6-b2fc-de37244bee7f | note | Acceptance Criteria - PE & PP pipe must comply with AS/NZS 5065.
a01ef998-5b8c-57d8-8502-7b2bbd39b3ec | note | Verifying Document - Data Sheet
54550490-41d6-5808-8b20-bd75e06041cb | note | Frequency - Per delivery/Item
caa3bacd-3731-5ac6-95e4-ef08a353ed8f | note | Inspection Type (Visual, other) - Hold Point
3885a3ea-7b2e-5061-9e0f-474aad796387 | note | Inspection: Key - H
f9be3de3-18ab-5876-a68b-e56dc06eab7c | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Precast Concrete Manholes
7482e83e-e3d5-5582-9362-d79b5938f9d4 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.5.1)
23bae768-aa43-5e8c-81bf-952458488794 | note | Acceptance Criteria - Unless shown otherwise on the Drawings, manholes (and manhole components) must be circular precast reinforced concrete manholes manufactured in accordance with AS/NZS 4058 with cast in base manufactured to NZ5 3109.
923a3d2c-04eb-5ff4-a028-33827908c988 | note | Verifying Document - Data Sheet
1acaad40-5a06-5773-b028-0abe02123e9a | note | Frequency - Per delivery/Item
e7194e3a-93bb-520d-995f-79aa85c4a8be | note | Inspection Type (Visual, other) - Document review
efb887e4-6270-59c9-99d8-11b8c9752596 | note | Inspection: Key - R
575a87a4-54f6-5daa-b46d-067bae1ce2bc | note | Inspection: By - SE/PS
| checkpoint | 3.2.8 - Manhole Lids
c7d986c1-c204-5006-a6b9-cb2374dd111e | note | Standard/Specification - As per project specification (Pipeline Supply, 2.5.2)
346642af-af88-589a-ada3-b0ac44ce01bc | note | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
fdefde71-1ec8-5e48-9d43-9380e6b4b0d9 | note | Verifying Document - Data Sheet
aadccf23-897c-5043-9b70-56ce3240cf73 | note | Frequency - Per delivery/Item
fa8fb378-2397-5125-a4be-3400309e0d89 | note | Inspection Type (Visual, other) - Document review
a35c8fa4-6c9c-5d7f-bef5-da8f2c339387 | note | Inspection: Key - R
bae93ea8-39f5-5ff7-b7e3-e205854232d5 | note | Inspection: By - SE/PS
| checkpoint | 3.2.9 - Frame and Covers
1109be8d-0f3e-593a-980b-1b945007c103 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.5.3)
45becf92-c41d-5c38-b590-8fa3173b391e | note | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
98116fed-21ed-5a82-9030-2a43d0f679d2 | note | Verifying Document - Data Sheet
1072ae6b-4707-52a3-a218-34e4929a1376 | note | Frequency - Per delivery/Item
6e8dafc3-59d6-55d1-95be-8e02f33200b6 | note | Inspection Type (Visual, other) - Document review
ac34f3d6-1529-5ee8-abed-7cbd3442e2ad | note | Inspection: Key - R
08d5f01a-f50c-5ff5-bdc4-8a694307cf7f | note | Inspection: By - SE/PS
| checkpoint | 3.2.10 - Catchpits and Grates
73e7c0b3-46c1-5f50-ab52-7c692f1e0cb6 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.6)
49af1c1c-b720-5cbd-8623-eb5b43336574 | note | Acceptance Criteria - Use precast single or double catchpits manufactured from reinforced concrete complying with NZS 3101 and NZ 3109. Each single catchpit must have minimum internal dimensions of 450 mm by 675 mm.
1818b4eb-13e0-5510-9315-b60a1f037892 | note | ○ Use grates rated to class D complying with As 3996 with
0cc044f2-ace1-5f09-86ff-fd3bb6f20d50 | note | Verifying Document - Data Sheet
51e22b4c-27c8-593f-a4b4-ad9be44aa3e6 | note | Frequency - Per delivery/Item
f2e3f709-77d3-5609-a887-eea082ed736a | note | Inspection Type (Visual, other) - Document review
2b6fb6e5-7535-5d90-a574-d6c4a8af74b0 | note | Inspection: Key - R
f726ca1c-0fe6-57aa-824d-69e70efb502d | note | Inspection: By - SE/PS
| checkpoint | 3.2.11 - Subsoil
986bfbe6-08a2-55e8-a75d-fb1a278611e3 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.7)
2ad183f4-b659-5c31-bfb1-8ca7f78147db | note | Acceptance Criteria - Unless shown otherwise on the Drawings, subsoil drains must be DN110 perforated corrugated plastic pipe complying with AS 2439.1-2007 Perforated plastics and drainage and effluent pipe and fittings, Part 1: Perforated drainage pipe and associated fittings, and be minimum SN 4
eb52050a-93cb-531b-b4f9-6402b5a4d9fe | note | Verifying Document - Data Sheet
7430ef7b-5f90-5f9d-b260-08ffd00897b7 | note | Frequency - Per delivery/Item
65ec4df1-791e-59da-8f74-5a4e57eaad41 | note | Inspection Type (Visual, other) - Document review
2d1113e9-d793-53cb-8c6d-fb4f40c1ad1e | note | Inspection: Key - R
fcc7c7e7-7231-5032-b4a9-46711b7b40b5 | note | Inspection: By - SE/PS
| checkpoint | 3.2.12 - Materials - general
df06711c-93ac-59b1-a8b2-a3f182bf198c | note | Standard/Specification - As per project specification T-WES 00012, Section 4.8
917674f4-e337-5857-9aca-9274665b9c4b | note | Acceptance Criteria - Do not change the source of supply of materials without written approval from the Engineer - refer Section 2.1
28240d72-9420-52f6-9d34-fd18aa531752 | note | Verifying Document - Approved list Verification / Datasheet
ca0b381f-e6b1-501e-a91e-e2892cae7939 | note | Frequency - Prior to use
8984fa9d-8eb8-5f06-8b6a-5bb9d42fe8b5 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
dbf72f73-1f56-5b5f-b566-dceb6dd27c25 | note | Inspection: Key - R
1e171845-16ff-5df4-8a66-c0c173f96089 | note | Inspection: By - SE/CR
| section | 3.3 Receiving Materials/Parts - Portable water
| checkpoint | 3.3.1 - Water Pipes
10f3a078-7782-5a34-b3fa-9d0646cdf3a4 | note | Standard/Specification - As per project specification refer T-WES 00013, 2.4
4fb0c022-d1e3-5bf9-9d37-586a00a4e4f8 | note | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
156e8c9f-a1e3-524f-abe0-9984b86f6a10 | note | Verifying Document - Approved list Verification / Datasheet
83c0654c-dc7e-5e51-b730-80d19c3e6ca7 | note | Frequency - Prior to use
02707c33-7d4c-5d71-ae47-3285adca787c | note | Inspection Type (Visual, other) - Document Review
b421b8e7-743c-5d21-97b0-c9c7bab1ec8b | note | Inspection: Key - R
cbe3f4a9-dcbb-56ee-93c5-a5ce56745470 | note | Inspection: By - SE/PS
| checkpoint | 3.3.2 - Water Fittings
ce65d7d7-7f28-52b4-91ff-90f6b69e98b4 | note | Standard/Specification - As per project specification refer T-WES 00014, 2.5
1a02b335-4ba1-59ea-a473-9c373d38bbf3 | note | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
14406c10-c582-5c1e-ac1e-7c856a9b0535 | note | Verifying Document - Approved list Verification / Datasheet
97bf562e-6cbf-5ac0-9114-f399d763b8a3 | note | Frequency - Prior to use
0e6e1e68-58c7-5ca4-ac4b-3b60a63f8ed8 | note | Inspection Type (Visual, other) - Document Review
f4c99b2b-7976-5383-ad2b-822bd3fa8318 | note | Inspection: Key - R
9874e5d8-ea1f-575a-b355-d9fbf411a268 | note | Inspection: By - SE/PS
| checkpoint | 3.3.3 - Joints
ad715436-75a5-541e-862f-3787581fc9df | note | Standard/Specification - As per project specification refer T-WES 00014, 2.6
c2d7a380-be35-5fb9-b733-c747cc35c166 | note | Acceptance Criteria - All Joints shall be of the material, grade and size shown on the Drawings/specifications and be on the approved material list
7af72bd8-6b29-5a0c-9b7c-a995d75e84b2 | note | Verifying Document - Datasheet
9068f991-d606-5183-9cb3-096238f2775f | note | Frequency - Prior to use
64c28d40-b319-5e02-b300-832cd28f6afa | note | Inspection Type (Visual, other) - Document Review
6302145d-268c-561c-a46f-85902f3b2459 | note | Inspection: Key - R
b8f7c672-1d1f-54b3-b91e-010c2395566f | note | Inspection: By - SE/PS
| checkpoint | 3.3.4 - Fire hydrant and Valve Covers
f59ee276-a307-5e19-a535-9d6d18672773 | note | Standard/Specification - As per project specification refer T-WES 00014, 2.7
724b3e5f-26ed-5b4b-8985-f5c83aad831e | note | Acceptance Criteria - All surface boxes and covers over buried valves and hydrants must be rated to AS 3996 Class B (footpaths and non-trafficable areas) or Class D (trafficable areas).
33e40043-81c3-5ac7-b59d-95fff30055f3 | note | ○ Use PVC risers and/or or concrete frames as necessary to provide access to the valves or hydrants.
a5aa130c-5dc8-5648-a12e-e7bc133a696a | note | Verifying Document - Datasheet
28419a3f-d461-5ec3-be02-ee4b33ca792b | note | Frequency - Prior to use
8472bc39-ba34-5423-aefa-a768ddb6919e | note | Inspection Type (Visual, other) - Document Review
92485112-41c1-5d2f-90d1-18046520772d | note | Inspection: Key - R
cbd26f86-b3b6-5da4-b75d-3e3f91343540 | note | Inspection: By - SE/PS
| section | 3.4 General
| checkpoint | 3.2.13 - Embedment Materials (1)
fcb3bac3-5394-5def-a746-a0a4dc2ace2a | note | Standard/Specification - As per project specification (Pipeline Supply, 2.8)
c4620db5-cd2a-5495-be83-9e3d5996015f | note | Acceptance Criteria - For flexible pipes, well graded processed AP20 complying with AS/NZS 2566.2 section 54.2. Any proposed alternative bedding material must meet the requirements of AS/NZS 2566.2 section 5.4.2.1 note 3 and may only be used if approved by the Engineer in writing.
02e8c805-be3f-5c14-9c71-043b56cf87fc | note | ○ Where low-fines embedment material is specified on the Drawings, the material must be a graded AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation. Screened in-situ materials may be used for embedment
b29120b5-1c0c-59f9-9ca2-628740f702c4 | note | ○ Pea metal may not be used
95774f54-0dfc-5e06-b5ac-d590d92cb57f | note | Verifying Document - Test result
f05fabb8-8b66-5a3b-b0bf-87aefd54c1cb | note | Frequency - 1 per 200m³
0190007f-f636-5249-beb4-539f927c38bc | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
a43baacd-d8ef-58d2-83a0-0f3cb18d6933 | note | Inspection: Key - R
8f7b5298-3d80-55fd-b757-d56bf6573353 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 3.2.13 - Embedment Materials (2)
045ccfbc-6fb6-5858-a263-46fd3bd6bf70 | note | Standard/Specification - As per project specification (Pipeline Supply, 2.8)
3dbe8f47-bb09-58fc-82b6-332006c48e71 | note | Acceptance Criteria - For concrete pipes, Material with grading limits in accordance with As/NZS 3725 and the CPAA Engineering Guideline Selecting Materials for Bedding Steel Reinforced Concrete Pipe available from the CPAA website.
576ed822-1d55-5447-ae54-5b6eec9f5c48 | note | ○ Where low-fines embedment material is specified on the Drawings, the material must be a gradec AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation It is expected that screened in-situ materials will be used for embedment. The material used is to have a Compaction Fraction (CF) of 0.1 or less as defined below
d127f439-659b-50ea-9998-52b8623a60bc | note | Verifying Document - Test result
bcbb677c-ba41-5dd8-b170-d99ad9ecd976 | note | Frequency - 2 per 200m³
a7dd9f8c-cb54-5dad-b2cc-33d2c043909f | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
623471f9-3df2-5831-84dc-fae2891923ff | note | Inspection: Key - R
176365a7-a647-5afc-8ba3-0e16d123e639 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 3.2.14 - Trench Fill Material
9d35a345-1d32-5142-b12d-c93164e0134f | note | Standard/Specification - As per project specification
9456d3c5-64f1-598a-b1df-23235931af5c | note | Acceptance Criteria - Before construction commences establish the maximum dry density using NZS 4402 Test 4.1.3 New Zealand vibrating hammer compaction test. Submit results to the Engineer one week before importing trench fill material.
7637506d-97cf-506a-a7b4-9ffd707cc41b | note | Verifying Document - Test result
94a7362e-5b76-52af-9b5f-2dcd0e528c27 | note | Frequency - Prior to imoport material
deb84044-6864-5be0-bf4b-270651da1a0e | note | Inspection Type (Visual, other) - Document Review
241e244b-20b8-5dc9-bbed-12a34fd38c4a | note | Inspection: Key - H
40b6f4d8-00e1-5301-891f-0ecce4353160 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.15 - Concrete
e8f571d6-87a4-5365-b160-36ba317d1912 | note | Standard/Specification - As per project specification (Minor Concrete Works, 2.1)
5299dc4d-8269-51af-a48a-771c15cc58aa | note | Acceptance Criteria - Normal concrete witht the requirements of NZS 3104 and strength shown on the drawings. Where the strength us not shown, use 25 Mpa normal concrete
77870918-606c-53eb-965c-c474b69f1586 | note | Verifying Document - Mix Design
2725eca6-40af-539c-8266-5b9382998940 | note | Frequency - Per mix
71fb4696-ca38-5c24-aa5c-b7a52916e407 | note | Inspection Type (Visual, other) - Document Review
4b91d06c-0ff2-5be1-a7f1-a69c19983b7c | note | Inspection: Key - R
a17f8875-c01f-56f3-accd-fd0ef191837b | note | Inspection: By - SE/PS
| checkpoint | 3.2.4 - Geotextile
8e826c02-acb6-5b87-8117-4b828a7f799f | note | Standard/Specification - As per project specification (Earthworks, 2.15)
4b82af43-8400-5dd5-84f0-455826a03f31 | note | Acceptance Criteria - Geotextile to be the grade and standards on the drawings and be on the Approved materials list.
b430d93f-547e-5063-95fc-0fdc0183beb5 | note | ○ Non-Woven Filtration Class 1 and Geotextile Strength Class C
fb724450-46bb-5050-9b96-306291b7fb3d | note | Verifying Document - Data Sheet
a114c081-99a0-543b-ba05-a776d83eb328 | note | Frequency - Per delivery/Item
f4ea8673-4cb5-5ee9-a936-e3d1de83c445 | note | Inspection Type (Visual, other) - Document review
f81885b6-e6e3-560d-ade6-4cb6803bfb74 | note | Inspection: Key - R
0de1120b-2c40-513d-87fb-223468d11c69 | note | Inspection: By - SE/PS
| section | 4.1 Soakage swale - Construction
| checkpoint | 4.1.1 - Swale - Formation and Levels
bdf29734-cc01-538d-a04f-d81fb1f89473 | note | Standard/Specification - As per design height
e9d663cc-4328-5fa8-ac30-5109b521bc37 | note | Acceptance Criteria - Ensure the excavation is clear of roots, projections, or obstructions. If overexcavation occurs, bring the bottom back to grade using excavated material, lightly compacting it. Do not leave loose soil. Notify the Engineer if the swale contains low-permeability soils; they will assess and advise on additional excavation if needed.
79d11e27-1415-55ca-bbbf-f035a01c6486 | note | Verifying Document - As-built check, photos
4720bac4-ab76-5508-a34a-7bff954d3a32 | note | Frequency - Before instal the drainage media
d7c91cc4-f690-5024-9566-639153db8ee3 | note | Inspection Type (Visual, other) - Survey, Visual
63f80e05-dae3-50ba-804d-61b2d0a0fff9 | note | Inspection: Key - V
5b41c233-b3cd-5f12-a491-9339706739a4 | note | Inspection: By - SV, SE
| checkpoint | 4.1.2 - Drainage Media
94706876-58ee-5ed6-816e-b7605863c25c | note | Standard/Specification - As per three water specification Section 3.3.2
6ff30aa1-b76a-54f5-ac58-6039262837c6 | note | Acceptance Criteria - Carefully position drainage media in a clean, excavated area free of contaminants after removing materials. Use the media as embedment around the subsoil pipe, ensuring it is lightly tamped in the bedding zone without mechanical compaction. Avoid placing or lightly compacting drainage media in flooded excavations or saturated in-situ soils.
2cb3fbdf-9906-560b-8040-35696b1387a7 | note | Verifying Document - Photo
046224b5-f4f6-5e63-aaa1-51ca3dc65b75 | note | Frequency - As progress
25a17837-71af-5fb7-829c-10635f9e0f8f | note | Inspection Type (Visual, other) - Visual
e694f0a4-e87f-56a9-bbdc-1bc145d7f9d6 | note | Inspection: Key - V
67255faf-0948-5786-be90-15d5a5182323 | note | Inspection: By - SE/PS
| checkpoint | 4.1.3 - Subsoil Installation
5cebe97b-8884-5e18-8808-6b3174c7bf95 | note | Standard/Specification - As per three water specification Section 3.3.3
4a4eea14-c350-57a1-9888-eb6f72f44934 | note | Acceptance Criteria - Position subsoil pipes centrally in the drainage media layer per specifications and drawings. Avoid laying pipes in flooded or saturated soils; no filter sleeves for perforated pipes. Install pipes parallel to bedding, avoiding ponded water in the swale. Carefully place a minimum of 50 mm of drainage media around the pipe, using it as embedment material without mechanical compaction.
dbc39d50-edbd-525c-bb0f-8487340d907f | note | Verifying Document - Checksheet,Asbuilt and Photo
f4f6f095-cf77-5981-b761-3c6be9e065f5 | note | Frequency - As progress
4e07f03c-8851-5f30-9bff-3f3fe0100158 | note | Inspection Type (Visual, other) - Witness,Visual
147970ab-62c2-57ec-91e4-ffcdcf046d56 | note | Inspection: Key - V
e7ed30c8-0b0c-5845-b6ad-bf83202becd6 | note | Inspection: By - SE/PS
| checkpoint | 4.1.4 - Sand Layer
850bf3a4-5d19-59ef-a49d-e74559c1e11f | note | Standard/Specification - As per three water specification Section 3.3.4
f1b0368a-03ff-5223-931b-e261721c4f50 | note | Acceptance Criteria - Place a 400 mm thick layer of uncompacted sand over the Drainage Media, avoiding compaction with construction equipment. Ensure the subsoil drain is undisturbed, and rake the sand for a level finish.
d12d0203-24ff-540a-9831-594a6af6440e | note | Verifying Document - Photo
bada3f7d-1548-5674-af04-6b0d379b1274 | note | Frequency - As progress
47d04126-7197-5b18-86ba-92f79374785d | note | Inspection Type (Visual, other) - Visual, Dimensional
1a1476c6-67b3-5e6e-bd9b-177a53b9b45f | note | Inspection: Key - V,D
46304cb3-7029-5ae7-a807-ddeced6acc88 | note | Inspection: By - SE/PS
| checkpoint | 4.1.5 - Soil Media
e52a1795-5a2e-5b32-8fa3-b62af9e2f2be | note | Standard/Specification - As per three water specification Section 3.3.5
a893d48d-01a1-5545-b28e-835857b7eced | note | Acceptance Criteria - Place soil media in a single lift up to 50 mm above the Construction Drawings' finished level for post-construction consolidation. Ensure a smooth, uniform surface, lightly consolidate the soil, and avoid disturbing the subsoil drain. Rectify sediment blinding as directed by the Engineer. Do not exceed 30% moisture content to prevent poor performance. Notify the Engineer for approval; upon acceptance, commence grass sowing within seven days.
36368dcd-efce-5eeb-a8bf-2c287679d0df | note | Verifying Document - Photo
7876eb7f-b37c-563d-92f2-b612962210a9 | note | Frequency - As progress
ece2e838-f292-5d43-b5d7-5c119296c2d1 | note | Inspection Type (Visual, other) - Visual, Dimensional
799aba0c-ab1d-5938-a6e5-c222542d75f7 | note | Inspection: Key - V,D
067ca8df-5c69-5bdc-971b-9fd060dce944 | note | Inspection: By - SE/PS
| checkpoint | 4.1.6 - Grass Sowing
d246421d-baeb-5846-ab99-b942ec870a87 | note | Standard/Specification - As per grass sowing mix
2083df4a-841f-5929-9d31-bc2572e67c0b | note | ○ Pernnial ryegrass 70%
e8246c2f-5458-507e-9202-e70c101af875 | note | ○ Chewing fescue 25%
076cf0e2-f94b-5228-a0e5-0675a33c0340 | note | ○ Brown top 5%
7d0f4f23-b79b-56b9-a4a6-3d7960aad1e5 | note | Acceptance Criteria - Sow an approved bird-repellent coated grass seed mix at 1 kg/30 m² and fertilize with diammonium phosphate at a minimum rate of 1 kg per 50 m². Aim for a 90% grass strike by the end of the Defects Notification Period, promptly fixing any surface depressions.
34cdc9d2-9258-5a06-8695-f48c2875bc41 | note | Verifying Document - Photo, Docket, Mix design
d2837b59-0363-549c-bbca-2edcbd61051f | note | Frequency - Per application
e5972e29-3415-5f89-856b-6fe06de0923e | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
c8c8d3ea-26fb-5121-bd43-90cfb41ef7dc | note | Inspection: Key - R,V
3ad3c4b1-9d6c-5982-9b43-78a7ca242b62 | note | Inspection: By - SE/PS
| checkpoint | 4.1.7 - In-situ Infiltration Test
87196d0c-d180-5a58-bb5b-e1a89b57c265 | note | Standard/Specification - Double ring infiltrometer Test Method
126274b4-38af-5160-9641-859e39d4dc0c | note | Acceptance Criteria - Test reslt > 50 mm/hr as per project spec Test to complete as per project's three water specification Section 3.5.1
b1ae5291-ef8b-5483-8b53-ce703ff95bee | note | Verifying Document - Test result, Witness Engineer
145393ae-7750-596b-8af3-2ee7b3bfb894 | note | Frequency - Two test per stormwater swale
61cbc882-f899-5a49-a058-e7bdb94b32f7 | note | Inspection Type (Visual, other) - Visual Inspection
e508c897-d3d8-5cec-a149-44a92eda4ae2 | note | Inspection: Key - W
04ff19d6-e264-54b9-adc0-466bf127a081 | note | Inspection: By - CR, SE/PS
| section | 4.2 Subsoil Drain - Installation
| checkpoint | 4.2.1 - Subsoil Drain Installation
9f712656-b309-5b32-bf48-92f4aa532227 | note | Specification - Downer Standard
e6fa27e6-09f2-5a5d-b04d-9fd9090da04c | note | Acceptance Criteria - Subsoil drains shall be constructed to the lines, levels and dimensions shown on the construction drawings and fully comply with the dimesnional and drawing specifications
a71d83a9-5836-57ad-9e56-c5ac8e50a9ce | note | Verifying Document - Checksheet, Asbuilt and Photo
63b1b381-6fff-58fc-a77b-73d2839450f1 | note | Frequency - Each subsoil drain
733c1db6-5f2a-5d46-ac80-c98d0bf667c5 | note | Inspection Type (Visual, other) - Witness, Visual
d793e691-f900-559c-ba56-ce41134c3312 | note | Inspection: Key - V
ef6308ad-7e3b-5137-9d90-7cf1bdcdf5d7 | note | Inspection: By (Role Key) - SE/PS
| section | 4.3 Drainge Pipe - Installation
| checkpoint | 4.3.1 - Length of Open Trench
8d557c63-d77f-5b3b-a7c9-3d6895f3e44b | note | Standard/Specification - Downer Standard
5a6bea0a-6adc-5018-905b-d8dc95b6a122 | note | Acceptance Criteria - The length of open trench shall not exceed the greater of one manhole length or 50m and when offsite this open trench shall be reduced to a maximum length of not more than 10 metres.
eae934ed-5b3c-5d60-929e-656fdfa90a13 | note | Verifying Document - Checksheet, Photo
e2197269-504a-572e-af5c-6b90ac7245e1 | note | Frequency - As progress
c1a6837b-89f8-50ba-9a38-989f4c6ce82f | note | Inspection Type (Visual, other) - Visual, Dimensional
d6f4cf12-58e8-5df2-b668-ff61902bba0f | note | Inspection: Key - V,D
a911eb61-ea2e-5492-a34e-d4cc4f02aa36 | note | Inspection: By - SE/PS
| checkpoint | 4.3.2 - Trench Width
b9f974d4-8939-5ad7-8f81-aeba00c25eac | note | Standard/Specification - Downer Standard
61c43796-3898-5042-8e84-aa2ff49060ae | note | Acceptance Criteria - The minimum trench width shall be 300mm wider than the external diameter of the collar of the pipe being laid, providing the haunching metal is compacted under and at the sides of the pipe.
ee662000-633d-505c-aae3-12be1c1adde1 | note | Verifying Document - Checksheet, Photo
b47f5f7f-7b19-5465-8482-ef5bbbda8edd | note | Frequency - As progress
069f8fa0-b49e-5898-84d1-58762c2d7a84 | note | Inspection Type (Visual, other) - Visual, Dimensional
7f37b989-c6c5-5a4c-bc21-32e28eb5314a | note | Inspection: Key - V,D
c5cfab5d-7d18-5fe2-a47c-c96d6512259b | note | Inspection: By - SE/PS
| checkpoint | 4.3.3 - Trench Subgrade
6b5dc6f0-436f-5ae7-9ed3-b5c70c538924 | note | Standard/Specification - Downer Standard
758fe442-22e8-5ddf-8919-6e8ac5bd1579 | note | Acceptance Criteria - Complete Scala testing on the trench Subgrade to a depth of 1m every 10m and when the subgrade changes appearance.
b1c61549-5f13-5e67-8c48-94571ebc194d | note | Verifying Document - Scala Results
aa4ea482-a9f4-5c62-9165-1192faefd256 | note | Frequency - Every 20 m
e3f3f9de-6f67-5a3b-9988-7d16eba9e752 | note | Inspection Type (Visual, other) - Inspection
90652750-9ae2-5a58-b58c-7cea1d2cdb33 | note | Inspection: Key - V,D
8d39d36f-fa05-55bc-b3c0-674181300cb1 | note | Inspection: By - SE/PS
| checkpoint | 4.3.4 - Line and Level
44611741-ceec-5d58-92a2-a8e0e8a6bd57 | note | Standard/Specification - Project Specification
758f9a58-b2fb-5141-925e-a943f89e41c7 | note | Acceptance Criteria - Pipe inverts shall be laid to ±10mm of the design vertical alignment. Pipes shall be individually aligned to grade. Gravity pipes shall not be laid at a negative grade. Pipe alignments shall be positioned horizontally within the greater of 50mm or 5% of the pipe diameter from the location specified.
3a944d3f-339b-509b-89c0-1d6f7d2d6e5a | note | Verifying Document - Checksheet
2b333994-4fe3-51e1-8ead-c7c4b1d85c33 | note | Frequency - Before backfill
786797de-6876-5247-8439-7f0dfc5ec7bc | note | Inspection Type (Visual, other) - Visual,Dimensional
044ad428-7867-5f94-8a2e-985091e03d63 | note | Inspection: Key - V,D
9549466f-c2b3-5f3a-9a99-9f7101fe304f | note | Inspection: By - SE/PS
| checkpoint | 4.3.5 - Backfill Placement
1963ee2a-0886-5fba-b1b3-5320b5212717 | note | Standard/Specification - Project Specification
00cdbc85-c329-5be6-ad01-9d405625f782 | note | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
6ad69aa4-6e68-587a-a539-8c446fe47ddc | note | Verifying Document - NDM Report
8a68fa52-a71a-551b-beaf-486998065956 | note | Frequency - One test every two layers per 50 m
450ea701-7814-5418-bece-96f89004ecb2 | note | Inspection Type (Visual, other) - Check
f910587c-3e85-5016-86cd-b205a766085e | note | Inspection: Key - C
bde7123a-11d9-53b3-8668-e45b5d33d936 | note | Inspection: By - SE/PS
| section | 4.4 Manhole - Installation
| checkpoint | 4.4.1 - Alignment
2d351b42-d216-5ac2-87d4-9a9ad22f87ce | note | Standard/Specification - Downer Standard
e80e8b3c-57f4-5cca-93d5-88fae98bf9b6 | note | Acceptance Criteria - Structures shall be positioned within 50mm horizontally of the location specified. All structures shall be watertight.
c011d604-29a2-542c-a9cb-0ef2f040ccab | note | Verifying Document - Checksheet, Survey
bc222069-6279-5757-a2df-6fb22c41ccf1 | note | Frequency - Each Manhole
4790e799-43b4-537e-8192-72036676080a | note | Inspection Type (Visual, other) - Check
858837eb-1bda-5c97-80f9-6ac3bef11840 | note | Inspection: Key - C
cdc7ae27-50ca-5bb5-bd00-515ec42fd1e0 | note | Inspection: By - SE/PS
| checkpoint | 4.4.2 - Drainage Structure Foundation
1b0be4b3-8083-5d82-8d8f-f5586a16890e | note | Standard/Specification - Downer Standard
2d059e4a-b5d3-5973-a2ef-cbb121194a81 | note | Acceptance Criteria - Complete Scala test on the subgrade underneath each structure to a depth of 1m
387567d3-c18a-5eb5-9d89-9daa968364f2 | note | Verifying Document - Checksheet,Scala
9d3496b6-7176-50e3-ad00-f48913bea5ac | note | Frequency - Each Structure
0f06d24d-9940-5e8c-add3-479a1474ebfd | note | Inspection Type (Visual, other) - Check
011df718-ca62-59a9-8d01-757af6ce52e4 | note | Inspection: Key - C
6c2c392e-086f-554d-b715-4ad4ddff5426 | note | Inspection: By - SE/PS
| checkpoint | 4.4.3 - Drainage Structure Bedding
b12d2162-6030-547e-a253-2e299e69cd76 | note | Standard/Specification - Project Specification
334d9ddb-4b73-5c2b-94c0-966ce1a407b6 | note | Acceptance Criteria - Unless specified otherwise, all catchpits, manholes and other stormwater structures shall be founded on a minimum 75 mm bedding.
994916db-82de-51a6-b4c2-f7c3062af9bd | note | Verifying Document - Checksheet,Photos
45d7847c-43bd-5fca-8506-af0434da3bca | note | Frequency - Each Structure
0d0ade91-61e1-5231-9bec-1b2e9454bbb9 | note | Inspection Type (Visual, other) - Check
94735ee6-ddca-5a05-8610-33d0fc55b1f7 | note | Inspection: Key - C
204dd716-e7e3-5043-bd0f-42edadd02c69 | note | Inspection: By - SE/PS
| checkpoint | 4.4.4 - Structure Backfill Testing
cb61e325-b75d-5862-9cc4-1fb54793bb5a | note | Standard/Specification - Project Specification
c4f947a3-228e-500f-b122-39605f1107b4 | note | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
4ff6d851-9de2-5dc7-a258-fc6abe981fa4 | note | Verifying Document - NDM Report
a69ccf33-e9bb-5c7d-9858-7a55802e6210 | note | Frequency - One test every two layers per manhole
173f79c2-b82d-57d5-b9b6-23bb70e67174 | note | Inspection Type (Visual, other) - Check
b4b15849-b551-5cbc-ac40-6ad5e70599d7 | note | Inspection: Key - C
e4b1f65f-78d8-5d16-b0ff-433e42794baf | note | Inspection: By - SE/PS
| checkpoint | 4.4.5 - Pipe Penetrations
4d276369-2411-5837-8254-feb10e7dec95 | note | Standard/Specification - Project Specification
b4ebbd53-aefb-5693-8bf1-0ebd54a03a00 | note | Acceptance Criteria - Drill holes around the intended cut line before removing the section to create pipe penetrations. Ensure that the diameter of the cutout does not exceed 100 mm beyond the outer diameter of the pipe.
8aba924d-337e-5533-9118-833304b33d7f | note | Verifying Document - Photo
b244ee1d-6491-5111-9aaa-65995f7783bc | note | Frequency - Each Structure
cec129b6-f28e-5b86-8390-5aea73934ac3 | note | Inspection Type (Visual, other) - Visual
4b8004a4-da07-5410-b223-7e019f3e5a69 | note | Inspection: Key - I
8715cf8a-42ba-5610-9885-705d19e4b548 | note | Inspection: By - SE/PS
| checkpoint | 4.4.6 - Benching
596896c2-1749-5443-8ac7-af90b75439be | note | Standard/Specification - Project Specification
e6568edc-a4c9-5e2a-a2a2-f830f2f5e130 | note | Acceptance Criteria - Construct manhole benching and channelling using 25 MPa concrete. Cast and trowel manhole benching to shape, sloping towards the channel at minimum 1:12 with a U2 finish.
bba47e45-d8f1-520e-a7fd-fde362b966fd | note | Verifying Document - Photo
6eefedec-2720-5d60-aea5-79e44d460514 | note | Frequency - Each Structure
089b7b61-ee35-5d72-9531-ae0489143442 | note | Inspection Type (Visual, other) - Visual
7d5bae99-4a4a-5999-b0d5-30c17d45eb74 | note | Inspection: Key - I
435a2743-c4a6-5451-bb02-8ffa9c9b0c11 | note | Inspection: By - SE/PS
| checkpoint | 4.4.7 - Corbels
80f41560-a0f9-54d5-82f4-6317cb04f073 | note | Standard/Specification - Downer Standard
686e128c-508d-5cca-906d-6ca3682bea28 | note | Acceptance Criteria - Pipes shall be haunched and surrounded with concrete to a minimum distance of 200mm from the outside of the manhole in accordance with the drawings.
e574d1d9-c5b3-5093-af94-e65902da6379 | note | Verifying Document - Photo
caa661ce-1eeb-5501-911a-78db7667fb24 | note | Frequency - Each Pipe Entry
8c3f339a-a4a6-5a0c-b8ee-70720e5a276b | note | Inspection Type (Visual, other) - Visual
4ddad4c4-9152-5cd0-a94b-7dc4c9349c77 | note | Inspection: Key - I
dee3f020-26f3-56bb-902f-29da7ef184f4 | note | Inspection: By - SE/PS
| checkpoint | 4.4.8 - Pipe ends
871cbc75-6b5d-584d-b29d-91f9a1d1bdb7 | note | Standard/Specification - Downer Standard
849b2d3e-62f6-5bc0-bb93-b093cc3a46a6 | note | Acceptance Criteria - Pipe ends shall finish approximately 50mm beyond the inside wall and be plastered with cement mortar or encased in benching concrete in accordance with the drawings.
03119f96-3509-5762-99c7-8dbbc1ac6e91 | note | Verifying Document - Photo
4a841283-2c0f-5aef-8599-790b5f3fc580 | note | Frequency - Each Pipe Entry
7e8aae6d-06fb-58a1-b1ab-2698a33a9e39 | note | Inspection Type (Visual, other) - Visual
24033853-c60f-5737-91c9-54078ff67d7b | note | Inspection: Key - I
02c29bce-1add-5890-adfb-019a6f3a1ee6 | note | Inspection: By - SE/PS
| checkpoint | 4.4.9 - Dewatering
7fbdb266-e47d-5933-acef-a778979130ba | note | Standard/Specification - Project Specification T-WES 00011, Section 3.5
c7410462-830e-560c-a2b4-60cd28665f07 | note | Acceptance Criteria - Provide a method statement for controlling water in trenches or dewatering for the Engineers acceptance five days before construction, including:
0d199846-4075-52ba-b003-9a5cb5da1420 | note | ○ Reasons why the proposed de-watering system has been chosen.
4f91a283-22e4-57b1-9091-089e0175beb3 | note | ○ Proposed location and details of any well points/spears.
7b319455-c6e3-513f-bef8-4f6bae846491 | note | ○ Details of back-up power supplies in case there is a power failure.
81d8afe5-e817-5664-8916-7b480c85645b | note | ○ Details of discharging (location(s), volume and flow rate) including environmental controls.
1e6e6262-955b-527d-b81a-629278765af7 | note | ○ A rsk assessment with respect to dewatering affecting adjacent structures.
03201419-4e49-5fea-ac9a-8dac0c1415d5 | note | ○ Detrails of how niose standards will be met.
b8edbca8-6dd2-5b7e-a248-fadaf2cd0988 | note | Verifying Document - Approved Verification
def5a9a6-5287-5805-a5a0-7aa48536a7c4 | note | Frequency - Prior to installation
8581c2b8-8b8a-5653-b6c5-9ec96708e20f | note | Inspection Type (Visual, other) - Hold Point
7c08b02d-e1e1-557f-8975-846c52f477c7 | note | Inspection: Key - H
391cdfbf-e3d3-583e-954c-2288b08a3006 | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| section | 4.5 Acceptance Testing and Commissioning
| checkpoint | 4.5.1 - Pipeline Testing - Acceptance Criteria
7dc71bd2-02cd-5061-893a-e4cfa13c573f | note | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.3
f328da7e-c7c2-5e7f-b811-d7c322d71318 | note | Acceptance Criteria - Pipelines including laterals shall be tested in accordance with one of the following methods as detailed in AS/NZS 2566.2 Section 6.4:
e1e7b08e-5a23-5ce7-8d20-fdff970de323 | note | ○ Low Pressure Air Testing
1a5fb9f1-7c4b-5dbe-be80-d9f2560e5157 | note | ○ Hydrostatic Testing
a922e601-6588-56a2-98aa-049f8ef8b3ea | note | ○ Vacuum Testing
0ab557a6-2780-57fc-8f39-e49b6df90cd6 | note | Verifying Document - Test Report
56e8fb6d-d75c-5b64-9d3c-18a174597cbf | note | Frequency - Each Pipline
84d236c3-8c90-5e05-8523-da926b93e94b | note | Inspection Type (Visual, other) - Check, Visual
b9559d78-a206-5f89-80c9-37641a7d9d00 | note | Inspection: Key - H
7485e3ee-0325-5adf-b106-9394c24a9ce3 | note | Inspection: By - CR, SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.2 - Pipeline Testing - Testing Record Requirements
60529a9e-f6d2-5fc1-a7a7-928d2a07a79c | note | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.4
509797eb-52eb-5928-8b29-7fd289cac00d | note | Acceptance Criteria - The Test must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
84166c63-14d5-5d35-83d1-3d4e97bbff78 | note | (a) Date
8bec501f-d4f8-551b-a922-0c7da25864e4 | note | (b) Full description of section of pipeline being tested, including pipe length, pipe diameter, class and manufacture.
1fa71828-a74f-5583-87b8-a0937deab299 | note | (c) Number of sump connections or laterals on the section being tested.
26fec5bc-feab-502d-bc53-6eb0f26a1e58 | note | (d) Test pressure and acceptance criteria
cb2ea67d-8ca0-531f-9b29-87c097eecefa | note | (e) The start time of the test
6cae5163-f767-5535-985d-ee9f5f38f578 | note | (f) The pressure at the start time
b2dfe186-2d75-519c-8da4-eed6f7ed7296 | note | (g) Time taken to drop pressure by 2 kPa
55a75b83-70c5-5491-afa7-56b484f3ecde | note | (h) Minimum and maximum pressure in the test section and water loss over 30 minutes
a901d165-b2a5-57b9-86f2-ff7fa82e81fa | note | (i) Whether the pipeline passed the test
107353e8-e6e9-575b-bd6a-9ac31b7696ca | note | (j) The name and signature of the Contractors personnel responsible for the test
9498cca9-52e8-57a2-a671-8b39ccaed68c | note | (k) The name and signature of the Engineers nominated personnel who witnessed the test
01d9d1e9-5412-58d0-adfe-03a984076ccd | note | Verifying Document - Test Report
b5d35ad6-dc11-5aca-84d5-8e728a289d30 | note | Frequency - Each Pipline
4b12f6d2-fb60-5dc0-a70a-7f852f021761 | note | Inspection Type (Visual, other) - Check, Visual
ae0d593a-c3e6-5ba4-bb80-8259cc506f37 | note | Inspection: Key - H
578b3532-5330-5b37-9be7-ce2efbf96082 | note | Inspection: By - CR, SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.3 - Flexible Pipe Ovality Test
d13de643-05cc-5dec-83fa-599a28e30a57 | note | Standard/Specification - Project Specification
753f333c-9fe1-57d4-bc27-576d97d46af5 | note | Acceptance Criteria - An ovality test shall be carried out on gravity pipelines in accordance with clause 6.5 of AS/NZS 2566.2 “Buried flexible pipelines – Installation”. The test shall be carried out at least seven days after the pipe surround is laid.
7849dc23-049f-5b52-a6ce-d66916052470 | note | Verifying Document - Test Report
4aa9ee65-93f0-5a90-9ad6-fd1fd27c5a28 | note | Frequency - Each Pipline
c3063717-38d4-5618-b10f-197b8f735f8d | note | Inspection Type (Visual, other) - Check, Visual
e53f77c2-33e8-5f10-9d0e-387eb7e55c5f | note | Inspection: Key - H
591136a5-68e9-5082-9c6f-d5e95d02cfd5 | note | Inspection: By - CR, SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.4 - CCTV Inspection
0a8782d3-9561-56fb-92a6-2bba555d428f | note | Standard/Specification - Project Specification, T-WES 00012, Section 4.6.7
43f3b1a2-2568-5232-a969-9dfad256dd35 | note | Acceptance Criteria - All completed pipelines (excluding laterals and sump connections) are to be inspected using CCTV after backfilling and leak testing is successfully completed, but prior to final surface restoration.
c7de77e0-5bde-5d5a-80f9-0850e12206e2 | note | ○ The specific requirements for the CCTV inspection are found within clauses (a) to (f)
6b5a49ba-3293-5334-8c4c-898bd0743635 | note | Verifying Document - Test Report
4dae5486-8277-5a59-817a-657eb5695881 | note | Frequency - Each Pipline
a8f25e30-da08-50ae-a02c-6a3677b9b3e0 | note | Inspection Type (Visual, other) - Check, Visual
75d60bba-b236-5c61-b998-b97cd5b547d2 | note | Inspection: Key - H
ebf70a1e-ee69-5881-b800-a7bad6fb94da | note | Inspection: By - CR, SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.5 - Manhole Testing
ff2495e2-b3b8-57c6-98af-6d739b608ac0 | note | Standard/Specification - Project Specification
4632dde4-d699-5e0d-a947-c25729bd8f66 | note | Acceptance Criteria - All manholes (new and refurbished) shall be water tested. Manhole watertightness testing must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
0005e159-03c6-5d8e-a8a8-af24b27d9be7 | note | Verifying Document - Test Report
b26783e1-881d-50a2-9ba8-f57cd47da320 | note | Frequency - Each Pipline
ba30afeb-64c4-5cd7-8a4a-3b5195028e9a | note | Inspection Type (Visual, other) - Check, Visual
e31e9da5-ba0d-56b9-b29c-e8876caeaf1c | note | Inspection: Key - H
7dc68161-2890-5fd8-bf02-ded4c1f75e82 | note | Inspection: By - CR, SE/PS
| signoff | AUTHORITY HOLDPOINT
| section | 4.6 Portable Water - Installation
| checkpoint | 4.6.1 - Trench Foundation
409cf5eb-ddf6-5443-b710-2fa50c1c6118 | note | Standard/Specification - Project Specification
01507894-bb73-585e-8e0a-8d30a69238c0 | note | Acceptance Criteria - Shape the foundation for uniform pipe support and alignment. Alert the Engineer if unsuitable trench floor material and await instructions before proceeding with additional work.
12364add-d7fa-5659-9637-648faa05a053 | note | Verifying Document - Scala Results
690f4172-5bf8-5907-ac4e-38d7528d284b | note | Frequency - Every 50 m
fdd4053b-4308-5884-bb47-dd61fc50bc71 | note | Inspection Type (Visual, other) - Inspection
69947bd6-2ff7-5443-b416-01d8a46257d8 | note | Inspection: Key - V,D
fc702e47-017d-5b73-963b-e30ec149ad9f | note | Inspection: By - SE/PS
| checkpoint | 4.6.2 - Soft Ground faft Foundation
928a2735-de04-526a-a508-62417cad93a1 | note | Standard/Specification - Project Specification
e402511a-c901-5fe4-bae3-fb1c9567ffa3 | note | Acceptance Criteria - Refer engineers advise where the foundation fails to meet the design requirments.
e150d299-eadd-5d93-a2ba-9e9e67f164c2 | note | Verifying Document - Checksheet
e4813268-ff25-5270-9e30-9eb97015dc5d | note | Frequency - for each event/as required
7981258f-9b0d-544b-ab17-fc78488a3426 | note | Inspection Type (Visual, other) - Check
070f8bbd-874d-5335-92f1-6be7879e01dc | note | Inspection: Key - R,V
2080e1b5-d1a6-5b7e-9849-f8e3c5af4221 | note | Inspection: By - SE
| checkpoint | 4.6.3 - Geotextile
b058d885-cd44-5915-b61e-870c7665f3f6 | note | Standard/Specification - Project Specification
6aea7868-6bdc-540d-9629-56525d6dbdb7 | note | Acceptance Criteria - Geotextiles shall fully wrap raft foundations, in accordance with the manufacturer’s specification, where rafts are required.
e8da2d83-1474-5094-9be8-9d49d62bb172 | note | Verifying Document - Checksheet
50fef4ff-0133-58c4-9128-933b0452f159 | note | Frequency - for each event/as required
c3f5a721-337c-59e7-9639-86617a942f27 | note | Inspection Type (Visual, other) - Review
47ca3ba2-a261-5a37-afa6-91bf587e867c | note | Inspection: Key - R
adf60014-463e-5578-b836-d6f4fbf777f6 | note | Inspection: By - SE/PS
| checkpoint | 4.6.4 - Embedment Construction
8daf7a26-5e2f-5e8f-ae98-6a2d53d9df53 | note | Standard/Specification - Project Specification T-WES 00013, 3.1.5
2035fd3f-5703-57bc-ab94-9ef4c770ae00 | note | Acceptance Criteria - Place and compact all filling materials in layers not exceeding 200 mm compacted thickness. For pipe embedment at least 90% of the maximum dry density (MDD)
76feeef4-e43e-5122-987e-7a46c2493fe1 | note | Verifying Document - NDM Report
49779254-d942-5e0f-bc88-d6970ea05e57 | note | Frequency - NDM Every 50 m per 200mm of fill
c9a305b0-94d5-5faf-933c-a79fe3c927bc | note | Inspection Type (Visual, other) - Inspection
541bc395-3851-52d4-9c8a-d915ade8e97b | note | Inspection: Key - R
cac8d4a9-c962-53da-b82e-33ee74e1bffe | note | Inspection: By - SE/PS
| checkpoint | 4.6.5 - Laying and Jointing of Pipes (1)
3b72a032-57d2-5484-8877-b73a5cc2c9b4 | note | Specification - Project Specification T-WES 00013, 3.1.6
7005e6cf-e01a-5063-bf6f-1a7e41550d35 | note | Acceptance Criteria - Lay in straight lines, beginning at the lower end of the line (unless agreed otherwise in writing with the Engineer), and complete each joint before another pipe is laid.
ec7da6e4-6d1c-5865-89c4-8ae0bc36de9e | note | ○ Lay all pipe with manufacturing codes and class markings facing upwards.
f4cd81c9-dab4-5eb8-a3c2-29e157b6f876 | note | Verifying Document - Checksheet
69d12d5e-585d-5eae-b95a-ec7e103755ac | note | Frequency - Each Pipline
c3662c52-6362-5ecf-8937-98b984d9d592 | note | Inspection Type (Visual, other) - Check
7b130bc9-cf2e-5ad8-8b1e-eaa650ee365e | note | Inspection: Key - Check
b4f2c537-398f-5c87-9478-8cd6cf8fbed0 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 4.6.5 - Laying and Jointing of Pipes (2)
1e29013b-81b8-5786-b6af-bac0292a505b | note | Specification - General, Project Specification T-WES 00013, 3.1.1
c0b8596e-a157-5cdc-bd39-25f76f53ffed | note | Acceptance Criteria - Submit the proposed methodology for pipe laying, concrete work, jointing and backfilling to the Engineer and obtain acceptance before starting pipe installation.
9c9a6038-1ec7-5e00-a9bb-4497f299c00c | note | Verifying Document - Approved Verification
598846fe-0351-5831-8393-0bde40e5ef82 | note | Frequency - Prior to installation
da4b5723-d36c-5b30-979b-eab7779181bd | note | Inspection Type (Visual, other) - Hold Point
205834ce-18bf-5fc0-a47b-fcc85dbe7505 | note | Inspection: Key - H
a29526fa-0f20-5d8c-8267-5bac8f6bb012 | note | Inspection: By (Role Key) - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.6 - Thrust Blocks
21321a55-3113-571f-b4aa-1da687b7320b | note | Specification - Project Specification T-WES 00013, 3.1.12
30a787fd-4a50-5b00-a8a6-d6867c4ec6fd | note | Acceptance Criteria - Unreinforced Concrete Thrust Blocks Precast concrete thrust blocks can only be used where approved by the local authority. Arrange for the Engineer to inspect the first completed thrust block.
e8b34942-1a94-59c0-8ae4-9e844a1c6d80 | note | Verifying Document - Checksheet, concrete test result
be47a696-b2e6-5981-8312-6092b7de6dd0 | note | Frequency - On the first completed thrust block
25b7679e-5b88-54c7-8dc4-9bb66b0c0a05 | note | Inspection Type (Visual, other) - Inspection
934087c0-27dc-56f6-af74-55dcfd91ef01 | note | Inspection: Key - H
23f5a3dc-c224-5d0a-a8c1-19e40e8bee2e | note | Inspection: By (Role Key) - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.7 - Thrust Blocks
528dadc1-7640-5e92-9268-ceff8348dd8b | note | Specification - Project Specification T-WES 00013, 3.1.13
217ae2b0-6b90-5690-a218-e9e9f63c7653 | note | Acceptance Criteria - Reinforced Concrete Thrust Walls / Thrust Blocks
cc7f7c4f-bbbc-5e88-86d9-1b169cadd6f0 | note | ○ All thrust wall steel reinforcement must comply with AS/NZS 4671. Have the Engineer inspect the thrust wall reinforcing and puddle pipe arrangement prior to pouring concrete.
f6fe2356-b40e-5282-b60f-9cf3db78f827 | note | Verifying Document - Checksheet, concrete test result
9e565e35-65c9-5cc3-85ef-7a30a71ea91c | note | Frequency - for each set of blocks pouring
e32a406d-579a-5861-9b81-4f6ccb10b221 | note | Inspection Type (Visual, other) - Inspection
da1f99cc-8c4b-5aeb-8f47-4767e457cff1 | note | Inspection: Key - H
de5ae475-76f6-5598-bba4-1dddf4b34173 | note | Inspection: By (Role Key) - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.8 - Flanges
f105267f-25a2-545c-9ce4-ce2b6a0ea6e9 | note | Standard/Specification - Project Specification T-WES 00013, 3.1.14
9d2393bb-90f2-55f0-9ca7-da0965ecdd48 | note | Acceptance Criteria - Complete the flange bolting procedure as per project spec and check sheet
57975c22-b10f-591f-a154-356ac2fca05b | note | ○ Have the Engineer witness the first flanged joint completed on the PE 100 pipeline
8513895e-f19a-5736-9609-a6fc223a4817 | note | Verifying Document - Check sheet, photo
306e9029-2714-52b9-8d7d-6aad7c34346f | note | Frequency - First flanged joint completed on the PE 100 pipeline
ba8f524b-8f6c-5d36-bf13-5cb62e34eca7 | note | Inspection Type (Visual, other) - Hold Point
0e4ab447-45e5-5b8c-909f-49f9cd053628 | note | Inspection: Key - H
c2426a03-5b91-5b87-8cbe-aeae08910fa2 | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.9 - Backfill
09b6ee0c-dbbe-5ebb-8e8f-56bdba57da19 | note | Standard/Specification - Project Specification
2cde2063-d072-54ab-94ff-0d6e1fc628b1 | note | Acceptance Criteria - AP65 backfill shall be compacted in 200mm loose layers to at least 95% of the maximum dry density (MDD) every 50m.
f9ab3409-67f1-5f0d-a021-e0ceb4dcd1fc | note | Verifying Document - NDM Report
d04e6f25-a4dd-5452-92b1-f9275a23f301 | note | Frequency - NDM Every 50 m per 200mm of fill
17a1622d-3a08-5333-acca-d505910bbb7e | note | Inspection Type (Visual, other) - Inspection
2b571044-d334-5381-89a3-bfcf4f9620a6 | note | Inspection: Key - R
60c3b01a-7ee4-5c79-8833-8725624a624a | note | Inspection: By - SE/PS
| section | 4.7 Portable Water - Testing and Commissioning
| checkpoint | 4.7.1 - Pressure Test
7c910951-25cc-5ba4-999b-d93de39976e6 | note | Specification - Project Specification, T-WES 00013, Section 4.5.7.2
1331785f-48a2-55a9-8d4c-4ca6004953e9 | note | Acceptance Criteria - Complete the pressure test in accordance with the project specification and the check sheet for pressure test.
142ef1a6-b3fc-5145-8331-03bbf1bb46b7 | note | ○ The system test Pressure (STP) is 1,000 kPa.
88bd8358-3e49-5ad3-a1c7-08b3318d01f5 | note | Verifying Document - Check sheet, photo
4efe6b2d-4025-5c63-8bf0-512791bf83f0 | note | Frequency - Each major pipelines
b9e09796-abd8-516e-a053-2918aaddea4d | note | Inspection Type (Visual, other) - Check
e8177d34-f0cd-512f-a050-406d1b4b342f | note | Inspection: Key - W
a1d8290b-0a91-5630-a2fd-af4e1f1ca900 | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 4.7.2 - Pressure Test
d6a91f2e-6512-5342-8b51-738ab6d0c328 | note | Specification - Project Specification, T-WES 00013, Section 4.5.3
c98c56ea-f241-531c-862b-abf0f1104e64 | note | Acceptance Criteria - Before commencing any pressure acceptance test:
87fd6fb9-73db-5eaf-908b-ae86dfc36718 | note | ○ Give the Engineer at least two working days notice.
b4685ea2-689c-5965-afa3-c33fad26c526 | note | ○ Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 working days prior to the test, including but not limited to:
519b35f8-0790-5941-815b-85edaefe92f6 | note | ○ Proposed equipment to be used, including pump/s, water meters, logging pressure gauge/s, check pressure gauge/s
735caf49-7b54-556b-81bd-0211bc6614a1 | note | ○ Proposed fill rate, noting the bulk fill must not be greater than the discharge capacity of any air valves and any local authority constraints relating to the supply of water
c946628f-4011-5594-968c-a0006610018c | note | ○ Calibration certificates for meters and pressure gauges
ab1cdb24-bdb3-5a41-b1b6-ca5cd72e2d09 | note | ○ Details of qualified personnel who will be carrying out the tests
75b23fcd-4f83-51f1-afe0-402f899551f5 | note | ○ Source/s of water proposed to be used
7352a276-dc76-5604-8e64-b2f1da4b6ce5 | note | ○ Provision for backflow prevention
88ce0f87-5659-594d-bacc-dd572a9e898e | note | ○ Location of the pressure test rig and the proposed test pressure at that location if the elevation of the test rig is higher than the lowest part of the test section
e7175577-a18c-52a0-8149-add881d73021 | note | ○ The test lengths proposed that will ensure that no pipes are over pressurised or inadequately tested
ec9a8219-1c98-5095-b721-c01544487128 | note | ○ Pressure test report template
cc1591d3-66f8-512c-9cdc-14a6593920b2 | note | ○ Health and safety risks and mitigation measures
b156180f-5377-5567-9545-2de630b628db | note | Verifying Document - Check sheet, (WMS)
f3985c99-9a70-55d3-9ba8-e8c44a0a475c | note | Frequency - Prior to pressure testing
db0ed3d4-69c7-5efe-8490-6947809927d9 | note | Inspection Type (Visual, other) - Review
79dd26ce-f813-5448-bdac-55f65c6652a5 | note | Inspection: Key - R
ad9a9d9e-7cb7-5e11-964b-9cde39133d61 | note | Inspection: By (Role Key) - CR/SE
| checkpoint | 4.7.3 - Water Main Disinfection
22ccc71f-a8eb-5099-96f4-a1e2d12a43c0 | note | Specification - Project Specification, T-WES 00013, Section 5
af04f8bd-da64-5706-b089-9df73e82a265 | note | Acceptance Criteria - A resolution with a remaining free available chlorine (FAC) level ranging from 15 to 20 mg/L (ppm). By the conclusion of the disinfection period, the water expelled from the pipelines should retain a minimum FAC concentration of 5 mg/L.
6d732a08-3e9c-5c48-9946-043ec70c4a1a | note | Prepare to submit a WMS for disinfection of potable water pipelines to the Engineer for acceptance before commencing disinfection work. The WMS must include (at least) details of:
24e95a3d-9262-560a-b497-f5378d271441 | note | ○ Swabbing all potable water pipes, valves, and other fittings (> DN 63)
2d08bf77-9781-52b9-ae52-79eb71ea6868 | note | ○ How the disinfection solution will be introduced with the initial fill water for pressure acceptance testing, if done, Note that this will be at the Contractors risk
c65d509f-3689-5a04-9c20-8d2b9d40e19f | note | ○ How the disinfection solution will be prepared and delivered reliably into the pipeline. Include calculations of dosing and flow rates, strength of the proposed liquid or powered form of hypochlorite as well as methods for checking that the required FAC is being achieved
6bce6bfb-bd86-5149-8e99-c1111b5c2e29 | note | ○ How it is proposed to ensure that all watermains, service pipes, valves and fittings will receive nthe disinfection solution
dc631fff-29f4-5afd-9f30-88af55bf2af1 | note | ○ How measurement of the FAC during and at the end of the disinfection process will be achieved to ensure that the system has been fully disinfected
4da904e8-c4eb-57cc-aa66-0873e61300a7 | note | ○ How the disinfection solution is to be disposed of safely at the end
235b7b66-2341-5210-a9ac-9c30cc3e8ece | note | ○ Identified health and safety risks and proposed mitigation measures
ad31b615-2083-53f8-8f65-515f25f5f2c9 | note | Verifying Document - Checksheet, (WMS)
7fe5f3a9-0676-50b8-aa53-f087266631c7 | note | Frequency - Before commissioning
b7d0a85a-7d98-5674-bafb-dab87360f565 | note | Inspection Type (Visual, other) - Review
a6d31a51-6476-5a8f-bb7a-6626d1f3de4a | note | Inspection: Key - R
b80a2674-86f5-5259-83f5-d821e73ee43e | note | Inspection: By (Role Key) - SE/PS
| checkpoint | 4.7.4 - Flushing of Reconnection
23edcb39-8f96-53ca-8758-50c583a7a513 | note | Specification - Downer Standard
8b48782f-f5b3-5dc2-83d8-1709f3065ebc | note | Acceptance Criteria - The Contractor shall open the front outside hose tap, if available, before the supply is reinstated to any premises. Wherever possible, the owner shall be notified prior to this work.
511435b8-2778-5d9b-8e20-afd512933ca6 | note | Verifying Document - Checksheet
eb9c6f56-0fc0-5535-945f-b6d0ac05e05a | note | Frequency - Each Connection
e2beac93-14ea-5dfc-8127-c579a75f657a | note | Inspection Type (Visual, other) - Review
b97b68c5-3aed-5505-b73f-a2a2def3fac5 | note | Inspection: Key - R
2cd5b66f-9df1-597f-a4a9-e93988db277c | note | Inspection: By (Role Key) - SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
b4d79b85-783c-526f-8a8a-90586367cbda | note | Inspection Point: Quality Control Activity - Upon completion of works
f218add7-b67e-522e-abd0-31b34826d997 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
d5425232-26fc-5077-8bae-6d4191a7a1c6 | note | Verifying Document - Closed-out NCR/Defects
58f9571e-c8d8-5c5f-80bf-85eff5ac3536 | note | Frequency - Post construction
4ebdc44d-a6e7-55b7-bd37-506e0985804b | note | Inspection Type - Review
cca8f0bd-92b7-5dcc-886f-0e60a2ac0ac2 | note | Inspection: Key - R
7e98de90-025e-555b-ae08-9867a3d7bf70 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
0b1a8f5f-d289-55fb-acfe-bb7545c069c9 | note | Inspection Point: Quality Control Activity - Upon completion of works
25688fed-42a6-5377-bb5c-03c2ee968b97 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
933ec047-b915-54e4-994c-9ba1308d7182 | note | Verifying Document - As built survey record completed
a3377df1-cd34-5a85-b182-c6cc3f2772ba | note | Frequency - Post construction
b81f2b81-3c75-5ebe-a2bc-d3ee7ba76480 | note | Inspection Type - Review
02377ff0-cb50-502c-9136-27833f7d47d7 | note | Inspection: Key - R
0c3fee25-de11-543d-ab7c-ae4ddaf90015 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
fb70ae6f-6d0d-5ffa-b289-82b80266283f | note | Inspection Point: Quality Control Activity - Upon completion of works
e67e0d55-2aea-5143-a4e6-fc10ba466c5b | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
1f21970d-20a6-524f-a9d2-b077556232e3 | note | Verifying Document - Signed As-built Drawings
aa85944a-5ccd-5984-86bb-9708d638f780 | note | Frequency - Post construction
d8cc83a9-0136-5534-9f19-d340ef90ba38 | note | Inspection Type - Review
8210f2ea-bbec-5cc8-910b-355746a46e26 | note | Inspection: Key - R
24f627de-f05d-57a0-9fd0-fdafc2e807b0 | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
311367fb-3bbe-5203-97c0-45243f7707ab | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
918a6697-c7d4-55f5-850a-cc7db5fb29bc | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
17b26ba6-db61-5b0b-96c5-40c1ed474868 | note | Verifying Document - Register
55afa045-5aac-569e-9aea-5bf05c538999 | note | Frequency - Post construction
3685a368-bf08-5082-91b4-9c4e3e24eec8 | note | Inspection Type - Review
479a5263-0a5b-594e-873c-05911b67f5eb | note | Inspection: Key - R
b00fc926-7ae9-5137-a65c-2b0c70090884 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
27d7d49f-1cf2-5f73-9e57-cb36d1b8a489 | note | Inspection Point: Quality Control Activity - Upon completion of works
cd449bf2-ab8c-5ce7-9bf5-135d3564c0c6 | note | Acceptance Criteria - All signed and closed out
445c1d29-8182-5b0f-b055-87b0f0171571 | note | Verifying Document - Signed off Documents
c6786072-850b-532d-836f-11a2f5c5f68a | note | Frequency - Post construction
bce0d59d-17d0-5915-ab56-d0463e1a1656 | note | Inspection Type - Review
7b55df9d-8c07-5d68-8566-50b192c1b83e | note | Inspection: Key - R
74180609-6372-5f01-9222-63e006cd6297 | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0029_v2 (VMS Site) | itp | 558020-DOW-ITP-PC-0029_v2 (VMS Site) | fceea54f-7a86-4acb-8ee6-123ebc1f909d
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
9f0f8c00-15a2-555a-ba25-66b2d2f92897 | note | Standard/Specification - Downer
953c773f-293c-56ce-8282-74db353b29f4 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
d45a5e56-ac5c-5a1e-96fa-e3a68e06b014 | note | Verifying Document - Survey Records
659cb2f1-9fae-57f0-8149-3e958553ecd0 | note | Frequency - Prior to Works
807e7e5f-0406-5a01-af98-0cc6de372967 | note | Inspection Type (Visual, other) - Document review
42fdca46-ba00-5cfc-981e-0f7dab9766fe | note | Inspection: Key - H
a4f1ad8e-a23b-5e85-86e7-40b0d21859c4 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
0c58f0ca-f3e4-5cd8-be2a-501166b33c0b | note | Standard/Specification - Downer
2f277f66-753c-5782-9a72-f567ba684d3f | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
af4d920b-cc99-555c-9f8b-eb2a41870938 | note | Verifying Document - Service location documents
df11cc87-ecd0-5915-a830-f4a1faac8440 | note | Frequency - Prior to Works
fd6b6421-2f79-5c42-a3a1-8a112ad5a663 | note | Inspection Type (Visual, other) - Document review
78f26b1b-4734-5035-a921-e5a40759cf72 | note | Inspection: Key - R
66640576-8dee-53a7-b917-768e9184eb13 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
dc1ae1ce-09b8-55b2-b8bb-b2c26173b149 | note | Standard/Specification - Downer
68496e9e-3651-5a71-a036-5544b3c1b480 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
1e51d5ae-61fd-568b-ad76-476666b5147f | note | Verifying Document - Internal Permits
ae692cbe-6b52-5890-b43f-a9a10d7383a9 | note | Frequency - Prior to Excavation
116db665-9a19-5942-b391-e48fcc620d32 | note | Inspection Type (Visual, other) - Document review
856a1db7-28a0-5192-a8df-4f09b4722603 | note | Inspection: Key - R
e5802c5b-9a76-554d-95b3-a649ab4efed4 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
96507db9-493a-54fe-95e0-6ce07d26503a | note | Standard/Specification - Downer
6821f9a2-8e7a-57c4-aeae-f93560f55e19 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
a36952e5-30d3-5fac-bb1a-1a4d18ae3c01 | note | Verifying Document - External Permits
d44a38e4-77f0-5ecb-92be-351647a2c0a9 | note | Frequency - Prior to Excavation
99a00494-db42-5e03-9725-e9dc391925e8 | note | Inspection Type (Visual, other) - Document review
eb4ccde0-16aa-5e6c-b0b6-5639a58b5a69 | note | Inspection: Key - R
5f03815c-dfc1-54b5-b333-7f1bccdcea93 | note | Inspection: By - SE
| checkpoint | 3.1.5 - Approved Construction Drawings
055b6989-3d87-5bc8-8142-02925704007d | note | Standard/Specification - Downer
4f378f8d-a86e-545a-b737-6b1cedc7fd43 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
66559a2a-d1c6-5212-aca1-06f045deb075 | note | Verifying Document - IFC Drawings
c3a72da2-d086-5738-97b9-467c83116571 | note | Frequency - Prior to works start
706d3b59-726a-5ec5-a134-19759cf4905f | note | Inspection Type (Visual, other) - Document review
b568347b-048c-522a-bb51-53057c6fd2b5 | note | Inspection: Key - R
ab6f8892-56b0-5ef0-a78a-353ddb1a073e | note | Inspection: By - SE
| section | 3.2 Receiving Materials/Parts - VMS Foundation with Plinth and cabinet pad
| checkpoint | 3.2.1 - Concrete mix design
5eef9408-6bb0-5540-bdf8-f4448112d1c1 | note | Standard/Specification - 30Mpa Structural Concrete
9cfd4344-d897-577d-9164-911fd73429f3 | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
2daa361c-5e68-588d-8bfb-87121b3282cb | note | Verifying Document - Concrete supplier mix designs
a41b3586-7abc-50a2-bcc6-2f6b30e6c415 | note | Frequency - Submitted to Client Engineer for approval before construction
8a046739-7407-5cff-a1de-f91a379973b9 | note | Inspection Type (Visual, other) - Document review
ff309f21-c8a4-5dd4-8bea-a1029634c2c2 | note | Inspection: Key - H
a36bf775-11bc-50a4-8694-584e6f0cbf46 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - Reinforcement
9f141ade-0f2f-50e0-8e9f-a72899ae2137 | note | Standard/Specification - As per Design Specification
6f8bfd5c-2a40-59d7-a6f5-357208f0a821 | note | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
823f76b9-97aa-5280-8bc0-53bbd306418a | note | Verifying Document - Mill Certs
68b0bcde-3352-5cc4-814b-ab8de33fe021 | note | Frequency - Each Lot
4949f69d-a787-5c7b-95f4-2251e2940831 | note | Inspection Type (Visual, other) - Document review
9c515e0f-4e4b-53e7-88bc-f84d5a6d8f67 | note | Inspection: Key - R
df1fb273-9713-5f2c-8646-ff9c9e41bab1 | note | Inspection: By - SE
| section | 3.3 Receiving Materials/Parts - Shoulder Widening and Sealing
| checkpoint | 3.3.1 - AP65 - Source Property Tests and Sampling
3f642520-b1ba-55ac-a473-fd20b4162db1 | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
26814663-388d-599e-b8d1-7e720a6f1b3f | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
903b4099-d436-5d8f-aa9b-d339454e93c7 | note | Verifying Document - IANZ Lab Reports
ae020f26-6755-5396-9de6-5a7993bdee60 | note | Frequency - 10,000m3
69b0d4b7-d7a1-5570-936a-79158d6d81bd | note | Inspection Type (Visual, other) - Document review
a76b1e01-77aa-5d1a-b2a0-1aa289327b01 | note | Inspection: Key - H
6d152c62-c20e-52f0-a444-47d8f5515ee8 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - AP65 - Production Property Tests and Sampling
defabf90-ccdf-5ac3-a0a7-edf3b69420be | note | Standard/Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
0ddb6f8f-64c1-52f0-9b8d-cc970b277682 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
d063ac88-acaf-5afc-982e-16f5dda22dd1 | note | Verifying Document - IANZ Lab Reports
2b96c6d6-5595-5b2b-a014-c0299f36dd6e | note | Frequency - 3 per source initially, then 1/1000m³
89655c91-e7b6-5399-af38-8bfa661ab939 | note | Inspection Type (Visual, other) - Document review
8652a7a3-5712-530f-86c9-1b49418203a7 | note | Inspection: Key - H
fcdb9c0d-358d-5868-96fa-0a3a3684d683 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.3 - AP65 - Testing for Layer Compaction - MDD
f1635765-8ad2-5305-8e60-0b19b9f1b6e4 | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
fafd2b3b-c30a-584d-b3a2-826fa2869a29 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
67fc1a94-54fc-5aff-937b-bfe76a812999 | note | Verifying Document - IANZ Lab Reports
f39330db-6883-5e2b-9ab6-131f837d1698 | note | Frequency - 5,000m2
a79b52a1-9e37-595d-bb79-ae138d662c6d | note | Inspection Type (Visual, other) - Document review
95a99424-1ec8-5bc5-9474-efb18805814f | note | Inspection: Key - H
eb1cdb99-535a-59fd-8a18-1eb46891d6a7 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.4 - AP40 - Source Property Tests and Sampling
f7ee7994-6d21-5716-abe4-eb9694af5a8c | note | Standard/Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991, NZS 4402 : 1986
ef03e607-0e02-5407-8115-7259c8232bb7 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
c9b792f1-0433-5321-af4b-8421c67b3378 | note | Verifying Document - IANZ Lab Reports
ca7e739c-77a8-5687-8c23-772501c0b8ef | note | Frequency - 10,000m4
74f52bf2-fe0e-5b22-b530-0994705cda93 | note | Inspection Type (Visual, other) - Document review
d3d2db60-3a16-5cfd-a5ea-d5c8aa5af6bc | note | Inspection: Key - H
ccf2a351-ceea-5335-9d82-150059e86254 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.5 - AP40 - Production Property Tests and Sampling
2e7ae853-e7b2-564b-96b0-447061b90c2e | note | Standard/Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
d0fda5f5-554d-530d-af0d-f297f89aa88d | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
101e62e3-1c30-5a85-bef6-08f1aadd8aa7 | note | Verifying Document - IANZ Lab Reports
379adfa9-9e32-5f4a-8be1-62c587ca40b1 | note | Frequency - 3 per source initially, then 1/1000m³
afd31085-c033-5fb2-b187-c5bf2af1c8fd | note | Inspection Type (Visual, other) - Document review
8547630c-0a0d-5d02-98d3-8aab11b2aba6 | note | Inspection: Key - H
d27310b4-2c72-5e38-8224-7fce5c095ff1 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.6 - AP40 - Testing for Layer Compaction - MDD
95a78956-97dd-5412-8a17-f19ee93039a2 | note | Standard/Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
749f894d-3ce5-5974-b634-2a5fd173c280 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
20799ec7-ee44-570f-bc17-0affc10c9a28 | note | Verifying Document - IANZ Lab Reports
5bed7e68-3de1-50d8-86ea-e958fd9e32d3 | note | Frequency - 5,000m2
e888d83e-0320-58f4-8964-efad6bc77c02 | note | Inspection Type (Visual, other) - Document review
aeddbf15-9960-53fc-8cbb-812056797b93 | note | Inspection: Key - H
05d2e0e1-cda8-5a81-a924-4803af941c4b | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.7 - Sealing Chip - Source Property Tests and Sampling
d409c447-667d-5634-8c59-507646c1ed80 | note | Standard/Specification - TNZ M/6: 2019 - 4
a92b2c66-a095-587c-9af0-c42db631aaee | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
e1deb9ce-104f-5be1-890d-261a0195e60e | note | Verifying Document - IANZ Lab Reports
35c05d12-82ee-5ece-a783-9871eeba9c48 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
e42bc826-0d5d-5e6f-b240-b2ba11250ec2 | note | Inspection Type (Visual, other) - Document review
d2c23af3-6381-5de3-8af9-0e2ad485d5ef | note | Inspection: Key - H
111c666a-55ca-5854-9a20-b11d216ad9a0 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.8 - Sealing Chip - Production Property Test Sampling
3ac21395-e6e1-5caa-9f93-c485e963eed7 | note | Standard/Specification - TNZ M/6: 2019 - 5
ff0252a7-3e36-53f6-a8bf-6ebcce1ac883 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
a5a6ffc6-d31a-53a7-9984-4f69f4c00070 | note | Verifying Document - IANZ Lab Reports
b1f10037-20ab-5008-b88a-d897f60adbdf | note | Frequency - Every 500m3
41f7d2eb-7bc9-5315-8006-1868be695217 | note | Inspection Type (Visual, other) - Document review
279e2ef2-8aef-549f-a96a-83b5b262d6d8 | note | Inspection: Key - H
9a701158-24b4-584d-8ed6-2e992cc92238 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.9 - Bitumen - Quality Testing
e3b8d4dd-a715-58c1-963a-f4d663826a39 | note | Standard/Specification - NZTA M01: 2022 - 6
78be2bbe-d782-5013-b45e-eb0769b9cfec | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
58f592be-bbb7-50c9-a616-369f69a04ca0 | note | Verifying Document - IANZ Lab Reports
b467ba7d-c6b6-563a-9715-2db3f3659c81 | note | Frequency - One test per grade supplied
4c559134-3106-57b8-9bac-fe91410106be | note | Inspection Type (Visual, other) - Document review
8b9fdde5-f979-57b2-b0d1-68a4909e7a6c | note | Inspection: Key - H
bdd66be8-2e51-58ea-9844-6a8a18afbd00 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.10 - Bitumen - Supply Testing
d6019319-1dab-5803-ab38-7c470454c0cd | note | Standard/Specification - NZTA Q05: 2022 - 6.2
e60441d5-4863-5e8d-97a0-7b37d3d152e1 | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
a151c44a-d4b6-5d28-9011-042dbef59347 | note | Verifying Document - IANZ Lab Reports
02a86b9c-9afa-50e8-ba5d-b742164b6afe | note | Frequency - Every 200 tonnes supplied.
c018b050-746d-525f-af0e-cbb375e80253 | note | Inspection Type (Visual, other) - Document review
a9319f6d-bb89-545f-85e5-5f1354af9de4 | note | Inspection: Key - H
df268e12-8417-53f8-b3fa-62ccfe1b6a2b | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Receiving Materials/Parts - Safety Barrier
| checkpoint | 3.4.1 - Barrier Mill Certs
4ca8caf2-e3d0-57dd-843b-e908025768e3 | note | Standard/Specification - NZTA M23 AS/NZS 3845
31037b77-85d2-559f-a32c-95f4b1dbcea7 | note | Acceptance Criteria - Compliance documentation
979de7a8-abb9-5f43-9751-33887e008a88 | note | Verifying Document - Mill Certs
8573636e-ba0f-5e5f-8766-5f84cb1870f0 | note | Frequency - Prior to commencement of works
49515c45-043f-5cdd-8c73-f705895db363 | note | Inspection Type (Visual, other) - Document review
f00e2c42-bb56-5f46-8432-5d375bb1440c | note | Inspection: Key - R
80d0f332-3e60-5c5c-b949-20cd77e226ea | note | Inspection: By - SE
| checkpoint | 3.4.2 - Concrete mix design
8cb7445e-1f1d-5d70-ad12-0194ec76a71e | note | Standard/Specification - As per Design Specification
3f69d689-8606-5fbc-96eb-c76c81c80717 | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
6c526965-a23c-5d35-8c11-efda407281d2 | note | Verifying Document - Concrete supplier mix designs
f56117b6-cb11-5db2-af10-85a9f3ae9011 | note | Frequency - Submitted to Client Engineer for approval before construction
b49865c6-b6d9-57e9-a196-575ca00ac527 | note | Inspection Type (Visual, other) - Document review
9bb64519-853d-51a4-aac2-200c3058d86d | note | Inspection: Key - H
7fc20ffc-3c73-5bd5-851d-343c3344d988 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 4.1 VMS Foundation with Plinth and cabinet pad - Construction
| checkpoint | 4.1.1 - Construction Location
0fc26a45-453f-5c29-a914-83ee1bdc22bb | note | Standard/Specification - Design Location
e0ab4673-5403-5e21-859c-2236d1550c42 | note | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
860c2b41-6d48-54cd-a25c-6ec2940d4599 | note | Verifying Document - Approval letter, Photos
4970450f-302e-518d-bdfe-4bf37a39cbae | note | Frequency - Prior to each foundation build
4a930f45-cc77-5034-ad51-c0f23c0a2e09 | note | Inspection Type (Visual, other) - Visual Inspection
5360d0e5-ea04-56aa-aac4-bc59dfc7d685 | note | Inspection: Key - V
1030e2f1-b383-54d4-a726-202eda00fc14 | note | Inspection: By - CR
| checkpoint | 4.1.2 - Ground Compaction Test
460a8151-0e50-54d5-89e6-4a574e36c949 | note | Standard/Specification - Downer Standard
1e0930fe-609a-53c7-b263-e2c2c2238f38 | note | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
bdd9f873-ed88-596c-b958-b543de492c76 | note | Verifying Document - Test reults, Location of Test
c99da392-9537-5317-9f16-b1c9f7a62c3b | note | Frequency - For each Foundation
d208e40c-7bcc-5a16-b6cd-12861323db60 | note | Inspection Type (Visual, other) - Check
6858c756-041b-5999-a531-ef1e40d9fab7 | note | Inspection: Key - C
6a4e5c82-708e-5964-8c9a-e55235112f8e | note | Inspection: By - SE
| checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
b96b7a0a-a50b-5ec7-ba5f-afd2d7314df7 | note | Standard/Specification - As per Design Specification
8c3ce9d8-c595-5945-b323-832f4090db87 | note | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
a3ee6a96-d5cb-5f0e-9945-85814239089a | note | Verifying Document - Pre pour, Photos
2ab46046-6e79-5630-8903-0ec3213e6e0d | note | Frequency - Prior to each foundation pour
35e25fd7-91ed-5af5-91b9-84d8b838c776 | note | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
3ee7bd84-329f-578e-abae-e1034a3ff362 | note | Inspection: Key - H
f8953abb-2a7c-58ea-a3fb-34abf1aac95d | note | Inspection: By - CR, SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
dbca843c-6073-52e4-a5cb-46bb4c637b2b | note | Standard/Specification - As per Design Specification
883fc8e2-d1c4-571a-babc-beeb05e42736 | note | Acceptance Criteria - Compliant with the construction drawings
c722f781-86de-5710-a956-6435001c7312 | note | Verifying Document - Pre pour, Photos
bd75c648-f6a6-5d25-aac7-bf35d6fa8e89 | note | Frequency - Prior to each foundation pour
207b678d-91e9-5322-add7-98d370dc11a1 | note | Inspection Type (Visual, other) - Visual Inspection
58f62cd4-59e1-55b0-9a5a-0e43dfdf2898 | note | Inspection: Key - H
561153c9-d568-5ac4-9e3a-19b138ab2739 | note | Inspection: By - CR, SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.5 - Pre-Pour Inspection
2b728140-874f-5194-9bcd-24fb15a7ca50 | note | Standard/Specification - Downer Standard
dcaa4f05-db01-535a-b75a-b5739a7551e3 | note | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
d6380559-17cf-527f-a485-c1333518bc39 | note | Verifying Document - Pre pour, Photos
e8872456-2061-5632-acf1-f093d1e87273 | note | Frequency - Prior to each foundation pour
377e18d4-1007-5f3b-bec6-5230d3c32793 | note | Inspection Type (Visual, other) - Visual Inspection
1a237e01-c2ba-5679-bc9b-c46c88389282 | note | Inspection: Key - H
a17bf911-85f5-5c5d-adca-38855c78a62d | note | Inspection: By - CR, SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Delivery Dockets
22946251-f9a3-54fe-8b5a-7c3fb59d97a3 | note | Standard/Specification - Downer Standard
dfab2c08-8a48-555b-8718-12f9d6e022cc | note | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
1e5278d7-319b-5684-8746-2763ccd5d11f | note | Verifying Document - Dockets
fa85baa8-4a13-5698-9dc3-cf00431f9b61 | note | Frequency - Each Pour
23f0f7e4-0a33-5583-bd28-1947b34958f7 | note | Inspection Type (Visual, other) - Review
c5dcd506-951d-5e09-b854-69e7855456ba | note | Inspection: Key - R
82e002e4-535a-524d-8669-ca7ffd81a12f | note | Inspection: By - SE
| checkpoint | 4.1.7 - Compression Testing
4f4765d2-528b-5ea5-ae71-ab9f5a4a5655 | note | Standard/Specification - As per Design Specification
480988e8-5f8f-5590-81e2-8b6269753f9d | note | Acceptance Criteria - One specimen from each pour shall be tested at 28 days.
c7c73f3a-213e-5082-9eb4-5e446a947974 | note | Verifying Document - Test Results
924544cf-2f3d-5f08-a171-2c2f09a9437b | note | Frequency - one test per 50m³/per pour
89fefacd-1029-5c19-a34e-1ddff17983e5 | note | Inspection Type (Visual, other) - Review
0a294fbf-351d-5d7d-90ac-b4393c5815f8 | note | Inspection: Key - R
cf082c0f-582e-5f7e-abb4-e916122faed0 | note | Inspection: By - SE
| checkpoint | 4.1.8 - Post Pour Inspection
76396d3b-7518-5f67-99a8-d31c446beb6b | note | Standard/Specification - Downer Standard
b0f81971-6e42-57e5-abd9-c37ffc69824d | note | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
0f97b485-5c2d-50e8-b2e2-59f9daff88c6 | note | Verifying Document - Post Pour, Photos
5a349e49-f3d3-5de1-a04a-54335e02de29 | note | Frequency - Each Pour
69eb2e47-9205-555b-a0bd-32e3c1dd496b | note | Inspection Type (Visual, other) - Visual Inspection
e51968dc-aced-56fa-9641-6fb8e3e0014d | note | Inspection: Key - R
ae48e476-906b-531c-84c5-36fe8d4671c1 | note | Inspection: By - SE
| checkpoint | 4.1.9 - Defective Concrete Finishes
cf9efce0-d016-521f-92b3-a2da95c429ee | note | Standard/Specification - Downer Standard
a46b95b4-cf2a-5607-8ba8-617a67d2a95f | note | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
ea45384d-faea-5c8c-b6b5-3ed33782c2c3 | note | Verifying Document - NCR
9be0f913-98de-5b20-81a5-196232d8e748 | note | Frequency - Prior to minor repair
4b983b73-edce-5f1b-be18-4f1a0c35b03d | note | Inspection Type (Visual, other) - Review
2acfb432-5880-5610-8bbc-240cc9db2a25 | note | Inspection: Key - A
3a48e665-0ff0-5050-b2f0-303bff591e37 | note | Inspection: By - SE
| section | 4.2 Shoulder Widening and Sealing - Construction
| checkpoint | 4.2.1 - Material Placement
b9c498ac-3884-5600-8d7e-3e94defdc617 | note | Standard/Specification - Downer Standard
4b6ace3c-f323-5a16-99f1-48d6f6932bf1 | note | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
e3ce0160-2503-551e-811a-1006522adda0 | note | Verifying Document - Survey / Level Checks
ee758110-0172-537c-af2c-6eeaa7d452b6 | note | Frequency - Continuous monitoring.
01150436-f80d-581c-a9fd-99f569517a70 | note | Inspection Type (Visual, other) - Check
ddc926f3-125b-5d40-9641-df0216dbcc6a | note | Inspection: Key - C
4b0e0dfb-87c7-5ff5-9640-00c926d3b36d | note | Inspection: By - SV, PS
| checkpoint | 4.2.2 - Pavement Shoulder Widening
b7a4e9d3-b4a3-5214-86a7-a71601b36552 | note | Standard/Specification - Design Specification, Appendix E, Section 2.1.4
60f676cd-65e2-5118-b531-12d54da68ad0 | note | Acceptance Criteria - Pavement sholder widening treatment will be confirmed with Engineer on site
82bf7a2e-88df-5d77-8360-ffd0e3840e63 | note | Verifying Document - Approval letter, Photos
bcf3978f-5b7f-5f92-a099-0431b023719e | note | Frequency - Prior to construction
0860543d-a34a-58bc-84b1-8681bff4e968 | note | Inspection Type (Visual, other) - Visual Inspection
d401e35a-9513-53cc-86f3-102a454b5d1d | note | Inspection: Key - V
d6379f2f-5cad-5673-9611-acd961c3bad1 | note | Inspection: By - CR
| checkpoint | 4.2.3 - Sub-basecourse Pavement Layer Compaction (NDM)
7370183e-c03d-5ee0-9a9f-5e6cb4347743 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
c3366f60-e3c2-552e-9b77-d18f11380600 | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
7fa33881-bf21-557c-8d6f-4b79053f58f8 | note | Verifying Document - NDM Report
1a8931ca-d4c1-5059-880e-b73caf572f38 | note | Frequency - 1/10m
cdf69064-428f-5833-881c-f5b69e10c0ea | note | Inspection Type (Visual, other) - Check
e69378af-3e90-5ab1-b04b-4e39f5344378 | note | Inspection: Key - H
63ba5535-1aff-5de5-9fee-190906c2c7ba | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.4 - Sub-basecourse Layer thickness
8a39d44d-aa44-5084-b4cc-a310f2d7d514 | note | Standard/Specification - TNZ B/02: 2005 - 5.1
2cc3cc06-1daa-501a-964f-97e7ff11bcd7 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
1ff580e9-fc09-5082-a79d-256a75be31b4 | note | Verifying Document - Survey / Level Checks
f4aa08cd-3286-5cc2-ab79-dc9783909951 | note | Frequency - 1/20m Full width
23ce93a2-305b-5459-a0b7-649560892625 | note | Inspection Type (Visual, other) - Dimensional Inspection
7e9913d9-6259-5844-b1f6-d86a01f720b1 | note | Inspection: Key - D
5cff7ea7-1c0b-543e-874a-e3c02d40fcf7 | note | Inspection: By - SV or SE
| checkpoint | 4.2.5 - Basecourse Pavement Layer Compaction
d4b1f239-bfde-5b05-8d98-ab3d74960e6d | note | Standard/Specification - TNZ B/02: 2005 - 7.6
1ca96846-533e-52aa-86d0-064851390949 | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
8c179a9b-6a1c-5d55-a4c6-6f2031ffa62a | note | Verifying Document - NDM Report
386f0529-39fc-5ad3-9ea9-af0570e164f2 | note | Frequency - 1/10m
03b11a6f-4949-5595-a29f-40f6a60981f0 | note | Inspection Type (Visual, other) - Check
a87cee9e-c527-59fe-868d-667cea553182 | note | Inspection: Key - H
701beef6-698b-5318-95b1-6ad38a06eb99 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.6 - Basecourse Layer thickness.
611e68be-f091-57d8-8149-0528f9d43a63 | note | Standard/Specification - TNZ B/02: 2005 - 5.1
d2d52cad-6e34-5523-b1f6-8990635a6984 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
fc56295d-a19c-5120-a357-78718b41135f | note | Verifying Document - Survey / Level Checks
e9bf3525-5083-5260-9431-d310478fefef | note | Frequency - 1/20m Full width
3ac5630e-4983-53d4-8740-b5328d20b2ad | note | Inspection Type (Visual, other) - Dimensional Inspection
5f66ea5a-5bf2-5f45-a44d-80cae562ad90 | note | Inspection: Key - D
3e8ffd4d-c936-50ad-8c16-eb1eb6a2761f | note | Inspection: By - SV or SE
| checkpoint | 4.2.7 - Surface Shape
cfeb9e0d-9614-5b09-b943-a7f000ef1e2b | note | Standard/Specification - TNZ B/02: 2005 - 7.7
2e566993-c8ba-5aac-a945-1c180a66dd72 | note | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
d7e16bb0-b5f0-5b85-8641-7d0768c321d3 | note | Verifying Document - Survey / Straight edge Report
529ca1d0-2316-57db-af88-6e9e8bd197e7 | note | Frequency - 1/20m Full width prior to sealing
0da59106-c043-5185-8d64-85ad954a0f8a | note | Inspection Type (Visual, other) - Dimensional Inspection
5cb7084d-f58d-51b8-abdd-4bb91e569ab6 | note | Inspection: Key - D
af48a3d7-a59e-5a6a-b8fc-ff7f47991226 | note | Inspection: By - SV
| checkpoint | 4.2.8 - Surface Finish post sweeping
3caed24c-aa41-5b20-9931-cfe037bbaf01 | note | Standard/Specification - TNZ B/02: 2005 - 7.8
f74d328b-85b5-5a5e-b72f-a771929dcd8d | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
2591656b-9e56-5b14-b9e0-84da1c4e38f3 | note | Verifying Document - Photos
13517ff2-8036-56d2-97cf-75d363708c39 | note | Frequency - Prior to sealing
5adada97-27e0-5227-a70d-5ad8e0d53d59 | note | Inspection Type (Visual, other) - Visual Inspection
d7f606fe-9cb2-500f-a97f-aac487cc3716 | note | Inspection: Key - V
7d63bf24-b6a6-57d2-b101-e08bb9a017fe | note | Inspection: By - SE
| checkpoint | 4.2.9 - Preselling Requirements
ea33dac1-30f7-5429-9273-e319843bb74a | note | Standard/Specification - TNZ B/02: 2005 - 12
53d9409c-ae1d-55d4-bc63-ddf76505644b | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
d4b05851-91b0-5c6b-a6a2-2ed45a365fe5 | note | Verifying Document - NDM Report
e922031f-fef5-58e8-a791-87af3870a6b4 | note | Frequency - 1/10m
96460e59-eac3-5b71-a376-4c9a7ce6a5ec | note | Inspection Type (Visual, other) - Check
a53d7844-0e9d-5c89-8cac-1adb4ca9cf25 | note | Inspection: Key - C
9a85fc4b-f6da-55a7-93ce-a1af4df06bcf | note | Inspection: By - SE
| checkpoint | 4.2.10 - PreSeal inspection
a0efccc1-92cc-5471-ad11-7d203340bd5d | note | Standard/Specification - TNZ P3 TNZ B02
96e61f1e-a76b-5ec6-bf2e-139d3be57363 | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
b11004ae-59aa-5dac-9658-99912784bed6 | note | Verifying Document - Hold point Release, ITP Sign off
7a92a8db-872b-5ec1-99ac-481c82949f2f | note | Frequency - Prior to sealing
6412c0be-0b67-5537-9936-bc3eb3170623 | note | Inspection Type (Visual, other) - Check
1f64f5fb-d9fb-5899-a5ef-a2eec7cd055f | note | Inspection: Key - H
4738ec2e-9134-5bfc-95d1-cdc55eefbb8f | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.11 - Spray Temperature
9ede48b2-0504-519e-bdb3-e4420a0b93f2 | note | Standard/Specification - TNZ P3
3135b8c9-eada-536d-ba6c-2e5ef0369d41 | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
f1639653-ffa8-5467-b4d2-1d9bffcfb353 | note | Verifying Document - Sealing statement
1254ee60-c231-51e5-9b08-a98d4b3b5a26 | note | Frequency - Prior to sealing
82169b69-dd05-5d72-b559-f108871118fa | note | Inspection Type (Visual, other) - Check
4cfbc7af-f76e-503d-8dcb-740902f38572 | note | Inspection: Key - I
18743f08-e7ad-5a40-b623-df12b93d2955 | note | Inspection: By - SE
| checkpoint | 4.2.12 - Chip Application
af27f0a4-354f-50b3-a9d7-f3e3ac75f570 | note | Standard/Specification - TNZ P3
4a874892-0ea0-5f49-b9a0-43a9aea23083 | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
e4695404-49d8-56c8-b6f7-7d4fd04fab91 | note | Verifying Document - Sealing statement
0b9d7362-5a66-5349-8ef2-29312f676f0c | note | Frequency - For every spray run
9b248a87-ea59-5a3f-b2b9-f6cdc40571dc | note | Inspection Type (Visual, other) - Check
090d7525-9ef2-5343-b584-20d3850fc76b | note | Inspection: Key - I
1212f9a1-d55f-5a57-a346-9bb465194303 | note | Inspection: By - SE
| checkpoint | 4.2.13 - Post Seal Inspections
86ae039e-0c6d-5fc0-855e-4617a12cee78 | note | Standard/Specification - TNZ P3
517ff4ba-f977-5de3-ae5c-0bcec1844e15 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
6a88ffc9-8ed5-573b-9921-b75154fbc933 | note | Verifying Document - Engineers Acceptance
96ce73d0-a148-5365-ae06-bf09f8e8f488 | note | Frequency - Prior to TM Removal and After Final Sweeping
121ee648-67c7-5a97-9075-b6bf54bafe14 | note | Inspection Type (Visual, other) - Visual Inspection
5e4f51d5-4456-5dc4-bf3c-c8013bcf0ea2 | note | Inspection: Key - H
8cbefcff-2fd0-5328-90a8-d7962c399e62 | note | Inspection: By - SE, CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.14 - Chipseal Repairs
0b8bd98b-bf04-5eae-9b48-53991dfdcf77 | note | Standard/Specification - TNZ P3
e88e7342-d587-54c6-87a1-296f23c73815 | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
40b2f63c-9a9e-5c0a-8d36-e27d2efac0a7 | note | Verifying Document - Approved Repair Methodology
4905f80b-4e39-5602-83f1-9b309d9736a2 | note | Frequency - Prior to Repairs
fd0eb68e-b0bc-571d-abcf-2ae562065d93 | note | Inspection Type (Visual, other) - Review
74d4029f-54b6-52bf-b4c5-34aa70b049c2 | note | Inspection: Key - A
1707bb87-aee4-5b0e-897e-2ba476c60594 | note | Inspection: By - SE
| section | 4.3 Guardrail - Installation
| checkpoint | 4.3.1 - Guard rails - Location
a94f3a6d-256b-5699-9524-0fcf39d72922 | note | Standard/Specification - Design Specification, Appendix E, Section 2.1.3
9eb2a0c3-a817-5334-9540-7931741f4a1d | note | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
4ecc8e4e-9a05-534c-9786-875706557829 | note | Verifying Document - Approval letter, Photos
839fff3d-61a6-5f75-a07c-1cd6dfc7b3c1 | note | Frequency - Prior to construction
8ad46d45-ea79-5121-b4da-e06cfb917540 | note | Inspection Type (Visual, other) - Visual Inspection
6efe3883-275b-5c8f-8abf-eacc815761cd | note | Inspection: Key - V
dea89459-c563-5d20-93c8-f6d55db700b4 | note | Inspection: By - CR
| checkpoint | 4.3.2 - Guard rails - Installation & Checklist
d3dd3fb4-535a-545d-8543-ab5e0d15d869 | note | Standard/Specification - As per design specification
fda05de9-098d-52f3-b387-7c40ab090fc3 | note | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
cb8854bd-e5e9-5acb-a207-40a69e98fc09 | note | Verifying Document - Check Sheet DN-QC-06 Photos
733855ea-4afe-5448-b2e9-580616ab2043 | note | Frequency - For each site
061a395b-67d5-5ec9-8618-e128acc8175e | note | Inspection Type (Visual, other) - Visual Inspection
bc3bd77e-7e86-50dd-b3a4-6cc8a81390f7 | note | Inspection: Key - V
73101cc1-d0fa-5a59-b673-ee3e5a62b451 | note | Inspection: By - SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
8c22fb4f-faa7-555b-9e52-346b425071ef | note | Inspection Point: Quality Control Activity - Upon completion of works
487a3231-45f2-5b85-8463-43a73e345f73 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
3d0b01ff-8af9-5725-9a13-4617b328dd36 | note | Verifying Document - Closed-out NCR/Defects
00e68288-e9ad-59af-b097-9f2569241cca | note | Frequency - Post construction
1b760f0c-3008-59c5-9403-1115ba6f1000 | note | Inspection Type - Review
6a505c92-7a6f-56f6-95b0-ea077ec55115 | note | Inspection: Key - R
100e39bf-6475-5147-b188-246c87fe4003 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
dd53efe1-f69c-581f-b218-48762f0338f5 | note | Inspection Point: Quality Control Activity - Upon completion of works
8e1b09c0-c1c8-5594-9415-73f8ef7592dd | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
721cc1f3-576a-59aa-8dbe-f3f66ae85fbd | note | Verifying Document - As built survey record completed
0b018249-6a39-57e2-bbe1-f30b9d3a2192 | note | Frequency - Post construction
e8bbbb78-d9d7-5720-a0a7-7831e2ffe549 | note | Inspection Type - Review
6e6fbe01-d876-5f4f-bc41-38d1ede1d12d | note | Inspection: Key - R
6bf46ddd-30bf-5478-821e-929109397d64 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
9afe30d7-a91c-55a2-8f9c-0b18abc81b9d | note | Inspection Point: Quality Control Activity - Upon completion of works
aa190efd-4198-5197-ab19-2fbdd7c623f2 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
31f8952a-2715-5cca-a76b-786d731e13b7 | note | Verifying Document - Signed As-built Drawings
0f0155ac-7a02-50c2-9470-f46e367d5e9c | note | Frequency - Post construction
0c3ee392-0713-5fda-85f3-0ee4ea32aa06 | note | Inspection Type - Review
410d1e24-79a9-5fa5-9083-3b20b142c61a | note | Inspection: Key - R
355319b4-a1ce-53a1-a258-4999206e6f84 | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
d1d27996-f874-5e41-981d-b09105b4cc86 | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
f0497240-bcab-5527-8fb9-32f4e5e2758c | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
f62d5114-ff39-54f9-941b-eef618e74573 | note | Verifying Document - Register
2dd01cb6-f476-554e-b441-204320e675ac | note | Frequency - Post construction
b3bd8cf4-8acd-5dc3-9848-a9fbaf19457a | note | Inspection Type - Review
6439a6e2-a7bb-5711-b7cd-e2f447fff0f4 | note | Inspection: Key - R
87e1330f-ccf6-5cc7-932b-0bf5b4805a70 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
029ed6ba-c489-53a9-8f0a-095d7fd63afc | note | Inspection Point: Quality Control Activity - Upon completion of works
1eaacec6-a668-5678-a20a-b0da2b9b473a | note | Acceptance Criteria - All signed and closed out
0a56cf2f-0303-5456-bef9-a339295d764c | note | Verifying Document - Signed off Documents
3488abcb-b90a-5e99-9d01-232be2d476c6 | note | Frequency - Post construction
f0a94e6a-40bc-5fbf-9c2f-a612d66c455e | note | Inspection Type - Review
6fe7021b-e5c1-5f34-816a-d87dadfc82b0 | note | Inspection: Key - R
488590c4-23c1-53f8-a090-8ed58609584b | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0030_v1 (Signs and Furniture ITPs) | itp | 558020-DOW-ITP-PC-0030_v1 (Signs and Furniture ITPs) | 209d96d3-bc76-4529-b4f6-203e913ea699
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
15b5a3b6-f305-553f-92f4-041b936b0892 | note | Standard/Specification - Downer Standard
5f413d20-c484-5a3e-9812-4b819c061ea1 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
adc7bc7f-eb2d-5fe1-9e94-d2a807d3ed26 | note | Verifying Document - Survey Records
ac43d07a-5a47-5c25-8ada-3f6b9779d639 | note | Frequency - Prior to Works
fc479203-73ae-512e-872b-0cab0c88598c | note | Inspection Type (Visual, other) - Document review
b848798d-cc91-55d8-9470-662bfa2760d1 | note | Inspection: Key - H
3fbb42b8-f71b-50a3-b1f5-f135f6d3c49e | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
51f439a6-c14d-518f-a3c6-434318394273 | note | Standard/Specification - Downer Standard
226dcb07-9e9b-53af-b834-dd4cc43c43e7 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
1a54fe2e-8ec8-51a0-8bd3-eb58af5128bd | note | Verifying Document - Service location documents
c40c5628-4cfa-565e-8b2a-bbe84f31585c | note | Frequency - Prior to Works
f7995e13-6bff-5b02-815c-055a3cbce4fc | note | Inspection Type (Visual, other) - Document review
e7b4f176-d413-5839-b7db-10dbacb1af31 | note | Inspection: Key - R
675bb295-8e1e-51f6-a03f-d2ce0f4b4a99 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
da297fed-9eee-53ee-905d-833c743b911a | note | Standard/Specification - Downer Standard
43e57517-bcea-57e3-a40f-21f96ca35b23 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
e578d6a0-b1ee-55c4-9e6d-130ae88aa1ef | note | Verifying Document - Internal Permits
a17ddfb2-e7c0-50c7-a2a3-fdba31117a35 | note | Frequency - Prior to Excavation
112a89c8-3b8d-5cbc-a805-60b624ab0c0e | note | Inspection Type (Visual, other) - Document review
77ee7957-aaf3-54c0-9929-e1022040ef3d | note | Inspection: Key - R
d1468d73-410a-5475-b9f1-de0c5e3d8f8d | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
5f7102df-f9e0-59d7-9948-6a746fe4e8d5 | note | Standard/Specification - Downer Standard
b9158945-6d9d-58b0-9ee9-253ff666efd6 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
93c7c59c-359d-523e-b794-eb7d74a90f63 | note | Verifying Document - External Permits
e568c4f4-db2d-5c6c-a925-756d126c9b62 | note | Frequency - Prior to Excavation
2f4e92ab-993e-5bb6-a6a6-eec4a7da7096 | note | Inspection Type (Visual, other) - Document review
755be6dc-4337-5d42-adc1-934eeb7112b5 | note | Inspection: Key - R
3452b75b-ddd1-5c46-916c-f168bc0ee84b | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
784b878d-3fc0-559e-ace3-89d3febc82fc | note | Standard/Specification - As per contracts
3fd5172d-1f8e-5dca-be73-5b8198cd32d5 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
08ee3ba2-572b-5fdd-8058-c05929dd763e | note | Verifying Document - Approved ESCP plan
f486b2e9-c888-5496-825b-91c2f5359447 | note | Frequency - Prior to Works
8445c868-a8b5-5109-9942-2c943c104e13 | note | Inspection Type (Visual, other) - Document review
df3509c2-5453-500d-a442-17465e5a2198 | note | Inspection: Key - R
161bbc59-7312-579e-8f15-409761af04d6 | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
1a2b8e3d-cd49-53e2-9f5d-0cdccf516f3b | note | Standard/Specification - Downer Standard
3628f919-ad57-543f-a50f-c5f8c2fb2b2d | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9998aaca-1a0b-5056-bdd5-995382182074 | note | Verifying Document - IFC Drawings
96653fbc-0896-504f-889f-ece65f52143d | note | Frequency - Prior to works start
d1cb93ba-7116-5246-b482-2a3627cd2b1a | note | Inspection Type (Visual, other) - Document review
e8bdb90c-fd15-57a5-bccc-b2612961b080 | note | Inspection: Key - R
25555e49-f1f5-55ee-8e6f-86db73e429ca | note | Inspection: By - SE
| section | 3.2 Signage - Incoming Materials
| checkpoint | 3.2.1 - General
de3824b0-ed1c-547c-b044-6c8defe45509 | note | Standard/Specification - NZTA manuals, NZTA P/30
a6a4161c-7aed-5d5d-ad41-1620dfb7c4de | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
8932fb90-5309-548a-80c0-799ad908506e | note | Verifying Document - IFC Drawings, Sheet No. C-2510
06dd765a-a3cc-5818-a14a-0a07ab5bfd92 | note | Frequency - All
a1a6429f-b098-5714-a8db-7bff8dc6b878 | note | Inspection Type (Visual, other) - Document review
5fc97e84-9c4b-51ba-91b3-5301205ed568 | note | Inspection: Key - R
d6a006b2-92c3-5d5a-8a45-9210734719b6 | note | Inspection: By (Role Key) - SE
| section | 4.1 Signage and Marking - General Notes
| checkpoint | 4.1.1 - General
9d225b17-afba-575b-8358-3a2fccd68d16 | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
d3bd3a77-807b-5859-bfaf-d21470dbfc24 | note | Acceptance Criteria - All signs and markings are to comply with MOTSAM
4e66d574-f3c2-58c4-a8ac-60faaab65e3c | note | Verifying Document - Photos
3b1f185a-7ea6-51df-857d-78ef992db427 | note | Frequency - All
07aa703c-08c7-566e-bfa8-b3523bc7b905 | note | Inspection Type (Visual, other) - Visual
ccd83fb9-2033-500a-8570-a1ef277424dd | note | Inspection: Key - V
ac486ef5-aa88-52d1-b305-89cda52c9650 | note | Inspection: By - SE
| checkpoint | 4.1.2 - General
3c26c1ea-dd92-51fb-a8e2-f9e2f9b6d79b | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
97460552-b31a-5751-b01f-603e9c82d162 | note | Acceptance Criteria - Sign positions are to be agreed with the Engineer on site
28ce1b09-91c2-53e8-adcc-0649c28e0100 | note | Verifying Document - Photos
f2bdd8c8-2739-537c-b21c-f36616df0c79 | note | Frequency - All
f5c0c48d-201b-577b-9511-269af8cdef12 | note | Inspection Type (Visual, other) - Visual
aa6318be-6d46-5309-aea0-124f2922601e | note | Inspection: Key - V
9b5d2750-e236-5235-aff8-0258cb41a8bb | note | Inspection: By - SE
| checkpoint | 4.1.3 - General
33dfe69f-1fe8-5fe2-bec7-885d8b7566e1 | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
49e3dc18-9849-5918-976b-f0da9eab6616 | note | Acceptance Criteria - All redundant road markings to be removed by water blasting. Residue from the water blasting is tobe removed by the contractor.
d4de5780-bad9-5525-9afc-8ea5eff249bc | note | Verifying Document - Photos
7a42b44c-3146-561a-ab4c-ed1fe79229f1 | note | Frequency - All
e2cb2748-51ca-5ed0-9188-6daacde1ebed | note | Inspection Type (Visual, other) - Visual
3076d84f-ace7-5f1f-b8b0-9663f205c715 | note | Inspection: Key - V
6872ea6d-54b3-5abb-b768-0f727db5bd84 | note | Inspection: By - SE
| checkpoint | 4.1.4 - General
b5603a03-b02f-5ede-98b6-dbc372a8e1e0 | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
25954ca6-891f-5227-b26d-0ccc115e9e8b | note | Acceptance Criteria - Unless otherwise indicated, all signs and bollards are to have a minimum of 500mm clearance from the kerb face to the edge of the sign/bollard.
22f76130-0734-57a1-ada1-cd22fbadcf33 | note | Verifying Document - Photos
377c1a49-9a50-570c-8be4-2a26dbc99aa2 | note | Frequency - All
ce06e5a3-fdc5-5fb6-8f86-94e988423fac | note | Inspection Type (Visual, other) - Visual
37a4f125-ee93-5cbe-beb5-219e47c100c1 | note | Inspection: Key - V
13aeb449-9cd4-59f3-ba70-bba1d18468ca | note | Inspection: By - SE
| checkpoint | 4.1.5 - General
aa645236-9cab-5653-87c0-de1d236097c7 | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
d5beec72-1155-5bfc-917d-60fb195ebdf0 | note | Acceptance Criteria - All road markings are to be a minimum of 300mm from the kerb
edf15f2c-3f8f-5e56-9e63-7339572af31a | note | Verifying Document - Photos
88f3a5c4-057d-5155-ad21-647bdc9f17ff | note | Frequency - All
90a62633-1a2f-57d7-8163-e1c67ade4382 | note | Inspection Type (Visual, other) - Visual
90257de7-588e-53c7-a921-01ac67b0cc48 | note | Inspection: Key - V
f0da3aa2-ef54-5d31-91f1-5eb4166501c8 | note | Inspection: By - SE
| checkpoint | 4.1.6 - General
c5c0c4ad-7510-57cf-8cff-18735b1a28ec | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
598f0c25-89d4-5cbe-a6fe-3df5d50a6bb7 | note | Acceptance Criteria - All existing remaining road markings disturbed by the works are to be reinstated.
e44b8864-e581-56dc-9e03-088c546f6d11 | note | Verifying Document - Photos
191f9fa5-511c-55b9-8af0-98abc536dd30 | note | Frequency - All
de64ba88-3bd9-507a-99d8-c89052ceb75f | note | Inspection Type (Visual, other) - Visual
17c38c3f-34ee-5cde-9d92-8e5d909dd7bf | note | Inspection: Key - V
d748b7c7-f923-5639-a500-148a1e074a56 | note | Inspection: By - SE
| checkpoint | 4.1.7 - General
1f0f8b4e-0744-5bfa-9d4d-e2767aa5b9bf | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
c365e7a3-3db2-52a3-8ad7-57302cdc5448 | note | Acceptance Criteria - All existing pavement markings to be reinstated unless approved by principles representative.
76c6ad00-2412-5d7c-859a-9da2562e47cd | note | Verifying Document - Photos
9b706170-9ab4-5754-ac70-8ec4d7877856 | note | Frequency - All
06336e3a-4f5a-5029-9f6e-52ec9fcec4eb | note | Inspection Type (Visual, other) - Visual
609b8ea3-4980-55ec-9816-54a0be928fe9 | note | Inspection: Key - V
63781ddd-02f8-51c2-8ba4-a0fc754f9e95 | note | Inspection: By - SE
| checkpoint | 4.1.8 - General
5ce1f0c9-a06c-58c6-b141-fe007c8a2e45 | note | Standard/Specification - IFC Drawings, Sheet No. C-0300
2c128d38-2cf0-5c17-b972-0c507eaf3ec6 | note | Acceptance Criteria - New line markings to join neatly to existing line marking at limit of works.
3b721626-3ec8-5603-88e9-d8b859529a3d | note | Verifying Document - Photos
bddd5ae0-88cb-5381-9d05-7d566713b38f | note | Frequency - All
1025692d-3d28-5339-a736-687d8ccc5ca5 | note | Inspection Type (Visual, other) - Visual
e98ee9bd-6293-5e82-942c-474ebb6c5786 | note | Inspection: Key - V
404c25e1-1298-5a21-8526-c68f6f65ad48 | note | Inspection: By - SE
| section | 4.2 Signage and Marking - Southbound Approach WIM Site
| checkpoint | 4.2.1 - Signs and Markings
7612f0aa-bae7-547f-bfc0-7435749d1dc0 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
7d567af1-0793-5dd7-8e24-27b2fa5a2570 | note | Acceptance Criteria - Manual of Traffic Signs and Markings.
ec88fca6-5db2-510a-b862-f52d9f9d46ba | note | ○ Part 1: Signs
7681e440-4867-57d5-bfea-b009ff5070b7 | note | ○ Part 2: Markings
a2095a94-d2d7-5d54-99c5-920f17507e73 | note | Verifying Document - Photos
279dc388-6e00-5d41-9c3b-156b837e65dd | note | Frequency - All
a7a66109-80ba-50e8-89ef-1fdce14420ca | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
de4dfee1-8fd2-5290-849d-eabe89e1c2b6 | note | Inspection: Key - D,V
c7cf6768-ac73-5d73-8040-a273ab06642c | note | Inspection: By - SV, SE
| checkpoint | 4.2.2 - Reflectorised Markings
101db8d6-177e-5c57-a151-dd01f6ed4f34 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
2b5d94b7-e37e-54d9-8b50-8dd5da7f1012 | note | Acceptance Criteria - Refer to IFC drawings
28523bb7-e246-5ee3-83ba-61f20e952177 | note | Verifying Document - Photos
139cb4d6-e822-51c2-ab2f-fb128cafb1d7 | note | Frequency - All
6d504444-81b8-5006-9298-1f839d6ef3e9 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
dbd26011-fefa-55dd-8a3d-da595951d8b2 | note | Inspection: Key - D,V
1ab6e672-8578-5366-a863-6e1e0b7fca26 | note | Inspection: By - SV, SE
| checkpoint | 4.2.3 - Raised Pavement Markers
eb6f62cf-0f72-55cf-830e-f945356d1329 | note | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
909dec1d-5270-5f59-bd9f-0da91675dfd1 | note | Acceptance Criteria - Refer to IFC drawings
bd709559-1978-5d0f-ae32-752bff972a7e | note | Verifying Document - Photos
4583d906-39d0-5e53-891a-30ee8eed57ef | note | Frequency - All
94bfbbd2-106a-52e2-a096-e4cb73bfa2e0 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
0dcd7549-2f8b-5368-9a33-3087c6794d47 | note | Inspection: Key - D,V
a3947f80-9e75-5228-a056-eb9e8d8ad7ad | note | Inspection: By - SV, SE
| checkpoint | 4.2.4 - No Cycling Signage
c8d923cc-12ad-5fdc-93e1-3fe9cadd0f10 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
b3611cb1-367e-5f04-ba3e-e314e969fb2c | note | Acceptance Criteria - Relocate existing RG24 no bicycles symbol sign
a2122dca-b812-5d73-8d9b-bf6cc626a7f7 | note | Verifying Document - Photos
351f61df-be34-5fea-ab36-d13986e59e3d | note | Frequency - All
05133a81-24b2-56c1-a03a-4a33f71a57be | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
c233b8de-1cda-5572-b26b-c598966d7904 | note | Inspection: Key - D,V
46df640b-6ae8-585a-8b38-c3e2677d1f12 | note | Inspection: By - SV, SE
| checkpoint | 4.2.5 - Sign Poles
c8b7a6b7-c913-52ca-9892-31b93309972f | note | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
475391ed-ac0e-5cee-9834-baa50084381d | note | Acceptance Criteria - All poles must be fluted alluminium
00dbe0df-a518-5254-828c-41466ddacf4b | note | Verifying Document - Photos
082dc680-2f84-5417-9d1d-6ecaf94a1be6 | note | Frequency - All
43148d59-c8a2-5137-b553-140d9a7e673a | note | Inspection Type (Visual, other) - Visual
8ea016b2-5df3-5737-a90f-811099980357 | note | Inspection: Key - V
25ff461d-8fe7-5268-aa81-c242c32c98f3 | note | Inspection: By - SE
| section | 4.3 Signage and Marking - Southbound Approach VMS Site
| checkpoint | 4.3.1 - Signs and Markings
b796ba1b-424a-5bea-a50c-eca2c61a953a | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
a623dfae-f453-5a0a-859e-5f74c5fe8be7 | note | Acceptance Criteria - Manual of Traffic Signs and Markings.
d9b88751-42eb-590b-9a8d-ba5c47b2c807 | note | ○ Part 1: Signs
6b8ff8b5-748a-53a2-84cb-04256d2ea823 | note | ○ Part 2: Markings
f29deb30-4fec-5785-b120-e81fc7683568 | note | Verifying Document - Photos
fd3eba65-3b07-59ad-9217-cf4c9cf21b41 | note | Frequency - All
9049d1ae-5f82-502b-897c-54faeac143e8 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
50e58e15-6791-5a80-afad-934aaa8185eb | note | Inspection: Key - D,V
10d32760-364c-5bed-aa0e-48c8972ee4d6 | note | Inspection: By - SV, SE
| checkpoint | 4.3.2 - Reflectorised Markings
a98731be-d200-5296-b4fc-f4330478b771 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
55fc2bb7-76e0-50e4-9361-704ecedb6870 | note | Acceptance Criteria - Refer to IFC drawings
ed8b52e0-e2a1-558f-9995-77c86a379a48 | note | Verifying Document - Photos
7a52c5d6-400a-5072-8c57-51bd3b976875 | note | Frequency - All
68739e3a-bbe8-5db1-b2ba-1ba7013469ce | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
41b535df-090a-5945-90b2-3efac027d893 | note | Inspection: Key - D,V
e031fba5-0e9b-589b-8851-140934a6ebd4 | note | Inspection: By - SV, SE
| checkpoint | 4.3.3 - Raised Pavement Markers
cd2f2655-9fb4-50c4-824b-8a5ea1f47bee | note | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
fc3558f6-6837-524f-b3fb-f121cd116664 | note | Acceptance Criteria - Refer to IFC drawings
555fb311-b5e7-5a5f-9752-bc61eb97b1bd | note | Verifying Document - Photos
100f6552-c7b0-52e6-87ab-f389143d8433 | note | Frequency - All
b8eac97a-dfde-51f8-9f56-b8d002174310 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
7d7b0f6c-98fa-50ed-9ba5-5031512ce9b4 | note | Inspection: Key - D,V
14534044-1a19-588f-b693-1e458484fe90 | note | Inspection: By - SV, SE
| checkpoint | 4.3.4 - Sign Poles
28825e36-e81f-5f4b-90ee-d31abe121d78 | note | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
10457d1e-c3c6-5928-8067-9c87e7c13c02 | note | Acceptance Criteria - All poles must be fluted alluminium
c6d7751f-1055-5ea8-845d-08a973234880 | note | Verifying Document - Photos
64c782f3-6691-5b35-9b23-17408ea3b362 | note | Frequency - All
4a880674-6515-5a2b-b139-41b568fbc860 | note | Inspection Type (Visual, other) - Visual
21a55b51-b5dc-523c-a840-4416a9db3a50 | note | Inspection: Key - V
174eba57-3102-5a83-9a6e-147482696312 | note | Inspection: By - SE
| section | 4.4 Signage and Marking - Northbound Approach WIM Site
| checkpoint | 4.4.1 - Signs and Markings
21edb19f-62a4-5444-9c58-52fce7e2f1e8 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
e2ce1481-f5f1-5497-8952-17efad9498d5 | note | Acceptance Criteria - Manual of Traffic Signs and Markings.
46eb8097-e242-5842-a884-ee7c9b0040e4 | note | ○ Part 1: Signs
ddcc57bf-9e50-5915-a88c-94e9cc6cb69b | note | ○ Part 2: Markings
0e200869-1131-51a6-a4e5-5312151a2fd1 | note | Verifying Document - Photos
d7682938-704a-5f0a-8158-ed35fc204d53 | note | Frequency - All
79b06141-d61a-5e43-a32f-21861626fcf7 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
ad0ef267-6928-51e6-bc62-0ffd20d40cac | note | Inspection: Key - D,V
1cc34beb-ad61-57f3-ab02-fc60d3face63 | note | Inspection: By - SV, SE
| checkpoint | 4.4.2 - Reflectorised Markings
2baa3412-ceb2-58c7-b5f5-7a21a3364890 | note | Standard/Specification - NZTA Manuals, NZTA P/30, IFC Drawings, Sheet No. C-2510
1701f73b-a0a0-507d-9abd-d64d00740e29 | note | Acceptance Criteria - Refer to IFC drawings
26c09661-421e-5899-a78f-cf13288f4f06 | note | Verifying Document - Photos
902ec163-f872-5351-92d0-a2b1e71ed4b3 | note | Frequency - All
0b3c0158-6740-5117-b916-f890c266e0e2 | note | Inspection Type (Visual, other) - Dimension Inspection Visual
a201a5e6-1662-5245-879a-7cd0d0429b3a | note | Inspection: Key - D,V
6cfdd2bb-7696-5dfa-a410-dacc83c084b3 | note | Inspection: By - SV, SE
| checkpoint | 4.4.3 - Raised Pavement Markers
a084a207-ab45-5d84-b207-c3b5f3aa01f6 | note | Standard/Specification - MOTSAM, IFC Drawings, Sheet No. C-2510
b923048f-7914-504e-998b-5bc2a07194b2 | note | Acceptance Criteria - Refer to IFC drawings
305ba9d3-f686-5918-8fec-5dd7b9f3eb1a | note | Verifying Document - Photos
d06c29fe-76cd-55d6-981c-ef6036c5c7d5 | note | Frequency - All
1f2b8a0d-d583-5cb2-b793-41d0d3f10974 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
31abfb7a-fe2d-52e8-b917-3db18c581310 | note | Inspection: Key - D,V
9e57b20a-c6a2-583c-a954-38a601940d7c | note | Inspection: By - SV, SE
| checkpoint | 4.4.4 - Sign Poles
b582128f-ff9e-5f4b-8318-9a03345ccf59 | note | Standard/Specification - NZTA Manual of Traffic Signs, Project Specification, Section 5.4
e6ddb1a3-0659-5636-903c-5fa94be30953 | note | Acceptance Criteria - All poles must be fluted alluminium
e54ef26d-60a0-55a8-9548-3f9810c22a19 | note | Verifying Document - Photos
4fd53072-322b-58a4-9e4a-5b3630aa20df | note | Frequency - All
ecfd3635-2982-5db7-962e-d3a73886a5cb | note | Inspection Type (Visual, other) - Visual
386d6677-c003-5423-90a8-421980b8c082 | note | Inspection: Key - V
ad1bdd60-d9b1-51e7-a127-6f7930d7b23b | note | Inspection: By - SE
| section | 4.5 Signage and Marking - Static Signage
| checkpoint | 4.5.1 - During Roundabout Construction
26822795-f7c3-5b8b-83fb-dc49eb9b6446 | note | Standard/Specification - IFC Drawings, Sheet No. C-7000
3c0bdc76-0248-5bbf-a67f-8b2ca7f2b0f2 | note | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details during the construction of the roundabout.
1d34b9d9-7130-51c8-8bf7-de2b0a66b536 | note | Verifying Document - Photos
16c9f45a-b252-50c8-b16f-9e8c0100f254 | note | Frequency - All
b89dd7d2-88b8-5896-a048-2e45c685a211 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
fd3abbb0-e8cc-5919-98fd-71013d77027e | note | Inspection: Key - D,V
83ddf2e8-0b62-5680-ae27-ad072bc532e4 | note | Inspection: By - SV, SE
| checkpoint | 4.5.2 - After Roundabout Construction
4ec32c8a-ebb8-5679-a5de-768df12978f2 | note | Standard/Specification - IFC Drawings, Sheet No. C-7001
6d3e214e-6675-5f91-aa95-70f5a41d2f94 | note | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details after the construction of the roundabout.
16acf711-bec9-55da-af33-c3b0592b18cd | note | Verifying Document - Photos
f33ec8fa-925d-59a4-b304-f8cdb4c4b4bd | note | Frequency - All
b8326a2d-9a7d-57b5-86e7-101f1462e23e | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
9b838979-3d7b-5d15-ba13-9a31e9a81464 | note | Inspection: Key - D,V
7289d044-8e8b-5398-ba8e-4909b1469106 | note | Inspection: By - SV, SE
| section | 4.6 Signage and Marking - Commercial Vehicle Safety Centre (CVSC)
| checkpoint | 4.6.1 - CVSC - Detailed Plan
41fa2137-dfa8-5790-97fe-ae9c78e609c0 | note | Standard/Specification - IFC Drawings, Sheet No. C-7011
73723e6c-be63-5562-9ae8-0c171e3b2b21 | note | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility.
9d380440-0926-532a-9102-52fb9e693aaa | note | ○ All dimensions and requirements are listed within the Legend of the drawing.
c046caf1-d5a9-5dec-b1d4-fd141d30d3db | note | Verifying Document - Photos
a85076d2-0516-5976-9bcb-6e33ffff9fa6 | note | Frequency - All
a0386117-ad46-5cb1-966d-8953be08a30c | note | Inspection Type (Visual, other) - Visual
80d27674-70b5-54a5-a849-def9c744ff92 | note | Inspection: Key - V
4c15f989-df65-59ac-8b8c-b713fd676326 | note | Inspection: By - SE
| checkpoint | 4.6.2 - CVSC - Detailed Plan
71e634fe-50c1-504f-9f70-6b92d876b163 | note | Standard/Specification - IFC Drawings, Sheet No. C-7012
09f809d3-d355-5345-8572-91206fbf3faf | note | Acceptance Criteria - Refer to IFC drawing to reference the sign and marking details for the CVSC facility.
2644af84-043e-54ac-a8e8-b333a5ac5827 | note | ○ All dimensions and requirements are listed within the Legend of the drawing.
b199f4c5-1989-587f-8d7e-7537b437c9ba | note | Verifying Document - Photos
4780dbe6-316e-5e06-931e-f99a6a092693 | note | Frequency - All
4a626696-cb27-5058-986d-2dbfe2d81c4b | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
8297f0fc-c1a4-5005-88d9-8f97fd460925 | note | Inspection: Key - D,V
1f70519a-7be1-5bfd-bb79-23e8ff8ebfaa | note | Inspection: By - SV, SE
| checkpoint | 4.6.3 - Sign Details and Dimensions
8f063f0b-bc7d-5c91-8d1a-09183a890460 | note | Standard/Specification - IFC Drawings, Sheet No. C-7100 and C-7101
8b2c984b-11f7-5029-af1b-183db497ed12 | note | Acceptance Criteria - - Legend is series E 125 unless stated otherwise
df4af1c6-c014-5c55-8a3b-d6059dc07002 | note | ○ Contractor to organise for shop drawings of traffic signs to be in accordance with the Traffic Control Devices manual and manual of Traffic Signs and Road Markings
d2aee1b5-0774-5bc3-bd2d-1d8cb5a65a45 | note | ○ Traffic sign posts to be in accordance with RSMA
53135ea5-cdaf-53b4-826d-ea976b584b6e | note | ○ All measurements are in millimeters unless otherwise stated
2ba65ae1-24f3-5e67-87af-b706409daf5e | note | Verifying Document - Photos
3f5d2cff-63a6-5484-b0a8-795d41399953 | note | Frequency - All
1ed03e04-73a3-54d8-bfab-7c09d1d433c4 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
a5170701-3b5f-503f-a515-f98472fff08a | note | Inspection: Key - D,V
4194e2bf-965e-57a6-b2f2-e9a0fb4bd886 | note | Inspection: By - SV, SE
| section | FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - Construction Record Compilation
1894db40-27ca-529e-a9fa-f538d956aca0 | note | Inspection Point: Quality Control Activity - Upon completion of works
d80c811e-22bd-5514-896c-80fd8063b705 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
be72658a-7fba-5a38-a54e-b20cffc0f7ae | note | Verifying Document - Closed-out NCR/Defects
ea32dcd1-2c36-5f7e-8ad6-d2d7cde46354 | note | Frequency - Post construction
6624ad2e-f84d-5b45-995e-67c87f5c16da | note | Inspection Type - Review
76c4767b-7acb-5947-92a9-3144845b4d98 | note | Inspection: Key - R
e10711ba-07d3-5235-be5c-3e0d1f6307e1 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
e0aa2e96-cda6-5f35-bb7f-8c87612ea7d2 | note | Inspection Point: Quality Control Activity - Upon completion of works
a3fb3335-d114-5379-b0ce-6c3389da505c | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
a0d2a9fc-7311-5d41-928b-c3d7ff4d3965 | note | Verifying Document - As built survey record completed
431834ab-2a82-57f0-8d54-1c36214ccdcb | note | Frequency - Post construction
8b666bba-31ef-55c1-928e-a2223099d9be | note | Inspection Type - Review
3e6b520c-4835-5e8c-9e68-8aa7e0b570e4 | note | Inspection: Key - R
61034d76-e423-5e10-ae1d-aa176225ba73 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
0911cc9d-0875-5716-8368-03c923cef9bf | note | Inspection Point: Quality Control Activity - Upon completion of works
263e7568-0448-5aed-98e6-45afe2bdc1b3 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
3f6bc590-38d4-5145-8d42-5c9f31f30b2e | note | Verifying Document - Signed As-built Drawings
89ed0819-ffeb-59ec-be9d-98eb5e41334c | note | Frequency - Post construction
fdac1706-36c7-5762-a48c-f4dd18bcdbbe | note | Inspection Type - Review
a2a60069-4b91-5bce-950c-9d0ab1fd2e43 | note | Inspection: Key - R
8fea0d5d-c0df-572d-b6b7-09b71043761a | note | Inspection: By - SE, SV
| checkpoint | 5.4 - Defect, Snag and Punch List
913ddecd-9857-5bd2-8fdb-4f72cb97189d | note | Inspection Point: Quality Control Activity - Defect, Snag and Punch List
27d8b3ef-88b5-5dc5-97b0-bb5d954cd7c1 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
0e54ae63-4d3d-52dc-9476-2fec4b8424b9 | note | Verifying Document - Register
4fceba29-88b0-5fd7-8a26-a790f8fbd934 | note | Frequency - Post construction
e767ce96-71e3-55dc-a833-bcd3ffec58af | note | Inspection Type - Review
de2953af-17ab-5055-b2f1-5a3844cb2507 | note | Inspection: Key - R
424229e8-c491-5a5f-9304-0f076f39ac03 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
a513b9d2-233e-523f-b96f-7d13acab4789 | note | Inspection Point: Quality Control Activity - Upon completion of works
382898bf-f874-5014-bf0a-1a5776c26e5c | note | Acceptance Criteria - All signed and closed out
359d2de9-c43d-5841-bc6e-ad025e56908f | note | Verifying Document - Signed off Documents
4c473178-289f-540e-ba64-b946ae902ee5 | note | Frequency - Post construction
decded61-9172-571f-ad85-144b1f9a78bb | note | Inspection Type - Review
c61a7437-6819-5e4e-8942-a1f7f1c7ce20 | note | Inspection: Key - R
d1084aac-e653-58cf-9e8a-a642dbc89260 | note | Inspection: By - QM
| checklist | 558020-DOW-ITP-PC-0031_v3 (WIM South) | itp | 558020-DOW-ITP-PC-0031_v3 (WIM South) | 0000f504-7b81-466f-b5e6-cc40216af71f
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
0cccf801-9177-5846-a9c6-83e61efcc937 | note | Standard/Specification - Downer
3f566eec-f380-5532-a642-2358c11630c8 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
e9dd6426-61c8-511f-92fe-337527e4ea3d | note | Verifying Document - Survey Records
d4261c91-6e9e-51ae-a055-50d7745f54c5 | note | Frequency - Prior to Works
7320c15c-98b9-5aef-8257-9570f4d4957d | note | Inspection Type (Visual, other) - Document review
066e13d7-c7d1-59e7-9ee4-ad9cd992b564 | note | Inspection: Key - H
79206745-21c1-54c5-9a0f-f6930634f260 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
37db69b7-850a-5b18-892f-2041640025ce | note | Standard/Specification - Downer
7257483f-306d-53c6-9057-5b1cdfdf3531 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
d9294a4c-7629-5c22-864f-67d0042af303 | note | Verifying Document - Service location documents
0f79d32f-5606-5bcb-bd0f-59073ad870a7 | note | Frequency - Prior to Works
b183b2f7-d76b-5a75-a198-42caf99d7db0 | note | Inspection Type (Visual, other) - Document review
7db05775-c5df-5b60-86dc-668237237d14 | note | Inspection: Key - R
b3467126-98b1-5541-be98-ebd8aba16f0f | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
cbdb5616-71c7-5211-99d5-489cb47c85cf | note | Standard/Specification - Downer
664a664a-4c98-57ee-b515-712e6edff570 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
e48abea4-1c09-5500-8827-a80542a1202e | note | Verifying Document - Internal Permits
af78b9c1-2da4-5458-a110-aa3f1bda2683 | note | Frequency - Prior to Excavation
e3266d25-d57f-5728-b415-860938412c9a | note | Inspection Type (Visual, other) - Document review
0a84eb93-b95d-5a41-9d3e-c0c4ee8cdc8e | note | Inspection: Key - R
05b310cd-6d2a-5497-a455-01ca8b125598 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
50af3f63-f256-5f79-bc9e-edb02ca66dc3 | note | Standard/Specification - Downer
4717f996-8bd0-5a66-bf45-fd5d26013d56 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
db019378-81b3-5980-98ad-1cc9fe11782d | note | Verifying Document - External Permits
9215ac6a-b958-590b-a899-6ee0a8b0cba6 | note | Frequency - Prior to Excavation
355beb86-db61-5f7e-84bd-6ceb1d694eff | note | Inspection Type (Visual, other) - Document review
a63b52eb-2a6b-57b4-a906-9c390186c2da | note | Inspection: Key - R
da290620-954b-57ff-b2be-608c131396f4 | note | Inspection: By - SE
| checkpoint | 3.1.5 - Approved Construction Drawings
1c5a2701-e889-52d6-b76b-f0a6d14092bd | note | Standard/Specification - Downer
84c66b93-e4ee-5004-bd6e-a7029afb04c9 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
432631c0-ca29-5d17-888b-470658c9c838 | note | Verifying Document - IFC Drawings
9796fb32-60bf-5f4a-ba1f-64e5fd8dfe58 | note | Frequency - Prior to works start
3a5ce91f-3061-5558-a345-43d7c74f3871 | note | Inspection Type (Visual, other) - Document review
aea612dc-f38d-55ea-9db0-79190cf5e536 | note | Inspection: Key - R
bb65884b-99d2-5d2b-981c-63560f95ba10 | note | Inspection: By - SE
| section | 3.2 Receiving Materials/Parts - ANPR + Cabinet Pad Foundation
| checkpoint | 3.2.1 - Concrete mix design
1e49a293-624b-5f61-985c-d22918da1fb8 | note | Standard/Specification - As per Design Specification 30Mpa
f3c05610-1f9c-5096-80e3-287803447b3d | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
93d9a508-ccee-5ade-93b9-2a40ffc5c8f2 | note | Verifying Document - Concrete supplier mix designs
5f058d21-054d-5fd0-9492-24de7ca72061 | note | Frequency - Submitted to Client Engineer for approval before construction
6d870b64-631f-51d3-be24-d516c1dbcd53 | note | Inspection Type (Visual, other) - Document review
c0de6ead-9da8-5210-ab6b-9d831278a7d2 | note | Inspection: Key - H
c11e03fc-5021-5d89-b8e2-6185e1e131c7 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - Reinforcement
3214cc14-e5c0-566e-b937-79fa939bfab7 | note | Standard/Specification - As per Design Specification
a3876c1b-aaa6-5e38-bd10-312d333338dc | note | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
15451b1b-f0e0-5d7e-8040-cb45f712e6fc | note | Verifying Document - Mill Certs
29dd3ffa-c90f-5f7b-9698-bc0bb8e11921 | note | Frequency - Each Lot
9ad6b550-16d1-5142-bc05-af99a95897d3 | note | Inspection Type (Visual, other) - Document review
7e7acb70-86e4-56c7-b44b-b774673ee9b2 | note | Inspection: Key - R
10801aad-0918-5293-9efe-417a15682fd8 | note | Inspection: By - SE
| section | 3.3 Receiving Materials/Parts - WIM plates + Ducts + Chamber
| checkpoint | 3.3.1 - Galvansied Ducts
12dee0b2-c717-5970-b2b8-a5e33a3a5c93 | note | Standard/Specification - As per Design Specification
fd31578f-ed1d-5b4e-812a-7159a07c80f6 | note | Acceptance Criteria - Galvanised steel pipe larger than DN 80 must be Schedule 40 Seamless Line Pipe to ASTM A106 and hot dip galvanised following fabrication
c2b99f9f-a363-5083-8e67-245b67caed01 | note | Verifying Document - Product data sheet/Docket
3bbfcc64-d855-590c-86f4-22c963c151ed | note | Frequency - Per Delivery/Batch
d9882258-c966-503b-99d8-350f4eeff59f | note | Inspection Type (Visual, other) - Visual, Document Review
40644da8-fe4e-5e3c-9240-25e97e884a22 | note | Inspection: Key - R
054c4be1-47e1-5aa4-8185-d2be3fe9ddf2 | note | Inspection: By - SE
| checkpoint | 3.3.2 - Concrete Chamber
3c4cba15-631b-562e-8735-4010793ff827 | note | Standard/Specification - As per Design Specification
4951f726-aad3-56fd-a9e2-94d175fc1d3c | note | Acceptance Criteria - Manholes or Precast Structures to be cast to NZS 3109 with surface finish to NZS 3114 standard
a0204e9a-1169-58d9-b360-ba65402e23d8 | note | Verifying Document - Product data sheet/Docket
4a768b2e-162d-5a02-8ecd-ce1be580be82 | note | Frequency - Per Item/Batch
39ca643a-5aa3-55b9-813a-1f69b00b951d | note | Inspection Type (Visual, other) - Visual, Document Review
910eb8c6-6e62-5cdc-b094-b7a01a2b8768 | note | Inspection: Key - R
a9eae3a5-a7b9-5383-b05f-c48e664a2619 | note | Inspection: By - SE
| checkpoint | 3.3.3 - Embedment / Bedding
a146c037-71de-5718-81f5-68fa4934193b | note | Standard/Specification - As per Design Specification
489044af-fd6c-5251-ae48-1c51ca527cbe | note | Acceptance Criteria - Free draining river cobble or similar bedding material
aa26c568-4f4c-5c64-aa73-ac0f07bcb2f5 | note | Verifying Document - IANZ Test Reports
aaf61837-d681-52d4-9724-86e2b137c934 | note | Frequency - Prior to Works
398d02de-ab55-5859-81d0-362ded74aeca | note | Inspection Type (Visual, other) - Document review
1e63123c-4f5a-5a9d-8ee7-5af874c6d667 | note | Inspection: Key - R
9d4aa3fa-5b15-57a5-8751-a4769b47d7a3 | note | Inspection: By - SE
| checkpoint | 3.3.4 - Concrete mix design
03b4eb6f-11f8-564c-88b2-5629cec96b59 | note | Standard/Specification - As per Design Specification Minimum of 20Mpa
5c8aff0b-239d-5cd6-8d52-8c89d702d39d | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
3c522cf5-b30f-54a8-9134-a8c392de8381 | note | Verifying Document - Concrete supplier mix designs
5eb4d81c-c74a-580d-af1d-b557f0c96f56 | note | Frequency - Submitted to Client Engineer for approval before construction
ec98fc11-7807-513b-9ab1-437ca10bc6a7 | note | Inspection Type (Visual, other) - Document review
f0ae9248-3a69-5b61-9f66-bea0233812cc | note | Inspection: Key - H
51158f40-f365-5af8-a4b2-55ee2cce7a65 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Receiving Materials - Pavement Materials
| checkpoint | 3.4.1 - Mix Design Approval AC20
149e73d4-1ccf-5dae-8ed1-fa9ab98c0efc | note | Standard/Specification - NZTA M10:2020 - 3.1 , 3.6
017b983b-4980-5907-9c70-5ac58cb48760 | note | Acceptance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
d032d85d-09f8-513e-bfc5-cb2f000bc5d0 | note | Verifying Document - Approved Mix Design
a5df4556-2fbc-5233-8542-f355c9afeeec | note | Frequency - Prior to Use
33bf92d8-6ca0-5042-9afe-a0168ceb2224 | note | Inspection Type (Visual, other) - Document review
73001d70-7d7b-56c5-84d3-d07ecac7c0c8 | note | Inspection: Key - H
c4d24e59-4211-5fad-80da-bb9849138fe0 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4.2 - Mix Design Approval SMA10/12.5
9a7cd4a3-6c77-576b-8c20-e1d2e136dbb9 | note | Standard/Specification - NZTA M27:2020 - 3.1 , 3.6
6524dc3a-54a2-5c36-898c-b6791c464ebb | note | Acceptance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
612bd06d-f93c-5b88-8896-5a7b482fd469 | note | Verifying Document - Approved Mix Design
60d31768-f4ec-58ca-b1fb-df9b19423823 | note | Frequency - Prior to Use
b1d65924-1e13-5bb3-89d3-05576aa29fe5 | note | Inspection Type (Visual, other) - Document review
847eded2-9a1d-5e47-a5f4-b1f8ff9c6619 | note | Inspection: Key - H
e27eb32f-6b4d-58b0-808c-0f553120bcd2 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4.2 - Bitumen
3df5a3a6-0da7-51a8-b525-b3d59ecb7cb1 | note | Standard/Specification - NZTA P11: 2007
1c30ca64-56b9-52b3-8226-7941246a9bd0 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
8d96b5a4-ee36-5305-81d9-4b16c5bf6bd8 | note | Verifying Document - IANZ Lab Reports
71003bec-f44d-5a21-aeed-5bcf65987fd2 | note | Frequency - Prior to Use
d3865b84-5143-5212-b49c-56c4e6d15613 | note | Inspection Type (Visual, other) - Document review
650d245e-0f6e-5dec-a18a-ce0bc3d99ff3 | note | Inspection: Key - H
8e6ee791-e05f-5379-a6c7-d1f6d22af2db | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.5 Receiving Materials/Parts - Shoulder Widening and Sealing
| checkpoint | 3.5.1 - AP65 - Source Property Tests and Sampling
03ade22a-2525-5289-b2a4-e54a281bbfae | note | Standard/Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
8d4378a7-c197-5735-bfb9-0eb22e5e2cb1 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
cb346244-b235-5e3a-955f-f92742b85aca | note | Verifying Document - IANZ Lab Reports
7fdef8cc-0bf1-5327-99b2-f8a1026ff055 | note | Frequency - 10,000m3
2df10e95-415e-5c5a-b177-8f45c3cc7c44 | note | Inspection Type (Visual, other) - Document review
d894f8b7-bea1-5cd6-8513-b987c942b003 | note | Inspection: Key - H
a0648f94-2104-539c-9443-944a508baae6 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.2 - AP65 - Production Property Tests and Sampling
e8c49f87-e7ac-5b0d-874e-a37f18da3e86 | note | Standard/Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2006, NZS 4407 : 1991
1262bdaf-195f-57b2-9756-ea89a9fd4ded | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
09509e79-966b-5dbb-aed2-493c5924480c | note | Verifying Document - IANZ Lab Reports
992a95cf-c97d-58b2-9304-06d9319624f9 | note | Frequency - 3 per source initially, then 1/1000m³
ca7bc9fa-af7d-50a4-b049-3e5c090a9775 | note | Inspection Type (Visual, other) - Document review
d4f45f99-226e-5a24-80f8-cf766860dfec | note | Inspection: Key - H
e1912bfa-b320-5b77-b9aa-eee07c754e2f | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.3 - AP65 - Testing for Layer Compaction - MDD
23ece319-a654-5bdb-97c2-f2bea974bfbe | note | Standard/Specification - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
6c909e62-5121-560c-b1c8-e94ccf982aff | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
8302e017-0bf2-5564-8cdf-0176fbe80313 | note | Verifying Document - IANZ Lab Reports
6990238d-5b58-5785-8474-a0b04445f38c | note | Frequency - 5,000m2
5f5b5802-a15a-5754-aa53-c9a4e5403505 | note | Inspection Type (Visual, other) - Document review
50862fa0-5078-5f96-9d76-f9a1bc08340b | note | Inspection: Key - H
f576b956-0364-5615-b388-d9fbc915865d | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.4 - AP40 - Source Property Tests and Sampling
40fffd28-34c4-5fac-b0d0-4da15c3c2da2 | note | Standard/Specification - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
5de4a164-4d26-53f1-a66a-40b86ef97b85 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
8e589d3f-b006-537f-9c4d-d6331fe2d7fc | note | Verifying Document - IANZ Lab Reports
693c1071-f4a4-5816-bd0f-c99dbe884db5 | note | Frequency - 10,000m4
efcf70c3-213b-5fb6-bcaa-ab85ad137c62 | note | Inspection Type (Visual, other) - Document review
b9628c02-1d34-51e3-94df-1f017d5e7459 | note | Inspection: Key - H
250bac37-bfca-5596-bea7-25ec883116ca | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.5 - AP40 - Production Property Tests and Sampling
5041c6ca-0426-5ad5-9bea-03b8df65809a | note | Standard/Specification - TNZ M/4: 2006 - 4, NZS 4407 : 1991
37e42a77-8a87-527b-abc0-864c35a13f96 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
32e469dc-15ee-56c1-9030-af40a7977944 | note | Verifying Document - IANZ Lab Reports
594b638e-83f3-56dc-9af8-5b9bd60df4f2 | note | Frequency - 3 per source initially, then 1/1000m³
e6ced37c-2781-5770-a716-f51d43e00316 | note | Inspection Type (Visual, other) - Document review
dda17191-396d-59fa-b5cd-6ad6401fcd7d | note | Inspection: Key - H
f99653c8-21e7-5089-b3cf-ca1c3b966947 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.6 - AP40 - Testing for Layer Compaction - MDD
f1031c1b-1b89-5bf4-b217-57adf64343ff | note | Standard/Specification - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
aacf3587-82da-5013-badc-8377e9c19c8a | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
c3788c56-8522-5251-ad20-c643590a22a5 | note | Verifying Document - IANZ Lab Reports
5201f200-7f25-583f-bdda-c8e06cce7fdc | note | Frequency - 5,000m2
701fe904-284f-5974-8dd6-a6bee57e9701 | note | Inspection Type (Visual, other) - Document review
a7224c29-ade0-500d-984c-f549de311264 | note | Inspection: Key - H
6f287db5-1aeb-5fc6-9799-96cc1e6fcccf | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.7 - Sealing Chip - Source Property Tests and Sampling
3b2ec559-a398-5d0b-9031-609085462d0e | note | Standard/Specification - TNZ M/6: 2019 - 4
835e1d64-974b-5595-97a1-3d0d3a2ffe37 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
e9005fce-03c1-5188-9896-f9a876c8ed04 | note | Verifying Document - IANZ Lab Reports
c98a8f01-65b2-503b-9961-75a37fba3f64 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
ca4fea4a-3628-52fc-8f3c-bb0f136512a6 | note | Inspection Type (Visual, other) - Document review
92a14da5-e29b-54d5-90ee-12a397b328f1 | note | Inspection: Key - H
07aa386c-904d-5186-9889-4c3aafab5763 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.8 - Sealing Chip - Production Property Test Sampling
004b1e7c-2738-5687-8908-ad036fbb3229 | note | Standard/Specification - TNZ M/6: 2019 - 5
41a2f2cc-e10c-59c7-9b7f-adeb96744380 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
4b751d72-7eb1-5dab-a40a-8a9fc214dda8 | note | Verifying Document - IANZ Lab Reports
9c4fd9dc-6dca-5c30-8314-55f8c8cd2e12 | note | Frequency - Every 500m3
f66bee46-5151-5a4d-bf27-a30e2ec1b2bb | note | Inspection Type (Visual, other) - Document review
206f1797-f91e-529f-9a70-02af67f52904 | note | Inspection: Key - H
13c2c718-218c-5057-8910-e56d6bf15e1e | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.9 - Bitumen - Quality Testing
48ef8dcd-d1f7-54f3-876d-d8be38c88a8e | note | Standard/Specification - NZTA M01: 2022 - 6
d9f4362b-836b-58fa-b3ed-787231e0ed82 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
921216c9-7ec0-58d0-8564-ce7a448763d4 | note | Verifying Document - IANZ Lab Reports
0d6d066d-6a0d-54d5-aeaf-0f496b7c9283 | note | Frequency - One test per grade supplied
849e3741-c565-5062-8819-0c7de1fc0e0e | note | Inspection Type (Visual, other) - Document review
626b8411-d0ac-5057-854e-1957ee3dda3c | note | Inspection: Key - H
dd0eb5ad-44d5-5be2-858b-534302a7b024 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5.10 - Bitumen - Supply Testing
7e526896-bfbe-59ce-b19e-6c61aef846ea | note | Standard/Specification - NZTA Q05: 2022 - 6.2
86c07b01-cf7b-555f-89e4-91618671b649 | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
2cb08073-d17c-5ca4-8264-3b1cc79ba0aa | note | Verifying Document - IANZ Lab Reports
423f5f4c-e434-5bbe-83a4-64c92aeeacc5 | note | Frequency - Every 200 tonnes supplied.
74282c23-4875-5fb7-a940-3c9841bd52b1 | note | Inspection Type (Visual, other) - Document review
e9de6625-678d-5ec3-9c52-c8a4a176be22 | note | Inspection: Key - H
8f6b205f-b292-509f-b535-543c95586f0a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.6 Receiving Materials/Parts - Safety Barrier
| checkpoint | 3.6.1 - Barrier Mill Certs
41013cb5-1f9b-5772-93de-5934dd4cef8d | note | Standard/Specification - NZTA M23, AS/NZS 3845
e42b9e57-fa77-5e84-a3b6-6b111304a531 | note | Acceptance Criteria - Compliance documentation
6ae65903-33ce-5a4a-b2f3-39b031bbaca8 | note | Verifying Document - Mill Certs
67117de6-529f-5788-bdb6-4560bdbd9663 | note | Frequency - Prior to commencement of works
9f6c900f-8a38-5782-85c2-8008ba805d3f | note | Inspection Type (Visual, other) - Document review
1230dbec-f1af-51ec-ba88-3d26b21f11e5 | note | Inspection: Key - R
5398a4e3-7422-52fa-b281-509db1199f4f | note | Inspection: By - SE
| checkpoint | 3.6.2 - Concrete mix design
ae227f84-be93-5dea-833b-2c76b498ece9 | note | Standard/Specification - As per Design Specification
18b67f51-99d9-550c-a924-09eb68f6e8b1 | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
602dc1a8-4751-5b32-b4c1-cd77d37cd421 | note | Verifying Document - Concrete supplier mix designs
37f3d7a3-e6a2-560d-b777-516b8444e0a8 | note | Frequency - Submitted to Client Engineer for approval before construction
8c951a2d-f3a4-545a-bfa5-a3ec3f579fac | note | Inspection Type (Visual, other) - Document review
f03e25e7-8843-5d51-9376-5e29db294884 | note | Inspection: Key - H
09749fc9-bb74-54fc-bd54-4b6959c4d8fe | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6.3 - Guard Rail
080d2896-963b-527c-9410-305036c9a95f | note | Standard/Specification - As per Design Specification, Appendix E, Section 2.1.2
d855a9b1-eea8-5d6e-b99f-ca592199cae2 | note | Acceptance Criteria - The Contractor will in advance nominate type of compliant system and manufacturer they propose to use and agree this with the Engineer.
e2888290-bbab-5f70-a773-560284ad4691 | note | Verifying Document - Concrete supplier mix designs
84428042-8160-5b3a-abe7-f397b013cc80 | note | Frequency - Engineer for approve before construction
f75589d9-5b7e-5d01-b6b3-4a7aba7df8ce | note | Inspection Type (Visual, other) - Document review
99c73e2b-f07e-5ed5-baed-c772a85ef0aa | note | Inspection: Key - H
688023a0-8db5-51ea-94ee-a38286bc52c5 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 4.1 ANPR + Cabinet Foundation - Construction
| checkpoint | 4.1.1 - Construction Location
652fd103-f4eb-585c-9e85-a179f19ba0e3 | note | Standard/Specification - Design Location
5834c04e-a226-506a-b517-276714c95724 | note | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
05771073-5426-5b9d-871c-d95650b90beb | note | Verifying Document - Approval letter, Photos
888a263b-727d-57dd-bcb2-b2651650f7f2 | note | Frequency - Prior to each foundation build
d45ac079-493e-5a0d-828b-d3b52713474a | note | Inspection Type (Visual, other) - Survey Setout
895273a0-4479-56c9-8e46-519bbf9d648a | note | Inspection: Key - V
0902bcec-0a0c-5347-8535-c8b994b5b944 | note | Inspection: By - CR
| checkpoint | 4.1.2 - Ground Compaction Test
4338350e-ed37-5e4f-ba8b-2aa3f65a4d6b | note | Standard/Specification - Downer Standard
214ffbca-eeae-56a5-8417-c3622005b2e0 | note | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
fc4324d2-6e00-580e-ac04-a1a21f6a3d84 | note | Verifying Document - Test reults, Location of Test
820bfaff-b5dc-5cab-b83f-3ad38150c837 | note | Frequency - For each Foundation
e6458465-188e-5dd6-b821-ffae811b8b1b | note | Inspection Type (Visual, other) - Check
647b88ed-aede-5f36-a456-032d6f3dd0bd | note | Inspection: Key - C
b11ad186-f0c2-57ed-9af0-599ce085ac1c | note | Inspection: By - SE
| checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
ea2265f6-3b55-5c07-9c3c-b37320de32fc | note | Standard/Specification - As per Design Specification
2edbcbab-c7ba-534d-9bb5-298bd1c191e7 | note | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
66ad0fcb-2093-5338-a0cf-6d4d61cc23de | note | Verifying Document - Pre pour, Photos
c4489d54-08c2-5704-9ec2-0e1c00ad10cd | note | Frequency - Prior to each foundation pour
48b76c79-a79c-5136-b9b8-9a45258b2ea9 | note | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
d9fa3b93-0107-5850-b863-224372d57263 | note | Inspection: Key - H
8336931a-949e-54b0-8409-7a7ffddfc7a2 | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
5bcc4ee0-967e-506b-bc65-6bd2fd6264e9 | note | Standard/Specification - As per Design Specification
21a81369-a847-5924-a7c4-d9df76b663d8 | note | Acceptance Criteria - Compliant with the construction drawings
46f27c8b-3649-5772-bde5-9dfe71473b7d | note | Verifying Document - Pre pour, Photos
7889d2d2-fd64-521c-95f4-33bf2830e003 | note | Frequency - Prior to each foundation pour
14da0ae0-b3b9-54f0-babc-0467879e4b92 | note | Inspection Type (Visual, other) - Visual Inspection
45b340c3-7c6d-5634-8523-3c39c6033436 | note | Inspection: Key - H
95342472-b2c1-5708-a63e-0be210f319da | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.5 - Pre-Pour Inspection
feffa34b-e60b-5bd9-bbac-c32fc16c5bf3 | note | Standard/Specification - Downer Standard
7a360861-ad7f-5033-b600-bad8a74293ad | note | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
71e9b2e1-bc73-5ce4-a71d-b27923ca5bda | note | Verifying Document - Pre pour, Photos
164ee379-dc62-513a-bf95-a35cdb350e07 | note | Frequency - Prior to each foundation pour
b89c8bbf-483c-50ca-83ce-6453884b6c39 | note | Inspection Type (Visual, other) - Visual Inspection
5c575963-059c-50f7-a560-3dd4a5f3ae71 | note | Inspection: Key - H
f22de9c1-1166-5554-82a4-c6a079dd3501 | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Delivery Dockets
b7023638-f0a4-52e2-b6b8-257db42b5251 | note | Standard/Specification - Downer Standard
13150183-6d74-51a2-8a74-0cd44cded9c2 | note | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
c087a41c-e3ff-5f33-a914-6d0aa3e09c81 | note | Verifying Document - Dockets
90930063-e861-561a-9489-5ef4434987eb | note | Frequency - Each Pour
2e20e24f-d9da-549c-8d52-01b3124c5a0e | note | Inspection Type (Visual, other) - Review
de4056c7-3654-5b39-8f6b-32d9e4282121 | note | Inspection: Key - R
abcfed65-6e12-5d19-9468-daf3a89dede3 | note | Inspection: By - SE
| checkpoint | 4.1.7 - Compression Testing
371f0c50-a0f7-51dc-8267-1aa6d7fcda9c | note | Standard/Specification - As per Design Specification
6f2603b4-8c3e-53b9-88d8-7bb98482a6d0 | note | Acceptance Criteria - Three specimen from each batch or upto 50m3 and shall be tested 1 at 7 days and remaining 2 at 28 days.
7d13ec9e-45cd-56df-a801-2e8b8bbc1e5a | note | Verifying Document - Test Results
d0f5c6c7-1fd8-5cd2-8244-4e9b1f271d83 | note | Frequency - 3 samples per 50m³/per batch
653a3d7a-a1f8-5db9-9d2f-0de79a52227d | note | Inspection Type (Visual, other) - Review
bff5a2f4-f8aa-549c-a808-c1469d372914 | note | Inspection: Key - R
e4c99a2a-f23f-50be-b443-10db7ca85dd1 | note | Inspection: By - SE
| checkpoint | 4.1.8 - Post Pour Inspection
3d26ac05-df51-550e-b361-e681ee16e34f | note | Standard/Specification - Downer Standard
2c8518a6-5d15-5765-b97a-57d44e08a8c9 | note | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
4b5c6594-1508-5e27-ae5e-d090fbe77487 | note | Verifying Document - Post Pour, Photos
81ea4c8e-947b-5a99-bf7f-6910c71da6b7 | note | Frequency - Each Pour
c1a1a30a-155c-51e2-bd95-00ff17bf5fd6 | note | Inspection Type (Visual, other) - Visual Inspection
dc7b1513-9301-5591-b578-f5f995b5b7e0 | note | Inspection: Key - R
758cc740-d5e7-520e-96b5-1e87d7a06ddb | note | Inspection: By - SE
| checkpoint | 4.1.9 - Defective Concrete Finishes
6f0256ec-8d3f-5e5f-956a-102058e5e9a1 | note | Standard/Specification - Downer Standard
9bfcf640-e22b-5d7e-83d7-d154a2782ea3 | note | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
62ac3d5c-09d5-54ed-b059-8311dbb54820 | note | Verifying Document - NCR
0c91f4a2-b9c0-54c2-9f98-920af668d189 | note | Frequency - Prior to minor repair
b2fd823c-05de-5074-b8d2-fbd156333c43 | note | Inspection Type (Visual, other) - Review
23274872-1650-5bab-b481-00a4b76be6fa | note | Inspection: Key - A
a7608e20-02f9-569b-ac14-54387736cddf | note | Inspection: By - SE
| section | 4.2 WIM plates and Ducts Installation
| checkpoint | 4.2.1 - WIM plate location
f98f8041-6966-560c-acff-9d1fd2642f39 | note | Standard/Specification - Design Location
8cb43a52-75e0-5370-9a23-498b904d207a | note | Acceptance Criteria - Set-out to be completed by Surveyor
8bf575d5-5cf6-5cce-b676-e9472118d072 | note | Verifying Document - Approval letter, Photos
b91797c6-ad9d-5258-bdec-59c8e4e28ed3 | note | Frequency - Each
1bba6a82-8166-5230-93a8-f0f8a0b64ca1 | note | Inspection Type (Visual, other) - Survey Setout
9ba845b6-dbe0-5f1b-bd98-4064e3eb51d8 | note | Inspection: Key - D,W
2646f47d-a0bc-59f1-9e33-52c7bedd08d2 | note | Inspection: By - SV,CR
| checkpoint | 4.2.2 - WIM plate installation
e5720eab-22ea-574a-ba2b-d0e14138db52 | note | Standard/Specification - Design Location
09319bf9-edb5-5c95-ae06-403d7c37a338 | note | Acceptance Criteria - To be completed as per the design and technical requirements, under supervision of PAT NZ
43094ac1-babb-5109-81e8-5e9cb7fb3caf | note | Verifying Document - ITP Sign off/Photos
2565d0b1-5691-59d0-847b-089370f83674 | note | Frequency - Each
bbc0bffd-5e7a-54c3-bc06-5c0166364c2a | note | Inspection Type (Visual, other) - Visual Inspection
b403aab1-f564-5709-a2d0-770c6bd8fefe | note | Inspection: Key - V
9621bcda-00fc-5085-9fbe-9bd4e6ccd2b3 | note | Inspection: By - SE
| checkpoint | 4.2.3 - Supply and installation galvanised pipe
e9772c88-35db-5acc-a799-729ccada8b53 | note | Standard/Specification - As per design drawing/notes Sheet No: C 8102
5132f563-e969-5846-a8f7-af42740332ef | note | Acceptance Criteria - 100mm Galvansied pipes, one each to the line of WIM plate location from concrete chamber, one connecting the chamber to cabinet
7b4e4b37-bd1e-5473-a952-df8e5f4801b3 | note | Verifying Document - ITP Sign off, As-built and Photos
1348fecc-6da4-5313-ba71-58159043ea04 | note | Frequency - Before backfill
f60bada5-bdb3-5dff-a65d-49b9492a9861 | note | Inspection Type (Visual, other) - Visual Inspection
7cee6dbe-22b7-5f28-967e-60060d74e7a7 | note | Inspection: Key - V
66dbc5d6-68b4-59a5-af31-6d47fe288bf0 | note | Inspection: By - SE
| checkpoint | 4.2.4 - Supply and installation concrete chamber
9aaa286c-c471-5d7b-8d5d-87d9ed1f4351 | note | Standard/Specification - As per design drawing/notes Sheet No: C 8103
c550a9a8-78c3-5a7b-a5bd-536b0f33b492 | note | Acceptance Criteria - To be completed as per the design and technical requirements
46c24f45-3431-50b6-b963-134e2f3f35d9 | note | Verifying Document - Photos, Checkcheet
cfb8f2c5-d9b9-59c4-af31-e3704368d1f5 | note | Frequency - Each
d60710cc-557a-5e57-b4b8-b8e306985f00 | note | Inspection Type (Visual, other) - Visual Inspection
1080fea5-c755-57d5-aeb7-ab7e083211c5 | note | Inspection: Key - V
41c19d24-a60d-515a-a028-8e29f5ce5701 | note | Inspection: By - SE
| section | 4.3.1 Preliminary
| checkpoint | 4.3.1.1 - Service Location
e0aaaa19-4d64-5326-b969-993c55db2a17 | note | Standard/Specification - Downer Standard
c7b4a9bf-be5d-52e9-b4d4-37ab27f1861d | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
c80efdcc-6be6-5243-ba6f-96d03ee8514a | note | Verifying Document - ITP Sign off/Photos
1c41051f-6710-5035-aa85-1d9d54ccce78 | note | Frequency - All
af16f3b1-2f7e-5ccf-a3f9-4c906ca5fada | note | Inspection Type (Visual, other) - Visual Inspection
7b3a6e38-7729-53df-8e0f-2d3d3121e4f4 | note | Inspection: Key - V
a78fbb01-5982-5aa7-baaf-840fc1bd87ae | note | Inspection: By - SP
| checkpoint | 4.3.1.2 - Pre-Construction Test Pits
31d396aa-ece3-5213-921f-ee5ad4e474ba | note | Standard/Specification - Scala test as per specification
7eb8db22-c94e-5108-afae-8608e8c475dc | note | Acceptance Criteria - Minimum CBR 3.5% as per design notes, Drawing/Notes Sheet No :C 8103
31d406b3-0565-56c9-b981-857eed15d7b8 | note | Verifying Document - Test report
8ae816d1-3745-5f8f-8dbf-f9523e28521a | note | Frequency - 3 test pits per site
0f8b1470-1364-5a46-965b-4beb5b6499ab | note | Inspection Type (Visual, other) - Report review
85617f6f-a4fc-549f-8535-ee519f49a80e | note | Inspection: Key - R
5ae7cf8e-286a-535a-8e11-7d6eac7e7dce | note | Inspection: By - SE
| checkpoint | 4.3.1.3 - Proofroll - Exisiting pavement(Minimum 350mm)
4d6841fb-59f3-5921-85d2-eea389795d50 | note | Standard/Specification - Visual Inspection
c3659758-7854-5d13-9d51-1547672ef6d9 | note | Acceptance Criteria - No signs of excessive deformation or springing
7f787131-76dd-5b40-aaa5-c54446ea300b | note | ○ As per project specified proof roll procedure
63df6f72-1108-54a1-9cd2-2ce61fc73d26 | note | Verifying Document - Check sheet, DN-QC-05, Video
b578e79b-b63a-5757-86c7-2c13b56fd952 | note | Frequency - Entire length of pavement
06ae2892-baca-5e42-ad9b-e34cd465c55b | note | Inspection Type (Visual, other) - Visual Inspection
a03b1497-f89d-56b8-a857-891dba6d5bd5 | note | Inspection: Key - V
10fa3236-1c24-5ed0-be22-6f2ef72d7f35 | note | Inspection: By - SE
| checkpoint | 4.3.1.4 - Undercut - If needed
965d80ae-481b-5314-baf6-ce20c0c88dbb | note | Standard/Specification - Visual Inspection
8a0e42fb-fb05-5158-99be-ed594cbebaab | note | Acceptance Criteria - Undercut to be treated as per specific Note: Drawing/Notes Sheet No : TD0002
b13ff5c2-d823-5125-9952-4c44981dae1a | note | Verifying Document - Undercut need to reproof roll after backfill and NDM comapction, Check sheet, DN-QC-05, Phtos
03ed66c1-3a23-564d-84c2-776c1c4dd2e9 | note | Frequency - Area of undercut needed
afba216a-740c-585f-9784-c9039b099925 | note | Inspection Type (Visual, other) - Visual Inspection
39bccd89-0e3d-50f8-997b-74a82a2438e6 | note | Inspection: Key - V
8a201e88-66e7-5271-9cc0-851f65032996 | note | Inspection: By - SE
| section | 4.3.2 Type B Asphalt
| checkpoint | 4.3.2.1 - Preparation of Area to be Paved
38498b74-95a9-5460-866b-e2654d812196 | note | Standard/Specification - NZTA M27:2020 - 9
1c1a3079-5639-55b7-b10e-24827f6b53db | note | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
eee4fa9d-6bd3-51c1-9dc7-030a80a65034 | note | Verifying Document - Site Notes/Photos
f042d4e8-76b0-563d-ac5d-7cee8253f843 | note | Frequency - Pre Seal
fa53ad1b-2637-58dd-ad8b-eeff52744d5e | note | Inspection Type (Visual, other) - Visual Inspection
cbeb36de-2d49-562c-83c0-19d7c0ad15b8 | note | Inspection: Key - V
0a95625c-b743-5273-9c91-ad71d67b7a20 | note | Inspection: By - PS
| checkpoint | 4.3.2.2 - Ambient Conditions for Placing
99695a79-eb0f-505b-8603-c605509e1e33 | note | Standard/Specification - NZTA M27:2020 - 9
520eabdc-da32-547c-ad7e-3e2133aa4195 | note | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
38a973cc-0681-5d9a-93d7-0e9cb527db6f | note | Verifying Document - Site Notes/ Weather report
7bff45cc-e281-5942-a270-ba94177b1eca | note | Frequency - Pre Seal
8336715f-8a89-57bc-9172-18e9ab21c599 | note | Inspection Type (Visual, other) - Check
8003933b-54fc-5f48-9513-f6e7089c6b51 | note | Inspection: Key - R
cb8e2f4e-7067-5e45-948d-0a4e621458cb | note | Inspection: By - PS
| checkpoint | 4.3.2.3 - Subbase check
de094304-f1e2-5a70-b7a5-c69f16ce0c18 | note | Standard/Specification - as per project specification 3.7.7
a65e2c88-b05c-5899-935b-3df6b78b7563 | note | Acceptance Criteria - Visual inspection by engineer's representative
1ee79c7c-5f5a-5b82-a2f0-94e62c07755b | note | Verifying Document - ITP Sign off
0d8ccead-93ae-5988-8e29-9d137666ab77 | note | Frequency - All
8480420c-c8fd-5141-9bdf-bc61e105871b | note | Inspection Type (Visual, other) - Visual
95195f86-bf51-5a6a-bf29-acf017114a25 | note | Inspection: Key - H
0fbd8939-2e55-5e82-aa70-8e177154e753 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3.2.4 - Benkelman Beaming on Subbase
0eb37086-c3df-5886-a5a0-0b222e65a31a | note | Standard/Specification - Contract Specification, Section 3.5.5
f5495e34-8f77-5acb-8e17-345c0cc086d5 | note | Acceptance Criteria - 90th percentile deflection ≤ 1.4mm.
6806e2d0-243f-5569-bfba-b59df99df2ee | note | ○ No single deflection > 1.5mm.
5351031f-167a-58b0-a992-a3d59aaf716c | note | Verifying Document - Test report
62cc27f1-10ca-56c7-8595-36d9d45736bc | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths)
d8745a67-7880-5caa-9dc7-cc6f10dd030e | note | Inspection Type (Visual, other) - Dimensional Inspection
e966d61f-1046-5484-9bf4-9dc2de844812 | note | Inspection: Key - C
a1cee712-4148-525b-a01c-ff2815c32f53 | note | Inspection: By - SE
| checkpoint | 4.3.2.5 - Heavy Tack & Blind
3f653b9d-c1a2-578c-b2b9-d8d5033c9f6f | note | Standard/Specification - Minimum Residual Bitumen of 1.2 L/m2, As per project based pavement specification
fe3ed551-9333-5956-b4c8-953f86867774 | note | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
f05435dc-bd73-5522-b978-1927942899f1 | note | Verifying Document - Run sheet, QA from Sub
d07c67e0-f1b0-536c-907f-97cd15ff9661 | note | Frequency - Entire length of pavement
8ea7e2d5-530e-516d-9549-8acdf7550677 | note | Inspection Type (Visual, other) - Visual Inspection
4fd45944-ef86-55cb-b6a1-4cc98178f813 | note | Inspection: Key - V
b50ab486-13e2-5f35-9d96-b7d11c5e19a2 | note | Inspection: By - SE
| checkpoint | 4.3.2.6 - Asphaltic Concrete - Base
625a311c-8703-5b75-8498-82cc2af2bd68 | note | Standard/Specification - NZTA M27
9b8a4a73-efcf-510c-a395-f0b6259942bc | note | Acceptance Criteria - 210mm of AC20 (PG58-V) Lifts of 105/105mm, As per project based pavement specification
4cb4822b-34f8-5882-b6dc-5c2162137092 | note | Verifying Document - Run sheet, QA from Sub
f1b0c1a8-1db3-5bc4-bb18-aa5136ad1180 | note | Frequency - Entire length of pavement
777ce793-6048-5c28-832f-068257743f33 | note | Inspection Type (Visual, other) - Dimensional Inspection
f8b92b9b-3ce3-5335-ad3e-0f38ca2712af | note | Inspection: Key - D
a5574aee-9293-5ee5-a6b4-6fbb38b319df | note | Inspection: By - SE
| checkpoint | 4.3.2.7 - Asphaltic Concrete - Surfacing
e3fb6858-db29-5ec4-a715-05054fe23520 | note | Standard/Specification - NZTA M27
ba317fc1-360f-51f4-8ed0-5c89430e00c3 | note | Acceptance Criteria - 40mm of SMA10 (PG58-V), As per project based pavement specification
8fcd01a5-35f4-54a9-ae1d-d900ebe013ea | note | Verifying Document - Run sheet, QA from Sub
cb23b8ee-0030-5232-ac83-ddb679fd5c76 | note | Frequency - Entire length of pavement
53ba87d7-5823-5b99-b085-a2a1389f85fe | note | Inspection Type (Visual, other) - Dimensional Inspection
d0ff7482-669e-528d-a46f-49931b4faf43 | note | Inspection: Key - D
8f976ed9-98eb-5c20-90e3-496243c57028 | note | Inspection: By - SE
| checkpoint | 4.3.2.8 - Thickness
5e0eb315-e6c2-51ea-96a2-9d0fd62c4b05 | note | Standard/Specification - Contract Specification, Section 3.7.15
d826866c-a6ec-5864-97d4-19e8598cb7b0 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20), Thickness of 40mm with +/-5mm (SMA10)
2bfd4335-92a7-5a37-8988-b50fde44762f | note | Verifying Document - ITP Sign off
2f00aae4-8e1b-5bd9-97db-7eb793ddd068 | note | Frequency - Continuous
b284a512-4865-503e-ba24-875f7ebc7c28 | note | Inspection Type (Visual, other) - Visual
71fbcfb6-838b-5182-a542-e7ffe26f7652 | note | Inspection: Key - C
96d1f1e7-8dc0-5eba-bf65-820e7a0504c8 | note | Inspection: By - SE
| checkpoint | 4.3.2.9 - Finished surface at joints
d8ac27ff-639c-53a9-82a5-0263d5dd853c | note | Standard/Specification - Contract Specification, Section 3.7.16
b735e53c-0fc6-529e-b285-ec24752b6010 | note | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
bc8439db-7ecc-55a9-ba09-2eb1551c4ff9 | note | Verifying Document - ITP Sign off
9f41b3b1-e3a7-5ba7-90ac-87e68eccbbbe | note | Frequency - Continuous
d857c8e4-452f-584b-ad31-5d0ea0009e3f | note | Inspection Type (Visual, other) - Visual
aa90e453-69b4-5a7e-830f-103ddb8bdfe9 | note | Inspection: Key - C
a13c155f-4383-54ae-a676-04217bb9e2f7 | note | Inspection: By - SE
| checkpoint | 4.3.2.10 - Air Voids
eb5115bb-3f91-5caa-b125-27fa6a3f2455 | note | Standard/Specification - NZTA M/10
463ccf59-ca52-531d-88ba-1eaa0c5744b8 | note | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
203b37f1-bd0e-5147-a03a-1f21693df2c4 | note | Verifying Document - Test results
5dfc0af2-0210-5791-8fa6-918839fe44fe | note | Frequency - Continuous
dfffea12-0f07-57cf-8ae8-297fc3d0ce47 | note | Inspection Type (Visual, other) - Review
676fd8c9-7e81-52e6-ac3e-fad795511455 | note | Inspection: Key - C
61de8891-7140-55a5-bc61-c3fe46c88d47 | note | Inspection: By - SE
| checkpoint | 4.3.2.11 - Level checks
172ce008-0795-5fa9-8356-98e8690f52dc | note | Standard/Specification - Survey
2419b2ec-0d37-56c3-b708-074e2a43a117 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20), Thickness of 40mm with +/-5mm (SMA10)
38c952b9-ef4d-5e6b-bcb0-c0afa4f37acb | note | Verifying Document - As-built drawing
e1807128-fca8-5e1c-ad96-48dd71f7d772 | note | Frequency - 1/20m full width
ddc8efbf-de90-53a7-a3ec-4cd45013f772 | note | Inspection Type (Visual, other) - As-built
f35d23d6-fc81-514a-b2d2-a1e4e45a94f7 | note | Inspection: Key - D
8745cab3-f787-5479-b1fc-c88906db0b92 | note | Inspection: By - SV
| checkpoint | 4.3.2.12 - Line marking
c2137876-289d-5c43-9db8-d92b9b82fe55 | note | Standard/Specification - Set out
9daec61a-b2ae-588b-8ef8-6a944f86d389 | note | Acceptance Criteria - 1. All signs and markings are to comply with waka kotahi nz transportagency manuals
855f769f-d14f-5878-9943-357792a48952 | note | A. Manual of traffic signs and markings.
896a009b-5969-5b2b-a1ab-1109f513b4b6 | note | ○ part 1: signs
101ffb71-b9f5-55fa-a17a-0e7ceca01d9b | note | ○ part 2: markings
26d555eb-4c5f-54ad-b22a-32ceb249df4f | note | B. Traffic control devices manual
1efd573c-b8fd-5246-8da1-fc113246ca7d | note | 4. All reflectorised markings to meet standards specified in waka kotahi nzta P30 document.
a852eb97-333d-591e-889a-8b6ce9046504 | note | 5. Raised pavement markers not shown, refer to motsam for locations and requirements
314f79bd-3cda-5b9c-8d30-0e6f380f4727 | note | Verifying Document - ITP sign off/ Photos
b136d658-663c-5543-bd63-6dc9cb2063fd | note | Frequency - All
620a0a25-e770-5796-8f42-4d1ac9bcf4aa | note | Inspection Type (Visual, other) - Visual Inspection
8d9376a1-082f-59df-9fb1-2143eba6c073 | note | Inspection: Key - V
2c7b4246-2c96-53d3-9c41-8411a4e131aa | note | Inspection: By - SE
| section | 4.4 Shoulder Widening and Sealing - Construction
| checkpoint | 4.4.1 - Material Placement
5a7ee543-aa64-5e27-8279-79395e95a91b | note | Standard/Specification - Downer Standard
c9a80e86-b19b-5716-864e-2ac09f6bc4e0 | note | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
9ca1a6e0-826e-53e8-a660-648327e4082f | note | Verifying Document - Survey / Level Checks
390de91e-f219-5ccb-900a-10e7ce086abd | note | Frequency - Continuous monitoring.
2d9cf65c-9f5c-5f94-aa86-41775f19e880 | note | Inspection Type (Visual, other) - Check
f1a079db-739b-522e-9b9c-5ccb8edf54dd | note | Inspection: Key - C
4dee6423-93ab-5819-acd6-fd8ca7de57eb | note | Inspection: By - SV, PS
| checkpoint | 4.4.2 - Sub-basecourse Pavement Layer Compaction (NDM)
02593bc9-7046-5e66-8041-5fc53234ddea | note | Standard/Specification - TNZ B/02: 2005 - 7.6
e73821e3-35f2-53a7-b785-2ee3719682ad | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
0f0feaaa-1a99-5209-aba7-f0b24506671d | note | Verifying Document - NDM Report
12a324d7-c40d-56f9-9c64-2c9748f9216f | note | Frequency - 1/10m
e6c203ca-97c0-565f-8889-d684d2b99810 | note | Inspection Type (Visual, other) - Check
a38dd0fe-522e-5383-a501-91e300b4094b | note | Inspection: Key - H
284ca326-ef86-5054-9f47-3703f6f0b3fe | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.3 - Sub-basecourse Layer thickness
5ad09047-a3f0-5f74-9cfd-890c7b7289e9 | note | Standard/Specification - TNZ B/02: 2005 - 5.1
f5855ddb-0fb8-567c-b66a-b223bee94eff | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
3e2631ff-fce8-5205-94b4-7628df322ac0 | note | Verifying Document - Survey / Level Checks
15302709-b020-54fa-a7d3-f1759d513314 | note | Frequency - 1/20m Full width
fe7f117a-cb4a-5f24-9a89-44b020c6f8e6 | note | Inspection Type (Visual, other) - Dimensional Inspection
b83e30e5-7b7f-5571-bd16-bf1f6be50fa1 | note | Inspection: Key - D
199bc08b-9ace-57f5-b699-2d92a659a20d | note | Inspection: By - SV or SE
| checkpoint | 4.4.4 - Basecourse Pavement Layer Compaction
ea96415c-0e9e-5282-9487-3216f21e9a47 | note | Standard/Specification - TNZ B/02: 2005 - 7.6
cf30b108-1cb5-5401-a053-8bd28e5f7e2a | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
00bc8380-df04-5ab5-b527-5923cb693bed | note | Verifying Document - NDM Report
4de23834-ed0c-5e33-af33-4814781e5c1a | note | Frequency - 1/10m
a4f26afe-972f-5ff6-8369-62a1bfae0fa2 | note | Inspection Type (Visual, other) - Check
58e8e502-0ebc-529c-b0ba-6d40155775d2 | note | Inspection: Key - H
4982b817-d0b0-5acc-a1e6-ffef92784ee9 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.5 - Basecourse Layer thickness
c3af43d9-b8e5-5bfe-b1ea-f0415e0f3e8e | note | Standard/Specification - TNZ B/02: 2005 - 5.1
5ffbf96c-e35d-538f-827a-d45afa664023 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
0c4ceecf-f2a8-509d-9346-df62771a9cc7 | note | Verifying Document - Survey / Level Checks
ea930c4f-b9e5-56db-a1ba-acc292773d48 | note | Frequency - 1/20m Full width
d31d8ae6-be9d-5716-9645-341b6ec70351 | note | Inspection Type (Visual, other) - Dimensional Inspection
8bef32e4-2b72-550b-8972-c13fe75c4abd | note | Inspection: Key - D
57828c84-484c-5f4c-99cd-48a6d57c4c70 | note | Inspection: By - SV or SE
| checkpoint | 4.4.6 - Surface Shape
53049582-a298-5e32-a9ac-f62b0ad6450f | note | Standard/Specification - TNZ B/02: 2005 - 7.7
7f9032b7-c114-5f9d-8284-f5ca24526dfa | note | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual. No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%.
a0f382a1-b036-5d2a-a8ff-8c5f08bca517 | note | Verifying Document - Survey / Straight edge Report
9486016b-cdb8-5326-af10-e6bf4d0427a9 | note | Frequency - 1/20m Full width prior to sealing
4060ed74-0de3-5517-881b-a32b2921297f | note | Inspection Type (Visual, other) - Dimensional Inspection
3ba271df-6993-527d-8b26-43060ea50658 | note | Inspection: Key - D
1a595efb-cdee-5c3b-9318-0fa41138b26a | note | Inspection: By - SV
| checkpoint | 4.4.7 - Surface Finish post sweeping
24322551-00a1-582d-b8ca-99110b80d963 | note | Standard/Specification - TNZ B/02: 2005 - 7.8
e9e77ad3-dd0e-5f9b-a727-8225c37e1023 | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
e03080e2-aba7-59e3-8c62-fbbdff4722b4 | note | Verifying Document - Photos
52db0ec4-b4c3-57ad-b3e5-1723f1eec4a3 | note | Frequency - Prior to sealing
c112ae62-8a34-5875-b09e-370bccb1b60f | note | Inspection Type (Visual, other) - Visual Inspection
e87c5da8-48a2-5043-8dbb-45861511ef8a | note | Inspection: Key - V
b42d27fe-40e4-5497-8d67-634f70a41ea0 | note | Inspection: By - SE
| checkpoint | 4.4.8 - Preselling Requirements
03080cec-98f1-5d76-b01e-b235d6833444 | note | Standard/Specification - TNZ B/02: 2005 - 12
685a76c8-a2e4-5d6b-8fa7-c15a7bfa536a | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
f48ac1eb-a83d-59b6-8729-e7585402ee86 | note | Verifying Document - NDM Report
608c136d-1e32-54cc-9bae-05adc79df815 | note | Frequency - 1/10m
541ba2a8-9c0e-5118-b7f6-ad510391cfa8 | note | Inspection Type (Visual, other) - Check
8bad0bf4-9b11-5a97-b4fc-34dbf4909d63 | note | Inspection: Key - C
659647fb-46a8-599e-b3b1-7bc6a2f20424 | note | Inspection: By - SE
| checkpoint | 4.4.9 - PreSeal inspection
cf225056-b7b6-53c3-992d-e71089a8ff23 | note | Standard/Specification - TNZ P3 TNZ B02
dee60fb2-d90a-5a82-ba9f-e7d1bbcc48b6 | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
c50db991-f6a8-54a0-a25e-643fbe11bc17 | note | Verifying Document - Hold point Release, ITP Sign off
3a1ea7bf-7929-5ea0-9c45-eda593131b80 | note | Frequency - Prior to sealing
d9306389-5453-5a7c-8ff1-de1e6e1c1532 | note | Inspection Type (Visual, other) - Check
d1f665da-bbd1-598f-93ee-3dc2edec34ae | note | Inspection: Key - I
13f52eaf-4561-540f-a1e7-f6e8bf25e213 | note | Inspection: By - SE
| checkpoint | 4.4.10 - Spray Temperature
2a6cb6b2-958a-5f70-a72f-191d64b1a970 | note | Standard/Specification - TNZ P3
93d15b6c-5425-5d16-a2d5-cfa886f2909c | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
98b37ed0-a3db-5f82-896f-d15e03ecf872 | note | Verifying Document - Sealing statement
d2c5c1a4-ac3c-5f17-86ce-30ed95805211 | note | Frequency - Prior to sealing
0cd496fd-0f68-5dfb-a498-66984315c957 | note | Inspection Type (Visual, other) - Check
8e37f267-0515-53b0-9595-3bd706cea494 | note | Inspection: Key - I
7c3a92b5-f0b2-517e-b882-a51e25284f0c | note | Inspection: By - SE
| checkpoint | 4.4.11 - Chip Application
01ddf1a5-a2a5-52e2-89a8-0f39b4cde405 | note | Standard/Specification - TNZ P3
41b606f9-5577-5df8-95b9-59feab7e221b | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
97d3265f-9211-5886-8b61-90a780563b62 | note | Verifying Document - Sealing statement
974e1688-591c-5b07-99a3-6d9cb0bf8b05 | note | Frequency - For every spray run
f252bc74-510a-52b4-a010-678cd0d81aad | note | Inspection Type (Visual, other) - Check
3ef0d7b4-3195-5f10-9f89-002916b76f92 | note | Inspection: Key - I
dafeb36e-fec9-59a2-a16b-4c709db80a48 | note | Inspection: By - SE
| checkpoint | 4.4.12 - Post Seal Inspections
bf2d0ed3-902d-5cee-8b9f-5875e7cf6ce2 | note | Standard/Specification - TNZ P3
f67d6b0b-286f-589e-bacb-01390132fc15 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
ae3b3c63-d24f-596d-b457-8f66404fe475 | note | Verifying Document - Engineers Acceptance
f56a042e-1e83-574b-b847-7adabdb02adb | note | Frequency - Prior to TM Removal and After Final Sweeping
d50c1cb4-df17-5ada-bb22-4679d4b070b3 | note | Inspection Type (Visual, other) - Visual Inspection
e36df336-d744-5e12-9d12-59c4cb12eef2 | note | Inspection: Key - H
fe6bdd05-c321-5370-933b-591de9012eba | note | Inspection: By - SE,CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.13 - Chipseal Repairs
e0a1bc6c-794a-5cd6-8e93-7306bde7ae78 | note | Standard/Specification - TNZ P3
29a06b0d-c503-5932-a783-2d120903a829 | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
ddb59e7f-2ae0-55af-8b9b-64958ead59e7 | note | Verifying Document - Approved Repair Methodology
33f7ac7c-f35d-500b-8938-29410120126d | note | Frequency - Prior to Repairs
c25bd8eb-959f-5110-9a6b-dfd797995b9d | note | Inspection Type (Visual, other) - Review
8cb6e652-d474-5474-a412-a18288a34669 | note | Inspection: Key - A
6aba17ee-34a9-5959-bc2a-5f5ba4747a78 | note | Inspection: By - SE
| section | 4.5 Guardrail - Installation
| checkpoint | 4.5.1 - Guard rails - Installation
06295c0c-fb83-569f-a72a-86ea38451a5a | note | Standard/Specification - Appendix E, Section 2.1.3
83d9d3c1-a9c5-506b-81ed-8a6e43dfc6f1 | note | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
5abf1a06-1735-5713-b75c-49b5988a71d4 | note | Verifying Document - Hold Point
29817e13-665d-5094-bb20-77bac2618790 | note | Frequency - For each guard rail
be336fc9-5fd9-59f3-a3d4-2d0bd9b6252c | note | Inspection Type (Visual, other) - Visual Inspection
6532ddeb-1b91-5c12-9704-ffefa97febd7 | note | Inspection: Key - V
4217285c-e8b0-571f-8522-3723996955e6 | note | Inspection: By - CR & SE
| checkpoint | 4.5.2 - Guard rails - Checklist
03421edd-34c1-5d59-a5f5-40628f604b30 | note | Standard/Specification - As per the Contract Specification
a214d891-0af6-5ad2-a905-06b9b513c0d8 | note | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
92f9eae3-9f5a-5d93-a7b6-fe2dc268027f | note | Verifying Document - Check Sheet DN-QC-06 Photos
97edc8df-43e4-5928-897c-30b04e2f0c7d | note | Frequency - For each guard rail
8267bce1-d71e-5380-aa4a-905aee905393 | note | Inspection Type (Visual, other) - Visual Inspection
462a90ba-2172-5faf-be66-7d10f0470b09 | note | Inspection: Key - V
7efd45d3-df4f-5709-918c-e1d0996cc75c | note | Inspection: By - SE
| checkpoint | 4.5.3 - Guard rail completion
1e81f6b9-6754-5ce9-bf3b-7b67d517b3f7 | note | Standard/Specification - NZTA M/23
a51be986-fdc5-55d5-9384-bb3c79119668 | note | Acceptance Criteria - All road safety barrier systems (including end treatments and crash cushions):
907977e4-ffae-520f-8c9d-463dfb998153 | note | ○ System checklists to be completed and co-signed by qualified contractor (who has completed the Waka Kotahi IMI workshop) and Waka Kotahi representative.
5015833b-322b-5328-a828-37dc94ba106f | note | Note: All faults to be rectified before acceptance into network operations (maintenance manual) and network assets register (and RAMM).
3323a1eb-b504-5771-8ac4-8bd3e096a04e | note | Verifying Document - Hold Point
b291af80-6408-55c2-9cc9-06fb389da7f0 | note | Frequency - For each guard rail
2b752ee1-7319-5507-be22-7a4e8b739fd6 | note | Inspection Type (Visual, other) - Visual Inspection
554bfcc0-091d-517f-a702-551ce1fe2591 | note | Inspection: Key - V
2061ced5-b4f4-5440-b9cf-21d091b01bca | note | Inspection: By - CR & SE
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
502a3340-d6b8-5d45-a6b8-38a9d9fafbb4 | note | Standard/Specification - Upon completion of works
4f45d8a5-6b80-5ba6-a81f-92ed9db58083 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
9358c80e-3e43-5e10-bb34-66e56d2af8a4 | note | Verifying Document - Closed-out NCR/Defects
57419d8a-bfd6-50ae-b579-ba247cd3efd7 | note | Frequency - Post construction
2626eed5-f07d-5e7c-b242-755d77a09bdb | note | Inspection Type (Visual, other) - Review
c9cee6b6-a7e3-5866-a8bc-bbd0944ce197 | note | Inspection: Key - R
c42ed981-619c-5215-82ba-053af587481c | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
24df8d36-5006-5fd6-8197-b3c4ff665c3c | note | Standard/Specification - Upon completion of works
0297bb9c-e6ed-5822-a1a0-876a1138e277 | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
1efc0ae0-39d5-52af-a997-27dfdddf3da7 | note | Verifying Document - As built survey record completed
480698ce-e795-571a-9655-28b617588d21 | note | Frequency - Post construction
c4de3f21-9b3c-57c7-b49e-bd04c3552f89 | note | Inspection Type (Visual, other) - Review
efc7d194-c4d7-5aea-979f-479826ee306e | note | Inspection: Key - R
1e177283-54a8-56c1-ba11-4bc497775804 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
d13fa5c0-f711-5560-83d8-124883746b7a | note | Standard/Specification - Upon completion of works
c7fd3243-6719-52df-a3db-8c83e3bcd0e4 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
546c4176-1096-559c-9a0a-01815fcdd018 | note | Verifying Document - Signed As-built Drawings
16f74117-9ba9-509b-a0df-8aab23337b2b | note | Frequency - Post construction
0e7df726-83b1-5ee1-a881-20fe9e8a4158 | note | Inspection Type (Visual, other) - Review
60e50c1d-c9d4-5bfc-a602-8ce43db2dad1 | note | Inspection: Key - R
f72e6481-7a9b-5169-b32b-90f15c34615e | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
2ecfc2c4-ac09-5aee-82bc-8cc091124a8a | note | Standard/Specification - Upon completion of works
f8c489f3-0e83-5a41-9573-585d2c971107 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
75482339-c941-5367-925b-15daf108cf9d | note | Verifying Document - Register
5cb2b2f0-7c7a-516f-8701-922d2910c116 | note | Frequency - Post construction
fff01c38-e37e-5c88-a6bb-c00a46ce4d98 | note | Inspection Type (Visual, other) - Review
42e32e5d-30df-5c8e-8c6e-4eb5e4ceff3e | note | Inspection: Key - R
13386f23-c7c1-5012-a358-b51cd98b435d | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
39309556-b07a-509e-b9cb-682885dfebe7 | note | Standard/Specification - Upon completion of works
83607579-dcdf-516e-b213-0c460d514835 | note | Acceptance Criteria - All signed and closed out
32432568-f70b-5dc6-99fe-ccb7c92e7cc6 | note | Verifying Document - Signed off Documents
77fdb9ef-1838-57c5-92cf-c7e90268c32e | note | Frequency - Post construction
9ecf517e-f146-5f51-b3bf-63b44731b2fc | note | Inspection Type (Visual, other) - Review
e959ba52-fab5-5acd-a904-c2e40cb9ea2a | note | Inspection: Key - R
1a9d3865-585c-5ee9-b2f2-343b5bc69033 | note | Inspection: By - QM
| checklist | Ω (Deprecated) DG-OWR-CVSC-ITP001_v1 - Earthworks for CVSC (v1) | itp | DG-OWR-CVSC-ITP001_v1 - Earthworks for CVSC | 58278128-dc4b-49b7-9a5f-da603a78a990
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
5ea79338-4be6-5c6c-a632-6db117171dae | note | Specification - Downer Standard
3000af96-66d4-5a95-a3c4-89f849d95640 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
523123cd-a0d6-569f-a901-a64b80bbe9df | note | Verifying Document - Survey Records
148e0b35-d384-5491-83d5-6cc443c8f0da | note | Frequency - Prior to Works
9f986bff-c6b8-52f3-87a1-dea1a6a5d217 | note | Inspection Type (Visual, other) - Document review
77678519-f6a4-50ea-bed0-66bb377b9427 | note | Inspection: Key - H
edf094df-7387-5c6c-a21e-b2653324227d | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
8042d1a8-9e1c-5f85-b0c3-cb430240f0e3 | note | Specification - Downer Standard
f052a53d-cdc1-5f77-99c0-12e2ab468718 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
384e4d8d-89c8-5c5b-8bd0-09a8b81ec442 | note | Verifying Document - Service location documents
f427d26c-81f9-5471-ac53-10956dd9f228 | note | Frequency - Prior to Works
73ba8e98-0140-5d83-b27e-19e8587b73b3 | note | Inspection Type (Visual, other) - Document review
16aa1ef0-051f-583e-aac6-4eb39cb5ab88 | note | Inspection: Key - R
8ca4e6fc-e445-5bff-b083-fc2ff29ac00c | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
5feaab92-891c-590f-b11f-4277517e0288 | note | Specification - Downer Standard
77976860-9fab-5ef5-afb7-1f3b734deb18 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
ab7e2c6f-3a5b-5ebc-a3f5-12f00d669ead | note | Verifying Document - Internal Permits
7c0b9290-3ac2-5731-ae4a-53cdaaad1280 | note | Frequency - Prior to Excavation
75853f5b-29c8-5c5f-a7fd-4d5f9da556a4 | note | Inspection Type (Visual, other) - Document review
7dfa052a-bba9-5912-9ac3-cc6b15f01843 | note | Inspection: Key - R
5cb1d215-f7f6-5ee3-b40c-a5d30b653fa6 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
276e5ad2-953f-5971-b8bf-6e5830819804 | note | Specification - Downer Standard
135b006b-5f3f-5302-9b96-378e60c22bf3 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
09d47dce-8523-59cc-8bae-0e0eb77c7ad7 | note | Verifying Document - External Permits
1430af08-9e0e-5a93-a02b-bc12ac22bf73 | note | Frequency - Prior to Excavation
d62e05ce-2762-516d-9465-54565440d8a8 | note | Inspection Type (Visual, other) - Document review
12da365b-754b-5808-9547-d0f3b4d26475 | note | Inspection: Key - R
5335c471-057a-5175-91e2-a595246b91eb | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
55d3cb11-63a9-5c33-aa3f-931db372cc29 | note | Specification - As per contracts
42130796-113e-50cb-9a8a-68f04b92e718 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by council is in place and valid
d3480a44-77c3-51c4-9e5c-33c3f982f921 | note | Verifying Document - Approved ESCP plan
97aa12eb-9581-5bdf-a2fc-2744809c0006 | note | Frequency - Prior to Works
9f52df8a-b9d5-5e5a-b486-4a827a011872 | note | Inspection Type (Visual, other) - Document review
8ab255bb-4581-5736-8ea7-fce34e5d973d | note | Inspection: Key - R
30a0bb5e-4b78-5e73-a8d3-73055ab9733c | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
e0a25ece-e2d3-51f4-9c08-6c58a1913820 | note | Specification - Issued by Client
5d9b2635-7161-5ca2-a9ca-ac8812e5eb64 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
46e8ba89-a5f5-5955-8e61-1d735f1d79ff | note | Verifying Document - IFC Drawings
748fb4d9-5665-599c-8632-95bdf410c81b | note | Frequency - Prior to works start
d6aee40b-5ae4-54b9-ab38-fb2893a3fe81 | note | Inspection Type (Visual, other) - Document review
48575751-5f68-52b4-a972-966cbf2b9cd8 | note | Inspection: Key - R
a6d3e903-76a8-585a-8e60-bdb07761e7d1 | note | Inspection: By - SE
| section | 3.2 Earthwork - Incoming Materials
| checkpoint | 3.2.1 - Imported Fill and Structural Fill Sources
69bf669c-3b45-5ec0-864e-8fecdfa04127 | note | Specification - NZS 4402:1986
5e0d9b96-2e13-5ef7-b2ef-da145ddad57f | note | Acceptance Criteria - Max Dry Density (standard) and Optimum Water Content
964eb4fe-8398-5c80-be51-b8d215c89063 | note | – Natural moisture content
e0459388-dce2-5448-b420-acb474a22cf7 | note | – Plasticity index
3e5c3295-cdb4-58c1-9dc3-62f65c7f6b35 | note | – Particle size distribution
ed021f76-5221-57ca-880a-c53306eae823 | note | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
9911f697-f2c6-5c8b-b285-c8ae37d6c32c | note | Frequency - Porior to works
6d8f5d79-2fde-5b7b-b04d-0f0411cd1bfc | note | Inspection Type (Visual, other) - Document review
f393f250-9109-5027-ac57-ca9da5cf7a5e | note | Inspection: Key - R
e0383ecc-7658-5541-9529-2d2ca9941a84 | note | Inspection: By - CR/SE
| checkpoint | 3.2.2 - Cut to Fill Material
0dcf45b5-693f-5cdc-8ec0-2f62e049b46e | note | Specification - NZS 4402:1986
ef8e655e-6242-5f4f-88f4-9634f9ee9f24 | note | Acceptance Criteria - Max Dry Density (standard) and Optimum Water Content
8fa5a31a-8ea5-56bf-817d-57799b8361f5 | note | – Natural moisture content
a01b75c8-78c0-5f22-8215-2f557ec7204d | note | – Plasticity index
c04ef4e5-2fec-5ea6-b46c-7ebad0b56545 | note | – Particle size distribution
2328fdad-01df-54bb-965f-f2eac623fc82 | note | Verifying Document - 1 set for each fill material and source (each 5000m3 thereafter)
75a6027b-2435-526c-9092-4f6841b381a6 | note | Frequency - Porior to works
687c368a-e067-5756-9d48-9dfca2e91bbe | note | Inspection Type (Visual, other) - Document review
20b0ab67-8ed4-507c-927e-686ff728f03e | note | Inspection: Key - R
07a494f6-5f4d-54fe-8e6d-7541136237f1 | note | Inspection: By - CR/SE
| checkpoint | 3.2.3 - Geotextile
f59708f2-b00e-52fd-b5f2-b1c978bbea44 | note | Specification - NZTA F/7
2fa4fc9e-ac7a-5de2-9a07-dc4304c63d0e | note | Acceptance Criteria - Non-woven filtration class 1 and Geotextile strenght class C.
ee58b2e5-ce13-5cf5-a93f-6c197c3fef43 | note | ○ Confirm the above grade from the Manufacturer's Certificate of Compliance with IANZ endorsed or equivalent test documents.
7d0d2851-a164-5104-8d3a-82775f03b71b | note | Verifying Document - Product data sheet, Docket
766cae4d-6634-5e53-a49f-0565b3c3610e | note | Frequency - Each lot
f610f793-3b02-508e-9661-6da8197a8537 | note | Inspection Type (Visual, other) - Document review
43f76847-48fe-5452-9344-404590f4b1bf | note | Inspection: Key - Inspection
a7d4711e-8d9d-5287-a228-763ca30da2bd | note | Inspection: By - SE
| checkpoint | 3.2.4 - Geogrid Prep Inspection
7fff7f27-a048-54dd-a23b-855b96349154 | note | Specification - As per project specification, Section 2.15
3f4c3b3b-6d52-56e7-8651-29c4eeb34994 | note | Acceptance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
fc3c90ea-845a-5c30-8bc7-a45a0122dd5b | note | Verifying Document - Product data sheet, Photos, As-built
547b45af-51b5-5675-9f1f-0a06d5a6d302 | note | Frequency - each application
38973dc1-f4e4-5d3c-a731-ef1b6c6db8ba | note | Inspection Type (Visual, other) - Action
3b7cfd3d-19cd-5fe1-898f-7e76fe197b37 | note | Inspection: Key - W
9445bc97-0787-56b0-9516-cb068ff9a8df | note | Inspection: By - SE
| checkpoint | 3.2.5 - Source Property Tests and Sampling (AP65)
57011fa8-0a3a-554a-be3c-6d9221088183 | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
c9e467ca-79c3-5e8f-9fe6-5214b9c972b7 | note | Acceptance Criteria - NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
105e06b9-3483-5b49-89d4-3a94d7de5ec5 | note | ○ NZS 4407 : 1991, Test 3.11 Weathering Quality Index Test. Aggregate shall have a quality index of AA, AB, AC, BA, BB or CA
60c3f43d-34e4-5427-b623-075beebbb879 | note | ○ NZS 4402 : 1986, Test 4.1.3 New Zealand - Vibrating Hammer Compaction Test at Optimum Water Content and,
1c4f42fb-cbc7-5da0-a7f8-78b1449b8598 | note | ○ NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
0c5430bd-20a8-5347-a562-7bbe2e0bcfb7 | note | Verifying Document - IANZ Lab Reports
d6e5486a-dc53-5210-815e-469de078fe8b | note | Frequency - 2 tests per source, submitted 4 weeks before use in the works – not older than 2 years old.
330b08f6-ad2d-5101-9f5d-9c2db393c429 | note | ○ 1 test per 10,000m3 thereafter.
28190d64-93ab-59dd-bcf2-5d35a0e0d396 | note | Inspection Type (Visual, other) - Document review
76022fec-7b72-591b-b0f5-5cb0e8317b0b | note | Inspection: Key - H
3da1fba1-958b-52c7-b627-5573fc1dd795 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.6 - Production Property Test Sampling (AP65)
8db03f40-c028-588c-b4ee-cbdb0914affd | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
68642b81-4c32-5039-92bd-83bd272e925d | note | Acceptance Criteria - NZS 4407 : 1991, Test 3.6 Sand Equivalent Test., The sand equivalent shall not be less than 40.
d5ab22a7-6411-5409-96cb-8bbda4ceec4c | note | ○ NZS 4407 : 1991, Test 3.5 Clay Index Test. The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3
c0af1bc9-b48d-5b8a-8524-a2f93daf530d | note | ○ NZS 4407 : 1991, Test 3.4 Plasticity Index Test. The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5
d8c47d69-8243-5e9b-99b2-88433731c215 | note | ○ NZS 4407 : 1991, Test 3.14 Broken Face Test. aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces.
b73d934f-4373-5da6-92fc-ba98e6ee9237 | note | ○ NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test. aggregate shall conform with the envelope limits defined in both Tables 2 and 3 in Clause 4.2.3.
d54dd4c9-0432-5110-a976-6f23cdd4cd06 | note | Verifying Document - IANZ Lab Reports
87b6f5f1-26c2-54b9-ba76-70be22ed4e77 | note | Frequency - 3 per source initially, then 1/1000m³
b8025965-6cf4-58a0-99e6-1ef470b2d657 | note | Inspection Type (Visual, other) - Document review
644627ca-f295-5c8e-a333-8a928e7c4c01 | note | Inspection: Key - H
72490d97-95fa-579a-ad51-d8c5300e0a29 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Testing for Layer Compaction - MDD (AP65)
9dbf2fd4-6357-5d68-93e4-c8fd0b2ebba9 | note | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
216f8358-c727-5bdd-b02e-a02de1f2c080 | note | Acceptance Criteria - Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at Optimum Water Content (OWC).
6d7e84d5-9942-541c-8666-6035c36ff0d4 | note | Verifying Document - IANZ Lab Reports
780ef9cf-478e-59ba-9836-876dc8030042 | note | Frequency - 5,000m2
b1f0f759-e0de-5a98-b2e6-8da1894e3bd2 | note | Inspection Type (Visual, other) - Document review
4a0ac706-3036-5b25-95c1-f8aa62cf380b | note | Inspection: Key - H
d0c6a449-8d36-5f2e-a4e8-4aaec186544e | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 4.1 Earthwork - Construction
| checkpoint | 4.1.1 - Site clearance
b03784c5-c31a-57a4-92ec-d87f410c88f0 | note | Specification - As per project specification, Section 2.3
05fe7ba0-56d0-5579-96da-d24723b10530 | note | Acceptance Criteria - Clearing shall include the complete removal of stumps, trees, logs, scrub and coarse vegetation and disposal by burning, or dumping and burying in accordance with any particular requirements of the contract documents
d7108f65-85e6-5448-bb14-495b074008ed | note | Verifying Document - Photos, Checklist as per requirements
f4984bb3-4416-58e7-996a-830c92e240e7 | note | Frequency - Prior to topsoil removal
58cde80c-e067-5920-bc6e-1b49595a7f51 | note | Inspection Type (Visual, other) - Visual
149bffc9-baed-57a2-88e4-bb7ff5d1dc4b | note | Inspection: Key - V
4d2a413f-2dbd-5ac5-a346-5c5ef69e0c4c | note | Inspection: By - SE
| checkpoint | 4.1.2 - Top soil strip
59c404bf-eb2c-5353-9f5a-bc36d096e746 | note | Specification - As per project specification (200mm), Section 2.9
6ed889cc-3585-5c97-b85d-15e40010571f | note | Acceptance Criteria - Topsoil shall be removed within the limits of the earthworks. Care shall be taken during the removal to avoid contamination of the topsoil.
53a16f35-ed9d-5cef-abf4-162c60bb9eae | note | Verifying Document - Photos, As-built
70d7f190-c2e0-5405-88c8-e2e40fe9e07a | note | Frequency - All
fe60cb86-c368-5f93-998f-f1e19a86dac6 | note | Inspection Type (Visual, other) - Dimension Inspection, Visual
68cded1f-1245-5d62-bdcb-49c561d18fea | note | Inspection: Key - D,V
e5576aec-d6c7-5f5d-a1c3-f6d8c3233fb6 | note | Inspection: By - SV, SE
| checkpoint | 4.1.3 - Subgrade Suitability Testing - Scala Penetrometer Testing
616cfb42-98b8-515f-bb41-51c627a318a2 | note | Specification - As per project specification, Section 2.18.2
3dada345-5835-521c-9476-9bf1a26a5d6c | note | Acceptance Criteria - The Subgrade must be tested by Scala penetrometer or Shear Vane to confrim suitability.
305e95ce-00df-5464-a21a-ae9015bc4bd1 | note | ○ 3 blows per 100mm
c2cdeb5b-8f7b-5b22-a865-bcf67a52a932 | note | Verifying Document - Shear vane/scala checksheet
fd9942b0-7eab-5071-975e-ba57dbf65391 | note | Frequency - Whole area by 20x20m Intervals
32aed00d-fc0e-5af9-9e01-4e353ad4287c | note | Inspection Type (Visual, other) - Inspection
1539b6b6-9992-5f42-9996-00378332ccc2 | note | Inspection: Key - H
d72c34d1-bb7b-5568-a4bc-21cfacca0b5e | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Subgrade Proof Rolling and Suitability Inspection
01304be2-c272-53cf-b3c1-b44e1feb0b9c | note | Specification - As per project specification, Section 2.10 and NZTA F/1, 10.5.1
8960fbd4-9173-519b-9d02-5e8aa90d4464 | note | Acceptance Criteria - The subgrade shall be proof rolled to verify the subgrade stiffness and consistency. "Indents" left in the compacte layer shoiuld be no more than 7mm for bulk fill and 5mm for subgrade fill.
8472f86c-75ee-5467-b189-f3c9fe93e570 | note | ○ The RL and area of proof rolling will be surveyed.
9d91746c-5a35-5f38-91cb-32b56877d8c1 | note | Verifying Document - Proof Rolling Sheet, Photos, Survey area
ad7d97a1-1acb-580e-8998-edd4cebb4b93 | note | Frequency - Prior to the placement of any filling, Whole area
e352592a-cbe0-53f9-8adb-d032330e0c3a | note | Inspection Type (Visual, other) - Visual Inspection
4d24919a-0361-554f-9d75-3849a12c05f0 | note | Inspection: Key - H
3f016e15-297c-59ea-a090-8b939dfe4729 | note | Inspection: By - CR, SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.5 - Imported & Onsite Fill (Gap65/AP65) Compaction Testing (NDM)
0cdd3e07-37a1-51e4-a224-c60001981f6e | note | Specification - As per project specification, Sections 2.13 & 2.18
3b9df407-7d66-5a4c-83b3-dd08a42c7cd8 | note | Acceptance Criteria - Bulk fill shall be tested by NDM with a minimum Dry Density of 95% MDD
2050cdd4-c756-58ce-922b-92e991afab7f | note | ○ Cohesive soils shall be compacted at OWC (moisture limits are 4% below OWC to 2% below OWC)
135b102a-a1c1-5139-aa0b-5cbf784c811b | note | ○ Minimum acceptable dry density for AP65 is 2100 kg/m3 , a minimum dry density of 95% must be achieved (moisture limits are 4% below OWC to 2% below OWC)
6eb91b31-d0a3-526c-b286-96f286ec09ff | note | Verifying Document - Test Results
edf2b1f3-7305-5362-8aaf-3259e8187e24 | note | Frequency - 10m x 10m grid
459fbf28-c945-59ce-af95-4961a8b1cd0d | note | Inspection Type (Visual, other) - Inspection
0f30f33f-ae6a-501f-932a-2d30e599a286 | note | Inspection: Key - H
100d7a2d-005c-5980-ac4a-9727f0e10374 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Geotextile Installation and Lap Length
50b5f06d-204c-540c-b081-e3ba0da0a208 | note | Specification - As per project specification, Section 2.15
bc741ff0-9838-528c-977d-3e9be2325879 | note | Acceptance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
7965527a-8e92-5bf7-b93e-0af5575bc18c | note | Verifying Document - Photos, As-built
399aec3b-aa59-5557-b5f2-7a442cad66e4 | note | Frequency - each application
e90998a0-6aa8-5fa9-955a-9ef1a19a164f | note | Inspection Type (Visual, other) - Action
4ad7abcf-e22a-5cd1-bfb7-7050ab60d8fc | note | Inspection: Key - W
33ec7bc7-2bef-5a6f-9091-013feca70902 | note | Inspection: By - SE
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
444f9d2e-016a-5885-8f51-73dcd654535c | note | Inspection Point: Quality Control Activity - Upon completion of works
0057b00f-172f-5c65-8611-36a726c53dca | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
6aca936c-a2f1-52bf-a25b-318b49930bce | note | Verifying Document - Closed-out NCR/Defects
f434ebff-35d7-582e-93ff-9c42afdf1bb5 | note | Frequency - Post construction
2fadefbc-2f6f-557f-9b27-10ffad40841d | note | Inspection Type - Review
dbc4a090-5dbd-5482-8511-a035abc88eaa | note | Inspection: Key - R
f5181e0d-9882-5eee-931e-c04648fe9c0e | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
fe2b3d22-f335-5761-bde8-e78339ee0b85 | note | Inspection Point: Quality Control Activity - Upon completion of works
f6078b77-776b-5950-92d0-f0e93114652c | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
54c5a71d-cc72-5b90-b49a-7c4db77b24d8 | note | Verifying Document - As built survey record completed
18619a85-1a25-5edb-97c8-9b0226ff3245 | note | Frequency - Post construction
09fa93c0-1467-57ed-a387-0e5a75468400 | note | Inspection Type - Review
a1a304b7-16b8-5112-8eaa-fed20d437616 | note | Inspection: Key - R
0151cc0c-94ab-5660-8886-a8b36d66da62 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
a481032f-4cb8-5796-8b8d-4ec4774fa05a | note | Inspection Point: Quality Control Activity - Upon completion of works
ac316f06-30ab-5d74-8110-9be58196cb8a | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
a4a4d8aa-dc92-5331-8cba-b451bbb8501b | note | Verifying Document - Signed As-built Drawings
63d88a95-c1ef-5fc6-b743-1b268b1acbe1 | note | Frequency - Post construction
ca2641fb-4fa7-564b-9c7e-473e65f348ce | note | Inspection Type - Review
21c597bd-3f9d-5aee-b121-d825ddb87d8a | note | Inspection: Key - R
63285eb5-21f3-5027-88e9-2974cb84a11b | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
d884891c-f30d-5edf-a53b-47ad6ccaf022 | note | Inspection Point: Quality Control Activity - Upon completion of works
ea107910-01ef-5799-8253-1389dabb8c27 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
1f606ee8-9964-5800-a80b-18ea7edf0a8d | note | Verifying Document - Register
65f08a41-2cdd-53eb-814a-d489416ea134 | note | Frequency - Post construction
651f080e-9905-57be-9604-df031ccf30ba | note | Inspection Type - Review
337bb5ad-d2c5-548c-8cd3-76630feae5d2 | note | Inspection: Key - R
3cde1df6-daa2-5dd5-8f98-684f56571a1c | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
c4b1db42-0eb6-52fe-9e63-ee1512df3b02 | note | Inspection Point: Quality Control Activity - Upon completion of works
22680dc4-5243-5c2d-b009-31ad57f21ee7 | note | Acceptance Criteria - All signed and closed out
1e3c33cd-a336-5b1f-a3bd-24a2223061ef | note | Verifying Document - Signed off Documents
f9eb6b99-8f09-5244-9b76-02110a94a34d | note | Frequency - Post construction
e4573c77-6299-5060-9266-dec3ecdbf339 | note | Inspection Type - Review
7207ac8d-4cfc-500b-90b9-8982c89a55df | note | Inspection: Key - R
1786aa1b-777f-5b3d-a224-6fea71579c41 | note | Inspection: By - QM
| checklist | Ω (Deprecated) DG-OWR-CVSC-ITP002_v1 - Kerb and Channel Footpath for CVSC (v1) | itp | DG-OWR-CVSC-ITP002_v1 - Kerb and Channel Footpath for CVSC | 11d517a4-7ebc-49bb-bd62-d85084ef8317
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
7839c477-3f68-5863-83f2-8f8c86c02db8 | note | Specification - Downer
00af6407-d66c-54e5-a19f-63176fc421d8 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
8d582c39-77c8-539f-89ab-7a7525f16439 | note | Verifying Document - Survey Records
cfcf306a-4346-51a3-a1a9-95b081c5f401 | note | Frequency - Prior to Works
338da471-fdbe-53e9-8d04-9ee519f55c62 | note | Inspection Type (Visual, other) - Document review
b71470d0-ee98-56d1-9f3a-ecc6994d34b7 | note | Inspection: Key - H
d3b41964-8cef-5d43-86af-d50116041065 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
c60c6403-75c2-5c2a-9d7b-9ba34245dcdc | note | Specification - Downer
521f927d-60b4-5910-99f8-3480263c07ac | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
dab39c89-1f3d-5c33-a725-23f256e92199 | note | Verifying Document - Service location documents
3dd3564a-21eb-581e-87c2-b284813bd45a | note | Frequency - Prior to Works
1a66cf0f-cf0b-52d5-915f-20780169855a | note | Inspection Type (Visual, other) - Document review
1ec18220-2a4d-5643-ba25-a86b835f06bb | note | Inspection: Key - R
49759fd1-36df-56e7-af02-c65a635a6292 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
bd46b9c4-39dc-5720-a208-c6df1e3d221e | note | Specification - Downer
326762bd-e9c9-5498-aa48-ef1e9f1ad929 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
684f488d-f965-50cb-b2c1-2ccf95f9b6f9 | note | Verifying Document - Internal Permits
f9c4cb55-a5f8-5bdb-81f1-6610befa6214 | note | Frequency - Prior to Excavation
7f1c1e6d-9a63-5ea6-88e0-2443d5c6e4f0 | note | Inspection Type (Visual, other) - Document review
e4ac0d43-04f8-5283-81d6-00ef57ac67ad | note | Inspection: Key - R
4ff2cbee-a224-5fee-a37b-dce289320312 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
059eb996-b571-5082-8ece-914156cd14c9 | note | Specification - Downer
eb4872c1-c81f-5480-9136-ff2e9fe30f22 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
667b1893-10e5-55a9-b247-3d6b221abe67 | note | Verifying Document - External Permits
8ebf5752-583d-5c11-b921-589f2b05f3a8 | note | Frequency - Prior to Excavation
4fe94164-97c9-534f-b4af-37fe103e3994 | note | Inspection Type (Visual, other) - Document review
2c1a3483-9f79-500a-9988-5891b089cd1d | note | Inspection: Key - R
2bf120a4-1c77-50b2-8a6a-e69fd2b1890d | note | Inspection: By - SE
| checkpoint | 3.1.5 - Approved Construction Drawings
c08976a1-c093-58a4-b28e-859acafe46c8 | note | Specification - Downer
cb41c45a-a604-5c98-a122-252fb7e6e0fb | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
a264f198-b79f-5137-a8af-4bbc0e558b7b | note | Verifying Document - IFC Drawings
6580930d-8a47-536f-928b-e429e58d8317 | note | Frequency - Prior to works start
1e4f9b37-5871-5c9e-9637-6b35235f68be | note | Inspection Type (Visual, other) - Document review
7aed777b-6577-55fd-9ec1-07bddf2705b4 | note | Inspection: Key - R
aea21d33-9806-5774-a510-f5116f4546b5 | note | Inspection: By - SE
| section | 3.2 Receiving Materials/Parts - Kerb & Channel/Nib
| checkpoint | 3.2.1 - Concrete mix design
c74e0f1c-6a61-5756-8279-e558ed8eeb53 | note | Specification - Pre-construction
e30e6633-6e1b-577c-98ea-9518048f243e | note | Acceptance Criteria - 20Mpa concrete as per design notes
f1d539fa-eb31-5e3c-93ba-527c386f1edd | note | ○ Drawing/Notes Sheet No :C 5110
574a16f6-66c6-570b-b875-b3b841fe0281 | note | Verifying Document - Mix design
0e0a1b05-ec8a-54f4-a8fb-652845aeb198 | note | Frequency - Per type of mix
bc2a967f-156b-541b-bb63-95d0280b76dd | note | Inspection Type (Visual, other) - Document review
a1137fe1-2b70-52ff-8ba1-13e8f1babf47 | note | Inspection: Key - H
a1b88bf0-09b9-5a3c-8fa5-93bf3c90ee3d | note | Inspection: By - SE,CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.3 Receiving Materials/Parts - Footpath
| checkpoint | 3.3.1 - Concrete mix design
04c21977-6cd7-5ae8-a987-a6068d8ef7c4 | note | Specification - Pre-construction
f7bf7a5e-a358-525a-8589-4a3fdd8f4739 | note | Acceptance Criteria - 20Mpa concrete as per Civil Technical Spec Section 5.3
9165dd35-ac53-54c7-9286-244ade9e07a5 | note | Verifying Document - Mix design
45a25bb1-69e6-5b90-beb5-2b4ced4f35cd | note | Frequency - Per type of mix
06332fba-b74d-5fea-a8d7-6f735c2dc05d | note | Inspection Type (Visual, other) - Document review
47f14ffd-3aa0-5df7-8485-caf2ad72aee1 | note | Inspection: Key - H
41cd1542-a4f3-530c-b0d2-46d12107ab9b | note | Inspection: By - SE,CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - Steel reinforcement
22b5c654-ad01-5a86-ace1-88076b6a1f66 | note | Specification - Pre-construction
d4ad3f5b-7f75-5c4a-88da-6682f8904b1b | note | Acceptance Criteria - As per Civil Technical Spec Section 5.3
2d5548f6-d709-511b-b5ee-9250fb332eb9 | note | Verifying Document - Material Certificate/Docket, Photos
91f9c32d-6ace-5f6e-8541-3d601be3d70e | note | Frequency - Per Delivery/Batch
f94a0c11-311c-5ba9-842f-f8622a1fa620 | note | Inspection Type (Visual, other) - Visual, Document review
4e9b3176-a86b-5316-b2df-24443fb96c9f | note | Inspection: Key - R
4039d944-9be3-57ac-b1d5-45e7a428f565 | note | Inspection: By - SE
| section | 4.1 Kerb & Channel/Nib
| checkpoint | 4.1.1 - Service Location
1f5aaa14-4024-51e1-b7c2-35798af8e317 | note | Specification - As per TDS
4fff63ca-6880-5b5a-beaa-9ed00f02bc5d | note | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
8b63addb-cbc7-5061-af63-de0084e21779 | note | Verifying Document - ITP Sign Off/Photos
5112451a-0ec1-5747-ae81-eb85ea85dc45 | note | Frequency - Prior to the works starting
cedbf0a7-a9e3-5da6-bb75-a6325176933f | note | Inspection Type (Visual, other) - Visual Inspection
fe7ea36c-a714-5c44-beee-299a7d0fe2d3 | note | Inspection: Key - V
2e165d19-996e-56af-9002-0b496b32cb05 | note | Inspection: By - SP
| checkpoint | 4.1.2 - Kerb/Nib Location
fd734497-41c0-5a7f-9a5c-6207770ff189 | note | Specification - As per design
55bc2988-8939-575b-98a4-7fbccd5bc87c | note | Acceptance Criteria - Surveyor to set-out location of kerb & channel for foundation preparation
6ef4ea00-6874-50e4-b8a1-5a60a397fc7f | note | Verifying Document - ITP Sign off
93248885-0c5a-5653-afb3-36babb947e09 | note | Frequency - Prior to constructing foundation
d192063e-51e4-5d9a-bdcd-c1476ddd7e02 | note | Inspection Type (Visual, other) - Survey Setout
da69b574-e782-5e39-86dd-d3a19f1081d6 | note | Inspection: Key - D
56f713f3-7068-559d-9764-33692e796ec8 | note | Inspection: By - SV
| checkpoint | 4.1.3 - Subgrade Testing
02fe956f-2489-5fa3-a780-be5b081ecb51 | note | Specification - Construction Drawings Sheet No: C-5110
e49e012b-f2b2-576f-bddc-bc32f20ab3c4 | note | Acceptance Criteria - Clegg testing at 10m intervals
2ce12cf6-f90d-5999-8cf9-958c439c33bc | note | ○ Subgrade CBR ≥ 7%
f91dd6a8-adb5-5bd9-98e0-e961b519101a | note | Verifying Document - Clegg Hammer Result Sheet
03252b8f-8436-5d53-914f-6d95bfc88043 | note | Frequency - 10m Intervals
a3d429f3-901b-5c38-90d7-79fb3230d5a9 | note | Inspection Type (Visual, other) - Subgrade Compaction Testing
778f9368-15c2-5d62-a0d9-5c5dce39e876 | note | Inspection: Key - H
6226ae3b-3a6b-5f24-afeb-0d2c321b3109 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Foundation Preparation and Asbuilt Survey
a90862c6-8956-5746-aa02-bbae326b1f97 | note | Specification - Civil Technical Specification Section 4.3
3db00ac8-8eca-5f8e-8291-453873551802 | note | Acceptance Criteria - 300mm of AP65 or cement modified basecourse
fe21b821-8f52-5bcf-85eb-81ee05dfab35 | note | Verifying Document - Photos & Asbuilt Survey
7943bcdc-d044-5367-8809-5f41ffe70489 | note | Frequency - 10m Cross Sections
a597d950-82fd-5188-922a-2e88447094bd | note | Inspection Type (Visual, other) - Dimension Inspection
b28078fa-1a27-568a-806d-32abb929b61b | note | Inspection: Key - D
a892e343-0311-5bda-b81e-1e0e71f81684 | note | Inspection: By - SV
| checkpoint | 4.1.5 - Foundation Testing
06463ed7-3b4e-5b80-b227-2127cfcd7f3a | note | Specification - Civil Technical Specification Section 4.3
b7b01999-c0b9-5a41-927c-8e9245b8bc0a | note | Acceptance Criteria - Compacted to a minimum dry density of 2100kg/m3
2f4566cd-669f-5872-ba03-7c75d5ebbbfa | note | ○ In accordance with NZS 4407: NZ Heavy Compaction
c0778441-150d-5091-9770-c933dd65e1b2 | note | ○ Results provided to Engineer to proceed
b2f1eb3f-233e-54e6-a6d7-bee40e8e1655 | note | Verifying Document - IANZ Accredited Laboratory Report
a26142a5-2465-5d8a-918e-5bbafee617a5 | note | Frequency - 10m Intervals
1c6ea4b9-4ba9-53ac-8c0f-83604e681560 | note | Inspection Type (Visual, other) - NDM Compaction Testing
12a79d78-88bf-5e22-b1f5-5cc251fd6d04 | note | Inspection: Key - H
362462c8-6e53-5c17-8b82-c6c3639b2bfb | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Kerb/Nib Setout
345aade0-3a8f-56ac-a804-f5d5f8f85638 | note | Specification - As per design & Construction Drawings Sheet No: C-5110
4fa0bd3a-21dd-543d-84a3-da403376ee80 | note | Acceptance Criteria - Surveyor to set-out stringline of kerb and channel.
a98f88a8-e9d0-5e97-a066-17b97399b053 | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No: C-5110
bae1914f-e686-59aa-8f20-b3d2f8f1a055 | note | Verifying Document - ITP Sign Off
a8abfab9-b046-5018-99ed-187f8f75037d | note | Frequency - Straight: 10m Intervals
f6369e1f-ecd9-52ea-8142-d27733ea4b27 | note | ○ Curve: 2m Intervals
4eed8e4b-9bbe-5fc1-a78e-3400946ff058 | note | ○ Survey every tangent
33144772-0520-549a-b940-fbed5ce7b504 | note | Inspection Type (Visual, other) - Survey Setout
8763ce7d-657c-56ba-a384-b612685eddcd | note | Inspection: Key - D
49979ba7-379f-5192-81dc-48ce995554d0 | note | Inspection: By - SV
| checkpoint | 4.1.7 - Heavy Duty Vehicle Crossing
41737162-95ae-55c5-890c-a00667d56ac0 | note | Specification - Construction Drawings Sheet No: C-5110
09635f20-253a-59bb-9998-84e684c06a62 | note | Acceptance Criteria - Construct heavy duty vehicle crossing including reinforcing steel as per standard detail in Construction Drawings Sheet No: C-5110
1eabdd7c-f5f7-593e-924b-ecae990582e9 | note | Verifying Document - ITP Sign Off/Photos
8011bd4f-14b0-5d15-8c00-08dc1dc777ee | note | Frequency - Prior to pouring the concrete
ab284e09-1124-55f4-a176-d0abc9b172d1 | note | Inspection Type (Visual, other) - Visual Inspection
0886ed99-4585-5933-9825-1d652a1083ed | note | Inspection: Key - V
5a16d6d2-ab3f-55e7-b93b-928089108feb | note | Inspection: By - SE
| checkpoint | 4.1.8 - Pre-Pour Inspection
3cdea2ca-de62-5eed-929d-35f35a929604 | note | Specification - As per TDS
6bb8cba2-d093-5ae8-b789-ae1e9af1ff69 | note | Acceptance Criteria - Stringline Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
66f902ee-57e8-5699-af71-323d1ccdc910 | note | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
6e776dee-1372-584d-ac3f-0f5e15da9101 | note | Frequency - Prior to pouring the concrete
fd3549f0-79c7-5052-a30d-abf6cf3f58b8 | note | Inspection Type (Visual, other) - Pre-pour Inspection
d0f1f9af-1378-5cc3-945a-af1649692ffd | note | Inspection: Key - H
f25df219-21d7-554b-a4fc-edf54ab76094 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.9 - Supply and Installation of Concrete
18a71490-e936-58aa-9f64-4c9da72e4ced | note | Specification - Civil Technical Specification Section 4.3
150579ab-8e67-5fdb-b094-516292671b3c | note | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
8ce631aa-1717-581e-93f5-2b9808b830f9 | note | Verifying Document - Mix Design Certificate
72ac6398-689c-5e3c-8ec1-e40b66e7cd4d | note | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
092f3e45-f3a6-5feb-96e3-7dff280493c1 | note | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
08ec5d09-8abb-5efd-a10a-0e83084dddcb | note | Inspection: Key - R
981c70e9-cafa-5381-9eca-13d97f7abad9 | note | Inspection: By - SE
| checkpoint | 4.1.10 - Concrete Testing
f05d64db-c102-504b-9ea8-9f749b4fe82d | note | Specification - Civil Technical Specification Section 4.4.1
6a33e3a3-abca-52f1-8ae3-0fc358d07f81 | note | Acceptance Criteria - In accordance with NZS 3109 and NZS 3112 Part 2 Section 9
c5e3148d-bcb5-549d-b5ae-8962efed6aff | note | Verifying Document - IANZ Accredited Laboratory Report
c7aac591-bae8-57f6-a501-39943a8c244d | note | Frequency - Minimum of 1 every 50m centres
460fa394-6bde-5ecd-8253-109977c0f3b9 | note | Inspection Type (Visual, other) - Core Compressive Strength Testing
26b838d2-c5f4-5d98-9706-f20e3df74acb | note | Inspection: Key - R
87a806ac-089c-52c1-942c-6764457254d8 | note | Inspection: By - SE
| checkpoint | 4.1.11 - Concrete Surface Finish
10122327-cc6c-5fe9-95e9-f30a41c130b5 | note | Specification - Civil Technical Specification Section 4.2
c3554255-4d27-5c73-a42a-2d15d00a8951 | note | Acceptance Criteria - In accordance with NZS 3114
f326930e-4eb8-56e8-93c5-870bf3fa46c7 | note | Verifying Document - ITP Sign Off/Photos
22ebedc3-342d-5df5-9e22-cf251683bc4f | note | Frequency - Every Pour
b5b7c980-282a-512f-8f1b-cf86b0931ed7 | note | Inspection Type (Visual, other) - Visual Inspection
56c681a7-e137-5470-a12b-328a998d1d14 | note | Inspection: Key - V
e40feae8-a597-592e-b0f8-fbedb81a8506 | note | Inspection: By - SP
| checkpoint | 4.1.12 - Construction Joints
18c8a258-1500-55ba-ae4b-29c072c63052 | note | Specification - Civil Technical Specification Section 4.3
3efe6c45-36f6-546b-8fc9-2f048dbf1c18 | note | Acceptance Criteria - Construction joints shall be installed in all kerbs and channels at 5m centres
b6e2e9ce-076e-52b6-b502-3c3ac9a89079 | note | Verifying Document - ITP Sign Off/Photos
7fa46d91-2f59-5356-9c15-750b94577f46 | note | Frequency - 1 every 5m centres
fd30d94a-4a88-5875-a9c4-9a5d14dea4a3 | note | Inspection Type (Visual, other) - Visual Inspection
2f2cee69-3a0c-508d-8e1d-0cb043df2a65 | note | Inspection: Key - V
dae11711-7ef6-532a-85cd-73f2bafbd200 | note | Inspection: By - SP
| checkpoint | 4.1.13 - Concrete Docket Tally
59634e49-64d4-5344-adb3-f7d9ad9bf088 | note | Specification - As per TDS
4f39b7b3-95f4-5511-8929-bb86a8fe931a | note | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
371d8d3c-5fa3-55fb-a607-8b571eafa6f3 | note | Verifying Document - Dockets
6aa3efc3-ece8-5106-beaa-c5eb7d74d606 | note | Frequency - Daily
f7fa6b06-04cd-57db-85b9-6bded34c1d1c | note | Inspection Type (Visual, other) - Check
26ae98f9-d3dc-5e02-8de6-de8f7fb18eb1 | note | Inspection: Key - C
00296afe-df88-512b-964c-d62f471ff9fe | note | Inspection: By - SE
| checkpoint | 4.1.14 - Asbuilt Survey
376a4956-3403-5288-92fc-78f7544cfff4 | note | Specification - Civil Technical Specification Section 4.3
c4e279d7-290c-506f-b0fd-e6516fc55348 | note | Acceptance Criteria - No discrepancies of greater than 6mm in line or level in any 3m length
0bed9583-20e2-5dda-b08f-bb384a5fbaa7 | note | Verifying Document - Asbuilt Drawings
bd4ec7b3-1da9-50e8-82fc-b62631450a0f | note | Frequency - Straight: 10m Intervals
579eaa50-3acd-5170-9479-37d2737c252e | note | ○ Curve: 2m Intervals
45fec357-b4a7-5f75-a35e-2a46aa8ab9bb | note | ○ Survey every tangent
98494e0d-f4bc-5dc0-87b7-9e2f606447c6 | note | Inspection Type (Visual, other) - Survey Asbuilt
2b4e634d-a31e-55b8-a278-71a19583a8e5 | note | Inspection: Key - R
80a98c37-fd88-5503-8365-c65c7950771e | note | Inspection: By - SV
| section | 4.2 Footpath
| checkpoint | 4.2.1 - Service Location
d5b24570-5531-5a35-a403-e02ffce59726 | note | Specification - As per TDS
0e2233b4-6f85-5d29-b2db-26120bc21674 | note | Acceptance Criteria - As per project specification locate on site 4 weeks prior to construction
da37338c-0d22-5acd-bdfa-457712cee35f | note | Verifying Document - ITP Sign Off/Photos
46abb3ff-d783-5319-8d1f-6aea04ac92b6 | note | Frequency - Prior to the works starting
50188652-79e8-5f19-8549-fcd323d9e374 | note | Inspection Type (Visual, other) - Visual Inspection
edc22370-ee4b-5d3e-9cf3-97969f98806e | note | Inspection: Key - V
c9cb6be2-5cea-50cd-b103-289b583361bb | note | Inspection: By - SP
| checkpoint | 4.2.2 - Footpath Location
320825be-e82d-526f-95f9-fb333b953688 | note | Specification - As per design & Construction Drawings Sheet No: C-5111
1f3291f8-7414-55a7-93c7-bcecac5b6c36 | note | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
57e8dc21-339b-5cc4-a727-332456fc3cbf | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111: Height 100mm, Width 1.5m, Slope 2%
f4d84854-9eda-5820-953f-fb03344bc983 | note | Verifying Document - ITP Sign off
0307b29c-ce4c-52e2-be3c-3770f12781df | note | Frequency - Prior to constructing foundation
4b22cdd2-6f64-52e2-a8ea-26351acbd936 | note | Inspection Type (Visual, other) - Survey Setout
17ba3d36-0a0d-5c6e-af0b-0a7752edb72f | note | Inspection: Key - D
8d1b3574-b1e9-5606-930c-23acdb7545b3 | note | Inspection: By - SV
| checkpoint | 4.2.3 - Accessible Ramp Location
daee2d32-52f2-51e8-9ea8-9ef96ed9a40f | note | Specification - Construction Drawings Sheet No: C-5111
bf9efe23-8819-5bac-9bbb-cd2413ff4600 | note | Acceptance Criteria - Surveyor to set-out location of footpath for boxing and prepping.
4038d366-6be8-5fbc-a22e-901a3626dc63 | note | ○ Dimensions as per standard detail in Construction Drawings Sheet No. C-5111:Slope 10%
f68022ae-47c4-57b1-8bb8-ff3043bf525c | note | Verifying Document - ITP Sign Off
8c3e3da9-7c9c-5021-9956-b1122be6a1a6 | note | Frequency - Prior to constructing foundation
6d84f8a4-ca88-59a9-83f4-bef60ef598ea | note | Inspection Type (Visual, other) - Survey Setout
f3c0a0c6-21c4-591e-ad1d-ec0b5110229b | note | Inspection: Key - D
bf5bf0a6-c456-5579-931d-d50827045072 | note | Inspection: By - SV
| checkpoint | 4.2.4 - Subgrade Testing
4fa9aa92-95c0-5a0b-b48c-16227042e448 | note | Specification - Construction Drawings Sheet No: C-5111
ddb498e5-7273-5bf3-92f0-f418ba219068 | note | Acceptance Criteria - Clegg testing at 10m intervals
cfab6fee-9b7a-50a2-a381-9fe933e5e1e6 | note | ○ Subgrade CBR ≥ 6%
73cb1738-d207-5db0-889f-496cec28cf9f | note | Verifying Document - Clegg Hammer Result Sheet
cce096ce-b15b-5154-b12d-3f215853f7d7 | note | Frequency - 10m intervals
182be0dc-bc70-528d-8902-620ce8fd1716 | note | Inspection Type (Visual, other) - Subgrade Compaction Testing
c2e60c7a-ca24-5d3f-a9c9-30f000436b55 | note | Inspection: Key - H
6741b4e3-6ab0-5677-9a31-3ea42ff04bdd | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.5 - Foundation Preparation and Asbuilt Survey
27720868-7ec9-5763-9bed-6ec66fba173f | note | Specification - As per design & Construction Drawings Sheet No: C-5111
48934c04-57d6-5040-8932-204f11d5add4 | note | Acceptance Criteria - Minimum 100mm of M/4 AP40 Basecourse
98b49e1d-0561-52ab-9ddc-c3f162c6799c | note | Verifying Document - Photos & Asbuilt Survey
883c086e-515e-5b86-8589-ce3a205ad421 | note | Frequency - 10m Cross Sections
6a5d1c6c-c7ee-56bf-88a6-0d9576f1fb0d | note | Inspection Type (Visual, other) - Dimension Inspection
f0511ae2-27cb-551e-bffa-f270fc256cce | note | Inspection: Key - D
3fd7f1be-a457-5735-8cf3-2cd24a430dd9 | note | Inspection: By - SV
| checkpoint | 4.2.6 - Foundation Testing
ab4cffb4-10a6-5afa-ae16-45e6b466a424 | note | Specification - Civil Technical Specification Section 5.5.1
2575328c-4703-5a65-81a6-35bf4c795e8b | note | Acceptance Criteria - NDM testing to be carried out by IANZ accredited laboratory. Site plan to be provided to Engineer showing every test point. Minimum acceptable result shall be 95% of the suppliers specification as per approved JMF.
08ff6a18-7d5c-5c6d-80fc-29a55e632483 | note | Verifying Document - IANZ Accredited Laboratory Report
b785ad72-38ca-5908-a9cf-cdd01b6fc2fc | note | Frequency - 10m intervals
8a49d980-4120-54e7-88a4-8186050a554f | note | Inspection Type (Visual, other) - NDM Compaction Testing
a99a2845-fe28-557c-9985-0e1256de571c | note | Inspection: Key - H
6913df6e-8ce7-51d7-bbb6-35c8e4610c69 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.7 - Foundation Testing
e10a3343-928f-5af1-abb5-7e8db09802c9 | note | Specification - Civil Technical Specification Section 5.5.1
a5d281f6-90b9-5ace-9786-88fea426ae51 | note | Acceptance Criteria - NDM testing carried out by approved user within Downer (with approval from Waka Kotahi) Min. Acceptable Compaction ≥ 95% of Target MDD
4d0ae3fa-7dc6-53e6-ac53-67512f06ca58 | note | Verifying Document - IANZ Accredited Laboratory Report
356a7245-aeb6-5353-8484-33897235eece | note | Frequency - 10m intervals with surveyed test point locations
47f037e8-16c1-50c6-924e-c44e012afbc1 | note | Inspection Type (Visual, other) - NDM Compaction Testing
f2e21701-df50-5c2b-9e10-052d930296b0 | note | Inspection: Key - H
8ddaad4c-4f43-5b31-b868-14de6cadff3c | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.8 - Foundation Testing
a13a9a24-7a95-5b65-a69d-a974ee68bdd5 | note | Specification -Civil Technical Specification Section 5.5.2, NZTA T/1
61b0822f-3f5f-5413-8e72-fd48ca74169f | note | Acceptance Criteria -Deflection testing shall be carried prior to kerb and channel being formed.
2266a154-6c2c-5ab9-8952-92169199b456 | note | – Allowable deflections are as follows:
de4c0721-dbdb-54e1-bf5d-c9432b69475b | note | ○ 95% of readings < 2.0mm
c8cf6f5f-e71b-5d0c-af5c-f2012b183aa5 | note | ○ Maximum reading of 2.5mm
097fa487-1e9f-5904-977f-2b3e1f56cd51 | note | Verifying Document - IANZ Accredited Laboratory Report
d668450e-ca47-55bf-97d7-6d6cb07a786b | note | Frequency - 10m intervals with surveyed test point locations
28689073-450b-5135-8113-414b558167e2 | note | Inspection Type (Visual, other) - Benkelman Beaming
9b2682ca-cf7d-5524-929a-347ec98f4aea | note | Inspection: Key - H
29c57450-f85c-5e82-a9ed-706e5ac5404b | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.9 - Formwork
52b5036b-23e2-571d-80fc-a1daf7125736 | note | Specification - Civil Technical Specification Section 5.3
08f085fe-cb71-527b-9864-28d22117abfb | note | Acceptance Criteria - In accordance with NZS 3109. Finished level of formwork shall be within +-10mm of design. The line of the formwork shall be straight with the maximum deviation from a 3m straight edge along the face of 5mm with a cumulative total of all visible gaps of not more than 10mm.
593a748d-d7ac-5f16-a022-b3dbecb45c2e | note | Verifying Document - ITP Sign off
08ccb90a-978f-59b6-9ed9-d2cd14c5c4ef | note | Frequency - Prior to pouring the concrete
661c08ad-dc54-529f-a888-79c4012f0f75 | note | Inspection Type (Visual, other) - Survey Setout
68753bf5-5678-5598-9782-8dd155043479 | note | Inspection: Key - D
a1351f1c-1d44-5717-a462-a80c3e37a241 | note | Inspection: By - SV
| checkpoint | 4.2.10 - Reinforcing Steel
5ab72423-2d56-58e2-8f6a-13a478cfbd9c | note | Specification - Civil Technical Specification Section 5.2
ced0a628-2d58-5277-ac04-c1473e09a9b1 | note | Acceptance Criteria - Reinforcing steel in accordance with AS/NZS 4671 Grade 500E Steel
149b00ed-ae6a-5698-85c4-785717a3550a | note | ○ Welded wire fabric in accordance with AS/NZS 4671 Class E smooth
818669ff-c81a-54cd-b43c-cd8e91001838 | note | Verifying Document - Dockets & Photos
93e05def-0a4d-58dd-9e53-e84ac0faf3e0 | note | Frequency - Per batch/delivery
0bb501b5-469c-518a-bbf2-a76db510e9b2 | note | Inspection Type (Visual, other) - Check
fb80e8c3-41fe-5f20-aa24-cf20b91abaf6 | note | Inspection: Key - C
8b34decc-ea03-58ec-a0e8-fbfd6e05d414 | note | Inspection: By - SE
| checkpoint | 4.2.11 - Pre-Pour Inspection
9bc89ddc-6730-5c12-9821-f7571f9b4661 | note | Specification - As per TDS
7e5c5e1f-6821-59bb-8ae4-e12a1e270ba8 | note | Acceptance Criteria - Boxing Check, Concrete Pour Inspection Checksheet completed, and Written approval from Engineer to proceed
68ec629c-4ba1-5a5c-8e8b-2d34f21e3345 | note | Verifying Document - Checksheet: DN-QC-04 & Written Approval from Engineer
c5ef0ff2-739e-5cae-848a-181ba6fed37f | note | Frequency - Prior to pouring the concrete
7182bc6c-b4e2-5203-86c8-e44cb8c492c0 | note | Inspection Type (Visual, other) - Pre-pour Inspection
9b3fc240-5b9c-507e-a7f0-daeea61c692d | note | Inspection: Key - H
33f7a7b4-85ed-5908-b1f7-9307b5c33c34 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.12 - Supply and Installation of Concrete
9732d647-3250-5eb5-8bbf-9e993cbcb44a | note | Specification - Civil Technical Specification Section 5.3
ce787dbc-8f90-530b-8d1b-77cfdcea74cc | note | Acceptance Criteria - 20MPa at 28 Days. Concrete strength & slump testing certificates obtained from concrete plant and submitted to Engineer.
f17e8b9c-def5-5cd5-8780-0100ffff3cbe | note | Verifying Document - Mix Design Certificate
d70180a0-96e0-51ce-a6f9-5e8f2783f7a8 | note | Frequency - 1 Test per batch/delivery, 1 Sample @ 28days.
e4ca07c4-aee2-59e3-93b3-e020e84dfc4b | note | Inspection Type (Visual, other) - Concrete Strength & Slump Testing
468ae64c-5940-5b15-a0a5-d1e7c2c5981d | note | Inspection: Key - R
5af49411-67ff-5a41-b603-d19cab6df867 | note | Inspection: By - SE
| checkpoint | 4.2.13 - Concrete Surface Finish
2a50ae01-66b6-52e1-bcb9-4a9ce55506a0 | note | Specification - Civil Technical Specification Section 5.3
2e40d385-a8d4-5d7c-869f-26572dbc8662 | note | Acceptance Criteria - U5 finish in accordance with NZS 3114
4d1f9e41-a45f-5ad4-a885-d5b9e22d3fd5 | note | Verifying Document - ITP Sign Off/Photos
5c32132f-7bb2-56b9-bb14-50a9dd7cae7a | note | Frequency - Every Pour
29fa07b0-caca-5394-8ea9-a42faafe969c | note | Inspection Type (Visual, other) - Visual Inspection
6e140252-80b4-5ecd-a2f2-e9cb67229950 | note | Inspection: Key - V
16e63b7f-7dc5-5854-a03d-1bc8809677a6 | note | Inspection: By - SP
| checkpoint | 4.2.14 - Saw Cutting
d95046f4-254d-5d76-9135-2c67651647e4 | note | Specification - Civil Technical Specification Section 5.3
fb8e90eb-4ef9-576d-af64-c58125660acd | note | Acceptance Criteria - Grooves to be between 1/4 and 1/3 of specified depth of slab, and any convenient width greater than 3mm. Max spacing of saw cuts shall be 3m.
00ad1ca3-3189-58b0-8887-c7e408f46a3b | note | Verifying Document - ITP Sign Off/Photos
21fe1d4b-19d8-50f9-bd50-cea73edcb466 | note | Frequency - No more than 3m Intervals
c41bc972-b92d-52c6-95fd-634e9a03d095 | note | Inspection Type (Visual, other) - Visual Inspection
10f1c465-8940-523f-922b-c3cd71a47a42 | note | Inspection: Key - V
4b995e4d-9355-5222-9d6e-7d51ca114e9d | note | Inspection: By - SP
| checkpoint | 4.2.15 - Concrete Docket Tally
fc8796a6-8dc6-56b4-8261-b87d7ddba78e | note | Specification - As per TDS
c3473dc0-de9a-5c33-a60e-d03a32c95914 | note | Acceptance Criteria - All concrete dockets to be collected on a daily basis and provided to the Site Engineer
ee96a538-dc8c-5298-a5f3-6e4f20db719d | note | Verifying Document - Dockets
4630ec4f-6ec4-5ea2-b7cb-574d875619d2 | note | Frequency - Daily
d56d5f32-3d59-5082-8bdc-e892201fba72 | note | Inspection Type (Visual, other) - Check
354a077a-a97a-5c4e-903c-04bdffc359c5 | note | Inspection: Key - C
9acd30b7-dae8-5584-94ae-0bbd3a2f1991 | note | Inspection: By - SE
| checkpoint | 4.2.16 - Asbuilt Survey
fa1a5b49-13b7-543a-ae54-7334aae2211b | note | Specification - Civil Technical Specification Section 5.1
a13112d2-bebb-5960-9abe-8e1831fb2fc8 | note | Acceptance Criteria - In accordance with requirements of the TA Minimum cossfall of 1%
5a749948-c595-5e76-91ed-353c528e9ddc | note | Verifying Document - Asbuilt Drawings
f46e9573-0348-5c22-8508-a1d7c77ec2e4 | note | Frequency - Appropriate intervals to represent asbuilt footpath
07169593-0a45-51e6-aa87-e09705eed07f | note | Inspection Type (Visual, other) - Survey Asbuilt
9469631b-2860-5bbb-ab2d-c54ea8407083 | note | Inspection: Key - R
e5c0e466-64d4-5489-8a17-8cd88857711b | note | Inspection: By - SV
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
3dc9693e-e4e0-5a84-995d-a12bc8876168 | note | Inspection Point: Quality Control Activity - Upon completion of works
ad874bb6-2d5b-5a94-9009-05321173874b | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
6e28c4bc-c0c8-504c-a873-17926bbb0170 | note | Verifying Document - Closed-out NCR/Defects
58bebf46-5a67-5f81-9b81-b94b54733520 | note | Frequency - Post construction
ec7307d5-9a08-5636-bcc3-83c48e576e2c | note | Inspection Type - Review
d7f9263d-379a-5918-afab-1c53c2a8e26b | note | Inspection: Key - R
ec968c67-ab49-5efc-8774-11396e8e62a2 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
6ac69cfa-cd32-5607-a4a0-0ea0342c6e4f | note | Inspection Point: Quality Control Activity - Upon completion of works
754b7c1f-68b9-5c40-bb4c-3668166b263a | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
1beaeaa2-5784-5968-bea3-c81d72f6548c | note | Verifying Document - As built survey record completed
3b834d10-d0b2-5ff1-b2ca-2f4e251125c5 | note | Frequency - Post construction
1cfcbc31-03a8-5ba9-91ea-0f28d3e1a286 | note | Inspection Type - Review
ac4f481f-100f-50eb-8949-74733015cdfb | note | Inspection: Key - R
1a019322-bad3-5594-9630-581f08498736 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
31d2fdf8-4a73-5deb-87ce-038dddfe6095 | note | Inspection Point: Quality Control Activity - Upon completion of works
611cde1f-7e23-5afc-a508-3bce08dc086d | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
74495633-cb90-5ff3-a17b-42bd957c8bfa | note | Verifying Document - Signed As-built Drawings
0341d3cb-972a-5262-8fb7-fc265db9ba33 | note | Frequency - Post construction
6f8a6be7-c651-5033-8f72-f0ea5eab9b2e | note | Inspection Type - Review
2733f5aa-d4a5-59b7-9101-99a7a2c5db55 | note | Inspection: Key - R
4547b8e0-2639-5603-8687-b56e0de6c7ad | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
4b5e5410-d548-5a63-ba20-dde67a2a64c3 | note | Inspection Point: Quality Control Activity - Upon completion of works
fcf7285c-5bd6-5f64-95da-38dc232410ea | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
3fa0482a-808e-5f32-838a-dcd2547035f6 | note | Verifying Document - Register
fc6939ff-821b-5dbd-ac92-0250f6992a36 | note | Frequency - Post construction
fd9f7e9a-01e6-5c58-8a05-b5827f62d91c | note | Inspection Type - Review
d7aff917-b1ad-5afc-9451-063b1a461901 | note | Inspection: Key - R
e07b6042-b815-58f8-806f-c9238a86794b | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
ae53e2f6-0970-5056-88d3-b04314aec63d | note | Inspection Point: Quality Control Activity - Upon completion of works
e900ac6a-aef0-5d69-8d12-b2954044ce4c | note | Acceptance Criteria - All signed and closed out
7b326107-1925-59b8-9319-274c61eb7f8b | note | Verifying Document - Signed off Documents
f452f2e4-84e2-54b0-ba8e-031d5494b4c4 | note | Frequency - Post construction
c8ac1681-c866-554a-81aa-e18af7cbfd6d | note | Inspection Type - Review
31d6cbe4-9902-5af2-b980-0d7527bd8b14 | note | Inspection: Key - R
e88afa6c-614f-5f92-9664-693e86d18f3b | note | Inspection: By - QM
| checklist | Ω (Deprecated) DG-OWR-CVSC-ITP003_v1 - Pavement for CVSC (v1) | itp | DG-OWR-CVSC-ITP003_v1 - Pavement for CVSC | 792bf593-b798-42a6-8737-e5a197e6b7a3
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
e1e7df34-234e-5f56-8918-d8758788a735 | note | Specification - Downer Standard
5cbd0069-94de-512d-899c-388abdf5d689 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
28db0eb2-e337-5cd1-989c-9dc8a63e79bf | note | Verifying Document - Survey Records
d2e3afe4-b08a-5558-a93b-323d4a25e5c0 | note | Frequency - Prior to Works
d4f73d65-9bb9-57e7-9379-b18bd84a08dd | note | Inspection Type (Visual, other) - Document review
91e58f1e-222b-50d4-882f-6e4c38dc4e52 | note | Inspection: Key - H
73c891cd-f3dd-5306-84d7-1cc511e3422e | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
a8dc4950-797d-5672-8226-76d4a1e68fb2 | note | Specification - Downer Standard
44014587-813f-5296-a1e2-9050b653e2c4 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
5bf9f472-526d-5278-be87-91d42fcee67a | note | Verifying Document - Service location documents
1da1b8f1-62f7-5ea2-b6ea-b816b2df21f7 | note | Frequency - Prior to Works
350deaad-b5b6-5b72-95fd-a0ed7a29cd1f | note | Inspection Type (Visual, other) - Document review
38c2fe85-1929-561f-add6-bf1fb0ca0b30 | note | Inspection: Key - R
11f376b3-46d2-5eda-9276-b00c4ecf57d5 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
c8ca52d3-d33d-59f5-9cac-519a9c5b56f8 | note | Specification - Downer Standard
b9ff61ac-d75a-5255-b32b-60f425a1553e | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
56392180-17fb-568f-8ee4-9d2b03333f73 | note | Verifying Document - Internal Permits
afff1ea5-07a2-5ee7-b0de-4835cfe8fe1e | note | Frequency - Prior to Excavation
e37a1da6-5445-5729-a40b-43007104f19b | note | Inspection Type (Visual, other) - Document review
d184ee30-134d-577d-8556-e2b9cbc24219 | note | Inspection: Key - R
6604d2b1-c970-51b7-8c29-b3d1c50842c4 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
87ad132f-000b-57b6-a205-a110e592a1b4 | note | Specification - Downer Standard
cc135626-2c6b-57c4-b618-6ab3fd679867 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
1d4fee9f-6020-548d-83d6-538f5f066ecb | note | Verifying Document - External Permits
1b219dbc-6187-548c-89a8-f46cccc7dc5e | note | Frequency - Prior to Excavation
2e3e7053-9ab9-56c2-b406-1979f108b030 | note | Inspection Type (Visual, other) - Document review
292ac3ab-98c9-5537-8671-84d897803ed8 | note | Inspection: Key - R
b0dd04d3-393c-5230-9fb2-8f07828419d1 | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
23c94754-4343-5792-b38d-480be86d3ee8 | note | Specification - As per contracts
1f1139bf-31d1-5bf3-8438-f6b5f2b17570 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
5c627c95-17c6-58cf-a5a4-40d84997a9ac | note | Verifying Document - Approved ESCP plan
e6b4b1c3-5c43-534e-8050-f208f4f33e9d | note | Frequency - Prior to Works
fda4497d-06a2-5636-bc16-3b2574f3595e | note | Inspection Type (Visual, other) - Document review
054ad1b2-6ef0-5c98-85f2-90d686ae0a63 | note | Inspection: Key - R
3369c131-a089-5db3-92dd-5f4f75aada1c | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
519e5346-d247-5e1d-a70d-d865d0dd706d | note | Specification - Downer Standard
405a79a6-ab4b-5cdf-ab60-2c9d15368479 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9a7ca7c3-b083-52fc-a673-6411c3f9503b | note | Verifying Document - IFC Drawings
891b9ec4-9107-5728-be2c-970b0045b5a0 | note | Frequency - Prior to works start
9af835c8-46f2-5484-a097-8aa7d38072a7 | note | Inspection Type (Visual, other) - Document review
108f9642-9168-548a-9e68-8d1cec40d4f8 | note | Inspection: Key - R
3725e88b-c6fd-5648-a0ab-348684f185c0 | note | Inspection: By - SE
| section | 3.2 Pavement Materials
| checkpoint | 3.2.1 - AP65 - Source Property Tests and Sampling
7e1b270b-408c-5b4e-bf14-b228ee5f9cf0 | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991, NZS 4402 : 1986
b4f98168-5fdf-58e7-958c-8a0c6d9577d6 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
afbaf291-b6cc-5b8b-8138-3dee8d2c4837 | note | Verifying Document - IANZ Lab Reports
c179cb07-9da5-50db-8d2e-442c390418d9 | note | Frequency - 1 per source
7d99980f-0a95-55e8-9bbf-3b8729a72b6f | note | Inspection Type (Visual, other) - Document review
fced344f-6702-5aa8-b5e8-c7ef0f13ca9d | note | Inspection: Key - H
9160f267-a8f6-574b-8800-55f645f1ef0f | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - AP65 - Production Property Tests and Sampling
82e0064a-9598-537b-824f-7e6b2d93e58b | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
0373d58b-45ab-54a1-8ea3-73913510c622 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
e0e16c80-2fc7-5257-a7c3-d4de8d4dfce6 | note | Verifying Document - IANZ Lab Reports
d2fad14d-bb0a-5293-b344-84de15ffdc4f | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
d83e307a-345f-5970-b867-de9965e8e5c9 | note | Inspection Type (Visual, other) - Document review
6faa0a71-d082-573c-be79-16e8942ae49d | note | Inspection: Key - H
2a561920-f314-5f9f-bbc7-25ee13c6168a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.3 - AP65 - Testing for Layer Compaction - MDD
486757b4-e5d9-5950-9a50-f82e67001454 | note | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
0b2e0798-41cf-539e-a55a-92936ea59122 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
8f12ce18-67b3-594d-848c-4ce77e11e682 | note | Verifying Document - IANZ Lab Reports
0b2443d2-538c-5b91-bd8c-6b83f4f12751 | note | Frequency - 1 per material source (stockpile sample)
e78e42b5-40c2-5a57-b829-ce74ba09b027 | note | Inspection Type (Visual, other) - Document review
de7198c1-7896-5d2b-81b9-eb66e2591e4f | note | Inspection: Key - H
1cb96e68-7d39-5d17-ad2b-0535be54cd81 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.4 - AP40 - Source Property Tests and Sampling
4f8b6fd9-ed83-544f-a6f2-dcba139b97d0 | note | Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991 NZS 4402 : 1986
cb9ceef7-7ad6-5774-8e05-22a2a4235456 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
1963d769-d1dd-5181-97c9-1e95df197c1b | note | Verifying Document - IANZ Lab Reports
1e7c51c3-1b9f-5185-8e1b-43229de2f853 | note | Frequency - 1 per source initially, then 1/1000m³ (stockpile sample)
ef42cfa8-f390-5ea5-acc0-48078f4d8213 | note | Inspection Type (Visual, other) - Document review
258abc30-1e9f-5ade-a37a-fab089c7b15d | note | Inspection: Key - H
49a356ee-7c8e-5f6a-84ad-9ca5f9dd880a | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.5 - AP40 - Production Property Tests and Sampling
b2d3fbd6-f79d-53ad-b476-5c92015269c3 | note | Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
5d805ac4-8e03-56ce-b6fe-748652d1eb24 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
d317ff76-53a9-54d0-8bdc-ef672787c123 | note | Verifying Document - IANZ Lab Reports
6446ca4d-9d93-5da1-9dde-1fb6a4c7b045 | note | Frequency - 3 per source initially, then 1/1000m³ (stockpile sample)
2ed9cd79-ba60-5571-8f8b-5937145f254d | note | Inspection Type (Visual, other) - Document review
cd94ae7c-6da9-56c3-8e07-61c20ef08f46 | note | Inspection: Key - H
83fe76ef-efcc-5544-ac35-a7bae3355723 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.6 - AP40 - Testing for Layer Compaction - MDD
ade9094b-ed49-5044-a6d3-858d499825f7 | note | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
bcc5d34e-63e4-54da-b34c-050ff5ef124d | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
f2500f74-011f-560b-a020-c1e2c2f35013 | note | Verifying Document - IANZ Lab Reports
2eaf91a8-e610-5eda-beb9-4e97555d64ec | note | Frequency - 5,000m2
2a80d207-2732-5587-a948-3cd0c530c7ec | note | Inspection Type (Visual, other) - Document review
3af662a2-f339-5e2d-908c-d5a5f6068e74 | note | Inspection: Key - H
32907b94-db98-5c93-b819-42cafa7de20e | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Sealing Chip - Source Property Tests and Sampling
4c01d3d1-c2ca-5aaa-96f7-c98f5ef982c3 | note | Specification - TNZ M/6: 2019 - 4
71a016de-4d55-5b98-97f6-100b8a022074 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
d57ece8e-d5e0-5d5c-b296-4494b9151059 | note | Verifying Document - IANZ Lab Reports
84e40308-4d65-5ed0-9176-b2d08fc00df7 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
6bf0ff7e-aa4a-576c-b55b-d21684561bf1 | note | Inspection Type (Visual, other) - Document review
3f7fdc28-5c3b-55da-b662-a5cf2f8207e7 | note | Inspection: Key - H
84936d61-522e-53d1-a1a2-393aa910b3e6 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.8 - Sealing Chip - Production Property Test Sampling
dfa0b8bc-723b-5d2e-a872-49d22ebfff22 | note | Specification - TNZ M/6: 2019 - 5
0ce43b7d-6dc0-5c81-ac23-08c057af9c29 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
9f4fb29d-7564-598d-82e5-87be2002fe17 | note | Verifying Document - IANZ Lab Reports
5f78d8a9-e3c7-582e-9c30-b9e153da3ce6 | note | Frequency - Every 500m3
f14a5e08-14bb-5540-b945-63a8dda6c209 | note | Inspection Type (Visual, other) - Document review
74b902d3-38b8-5720-9cc4-d995e9ec8357 | note | Inspection: Key - H
dde65329-071c-57f5-baf0-2f07acfdb750 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.9 - Bitumen - Quality Testing
cddb8a91-f702-5eaa-a0e9-b23fddd0ca6b | note | Specification - NZTA M01: 2022 - 6
32deb0b1-f7ec-5010-814c-c01a3c312694 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
28a3e419-a8c2-53f3-91c6-4dcb5d9ec89c | note | Verifying Document - IANZ Lab Reports
5e2b7952-7866-5d36-9718-b452d3f495cc | note | Frequency - One test per grade supplied
e0f586cc-3478-5e3c-a099-cf505c52cf5d | note | Inspection Type (Visual, other) - Document review
966e7abf-f715-5cf6-aed1-4c851a5df8b0 | note | Inspection: Key - H
78a267fd-800e-5e09-8177-06a8537d29e5 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.10 - Bitumen - Supply Testing
734fd87d-bab6-5c80-bd82-7fbd8b5ed5ca | note | Specification - NZTA Q05: 2022 - 6.2
86c30fc2-a5bf-596d-ba25-1cc2cf9e577d | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
26454479-6dd0-5bda-9a1a-6daa07372a2c | note | Verifying Document - IANZ Lab Reports
6cfdf056-d20f-5cd0-a7d6-29281daa7ac8 | note | Frequency - Every 200 tonnes supplied.
70ad2545-c6b0-5d84-99eb-b5490f24a7ee | note | Inspection Type (Visual, other) - Document review
be91ab34-2835-5e8a-bac4-68db1255e7ab | note | Inspection: Key - H
1eef18e4-9887-5b20-a5d8-47ee0a488a52 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.3 Cement Treated Basecourse
| checkpoint | 3.3.1 - Cement
7cae0417-276a-5247-94a9-bf9d50370483 | note | Specification - NZS3112
53905e53-ef2b-5e23-9cea-a3c8465a1e77 | note | Acceptance Criteria - General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract documents.
8781a233-249a-5b1d-a30b-67a3678adb06 | note | Verifying Document - Datasheet
8a37bb94-58ed-5dd5-ae0c-358b20606650 | note | Frequency - Prior to use
50206914-a145-5f4f-b409-fae6d29aafd1 | note | Inspection Type (Visual, other) - Document review
a0ffacc4-6d7b-5fbb-801c-5d24ccd59fa0 | note | Inspection: Key - H
42a8ea2b-25aa-58d5-9814-8213414eadce | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Asphalt
| checkpoint | 3.4.1 - AC14
6284ded8-b5de-512d-9b5c-e6de98731a21 | note | Specification - Pre-construction
dac0b0f4-c762-5139-b8e9-cc88d2bd867d | note | Acceptance Criteria - As per NZTA M/10 specification
f8aa5ac7-b8bb-5a07-9395-99a2f5e43311 | note | Verifying Document - Mix Design, Production Test report or Volumetric properties
8fe4b3c3-8cf8-5c4e-bcc6-d2ce2082ed5a | note | Frequency - Per Mix
f3c59583-17f5-576e-8041-f78d8c148483 | note | Inspection Type (Visual, other) - Document review
3a8903fa-09e5-5c9c-be02-e6a5a9121d34 | note | Inspection: Key - H
88463d42-90c4-57c9-b04e-01ef12c10aa9 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.5 Geotextile and Geogrid
| checkpoint | 3.5.1 - Geotextile
15cb2363-0fa1-52ca-96e3-680d28475171 | note | Specification - Class C as per design spec
b88bde17-797e-511e-b139-0e6c01d8dbc9 | note | Acceptance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
dfe02ab4-68d2-5efe-93cb-b99beaf9ba51 | note | Verifying Document - Datasheet
2ec5d26f-527b-567c-bd53-abaef0fedfe1 | note | Frequency - Prior to use
0468b0e5-2f64-5d17-a790-2006c8a0e4aa | note | Inspection Type (Visual, other) - Document review
e75f9a67-765e-5a24-8983-c476cc11c44f | note | Inspection: Key - R
a2eb2d02-7c56-557d-9055-c1f9d8424f6b | note | Inspection: By - SE
| checkpoint | 3.5.2 - Geogrid
bb367b63-c7f4-528c-9660-57644fd3dcb0 | note | Specification - TENSAR TRIAX TX160 as per design spec
341892c5-20a8-5ff9-8d0c-32bcfee4c1cd | note | Acceptance Criteria - The geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001.
a53b113c-6e6e-559a-a953-f39b136aaef2 | note | Verifying Document - Datasheet
ea6273ed-1085-5bce-961b-58aeb848e611 | note | Frequency - Prior to use
43f3d4e3-4938-5c82-9af2-cdbd722721e8 | note | Inspection Type (Visual, other) - Document review
978331c2-c2cc-5711-99ed-ba924773f9e2 | note | Inspection: Key - R
5be7835a-d2c8-5ca4-aba3-db0c611d1d11 | note | Inspection: By - SE
| section | 4.1 Unbound Pavement Construction
| checkpoint | 4.1.1 - Material Placement
40b0981c-583c-5c0f-8bcd-672d34fb7380 | note | Specification - Downer Standard
7fe446bc-091e-5006-8939-68d3b23d95a0 | note | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
2d4765e2-52c1-5fda-a7c1-ff294c5a1dac | note | Verifying Document - Survey / Level Checks
93d690f6-772f-5fa3-981d-14fd1b04d741 | note | Frequency - Continuous monitoring.
cf3d5cc0-c6dc-5967-96d8-8f531a669537 | note | Inspection Type (Visual, other) - Check
1b0343c6-9215-543f-a8c6-863d9c95548e | note | Inspection: Key - C
04ffcaad-5906-531d-81c7-1b4e48991799 | note | Inspection: By - SV,PS
| checkpoint | 4.1.2 - Plateau Density Tests (Sub-basecourse)
2b1d0292-e71d-51be-b270-19ecfac01d58 | note | Specification - TNZ B/02: 2005 - 7.5
8e9d87b8-cc09-5c3e-8d5f-a8fb4013358d | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
f2a00605-eaf9-5590-a0e1-6dd5865e0b21 | note | Verifying Document - Plateau test results confirmance
a4f53940-1cd6-5a98-8139-912c0029737c | note | Frequency - Continuous monitoring.
3a05fefb-42d4-5955-9e59-04db0cd199bb | note | Inspection Type (Visual, other) - Check
437b04b9-8a10-51b9-a5f0-17505d055905 | note | Inspection: Key - C
c9585ac6-ab8b-574a-a8a2-d41c6ff04fdc | note | Inspection: By - SE
| checkpoint | 4.1.3 - Sub-basecourse Pavement Layer Compaction (NDM)
7a6c81ac-66ee-5e80-af68-ae3ecfbe0418 | note | Specification - TNZ B/02: 2005 - 7.6
f01f03e2-d74f-514e-bad6-62e02623ce86 | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
3a5d5679-046d-5797-a748-42c908dee489 | note | Verifying Document - NDM Report
b65e14b2-5cae-5521-951d-c20e6f257774 | note | Frequency - 1/10m each layer not exceeding 200mm
b22b4e8c-1f05-5a85-9158-72ad53bb328c | note | ○ If no clear lanes then 1 test per 50m2
7b5e0d44-6d84-5092-b882-20f118f5ab44 | note | Inspection Type (Visual, other) - Check
92c2d8ec-5c78-5bc2-970e-0328a04291d1 | note | Inspection: Key - H
26cb6191-6e83-5779-8b7f-f7fe97b25cdc | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Sub-basecourse Layer thickness
03c4349f-0f87-5efe-9de9-dfa9179481b3 | note | Specification - TNZ B/02: 2005 - 5.1
a538bdc8-9bea-513b-8f06-ad8a7e0407a0 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
29dd4752-359a-5fc7-b27e-8abfa531d844 | note | Verifying Document - Survey / Level Checks
c0c9348e-a74a-5434-a4c0-dabfa7b36aeb | note | Frequency - 1/20m Full width
0d1b68f2-d496-5db5-8796-8d0081443a19 | note | Inspection Type (Visual, other) - Dimensional Inspection
606991e7-c52e-591d-882c-4dc314e8164f | note | Inspection: Key - D
1a832627-4ef3-5223-87dc-09879f379e5d | note | Inspection: By - SV or SE
| checkpoint | 4.1.5 - Plateau Density Tests (Basecourse)
e20066a6-600d-5f97-a5a6-8f3af9beaf69 | note | Specification - TNZ B/02: 2005 - 7.5
f2462a7a-c1f9-5927-a6e0-d7d45887cf4a | note | Acceptance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
0fcc7056-8aba-5a0b-8a8f-a8430425f623 | note | Verifying Document - Plateau test results confirmance
0d63d3a6-cc3e-5c93-95c9-eb8aba389264 | note | Frequency - Continuous monitoring.
cc08df07-f1ff-5d04-a73f-133d6de84590 | note | Inspection Type (Visual, other) - Check
9fa79898-3e1f-5425-ae48-267b3c5efdc2 | note | Inspection: Key - C
ed7d8578-364d-5609-8887-0d2e8d2b4297 | note | Inspection: By - SE
| checkpoint | 4.1.6 - Basecourse Pavement Layer Compaction
231b3d4b-2603-54a3-8ef7-1865b33ebcf5 | note | Specification - TNZ B/02: 2005 - 7.6
35c02e8b-878b-5cc2-a7e3-0c3101fe5794 | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
a555e914-a147-5aad-aa1d-1939b59969fb | note | Verifying Document - NDM Report
81970db2-09d8-598d-8787-b615b1bbf112 | note | Frequency - 1/10m each layer not exceeding 200mm
9edb6b09-b7d0-550b-a8a8-5971fd50fce0 | note | ○ If no clear lanes then 1 test per 50m2
4359a7b0-0433-5339-8e39-336a4ab40ebd | note | Inspection Type (Visual, other) - Check
0dd6dbd6-c516-54b9-ab46-5ee4beb885d2 | note | Inspection: Key - H
c542fd59-a547-54ba-86f1-ce0d209c1617 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.7 - Basecourse Layer thickness.
927a2f45-fc3c-5b02-b5e7-f1137e20d914 | note | Specification - TNZ B/02: 2005 - 5.1
3662206c-f1e0-5528-b0d1-45886898d799 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
8e1c137d-cb68-5649-8172-fa2e696e72b2 | note | Verifying Document - Survey / Level Checks
e5c62cbd-5026-5b9d-914d-bac8bd3a44fb | note | Frequency - 1/20m Full width
4e0b6f3c-45a8-5923-82cc-9aed06987152 | note | Inspection Type (Visual, other) - Dimensional Inspection
526bd4ee-42e4-5b6a-81f8-1d0fea08f119 | note | Inspection: Key - D
853447a7-1bee-53f4-8fb7-0cf53825779d | note | Inspection: By - SV or SE
| section | 4.2 CTB (Cement Treated Basecourse)
| checkpoint | 4.2.1 - Pre-Stab check
48f73350-7d75-5bc9-b5bf-e301655a1632 | note | Specification - Downer Standard
e9da3bef-baba-5962-a86e-4074af74a944 | note | Acceptance Criteria - Check the temperature(between 5 °C or and 30 ºC), Wind (not exceeds 25km/hr), Rain, Time limitations(Primary compaction within 2 hr and the final trimming compaction within 4 hrs)
5d727753-99c6-545a-bfc6-79158d2ad687 | note | Verifying Document - Checklsit
a59ce5e3-6efc-557d-b758-f41577fe165e | note | Frequency - Befoore the stabilisation
8f1d76e2-1a7b-5f77-885a-ce07b2352f95 | note | Inspection Type (Visual, other) - Check
216e350c-6fd2-53b3-8eaf-5caec4760a4b | note | Inspection: Key - C
fa4477b1-865f-59c1-b398-9380ed9398c0 | note | Inspection: By - SE
| checkpoint | 4.2.2 - Mat testing
3261b159-c95f-5405-bcc3-658effe5206f | note | Specification - NZTA B/5: 2008 - 7.3
65910511-1e96-5f9a-8c91-76d012420219 | note | Acceptance Criteria - Every 400 m2 complete a Mat test using a 1m2 cancas. The ammount of Stabilising Agent on the canvas shall be within ±0.5 kg/m2 of the specified rate.
984ca632-301f-5318-a298-525d74481648 | note | Verifying Document - Test Results/Photos
6f454ad5-86fe-5c93-bf85-ea82876a9ff3 | note | Frequency - Every 400 m2
d0a903b5-b807-5193-88c7-bc005a4b961c | note | Inspection Type (Visual, other) - Dimensional Inspection
f45a2da1-314e-5a3b-98cb-fc04dc210a21 | note | Inspection: Key - D
e37f69de-1674-5e10-bdc6-5b83962b4841 | note | Inspection: By - SE
| checkpoint | 4.2.3 - Average usage test
f30140f4-291b-5c0c-8c35-9efe1ab0008b | note | Specification - NZTA B/5: 2008 - 7.3
2ea87fdb-e095-5a44-9885-fe279ab8c1d8 | note | Acceptance Criteria - Upon emptying the spreader and bulk tanker, Compare tonnes of Stabilising Agent used (from delivery docket) with measured area. Usagese shall be within ±2.5 % of the specified rate
68eca327-ad00-5037-bdb5-6f9329c8f0b0 | note | Verifying Document - Calculation with Dockets and Weights
a0e5e185-1ecf-5ff0-9620-206f20f90196 | note | Frequency - Upon emptying the spreader and bulk tanker
f319644a-b0eb-5ab5-baa6-92e860023dd3 | note | Inspection Type (Visual, other) - Dimensional Inspection
b4a74d8a-3af7-549c-bc00-7d8dcb536108 | note | Inspection: Key - D
f53737de-1dd2-52a2-a7e6-724c8e7e8c33 | note | Inspection: By - SE
| checkpoint | 4.2.4 - Water content during compaction
1ad4a8d2-6f9e-5563-ba11-87bee1e35c31 | note | Specification - NZTA B/5: 2008 - 7.5
49905c78-cf74-5727-880e-e3d23d7c28cc | note | Acceptance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content. The water content tests taken prior to stabilising and the water consumed per cut shall be recorded in the production plan records.
8aec5ada-f244-5952-957f-23e9bbaf7e01 | note | Verifying Document - NDM Results, delivered weekly
2583738b-b66c-55c8-85c0-cfc702f6fc63 | note | Frequency - 5 tests per 1000m2
bf835b91-a32f-548a-9763-7ac840700f2b | note | Inspection Type (Visual, other) - Check
a5e3c5bc-b98f-5841-a1df-f738cbab2773 | note | Inspection: Key - C
4ed3c909-2295-5cd3-b1cf-9f212af01260 | note | Inspection: By - SE
| checkpoint | 4.2.5 - Control of cut depth
38ab8ba4-d7ce-5477-abf2-f8f8a7766beb | note | Specification - NZTA B/5: 2008 - 7.6.1
51f5ee06-2001-5ec3-9797-fd355923af69 | note | Acceptance Criteria - The actual depth of the cut shall be physically measured at both ends of the stabilising drum at least once every 200 m along the cut length. Maximum variation from the specified depth of cut is –0 mm and +20 mm. Unless specifically allowed in the project specification, the depth of cut shall not intrude into a subgrade layer.
8e2533be-e530-5c77-8d68-a30125cf295c | note | Verifying Document - Site Records/Photos
52682a96-68fb-5955-9f07-deb62879c5c5 | note | Frequency - Each Cut
848d66e9-f8af-5127-a07d-7d10f0dafd9e | note | Inspection Type (Visual, other) - Check
626506f5-b713-5bcc-b27a-fa77636987dc | note | Inspection: Key - C
782f776f-fc6c-5b64-9fc6-75b6feeb32c4 | note | Inspection: By - SE
| checkpoint | 4.2.6 - Overlap on longitudinal joints
dbf91615-93d4-56f4-9fbd-0368e2c2e736 | note | Specification - NZTA B/5: 2008 - 7.6.2
71affed4-06ab-51ba-887d-3fa2dbcc4c46 | note | Acceptance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by minimum of 200 mm or half the layer thickness, whichever is the greater.
0711c71a-2381-5340-b12d-fad70cae7b42 | note | Verifying Document - Site Records/Photos
5cf5e222-5b46-5b3a-9a23-4c6d53102922 | note | Frequency - Each Cut
ce5ccd85-aec7-50b1-97bd-cdf2f85b0817 | note | Inspection Type (Visual, other) - Check
0236e8fd-b3e1-5b58-a0d2-61dd511edf6e | note | Inspection: Key - C
630a33bf-c5e5-5096-b9dc-824b88d076e5 | note | Inspection: By - SE
| checkpoint | 4.2.7 - Continuity of stabilised layer
24c39c3a-4cb2-527e-8884-7484575f05df | note | Specification - NZTA B/5: 2008 - 7.6.3
27592236-0c3d-5581-9b7f-80e122e0459c | note | Acceptance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of the stabilising agent ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 1 m behind this mark.
9c93ba01-0bf1-5aad-bb93-0ce017a179e7 | note | Verifying Document - Site Records/Photos
cac841fa-c488-5b08-a327-dbd020fb875b | note | Frequency - Each Cut
9464adf4-fe46-51e5-ac68-3212f0be9aef | note | Inspection Type (Visual, other) - Check
afb3e057-d951-5f60-97dc-614a50e78ef7 | note | Inspection: Key - C
c7cc0785-e075-53a7-8b39-f99ccefd4213 | note | Inspection: By - SE
| checkpoint | 4.2.8 - Plateau Density tests
730b4bdc-3585-5c7d-93eb-6989f13d4c10 | note | Specification - NZTA B/5: 2008 - 7.7
22534638-ad37-5ff0-a5ed-1db1dc590f69 | note | Acceptance Criteria - At the outset of compaction the contractor shall undertake plateau density tests for the purpose of determining the practicality of both the OWC and the MDD mix design targets, the minimum, and possibly the maximum, number and type of roller passes required to achieve the MDD for the proposed compaction plant and stiffness of lower pavement ‘anvil’ beneath the layer to be compacted.
4a8d383b-707e-5b5e-bf67-f18a0b35b5db | note | Verifying Document - Plateau Density test
221a908f-a111-503a-9f50-cfd6a3e9ba99 | note | Frequency - Continuous monitoring.
479c83a7-e9f6-5a34-b84d-3d6deffebc32 | note | Inspection Type (Visual, other) - Inspection
601a2d2b-7234-57df-96ba-e5c4a98cce34 | note | Inspection: Key - I
75af6790-fe03-53f6-9f04-28a8dac8755d | note | Inspection: By - SE
| checkpoint | 4.2.9 - Compaction testing
136b7798-7244-5c97-8d4e-e2962e94f4d0 | note | Specification - NZTA B/5: 2008 - 7.7.1
1dde9158-8950-5182-8791-21c812a2c582 | note | Acceptance Criteria - The Degree of Compaction for Cement Treated Subbase shall have a Mean Dry Density of ≥ 98 % and a Minimum Dry Density of ≥ 95%. Compaction testing during construction of the stabilised pavement layers shall be carried out in lots. The area of a lot shall not exceed 1000 m2
826f8fe4-3337-518c-ad0e-b9f8865fc88f | note | Verifying Document - NDM Results
d7fce366-aac3-5933-9cb5-b616e6685243 | note | Frequency - 5 tests per Lot
e762ded8-34a5-5837-9532-b899ad6ddb1d | note | Inspection Type (Visual, other) - Check
f27ed7eb-5a03-5722-856c-8641a972aaab | note | Inspection: Key - C
4855adb5-257b-5879-b811-17d63421e38e | note | Inspection: By - SE
| checkpoint | 4.2.10 - ITS Testing
19c4995c-b7d9-5e65-a258-890867e7a73d | note | Specification - NZTA T/19, Contract Specification, Section 3.6.5, Appendix F
6ca0aad9-6e1e-5873-b939-1d83183e89d1 | note | Acceptance Criteria - ITS testing shall be carried out in accordance with NZTA T/19. The maximum time between mixing and compaction shall be 2 hours. The ITS test ranges shall be as follows:
a55e0140-445e-5853-9e7c-fb7366685d20 | note | – Dry: 150kPa - 350 kPa
5cf433f8-8f94-525c-8e04-761fff37218d | note | – Soaked: 100kPa - 300kPa
c2536fd0-ed11-5e5a-b72a-5270e5b62a78 | note | ○ The Tensile Strength Retained (TSR) shall be no less than 75%
5dd8b844-4771-5e04-94fb-e0d6f5ca441e | note | ○ If results are below the target strengths then notify the Engineer immediately.
3a623382-6ff6-51c7-b827-3331ca57fbaa | note | Verifying Document - Test Results, delivered weekly
bbfae43b-6259-55b3-bcff-422229b4e7ef | note | Frequency - 2 ITS (dry) and 2 ITS (soaked) for behind the hoe sampled each day of stabilisation.
cca24be9-99cb-58cf-8b14-85dc6baff6a4 | note | ○ Samples are to be taken from seperate locations.
896b0c3d-7d7a-5e8d-83b9-1418afb1df7e | note | Inspection Type (Visual, other) - Check
6c491904-4170-5b70-aad0-964432f59268 | note | Inspection: Key - C
51be8a34-76ad-5a65-a173-be25b5563ea5 | note | Inspection: By - SE
| checkpoint | 4.2.11 - Benkelman Beaming on Basecourse (cement modified)
9d737656-e526-5d17-8de4-d29064d4259a | note | Specification - Contract Specification, Section 3.5.5 CHAR(AMP) Appendix F
9a52a6e2-1a3b-595d-907b-f5910404883a | note | Acceptance Criteria - 90th percentile deflection ≤ 1.0mm. ○ No single deflection > 1.1mm.
81ead818-a9d4-565c-819e-f11a985ee78c | note | Verifying Document - Test report, delivered weekly
bf136c36-0575-5ce3-ae3f-7ceab07a391f | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
e3d3ecb2-2cff-5247-bac1-574c5a74faf5 | note | Inspection Type (Visual, other) - Dimensional Inspection
74e674b0-5d36-55bc-a2dd-45073be7e6c5 | note | Inspection: Key - C
af9c8f32-07a7-5b2b-bf3f-a769cd59e98c | note | Inspection: By - SE
| checkpoint | 4.2.12 - Construction Tolerances
edfa01aa-d61c-541a-aae0-afd9d4d6c4fe | note | Specification - TNZ B/5: 2008 - 7.8
4b2cc29f-9f53-5cad-b80f-e50841f11717 | note | Acceptance Criteria - Basecourse where asphalt surfacing with concrete channel
4e9cbce8-faee-5412-ae1e-3db9a3f6d9ca | note | (i) at or close to the lip of channel –5 +5 mm
c6d12c33-b3dc-5f07-bb52-c7670fb921ff | note | (ii) at other locations on pavement –15 +5 mm
a4aa7843-ca56-5e6a-be7c-0bab4ba9be3c | note | (iii) at other locations on pavement –5 +15 mm
39b9a381-45c2-5a48-b8f8-673dc28c7b30 | note | Verifying Document - Survey Records
6ffc0129-adee-5a8d-beb0-e5eb92706abc | note | Frequency - On final layer
ce4fb407-d771-5b54-8887-4b9be0922002 | note | Inspection Type (Visual, other) - Dimensional Inspection
eed7a56c-3c34-5be6-9bab-aedcaf7e7070 | note | Inspection: Key - C
a90ed740-05ba-5dc6-b000-855d7b763ef0 | note | Inspection: By - SV
| checkpoint | 4.2.13 - Surface Finish post sweeping
18d68639-8183-521d-933a-441319e3a5b5 | note | Specification - TNZ B/02: 2005 - 7.8
f85ea0b2-2801-51d6-a2c7-276b2b98e3e6 | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
fe3a5352-d470-5a1e-85b3-c38ace55bc40 | note | Verifying Document - Photos
ba7bc0e9-d614-5588-9f8f-cf6bfa157489 | note | Frequency - Prior to sealing
ec318afe-7531-54e8-8afb-d2e84e34eb02 | note | Inspection Type (Visual, other) - Visual Inspection
ff8f78f1-7b8a-54a0-9ec6-a729b82a56ec | note | Inspection: Key - V
ecd621df-8c09-5d25-a0e7-03936a130d35 | note | Inspection: By - SE
| section | 4.3 Sealing
| checkpoint | 4.3.1 - Presealing Requirements
cfb49f2c-b6ca-59a8-afc5-d34bd17c1eb2 | note | Specification - TNZ B/02: 2005 - 12, Contract Specification, Section 3.6.7
4c9f3afa-7421-5023-ac42-d33d4b102002 | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 70%.
f4d03947-78cb-5a59-bdf2-1db3861f84a2 | note | Verifying Document - NDM Report
7508590c-ce20-5ef8-9a45-4237b6ddb700 | note | Frequency - 1/10m
67558048-1109-50bf-ad7b-7b0627b8ba63 | note | Inspection Type (Visual, other) - Check
16f55a8f-6bc0-50dd-9802-be4e5f46073b | note | Inspection: Key - C
11ef69f7-4618-5559-9774-eff9ce38fe20 | note | Inspection: By - SE
| checkpoint | 4.3.2 - Benkelman Beaming on Subbase (on AP40 CTB)
4e1fd495-1838-54cf-8fc9-931b99768be2 | note | Specification - Contract Specification, Section 3.5.5 & Appendix F
704f9785-8292-5afc-8249-a4663fba187e | note | Acceptance Criteria - 90th percentile deflection ≤ 1.4mm.
fa7b5aec-0aa2-5477-9ff4-c1bdfd110837 | note | ○ No single deflection > 1.5mm.
220fa8c2-e8d1-51bf-9473-eea21167e9f8 | note | ○ For CVSC, no deflection > 2.2mm
7233c88b-8182-57d8-910a-25b1d64f9fd8 | note | ○ For CTB, no deflection > 1.4mm
3b53c12b-cf38-5b10-af81-3c3b8f4f7bde | note | Verifying Document - Test report, delivered weekly
d0aa7978-47dd-522c-9bc8-9496a690a1e5 | note | Frequency - 1 per 10m each traffic lane (alternating wheel paths) or 1 test /50m2 if no clear lane
8c08f830-1cc5-5f48-816c-41580f2cea3f | note | Inspection Type (Visual, other) - Inspection
652c355c-f635-50bd-9e41-cd04e5e92f53 | note | Inspection: Key - I
6a048d54-6154-5e43-b669-fcf390a7e75c | note | Inspection: By - SE
| checkpoint | 4.3.3 - Preseal inspection
4551f32d-ede3-5155-9bdf-c2600752ce42 | note | Specification - TNZ P3 TNZ B02
9106d950-9807-5ac6-9554-4bcab25ef939 | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
80cccc36-b745-538b-9b50-369f4ecdcb2a | note | Verifying Document - Hold point Release, ITP Sign off
651d3c7e-c988-5fe7-8f64-ccf09e2c9f22 | note | Frequency - Prior to sealing
1d7132b4-0e7b-5250-a4ae-66eccbd16074 | note | Inspection Type (Visual, other) - Check
1c413b8c-b241-5812-9a0e-cf03ad9ea914 | note | Inspection: Key - I
8701b84d-f648-5026-9e7c-5aab137ddce8 | note | Inspection: By - SE
| checkpoint | 4.3.4 - Spray Temperature
abddb3ea-2a34-52cb-9ca2-674008cbdf60 | note | Specification - TNZ P3
b810ae45-6a83-548f-9d4c-34819a5600c9 | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
d412102b-661b-5d58-985b-ab24706ea2fa | note | Verifying Document - Sealing statement
f67b432f-14f6-5692-80c3-af335089bb88 | note | Frequency - Prior to sealing
d966cbdc-b89a-5094-9d26-0e76839fcd5f | note | Inspection Type (Visual, other) - Check
ae01529d-85e7-5dff-9a1c-b5fbe8bab1db | note | Inspection: Key - I
c74861db-b789-57c0-bf0f-c5c8cc113be4 | note | Inspection: By - SE
| checkpoint | 4.3.5 - Chip Application
d0dc0ef9-048f-506d-999e-602e145b3495 | note | Specification - TNZ P3
964b2ba7-edd1-574e-90e8-f5b39b209320 | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
fe4f2336-05ef-5d07-b5e8-5b7e87d1c7f9 | note | Verifying Document - Sealing statement
49857a33-3e9f-530d-a79f-3b296379a364 | note | Frequency - For every spray run
4d7b3bca-8123-5f83-a489-ac5454382027 | note | Inspection Type (Visual, other) - Check
0059103e-b7c7-54cb-a280-cf668ca092e5 | note | Inspection: Key - I
a3d3d380-8833-5ce4-b5ff-3877040a0ead | note | Inspection: By - SE
| checkpoint | 4.3.6 - Post Seal Inspections
54e9d136-f39f-5429-ab25-5bbae8d6d335 | note | Specification - TNZ P3
5c99b095-8adf-54ef-863e-e9b55c3ba381 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
09a2d3ba-a1b8-5bdb-87a1-936dbc5609f3 | note | Verifying Document - Engineers Acceptance
fe39fe81-4ce5-51f9-98e9-7ecd9984cfb9 | note | Frequency - After Final Sweeping
295221f0-b246-5542-b54b-678b03f1f747 | note | Inspection Type (Visual, other) - Visual Inspection
03d5e9dc-de59-5fe2-bc7a-ab6830cde5d2 | note | Inspection: Key - H
f4e54259-5fce-520e-8f0c-dcc5f8cbda5b | note | Inspection: By - SE,CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3.7 - Chipseal Repairs
9e0e7825-3f22-5b72-9308-d16040e9a11f | note | Specification - TNZ P3
14ab105e-175a-5746-93c9-c5ba83c1361c | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
5633e86d-a91a-51e1-b964-4704f26907d7 | note | Verifying Document - Approved Repair Methodology
ed221f80-f17c-53c8-9175-8934a4be4f73 | note | Frequency - Prior to Repairs
ee99c332-f057-5e9e-87ab-c1b9f39598c4 | note | Inspection Type (Visual, other) - Review
d9fba640-685b-5a38-9c53-b3462a2649aa | note | Inspection: Key - A
7d6f983e-a54a-56ae-9b29-1529ab6a3f1a | note | Inspection: By - SE
| section | 4.4 Asphaltic Concrete (AC14)
| checkpoint | 4.4.1 - Preparation of Area to be Paved
14434536-2797-52e4-a223-08e0c8fdb86c | note | Specification - NZTA M27:2020 - 9
16fd8c89-5918-521a-9676-78ed7f230e41 | note | Acceptance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
0021d1da-a0c3-5894-ba2d-737afcc57deb | note | Verifying Document - Site Notes/Photos
0a16c8f8-c1f2-554c-8658-1f63ff471bbd | note | Frequency - Pre Seal
d67b095b-8d60-509f-88c5-e7e86f66e88b | note | Inspection Type (Visual, other) - Visual Inspection
fd4ef90f-ee2d-5277-b83c-2f86a7d711b8 | note | Inspection: Key - V
87408e15-ed0a-5f2e-bbcd-acb1976a6edb | note | Inspection: By - PS
| checkpoint | 4.4.2 - Ambient Conditions for Placing
ad22a04f-a8d9-5486-8b57-436a5ebb0554 | note | Specification - NZTA M27:2020 - 9
55bf05f2-21df-5a4f-9825-f4d441fb2116 | note | Acceptance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
435aa420-32db-54bd-8dc4-f5937692b930 | note | Verifying Document - Site Notes/ Weather report
57d33748-8163-528f-9b4e-5a147c189bec | note | Frequency - Pre Seal
bbc5e2b9-d64f-5f80-bbdf-6516a91e712f | note | Inspection Type (Visual, other) - Check
08147180-fbb7-56ee-8e33-0d16de7facda | note | Inspection: Key - R
5cf2ab57-ee97-5f84-b943-27979edfcbc5 | note | Inspection: By - PS
| checkpoint | 4.4.3 - Subbase check
fc4a60d4-e529-5f49-8922-bef4e201595e | note | Specification - as per project specification 3.7.7
ad0d82c9-0af9-5f55-9af1-2e5e9df57b48 | note | Acceptance Criteria - Visual inspection by engineer's representative
bfeae925-658a-5b37-a57e-fb0c4aad67f9 | note | Verifying Document - ITP Sign off
bdc39523-f019-5726-9c7a-29928210d80a | note | Frequency - All
ff57d7ee-3260-51bf-8590-6cdcb6a506f0 | note | Inspection Type (Visual, other) - Visual
b989a6d9-77d7-5d98-9a76-305318a86151 | note | Inspection: Key - H
ccf48de6-49db-5408-9e0b-ff7a935c4345 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4.4 - Heavy Tack & Blind
6584fa4c-e343-5996-b34e-4d7ca977f547 | note | Specification - Minimum Residual Bitumen of 1.2 L/m2
0bc21e84-6513-5e27-b28b-2a55e4253c1f | note | ○ As per project based pavement specification
882a5d98-1226-5ac9-be4b-dc21047f8d4d | note | Acceptance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
88e4b632-4dba-50a0-b209-60f64e6a9328 | note | Verifying Document - Run sheet, QA from Sub
650e6494-5c87-55d9-b9a9-d6665cc749fb | note | Frequency - Entire length of pavement
e90b8d8a-9aad-5e10-a33e-38b4e74fb31d | note | Inspection Type (Visual, other) - Visual Inspection
409e25a7-ba00-5656-849e-2680cd28dba2 | note | Inspection: Key - V
f7f43605-fde0-5180-a189-feb858ba7f6c | note | Inspection: By - SE
| checkpoint | 4.4.5 - Asphaltic Concrete - Surfacing
4533a8a6-633c-5de0-8345-4257349da843 | note | Specification - NZTA M10 & M27, Contract Specification 3.7.15, Appendix F, Section 10.15
00a9de70-35b2-50e7-85fe-c577d907bdc2 | note | Acceptance Criteria - 55mm of AC14
daef6c77-df05-545b-9cf4-cd9e79bf4c40 | note | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
3220622b-f5e7-5b48-873b-6e90c207ac15 | note | ○ The combined thickness of all asphalt layers should not be less than the specified total asphalt depth.
431e096e-6d4f-59db-8c7b-f902f84a24b5 | note | Verifying Document - Run sheet, QA from Sub
618f3be1-87b6-56e6-aa60-811bb53ca8b1 | note | Frequency - Entire length of pavement
6aab9ef8-9469-5329-9ef0-1b1de7c5291b | note | Inspection Type (Visual, other) - Dimensional Inspection
413987ed-6f6e-51a2-9d32-c4454eee9d92 | note | Inspection: Key - D
0eb30c40-df5b-5a24-8a17-73a08fbc217b | note | Inspection: By - SE
| checkpoint | 4.4.6 - Asphaltic Concrete - SMA 10
81ecf3f4-818d-5b99-9aef-4bca2db977a6 | note | Specification - NZTA M10 & M27, Contract Specification, Appendix F, Section 10.15
1c7c6aee-411d-5aa9-9a84-dd619458956b | note | Acceptance Criteria - 40mm of SMA10
baa9eb58-9b9a-5f67-b53f-49140ff50ef1 | note | ○ Asphalt layers less than or equal to 55mm shall be +/- 5mm from the specified design thickness.
83815586-d15f-5a78-9ced-dd4b29ada115 | note | Verifying Document - Run sheet, QA from Sub
4c458011-b754-5929-9893-3da93e2748f3 | note | Frequency - Entire length of pavement
4ec33b43-d258-59f9-ae01-0b5677ea57b1 | note | Inspection Type (Visual, other) - Dimensional Inspection
845e24bc-82c6-5e7d-b5e3-75428f27a62d | note | Inspection: Key - D
4d58785c-1ed3-59b8-86b3-c69357c859c0 | note | Inspection: By - SE
| checkpoint | 4.4.7 - Thickness
964ccb17-fcfb-5b61-9a81-9151f1b772dc | note | Specification - Contract Specification, Section 3.7.15
8fe38722-1b6a-5f1c-a803-2786f560d453 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC14)
c68c13b2-d2aa-52e3-b751-d67f8c4be39b | note | Verifying Document - ITP Sign off
4d409a0d-5f9c-5da0-a56f-3bb05a8a4b7b | note | Frequency - Continuos
e0eb1c62-ab4f-5017-971e-bc91372d14bb | note | Inspection Type (Visual, other) - Visual
1d33cbb8-d2c3-524f-80c7-1db8ea6a1859 | note | Inspection: Key - C
50f7e84a-edf5-5a23-b718-248b14a4c56d | note | Inspection: By - SE
| checkpoint | 4.4.8 - Finished surface at joints
2389c8a7-c54a-5e3a-8acf-ba36d5d437e1 | note | Specification - Contract Specification, Section 3.7.16
52d58211-11fc-51fe-aa24-9e030ded315b | note | Acceptance Criteria - No more than 5 mm variation under a 3 m stright edge
77b6690e-f8c3-503e-ac86-77e79548bc16 | note | Verifying Document - ITP Sign off
73129f31-7528-5933-a8b4-f9b618504d0e | note | Frequency - Continuos
5a4242d5-af62-57dc-a479-21788759aef8 | note | Inspection Type (Visual, other) - Visual
d7f791a9-c8ff-5087-95c2-fc19d89c000d | note | Inspection: Key - C
9180af3c-3000-553d-91a9-5d86c78db164 | note | Inspection: By - SE
| checkpoint | 4.4.9 - Air Voids
8b26ea1d-877e-5473-adad-dee74fa24844 | note | Specification - NZTA M/10
2a25ba27-d9bb-5733-87a1-022eef03c0d4 | note | Acceptance Criteria - The maximum and minimum air voids for each core shall be +3%/-2% from the mix design air voids.
79cfb899-5862-5a3d-be71-97272f566afc | note | Verifying Document - Test results, delivered weekly
cfcae530-d7cc-5efb-9322-18604afbc174 | note | Frequency - Continuos
2f57d707-9a32-5999-b28f-c1322140da42 | note | Inspection Type (Visual, other) - Review
fc33f901-5f7f-553f-8c06-f2de55dfb5da | note | Inspection: Key - C
6519a069-958c-52c9-a7c1-4b4d009fdbe2 | note | Inspection: By - SE
| checkpoint | 4.4.10 - Level checks
d362f920-8e8b-5f3f-a181-788ef6a89fcd | note | Specification - Survey
067d1f5b-507e-5a7c-a143-ad1e21651130 | note | Acceptance Criteria - Thickness as per design lift with +/-10mm (AC20) Thickness of 40mm with +/-5mm (SMA10)
6a117289-1545-59c7-a3ee-634018bc6524 | note | Verifying Document - As-built drawing
fd9bc6c4-534a-51e0-896c-4c1ce2bb3365 | note | Frequency - 1/20m full width
31f9da68-2ee1-5329-af76-6b20efd5d493 | note | Inspection Type (Visual, other) - As-built
0816d7ea-08e6-5307-a64d-46bc396fd9dc | note | Inspection: Key - D
dfba6d45-1824-505a-a046-1a1b769cda3a | note | Inspection: By - SV
| checkpoint | 4.4.11 - Line marking
21d0876d-bea7-5a8a-a8f3-b511af327bc5 | note | Specification - Set out
943868de-7165-5dff-b501-5b5e28367f3f | note | Acceptance Criteria - As per NZTA standard/ design drawings
a6cc7ec8-908c-5ed6-9a0e-1382f4c1f1c1 | note | Verifying Document - ITP sign off/ Photos
3f1b8d90-e9ff-58f9-9d29-14a5d040e456 | note | Frequency - All
da18aff3-025e-5a1c-997a-aa9c57c03fc5 | note | Inspection Type (Visual, other) - Visual Inspection
cda7737c-9393-5aa0-8a72-28f846298743 | note | Inspection: Key - V
dd249c85-4d9a-5e30-94d2-3787dcf918e6 | note | Inspection: By - SE
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
b6bbdc37-ff00-528e-b355-5f3cb4d14638 | note | Inspection Point: Quality Control Activity - Upon completion of works
6ec7baed-145e-5caa-8435-98551843f221 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
2e5a10a2-d231-5a00-a304-0727d516fbc8 | note | Verifying Document - Closed-out NCR/Defects
9fd668e8-e984-516d-a0f5-2ad7e21ad40f | note | Frequency - Post construction
bf6358a8-942d-5b89-8965-bb9d20826aef | note | Inspection Type - Review
a0e8994f-f4f9-5b84-acdb-d21049942207 | note | Inspection: Key - R
c8dff98d-59e9-517d-8c4d-5147b075da24 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
73462cb0-43b6-5fcc-8315-2772ca811555 | note | Inspection Point: Quality Control Activity - Upon completion of works
76571540-43e2-5649-96ae-02f0fdbfa51e | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
f3f5d6dc-55ef-5499-af82-40e96f092298 | note | Verifying Document - As built survey record completed
9dd97f57-9f6b-5016-acc4-c3666124ffd4 | note | Frequency - Post construction
ebf8e2c4-7800-57b0-be76-9bceeb510663 | note | Inspection Type - Review
5601615c-ab0d-5ac3-aec1-0cc85e0ba944 | note | Inspection: Key - R
00862459-ec18-5a8d-82fa-cb4e87a7e9af | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
f4a3647a-35c1-5ad8-9f3d-b6a5a2f6d37d | note | Inspection Point: Quality Control Activity - Upon completion of works
4dca5519-2be4-5819-ad23-15e21b6350a6 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
e4fe9cbc-01cf-5cea-b2f6-cebe9c4f9485 | note | Verifying Document - Signed As-built Drawings
521481a6-6f34-5b3b-857a-af2e97e856c1 | note | Frequency - Post construction
0e7e6f71-19c5-5be0-897e-c4edfeb65d3f | note | Inspection Type - Review
110a7c28-da7d-5b9a-8ba9-ea1077a2188a | note | Inspection: Key - R
6977b4f4-7b73-56b4-9ffb-5b38a8b4f4fe | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
1d26d795-c8b2-549e-9912-7d80c4464ab2 | note | Inspection Point: Quality Control Activity - Upon completion of works
f4e02652-5eaf-5cdf-9108-fe99cf6fdcc0 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
95c63a1e-9941-563c-a0c4-03ed43ba2197 | note | Verifying Document - Register
a52ae4e6-29ba-58e7-80d4-a3b17cb7edbe | note | Frequency - Post construction
d7f77f8b-45dc-5b66-95f6-3ae302c47ea3 | note | Inspection Type - Review
cff9c2ca-0356-51b8-8656-915eca05f181 | note | Inspection: Key - R
5f19ca2b-7427-5852-b4f6-ccc6bbf0d710 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated & signed-off
9c7fbd9a-f029-5d94-8136-4ae6488ed526 | note | Inspection Point: Quality Control Activity - Upon completion of works
6b0213c0-bff8-5add-a290-79e4aafe334e | note | Acceptance Criteria - All signed and closed out
e671f164-6b03-5280-8204-f7383d845d6d | note | Verifying Document - Signed off Documents
ec75264f-14b5-51df-9913-de143c654de2 | note | Frequency - Post construction
d3fa14cd-4167-5653-ad8f-348cea35031a | note | Inspection Type - Review
257022c8-17e3-506c-b6c0-b071377b1b4e | note | Inspection: Key - R
b985f55b-ac5d-56a2-8e59-99d27cde9a1f | note | Inspection: By - QM
| checklist | Ω (Deprecated) DG-OWR-CVSC-ITP004_v1 - 3 Waters for CVSC (v1) | itp | DG-OWR-CVSC-ITP004_v1 - 3 Waters for CVSC | 02485a20-6e3c-4e17-9af1-0e0f1baac959
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
f6fbd3b3-b644-5aeb-bf30-e52687b11c91 | note | Specification - Downer Standard
935ff9b1-8db8-5dcb-ae67-bc399fad3335 | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
6aecbd72-aab3-54db-8e9b-6902c7eec4fe | note | Verifying Document - Survey Records
0d833fbd-a55d-50a3-b912-43925fec4dcc | note | Frequency - Prior to Works
7649b8a0-6777-54b4-918b-32443a33ef42 | note | Inspection Type (Visual, other) - Document review
715e1434-4191-5ef5-adfe-eadaeb5e0ce3 | note | Inspection: Key - H
a1e71aeb-ce15-56a7-acc3-29b05cb50bc1 | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
b9f7a4ee-895b-55e1-bd8a-c9d820041b5d | note | Specification - Downer Standard
cb10510d-8aea-5f13-a1a7-298889f69ffa | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
9feba03e-298f-525a-be59-e469ec33fc17 | note | Verifying Document - Service location documents
575f97c3-8ffa-5cd0-9ef2-fdafc8f8c6f5 | note | Frequency - Prior to Works
f44e84fa-b621-54e9-b9cf-70b1224aa798 | note | Inspection Type (Visual, other) - Document review
40c83d7b-b49c-5e74-9e8d-7c7675d3ec20 | note | Inspection: Key - R
716d8ebd-2eff-53d4-81e8-a1d26cdac11c | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
52a05807-b3bb-5848-814c-911ca3a5c4e8 | note | Specification - Downer Standard
3adc1500-ff22-5029-b723-022f8cbc6c12 | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
ecf82b5e-4b50-5fbc-aa72-f24897de840d | note | Verifying Document - Internal Permits
cf7348fc-6f03-5bfc-8f89-53e1814ad2a1 | note | Frequency - Prior to Excavation
17fccf47-0ff1-55aa-bcb0-af7a53aa9433 | note | Inspection Type (Visual, other) - Document review
336008f4-45fb-560b-8ffd-f2eae7df86c9 | note | Inspection: Key - R
542edf94-6496-5636-bce4-d222f46185c9 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
e5c834a3-1e74-518e-97d9-5e34ad778259 | note | Specification - Downer Standard
b78e7fec-4643-5b8b-8acd-770d443abc59 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
73c0d779-15c8-539e-a063-d64e024c6227 | note | Verifying Document - External Permits
7a0c59c3-105e-5751-b3c0-eadf81668c3c | note | Frequency - Prior to Excavation
bb365429-b8ed-5ab0-932b-95d3a30c9887 | note | Inspection Type (Visual, other) - Document review
df46fc17-f6d4-5d44-b67f-4214fd4db0dd | note | Inspection: Key - R
0af03ec6-9593-56d7-8204-80311383ea35 | note | Inspection: By - SE
| checkpoint | 3.1.5 - ESCP
b9e06372-c3f7-5508-85b9-9ce2e1dde6c8 | note | Specification - As per contracts
3ed8e994-5ff5-5f21-a13c-cfd7601d1105 | note | Acceptance Criteria - Prior to starting works, Ensure that ESCP plan an approved ESCP by counsil is in place and valid
119d970b-30ed-57a4-87d7-56b842642c7d | note | Verifying Document - Approved ESCP plan
fc72c2ab-2798-55b6-9f04-0e082d1d48c7 | note | Frequency - Prior to Works
1994c307-886e-5abc-832f-3ef5e9ac16ba | note | Inspection Type (Visual, other) - Document review
013e0f05-6e08-5164-ae05-24cee70bf9cd | note | Inspection: Key - R
47984f23-b94d-5b81-afe1-e79e7dab3954 | note | Inspection: By - SE
| checkpoint | 3.1.6 - Approved Construction Drawings
801269f9-cab8-5367-939a-4209780e1c33 | note | Specification - Downer Standard
72512a1b-8ddf-5d3b-827a-7d4fc7304126 | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f57c41a3-567c-5265-ba89-abea90d1933e | note | Verifying Document - IFC Drawings
4488d975-3623-59b5-83a5-6e3d2fc4c19b | note | Frequency - Prior to works start
baadfc6c-5ef9-5d5e-b881-6c4199f7b3c3 | note | Inspection Type (Visual, other) - Document review
96589cfc-c6c3-579a-bed7-65d6ff83930b | note | Inspection: Key - R
b1384293-a889-52c9-a4ea-c6ab96b3cc05 | note | Inspection: By - SE
| section | 3.2 Stormwater and Wastewater - Materials
| checkpoint | 3.2.1 - Sand
14142408-4d31-5f86-ad6d-83b7eece6a20 | note | Specification - As per project specification (Stormwater Swales, 3.1.2)
788db4e0-a8a4-5628-9988-2b993ff694e2 | note | Acceptance Criteria - Sieve analysis NZS 4402 Test 4.2.8.2
da1d9e6c-22a7-536e-bd06-7787d7369bee | note | – – – – – – – – – – – – – –
ed138eaf-d1dd-5347-8879-11ace2425b14 | note | Grading criteria:
e47eedb3-7f93-5d9d-93b2-1bcf4afcd1f4 | note | – – – – – – – – – – – – – –
f1633069-1f10-533e-9f52-b3166906d352 | note | Sieve Size ¦¦ % Passing
92b4b3e2-d181-520b-a6e4-8bb554d16090 | note | 9.5mm ¦¦ 100
73e30793-4dc2-5204-a9fd-dcdbdc96d9c9 | note | 5.4mm ¦¦ 70 - 100
2203fd85-a7af-5284-beaa-6feadcdd259c | note | 2.36mm ¦¦ 50 - 70
5ad777eb-22a3-5493-abcf-6284f32dde09 | note | 0.6mm ¦¦ 15 - 35
b70a4e8a-c0a5-535d-ba22-032ae701ffc9 | note | 0.3mm ¦¦ 5 - 15
6e507150-d3f7-5734-8bdf-e9c6ea956d07 | note | 0.075mm ¦¦ 2
031e3e5e-675c-510f-800b-6d90224bb224 | note | – – – – – – – – – – – – – –
5c346aa4-d6e3-5b62-9210-6a9fa470fda5 | note | Verifying Document - Test result
e1e2dd8b-6dc9-5e1d-a39a-85ba91c8ba90 | note | Frequency - 1 per 200m³
dca4ab8c-3db6-50d2-829c-a5d493e8a6f1 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
2632ffd3-9a5d-5dcb-934d-04f2624f23c7 | note | Inspection: Key - R
edd86eef-7989-5556-b539-73d02335ffee | note | Inspection: By - SE/PS
| checkpoint | 3.2.2 - Drainage Media
f2191d0a-c744-5214-9fec-0463f980037c | note | Specification - As per project specification (Stormwater Swales, 3.1.3)
a47e37ff-5a60-5331-a21c-78295c1dd621 | note | Acceptance Criteria - Single size angular stone chip no larger than 9.5mm
86b61ba5-f272-5291-8d97-b3f8892ff280 | note | – – – – – – – – – – – – – –
85f17d73-cd14-5f52-9349-68b7775ae262 | note | Grading criteria:
98462538-72a2-5a90-b164-3b47e5dd30a6 | note | – – – – – – – – – – – – – –
8d61bcf0-c42c-58de-bfdd-45910513a871 | note | Sieve Size ¦¦ % Passing
c2040a44-c190-56c8-a815-f44f87fe972b | note | 9.5mm ¦¦ 80 - 100
1c734feb-627d-5338-93a3-3cc5cfddc9ef | note | 2.4mm ¦¦ 0 - 20
a0efa6d7-487e-5247-bab6-1542b376ca32 | note | 0.6mm ¦¦ <2%
2dcc5f6d-3c10-5abd-bc56-3940142a025a | note | – – – – – – – – – – – – – –
dd9cfcf5-0b5c-55a1-9f1a-622661cd869f | note | Verifying Document - Test result
db1c0622-76cc-5499-b8c2-a5e2b21e54b3 | note | Frequency - 1 per 200m³
563d7410-d4ba-5001-9fc2-16a4f56bdb1e | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
f12a25fc-2e3b-5c0b-b052-bb1db307753a | note | Inspection: Key - R
83f587e9-2605-5bc8-9d3e-4098abbd9499 | note | Inspection: By - SE/PS
| checkpoint | 3.2.3 - Soil Media
55630cd9-752a-52aa-8563-330d259250dc | note | Specification - As per project specification (Stormwater Swales, 3.1.5)
08391ab8-6cb8-51e0-8e57-35f252997607 | note | Acceptance Criteria - The media must consist of material that has:
fdcb1fa8-4d59-5a2c-a880-7f10bf17581a | note | ○ 5% clean organic compost from a consistent source. The source of clean organic material must have been provided to the Engineer for acceptance prior to supply.
e42c55aa-9784-5747-a280-43a0b8677280 | note | ○ Locally sourced topsoil (free of weeds or contamination)
518ea491-8754-58bc-b8e4-557f4a5e9aeb | note | ○ No obvious seeds, weeds, any contamination and material > 25mm in nominal diameter
333d9845-a156-51ab-8655-a7b46b95fd5f | note | ○ < or = to 50% coarse sand from a consistent source to improve permeability and structure.
28c43e50-04fe-5108-85ac-95e437eb5379 | note | ○ < 3% clay (particles < 0.002mm)
5ba19bbd-68ed-5778-9923-7fb34c4870df | note | ○ < 5% by volume of particles exceeding 4.75mm nominal diameter.
7526311d-cc64-5cac-a991-633f45a75586 | note | ○ A pH rangeof 7.5 - 5.5
32ba279d-a183-51df-b4cb-fca591a51dda | note | ○ Well graded particle size from 0.075mm through to 4.75mm with no gaps in the grading.
a0bf880b-4c2b-50c8-aab5-e06473c08bd9 | note | ○ Compacted hydraulic conductivity of at least 50mm/hr and nort exceeding 400mm/hr based on the ASTM F1815-069 methodology.
67be8bb1-7eee-515b-8dd7-952258ba9f4c | note | ○ Total Phosphorus < 100mg/kg
ccbcd50c-c946-5f09-8979-7e7f759f3baf | note | ○ Total Nitrogen < 1000mg/kg
75a81bc5-037e-5f1c-95bf-c038bce5b2b0 | note | Verifying Document - Test result
010a10eb-4c9f-5b38-be41-82b5324b82ee | note | Frequency - 1 per 200m³
f43c5a46-2df3-5223-8bbd-5f87182baa23 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
ab5f33f0-f775-59d9-8ce1-e821bcb18376 | note | Inspection: Key - R
ae53d903-985b-5226-8180-5b6fb2873531 | note | Inspection: By - SE/PS
| checkpoint | 3.2.4 - Concrete Pipes
9229ceb1-5aa5-5379-be98-8397dc0307a7 | note | Specification - As per project specification (Pipeline Supply, 2.4.4)
f4baf8b4-c80f-5f93-aa9c-8cf08274aadf | note | Acceptance Criteria - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
7b411cac-bd04-515b-9cb5-44690e7bd180 | note | Verifying Document - Data Sheet
1124c832-4247-5fdb-ad31-06128892b8c5 | note | Frequency - Per delivery/Item
d0f3774f-8676-522d-bc35-ac1da51c42d9 | note | Inspection Type (Visual, other) - Document review
23184745-0f44-5ab8-8e19-a2c5b9d4a43e | note | Inspection: Key - R
a8c38e38-5618-550e-923b-6bd66dbdbc68 | note | Inspection: By - SE/PS
| checkpoint | 3.2.5 - PVC-U Pipes
316d8372-18ca-58f7-8a5c-6580da1ca53c | note | Specification - As per project specification (Pipeline Supply, 2.4.2)
968937d3-f20c-5795-8e58-785e99d681d1 | note | Acceptance Criteria - PVC-U pipes and fittings for gravity stormwater must be plain wall construction rubber ring jointed and must comply with AS/NZS 1254.
f67dac18-00b7-5802-9ab9-faaf75e81a2e | note | ○ All PVC pipes must have factory fitted, composite rings; loose Z type rings must not be used.
8420321d-b302-53bd-82e1-8698c6874954 | note | ○ PVC-U pipe diameters shown on the Drawings are the nominal diameters unless shown otherwise. Pipe classes are to be as shown on the Drawings
d4e5cb4d-e9eb-5170-98b7-8f13c9797e3b | note | Verifying Document - Concrete pipes must be reinforced concrete rubber ring jointed pipe complying with AS/NZS 4058.
d89ffaeb-87bf-5fca-a133-efafeccd1a2d | note | Frequency - Per delivery/Item
e58bb0a8-76a9-5c79-a60f-14d42e48fde3 | note | Inspection Type (Visual, other) - Document review
2b53a682-d3e8-57c9-9ae5-535148631e2d | note | Inspection: Key - R
938da9d1-770c-5025-b5b5-04156aabcfc5 | note | Inspection: By - SE/PS
| checkpoint | 3.2.6 - PE & PP Pipes
e4911f16-f556-59df-818e-e30863d11269 | note | Specification - As per project specification (Pipeline Supply, 2.4.3)
99db7830-98c2-56f2-8ed7-d221cffbfffa | note | Acceptance Criteria - PE & PP pipe must comply with AS/NZS 5065.
2f1f735f-f4bb-5055-a701-eaf0b4843547 | note | Verifying Document - Data Sheet
b901239b-c3c3-5a6a-b44f-fe87380f4d26 | note | Frequency - Per delivery/Item
8e783e51-7e34-5ce7-9e55-c8e198e674c1 | note | Inspection Type (Visual, other) - Hold Point
f58a6c31-4c1f-5398-a465-859b49c19f92 | note | Inspection: Key - H
61acb71b-adac-586b-b935-8aacf8b9032b | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Precast Concrete Manholes
9773c656-81a4-55ab-89fc-ff47b20778bb | note | Specification - As per project specification (Pipeline Supply, 2.5.1)
c4661a7c-f3cf-5ec9-88f6-ad82e9eea926 | note | Acceptance Criteria - Unless shown otherwise on the Drawings, manholes (and manhole components) must be circular precast reinforced concrete manholes manufactured in accordance with AS/NZS 4058 with cast in base manufactured to NZ5 3109.
ddd04186-a6ba-5c7c-8292-38ea53cd18d8 | note | Verifying Document - Data Sheet
22c1f861-089b-55dd-b4ec-8c93c1cdebb5 | note | Frequency - Per delivery/Item
6d634d51-4574-5ce4-a51b-7339856cf0ba | note | Inspection Type (Visual, other) - Document review
82d4f308-16c6-5985-897c-fbf137ae80a3 | note | Inspection: Key - R
e1979525-f253-51bc-9904-8919dea69df5 | note | Inspection: By - SE/PS
| checkpoint | 3.2.8 - Manhole Lids
80fd3472-b2a7-52fa-b57b-a7b3561423b0 | note | Specification - As per project specification (Pipeline Supply, 2.5.2)
fbbd643a-a9ac-58b1-a05c-a5f013324a17 | note | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
1ec3ece9-6e15-58c6-b852-64de3620e591 | note | Verifying Document - Data Sheet
f2ec970d-5e80-5dc7-b437-82e7eeff17a1 | note | Frequency - Per delivery/Item
c62264ab-b8a2-51a6-8b8b-cb55aada10ca | note | Inspection Type (Visual, other) - Document review
c5d95ccd-7bca-5386-99a1-287ca785e783 | note | Inspection: Key - R
d6f2524f-7f1d-51d8-bbde-31d66f69035c | note | Inspection: By - SE/PS
| checkpoint | 3.2.9 - Frame and Covers
fcb5df1a-99d0-53ac-969f-d96e435ae456 | note | Specification - As per project specification (Pipeline Supply, 2.5.3)
c010ffdb-0315-5963-a29d-914130c81fd1 | note | Acceptance Criteria - Manhole lids must be precast reinforced concrete manufactured in accordance with NZS 5109 rated heavy duty (HD60) or HN-H0-72 as specified on the Drawings or as required by the local authority
164e8cd7-b60a-5416-a9ab-933a9acb08e6 | note | Verifying Document - Data Sheet
1212d052-c58a-5378-a216-a1f1add65962 | note | Frequency - Per delivery/Item
071e1b24-d697-55fb-9504-b663c95ca15c | note | Inspection Type (Visual, other) - Document review
51a59758-6b59-56f1-8be3-84f0726f3a29 | note | Inspection: Key - R
e2f2a9dd-5c5a-5c90-b4de-2f1f0e218c69 | note | Inspection: By - SE/PS
| checkpoint | 3.2.10 - Catchpits and Grates
7b6f3afa-ab4e-5752-b685-37941f6edb79 | note | Specification - As per project specification (Pipeline Supply, 2.6)
2af7c159-cc16-50b1-bb87-1bb0f031b70b | note | Acceptance Criteria - Use precast single or double catchpits manufactured from reinforced concrete complying with NZS 3101 and NZ 3109. Each single catchpit must have minimum internal dimensions of 450 mm by 675 mm.
f7adb9f4-902a-5a7a-b700-39ee84ce79b3 | note | ○ Use grates rated to class D complying with As 3996 with
4c6f898e-60d0-54f2-aed1-9e890cf99c8f | note | Verifying Document - Data Sheet
a4653dd6-5e83-53bf-9502-addf6eec1834 | note | Frequency - Per delivery/Item
85b7ad35-61b6-5d45-b37c-a33d788b6d88 | note | Inspection Type (Visual, other) - Document review
312e8852-3393-5ca2-ab23-c6c4600efbe6 | note | Inspection: Key - R
58b2609b-bb2c-596d-a71f-ee0b77df8636 | note | Inspection: By - SE/PS
| checkpoint | 3.2.11 - Subsoil
2e20ffe6-2c49-55e9-a841-182049907606 | note | Specification - As per project specification (Pipeline Supply, 2.7)
46a7dca8-d77a-50e9-867b-6f26f065c86b | note | Acceptance Criteria - Unless shown otherwise on the Drawings, subsoil drains must be DN110 perforated corrugated plastic pipe complying with AS 2439.1-2007 Perforated plastics and drainage and effluent pipe and fittings, Part 1: Perforated drainage pipe and associated fittings, and be minimum SN 4
efbce925-515a-58e4-aa31-73fcc3f817d8 | note | Verifying Document - Data Sheet
bd89f12b-55e9-5bc8-92bd-6b9600d7bf91 | note | Frequency - Per delivery/Item
3ab0f9f3-5ff4-52e9-b689-606002d49359 | note | Inspection Type (Visual, other) - Document review
6974ae86-fb94-5deb-b3c1-6d8b88b3182d | note | Inspection: Key - R
35bc2148-a73c-52f2-8d8d-f5b116ec4f6d | note | Inspection: By - SE/PS
| checkpoint | 3.2.12 - Materials - general
ce022224-c10a-5f62-af7b-3ad2895a77c4 | note | Specification - As per project specification T-WES 00012, Section 4.8
993f1b1c-ec7e-5b3a-96aa-676ad02e4bb8 | note | Acceptance Criteria - Do not change the source of supply of materials without written approval from the Engineer - refer Section 2.1
8d9c2559-b1dd-5d5d-ab07-11d4fcf2052b | note | Verifying Document - Approved list Verification / Datasheet
572c2317-fdb6-523a-a372-3dfd3d5e3437 | note | Frequency - Prior to use
8f407eda-7a18-55ef-ac92-569a7266f3a9 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
d9c99c3c-886c-556c-9d4b-7864bf8a2816 | note | Inspection: Key - R
486e14f2-1992-5930-a3b6-eb83be3bcf24 | note | Inspection: By - SE/CR
| section | 3.3 Receiving Materials/Parts - Portable water
| checkpoint | 3.3.1 - Water Pipes
8a2debff-70ac-5e57-b166-0b7c99095a68 | note | Specification - As per project specification refer T-WES 00013, 2.4
f6d62be7-a4e6-568b-99e3-5781f8851c62 | note | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
19ed925b-b027-5421-a887-28816c5bd4eb | note | Verifying Document - Approved list Verification / Datasheet
192a745a-3cb3-5109-886b-2ab28f23b71d | note | Frequency - Prior to use
915d003a-5da3-5f1b-bfe7-2c9a53e5f12d | note | Inspection Type (Visual, other) - Document Review
0d4f50c4-3b10-58dc-9d41-3a9e19588fd4 | note | Inspection: Key - R
e6d358a8-4cf5-5da8-80d3-3441e9430001 | note | Inspection: By - SE/PS
| checkpoint | 3.3.2 - Water Fittings
6c9542b8-9ddb-5609-becb-3fe68e1c8fc3 | note | Specification - As per project specification refer T-WES 00014, 2.5
877b6eea-44c9-5167-921d-610ff138f97e | note | Acceptance Criteria - All fittings shall be of the material, grade, diameter and pressure class shown on the Drawings/specifications and be on the approved material list
e9519f18-a0d9-502f-8704-61d8c575182e | note | Verifying Document - Approved list Verification / Datasheet
3413ff25-afd8-5c53-a88e-f00a1fcc7b53 | note | Frequency - Prior to use
ec49742e-482d-5ee9-ace4-920156057565 | note | Inspection Type (Visual, other) - Document Review
dc0fe4a9-b658-5411-8423-bccb465bccf8 | note | Inspection: Key - R
5f57c312-251c-5898-8c28-ae74e69a9189 | note | Inspection: By - SE/PS
| checkpoint | 3.3.3 - Joints
9446077c-fea9-5d0a-8939-5455354df3ed | note | Specification - As per project specification refer T-WES 00014, 2.6
fc8bb72f-fa91-598e-a480-864c0818b2b7 | note | Acceptance Criteria - All Joints shall be of the material, grade and size shown on the Drawings/specifications and be on the approved material list
a9a30492-d71a-5d11-a40e-243640844781 | note | Verifying Document - Datasheet
0e2f0408-43fd-52c4-bfed-d8d34eed632e | note | Frequency - Prior to use
77255dfb-c0ed-54a8-a0f3-b2db91e99603 | note | Inspection Type (Visual, other) - Document Review
f32afd7f-5aa5-5332-968f-9a2edfbd767f | note | Inspection: Key - R
d55e7123-8ab2-5f61-9295-f30398c6e0d1 | note | Inspection: By - SE/PS
| checkpoint | 3.3.4 - Fire hydrant and Valve Covers
9c80aad0-8794-500f-888e-d8365f03132d | note | Specification - As per project specification refer T-WES 00014, 2.7
b1e32df7-47be-5ec4-9a56-b77568f95959 | note | Acceptance Criteria - All surface boxes and covers over buried valves and hydrants must be rated to AS 3996 Class B (footpaths and non-trafficable areas) or Class D (trafficable areas).
b9d98fd1-9fa0-5b6d-905e-4ed0ee00c8d1 | note | ○ Use PVC risers and/or or concrete frames as necessary to provide access to the valves or hydrants.
251e4d01-5835-5911-a57e-1020ba79e4a0 | note | Verifying Document - Datasheet
f60eb62b-6111-539a-8fac-11e42f939113 | note | Frequency - Prior to use
7b790402-942a-5910-8a0e-65ffd2582c39 | note | Inspection Type (Visual, other) - Document Review
4d28867f-96f7-56d6-a9ac-f9c238788a78 | note | Inspection: Key - R
d3d4a365-bd34-55f2-81c2-f2271c29d99c | note | Inspection: By - SE/PS
| section | 3.4 General
| checkpoint | 3.2.13 - Embedment Materials (1)
0f0bc58a-0e19-5bf4-b5a5-eac8324c9d78 | note | Specification -As per project specification (Pipeline Supply, 2.8)
b2dbfc7b-c09f-5c98-97e7-79a3e6da2a90 | note | Acceptance Criteria - For flexible pipes, well graded processed AP20 complying with AS/NZS 2566.2 section 54.2. Any proposed alternative bedding material must meet the requirements of AS/NZS 2566.2 section 5.4.2.1 note 3 and may only be used if approved by the Engineer in writing.
26e99d3b-184a-5e27-9aea-8b51b7a524bb | note | ○ Where low-fines embedment material is specified on the Drawings, the material must be a graded AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation. Screened in-situ materials may be used for embedment
2d83174a-69fe-58e7-8fdc-e9a59b083fd0 | note | ○ Pea metal may not be used
75525fdd-3c27-5f1d-8bd9-1af625528c43 | note | Verifying Document - Test result
f521404c-d711-5520-8cb4-6be12b646263 | note | Frequency - 1 per 200m³
5514e32f-7f11-5262-9bb9-48769706bf79 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
da3bd11e-d2be-543b-a8fa-ce1c0139b09b | note | Inspection: Key - R
4b93c929-8c55-5b0a-8084-66bbf6105b64 | note | Inspection: By - SE/PS
| checkpoint | 3.2.13 - Embedment Materials (2)
aebe07cd-b4ae-5eff-ba27-8dd9d8504a14 | note | Specification -As per project specification (Pipeline Supply, 2.8)
040034c3-d25e-5a59-a0d2-255908409ead | note | Acceptance Criteria -For concrete pipes, Material with grading limits in accordance with As/NZS 3725 and the CPAA Engineering Guideline Selecting Materials for Bedding Steel Reinforced Concrete Pipe available from the CPAA website.
314cf994-46c5-57bd-8633-8219c518c4d1 | note | ○ Where low-fines embedment material is specified on the Drawings, the material must be a gradec AP20 with none passing the 2.36 mm sieve size (no fines material) that has the consistency and moisture content suitable for placement without segregation It is expected that screened in-situ materials will be used for embedment. The material used is to have a Compaction Fraction (CF) of 0.1 or less as defined below
4100e29c-9b3a-5e1b-9a65-b1fbc0dfaea4 | note | Verifying Document - Test result
05d21795-8fcb-53da-ad08-6ede865b45bc | note | Frequency - 2 per 200m³
03128e7e-3e66-581f-a8ef-41949448fd92 | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
6a74ee8f-eea8-557b-87cd-591b6e5162e9 | note | Inspection: Key - R
e69294d6-eedc-5be3-85ab-e45972f270aa | note | Inspection: By - SE/PS
| checkpoint | 3.2.14 - Trench Fill Material
355fa3e6-78e3-53fb-8755-4b6a39d5ecc7 | note | Specification - As per project specification
18bd78ca-cc14-5e30-9fab-f71af9c76c38 | note | Acceptance Criteria - Before construction commences establish the maximum dry density using NZS 4402 Test 4.1.3 New Zealand vibrating hammer compaction test. Submit results to the Engineer one week before importing trench fill material.
9a9ec8e7-1d58-564a-a942-ea7d6b309ac4 | note | Verifying Document - Test result
307e9e30-c6a6-5509-b62c-e087102e6666 | note | Frequency - Prior to imoport material
0da35efa-c238-5e41-ac2a-90a3ac3c2dc7 | note | Inspection Type (Visual, other) - Document Review
dc295222-6c34-58c6-a639-54002ef4f1eb | note | Inspection: Key - H
f70d59e2-00d2-51c1-8b1a-18c369077ae9 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.15 - Concrete
4523d2b1-1947-5886-bca7-be3e5de9e6fe | note | Specification - As per project specification (Minor Concrete Works, 2.1)
92e69120-0d6a-58fe-88e5-93a65a113bb3 | note | Acceptance Criteria - Normal concrete with the requirements of NZS 3104 and strength shown on the drawings. Where the strength us not shown, use 25 Mpa normal concrete
1168abee-ab94-57ec-bb0b-3d0f24c3cc9f | note | Verifying Document - Mix Design
803791d2-b1d7-5eb4-bf30-012ceabfc5a6 | note | Frequency - Per mix
26c87be8-ab35-5f4e-916b-9e803230c544 | note | Inspection Type (Visual, other) - Document Review
194ea468-784b-542c-8a24-2ad280fc01d3 | note | Inspection: Key - R
b09c6e9f-b6e0-53c0-b883-3135972314e6 | note | Inspection: By - SE/PS
| checkpoint | 3.2.4 - Geotextile
38e0fe2c-fb8b-523f-994f-d35ce0fe4a2a | note | Specification - As per project specification (Earthworks, 2.15)
1367a44e-2648-5091-9679-242e9edfaccf | note | Acceptance Criteria - Geotextile to be the grade and standards on the drawings and be on the Approved materials list.
6dc126b4-ca6e-5865-b03b-954959e1126c | note | ○ Non-Woven Filtration Class 1 and Geotextile Strength Class C
95778764-f363-5faa-a71d-ff5e94ef8894 | note | Verifying Document - Data Sheet
eb41fdf3-8d7c-58ad-9c60-15f5cf3b64ce | note | Frequency - Per delivery/Item
98bf6ee2-98ad-5fff-a3d4-80d0643956f4 | note | Inspection Type (Visual, other) - Document review
7c1dc271-a020-568b-9d80-d2012695d79d | note | Inspection: Key - R
6a6ece8e-227c-53d1-8160-34458891edf0 | note | Inspection: By - SE/PS
| section | 4.1 Soakage swale - Construction
| checkpoint | 4.1.1 - Swale - Formation and Levels
86f7e5cf-6635-5d08-aa4e-5a54463817de | note | Specification - As per design height
a96f0984-073d-5c3c-b62d-261102327454 | note | Acceptance Criteria - Ensure the excavation is clear of roots, projections, or obstructions. If overexcavation occurs, bring the bottom back to grade using excavated material, lightly compacting it. Do not leave loose soil. Notify the Engineer if the swale contains low-permeability soils; they will assess and advise on additional excavation if needed.
064be059-3198-5772-a75a-1cc7be51697d | note | Verifying Document - As-built check, photos
a739b6ec-baf1-555c-94b2-d9693a77ee0f | note | Frequency - Before instal the drainage media
50d78877-7486-5ff1-bdec-72c86c508250 | note | Inspection Type (Visual, other) - Survey, Visual
140b38f8-b9db-5f20-9e09-b4340db7790f | note | Inspection: Key - V
f1199d5d-2ae4-5e19-9763-e9587f36ea86 | note | Inspection: By - SV,SE
| checkpoint | 4.1.2 - Drainage Media
32380869-9db5-54cb-9651-091af4b75c28 | note | Specification - As per three water specification Section 3.3.2
d6d73a7e-9805-56ea-91ff-912b9cce859b | note | Acceptance Criteria - Carefully position drainage media in a clean, excavated area free of contaminants after removing materials. Use the media as embedment around the subsoil pipe, ensuring it is lightly tamped in the bedding zone without mechanical compaction. Avoid placing or lightly compacting drainage media in flooded excavations or saturated in-situ soils.
780b2f2a-d043-5eca-b5ea-6d822144d216 | note | Verifying Document - Photo
1e90e276-4865-56d0-aee3-4a3647788942 | note | Frequency - As progress
f3bedacd-1964-5192-a959-837ad4e19e0f | note | Inspection Type (Visual, other) - Visual
87543a0a-34b1-5453-81f4-f6c33951da1f | note | Inspection: Key - V
f0c3364b-997f-571b-a927-7a14fa13d317 | note | Inspection: By - SE/PS
| checkpoint | 4.1.3 - Subsoil Installation
5c4cb7a3-36a1-5325-b293-2e9f21402db6 | note | Specification - As per three water specification Section 3.3.3
6e9e0350-524f-5f92-85e4-df3349f186e5 | note | Acceptance Criteria - Position subsoil pipes centrally in the drainage media layer per specifications and drawings. Avoid laying pipes in flooded or saturated soils; no filter sleeves for perforated pipes. Install pipes parallel to bedding, avoiding ponded water in the swale. Carefully place a minimum of 50 mm of drainage media around the pipe, using it as embedment material without mechanical compaction.
104ed222-74bb-54d6-bc68-017b65bb5dfd | note | Verifying Document - Checksheet, Asbuilt and Photo
a102b39c-251c-5a76-9adf-0642322ee3dc | note | Frequency - As progress
1f269ea8-286b-5e99-a853-fecf8fd3a944 | note | Inspection Type (Visual, other) - Witness,Visual
789ca743-3162-5651-beaf-37bfdf6f5dac | note | Inspection: Key - V
ed2e555b-f0ce-58c6-9df8-ecea87a7ae50 | note | Inspection: By - SE/PS
| checkpoint | 4.1.4 - Sand Layer
ca9b5f65-3789-5560-97de-46da58c0f661 | note | Specification - As per three water specification Section 3.3.4
31b9ac52-ad62-51cd-936b-1d4c52a2a66a | note | Acceptance Criteria - Place a 400 mm thick layer of uncompacted sand over the Drainage Media, avoiding compaction with construction equipment. Ensure the subsoil drain is undisturbed, and rake the sand for a level finish.
49b9595f-9318-5f64-9f57-7dd34e318cf2 | note | Verifying Document - Photo
90e251d4-aa32-5128-b484-395d5a292513 | note | Frequency - As progress
a32442ad-c305-5ce2-aa58-136f464da920 | note | Inspection Type (Visual, other) - Visual, Dimensional
c30ef8fe-8046-57f9-80d5-aac3c3cab3ea | note | Inspection: Key - V,D
c6561c88-7b11-5429-8eb9-81b6e1b358bf | note | Inspection: By - SE/PS
| checkpoint | 4.1.5 - Soil Media
a57fd2ff-0cfb-5489-9e30-7a7249d30d4e | note | Specification - As per three water specification Section 3.3.5
f085af1c-4d71-547f-aaac-846e1e054d45 | note | Acceptance Criteria - Place soil media in a single lift up to 50 mm above the Construction Drawings' finished level for post-construction consolidation. Ensure a smooth, uniform surface, lightly consolidate the soil, and avoid disturbing the subsoil drain. Rectify sediment blinding as directed by the Engineer. Do not exceed 30% moisture content to prevent poor performance. Notify the Engineer for approval; upon acceptance, commence grass sowing within seven days.
99b7ca7b-c831-5ea3-ad14-f0a39203a365 | note | Verifying Document - Photo
836aaa52-6fba-509c-90c5-c258ecefd720 | note | Frequency - As progress
46ede2fe-7ae6-5271-a0ab-74cd3a82846f | note | Inspection Type (Visual, other) - Visual, Dimensional
c03078b4-1387-5b9a-9855-a3995c8bef29 | note | Inspection: Key - V,D
c1257820-2dbf-5a40-9bfa-a08f7cba678a | note | Inspection: By - SE/PS
| checkpoint | 4.1.6 - Grass Sowing
50759d7f-fcb0-5109-acd3-2d45406ae2b8 | note | Specification - As per grass sowing mix
a636fdc5-9e45-57a1-a4af-17bad422dbb8 | note | ○ Pernnial ryegrass 70%
73ab9e2b-495c-5576-a0ee-68a6d7d53bae | note | ○ Chewing fescue 25%
3fd51d71-908d-5aae-aac3-2bbf7466e470 | note | ○ Brown top 5%
2d7ce0aa-5234-59b2-9e4d-8c63db3ede15 | note | Acceptance Criteria - Sow an approved bird-repellent coated grass seed mix at 1 kg/30 m² and fertilize with diammonium phosphate at a minimum rate of 1 kg per 50 m². Aim for a 90% grass strike by the end of the Defects Notification Period, promptly fixing any surface depressions.
0cce5381-8cc2-59e3-8e98-bc08cda36e73 | note | Verifying Document - Photo, Docket, Mix design
92b5bf8a-f59d-50f9-a260-6b7dcbe7ea2f | note | Frequency - Per application
c13e722d-6f07-55f5-a6d5-160a3936cf4e | note | Inspection Type (Visual, other) - Visual Inspection, Document Review
01f46e31-c278-5904-a452-e44e36ed5c05 | note | Inspection: Key - R,V
d388d7e3-3b0c-53ff-94e8-1a8c2a050bbf | note | Inspection: By - SE/PS
| checkpoint | 4.1.7 - In-situ Infiltration Test
85b136bb-7cda-5112-bd49-2282c7411865 | note | Specification - Double ring infiltrometer Test Method
86bc4dcd-631b-5682-8204-12ff974bb1d1 | note | Acceptance Criteria - Test reslt > 50 mm/hr as per project spec
de881d07-f349-50c6-8356-3e7d10d936b7 | note | ○ Test to complete as per project's three water specification Section 3.5.1
e259c5aa-4d02-52ae-abed-c2654a054c80 | note | Verifying Document - Test result, Witness Engineer
43b5ca88-9208-5f45-9789-504a88e55644 | note | Frequency - Two test per stormwater swale
38b6c5df-ad89-55df-bcd2-283daa467d40 | note | Inspection Type (Visual, other) - Visual Inspection
d8e1b744-f402-53ca-98fb-d5f38d1317d5 | note | Inspection: Key - W
c18e0fbf-6d96-5f47-be2b-e18967bc7bc1 | note | Inspection: By - CR,SE/PS
| section | 4.2 Subsoil Drain - Installation
| checkpoint | 4.2.1 - Subsoil Drain Installation
36844eee-2cd0-5bf3-b092-d99a42c4269d | note | Specification - Downer Standard
f606ce93-ca05-5d30-aa95-55aca5f41d4a | note | Acceptance Criteria - Subsoil drains shall be constructed to the lines, levels and dimensions shown on the construction drawings and fully comply with the dimesnional and drawing specifications
efb5d01e-57cc-5ae8-99f4-c99c8a27e2df | note | Verifying Document - Checksheet, Asbuilt and Photo
d269721f-2835-59b2-8444-0e6a4d0e3963 | note | Frequency - Each subsoil drain
2895a1f0-3107-5485-9e26-d626a518458c | note | Inspection Type (Visual, other) - Witness,Visual
f5be996b-b734-5d43-bf3c-fb16fc601310 | note | Inspection: Key - V
06c53fae-a62a-5ebd-b09d-437683838249 | note | Inspection: By - SE/PS
| section | 4.3 Drainge Pipe - Installation
| checkpoint | 4.3.1 - Length of Open Trench
5fd3ba51-890e-5a50-92af-0aa78b9c2ef7 | note | Specification - Downer Standard
e1fa63c0-4cef-5870-a821-41cbdff0be06 | note | Acceptance Criteria - The length of open trench shall not exceed the greater of one manhole length or 50m and when offsite this open trench shall be reduced to a maximum length of not more than 10 metres.
1a7404bf-3ac9-5bbd-8b6e-8c9ffe2e178a | note | Verifying Document - Checksheet, Photo
aa25e30c-0059-53ee-9d9e-7d6cb0e96653 | note | Frequency - As progress
20207bfc-8189-581b-9fd7-d3a214e9c46c | note | Inspection Type (Visual, other) - Visual, Dimensional
83ca0b3b-9bf5-50e4-ab44-b90d0bc567d3 | note | Inspection: Key - V,D
6d4f1a59-2703-53ca-b8b5-36e23c0e35fb | note | Inspection: By - SE/PS
| checkpoint | 4.3.2 - Trench Width
c0847ab4-9788-5177-b04a-41f1bc767c54 | note | Specification - Downer Standard
2448d593-54d8-54e1-bf84-8e8375e5fd0c | note | Acceptance Criteria - The minimum trench width shall be 300mm wider than the external diameter of the collar of the pipe being laid, providing the haunching metal is compacted under and at the sides of the pipe.
1a483db6-b774-5739-9e38-9997f4ff580c | note | Verifying Document - Checksheet, Photo
c5d6f033-9f08-56f6-83d2-1f57b3656f8b | note | Frequency - As progress
b1acdd73-14fa-5fb2-b947-0669475f446f | note | Inspection Type (Visual, other) - Visual, Dimensional
79da8c8f-9514-515c-9c63-4e9d8baebb2b | note | Inspection: Key - V,D
583da95f-4f2d-5667-8aa0-e8146c6e2038 | note | Inspection: By - SE/PS
| checkpoint | 4.3.3 - Trench Subgrade
11da1cff-c1b3-5e12-b325-922723091f9f | note | Specification - Downer Standard
2ef3996c-0d0f-5107-817b-8b46b4d6199f | note | Acceptance Criteria - Complete Scala testing on the trench Subgrade to a depth of 1m every 10m and when the subgrade changes appearance.
2af7a940-c635-5ab8-9d33-4d6b28537749 | note | Verifying Document - Scala Results
ea6a0883-0a9c-560b-b1f3-3c7423f77903 | note | Frequency - Every 20 m
90e6a55a-b142-55d4-955d-e4c5fc01da07 | note | Inspection Type (Visual, other) - Inspection
3c5b0b5f-633e-57d7-a351-6557a115e1db | note | Inspection: Key - V,D
43b2e580-ecea-56f0-a1d7-4f8ed318655d | note | Inspection: By - SE/PS
| checkpoint | 4.3.4 - Line and Level
7e05614a-32b3-565a-8b9a-e73e17dd24c7 | note | Specification - Project Specification
72043555-87ee-519f-9a75-5b8cda2fdd3e | note | Acceptance Criteria - Pipe inverts shall be laid to ±10mm of the design vertical alignment. Pipes shall be individually aligned to grade. Gravity pipes shall not be laid at a negative grade. Pipe alignments shall be positioned horizontally within the greater of 50mm or 5% of the pipe diameter from the location specified.
13ff3b7d-9f2e-53f6-951e-9eb6b1c19399 | note | Verifying Document - Checksheet
b305c4dd-7ab6-55a8-bb16-8daca08cd624 | note | Frequency - Before backfill
e98677a9-3e88-5636-8dcf-7792033e9030 | note | Inspection Type (Visual, other) - Visual,Dimensional
96e4a965-693e-51c1-a5be-ff9250509342 | note | Inspection: Key - V,D
6f3b080f-66c2-5ca9-930e-8b63bc13213e | note | Inspection: By - SE/PS
| checkpoint | 4.3.5 - Backfill Placement
5a989e33-6fb4-5dab-ad56-a86f10b4736f | note | Specification - Project Specification
a6c7381b-dc37-5e1e-bb6d-add6c4aca3df | note | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
45bd4629-01cb-564c-bd30-28c68c6d61e4 | note | Verifying Document - NDM Report
66152484-d31b-5e6c-a0c1-a1d8f1430898 | note | Frequency - One test every two layers per 50 m
cd0c96ec-59b9-50f6-ae3e-acd80440465f | note | Inspection Type (Visual, other) - Check
8be37896-8378-5343-9caf-b1cf2a1126e7 | note | Inspection: Key - C
6b7edab5-bd0a-5a0b-8c82-b516021e03a9 | note | Inspection: By - SE/PS
| section | 4.4 Manhole - Installation
| checkpoint | 4.4.1 - Alignment
82b17b1c-9afb-5976-9924-bf319845dd74 | note | Specification - Downer Standard
8e56e086-2b2e-5287-84f9-202ea4ae2e42 | note | Acceptance Criteria - Structures shall be positioned within 50mm horizontally of the location specified. All structures shall be watertight.
6e1295d8-32f0-526c-a3e6-aaed9e50e54a | note | Verifying Document - Checksheet, Survey
53fc4508-c60e-56aa-a0c5-c28cbfb5f0a2 | note | Frequency - Each Manhole
74415834-cd75-53f6-afa0-9f7a6cc329cb | note | Inspection Type (Visual, other) - Check
edf1d271-23a2-5eb4-86e9-7bcb99561391 | note | Inspection: Key - C
41929c42-2467-5f16-b099-d7682c617da5 | note | Inspection: By - SE/PS
| checkpoint | 4.4.2 - Drainage Structure Foundation
31fc0728-cb4c-534f-91e3-0f00a76cb505 | note | Specification - Downer Standard
214578ae-5493-58e1-8ba3-fd0b10b9da7d | note | Acceptance Criteria - Complete Scala test on the subgrade underneath each structure to a depth of 1m
e526b8d4-1935-5ddf-b666-1759021d9c02 | note | Verifying Document - Checksheet,Scala
6d8aeb88-32a3-5219-a9c5-1d27fbf34bf6 | note | Frequency - Each Structure
97c03ca3-33f5-562d-aa4a-cdcffb9da1c7 | note | Inspection Type (Visual, other) - Check
9580b4fc-6b78-5d9a-85e9-5690471a0b69 | note | Inspection: Key - C
69a15cfe-9fa0-5768-a08e-07b953d3d930 | note | Inspection: By - SE/PS
| checkpoint | 4.4.3 - Drainage Structure Bedding
a928c0c7-058a-5eb1-89e9-6093c6cc86fe | note | Specification - Project Specification
587fe63d-a225-55d1-a81d-be0568c975a8 | note | Acceptance Criteria - Unless specified otherwise, all catchpits, manholes and other stormwater structures shall be founded on a minimum 75 mm bedding.
11edbf3c-8440-58f6-bf58-5628f9dfde3d | note | Verifying Document - Checksheet,Photos
8fc45c42-e31c-5f40-875c-9130c9fc839f | note | Frequency - Each Structure
6f3e7a44-e49b-5c6d-af61-a601045c50d8 | note | Inspection Type (Visual, other) - Check
603aee79-a105-5b8a-bcdd-a61fa89df027 | note | Inspection: Key - C
d40f1982-43d2-56d0-9ab8-6b6e5e5843b8 | note | Inspection: By - SE/PS
| checkpoint | 4.4.4 - Structure Backfill Testing
33a66237-8729-5fdc-9787-4efd9f4fa390 | note | Specification - Project Specification
fd207078-3a7e-5334-98fc-463afb802e8a | note | Acceptance Criteria - Backfill shall be placed and compacted in layers not exceeding 200mm to 95% of MDD.
ce78f519-23a2-57a5-b1c8-545dbcc993ab | note | Verifying Document - NDM Report
8de425d2-f6b1-5a97-b356-f5672e0a923c | note | Frequency - One test every two layers per manhole
e4d02464-d970-56c9-8cd6-e6dc0305d1c8 | note | Inspection Type (Visual, other) - Check
159934b9-874c-5e0e-8046-63fb917ee7d6 | note | Inspection: Key - C
746895e7-e858-52fd-a0d4-7e86f5ee0dec | note | Inspection: By - SE/PS
| checkpoint | 4.4.5 - Pipe Penetrations
44a4ba45-ce3a-58ff-ada6-ead4288acf38 | note | Specification - Project Specification
0eb2609d-4672-5310-a0dc-f5790fef518d | note | Acceptance Criteria - Drill holes around the intended cut line before removing the section to create pipe penetrations. Ensure that the diameter of the cutout does not exceed 100 mm beyond the outer diameter of the pipe.
d81474cd-4e19-52ca-bbfe-f9e196d68465 | note | Verifying Document - Photo
a7702891-9a68-5568-9fda-0aace4248945 | note | Frequency - Each Structure
c783852a-7faf-5560-8858-a7c0e277c3b3 | note | Inspection Type (Visual, other) - Visual
bc4f49a3-b362-5902-9ae5-fdbf336773ef | note | Inspection: Key - I
7d276012-2c31-5754-a894-b4539230dd2c | note | Inspection: By - SE/PS
| checkpoint | 4.4.6 - Benching
c1ffa80b-4c97-5485-8efb-3dd5625b992a | note | Specification - Project Specification
0120b6ab-b0c0-55d7-ae4c-ceee6fef5997 | note | Acceptance Criteria - Construct manhole benching and channelling using 25 MPa concrete. Cast and trowel manhole benching to shape, sloping towards the channel at minimum 1:12 with a U2 finish.
0b5c9b32-732f-5b58-b461-5eb1c85ecf31 | note | Verifying Document - Photo
0b3ab359-a843-5fee-ba9a-2a12071d7d9f | note | Frequency - Each Structure
10ed3475-19ad-56f0-9543-a1a9633b8813 | note | Inspection Type (Visual, other) - Visual
928131fb-4493-5918-ad9b-478a05dab343 | note | Inspection: Key - I
804cca1e-8596-5701-a3d3-fd634426f318 | note | Inspection: By - SE/PS
| checkpoint | 4.4.7 - Corbels
2ba23315-98bf-5cc0-a3aa-7a4a48ea1715 | note | Specification - Downer Standard
4b97f1f8-2e68-5409-b45b-fcca64e575c8 | note | Acceptance Criteria - Pipes shall be haunched and surrounded with concrete to a minimum distance of 200mm from the outside of the manhole in accordance with the drawings.
3ad4ef5f-680a-5842-b0dd-079446cf5048 | note | Verifying Document - Photo
76f68686-0a3c-5bf3-8db2-ef9ba8cdc33a | note | Frequency - Each Pipe Entry
19f4414f-dd65-5367-9946-b75359088691 | note | Inspection Type (Visual, other) - Visual
292cd75a-de74-506f-aa5d-c5fd012a81d9 | note | Inspection: Key - I
5b9cc270-fb4e-5967-9061-783576f51433 | note | Inspection: By - SE/PS
| checkpoint | 4.4.8 - Pipe ends
a9b0d3d7-e823-517b-8301-33363a253167 | note | Specification - Downer Standard
9f230bcb-1182-5674-86a3-0f19bd10ee50 | note | Acceptance Criteria - Pipe ends shall finish approximately 50mm beyond the inside wall and be plastered with cement mortar or encased in benching concrete in accordance with the drawings.
c6978a68-b0da-554b-bbd3-d2bb42b8d302 | note | Verifying Document - Photo
d753e5fe-1e46-51b4-8065-e155ab1e097f | note | Frequency - Each Pipe Entry
4129fdeb-29ef-59f3-9c75-18ed538da163 | note | Inspection Type (Visual, other) - Visual
f89efad3-9075-5492-9676-0d25eda1fcc7 | note | Inspection: Key - I
2fcdbb2d-7e44-5db9-a01f-9934d8ce8137 | note | Inspection: By - SE/PS
| checkpoint | 4.4.9 - Dewatering
2cac6c78-28eb-5c78-9a74-6ea095f7603c | note | Specification - Project Specification T-WES 00011, Section 3.5
5581f99e-5049-5fc4-ad57-6dd32ce7098d | note | Acceptance Criteria - Provide a method statement for controlling water in trenches or dewatering for the Engineers acceptance five days before construction, including:
b6ae95d8-4455-519f-bc28-d1405fd5c190 | note | – Reasons why the proposed de-watering system has been chosen.
1cc17060-cd00-58b3-8ca2-ad902d8741a2 | note | – Proposed location and details of any well points/spears.
0fdf45da-f98a-57fe-9f13-a0a374b527ac | note | – Details of back-up power supplies in case there is a power failure.
45c16ccd-07ef-510c-a34f-a5fe1d14aec3 | note | – Details of discharging (location(s), volume and flow rate) including environmental controls.
50535652-91d7-54b0-be4a-312d5c07baf6 | note | – A risk assessment with respect to dewatering affecting adjacent structures.
93af65e2-792f-5909-a10a-47f642b79a74 | note | – Detrails of how niose standards will be met.
23fe56f0-2455-5869-aff6-027c046ae936 | note | Verifying Document - Approved Verification
150aa7f0-b106-5be1-b699-1e61c347ca6b | note | Frequency - Prior to installation
568254f7-42fd-55a4-ac2d-bc6b6477be8d | note | Inspection Type (Visual, other) - Hold Point
98bb3c0a-47c0-523a-aeb5-59fc068a5dab | note | Inspection: Key - H
6cea0f9b-0917-59c9-b58b-034e101d4a6a | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| section | 4.5 Acceptance Testing and Commissioning
| checkpoint | 4.5.1 - Pipeline Testing - Acceptance Criteria
cf23478a-5a18-5173-bbff-8edc65cf2c27 | note | Specification - Project Specification, T-WES 00012, Section 4.6.3
6bd84d65-86e3-53e0-89a6-b9a745856546 | note | Acceptance Criteria - Pipelines including laterals shall be tested in accordance with one of the following methods as detailed in AS/NZS 2566.2 Section 6.4:
b2b2c4f8-398d-59b7-ad17-c87942a91285 | note | ○ Low Pressure Air Testing
19ae0af1-d76a-5c06-8b56-0aa9631d61ef | note | ○ Hydrostatic Testing
c317db39-ac2e-55a1-a752-116f4b24e602 | note | ○ Vacuum Testing
50ee42a1-24fc-511d-a89e-3b352a657107 | note | Verifying Document - Test Report
68ea479f-2a8f-5df1-883f-f5970bd6ca93 | note | Frequency - Each Pipline
d5f66706-d2ee-568b-b0ad-5e7d6585182c | note | Inspection Type (Visual, other) - Check, Visual
0938d6d9-6749-5be9-bd27-62d4d23ea56d | note | Inspection: Key - H
9d58b827-8c7d-503b-9d6f-2efd50aa2ed1 | note | Inspection: By - CR,SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.2 - Pipeline Testing - Testing Record Requirements
9f6f3d62-1d2c-5cc9-885f-0baf8c17b022 | note | Specification - Project Specification, T-WES 00012, Section 4.6.4
a8db0382-0525-5444-9948-11df057d9297 | note | Acceptance Criteria - The Test must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
0121adeb-cb0d-51c7-85e6-074d04979967 | note | (a) Date
eab5ccf6-70d8-5dd4-b57c-8842fa9f9636 | note | (b) Full description of section of pipeline being tested, including pipe length, pipe diameter, class and manufacture.
a1be1231-4296-57ee-95a5-4b30caf93edb | note | (c) Number of sump connections or laterals on the section being tested.
fcf288da-adb4-52ef-a15e-e6da0a6c05cd | note | (d) Test pressure and acceptance criteria
b7c22ee7-78f8-52de-9da1-2cf12318657e | note | (e) The start time of the test
7e739371-e268-500a-90b1-b964d8511557 | note | (f) The pressure at the start time
d409a400-c9b5-53f0-a125-241896dd4651 | note | (g) Time taken to drop pressure by 2 kPa
d620e927-86ff-53f4-bbca-d4295c90064a | note | (h) Minimum and maximum pressure in the test section and water loss over 30 minutes
267a3219-23dc-5418-924e-211ada171112 | note | (i) Whether the pipeline passed the test
776a7c15-cc79-5fa0-8578-445c9345b591 | note | (j) The name and signature of the Contractors personnel responsible for the test
cb485ad5-d0aa-52b0-99ad-913fc672265d | note | (k) The name and signature of the Engineers nominated personnel who witnessed the test
9d45aa15-2b64-52d9-96f0-819c1a241ec4 | note | Verifying Document - Test Report
752aaed2-22f0-5713-8056-c2afc243b8d3 | note | Frequency - Each Pipline
2920e26b-9601-5e2e-98b1-4243b436b5b1 | note | Inspection Type (Visual, other) - Check, Visual
22e2dd4c-3445-53f3-a29a-4a37238ef498 | note | Inspection: Key - H
f937eb80-47a3-50a8-a936-54358046a3f8 | note | Inspection: By - CR,SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.3 - Flexible Pipe Ovality Test
7dec9206-82be-5b87-9ba1-762cbdba3d93 | note | Specification - Project Specification
b449b350-b18b-5e5c-ade6-95b0647474b9 | note | Acceptance Criteria - An ovality test shall be carried out on gravity pipelines in accordance with clause 6.5 of AS/NZS 2566.2 “Buried flexible pipelines – Installation”. The test shall be carried out at least seven days after the pipe surround is laid.
1fa4769e-3447-59b3-80c0-b56529bf2951 | note | Verifying Document - Test Report
ab3214d7-bbf1-5c5d-ae1e-017ff7ffa082 | note | Frequency - Each Pipline
1a0fc0d2-cf5c-5636-b99e-196f68c36ef9 | note | Inspection Type (Visual, other) - Check, Visual
2e86dc49-3332-5313-830c-c3304cafe292 | note | Inspection: Key - H
f0f63cfc-4f67-5047-b609-ba59f1670a0a | note | Inspection: By - CR,SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.4 - CCTV Inspection
a954c86e-1681-5035-9eca-6f914f93b0bd | note | Specification - Project Specification, T-WES 00012, Section 4.6.7
047ba5ad-f534-5d8c-a198-8f614d329883 | note | Acceptance Criteria - All completed pipelines (excluding laterals and sump connections) are to be inspected using CCTV after backfilling and leak testing is successfully completed, but prior to final surface restoration.
7f211f1b-8342-5471-9dce-dbbe091bb2eb | note | ○ The specific requirements for the CCTV inspection are found within clauses (a) to (f)
8059104b-64c5-5153-9c88-ad93163075f7 | note | Verifying Document - Test Report
e7378419-aba1-5d32-96c1-dd3686457643 | note | Frequency - Each Pipline
360bc035-96fb-52eb-b849-8b9a3372c39b | note | Inspection Type (Visual, other) - Check, Visual
255614d5-0d80-5952-a16f-cd0c79357c20 | note | Inspection: Key - H
033fee25-6e73-5e6f-9fa5-3d4c4ced0d9c | note | Inspection: By - CR,SE/PS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5.5 - Manhole Testing
d012645b-4d1f-5a89-a84e-c8677b406767 | note | Specification - Project Specification
bd294820-4a5f-52e4-bf92-a5ef4a57de04 | note | Acceptance Criteria - All manholes (new and refurbished) shall be water tested. Manhole watertightness testing must be witnessed by the Engineer or their representative. A record of all tests shall be made and forwarded to the Engineer within 24 hours of test completion.
254a0566-c750-5bbb-82e9-b00980eb1cae | note | Verifying Document - Test Report
fcb73eb0-ef33-5f7a-8c04-873eb8891617 | note | Frequency - Each Pipline
972c4788-900b-5032-9c1c-409f711c7f6a | note | Inspection Type (Visual, other) - Check, Visual
7525b8ce-b32f-552c-9507-60da541d4e7c | note | Inspection: Key - H
d9941400-fdbc-548d-a4a4-c0e6d8f6074e | note | Inspection: By - CR,SE/PS
| signoff | AUTHORITY HOLDPOINT
| section | 4.6 Portable Water - Installation
| checkpoint | 4.6.1 - Trench Foundation
b1c08006-ebe8-51c7-b5aa-a09b66975ce1 | note | Specification - Project Specification
c9ac4ee2-a61f-5a52-8783-56ab99bd45c1 | note | Acceptance Criteria - Shape the foundation for uniform pipe support and alignment. Alert the Engineer if unsuitable trench floor material and await instructions before proceeding with additional work.
81005241-5da4-5e67-804f-1e8fcc4b2bee | note | Verifying Document - Scala Results
2ccaef25-71ea-554e-a22d-04174caa82a8 | note | Frequency - Every 50 m
7c0a48d0-3cdf-53a2-ae2f-354ec137cdb9 | note | Inspection Type (Visual, other) - Inspection
93bb131c-093d-5260-82f2-3d914b04d99e | note | Inspection: Key - V,D
0011e745-b2ba-509a-b6c9-0ed07e695c29 | note | Inspection: By - SE/PS
| checkpoint | 4.6.2 - Soft Ground faft Foundation
dc62371a-e6d6-5cb1-8483-605e915c1a6c | note | Specification - Project Specification
f79c01d1-4d67-57b4-bf58-0ff17c2a4324 | note | Acceptance Criteria - Refer engineers advise where the foundation fails to meet the design requirments.
78534871-a998-51ae-aa6d-063d1a2d6f31 | note | Verifying Document - Checksheet
db88966b-21b6-544b-9376-7d0068bc3373 | note | Frequency - for each event/as required
75a16737-5fbe-5bdd-a87c-487588ba296e | note | Inspection Type (Visual, other) - Check
765a3cd2-f5bc-5e95-bc43-d3447c4a1107 | note | Inspection: Key - R,V
5ebe68bc-870c-5a1d-bf86-8359a3528158 | note | Inspection: By - SE
| checkpoint | 4.6.3 - Geotextile
ad5a881f-535d-5d03-9846-0b9abd560ac1 | note | Specification - Project Specification
a3929d6a-75e7-5c33-8547-880b518602ae | note | Acceptance Criteria - Geotextiles shall fully wrap raft foundations, in accordance with the manufacturer’s specification, where rafts are required.
0d6125a3-2236-51f0-9942-f00d55870d64 | note | Verifying Document - Checksheet
dfe05db6-02b6-567b-a3f8-5d7dbdd9bdbf | note | Frequency - for each event/as required
a52dab91-b465-5324-acf3-961a3c5bdc76 | note | Inspection Type (Visual, other) - Review
d61b598f-b0db-5402-8d1a-91c9d7f5a3aa | note | Inspection: Key - R
f93c4330-d8a2-525b-a064-a3337e8e882c | note | Inspection: By - SE/PS
| checkpoint | 4.6.4 - Embedment Construction
85d5b34b-e98b-5295-853d-7a08ae32be52 | note | Specification - Project Specification T-WES 00013, 3.1.5
93e583bc-ad06-5bc9-806d-086190c8f24a | note | Acceptance Criteria - Place and compact all filling materials in layers not exceeding 200 mm compacted thickness. For pipe embedment at least 90% of the maximum dry density (MDD)
a68ddf4e-023d-5ce4-8920-a5fb88aea410 | note | Verifying Document - NDM Report
f274c23a-925d-5b44-994e-d167619418b5 | note | Frequency - NDM Every 50 m per 200mm of fill
0e32a60a-9a0c-57b7-825a-4ec6e1fd9b4c | note | Inspection Type (Visual, other) - Inspection
0cb4778d-d68d-53a3-aa4f-dc45fc22ff15 | note | Inspection: Key - R
1a0d8a48-a7bc-5150-87a4-5061b8c3c55c | note | Inspection: By - SE/PS
| checkpoint | 4.6.5 - Laying and Jointing of Pipes (1)
d401548b-2739-5e45-85a5-e51526f26800 | note | Specification -Project Specification T-WES 00013, 3.1.6
405a5221-cedb-5c93-9e4d-4866eaf46540 | note | Acceptance Criteria - Lay in straight lines, beginning at the lower end of the line (unless agreed otherwise in writing with the Engineer), and complete each joint before another pipe is laid.
feb535eb-a5fd-5d8c-91f1-9acf69da0109 | note | ○ Lay all pipe with manufacturing codes and class markings facing upwards.
d9b8cdb7-0c53-5074-9c4f-c059dbc62781 | note | Verifying Document - Checksheet
41bcbda4-1d50-5b7d-b95b-1630339c3b49 | note | Frequency - Each Pipeline
e5aa21d9-0084-5ced-bfce-0a88091d3dab | note | Inspection Type (Visual, other) - Check
cb27036c-4923-5797-b629-29a9c51e5fc9 | note | Inspection: Key - Check
e20c7d43-c207-567a-9150-4c141d264ebe | note | Inspection: By - SE/PS
| checkpoint | 4.6.5 - Laying and Jointing of Pipes (2)
dde10345-e968-5e26-a7b1-fca003c2ff1b | note | Specification - General, Project Specification T-WES 00013, 3.1.1
e33d6b6b-5f38-56b2-98c5-a2f4584eb43f | note | Acceptance Criteria - Submit the proposed methodology for pipe laying, concrete work, jointing and backfilling to the Engineer and obtain acceptance before starting pipe installation.
e5e57973-24f6-544f-881a-0e9c47e7a7a1 | note | Verifying Document - Approved Verification
060ef314-e6d3-5963-aa1c-800f84b08602 | note | Frequency - Prior to installation
10f25e21-3e24-531e-a772-3880fdc96427 | note | Inspection Type (Visual, other) - Hold Point
7cadb874-5f2e-5e6c-bf1c-8708a562bbe9 | note | Inspection: Key - H
7877a050-b3d8-56a6-9a90-76e1784e839e | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.6 - Thrust Blocks
b57aa003-0f38-5220-aad0-7e7301693db0 | note | Specification - Project Specification T-WES 00013, 3.1.12
3c4230f4-c7a0-5c00-99e9-e9d56e8656a5 | note | Acceptance Criteria - Unreinforced Concrete Thrust Blocks
dd0ecf40-399c-549a-99cd-ed0b4bcfff9d | note | ○ Precast concrete thrust blocks can only be used where approved by the local authority. Arrange for the Engineer to inspect the first completed thrust block.
0889e563-1a9d-5132-a2f4-8875fa9b2982 | note | Verifying Document - Checksheet, concrete test result
69461ffd-4a82-5a3c-90de-3d4580aef2ef | note | Frequency - On the first completed thrust block
fa1ad160-2ad4-5124-9490-283cedca83c3 | note | Inspection Type (Visual, other) - Inspection
54d9b6ea-3e64-59d4-b1db-7e9fe87f313c | note | Inspection: Key - H
753fab1c-2362-5960-87f9-68f0b8475a00 | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.7 - Thrust Blocks
8c9e1b5a-0c02-5563-88fd-7caf8a076ff0 | note | Specification - Project Specification T-WES 00013, 3.1.13
58142845-46ba-5dcd-83e9-60e8c0aad5bf | note | Acceptance Criteria - Reinforced Concrete Thrust Walls / Thrust Blocks
23ebf643-65b8-5616-9fd2-48c589b798a3 | note | ○ All thrust wall steel reinforcement must comply with AS/NZS 4671. Have the Engineer inspect the thrust wall reinforcing and puddle pipe arrangement prior to pouring concrete.
041845e8-52a1-599f-ade1-7c8ffdc57b5e | note | Verifying Document - Checksheet, concrete test result
5f74ed19-f5fe-51de-bb6a-b5d8bc2d8f40 | note | Frequency - On the first completed thrust block
0303175b-2a65-55ee-90c5-84b5fb5b8054 | note | Inspection Type (Visual, other) - Inspection
072647fe-9067-5bd7-b9f3-5ea0f1a492cc | note | Inspection: Key - H
c8674d03-be46-5f79-b39e-7fc824a366a9 | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.8 - Flanges
b787bb1b-869f-5b38-ad5f-b0df457785c9 | note | Specification - Project Specification T-WES 00013, 3.1.14
cff2febc-ac75-5321-b533-3a76414b1dcd | note | Acceptance Criteria - Complete the flange bolting procedure as per project spec and check sheet
d768ca11-de27-5fc5-ac13-29d46575ec4c | note | ○ Have the Engineer witness the first flanged joint completed on the PE 100 pipeline
aa926442-8053-57ab-ab38-2cc64c2c9777 | note | Verifying Document - Check sheet, photo
6a1cb8f5-141a-55eb-832c-285be61da8c4 | note | Frequency - First flanged joint completed on the PE 100 pipeline
0f43155f-65ec-5bbc-9cdb-872215a35cc3 | note | Inspection Type (Visual, other) - Hold Point
2a0eab65-21fe-5980-9d59-97eea18102ac | note | Inspection: Key - H
ed5b87d8-d65f-5498-aded-9784f0a1d0bd | note | Inspection: By - CR/SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6.9 - Backfill
05d58c06-66fd-573c-a6d3-a681057691e4 | note | Specification - Project Specification
f0cca8c0-ca96-58d5-909b-46b46cf365c0 | note | Acceptance Criteria - AP65 backfill shall be compacted in 200mm loose layers to at least 95% of the maximum dry density (MDD) every 50m.
71dc5ac3-43a2-5e83-8707-98151e5b0d96 | note | Verifying Document - NDM Report
2a3a03ea-1b12-5996-a960-a405275d9239 | note | Frequency - NDM Every 50 m per 200mm of fill
3eed26af-88aa-5b40-8963-9fab6eb39ede | note | Inspection Type (Visual, other) - Inspection
9896cdeb-8922-51a2-887e-8759587d0a4d | note | Inspection: Key - R
b5f821ae-ae8c-5d6f-b4db-de1cca113b5a | note | Inspection: By - SE/PS
| section | 4.7 Portable Water - Testing and Commissioning
| checkpoint | 4.7.1 - Pressure Test
43c75bb1-44e7-5d7b-8cfe-430300d9e63c | note | Specification - Project Specification, T-WES 00013, Section 4.5.7.2
def11b13-b802-52ff-afa2-bc71a6dfac24 | note | Acceptance Criteria - Complete the pressure test in accordance with the project specification and the check sheet for pressure test.
a65dda83-08f2-5d84-b1b0-ebeddf87652c | note | ○ The system test Pressure (STP) is 1,000 kPa.
94751220-6cd3-57fa-b44f-d483d0722d85 | note | Verifying Document - Check sheet, photo
8e11ec10-1e90-5780-bea3-ab5d872ec641 | note | Frequency - Each major pipelines
f81bcbec-107a-50af-9471-063ba6569529 | note | Inspection Type (Visual, other) - Check
e868b285-44cc-517f-a9d9-6e15decaa630 | note | Inspection: Key - W
00316a4d-c401-5ec6-b2f9-07cb1d1e066f | note | Inspection: By - SE/PS
| checkpoint | 4.7.2 - Pressure Test
ca283725-72d1-55df-9574-55928faa7cd7 | note | Specification - Project Specification, T-WES 00013, Section 4.5.3
1ca752cd-042f-50a7-ab4f-427d1fcd224d | note | Acceptance Criteria - Before commencing any pressure acceptance test:
9fb783a8-b50d-5842-ac6f-948254faa713 | note | ○ Give the Engineer at least two working days notice.
e7b9a128-2895-5703-96d5-24f6d5c001c0 | note | ○ Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 working days prior to the test, including but not limited to:
5c2a69d7-f909-575e-9964-4b4021f33d97 | note | ○ Proposed equipment to be used, including pump/s, water meters, logging pressure gauge/s, check pressure gauge/s
499cdbc5-2e13-5765-8929-7e2a354383c4 | note | ○ Proposed fill rate, noting the bulk fill must not be greater than the discharge capacity of any air valves and any local authority constraints relating to the supply of water
709235c1-0b75-5e6a-8f01-67bdb508e78b | note | ○ Calibration certificates for meters and pressure gauges
e0671784-390d-5911-ae60-5012d9e4427c | note | ○ Details of qualified personnel who will be carrying out the tests
e126cafd-0f92-5a40-870e-058f1f903034 | note | ○ Source/s of water proposed to be used
41e9fa4b-3e32-56ed-8267-6ee09828ba60 | note | ○ Provision for backflow prevention
53237996-366f-5138-91cf-f7ec466b297b | note | ○ Location of the pressure test rig and the proposed test pressure at that location if the elevation of the test rig is higher than the lowest part of the test section
9b50cc49-6dab-5617-b73a-d7684d3a4d12 | note | ○ The test lengths proposed that will ensure that no pipes are over pressurised or inadequately tested
b808b65d-e306-5049-997b-92219b793227 | note | ○ Pressure test report template
74d516ae-50fc-5b11-9f16-dd621dd924df | note | ○ Health and safety risks and mitigation measures
aa4e1cf4-f3f2-5cda-a269-f9f85976e50e | note | Verifying Document - Check sheet, (WMS)
bbd8b5d6-be77-583f-8b57-0e04fb18c7b2 | note | Frequency - Prior to pressure testing
50b24ff6-bab9-5934-bcd8-26768e1b40ff | note | Inspection Type (Visual, other) - Review
0c629d6b-6e7f-58fe-b2f4-5911ffb6b713 | note | Inspection: Key - R
3b290881-c736-5de8-928c-36b9d6e708a1 | note | Inspection: By - CR/SE
| checkpoint | 4.7.3 - Water Main Disinfection
24d7b2dd-699c-591d-ae16-2b7c7d99503a | note | Specification - Project Specification, T-WES 00013, Section 5
9d44ba70-59b6-53fe-b219-5528e1a9de0e | note | Acceptance Criteria - A resolution with a remaining free available chlorine (FAC) level ranging from 15 to 20 mg/L (ppm). By the conclusion of the disinfection period, the water expelled from the pipelines should retain a minimum FAC concentration of 5 mg/L.
36dfe76e-0e3e-5e97-ad91-6de125786ee1 | note | – Prepare to submit a WMS for disinfection of potable water pipelines to the Engineer for acceptance before commencing disinfection work. The WMS must include (at least) details of:
3b8d60a7-08b5-5493-8279-784dd3fd20cd | note | ○ Swabbing all potable water pipes, valves, and other fittings (> DN 63)
bd363fcc-68c5-5b4f-a4a6-baa48755142b | note | ○ How the disinfection solution will be introduced with the initial fill water for pressure acceptance testing, if done, Note that this will be at the Contractors risk
7d3f3723-4abe-5bda-8d3a-e83ba6088080 | note | ○ How the disinfection solution will be prepared and delivered reliably into the pipeline. Include calculations of dosing and flow rates, strength of the proposed liquid or powered form of hypochlorite as well as methods for checking that the required FAC is being achieved
6c938862-7f78-5e67-88d9-77411d447a09 | note | ○ How it is proposed to ensure that all watermains, service pipes, valves and fittings will receive nthe disinfection solution
e2ee3341-9043-5dac-a30a-dfba690f131f | note | ○ How measurement of the FAC during and at the end of the disinfection process will be achieved to ensure that the system has been fully disinfected
c38413a7-96be-5b7e-8c0e-a7e50bf59b2b | note | ○ How the disinfection solution is to be disposed of safely at the end
5e9a4137-cf81-561e-9351-c0a4ccd6c731 | note | ○ Identified health and safety risks and proposed mitigation measures
bc125590-d432-583c-bd2f-b2bda88c44c5 | note | Verifying Document - Checksheet, (WMS)
ac21b588-d773-5d42-b9fa-69c0154d8787 | note | Frequency - Before commissioning
d4b2d092-3fa3-5d8e-a847-06097ebadb76 | note | Inspection Type (Visual, other) - Review
63b89a29-c441-5f37-b7ee-6d26dec5314d | note | Inspection: Key - R
de880e00-5032-57a2-a9b6-4fa8e25fe6b0 | note | Inspection: By - SE/PS
| checkpoint | 4.7.4 - Flushing of Reconnection
66e26222-30e8-57da-8f5b-fd97daf5b817 | note | Specification - Downer Standard
d23b93bf-448f-55ad-9e55-90dc8af7ecba | note | Acceptance Criteria - The Contractor shall open the front outside hose tap, if available, before the supply is reinstated to any premises. Wherever possible, the owner shall be notified prior to this work.
34f7518c-2223-578e-b738-0269cb5f8f82 | note | Verifying Document - Checksheet
8f0df7af-a32f-5284-9665-0cfeaac65cf6 | note | Frequency - Each Connection
cbfcd16b-9618-529c-911a-122f114eb6bf | note | Inspection Type (Visual, other) - Review
4bd39009-8ba6-51c3-9989-58df932553d5 | note | Inspection: Key - R
5441c512-bbf9-5649-8ce6-7fc020353271 | note | Inspection: By - SE
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
c7d572e6-7ae2-5e1e-b33a-6e39ed374d19 | note | Inspection Point: Quality Control Activity - Upon completion of works
01403bdb-1c2c-5d72-860d-f0bf4f61e689 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
83717ca1-d771-568c-afde-a8e43bdf0d20 | note | Verifying Document - Closed-out NCR/Defects
40c7cbfe-cd2b-5107-b38d-8d24a95681ce | note | Frequency - Post construction
7737ac79-621a-5525-b3e3-098f5873e0db | note | Inspection Type - Review
48cc0f57-3b22-538d-a6d9-5ba5cd23b6d7 | note | Inspection: Key - R
e9efde8f-fb54-584e-879e-c8a69f6fcf4d | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
2d0e2484-9315-5062-92fe-96b0e6436c9b | note | Inspection Point: Quality Control Activity - Upon completion of works
38db2921-4b66-5549-851e-1db12d63deea | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
ca05b3ed-5970-5946-9ed0-ba9e9d281b8a | note | Verifying Document - As built survey record completed
8ab129fa-8817-578c-a64d-62513390ef07 | note | Frequency - Post construction
12947246-1b7e-59bb-9ad0-ab286fdf1668 | note | Inspection Type - Review
6b4c6c1d-47a5-5f08-bcf1-65d462635760 | note | Inspection: Key - R
0d1cef4d-dacc-5abc-80c1-e55052135be1 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
486e061b-d2b3-5a7b-8f69-0d06558b04f9 | note | Inspection Point: Quality Control Activity - Upon completion of works
44019f63-3eb0-5a11-9e60-478b2dd41cac | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
3bb50b29-2447-57fa-97e3-3ccec101355d | note | Verifying Document - Signed As-built Drawings
7fef968a-2468-5b5d-a5c5-67bb204b1217 | note | Frequency - Post construction
caca1982-7ad8-555c-bcb9-31c0d0a8279d | note | Inspection Type - Review
db44fe1a-4ef3-5d3e-8a6c-d665a3427695 | note | Inspection: Key - R
0cefa4b9-1097-5873-8430-fa8347fcf3d8 | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
9f11196f-4ff9-5404-9a78-fd0607ea08ef | note | Inspection Point: Quality Control Activity - Upon completion of works
ee3686d4-6063-572d-b005-d405b64bbd94 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
56b5161e-48fb-5983-9ce7-abba0702ce9b | note | Verifying Document - Register
3eaa36de-83d8-5139-b46e-1ecffea8a117 | note | Frequency - Post construction
a1aff9b6-36be-57bc-bea5-e9480ca19bbf | note | Inspection Type - Review
b8e95476-7523-5db8-a558-05d4250b2b2a | note | Inspection: Key - R
9e1419c7-d68e-57b8-b8d1-3b5e14839072 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated and signed-off
0f3a0c20-2d2d-5dab-92d4-85d47e2f5aa6 | note | Inspection Point: Quality Control Activity - Upon completion of works
bcd00112-9917-5edf-a3b8-b5ea2bc8551d | note | Acceptance Criteria - All signed and closed out
eca34f9d-48a6-5fbb-82ad-64684e894446 | note | Verifying Document - Signed off Documents
8d8ae49f-1258-5ffe-9371-b41bdeb21c8d | note | Frequency - Post construction
81ddee49-f059-5f7c-b4e3-3de7be88d6c7 | note | Inspection Type - Review
61f8388c-473a-5d89-9606-8c6d09f33062 | note | Inspection: Key - R
9e1052c9-45a5-5a3d-bded-84a24f5273b8 | note | Inspection: By - QM
| checklist | Ω (Deprecated) DG-OWR-VMS-ITP-001_v1 - Variable Messaging Sign (VMS) Site (v1) | itp | DG-OWR-VMS-ITP-001_v1 - Variable Messaging Sign (VMS) Site | 8e45936a-a0c2-47e0-b904-21d3d7b05f50
| section | 3.1 General Preliminary
| checkpoint | 3.1.1 - Survey Setout
db170fe4-ad1d-5ea2-8e70-7978e1f4b6c6 | note | Specification - Downer
eb51b859-eaea-5c37-8c01-1ff00fa718aa | note | Acceptance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
4e5698f5-6ce9-5e9e-b442-410fca351c0a | note | Verifying Document - Survey Records
af0b74c4-ab6c-5dbb-a4e8-b29685983c9d | note | Frequency - Prior to Works
f0dcb600-8b36-55db-a832-177c5a02462b | note | Inspection Type (Visual, other) - Document review
ac33c05e-4543-5cba-afbc-6b2107defa72 | note | Inspection: Key - H
54563c1f-69ab-5f57-ba41-e5ebbf760dab | note | Inspection: By - SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Service Location
907a4db6-5144-5a78-8d11-76d3c2e84c7f | note | Specification - Downer
0cd550b5-6ece-5b83-8c18-b196a40a58c7 | note | Acceptance Criteria - Complete the on site check to identify, locate and protect all services.
97f38751-362c-5a9e-b74f-7a89e9e16e8f | note | Verifying Document - Service location documents
4c5ef64f-5c48-520a-8010-906255ea29e7 | note | Frequency - Prior to Works
4067af60-6bc7-503c-a332-a311c334697e | note | Inspection Type (Visual, other) - Document review
a889d65a-6e16-554e-b482-219772735cd0 | note | Inspection: Key - R
4cf30c70-a2d6-5ef7-8a4a-99e65a927fd7 | note | Inspection: By - SE
| checkpoint | 3.1.3 - Internal Permits
2041d0e8-eaac-5b95-9f78-5e28aa684b65 | note | Specification - Downer
9b5ad21e-e091-55c0-8489-8b64e178702e | note | Acceptance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a654d987-96e3-5866-a250-066ab43eb3de | note | Verifying Document - Internal Permits
02ffa68e-23a8-503e-80ba-33c42581f16f | note | Frequency - Prior to Excavation
e7a9c2a1-319b-566e-84fd-46934c021ae7 | note | Inspection Type (Visual, other) - Document review
67b8e688-7d17-5fa6-80b0-552d2ad2f9d3 | note | Inspection: Key - R
c2df5860-ece0-5c14-ac71-3f49e088c111 | note | Inspection: By - SE
| checkpoint | 3.1.4 - External Permits
8a3610e7-cc76-5e63-9719-c7b8be60aad8 | note | Specification - Downer
4117e5bc-fec9-5023-8f90-f0cb2c8c8574 | note | Acceptance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
cb9b52d2-d06e-59ea-87b7-1c55fcecb378 | note | Verifying Document - External Permits
726d1e24-035e-5ce2-895b-1b63393e420b | note | Frequency - Prior to Excavation
bf8a7fbd-ec14-5084-9cbc-b907dcdd88db | note | Inspection Type (Visual, other) - Document review
e8276f1b-3696-56a1-a19c-21e9f9205264 | note | Inspection: Key - R
b3785eb9-ecd3-5003-be97-e17bbb1abad8 | note | Inspection: By - SE
| checkpoint | 3.1.5 - Approved Construction Drawings
275ec621-0502-558a-bece-d54ca6cb8379 | note | Specification - Downer
2207dd36-bb92-559e-9c13-463a5feea8ed | note | Acceptance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
2d422072-e7b0-532e-87d0-439fd115808b | note | Verifying Document - IFC Drawings
a1cda6b4-fdce-5d9c-8104-af1785db5bb6 | note | Frequency - Prior to works start
02c7b21c-dc86-521f-9540-c1b4b9a4c74f | note | Inspection Type (Visual, other) - Document review
b3f552cc-e40a-598d-8dd6-55070439a328 | note | Inspection: Key - R
6615fb2a-e455-5780-9a52-9445ab01fb56 | note | Inspection: By - SE
| section | 3.2 Receiving Materials/Parts - VMS Foundation with Plinth and cabinet pad
| checkpoint | 3.2.1 - Concrete mix design
bb85f5e8-118a-57a1-90a5-882dfa4068a0 | note | Specification - 30Mpa Structural Concrete
14743aa9-0b1e-5486-be96-f0dbc7e9854d | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
1f4603b1-0245-502f-baee-958f176a623d | note | Verifying Document - Concrete supplier mix designs
95f8b237-746e-56f6-9f43-85b553e288dc | note | Frequency - Submitted to Client Engineer for approval before construction
dae10ede-a033-596d-a3a8-08ada22de518 | note | Inspection Type (Visual, other) - Document review
6552fbb6-ce10-5a85-a281-7448ba7bfc0f | note | Inspection: Key - H
33fa859a-d6b5-5200-a0a3-e5954cf1d8b5 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - Reinforcement
c09b7466-15b4-5411-a737-d3c5772f1f65 | note | Specification - As per Design Specification
d52c47bf-146d-5ba7-a67d-82946b987d18 | note | Acceptance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
38ecc65a-c756-5584-8d21-a85cf16f6eb1 | note | Verifying Document - Mill Certs
6b525724-6458-5881-9886-dac25b98c884 | note | Frequency - Each Lot
92645d27-28b8-5fe3-9c24-26c86e721eb3 | note | Inspection Type (Visual, other) - Document review
c36ec62d-7412-5a77-a96b-643bcb2a73d8 | note | Inspection: Key - R
c3df58e3-f54f-5c73-906c-5ee1c89dc081 | note | Inspection: By - SE
| section | 3.3 Receiving Materials/Parts - Shoulder Widening and Sealing
| checkpoint | 3.3.1 - AP65 - Source Property Tests and Sampling
f7782e16-8e58-592a-bc47-449a7c3fcef1 | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006 NZS 4407 : 1991 NZS 4402 : 1986
e2ba20c3-55d2-5fc7-b308-a4ec5220a9cf | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
02eea1db-65e5-5be9-a84a-64cc6f98d58e | note | Verifying Document - IANZ Lab Reports
58384f08-4002-55ff-9679-008c7cd7b725 | note | Frequency - 10,000m3
fd6440b8-814b-57db-b608-9fc89f488485 | note | Inspection Type (Visual, other) - Document review
ada56867-1c61-5d4c-8dad-ea8d06ca821f | note | Inspection: Key - H
e14f2af5-6584-58d1-a23d-7c8225191059 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - AP65 - Production Property Tests and Sampling
0d8d9377-8e3f-5c0c-aae9-4ee70d00f372 | note | Specification - TNZ M/3 Notes : 1986 TNZ M/4: 2006, NZS 4407 : 1991
2e095677-478f-5aaf-b9a1-1ea57eddcc92 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
68e14abc-2804-5c13-add9-1a46575345ae | note | Verifying Document - IANZ Lab Reports
a36700ff-57cc-55a6-b7be-506ea7acea89 | note | Frequency - 3 per source initially, then 1/1000m³
e7a589e7-aa54-501c-8a34-dd56550200ad | note | Inspection Type (Visual, other) - Document review
af6793b6-63c5-5e18-bf1e-3b7a45b3b782 | note | Inspection: Key - H
a1b719d7-042e-59eb-ba1f-95c018016b3b | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.3 - AP65 - Testing for Layer Compaction - MDD
73b19890-296a-577a-99e3-5727ce6124d4 | note | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
3cb4b5dd-8ee7-52ef-bab8-318ca6c01180 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
7355d2a7-7926-5a3d-9aea-4873aa197ff3 | note | Verifying Document - IANZ Lab Reports
540c77dc-5e62-56ff-934f-5cd7d496f956 | note | Frequency - 5,000m2
a69d7608-845c-5429-8df6-dfc5c654a7b4 | note | Inspection Type (Visual, other) - Document review
e2636e90-13f4-5472-b3a6-c608983be663 | note | Inspection: Key - H
99d36c70-05db-5afc-bc59-ee2c23e29a4f | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.4 - AP40 - Source Property Tests and Sampling
e27cf4c1-b368-5b42-8dbc-3cd63cf0d807 | note | Specification - TNZ M/4: 2006 - 3 NZS 4407 : 1991, NZS 4402 : 1986
f0b1a043-bb9d-5a51-b118-e0c10eb30b53 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
b4588984-6082-5d1d-895f-adad642af4d4 | note | Verifying Document - IANZ Lab Reports
bfdd41a2-6645-5263-9994-73630c41ca37 | note | Frequency - 10,000m4
27002e23-fa87-52bc-9b3e-59ad6ee6f39c | note | Inspection Type (Visual, other) - Document review
399d61cb-eb2b-516c-897f-e0a5914cfcc2 | note | Inspection: Key - H
c5b55e8d-3164-5110-8eed-fb3e9f7061cf | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.5 - AP40 - Production Property Tests and Sampling
8f14a4e2-149c-5ad2-8a39-23b096cecb75 | note | Specification - TNZ M/4: 2006 - 4 NZS 4407 : 1991
a15469b1-bae1-596b-a56c-31e18ff8bcd2 | note | Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
39783722-dc43-56f0-b334-a32c07b2f86d | note | Verifying Document - IANZ Lab Reports
823e1555-14d7-54e2-b9f7-01738ff4cbf0 | note | Frequency - 3 per source initially, then 1/1000m³
ce9e76a3-ab04-5a47-a188-bac2fb5cbb4c | note | Inspection Type (Visual, other) - Document review
65d62e8e-a063-50b4-a120-147396d064ac | note | Inspection: Key - H
8db283e5-4a71-5f72-bbc2-66b385945429 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.6 - AP40 - Testing for Layer Compaction - MDD
09a9abdb-e53e-5d51-a7c7-76e3763329c0 | note | Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
ff22b021-6f3d-5a90-adb0-0c78ea773851 | note | Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
4fbbc037-2c82-5dce-a404-7a64794a599f | note | Verifying Document - IANZ Lab Reports
2393eb56-2e2f-5aa7-b091-b3f0d8016eac | note | Frequency - 5,000m2
11009622-1ba9-54d0-87b2-be020766c5c8 | note | Inspection Type (Visual, other) - Document review
3415a0b7-6442-5ecf-ac1f-6bad2262e73b | note | Inspection: Key - H
d8a4c9a4-eabf-52c6-807b-36c19ccd7748 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.7 - Sealing Chip - Source Property Tests and Sampling
a5562eea-5704-5028-aa17-d604b495418f | note | Specification - TNZ M/6: 2019 - 4
0cf1d76f-f088-5dc9-8012-45fc351d3e40 | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
10f82895-c752-5abe-92e7-4d691f1ac0df | note | Verifying Document - IANZ Lab Reports
7e3e2781-dc4e-5002-bcce-27fae3c59847 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
c65c362f-af51-53fd-8a41-561b4ead189c | note | Inspection Type (Visual, other) - Document review
e4ac2782-6314-52b5-a2ae-2ead7f8dbd0f | note | Inspection: Key - H
1c9c5d80-d2a5-548d-9276-2747e26b2650 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.8 - Sealing Chip - Production Property Test Sampling
94dbe4fa-74cc-5a5d-aa86-a4b6bf35ac35 | note | Specification - TNZ M/6: 2019 - 5
c7698ee5-a71d-505e-9e81-5c43201d1bea | note | Acceptance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
23d9b0ef-718a-5a38-8f4e-faaf3854ba08 | note | Verifying Document - IANZ Lab Reports
2cfc9e5b-53f3-51d7-9b75-acacf283d5e6 | note | Frequency - Every 500m3
ed3fe3e3-3639-537a-933c-ee58e2509858 | note | Inspection Type (Visual, other) - Document review
c6a6a81f-a4bd-5b09-bf77-0214678d9eb5 | note | Inspection: Key - H
50bf2870-3d34-5350-8a40-b91160dbe643 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.9 - Bitumen - Quality Testing
5d282093-b43a-5750-bbe5-742c6493c059 | note | Specification - NZTA M01: 2022 - 6
e74acb8c-9d94-5b71-81ef-6660ff7f8df5 | note | Acceptance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
4010ec20-0ca3-5bd4-86c0-7cda72129c56 | note | Verifying Document - IANZ Lab Reports
fd0ebdb0-4239-55dd-b69f-5c6a827084b2 | note | Frequency - One test per grade supplied
665c43e8-b73e-58d9-ba65-68c0767860e7 | note | Inspection Type (Visual, other) - Document review
b015c3a4-7d94-524e-9348-67d5a70579e1 | note | Inspection: Key - H
7e8ec164-a714-5b0a-9052-e54b4bf4cc2f | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.10 - Bitumen - Supply Testing
ad763527-96dd-5acf-8f92-cdd2a4332e7b | note | Specification - NZTA Q05: 2022 - 6.2
2f403523-da12-588c-9ac5-00b6a8ba7d18 | note | Acceptance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
03f99bf9-e351-526a-8fec-b00557bc1852 | note | Verifying Document - IANZ Lab Reports
b95f7721-b14e-5529-8222-f407ddad7dcd | note | Frequency - Every 200 tonnes supplied.
394a54d6-8436-5af4-89c0-d71a93d5dda7 | note | Inspection Type (Visual, other) - Document review
534a5be4-16ca-5e81-8d6c-b5b86ff799dc | note | Inspection: Key - H
5dbaac16-fe43-5f8f-b83f-f69278f38a4e | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Receiving Materials/Parts - Safety Barrier
| checkpoint | 3.4.1 - Barrier Mill Certs
1b95a741-b364-54c8-a469-2083547998f2 | note | Specification - NZTA M23 AS/NZS 3845
6abee064-9826-51be-8cf7-cde737ddabd0 | note | Acceptance Criteria - Compliance documentation
05041540-7cdb-5217-be4c-b4e7b061a300 | note | Verifying Document - Mill Certs
c5623d7a-cd7e-5570-beff-694010a6d441 | note | Frequency - Prior to commencement of works
92315ef5-1f71-5a0d-b30c-2c8d386b8992 | note | Inspection Type (Visual, other) - Document review
47a9a8f8-1119-5717-b6a2-925f0b19f415 | note | Inspection: Key - R
ee53c4dd-6fc0-52b2-a5f7-814a6b101c92 | note | Inspection: By - SE
| checkpoint | 3.4.2 - Concrete mix design
34eeb4be-7a61-51a6-83fa-f23f94dfe3ef | note | Specification - As per Design Specification
c638ac65-eb1f-5de6-a46c-e2ce8a38fdde | note | Acceptance Criteria - Concrete Mix design for each mix comply with the requirements of the Project Specification
a2dc26e6-2788-52ce-bee8-9d353b636e78 | note | Verifying Document - Concrete supplier mix designs
3ba31a56-a9dd-5e34-9249-1e60199e2005 | note | Frequency - Submitted to Client Engineer for approval before construction
3dcdf14b-2a35-5f51-a621-c7baf5b022df | note | Inspection Type (Visual, other) - Document review
b4803cc2-b45e-59bd-906b-9d183698eb2a | note | Inspection: Key - H
421ffe80-7544-5bc3-9320-dec8125a4ae6 | note | Inspection: By - CR
| signoff | AUTHORITY HOLDPOINT
| section | 4.1 VMS Foundation with Plinth and cabinet pad - Construction
| checkpoint | 4.1.1 - Construction Location
aa864b0e-1f5a-50d7-8d43-610fe6dbae18 | note | Specification - Design Location
c220a4a6-5886-5390-8f42-8903cad9053b | note | Acceptance Criteria - Proposed location of construction to be staked out to the engineer for review prior to construction
8e03d8cf-dad7-54b6-a7ed-04ded32c5dd0 | note | Verifying Document - Approval letter, Photos
6694ac7c-958d-5bdc-b633-c6f753ed3ffe | note | Frequency - Prior to each foundation build
194ec37e-35b6-52c8-b847-d272eae15bd1 | note | Inspection Type (Visual, other) - Visual Inspection
51e8be2d-7fc4-5587-81b5-7a8702d79024 | note | Inspection: Key - V
a8c7db3b-fc50-529f-b9c2-5a2ac57192ab | note | Inspection: By - CR
| checkpoint | 4.1.2 - Ground Compaction Test
13f1a6e6-9ecc-5652-b8af-e31a082e09cd | note | Specification - Downer Standard
3631c764-5f77-58d0-ac32-80ac47ee6062 | note | Acceptance Criteria - Compaction shall achieve a minimum Clegg Impact Value (CIV) of 20 on the first layer and 25 on subsequent layers
1719d238-8f7d-530b-a83d-cbb398924691 | note | Verifying Document - Test reults, Location of Test
33016c94-df99-5ef8-91c7-42e26d9fdc4a | note | Frequency - For each Foundation
c5b9d632-1592-5190-8959-a3b19a78accb | note | Inspection Type (Visual, other) - Check
2b7c88fa-dade-546e-a5f4-6649ddbc1a32 | note | Inspection: Key - C
dcb00c3a-f92b-590c-b05a-c1b2e6cd0d21 | note | Inspection: By - SE
| checkpoint | 4.1.3 - Reinforcement and Hold Down Bolt Inspection
31d0e151-5330-59cd-8578-77ebc555b2d9 | note | Specification - As per Design Specification
d5ed90dd-4331-5ff3-a5a7-5c1c78e5bae4 | note | Acceptance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
1e36869e-a03f-5177-853f-b54b6409c983 | note | Verifying Document - Pre pour, Photos
1a75317b-32b3-59db-a4eb-3c31ad7a8434 | note | Frequency - Prior to each foundation pour
c06fa45a-92f1-535a-99a7-7ac704e11026 | note | Inspection Type (Visual, other) - Visual Inspection, Dimensional Inspection
f925105d-9ab8-504f-8f7e-9c64f62e655f | note | Inspection: Key - H
9fe00352-1412-521a-8d81-ca1f4733d3cc | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.4 - Electrical & Comms Ducts Placement
63e3b5b6-a8d8-569c-9f40-c83bdec60bac | note | Specification - As per Design Specification
95b0e6d2-3fb3-5376-88c9-f7c7004a577a | note | Acceptance Criteria - Compliant with the construction drawings
0d786c36-8710-51aa-84d0-6f3b43ae80b6 | note | Verifying Document - Pre pour, Photos
05fd55cf-7cb1-5d6e-a29a-4ed71da6e88e | note | Frequency - Prior to each foundation pour
96d79acd-1518-54e4-aa15-497c889f830a | note | Inspection Type (Visual, other) - Visual Inspection
0b882a37-025c-537e-9dab-679ab9eb34ad | note | Inspection: Key - H
11d2e717-7415-52ac-b6f7-6c169efdaa2e | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.5 - Pre-Pour Inspection
de858135-c648-53f0-b98c-7e5462e78cf5 | note | Specification - Downer Standard
7aa13700-bdf9-5bde-80eb-494139f4d96f | note | Acceptance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
94184449-1fc0-50c9-8cdb-7d5e27f963d7 | note | Verifying Document - Pre pour, Photos
93480235-1c59-5d82-890e-c3a4fae18259 | note | Frequency - Prior to each foundation pour
e2c1e96c-9429-5a2e-a095-db312118fe43 | note | Inspection Type (Visual, other) - Visual Inspection
477c20f6-d99c-582b-bffd-8af7dceed4f9 | note | Inspection: Key - H
1b11d0f0-ff3e-5352-a02c-b2ea4bc7517c | note | Inspection: By - CR,SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1.6 - Delivery Dockets
0380b90c-ae2f-54e2-accc-942e77c86fc8 | note | Specification - Downer Standard
54868f82-c47a-5d05-a049-4f32c1165796 | note | Acceptance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
8476e372-df9d-5da2-90fb-27ae8b4e430f | note | Verifying Document - Dockets
10900ae8-2745-59ab-a2e4-3517576f7dce | note | Frequency - Each Pour
bd219ce7-45d7-5852-82fd-65dd3353926a | note | Inspection Type (Visual, other) - Review
b908dbdc-32fc-57aa-8b6d-b99ccf4be966 | note | Inspection: Key - R
e81162f5-56b3-5d91-9778-97687a9e7dde | note | Inspection: By - SE
| checkpoint | 4.1.7 - Compression Testing
c4b71c23-0f5c-5019-9c30-b4c431b30f7b | note | Specification - As per Design Specification
b7cbac36-fea4-51a2-a3bf-09a143801947 | note | Acceptance Criteria - One specimen from each pour shall be tested at 28 days.
0f4ff113-35b3-566e-9bdb-fa5b96f66e7b | note | Verifying Document - Test Results
5e3f5b9c-1e30-5f5d-85e9-6d0039c3a6e7 | note | Frequency - one test per 50m³/per pour
661d496b-c11e-5b7e-bb1a-7bd5c21f0095 | note | Inspection Type (Visual, other) - Review
664a8560-4897-5a7d-a466-8f6c806ba500 | note | Inspection: Key - R
10d7dbff-7339-5ccd-92dc-6e2ec620a21e | note | Inspection: By - SE
| checkpoint | 4.1.8 - Post Pour Inspection
855c45f6-60e3-59c2-b33d-2eb43bec65f2 | note | Specification - Downer Standard
2850c0a1-1895-5e44-b21d-54fa13c87383 | note | Acceptance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
eb5ca30c-4daa-521e-b1c1-fa78a1f3a939 | note | Verifying Document - Post Pour, Photos
e5b2f7e3-263b-5879-ae4f-7ccce2dca50a | note | Frequency - Each Pour
2b5f2777-a195-5bb9-b14c-8f6b9f68dd05 | note | Inspection Type (Visual, other) - Visual Inspection
9d49de03-96f3-589e-a2cc-717023d9cfd1 | note | Inspection: Key - R
a8e63215-04d4-5c11-bf3a-7381184006fb | note | Inspection: By - SE
| checkpoint | 4.1.9 - Defective Concrete Finishes
277a523d-73bc-5386-b0b9-744af86c18a9 | note | Specification - Downer Standard
9325e3cc-4229-55c8-9343-3b68f4f18162 | note | Acceptance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
d3389205-90c4-59a2-8e82-ba9ded05985d | note | Verifying Document - NCR
1fd0cecc-7b0a-5721-b00a-fc7da34c8e71 | note | Frequency - Prior to minor repair
25f5e59f-047d-57ae-9418-ec0a4314b2d7 | note | Inspection Type (Visual, other) - Review
35acfbf5-fe23-5098-94d0-367a81da3fb5 | note | Inspection: Key - A
352b653f-d126-558a-8925-8cfc400ef209 | note | Inspection: By - SE
| section | 4.2 Shoulder Widening and Sealing - Construction
| checkpoint | 4.2.1 - Material Placement
821eb356-1b61-505e-994d-be1ebb904fc5 | note | Specification - Downer Standard
c5f6934a-b162-5e4e-b5b3-dcd6a53dde21 | note | Acceptance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored thoughout
2b8b9faa-1017-5c34-b05a-fc58f40b7d91 | note | Verifying Document - Survey / Level Checks
041e6260-a511-5ca6-80fe-b6c7ced1e038 | note | Frequency - Continuous monitoring.
8766a392-3ef2-544f-b691-c40a704ec8a6 | note | Inspection Type (Visual, other) - Check
f6ead409-a13b-5931-aafd-14ab2afcc201 | note | Inspection: Key - C
91cdc113-7abd-5fad-bc10-dd6365811238 | note | Inspection: By - SV,PS
| checkpoint | 4.2.2 - Pavement Shoulder Widening
0e62da8d-027b-564e-9719-a0c4b29656d6 | note | Specification - Design Specification, Appendix E, Section 2.1.4
1bf63150-fa16-5c2b-baaf-e5b958069172 | note | Acceptance Criteria - Pavement sholder widening treatment will be confirmed with Engineer on site
4b7138a8-1eaa-5362-a4ad-f804f9d9d055 | note | Verifying Document - Approval letter, Photos
636d26c7-de03-5629-804f-c73c10c19b5f | note | Frequency - Prior to construction
9e43a4f1-dfcb-53c8-8c56-f9a0b8ce3aa5 | note | Inspection Type (Visual, other) - Visual Inspection
90dbf6a4-7850-57c1-b58f-fb45326e6855 | note | Inspection: Key - V
d8ad4318-d543-5fbc-9bfd-9e889d2f3378 | note | Inspection: By - CR
| checkpoint | 4.2.3 - Sub-basecourse Pavement Layer Compaction (NDM)
fd8f3c26-0894-5de3-ace0-421c72319647 | note | Specification - TNZ B/02: 2005 - 7.6
166d50bd-5dfa-5a3e-aaa6-d06ad5326617 | note | Acceptance Criteria - Mean Value ≥ 95 % of MDD Minimum Value ≥ 92 of MDD
0c77ac56-5df1-5b09-a2c7-367ece07c4ba | note | Verifying Document - NDM Report
bd680175-786b-5f27-9604-9ad426c0e79a | note | Frequency - 1/10m
e63a94d5-281f-5e32-8983-6faa2ac7610d | note | Inspection Type (Visual, other) - Check
7114aa04-3844-512e-89d1-aad53403a888 | note | Inspection: Key - H
c83c38df-a483-59aa-8b60-1427f95cc422 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.4 - Sub-basecourse Layer thickness
b13c5b0d-7bed-554f-beb3-d586100c5519 | note | Specification - TNZ B/02: 2005 - 5.1
d595c12a-f301-5374-8e13-4d75c6061c2c | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –25 mm +5 mm
99463640-fc4f-58ba-a62f-596f92deb029 | note | Verifying Document - Survey / Level Checks
949b2ae0-23b8-5edd-991a-255443275a85 | note | Frequency - 1/20m Full width
9e19ed13-1253-543e-b5d7-c4b047eb9ac7 | note | Inspection Type (Visual, other) - Dimensional Inspection
31248c1b-898e-5d23-9847-a25658dc6b3a | note | Inspection: Key - D
737ed9dc-2f12-5461-8b9f-fd40d341e1f3 | note | Inspection: By - SV or SE
| checkpoint | 4.2.5 - Basecourse Pavement Layer Compaction
e9eb6aed-a2b4-598e-ba3e-87d08e71c26b | note | Specification - TNZ B/02: 2005 - 7.6
2b37d76c-9bb1-5d4c-a9ee-9e5278c50c39 | note | Acceptance Criteria - Mean Value ≥ 98 % of MDD Minimum Value ≥ 95 of MDD
56fc585d-2c09-5945-822e-2b7b88cf4fc6 | note | Verifying Document - NDM Report
637a6f31-c798-514f-b545-8c036f5ca995 | note | Frequency - 1/10m
b86845fa-8145-599c-8fe3-1d1b046f025f | note | Inspection Type (Visual, other) - Check
49ccf00f-1d58-5a48-bb2e-6239d57ea06d | note | Inspection: Key - H
c8ce5694-303d-59bf-9315-d6743b84c258 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.6 - Basecourse Layer thickness.
2be3381c-4c7c-5c99-a8b9-2d83a454c112 | note | Specification - TNZ B/02: 2005 - 5.1
ecd04136-9e3d-5fe4-affe-8405ecad7d87 | note | Acceptance Criteria - The Sub-basecourse shall be monitured for Layer thickness. –5 mm +15 mm
5aef12f1-f929-568a-8536-cd5ed24efe16 | note | Verifying Document - Survey / Level Checks
fc8221f0-d6ae-5f16-9e1c-968a1f3d0cf8 | note | Frequency - 1/20m Full width
42435a08-dd94-5ff3-a1ff-35f555d36183 | note | Inspection Type (Visual, other) - Dimensional Inspection
aaef20d2-f6bf-576e-baa6-46a9dfa9f34b | note | Inspection: Key - D
6e9cf795-0efd-5461-8a6f-5e80f1696623 | note | Inspection: By - SV or SE
| checkpoint | 4.2.7 - Surface Shape
5da8d607-6b7a-5b60-8f1d-5a54741cec78 | note | Specification - TNZ B/02: 2005 - 7.7
d986c9d3-d84f-58dc-ba97-5a3f32849d6b | note | Acceptance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
72e36426-d8b9-5243-acf7-a876dc70170b | note | Verifying Document - Survey / Straight edge Report
f6d8d949-a9a8-5ad1-8ece-48df5d1c6722 | note | Frequency - 1/20m Full width prior to sealing
f48b9fea-251f-548b-93d2-413eeffeef02 | note | Inspection Type (Visual, other) - Dimensional Inspection
014e6a6f-1058-574b-b416-23c4ad6f88da | note | Inspection: Key - D
e9099251-daaf-5d67-a335-b624ed1b69ab | note | Inspection: By - SV
| checkpoint | 4.2.8 - Surface Finish post sweeping
352648b1-7cd6-5a04-9cb8-cf6d23531a8a | note | Specification - TNZ B/02: 2005 - 7.8
d43dc7e7-5a63-55cf-bce4-fc845023cbd8 | note | Acceptance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
81b80656-16d1-5fd2-bcb0-f0bcbb269bed | note | Verifying Document - Photos
fc5af306-482e-5435-9079-96325fd41dbc | note | Frequency - Prior to sealing
61f14c35-8ae3-5cef-adb3-9fa51a54f3b8 | note | Inspection Type (Visual, other) - Visual Inspection
17895c04-887d-5802-9e2e-830936a58fdb | note | Inspection: Key - V
4b9f5328-0ac8-5c4d-8eaa-dd0de50e8eb0 | note | Inspection: By - SE
| checkpoint | 4.2.9 - Preselling Requirements
f2a88d12-f80f-56fd-afd0-c7724f60fbe5 | note | Specification - TNZ B/02: 2005 - 12
a6ed1378-6c31-5776-b8aa-efc26b9b44d1 | note | Acceptance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 80%.
70c9796d-6053-5645-a1db-2e9f8d5ab004 | note | Verifying Document - NDM Report
6d7e8f9b-b878-5149-92f7-267a7fe16c51 | note | Frequency - 1/10m
0e6eb6f0-7345-5b60-9c42-fa94fc22ccf4 | note | Inspection Type (Visual, other) - Check
bb7123f0-b025-5c66-9ca7-9c6108334181 | note | Inspection: Key - C
6085c447-2f70-5832-8ca4-b51f2092dc8c | note | Inspection: By - SE
| checkpoint | 4.2.10 - PreSeal inspection
fc9a5e93-e67a-5778-9262-9202e4a672c9 | note | Specification - TNZ P3 TNZ B02
4460d4eb-6ece-5760-94b3-ec6a0bcb3bcc | note | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
c17827ae-8834-594e-8973-326b9755ba9f | note | Verifying Document - Hold point Release, ITP Sign off
c6731058-1f47-5d06-a4e7-d46c5aa53116 | note | Frequency - Prior to sealing
870cc00c-07cd-5a1b-b4a1-082082bacf45 | note | Inspection Type (Visual, other) - Check
c1bf241a-9be2-55f4-9524-71e0412bb717 | note | Inspection: Key - H
51f78c7c-b83e-5d63-807b-b7a88104e733 | note | Inspection: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.11 - Spray Temperature
6eb9f4a1-4d99-55a0-af7c-616ed959ce11 | note | Specification - TNZ P3
6601acc1-63d9-5568-ae50-56f08f2bc3db | note | Acceptance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
2eab4ebf-ce63-5a59-9f19-9a0b9c625c79 | note | Verifying Document - Sealing statement
b6cae85a-20a4-5536-a02c-aa36a0c09ec9 | note | Frequency - Prior to sealing
290b80de-97b7-52ff-a9b9-125c0b9d9e48 | note | Inspection Type (Visual, other) - Check
b6087a4e-1793-514a-8732-21fcad955688 | note | Inspection: Key - I
a36527ae-826b-5d4c-92dc-59f7e2f7e750 | note | Inspection: By - SE
| checkpoint | 4.2.12 - Chip Application
2436ce2b-77cf-5be0-8444-2b489b723428 | note | Specification - TNZ P3
08beb5c1-54f6-50c9-8241-c1bab6dfe8b2 | note | Acceptance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
6e3dfdc0-bbac-53f8-89c3-a8ab7c206d98 | note | Verifying Document - Sealing statement
d9a44d2b-803c-5f73-ac0d-e04b6cc7fba6 | note | Frequency - For every spray run
78f71e81-03df-51d9-85d9-770923612993 | note | Inspection Type (Visual, other) - Check
d5a7c88c-1eb2-53c5-abf1-d0d50195eca3 | note | Inspection: Key - I
90537e88-b679-59ef-963e-64db10427c3f | note | Inspection: By - SE
| checkpoint | 4.2.13 - Post Seal Inspections
f4dd3e8b-b2f3-5482-b8f6-5915af2065c6 | note | Specification - TNZ P3
e6a18fdc-f372-55d9-97e7-1d2795cbc810 | note | Acceptance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
5874a92d-5e89-5d68-98ee-97d8ace0e857 | note | Verifying Document - Engineers Acceptance
8b6329e8-9c46-56d1-892e-05812558fb04 | note | Frequency - Prior to TM Removal and After Final Sweeping
ff96f12d-6e45-5e57-a38e-dbff9e14f096 | note | Inspection Type (Visual, other) - Visual Inspection
ac8c15a9-7f7e-5303-a887-122764ee061f | note | Inspection: Key - H
4a99bf1a-64cc-5fd9-9a1e-23360ac748ad | note | Inspection: By - SE,CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2.14 - Chipseal Repairs
b34b74f0-3ffc-5c4a-9d86-700863f3b056 | note | Specification - TNZ P3
10876410-2926-59a0-bf85-5e44281a77fd | note | Acceptance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
d539d563-0565-5f04-a9d7-864350cdc9ce | note | Verifying Document - Approved Repair Methodology
6f10095e-fdcc-5aa1-8718-4b4b8798c019 | note | Frequency - Prior to Repairs
b3062b9c-e1a5-5730-b6a8-be78d475e7a2 | note | Inspection Type (Visual, other) - Review
5c0b1e71-562c-59db-87b8-c0b98a8e94b4 | note | Inspection: Key - A
d1d87885-2dce-539b-926a-2a7b809f7180 | note | Inspection: By - SE
| section | 4.3 Guardrail - Installation
| checkpoint | 4.3.1 - Guard rails - Location
b13ef075-97b4-5888-84ba-57a732d8d6c9 | note | Specification - Design Specification, Appendix E, Section 2.1.3
e7844cd5-9cff-5b2c-aba7-d464690c15b1 | note | Acceptance Criteria - The Contractor will set out the guardrail location with the Engineer on site.
b0a86d32-fdde-5219-ae9b-60423fcbda09 | note | Verifying Document - Approval letter, Photos
3981890d-8040-541c-a180-ff3f6bb9417b | note | Frequency - Prior to construction
4c020104-453b-5692-9c33-6de65fbdc0dc | note | Inspection Type (Visual, other) - Visual Inspection
e353eb9c-cfa8-5b86-94c3-2ed25412417f | note | Inspection: Key - V
868e47c7-328f-53eb-8968-c6fbac24f65b | note | Inspection: By - CR
| checkpoint | 4.3.2 - Guard rails - Installation & Checklist
8573c815-55de-5a32-a78a-94547d2971d0 | note | Specification - As per design specification
7259509b-744b-5be6-93ec-c0db8a6c031b | note | Acceptance Criteria - To complete the check list along with the guard rail installer after the construction
c3fd3168-a890-58d6-adbc-9b3ece4d876b | note | Verifying Document - Check Sheet DN-QC-06 Photos
220c80c8-04d6-5aa6-86e5-248ad3afe63f | note | Frequency - For each site
69f87d94-e007-57f9-ad89-726a28e59c0c | note | Inspection Type (Visual, other) - Visual Inspection
9db3b232-f299-5ccb-addc-5dcfe22b60bc | note | Inspection: Key - V
d46242eb-edba-530f-8267-060702407889 | note | Inspection: By - SE
| section | Final Inspection and Handover
| checkpoint | 5.1 - Construction Record Compilation
b85898fe-4bad-5e1a-81a8-3dd141a5e7e7 | note | Inspection Point: Quality Control Activity - Upon completion of works
a6f728de-6741-5877-9bae-057cd0cc70c0 | note | Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
8da32013-b30b-58e1-af11-e7545f4527c7 | note | Verifying Document - Closed-out NCR/Defects
a4c9824a-2192-54ba-8c5a-8c772bec2f2b | note | Frequency - Post construction
ed5ee712-3fdc-507f-aadd-5b492503a46d | note | Inspection Type - Review
539363cf-fca8-56bb-9b63-eef554db9e83 | note | Inspection: Key - R
1e2d7c9b-25c2-5a8b-9529-ef695b7a1205 | note | Inspection: By - SE
| checkpoint | 5.2 - As-built Survey
ccf54a8b-1fed-5c68-bd0d-b377a89b6aa2 | note | Inspection Point: Quality Control Activity - Upon completion of works
2cb2e228-035a-51a6-9f3d-71533c27451d | note | Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
b2ea4278-9472-5750-810b-fe4512eb6801 | note | Verifying Document - As built survey record completed
46e2e1dc-e187-5bd2-a9dd-c67642a0f836 | note | Frequency - Post construction
117bb36a-2228-5f2d-9873-7001ed60132d | note | Inspection Type - Review
d16ce079-e4e3-59a8-84b7-0c9d9d34d516 | note | Inspection: Key - R
e0ea706e-673f-572c-9939-1919723f48f2 | note | Inspection: By - SV
| checkpoint | 5.3 - Red-line As-built Drawings
7a4d8ff8-3803-5877-9fe2-4dbce0a175fb | note | Inspection Point: Quality Control Activity - Upon completion of works
ee8d7743-ffda-5ff5-bced-3c947ffa7b56 | note | Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in CAD or Similar
7d513763-643c-5d76-ad64-c2088cb9ff90 | note | Verifying Document - Signed As-built Drawings
2a84d852-feb6-5e69-ad70-fcab460a1b9a | note | Frequency - Post construction
fbcc93da-9ab6-5012-863b-245f943581ee | note | Inspection Type - Review
2f5366ae-f540-52a0-82f9-816123c14c72 | note | Inspection: Key - R
09f05103-0b9d-5108-bd1e-533716a190fd | note | Inspection: By - SE,SV
| checkpoint | 5.4 - Defect, Snag and Punch List
33a6fd95-6480-5d2f-b94d-929d99737d9b | note | Inspection Point: Quality Control Activity - Upon completion of works
1e5416b1-ed81-5ccb-beac-3c6d91540f85 | note | Acceptance Criteria - Update the project Defect, Snag and Punch List Register
8d234370-b771-5b67-ad27-4ab6b79584f9 | note | Verifying Document - Register
9b601ec5-edde-5b04-89b9-78ce9dc1f186 | note | Frequency - Post construction
d5b15d48-6c01-5012-b718-7122053a4c07 | note | Inspection Type - Review
db0638e5-0ed0-5833-9024-f5875e7d4ea6 | note | Inspection: Key - R
2ed18982-cc74-556c-840b-6d8229a577c8 | note | Inspection: By - PE
| checkpoint | 5.5 - All QA documentation collated and signed-off
dc8f9ebe-b025-533f-a3dd-a9e3489ebe93 | note | Inspection Point: Quality Control Activity - Upon completion of works
acfaa74e-3226-58cb-af74-d3d1adfa9c22 | note | Acceptance Criteria - All signed and closed out
308c3525-1294-56c3-830b-3713033938e3 | note | Verifying Document - Signed off Documents
ee128cf5-cc69-5ffa-8c13-059255c7dfa6 | note | Frequency - Post construction
4347fcf8-7780-53d6-bfaf-dc69f8aed3a0 | note | Inspection Type - Review
6480a4cb-f302-5820-b43f-7bda3c9e5fb3 | note | Inspection: Key - R
9d7fd662-e58f-5cb2-b0f5-7a9bb0fedf0e | note | Inspection: By - QM