## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
868c294b-fbf3-4af3-998b-f6aab090fcc6 | checklist | ITP-001 - Clearing & Grubbing | itp | ITP-001 - Clearing & Grubbing
ec7f923a-5cf4-421d-83f7-bd17478d95d4 | section | 1 - Preliminary Works
9f7d4d15-85ed-443b-9cda-3ca2ba760237 | checkpoint | 1.1 - Check current drawings are used on site for works
37461fec-1f61-5826-b4fa-e03b688afbab | note | FREQUENCY: Prior to commencing any activity
e0adb788-32a9-5f97-af08-de07112bd1c8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b4d043e1-c0ed-5322-8318-142076aec18e | note | – using the correct and complete set of drawings
7e283d76-4e32-56f5-9808-39e2f60078bb | note | – all drawings are the latest revision
72e47ca7-f4fa-5d8b-9b34-00c9c0b197a5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
afe145f7-ba58-53c5-8fbb-54e66c2a5bc2 | note | INSPECTION/TEST METHOD: Visual inspection
09d6faaf-067c-5fff-810d-65cc24042965 | note | RECORD OF CONFORMITY: This ITP signed
0057b7f2-e660-5184-bf89-ee4f69da48c4 | note | HP*
db4f5a2c-f75c-5c97-9ed6-8cee711c97b2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
939177f6-18b0-55bf-8014-66b8c5815b4d | date | Date Completed:
bc083039-3283-4bfb-b6ec-399d9c718a44 | checkpoint | 1.2 - Implementation of all measures and controls
441a576f-bcdf-53a4-85b9-bfb2f17dd0c3 | note | FREQUENCY: Prior to commencing any activity
f263a616-2ec7-5a3b-91aa-0013707f0527 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
2ca07ec9-5047-5651-9eee-543b6394e657 | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
e4dfd1ba-3681-5773-bf0e-d9ee80e58026 | note | INSPECTION/TEST METHOD: Visual Inspection
f959abce-1b6d-580b-bf3c-086113bbef80 | note | RECORD OF CONFORMITY: This ITP signed
1357b53e-0632-5ce1-8020-8c96c76c6279 | note | HP*
dab1fccb-e385-57d3-b267-4bf0b392ebea | note | RESPONSIBILITY: Site Engineer / Site Foreman
c46d1a53-705a-54d6-bd83-317849330071 | date | Date Completed:
c4426609-f76d-401a-844c-3db010c9d193 | checkpoint | 1.3 - Excavation Permit issued
270002fd-430f-5db2-9798-6bda36b58fc4 | note | FREQUENCY: Prior to Commencing
59e613d4-4d9b-5333-ba29-b5becc77aadf | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
3a33bc41-544a-5b0b-945c-af50bf3f12ac | note | REFERENCE DOCUMENTS: Excavation Permit
eb926676-841e-5887-8e09-ebcdfee9d865 | note | INSPECTION/TEST METHOD: Document review
36ceb204-46f2-5b6e-bc18-9ccc61c1a491 | note | RECORD OF CONFORMITY: Excavation Permit #
e41ec7b6-8218-5c76-aea4-2ccfc07045e9 | note | IP
7ad51e22-14d4-5cd2-9c54-9eb41f8a9822 | note | RESPONSIBILITY: Site Engineer
c34cba54-35c2-50fe-99e5-59588ac0a247 | date | Date Completed:
10430b79-fd51-4d89-9f01-9afed8fe8316 | checkpoint | 1.4 - Flora & Fauna
e4b0cb6d-85c2-5c67-b935-4548297b37f3 | note | FREQUENCY: Prior to commencing clearing
d0de6014-8802-5296-b3fb-006b59bd4320 | note | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
f792945f-5d18-54ed-b50e-7c17f7b1757f | note | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
2e9d16c5-3497-52f6-9313-299bdbc8fa13 | note | INSPECTION/TEST METHOD: Visual Inspection
eb06030d-6c97-55ee-b278-c98357a57a49 | note | RECORD OF CONFORMITY: This ITP Signed off
c6ad0c26-a1a9-5f7e-b14f-fad553d21aed | note | IP
dccbcb61-0bd3-51ca-b3c2-2ff33841904e | note | RESPONSIBILITY: Site Engineer / Site Foreman
2803c394-e05d-523e-9a1a-ef1ed3feb6c8 | date | Date Completed:
94cfad79-9234-448e-b1cb-dc2a9ff12a3a | checkpoint | 1.5 - Permit to distrurb flora & fauna
f1a83266-633c-53fa-80e9-2e007105eaec | note | FREQUENCY: Prior to commencing clearing
5143eb8b-4a7c-5a90-96df-e79ef1178fae | note | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
25ba204b-b7ad-5a2b-821f-2d65a7582422 | note | REFERENCE DOCUMENTS: Condition Plans endorsement
d784cf23-e7ed-591f-bbae-a4534456d35f | note | INSPECTION/TEST METHOD: Visual Inspection
86b8c026-b959-5f11-b775-361f7eb127a2 | note | RECORD OF CONFORMITY: This ITP Signed off
049dacca-77d5-57c5-a965-152ba557d65f | note | IP
9b4e5ff5-1530-53a9-88c8-1be69e9b4f9f | note | RESPONSIBILITY: Project Engineer
0ab1cbf6-9906-51b6-9cd7-685dee6c0598 | date | Date Completed:
05bd63ee-3883-47d0-9fa3-10fb43063aea | section | 2 - Clear & Grub
48499691-6437-4a50-a643-ab9349ce5c72 | checkpoint | 2.1 - Define work area
9afa3173-ada7-5334-9fb8-408681f18742 | note | FREQUENCY: Prior to commencing clearing
41da9b0a-e99f-5c4c-b7a5-500fdd1ae3d6 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
a39f14c2-753a-529c-9ce2-121a7b4734f3 | note | REFERENCE DOCUMENTS: 201.1
8e52a33a-cfe8-518b-b6ce-8a3b5b6a67e2 | note | INSPECTION/TEST METHOD: Inspect
55e01d86-5d9f-588c-9db8-92f956ad161c | note | RECORD OF CONFORMITY: This ITP Signed off
a00b4a4f-93a7-558b-a211-809fa98ec22b | note | HP
123c9743-2b54-5854-809b-49ad70392f79 | note | RESPONSIBILITY: Project Engineer/ Superintendent
d46b48f5-92ba-59c3-a4c3-6f99493bed6c | date | Date Completed:
337685d6-c7e5-4b60-88f2-6df4f89d185c | signoff | AUTHORITY HOLDPOINT
2ec3fc8f-e5df-448c-9b49-2e3b1a6d53f7 | checkpoint | 2.2 - Cultural Heritage and Areas of Significance
b30b995d-dc9d-5318-a80d-84937fc53fa6 | note | FREQUENCY: Prior to commencing clearing
40a88011-39d6-57ba-af7f-93064aab254f | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
271a6835-8cd4-5012-b35e-d5b6ef526795 | note | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
c68aa31d-98f1-5767-8739-95b509fa5a3e | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
70a4dfde-7f1d-5b09-b04b-f67d663e5f50 | note | REFERENCE DOCUMENTS: CHMP
82cbbfb1-a390-5f41-ae0d-8576ab357740 | note | INSPECTION/TEST METHOD: Inspect
7911a9c5-cb11-5aeb-9dd9-e7b4fe5de561 | note | RECORD OF CONFORMITY: This ITP Signed off
333c212d-da90-584e-b3d9-d61ca788b4a7 | note | HP
cc8d5f70-7139-52ee-a8c5-83c95be22482 | note | RESPONSIBILITY: Project Engineer/ Superintendent
4802e094-c5ab-5cfb-8148-2fddeceef4fe | date | Date Completed:
79a72f54-4be9-4911-ba34-479a6b9aaca0 | signoff | AUTHORITY HOLDPOINT
a5673571-6518-42dc-8448-8e5d222bcfad | checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
b7c2fe81-0dbf-55ad-84e4-65db3708030f | note | FREQUENCY: Prior to commencing clearing
986edc45-ca33-541e-be83-cbdc3a289de1 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
546dbb7a-9c0c-5ee1-8685-04226da49a14 | note | REFERENCE DOCUMENTS: Drawings, CEMP Tree Management Plan 176.I1
d0df637d-18d5-57f9-a1ab-35f31029a536 | note | INSPECTION/TEST METHOD: Visual Inspection
6c380d13-a980-5d0b-baf5-f12b9ff494b0 | note | RECORD OF CONFORMITY: This ITP Signed off
446a9b14-03e3-5fb5-9ba8-cbe3fef5915b | note | HP
fe17d19b-f7de-5bd2-9f05-de9eb8f97c56 | note | RESPONSIBILITY: Project Engineer/ Superintendent
222c4512-2279-55a0-bed5-b0192d90edf0 | date | Date Completed:
f765ee28-f4f6-4e56-aac9-8a2faec11b2a | signoff | AUTHORITY HOLDPOINT
98caa776-6a27-4aab-b22c-0f392b0b5dec | checkpoint | 2.4 - Felling of Trees
2fbca00a-b580-5dcf-8534-4a36c026b233 | note | FREQUENCY: Prior to commencing clearing
1c1ed8d1-8776-565f-9fee-af40a2f683e6 | note | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
7778cb80-5184-5574-95ea-2285960a803e | note | REFERENCE DOCUMENTS: 201.04
875d43bb-1464-56ef-b3e3-1ad51db09926 | note | INSPECTION/TEST METHOD: Visual Inspection
d8d190b9-497c-58a6-82ec-75d513a60da4 | note | RECORD OF CONFORMITY: This ITP Signed off
a67796ff-e0cb-5a99-981c-4cc2959d59a9 | note | IP
0df41d18-be7a-563b-a415-586999ce9121 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3e3992d4-66c6-507c-992d-300a0013efad | date | Date Completed:
8b906c2b-9900-4de6-bd84-e1a0d340d81e | checkpoint | 2.5 - Backfill holes
0e221d54-d2e7-54cf-8628-2c45b6a5a48e | note | FREQUENCY: After clearing
021c8834-8322-5eea-94e6-544b1fb6b8cd | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
76a59ac1-3b19-5d38-a00a-9c6fbf92d021 | note | REFERENCE DOCUMENTS: 201.05
26e94fe5-2869-54d1-b463-2bbce2767624 | note | INSPECTION/TEST METHOD: Visual Inspection
73cbc76e-be07-59ab-abe1-11fd9bd76188 | note | RECORD OF CONFORMITY: This ITP Signed off
a2270088-4fe6-5675-9298-b076f922fb9d | note | IP
287eb28f-5bca-5e40-9865-7a8da8752fdc | note | RESPONSIBILITY: Site Engineer / Site Foreman
afd176cd-3568-573a-be9e-1f8e91a09ce8 | date | Date Completed:
19f42b79-a87b-4bd7-814b-00ceee4d65af | checkpoint | 2.6 - Dispose of Trees and vegetation
da2494a1-67b9-5d64-bd0e-b53c312365b6 | note | FREQUENCY: After clearing
e99c61b1-e597-5745-bf5d-b0e2778e1c35 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
2824c735-62d1-564d-8c41-1a5d655f8d61 | note | ○ Noxious weeds shall not be mulched.
cac06cd7-d274-564e-b8cd-d15a42682a7a | note | REFERENCE DOCUMENTS: 201.07
19abc7e8-ee35-5510-b92f-ceac3189f8a4 | note | INSPECTION/TEST METHOD: Visual Inspection
1533688d-8d49-54da-a1c2-a64a9936d776 | note | RECORD OF CONFORMITY: This ITP Signed off
78106104-c072-5fa9-ba4c-393c0db8829b | note | IP
cb5e17e4-0140-5a2d-b7f9-f3bd8eeff965 | note | RESPONSIBILITY: Site Engineer / Site Foreman
12492828-1ae6-5145-8c46-d95775249721 | date | Date Completed:
eb04126d-d27a-4e60-a801-c91de60ca74a | checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
029b2e50-38f5-508a-b000-0d19e5ae0bb8 | note | FREQUENCY: After clearing
fb272192-1e2d-5b5a-bc1b-59e1e36b86b7 | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
ba4cec91-77d5-5c3d-8660-953f5ced47fb | note | REFERENCE DOCUMENTS: 201.07
456b6c13-6f94-5dc0-abf3-c7734c1eb5c1 | note | INSPECTION/TEST METHOD: Visual Inspection
06d4c906-3cdb-5dc1-a0d6-c955f5e3f0bb | note | RECORD OF CONFORMITY: This ITP Signed off
de7d993c-70cd-5345-90cd-e2e5206daba2 | note | IP
3b97770a-ca24-526d-8a86-b34cfe95cb9d | note | RESPONSIBILITY: Site Engineer / Site Foreman
ce2382ca-a171-5fbb-8e6a-423268deee45 | date | Date Completed:
8a0b0c03-1b1e-453d-a6f4-61d5f7467d82 | checkpoint | 2.8 - Stripping of topsoil
e6fd97c9-d463-5cfe-8c0a-5f02830e0faf | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
5c973e3d-1bdd-5b44-a3c5-d5fbcb52198a | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
654cbed4-aeca-5dc2-b6b4-595bf4a9eecb | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
e820ca81-2cab-543d-95d6-79cb26e03300 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
8811d8cd-00a6-55f4-a75d-f234401ff74f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
02035d91-81b2-554b-8673-fddabcf35ab7 | note | INSPECTION/TEST METHOD: Visual Inspection
510bc2a2-548e-5424-9b38-18ea74a595ab | note | RECORD OF CONFORMITY: This ITP Signed off
e332cc32-58a2-55bd-ab89-199b200a90a2 | note | IP
fe52d679-963b-5e87-8cab-6fe87c40ecd8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0fabe42d-6e1c-5a1b-8287-24c8979fb078 | date | Date Completed:
1ea835a3-2594-4fdd-86e1-5ef841782fb4 | checkpoint | 2.9 - Removal of abandoned services
f1a2bf6b-dd39-5afd-963e-cc74355f1f9c | note | FREQUENCY: Prior to commencing works
11b15a02-cbae-551a-8a34-9704a7bccc4f | note | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
3a4120eb-e1e6-5f7a-97ea-9baa86f2bc35 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
4183272a-daca-5a3d-8c6a-1fdc91162df0 | note | INSPECTION/TEST METHOD: Visual Inspection
fbe9565e-8c34-5b08-815f-bef5e711cb14 | note | RECORD OF CONFORMITY: This ITP Signed off
060302a4-3337-59cf-9aa3-cd21d3039826 | note | IP
d80b0194-bf05-5c23-b9b3-9167cd2dd29c | note | RESPONSIBILITY: Site Engineer / Site Foreman
f587fc6b-bf81-5749-8b29-cc74988a0c27 | date | Date Completed:
6ed336fc-1050-4ccc-9782-f999bb6d335e | checkpoint | 2.10 - Clearing of Trees and Vegetation
8cb07e0b-22f6-5f48-b2f7-0b36ea6510c9 | note | FREQUENCY: During clearin works
d1901e12-c35b-5e6c-b70a-d304bae3dae4 | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
b29ce6e1-98ae-5855-b990-ee63e1e405b0 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
0e985b5f-03ea-58b5-948c-34bb91f4ec22 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
f98fa520-ae06-572d-af50-d3ddb5f5294a | note | INSPECTION/TEST METHOD: Visual Inspection
adafff00-2644-5a51-b8f7-8b9f4b98d75f | note | RECORD OF CONFORMITY: This ITP Signed off
fb43626a-bfa3-55bb-8718-313c30241228 | note | IP
9a892baf-4962-50ca-97a1-7cc060ce1850 | note | RESPONSIBILITY: Site Engineer / Site Foreman
35cacc88-8a65-5e6f-86d2-62afc2a9e39b | date | Date Completed:
5eb35407-b5c8-4940-b324-a09227163dbe | checkpoint | 2.11 - Grubbing of vegetation
3c102ec6-7480-57ba-aa2e-9c7ddfe20202 | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
65f8b9c6-c0d9-5342-a290-c9cca2b40510 | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
cc693e16-f09c-5c73-9c26-46317c9e6b5d | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
ec979db5-0ac3-50d7-96f8-8c2788201e75 | note | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
8a3cbe2c-7a06-598c-8c1e-ce1acbc31a82 | note | INSPECTION/TEST METHOD: Visual Inspection
fa8b07c8-f5ca-5cac-a647-1c5ac39e4d09 | note | RECORD OF CONFORMITY: This ITP Signed off
e0debd67-faaf-57ae-9efe-a8459b6f8ed4 | note | IP
b1fea219-1530-5efd-827e-5b98ec72b7f3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
bc9439cd-c1d7-5f79-b89c-8764d6e7e541 | date | Date Completed:
05864c11-03a1-4e24-b63f-552c3246c46d | checkpoint | Final Inspection
f7444ee1-26f8-508d-a042-11bc3991358d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9de37f75-dd58-59ef-adbc-0e6a66d3d884 | textbox | Print Name:
df32701b-d705-5f11-89a9-ae33a1ac9121 | textbox | Position:
4d66ca06-9650-5eac-b955-6c77167a8e84 | date | Date:
013fac42-003f-42c9-bd08-4879c860472d | signoff | Sign ITP
399125df-d015-4052-8deb-e371961edb51 | checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp | ITP-002 - Construction of Underground Stormwater Drainage
73fc7746-d6b7-42fc-9d5b-faa711fb1a83 | section | 1 - Preliminary Works
4439aca7-78d0-4178-95f5-f92515c75bdc | checkpoint | 1.1 - Check for correct documentation
39ca293c-6b20-5017-889e-6754e552a7ee | note | FREQUENCY: Prior to commencing any activity
00b6dde3-bc18-53cf-b07c-83cc5f5a408b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
02da829c-09f8-55ab-9e5b-9cc6ab0ec626 | note | – using the correct and complete set of drawings
4d84c657-2d37-5b69-91f4-3c78be1e0b6d | note | – all drawings are the latest revision
ea5369d7-ad79-5ac8-8305-8a8797c20384 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5817dbde-875b-5489-aeca-33d142a2a49f | note | INSPECTION/TEST METHOD: Visual inspection
95d9af25-e7bc-53c6-91c6-7720619f09bf | note | RECORD OF CONFORMITY: This ITP signed off
daf10196-3e07-5847-bd02-6ad11cc2de2d | note | HP*
7d5d25c2-3dc4-51f7-afe3-368a7ca857c7 | note | RESPONSIBILITY: Project Engineer / Site Foreman
20096430-48ea-5aa1-8bc0-f3a12ea91bac | date | Date Completed:
42c4767a-0ffb-4758-8c91-e85f7ead3c98 | checkpoint | 1.2 - Implementation of all measures and controls
c56907d4-af19-50ec-ae00-f2bbd7eb3587 | note | FREQUENCY: Prior to commencing any activity
67604119-aae3-5a3b-a3bd-b7b81df65102 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
1de166c8-70fe-5d0e-a46b-1dd5b0a77e0c | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
107ba223-7857-577e-9fd8-2690611968d9 | note | INSPECTION/TEST METHOD: Visual Inspection
8af56341-c559-5a86-a1d9-c96858bd5e85 | note | RECORD OF CONFORMITY: This ITP signed off
8780657c-aaef-534d-b5d6-7d0594522d3f | note | HP*
60fafc45-ca54-5751-a360-1f048c34a1a3 | note | RESPONSIBILITY: Project Engineer / Site Foreman
0e416e02-8aa2-568f-a7e6-667189a9a632 | date | Date Completed:
b960b3f1-c5fe-41a7-92e1-92fd812d304a | checkpoint | 1.3 - Precast Materials Inspection
f8c1a2ad-93b0-5688-9419-4fc8aaaa61da | note | FREQUENCY: Each Delivery
f40201b5-1b95-5fb5-84ae-e6cb0602c83d | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
ef34791b-1001-58bc-95a7-1ef26aa02828 | note | REFERENCE DOCUMENTS: 701.04b
1855989c-4d66-572e-859f-8b44b530fc70 | note | INSPECTION/TEST METHOD: Visual Inspection
01fc0980-1805-501f-b03f-c000347c67f5 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
a1201b53-4c28-5f22-9cb2-f16a69a731ce | note | IP
c3b1402e-c1ae-55ce-8b94-e1cdef6ee449 | note | RESPONSIBILITY: Project Engineer
0800dc57-5cd4-54fb-b467-3ef5cfe3ca0b | date | Date Completed:
46c98a9e-5cf8-4f84-89a4-f93df03cc96d | checkpoint | 1.4 - Precast Pipe Compliance
1d9c327a-46b5-52bc-a9eb-28bcdd3bfe98 | note | FREQUENCY: Prior to Commencing
0e9ce6eb-2284-5a1b-af14-866316e39707 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
389aacad-5cc5-5711-928d-b6fbf24eae01 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
90ace4d4-b8a8-5952-a8c3-50f82687d5b2 | note | REFERENCE DOCUMENTS: VicRoads Spec.
10ae82c0-91f0-54b7-97f7-d663af1169f8 | note | ○ Cl.619
e53155f3-e9b3-526e-8fb6-8d032009746f | note | ○ Cl. 701.04(a)
5ad6d5df-5ed0-536f-891a-c544c0a70efa | note | ○ Cl. 701.04(b)(i)
a039e119-a02a-5678-be7a-83e7f607fc2e | note | ○ Cl. 705.04(d)
dd727981-67e0-55ea-be15-ef772c936dac | note | ○ Cl. 705.11
3e4bb8d1-c4d0-5bba-ab21-3945f18d2d5a | note | ○ AS4058
7552245d-c9f0-5e70-92dd-99c9ff49f97a | note | ○ AS4680
89fac7bd-c37d-53ea-a71a-70882e26d501 | note | INSPECTION/TEST METHOD: Document review & Site inspection
af96b4f0-30a1-50fa-9122-4e5cfc2335d7 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
3aabfdc9-401d-5df2-96fd-1d99d5d8456b | note | IP
90d00731-2f31-5b95-a657-45e8edb2dbef | note | RESPONSIBILITY: Project Engineer
cf269d02-b93a-55ad-9295-1564cead80e8 | date | Date Completed:
4000e764-dcec-49a8-a42f-4bd9467b1d66 | checkpoint | 1.5 - Bedding material classification
29abe766-f849-5925-a810-941525006bcf | note | FREQUENCY: Prior to start
3ca5acbe-3aa0-5ee7-b6be-c43b26d310c4 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
39d5efa9-9945-54e4-8891-5fc5337b1e63 | note | ○ 100% passing 19mm sieve.
5d291ee3-d14e-524f-b10e-ff26b7b21764 | note | ○ 5%-40% passing 0.075mm.
2e2923dc-d29c-51f9-8a77-9aff6bd0ba51 | note | ○ PI = 20 max.
96ce9c96-eb83-5985-af69-382adef26407 | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
69ccc8d0-56d5-5fe2-891f-d59b1c4c729b | note | INSPECTION/TEST METHOD: Verify
3db49b43-5330-590c-a2b3-ac01e0554254 | note | RECORD OF CONFORMITY: Test Reports from supplier
4b23b462-8934-5d57-87e4-8b2339c8b524 | note | TP
b102c4c4-f3ba-5ed1-ae32-fccd52455b80 | note | RESPONSIBILITY: Project Engineer
4c1504fc-2597-5609-ab5e-4ea4a923586c | date | Date Completed:
7b0594c9-e9b3-4bb1-84f4-8eccf4e0bd8f | checkpoint | 1.6 - Backfill material Classification
474e650a-54f1-578e-aeff-8dc693c9713a | note | FREQUENCY: Prior to start
dd9cddd3-adbd-59f7-a63c-816874ad2167 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
7501c6d9-6fcb-58ad-982f-02583b4a3fb2 | note | ○ 100% passing 37.5mm sieve.
cbb51649-67ea-56b2-bcfa-d911e53f1946 | note | ○ 5%-40% passing 0.075mm sieve.
63a188d7-7cc8-5f37-9b64-2d004859b56a | note | ○ PI = 20 max.
df71779f-a586-52f5-bbff-90162440c848 | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
127e5373-c686-5ab9-a8f3-ea73f7d0bfe8 | note | INSPECTION/TEST METHOD: Verify
dca10fe8-9d8e-5284-991e-8576659d6271 | note | RECORD OF CONFORMITY: Test Reports from supplier
4fb3afe7-27e8-5371-acda-6439f2710126 | note | TP
11072640-4ad3-572f-b421-343b88e7ac85 | note | RESPONSIBILITY: Project Engineer
b359639e-5cfb-5874-a21b-00e8f555fd07 | date | Date Completed:
af71c84d-3c9b-4c50-986e-3d61e8736a67 | checkpoint | 1.7 - Mortar material classification
0080fc2e-e9d4-5086-bf7a-40975ef49003 | note | FREQUENCY: Prior to start
6d65f12f-9264-59d6-b85b-99076c7568c2 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
2796c4b7-c4df-5732-ae97-83e1fad1c17d | note | REFERENCE DOCUMENTS: 610.33
23e2e510-8e8b-5047-96b5-3c9138aab903 | note | INSPECTION/TEST METHOD: Verify
a318cedc-dd21-5788-af3f-44767f8431ba | note | RECORD OF CONFORMITY: Test Reports from supplier
a5ad7d75-75f3-5a5b-a0b3-fbfceac730c8 | note | TP
df9211b3-e817-5817-8786-cb7b0ea8e645 | note | RESPONSIBILITY: Project Engineer
ffd45379-595c-56a1-955f-784af9a1862b | date | Date Completed:
23705d2f-4f0d-4fe2-94b7-ae084e1d5f85 | section | 2 - Construction Works
7b234848-bba3-4026-a8d9-047b3202c018 | checkpoint | 2.1 - Excavation Permit
3599b363-e74b-5fe5-9e03-3e6c0e4c8ab7 | note | FREQUENCY: Each lot
8e6ee257-a184-5148-8e7b-e57ff0a1aef5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
f5dab8ea-dc43-59f2-be15-7f2ddf0fae0d | note | ○ Plant and equipment shall be appropriate for the task.
76891574-45fa-56bd-9d4c-898354e3c280 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
2103358a-920f-5043-97aa-2de11eeadfeb | note | REFERENCE DOCUMENTS: Excavation permit
92a9a309-a426-579d-ac3c-f7b83a4714d2 | note | INSPECTION/TEST METHOD: Verify
bd18cc3a-388c-5a79-a8fa-deee3dfec912 | note | RECORD OF CONFORMITY: ITP Signed
fd6dde4a-08e2-55e9-9f2a-0680f87f97b3 | note | HP*
f12c3de8-0145-5ebd-89e3-10a6012988bc | note | RESPONSIBILITY: Project Engineer
97da9f30-aa33-5680-b268-ff2189a318a4 | date | Date Completed:
e7950efb-cc69-4933-921c-04e618dbd233 | checkpoint | 2.2 - Set out drainage
6677b1e9-4e36-5dda-9ff3-d4156bd1e2cb | note | FREQUENCY: Prior to excavation
9f4ba273-8c64-524c-9aad-6f019ec38d77 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
8222efc5-f0fc-5a2e-a37a-b9b5c816ab2b | note | REFERENCE DOCUMENTS: Drawings 701.10
b0fcafc0-2b47-5284-8eae-87705872ebea | note | INSPECTION/TEST METHOD: Visual Inspection
d855a7a3-15fa-5691-a07e-83a9fbb8800c | note | RECORD OF CONFORMITY: ITP Signed
44a5edb8-8679-5d9b-8693-279ff06035b2 | note | HP
20c3f893-70b4-5d65-a628-7992b89b3a5a | note | RESPONSIBILITY: Engineer / Forman & Superintendent
a89b91f2-400e-5bcc-9b81-8a908e265054 | date | Date Completed:
52b6d1a9-4ff9-4928-ae5f-a68575a19b6f | signoff | AUTHORITY HOLDPOINT
a2f1b847-9315-4455-a892-b40ebcc31cae | checkpoint | 2.3 - Excavation (pipes)
d8c901a6-f991-5599-92a2-fc6a10dee30e | note | FREQUENCY: Each Trench
0a8fca57-a93f-5a86-9b86-d3ed3d3171ea | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
14b3e5b0-a7b4-5c26-98ca-18baf9767213 | note | Depth of trench:
dc7914f0-58ec-5488-b1dd-1ec29a3147a1 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
be442c1a-26cb-5c4d-96d2-38fb1200fd8c | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
06e991e7-c420-55e2-9446-ac6cdab28d64 | note | REFERENCE DOCUMENTS: 701.15 Table 701.151
7ae4b5a2-51b5-54b1-b83e-4e62ac8818c3 | note | INSPECTION/TEST METHOD: Visual Inspection
1ca7861b-52f2-5211-b016-958dd30d80bf | note | RECORD OF CONFORMITY: ITP Signed
967d6a64-a75e-563e-949d-bf135d3a0db1 | note | IP
d6290938-ee1d-5afe-8532-84f6b69bb14e | note | RESPONSIBILITY: Site Foreman
0c631666-5f21-5c9e-b91d-8007a3b627a7 | date | Date Completed:
b6c45271-70f3-4d68-a9ff-c83e2935d719 | checkpoint | 2.4 - Compact base of trench
afcfb756-50da-5894-ae49-588be93f8a6c | note | FREQUENCY: Each Trench
e86a5ecb-f165-5dae-b692-7c7e0d5aa108 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
5952e247-80fa-5bab-8585-5f023085dc55 | note | REFERENCE DOCUMENTS: 701.1
c33a95bf-6b43-565b-9f93-36707a6c34c9 | note | INSPECTION/TEST METHOD: Visual Inspection
95b753d3-0a01-5f25-a4ed-0836b17d2828 | note | RECORD OF CONFORMITY: ITP Signed
8ad68588-9ed1-5924-a118-36adfcfb0357 | note | IP
1a23a4e8-816d-5bcd-adf8-ae187197eb3e | note | RESPONSIBILITY: Project Engineer
45986b3d-55b3-58e7-9d54-ed33157a5851 | date | Date Completed:
d679292f-867c-46ef-be58-f418a89184e4 | checkpoint | 2.5 - Place bedding material & compact
9765ff07-9aa0-5ed9-833a-9d80c26d089a | note | FREQUENCY: Each Trench
df2ff3c4-5d18-5947-8f9a-68c05dc518e2 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
045ed82d-9b25-57b6-892b-2f5a7bd739e7 | note | ○ 100mm under pipes.
b275f6a5-a638-5311-a28b-f4e7087abe29 | note | ○ 80mm (earth foundation)
faa98468-7f08-5153-8d6f-d92a9e977587 | note | ○ 150mm (rock foundation)
6746bc27-9cab-5675-85d0-0d8aae9f02df | note | REFERENCE DOCUMENTS: 701.19
149a889e-8beb-5292-bebc-15f17de25a57 | note | INSPECTION/TEST METHOD: Visual Inspection
5f55669e-f427-55d9-b83a-b42d9a0c3dc5 | note | RECORD OF CONFORMITY: ITP Signed
f218a414-a415-576d-b2f0-a46eed8a6531 | note | IP
6d39803a-dd20-5e5c-938b-94f7e3e0cae5 | note | RESPONSIBILITY: Project Engineer
8eef0660-1f69-5eb0-a67b-5d8bf231166d | date | Date Completed:
fc137e4a-dafb-4733-a691-1838802c27c5 | checkpoint | 2.6 - Place pipes
be4d6734-f29e-5d70-90d4-96b8d03c996e | note | FREQUENCY: Each Line/Pit
8a0c58bc-46bb-536a-9cec-e803b9168795 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
188079ca-6f43-59c3-83c1-5252ed582b37 | note | REFERENCE DOCUMENTS: Drawings 701.17
30110b06-af03-54b3-98d7-779d1a8fc883 | note | INSPECTION/TEST METHOD: Visual Inspection
f6c1369b-8171-50f6-9a44-f7d52c8058dc | note | RECORD OF CONFORMITY: ITP Signed
4f78cb64-f27f-569f-974d-a11ba68a5716 | note | IP
fb0379df-cf31-5ef7-9ebb-1e1d44979022 | note | RESPONSIBILITY: Project Engineer / Site Foreman
cce38b8f-7c4c-5dd4-93b1-a5565a657d10 | date | Date Completed:
8b6c8be0-bcd1-4eb5-aada-2af8f39370e2 | checkpoint | 2.7 - Jointing pipe sections
a26eb157-d324-5166-95fd-406c87bc03ce | note | FREQUENCY: Each Line
b2f097cc-6993-5728-8e2d-ef0f2c232ae5 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
38bbac96-d3b1-5337-b07b-df24c1bce702 | note | REFERENCE DOCUMENTS: 701.18
62cf8aa9-8fc5-57ce-8d8b-e3cd3090c2e0 | note | INSPECTION/TEST METHOD: Visual Inspection
71e099e9-5058-5033-bc55-4c4ea0775df9 | note | RECORD OF CONFORMITY: ITP Signed
ec715e00-c930-5b5d-a756-a8b1d63f2cc0 | note | IP
b9b89c0c-5df5-5259-a456-7e042075eb3d | note | RESPONSIBILITY: Project Engineer / Site Foreman
612c002d-30b4-5aad-9f40-3139765f7adc | date | Date Completed:
e914785c-0740-455e-a4af-c5d3d15d63d2 | checkpoint | 2.8 - Place & compact backfill material over pipes
2a427f6d-90ff-5635-8577-8ceaa731dce7 | note | FREQUENCY: Each lot
21117db4-6847-5c13-a01c-a2d820ab28a9 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
139d657c-e813-5fe5-ab14-5e06c1b9eafc | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
9ba9b7e1-3f16-5278-8f09-02bdc932e9d2 | note | ○ Loose layer thickness <= 150mm.
2261bfbd-fbc1-5aac-a66e-44921b7412ff | note | ○ 1 lot = 150mm layer
5d8219a7-3ee9-5abf-9c44-5727f2185d78 | note | REFERENCE DOCUMENTS: 701.14, 701.15
2141af66-c6c7-5ad8-8838-47a1139bdd98 | note | INSPECTION/TEST METHOD: Visual Inspection
1072f884-7ff8-5c7e-8406-ee771c7c7ee4 | note | RECORD OF CONFORMITY: ITP Signed
1fe283bd-2c1a-5d5d-adf7-644f3543531f | note | IP
7af73d79-4758-50e1-93b3-8a2d3a56711e | note | RESPONSIBILITY: Site Engineer / Site Foreman
0f7df837-941c-50d4-9f88-05cda97d5f1f | date | Date Completed:
12688c52-5b9d-4d0b-a46c-3448e8a44927 | checkpoint | 2.9 - Repairs to damaged pipes
b1e14120-63ef-5570-ab36-0af557d35921 | note | FREQUENCY: Each damaged pipe
c69e3263-298b-509b-86da-479aac12fc60 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
e446ce22-802c-54fa-9352-e672ba328363 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
90bd7024-2db2-5a6b-84e4-31b530d79d65 | note | REFERENCE DOCUMENTS: 701.31
586964b5-c63f-54cf-8203-91f5bce8c91a | note | INSPECTION/TEST METHOD: Verify
01474c49-9757-573d-a860-06d2a9c5eaa1 | note | RECORD OF CONFORMITY: ITP Signed
9b7ae0ef-ba62-5f19-8764-c58c831da129 | note | HP
90936032-6ece-5d85-ad17-6f7ec0e65543 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
ee06228f-7302-58a4-859c-4a59c7b9816f | date | Date Completed:
b81d6aed-8610-495f-9b0b-28bcd4db7f72 | signoff | AUTHORITY HOLDPOINT
635fdd8a-c251-4bf8-92fe-b62c8fba5020 | section | 3 - Testing & Completion
12e9a753-ffdd-41eb-a00b-b45fe00653ab | checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
de469d03-7fa6-5a30-b375-27a60541d099 | note | FREQUENCY: as required/requested
9f6285c4-29fd-53a2-b974-6d04ef9d7452 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
edc6ac4b-a839-56b7-b53a-f9ee0e540c0d | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
7dfc907f-0658-5556-b89b-82aca20999d7 | note | REFERENCE DOCUMENTS: 701.2
0946150b-dad2-5f7a-aef5-5b3f31a9f167 | note | INSPECTION/TEST METHOD: Verify
7018b52b-51c0-5f92-9b55-cbeffcf33f75 | note | RECORD OF CONFORMITY: Test Reports
1cdb5dcf-9fe8-53f2-b7f6-2ed38b6fa50c | note | TP
c25a7392-4bb4-51c9-81ed-14d798871225 | note | RESPONSIBILITY: Project Engineer
2120a27d-7f86-59b0-9ba8-0d0d708fb0ce | date | Date Completed:
fad6ace6-8867-4b86-9e2f-85798b54fde3 | checkpoint | Final Inspection
4c7bebed-f119-5382-83a6-1d6b0be899ec | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
686e4c6e-ec20-5efc-97e3-9b9262827aa8 | textbox | Print Name:
5a8612ab-10c3-57ed-84d8-a529288c0c67 | textbox | Position:
16c512f3-dee9-5ccf-9388-98ecf105803c | date | Date:
63a694c2-2178-499e-9502-0e345c77546f | signoff | Sign ITP
0450a2f0-0b93-457d-80f7-14651297c331 | checklist | ITP-009 - Subsoil Drainage | itp | ITP-009 - Subsoil Drainage
2601c78b-4689-4ff1-a8b0-d63a9dfcb65b | section | 1 - Preliminary Works
932fea6d-654e-4722-877f-144df16e3c26 | checkpoint | 1.1 - Induction
28611af2-799d-5f09-837b-c1a0f6cb2895 | note | FREQUENCY: Prior to Commencing
2ec67a90-6cf7-5ad0-9e19-d5cf655a455a | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
e49894c6-d240-546d-aa12-b695256a493a | note | REFERENCE DOCUMENTS: Inductions Register
fbd82473-481e-5071-b22c-5a53f8d446f3 | note | INSPECTION/TEST METHOD: Document review
7b0fb1c0-3ecf-5a04-8f41-cb121235f7c6 | note | RECORD OF CONFORMITY: Site induction signed.
d40da650-0397-5795-afdd-346ff5d2ee63 | note | AP
827392c4-ae32-5e17-9e35-18625564bf68 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b15f0454-27b0-5b82-8ae5-cc97bdd97614 | date | Date Completed:
9a63fb25-eaaa-40f0-bf49-0f7aacc161cf | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
c2cbbdac-9377-5b8e-bfcc-169b75a7c675 | note | FREQUENCY: Prior to commencing
0a8fda2c-2961-5a8f-8d64-a9756fd3e7be | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
64ac9418-730a-5b91-b19e-4376392eefda | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
06c5fc41-0fec-5987-8e5b-43303de1d4c1 | note | INSPECTION/TEST METHOD: Document Review
db2fc120-f753-5d51-8259-20e600d7094e | note | RECORD OF CONFORMITY: SWMS(s) signed
99841848-60b7-583b-b12d-895c7e680bd7 | note | HP
b8e64f75-1373-5e88-b3f0-c56d73789487 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
203186fa-faec-59b7-8306-b5e977a35520 | date | Date Completed:
fc5cd075-4304-4df7-92e3-2e545e9967b5 | signoff | AUTHORITY HOLDPOINT
0b2cc719-0d33-4820-b6dd-bd6ce63eae99 | checkpoint | 1.3 - Check that current revision drawings are being used
9f93be1f-0b8f-5ef1-9518-88b90ebcaddb | note | FREQUENCY: Prior to Commencing
d07acba9-acd0-52a0-9595-589910c535aa | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
36a0f26f-a946-5e1f-acf7-bb302a663998 | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
117e23aa-87bd-5653-8d99-96bedb720bfa | note | INSPECTION/TEST METHOD: Document review
34c29559-fa4d-530e-ba65-afcd160d0396 | note | RECORD OF CONFORMITY: Latest Revision Drawings
676f2c95-4baa-511f-abca-3593ba097952 | note | AP
78df9ea4-e1e3-5de7-92ff-0ba761904768 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b461ae1d-64c6-57a9-8e38-f92cc36bf787 | date | Date Completed:
52c2d813-b2aa-4f34-9a18-1864d201a490 | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
c1a2dc1a-fa91-522c-b89d-e01bfb172b56 | note | FREQUENCY: Prior to Commencing
4907bad0-bbff-5032-bd78-7a2a04bc319a | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
1aa1eb07-3ab7-5815-baf7-2dce6fe5e9a6 | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
754b1bff-f1d5-513f-82cf-0b063e2fc4d1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
231c5c92-a1b5-5f9e-b0b4-55ce3ed2cd5b | note | RECORD OF CONFORMITY: Signed ITP
06c46c34-ca94-531c-afb4-0da08311308b | note | IP
846232b4-8bff-5f61-a8ab-9190160c9c77 | note | RESPONSIBILITY: Site Engineer
34b6fa49-398b-5b93-aae0-c3a76382467a | date | Date Completed:
d270551f-78b2-4991-b21c-339198e6a342 | checkpoint | 1.5 - Excavation Permit issued
a6800f17-640d-554a-a679-cd8c811f75da | note | FREQUENCY: Prior to Commencing
ccb2f0f8-0ef7-5de3-bf37-0e1ed2457da6 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
eb94312a-9755-5396-9fb6-3bcacb0d2ba1 | note | REFERENCE DOCUMENTS: Excavation Permit
bfda3e6d-dc17-53bc-b5ef-3ef0f8240d18 | note | INSPECTION/TEST METHOD: Document review
8565dfac-b801-59c0-bce3-08828f1f92ab | note | RECORD OF CONFORMITY: Excavation Permit #
ae0d588d-224b-532b-a734-e1223ebae657 | note | IP
57eebf95-4196-51f3-ab5f-71d301c91296 | note | RESPONSIBILITY: Site Engineer
14899865-719a-596d-8e0c-b6c2080bbb93 | date | Date Completed:
7a3dbb9a-6ec9-4fd1-93c6-44f076fa88c9 | checkpoint | 1.6 - Materials
7a25a0fa-35d9-54d9-9edf-c86650de02fa | note | FREQUENCY: Prior to Commencing
83ec995f-cb55-588b-8967-d8a975512e64 | note | ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2
8f652289-b10e-5f8a-a335-6ff060b679bd | note | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a)
ef171110-8097-5e33-adce-0045af7d9438 | note | INSPECTION/TEST METHOD: Document review
5c263590-5b29-510b-8207-0c1c41428d43 | note | RECORD OF CONFORMITY: Signed ITP
02d8e184-4629-54b8-afc8-9d8be17d5161 | note | IP
be475d26-fb66-54c0-99a0-75be6b009891 | note | RESPONSIBILITY: Site Engineer
e22df9e6-cdd3-5170-9861-7e9216758f60 | date | Date Completed:
2cd7eee9-ded8-4e3b-9a62-5fc0e373f46e | section | 2 - Drainage Works
f7810f7d-5b9d-4354-b8f3-120a06fd5e25 | checkpoint | 2.1 - Excavation of Trench
2e073f4b-5174-5bed-ac54-4be48c7a43af | note | FREQUENCY: When placing drainage
78e2f4ee-20dd-52d6-8f13-738dcad9209c | note | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
71e28748-76e6-54e6-8fa6-88f5beadf6cc | note | ○ Perforated Pipe Crown level to be minimum 200mm below subgrade level.
5a192871-1c18-5614-bc27-46fcad54e801 | note | ○ Grade of trench to be not flatter than 1 in 250.
fa5db38e-e8c5-5547-b099-8c908d3e3e5d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08, VicRoads Spec. Cl.702.09(a)(b)
5d7fca2a-94e4-5395-b312-6619402cb643 | note | INSPECTION/TEST METHOD: Site inspection
bef37d72-a5a2-54f8-85e0-df74bcc5f2e9 | note | RECORD OF CONFORMITY: Signed ITP
1647c6f1-52fe-5249-8d05-647e49a930a6 | note | HP
4c6bf3dc-0458-51c3-a2dd-0541a9778b00 | note | RESPONSIBILITY: Superintendent / Site Engineer
da2347ba-5649-5009-be4a-266fb39a6bfe | date | Date Completed:
8fae8ce0-e61c-4b84-abff-e034ca856908 | signoff | AUTHORITY HOLDPOINT
63976383-18cb-4fca-9721-5adc0d6255ac | checkpoint | 2.2 - Use of Geotextile
f972bf38-2b75-5678-b653-9b0abec85c47 | note | FREQUENCY: When placing drainage
b6a5f342-2096-5a35-ab4e-99699cf5e5c0 | note | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
5a0f2f56-fd3e-5347-884b-f99cd8a2fd69 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
ba25f5f1-391f-5bf6-9711-3c9d99aed813 | note | INSPECTION/TEST METHOD: Site inspection
abacb16f-2132-5cf3-a9a1-09ee023eb121 | note | RECORD OF CONFORMITY: Signed ITP
cc989b5f-9ea8-5dc1-99c0-f0c593d0e238 | note | IP
a1dd50ea-9d13-5462-9606-2968cb521270 | note | RESPONSIBILITY: Site Engineer
86999a94-04a7-5fac-bd37-36107527c44b | date | Date Completed:
838c6828-af9c-43fb-8b71-230b7f2053d3 | checkpoint | 2.3 - Installation of Subsoil Drainage
fecb07f1-e5c3-5697-a7be-7c434c09abdd | note | FREQUENCY: When placing drainage
3b8e4d50-090e-57f9-9d70-2f34c486ac43 | note | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
7e10858c-3639-507a-8e12-04065e80a795 | note | ○ Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe
a82612ce-0f52-5bff-9f70-6da212a1aa16 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
a45fa007-68aa-53f1-9aa4-9cc0208a6bd6 | note | INSPECTION/TEST METHOD: Site inspection
25d778a0-1441-54be-aab3-0ec5915760b9 | note | RECORD OF CONFORMITY: Signed ITP
2cc9314f-4f44-5cc5-85c5-d53a3e227ed2 | note | IP
70975899-643a-5326-a6a6-bf11837ea371 | note | RESPONSIBILITY: Site Engineer
71a2cd26-049e-529d-b6e0-0df86d099c49 | date | Date Completed:
aa871123-a796-4497-838d-5caf4a217f10 | checkpoint | 2.4 - Placing of Granular Filter Material
c5e8ea0b-a131-55bf-8bce-aa926954677a | note | FREQUENCY: When placing drainage
787e4c91-b7ff-57b5-bda7-fd74ba967394 | note | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
9eec40bb-1765-52a9-9fdc-7328fee28ad6 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
b4537b46-3f26-5127-bd30-240cf240e92b | note | INSPECTION/TEST METHOD: Document Review
77ff9ad9-881f-5910-8601-940cad6011b4 | note | RECORD OF CONFORMITY: Signed ITP
f7fa96e9-56ed-53fd-99e3-6ee11b7e0c52 | note | HP
e042e17b-fe63-5fd7-b49d-e924f7509615 | note | RESPONSIBILITY: Superintendent / Site Engineer
068c8fd9-8288-5525-ba38-398d3ae9e488 | date | Date Completed:
eb04fa72-0317-413d-9d37-e7a078a45be0 | signoff | AUTHORITY HOLDPOINT
529240fb-8497-49b1-b4e1-7fefbf15afc7 | checkpoint | 2.5 - Flushing Test
48793a4a-ad7e-52f7-89c6-f6af7d68e294 | note | FREQUENCY: After drainage is placed
2e65fe8d-3fa0-5e10-a160-1a675dc47257 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction
6e396358-2330-52c8-b73e-5d9dde2d0d49 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
b5fd1990-feab-5d04-ad8c-b378c620cb32 | note | INSPECTION/TEST METHOD: Site inspection
a7648f60-13bd-535a-bc98-b8081d5d8692 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
b1c99f56-875a-57e3-a345-de80577078e4 | note | WP
4c7db36c-f003-5086-9c17-084f9d4e608f | note | RESPONSIBILITY: Superintendent / Site Engineer
8ebc6321-dec6-5d2c-9f2d-bd53b8363bd4 | date | Date Completed:
8b13771e-d1b4-4ad8-b0c6-52705f3e39be | checkpoint | 2.6 - CCTV
34af399a-fb7d-51a9-adbf-f3258233412a | note | FREQUENCY: After drainage is placed
9d7f6344-2649-5f2e-b357-6c538e11e4fd | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
bd98426a-4536-5280-8109-838b29bb75a5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i)
4c2f2df5-1b3b-50e6-8678-f01ed999305d | note | INSPECTION/TEST METHOD: Site inspection
865a8322-587f-5c44-828e-8bc17b58f1e9 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
f932b4f6-9302-5dc8-b16f-21d516264d4f | note | HP
93c882ca-52c0-503e-806a-679b8705bf72 | note | RESPONSIBILITY: Superintendent / Site Engineer
f61cc75a-15f6-5f26-ab8f-9b6959e1f0ac | date | Date Completed:
ef52dcf0-77b9-4716-97c4-6b8b2c4b73ba | signoff | AUTHORITY HOLDPOINT
6943f5a8-1e8e-42e0-9f72-a8ff2d5ea6fa | checkpoint | Final Inspection
9e4e3b98-e267-5c1b-b632-639e3a3b0096 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6a5e6a56-a298-542f-9d7f-c7dabf6ab8d8 | textbox | Print Name:
bb81df78-141e-527d-b1b1-ddbf95d77a35 | textbox | Position:
c0a09d59-867b-57c3-84b8-3b32d7f8ce84 | date | Date:
df934988-f74f-427d-9905-7c2d0269eba4 | signoff | Sign ITP