## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-010
[11 empty] | Revision : 1 | 2024-11-06
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Howitt Avenue Traffic Signals |  | Insitu Pit Construction |  | Name: | Justin Barnes | Name: | Brett Walker |  | Name: | Brett Walker
Contract No: |  | DOT34605 |  | Specifications: VicRoads Standard Specification Section 705
|  |  |  | Structure / Component: Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Wy Yung |  | Date : | 2024-11-06 | Date : | 2024-11-06 |  | Date : | 2024-11-06
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Activities
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | ITP signed | HP* | Site Engineer/ Supervisor | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP | QMP, TMP, JSEA, SWMS, ITP | Visual Inspection | ITP signed | HP* | Site Engineer/ Supervisor | N/A |  | N/A
1.3 | Use of approved mix design |  | Prior to commencing any activity | Concrete mixes used will be inline with Table 705.041 - VR330/32 for drainage pits | Cl 705.04 | Verify | ITP signed | HP | Site Engineer | N/A |  | N/A
1.4 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2 | Excavation and erection of falsework/formwork
2.1 | Excavation |  | Prior to concrete pour | Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation | Cl 705.05 | Visual inspection | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
2.2 | Construction Methodology |  | Prior to erection | Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction. | Cl 703.12 | Verify | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
3 | Steel reinforcing
3.1 | Placement methodology |  | At all times | All steel reinforcement to be securely held during placing and compacting of concrete Supports shall be of a material durable to impose loads without movement of the reinforcement The placement method shall not allow the reinforcement to become contaminated by contact with other steel | Cl 703.13 | Verify | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
3.2 | Minimum Cover |  | At all times | The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed. | Cl 703.13 | Visual Inspection | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
4 | Pre-pour Planning and Inspection
4.1 | Pre-pour inspection |  | Prior to concrete pour | Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications. Hold Point released by the Superintendent. | CL 705.06 | Verify | ITP signed | HP | Site Engineer/ Superintendent |  |  | N/A
5 | Placing Concrete
5.1 | Carry out sampling of concrete |  | 0-50m3 - 1 sample | No. of Samples: 0 to 50m3 - 1 No. | Cl 703.11 | Checklist | CLB CLC | TP | Site Engineer | N/A |  | N/A
5.2 | Compressive testing |  | 0-50m3 - 1 sample | A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days. The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additioinally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days. | Cl 703.11 | Verify | Concrete test records | TP | Site Engineer | N/A |  | N/A
5.3 | Placement methodology |  | Each concrete pour | Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials Concrete shall not be freely dropped from height >2m Concrete shall not be moved horizontally by vibrators |  | Verify | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
5.4 | Compaction |  | Each concrete pour | Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs. |  | Verify | ITP signed | IP | Site Engineer/ Site Supervisor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on E17: McDowell, Peter: General comment - This is very onerous. They are just council pits 150mm thick with mesh. Most of this stuff is unrequired and can be covered with a simple prepour checklist signed off by the Superintendent. take one compressive test per pit.
Note on E27: McDowell, Peter: And gives approval to proceed with the pour
Note on E29: McDowell, Peter: One compressive test per pit