## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-003 - Earthworks Foundation | itp |  |  |  |  | ITP-003 - Earthworks Foundation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Induction Register
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.4 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.6 - Verification of Site Clearing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05 ITP-001
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Material Category
label | FREQUENCY: Prior and During Excavation
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of material in accordance with Clause 204.04
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.04, Cl.204.06(c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.8 - Placing Fill
label | FREQUENCY: Prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.9 - Rock Subgrade
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.10 - Ground Water
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.11 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.2 - Surface Preparation
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: For areas where the subgrade height is less than one metre above cut height, the cut should be scarified to 150mm and recompacted with Type B material
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Foundation Treatment (if required)
label | FREQUENCY: Prior to Treatment (if required)
label | ACCEPTANCE CRITERIA: Proposed method reviewed, refer relevant ITP
label | REFERENCE DOCUMENTS: Relevant ITP
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-006 - Subgrade Preperation | itp |  |  |  |  | ITP-006 - Subgrade Preperation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | REFERENCE DOCUMENTS: Project Spec. Cl.1190.07, Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compliance with latest IFC drawings, Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Material Category
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06(c)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent agreement, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Trimming and level conformity
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level. Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns. Water shall not pond at any point. The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Cut to Fill Zones
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(g)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing for Compaction and Material Properties
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot (one day's production), prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.03, Cl. 204.12
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Rolling Register signed.
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 3.2 - Testing for Compaction and Material Properties
label | FREQUENCY: Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks
label | ACCEPTANCE CRITERIA: Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.04, Cl. 204.13, Cl. 204.14 Table 204.131,Table 204.141
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-007 - Guardrail Installation | itp |  |  |  |  | ITP-007 - Guardrail Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Approval of Guardrail System
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | REFERENCE DOCUMENTS: RDN 06-04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP/Email
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Approvals
checkpoint | 2.1 - Approved steel supply
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(b)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved), Material Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Approved Galvanisation records
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(d)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance, Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Installation of Guardrail & Maintenance strip
checkpoint | 3.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | SCP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | REFERENCE DOCUMENTS: Services file & Current DBYD notifications
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Services marked on the ground
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Approval of location and length
label | FREQUENCY: Prior to Installation
label | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Install posts, rails and terminations
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Tolerances
label | ○ W-beam guard fence shall be erected to the following tolerances:
label | (i) Variation from true plan position of posts ±20 mm
label | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
label | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
label | (vi) Dimension of holes -0 mm, +50 mm
label | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
label | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(d)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Construct crushed rock base for maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Construct concrete maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam. Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Concrete dockets/Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
section | 4 - Testing
checkpoint | 4.1 - Compliance Audit of Barrier System Installation
label | FREQUENCY: Prior the issue of the Certificate of Practical Completion
label | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.10
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Safety barrier compliance audit, Manufacturer compliance certificate
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Completion
checkpoint | 5.1 - Delineators
label | FREQUENCY: Once installation of assets is completed
label | ACCEPTANCE CRITERIA: The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
label | ○ red delineators on the left side of one-way and two-way roadways;
label | ○ white delineators on the right side of two-way roadways; and
label | ○ yellow delineators on the right side of one-way roadways.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.11
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Site Photos/Signed ITP
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Survey data captured for As-Builts
label | FREQUENCY: Completion of Works
label | ACCEPTANCE CRITERIA: As-Built drawings to be submitted to client
label | REFERENCE DOCUMENTS: VicRoads Spec. 708
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: As-Builts, Survey reports
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-008 - Cement Treated Subbase | itp |  |  |  |  | ITP-008 - Cement Treated Subbase
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Material Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval
label | REFERENCE DOCUMENTS: Cl 812.04 Section 820.04 to 820.09, RC 500.02
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.3 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Materials
label | FREQUENCY:
label | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
label | REFERENCE DOCUMENTS: Cl 306.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.2 - Moisture Content
label | FREQUENCY:
label | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
label | REFERENCE DOCUMENTS: Cl 306.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.3 - Jointing
label | FREQUENCY:
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
label | (a) material shall be spread in such a manner as to minimise the number of joints;
label | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: Cl 306.08
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Test Rolling
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
label | REFERENCE DOCUMENTS: CL 306.09
label | INSPECTION/TEST METHOD:
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Superintendent / foreman
date | Date Completed:
checkpoint | 3.2 - Compaction
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Testing and Acceptance of Compaction
label | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
label | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula:
label | REFERENCE DOCUMENTS: CL 306.09
label | INSPECTION/TEST METHOD:
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 3.3 - Survey Conformance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
label | (a) Width and Alignment
label | – The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
label | (b) Surface Level of Subgrade and Pavement
label | – The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12.
label | ○ Surface level tolerances: Range x = +6, -12mm
label | REFERENCE DOCUMENTS: Cl 306
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Cl 306.12.
label | SCP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 3.4 - Curing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
label | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
label | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
label | ○ The subbase shall be kept in good order and condition and free from contamination.
label | REFERENCE DOCUMENTS: Cl 306.11
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP signed off;
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-010 - Insitu Pit Construction | itp |  |  |  |  | ITP-010 - Insitu Pit Construction
section | 1 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.3 - Use of approved mix design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Concrete mixes used will be inline with Table 705.041 - VR330/32 for drainage pits
label | REFERENCE DOCUMENTS: Cl 705.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Excavation and erection of falsework/formwork
checkpoint | 2.1 - Excavation
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | REFERENCE DOCUMENTS: Cl 705.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
label | REFERENCE DOCUMENTS: Cl 703.12
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 3 - Steel reinforcing
checkpoint | 3.1 - Placement methodology
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: All steel reinforcement to be securely held during placing and compacting of concrete
label | ○ Supports shall be of a material durable to impose loads without movement of the reinforcement
label | ○ The placement method shall not allow the reinforcement to become contaminated by contact with other steel
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 3.2 - Minimum Cover
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 4 - Pre-pour Planning and Inspection
checkpoint | 4.1 - Pre-pour inspection
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications.
label | ○ Hold Point released by the Superintendent.
label | REFERENCE DOCUMENTS: CL 705.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Placing Concrete
checkpoint | 5.1 - Carry out sampling of concrete
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: No. of Samples: 0 to 50m3 - 1 No.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: CLB, CLC
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.2 - Compressive testing
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days.
label | ○ The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additioinally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete test records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.3 - Placement methodology
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ Concrete shall not be freely dropped from height >2m
label | ○ Concrete shall not be moved horizontally by vibrators
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 5.4 - Compaction
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-011 - Sign Installation | itp |  |  |  |  | ITP-011 - Sign Installation
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.3 - Signage Conformance
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | REFERENCE DOCUMENTS: Drawings AS 1742
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Service Identification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.2 - Post & Foundations
label | FREQUENCY: Prior to Start
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: 714.06
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Signage Install
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | REFERENCE DOCUMENTS: AS 1742, TS 1313 Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-012 - Miscellaneous Concrete Paving | itp |  |  |  |  | ITP-012 - Miscellaneous Concrete Paving
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.3 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | REFERENCE DOCUMENTS: 703.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
label | ○ 75mm thick layer of 20mm Class 2 crushed rock bedding for median infill
label | ○ Bedding trimmed, moistened, and compacted as per Section 304
label | REFERENCE DOCUMENTS: 703.21 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.5 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: 703.12, AS 3610
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.6 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL62 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
label | REFERENCE DOCUMENTS: 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.7 - Concrete Quality
label | FREQUENCY: Each Batch
label | ACCEPTANCE CRITERIA: Check the deleivery of the batch is an approved concrete mix as ordered. VR330/32. Check for the time from plant to site,Check for the water qty added.
label | REFERENCE DOCUMENTS: 703.13
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.8 - Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | ~ N32 for concrete infill
label | REFERENCE DOCUMENTS: 703.05(a), 703.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.10 - Surface Finish
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Footpaths and other Surfacing shall be compelted with a wooden float.
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.11 - Pram Crossings
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | REFERENCE DOCUMENTS: Booroondara Standard drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.12 - Joints
label | FREQUENCY: Each Joint
label | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
label | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
label | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.13 - Protection of concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | REFERENCE DOCUMENTS: 703.27
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
label | FREQUENCY: Lot
label | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | REFERENCE DOCUMENTS: 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: ITP Signed/Test Records
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.2 - Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | ○ Section dimensions shall be constructed within the following tolerances:
label | – 5mm and 15mm for width; or
label | – ±3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-013 - Construction of Subsoil Drainage | itp |  |  |  |  | ITP-013 - Construction of Subsoil Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
label | ○ Geotextiles: Shall comply with Cl 702.06.
label | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
label | REFERENCE DOCUMENTS: Cl 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: Cl 702.09 (c )
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: Cl 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Placement of granular backfill
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: Cl 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: Cl 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: Cl 702.10
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | REFERENCE DOCUMENTS: Cl.702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-014 - Pavement Construction | itp |  |  |  |  | ITP-014 - Pavement Construction
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Material classified as silt
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation Signed ITP/ records
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Unsuitable Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
label | REFERENCE DOCUMENTS: 204.07(d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Groundwater
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | REFERENCE DOCUMENTS: 204.06 (h)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | REFERENCE DOCUMENTS: Cl 204.12 Section 173
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP* WP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-017 - Sealing Works - Asphalt Laying Works | itp |  |  |  |  | ITP-017 - Sealing Works - Asphalt Laying Works
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least
label | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Tack Coat
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | REFERENCE DOCUMENTS: 407.15, AS2150 11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Spray area
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.2 - Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: 407.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.16 Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.6 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.23 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.23 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.8 - Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | – 94.0% or greater Accept lot
label | – 91.0% to 93.9% Lot may be accepted at reduced rate
label | ○ For layers ≥50mm, if characteristic thickness is:
label | – 96.0% or greater Accept lot
label | – 91.0% to 95.9% Lot may be accepted at reduced rate
label | REFERENCE DOCUMENTS: Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | FREQUENCY: Per 4,000m2 at completion of work
label | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | REFERENCE DOCUMENTS: Table 407.232
label | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
label | RECORD OF CONFORMITY: Survey Conformance
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-019 - Construction of Kerb & Channel | itp |  |  |  |  | ITP-019 - Construction of Kerb & Channel (Rev 01)
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to Fulton Hogan site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: A Safe Work Method Statement for identified hazards shall be signed onto by the contractors on site.
label | ○ Where a SWMS is amended, a copy of all relevant documentation and details shall be immediately submitted.
label | REFERENCE DOCUMENTS: Fulton Hogan OH&S
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest revision IFC drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: EMP, induction register
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Site induction signed, This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Traffic Management (When required)
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Approved TMP and MOA
label | REFERENCE DOCUMENTS: TMP Relevant to work zone
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional properties as shown on the drawings.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.17
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground, This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer, Superintendent & Surveyor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current DBYD documents received and works executed by qualified service locator.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Services marked on current IFC drawings and on the ground.
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Temporary Drainage Provisions
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge and stormwater to be in place. The safe discharge of drainage and stormwater is to be maintained at all times during construction, with prior written approval sought from the relevant waterway authority.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.18
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Writen approval from relevant waterway authority, This ITP to be signed
label | AP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material used for cast in place concrete paving works shall be compacted size 20mm Class 3 or 4 Crushed Rock or Class 3 or 4 Crushed Concrete, manufactured and supplied in accordance with sections 812 or 820 respectively. Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.21
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed. Visual proof record and Crushed Rock Certificate.
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C. Unless otherwise specified concrete shall be N32 standard strength. Approved VR mix used. Concrete extrusion machines have minimum cement content of 320 kg/m3.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl.703.09, Cl.610.17 (a)(b) (c)(d)
label | INSPECTION/TEST METHOD: Site Inspection/ Temp Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.6 - Machine Extrusion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete shall be fed to the machine at a uniform rate. The machine shall be operated to produce a satisfactorily compacted, dense mass of concrete free of any faulty or honeycombed patches. Surfaces shall be substantially free from surface pitting larger than 5mm diameter.
label | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Tolerances
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas. Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.15
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Finish Surfaces
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Egdings: Rendering shall be applied witihin 30 minutes of placing or extruding concrete. Rendered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.25
label | INSPECTION/TEST METHOD: Site Inspection/ Temp Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor/Site Engineer
date | Date Completed:
checkpoint | 2.9 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints: constructed at right angles to the back of edgings and the edge of surfacing at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.26
label | INSPECTION/TEST METHOD: Site Inspection / Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor / Site Engineer
date | Date Completed:
checkpoint | 2.10 - Backfilling
label | FREQUENCY: Frequency
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.29
label | INSPECTION/TEST METHOD: Site Inspection / Verification
label | RECORD OF CONFORMITY: This ITP to be signed
label | IP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Survey data captured for as-built purposes
label | FREQUENCY: Completion of each lot
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings / survey records
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: As-built survey records
label | SCP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP