## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-STR Structural Concrete Coatings (Moisture Resistant Pore-lining Penetrants) | itp |  |  |  |  | ITP-STR Structural Concrete Coatings (Moisture Resistant Pore-lining Penetrants) Rev 2
section | Referenced Documentation
checkpoint | 1.1 Non Dependent
label | REFERENCE: Department of Transport & Planning Section 686 November 2018
label | ACCEPTANCE CRITERIA: N/A
label | METHOD: N/A
label | FREQUENCY: N/A
label | CATEGORY: N/A
label | RESPONSIBILITY: N/A
label | VERIFYING DOCUMENTS: N/A
textbox | Date Completed:
section | Preliminaries
checkpoint | 2.1 Material Selection
label | REFERENCE: Product TDS 686.04, 686.05 (h), 686.05 (c) (iii), Request for Concession #1
label | ACCEPTANCE CRITERIA: The material shall be selected based on the following criteria:
label | i. active ingredients: Silane = at least 95%
label | Solid Silane / Silane Cream = at least 80%
label | Silane-Siloxane & Siloxane = not specified
label | ii. application rates:
label | Silane = 2 applications of 0.3L/m² min. Solid Silane / Silane Cream = 1 application of 0.4L/m² min.
label | Silane-Siloxane & Siloxane = as per the rates on the manufacturer's TDS
label | iii. penetration level: Silane = 5mm min.
label | Solid Silane / Silane Cream = 5mm min. Silane-Siloxane & Siloxane = 3mm min.
label | iv. contain a fugitive dye
label | v. be compatible with any future film-forming coatings (where applicable)
textbox | Enter: Teambinder Material Approval number:
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, 21 days prior to application
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Quality Documentation
label | REFERENCE: 686.04
label | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Hold Point number
label | METHOD: Document Review
label | FREQUENCY: Once, for each product, 21 days prior to application
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Application Personnel & Equipment
label | REFERENCE: Product TDS 686.07 (a) (i), 686.19
label | ACCEPTANCE CRITERIA: The supervisor shall remain present at all times.
label | ○ Silane: Atmospheric sprayer or roller are acceptabe
label | ○ Solid Silane / Silane Cream: The spray equipment shall be an airless pump system not exceeding 70kPa so that no atomisation or misting of the material occurs, but roller is acceptable for smaller areas.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to application.
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.4 Protection of Adjacent Works & Property
label | REFERENCE: 686.1
label | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and material application processes.
label | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, drains, pedestrians or vehicles without protective measures in place.
label | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | METHOD: Visual, Document Review
label | FREQUENCY: Where applicable, 2 days prior to application.
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Minimum Concrete Curing Period
label | REFERENCE: 686.16
label | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | ○ Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | ○ Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
label | METHOD: Visual, Document Review
label | FREQUENCY: Once, prior to application.
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Pre-application Activities
checkpoint | 3.1 Material Records
label | REFERENCE: Product TDS 686.12
label | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | i. the manufacturer's name & address
label | ii. product reference
label | iii. batch number
label | iv. quantity manufactured in the batch
label | v. date of manufacture
label | ○ Product beyond the manufacturer's shelf life shall not be used.
label | ○ Record: Trace each product to it's final location on the Application Record.
label | METHOD: Visual
label | FREQUENCY: Prior to application
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.2 Weather Conditions
label | REFERENCE: Product TDS 686.11, 686.14 (a) (iii)
label | ACCEPTANCE CRITERIA: Materials shall not be applied under any of the following conditions:
label | i. windy conditions where spray/splatter may be generated
label | ii. when wind-borne debris is likely to contaminate the uncured surface
label | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Material TDS states otherwise
label | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of application
label | vi. when rain splatter, water run-off or water deposits onto the surface and affects penetration into the substrate
label | vii. when the substrate surface is wet or damp (unless it is required for, or acceptable to specific material as shown in the Product's TDS)
label | ○ Record: Weather conditions on the Application Record
label | METHOD: Visual Measure
label | FREQUENCY: Prior to application and every 4 hours per shift
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.3 Surface Preparation
label | REFERENCE: Product TDS 686.06 (a & b)
label | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Product's TDS, but as a minimum, all surface contaminants such as release agents and curing compounds shall be removed by high-pressure (e.g 3,000psi) washing with potable water or other suitable means.
label | ○ The surface shall then be flushed with water and be surface dry for at least 24 hours prior to application commences.
label | ○ Where surface preparation is performed in stages (e.g pressure washed the previous shift), remove any loose particles with compressed air or air-blowers prior to the application.
label | ○ Any concrete defects exposed during the surface preparation shall be repaired
label | METHOD: Visual
label | FREQUENCY: Once, prior to application
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.4 Surface Moisture Inspection
label | REFERENCE: Product TDS 686.14 (a) (i) & (iii)
label | ACCEPTANCE CRITERIA: A 1m³ representative sample of prepared concrete surface shall be inspected for surface moisture condition and environmental conditions.
label | ○ The surface moisture conditions shall satisfy the Product's TDS.
label | ○ Record: Surface moisture conditions on the
label | METHOD: Visual
label | FREQUENCY: 1m³ / lot, immediately prior to application
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Application Activities
checkpoint | 4.1 Trial Application
label | REFERENCE: 686.13
label | ACCEPTANCE CRITERIA: A trial application of the material shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate to determine the technique to achieve the approved application rate.
label | ○ Attach: Photographs
textbox | Enter: Teambinder Hold Point number
label | METHOD: Document Review
label | FREQUENCY: Once, for each Material, 7 days prior to full application
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 Application
label | REFERENCE: Product TDS 686.07, 686.09, Request for Concession #2
label | ACCEPTANCE CRITERIA: Application should be carried out to the Product's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
label | ○ The material shall be applied in a continuous operation, starting at the lowest point proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
label | ○ Where a second coat is required (e.g SIlane), re- application, shall be within the recommended timeframe from the Product's TDS and treated as a separate Lot.
label | ○ Times of application(s), product names, locations applied and volumes used shall be recorded.
label | METHOD: Visual Measure
label | FREQUENCY: Each coat
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Inspection & Defect Identification
label | REFERENCE: 686.07, 686.15
label | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity and appearance between coats.
label | ○ Re-application at dry-appearance locations may be required.
label | METHOD: Visual
label | FREQUENCY: After each coat
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.4 Drying & Penetrating Periods
label | REFERENCE: Product TDS 686.09
label | ACCEPTANCE CRITERIA: The material shall be protected from adverse conditions and traffic during the (wet) penetrating period.
label | METHOD: Visual
label | FREQUENCY: After each coat
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-application Activities
checkpoint | 5.1 Clean-up & Waste Disposal
label | REFERENCE: 686.1
label | ACCEPTANCE CRITERIA: All material pooling and over-spray shall be removed from all surfaces, including surfaces not being treated.
label | ○ All rubbish and remaining material shall be removed from site.
label | METHOD: Visual
label | FREQUENCY: At completion of Works
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Penetration Depth Testing
label | REFERENCE: 686.14 (b) (v), Request for Concession #3
label | ACCEPTANCE CRITERIA: 50mmØ core samples, 50mm depth, are to be taken and immersed in a dye to determine the depth of penetration.
label | The subsequent results shall be:
label | i. Silane = 5mm min.
label | ii. Solid silane & silane cream = 5mm min.
label | iii. Silane-siloxane & siloxane = 3mm min.
label | ○ Attach: Penetration Depth Testing Results
label | METHOD: Test
label | FREQUENCY: 3 no. tests every 50m² or part thereof
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Non-conformance Report (NCR) Closure
label | REFERENCE: Fulton Hogan Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
label | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
textbox | Date: