## Master List Templates
Id | Type | Name | Values | Prompting Name
888ae02b-04ac-49ad-b409-58ed5312b28e | checklist | 1. Standard |  | 1. Standard
6c36f296-e45a-4cdb-bf92-c6afa94259e4 | section | Precast Element Details
210ea1e7-2b49-4212-a6e7-864f6c88147e | checkpoint | Concrete Details Complete
e60845e7-311e-5010-bd8c-b77aba89e4b7 | textbox | Concrete Volume
5388bff2-c21f-5651-aa6f-a546844f144d | textbox | Concrete Strength
82ee082b-96a9-5528-8301-b5e600f5e207 | textbox | Enter Drawing Revision Number
b348e89b-fb78-5dc3-802b-14c3a842e6bb | textbox | Cast Date
97eebc5b-4b98-5e29-8c8b-a749f13a1048 | textbox | Admixture Required
082377d9-99a4-407a-a5c6-4c7e1f509532 | section | Reinforcing Yard Checks
38a44764-8dcb-4bd3-b5de-b5ab46080097 | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
2b9bd64e-c72f-44a0-adb8-d43c540e6985 | checkpoint | Cast in Items coordinated and marked on cage (Dross Ducts, Inserts Weld Plates)
5b215c52-1170-4ea1-afe7-2908f81175ac | checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
8cda3086-f80b-4e05-8d34-cbc6e9a633d7 | checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
fe10f23f-5f3b-4129-b750-2e4a0f11a94b | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
aa6bac79-5691-4039-9896-bdaf570cbf8d | section | Formwork Set Up Checks
2c992907-738d-412f-b627-13ec7f512ae4 | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
3ca86a17-a308-44a1-9783-a5d535834366 | checkpoint | Edge Details & Rebates
db3218ba-1b01-48f9-b96f-7ab433cc0cb8 | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
e1a020e5-82ad-4b4d-8103-bb87db0b8575 | checkpoint | MF roughening's
b54927e9-6be7-4f7c-9abe-ca283b61d67b | checkpoint | Sides Straight & Magnets Fastened
7a7c8090-a806-4d69-90bc-42d5777e3947 | checkpoint | Mould Face Clean
da70a40f-183f-420a-b054-197c1b79ccc7 | section | Prepour Checks
e11dd016-b6a9-4989-8b4c-dac91119298c | checkpoint | Mould Cleaned & Oiled
9f5e2fc5-e829-44e5-8cb7-afc1a4ef623e | checkpoint | Check covers on all sides, MF and TF, openings
ce985fea-fe6a-40dc-b878-ad355b3d5492 | checkpoint | Starters (Size, Grade, Setout and Length)
f686182e-b245-4d3e-9b8c-f40191713f89 | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
7dcefd45-26ae-425e-9588-487412187fc2 | checkpoint | Lifters
40647ea8-cdbb-46b0-905c-9537c5823153 | checkpoint | Tie wire Trimmed
7677866e-857c-4458-b977-b9625bca5c79 | checkpoint | Panel fully clean
6a406d25-ac34-405a-ac7f-e50aff1e4231 | checkpoint | General Photos Attached
9183db28-ce82-4e15-aff5-01a04b4cf36c | checkpoint | Concrete Docket Attached
f9bf9297-c41d-4ebb-91a1-a66fabe17e2a | checkpoint | Shop Drawing Checked Off (attach photo)
209edfa4-355f-46a7-8de9-5029a3445c6a | section | Post Pour
4baade08-c32b-46c6-b006-e177efdecdcd | checkpoint | Confirm formwork has not shifted during placing of concrete
20663429-0311-4634-ba9d-c7298f34dbf0 | checkpoint | Face lifters placed in correct location
e1e6f4d2-9726-4543-96ee-3be2977115ed | checkpoint | Roughening Lines Correct
8a652e73-1ded-41d3-89b1-246a2f99e954 | section | Demould Inspection
8973bb61-aa31-4660-a8f7-672922c3c192 | checkpoint | Mould Face Acceptable?
e1fd58c1-885e-460a-b0e0-db510088258f | checkpoint | Trowel Face acceptable?
f2a55c62-aacb-4437-a826-4ba9d6828fa4 | checkpoint | Item Labelled?
8b4b1866-89b2-4122-8da5-f3248e227a95 | checkpoint | Drossbachs cleaned out and clear?
fdf9e859-093a-4ee8-914d-808aa17549ec | checkpoint | Top lifters are cleared out and eyes are free of concrete?
6f654f0b-ce4c-4365-b91b-5006f8f954aa | checkpoint | Drossbachs drilled ?
2d382d5f-3885-44f3-bf02-edc942382aed | checkpoint | Nail plates removed?
8442a120-1e73-4889-8620-ea0af0a76181 | checkpoint | Jet washed?
60d79a94-5454-4d4f-87b7-d2f522b6560a | checkpoint | Weld plates are cleaned and free of concrete?
9eaaa2e7-4ec1-49f7-a82c-586756a1e698 | checkpoint | Starter bars bent for transportation?
b1da6ad0-fc1d-45c4-87aa-fb26cd7284a3 | checkpoint | Structural repair required?
952d92f1-95d4-4840-80df-1e8aee5443aa | checkpoint | Chamfer Inspection
12d90b58-5b2c-45a7-af00-cab22e20cc65 | checkpoint | Silicone Inspection
9ee51ac8-48f0-4dff-863b-1eb98cdfcee5 | checkpoint | Honey combing from Vibrating
9960eae4-e7e0-47b8-9161-f2e76ed25f61 | checkpoint | Final check with drawing
ffc9a475-8859-45f1-8ed4-beaec83ae7bf | section | Loading Out
4ca5fc7d-8cdb-40ee-b1d5-4073ff2fb67e | checkpoint | Photo taken of Panel on Truck
ed28e9b2-f873-405a-a6db-8c111af8bcaf | checkpoint | No remedial work required on site
68b30628-65e2-4266-91e5-e1e7af196107 | section | Test Results, Certificates and Documentation
584f35b7-7ade-4890-a208-25255966c0b4 | checkpoint | Upload reinforcing detail sheets
29957942-5cb5-494b-a852-e27f1bfdbfb5 | checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
a306bc84-106c-439f-b159-91b89e8bccb9 | checkpoint | Upload Concrete test results
3a2edcf7-94ef-451e-b661-8c2c021a9af7 | checklist | Add Defect/Remedial |  | Remedial -
e970f2e8-38be-47ea-88e8-55a317040604 | checkpoint | Defect Details Inputted
02fb74a6-9297-5b69-8d8f-5d0c48b9c66b | dropdown | What is the Defect | Chip in panel, Crack in the panel, Level of finish inadequate, Incorrect Location of Cast in Items, Missing Cast In Items, Other Remedial - Specify below
5643327d-d65b-5388-9530-86f7463e6f6b | textbox | Other Defect (specify here if applicable)
0a0c215a-1923-5c54-9bd7-a2a864f6723e | textbox | Defect Location on Panel (Attach Photo)
7152a2c6-2eb2-5247-8f3c-096388865e18 | textbox | Remedial Work Required
502296f5-6918-4b50-a34e-45b8d43935b1 | checkpoint | Panel Location Inputted
96be865a-2544-5cb4-9d0c-5574d44c5bb8 | textbox | Panel Location
98dc4c4e-edbc-4b97-8033-8b15d5166725 | checkpoint | NCR Raised if Required
883a5a98-2c88-4d02-aa0d-e0db0e558895 | checkpoint | Remedial completed - (Attach Photo)
496ad6f2-797a-4b17-a0c0-69cd3b3dcd4a | checklist | Compliance Documentation Checklist |  | Compliance Documentation
f58889c0-5e6b-482f-bec0-0ae5a115ed21 | checkpoint | Concrete Test Results
066d13f7-4c78-53cf-ae07-c6288d05b188 | note | Pass once all test results for this project are attached
4fe06e26-34cc-58f5-876f-027f90ea4833 | textbox | Concrete test requirements for this project
a40742db-3201-4a72-ac32-2faed3ed3e97 | checkpoint | Mill Certification
95c90d50-faae-57db-8f9a-9e8b3b1bada8 | note | Pass once all mill certs for this project are attached
75aa4f73-99ce-4d2a-a05b-d954d6eb38ed | checkpoint | PS1 Attached (if applicable)
49b1e850-1ca9-4741-8c28-ee80ef9b1a01 | checkpoint | PS3 Attached (if applicable)
2e7a2ce4-b667-435d-b89d-f639ced12998 | checkpoint | PS4 Attached (if applicable)
b0a94f9c-8d3f-4a14-a6b3-95f2bb9efe13 | checklist | Demould Inspection |  | Demould Inspection
cc713758-c7d1-4000-94a0-49771f36458f | section | Post Pour/Demould Inspection (Yard Manager)
570fd16c-c2c0-47b8-82ba-d7fe8f574853 | checkpoint | Mould Face Acceptable?
21acafad-a707-45c5-b33d-57431f8e4b8e | checkpoint | Trowel Face acceptable?
be276187-75d3-4dd7-9792-8c817e0cc7ce | checkpoint | Item Labelled?
949b98e5-d84e-4eda-abf1-882f7821cb3f | checkpoint | Drossbachs cleaned out and clear?
3a946079-7e35-4cfb-b92e-ef247a29cfd7 | checkpoint | Top lifters are cleared out and eyes are free of concrete?
64edf7d7-0241-4bfb-b135-6ffb9ee7bfeb | checkpoint | Drossbachs drilled ?
73ef77bc-512d-4974-8e61-9384c0739d02 | checkpoint | Nail plates removed?
8c21555a-3f20-4971-a39d-2e9513cfb1ac | checkpoint | Jet washed?
3ed83de0-2c13-491f-b12d-ddb3518766e4 | checkpoint | Weld plates are cleaned and free of concrete?
363dbd71-56fc-4f5b-b879-25a2a10fbc48 | checkpoint | Starter bars bent for transportation?
49f08527-c22a-470b-b3a7-4cadc7089370 | checkpoint | Structural repair required?
3e28e816-1c9f-465c-a049-bbd09d29d034 | checkpoint | Chamfer Inspection
f192b395-a8f0-4f6a-be06-f3dd0f917ff2 | checkpoint | Silicone Inspection
272b8afc-ded7-4634-8af4-56fedd48df35 | checkpoint | Honey combing from Vibrating
be14bedc-6405-45e3-9788-10a3eb991fa4 | checkpoint | Final check with drawing
cb39f9e7-7e8f-4740-8ac4-ef68fc245ea4 | checklist | Job Details Checklist |  | Job Details
3d098030-e418-4675-b5b1-7520caf5ee77 | checkpoint | Project details entered below
8724734a-b967-59e4-b175-c5c6f1db0e60 | textbox | Job File Number
45b6015f-22e3-5b0c-8117-3a27221048ee | textbox | Project Name
ef1b5d06-622a-5aca-84c2-8a00931e8d8a | textbox | Site Address
31c83e66-7544-5cd3-a918-a8f6baca03e9 | textbox | Main Contractor (e.g. Teak)
b1590901-5990-5ddc-9dee-19725346ccbb | textbox | Main Contractor POC
04d29bad-dab1-5357-9860-e83c0c02444f | textbox | Structural Engineer
78611fa4-7a52-594c-8bc7-427229a97b3c | textbox | Architect