## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Internal Tiling checklist |  | Internal Tiling checklist | a6c07f11-a458-4dfc-af56-0ecdb82ffd03
| checkpoint | 1. Ensure Material and Tiles Set out Approved As per the drawings and spec
0c051b15-aa58-5d21-9c47-e5515b0ba8cb | textbox | Drawings in uses:
| signoff | HOLD POINT
| checkpoint | 2. Apply Mudfixing Mortar under Terazzo Tiles
| checkpoint | 3. Apply Approved Tile Adhesive - Ultralite S1
| checkpoint | 4. Lay Floor and Wall Tiles
| checkpoint | 5. Grout - Mapei Keracolor FF
| checkpoint | 6. Apply Anti-Slip Sealer to Terrazzo Floor Tile
| checkpoint | 7. Inspect Waste Blockages - Provide Photo/s
| checkpoint | 8. Clean Area
| checkpoint | 9. Caulking - After builders clean
| checkpoint | Wetspot Supervisor signature
| checklist | Internal Waterproofing checklist |  | Internal Waterproofing checklist | f86f7fde-fc12-40b2-b370-2d6e06c3512e
| checkpoint | 1. Inspect substrate including wall junctions. Do not proceed works if substrate is unsatisfactory. Report any issues to MPX for rectification.
94a68f9d-552a-5e86-bf43-5dbf309aca14 | note | Record Moisture content test and provide photo of gauge. Reading must be 5% or less.
| checkpoint | 2. Preparation
6885b56c-9fca-5d6c-9a34-8069d0cd71c8 | tickbox | Clean substrate with moist sponge to ensure free of debris and dust.
2f374082-8a13-5eb4-ae00-6d7d92a08edc | tickbox | Ensure drain points are protected.
c99366b8-bdbf-5c64-a130-2ac22ede11ae | tickbox | Apply approved primer - Mapei Primer G
| checkpoint | 3. Seal junctions and glue down angles with polyurethane fillet - PascoflexPU25
ba7d5be8-3e7c-5a78-ad65-b7e26091eb28 | note | Minimum 12mm thickness. *Waterstop angles installed to shower entry, bathroom entry, laundry entry *
| checkpoint | 4. 1st layer of Waterproofing: - Apply 2 coats of min 1mm Mapelastic Smart membrane to achieve min 1.6mm DFT including turn-ups to wall - Measure and record DFT. Provide Photo/s of guage
d470a9e2-4d65-5662-aeb3-6f74c17377c5 | note | Allow minimum 5 hour wait time inbetween coat applications. Immerse reinforced bandage into membrane on all wall/wall and floor/wall junctions during 1st coat.
| checkpoint | 5. Conduct Flood Test. *Minimum 2 x showers per level* Provide Photos.
| signoff | MPX Co-Sign
| checkpoint | 6. Apply Screeds.
08438849-c563-5fe7-b520-51daeb7c34fc | note | Standard sand & cement screed up to 60mm.
7d88adb3-5881-5e5f-89e5-fad98d8db05e | note | Create Drainage Falls towards waste as per standards: 1:80 shower bases achieve with screed & Bathroom floors 1:100 achieve with adhesive
| checkpoint | 7. 2nd Layer of Waterproofing (Where Required)
59f4470b-ac12-5bba-a737-f27d6cea4b64 | tickbox | Apply Primer above screeded areas and seal junctions with polyurethane.
30a38db0-9457-5801-b6be-bdce00f437c2 | tickbox | Apply 2 coats of minimum 1.0mm Mapelastic Smart membrane to achieve minimum 1.6mm DFT including turn-ups to wall.
c6dd9458-26f4-59d0-aa35-eeb8af02b6ab | note | Allow minimum 5 hour wait time inbetween coat applications.
| checkpoint | 8. Manufacturers Inspection by Mapei and acceptance
9b9c0db1-0b4d-5469-877a-45c9f39a4cef | note | Inspections of works at to occur throughout multiple stages of the waterproofing system (one inspection per levell for each building). Wetspot to schedule inspections with Mapei - MPX to be notified prior.
| signoff | HOLD POINT
| checkpoint | Wetspot Supervisor signature