## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Panel Stitches |  | Panel Stitches | 06a0d985-2f51-4989-8bb8-7b53443605b0
| section | QA
| checkpoint | Delivery/material check
94fbddf0-264e-5f43-b286-469ceb5b6200 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
d5e735fe-100f-50b6-8bdc-d4facdc90790 | button | Safe | PASS, FAIL, N/A
9655797a-70c9-5e03-a894-c712bb21f44c | button | Set out | PASS, FAIL, N/A
17f7fbe4-ee90-55d7-aa8f-4e3a29785df9 | button | Starters from panels protruding from panels as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Verticals
7447bdd2-d3ab-590f-9737-336ca5d6574f | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
e5499fbc-f3dc-5852-9108-c8e8f1d7981b | button | Correct level at base | PASS, FAIL, N/A
864e57f8-b830-5dba-9f5e-f37f045a441b | button | Correct length | PASS, FAIL, N/A
b4b8ecbc-d5e8-5e2c-8e9d-671807b6c735 | button | Correct laps | PASS, FAIL, N/A
bb4ed56d-363f-5e70-8dec-0e10092fb8b2 | button | Sufficient protruding lap | PASS, FAIL, N/A
b5894fdd-20fa-5b82-ae5b-79614e280704 | button | Top cover where returns terminate | PASS, FAIL, N/A
65cf26b3-d728-5ded-9082-1fc1738f8df0 | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
| checkpoint | Horizontals/stirrups/links
138bc8e1-20e9-538d-bd6a-bc6242b484b9 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
b6d5b740-2965-531d-9ee2-342a3deaa884 | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Miscellaneous
ef5c6685-f4d6-5125-8fc2-cabf302725d2 | button | Structural steel | PASS, FAIL, N/A
92ded69d-16d8-5130-af91-a58d5c7e2887 | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
57150108-33f5-59d4-9a84-2217130c99fa | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Column |  | Column | 0e5f0e28-9160-41dc-af53-5867198c8ea3
| section | QA
| checkpoint | Delivery/material check
6340778d-3d0f-564f-b193-26be6f15a3f4 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
805bd82c-33ed-593d-a49f-ad919c23119e | button | Safe | PASS, FAIL, N/A
163e5924-0f35-5568-94d8-8b84602fda0b | button | Set out | PASS, FAIL, N/A
da13c6fd-1ad8-5809-9a33-d460276f31ef | button | Starters perpendicular (not bent by other trades) | PASS, FAIL, N/A
| checkpoint | Column
ba32c06e-b82d-5570-96d2-83826b478697 | button | Bar diameter/quantity/correct protruding lap | PASS, FAIL, N/A
c7cdde60-fe3b-5ace-b90f-0a7cedec1a27 | button | Laps to starters | PASS, FAIL, N/A
e9e378e8-7399-535d-99ae-56cf17702210 | button | Couplers in lieu of starters. TYPE? | PASS, FAIL, N/A
dcdc6a5e-2562-574e-b2d0-e47896217f67 | button | Vertical and horizontal laps correct | PASS, FAIL, N/A
1f47732c-268f-51f5-8844-d7f774b1f61a | button | Stirrups/links diameter/grade/spacing | PASS, FAIL, N/A
f4f69ed9-efc5-5632-90b6-87a7f44cfeef | button | Stirrups/links to top of concrete pour | PASS, FAIL, N/A
4a62e782-050c-54e9-a5f7-c8d1bd4f62f2 | button | Holding stirrup at top of column | PASS, FAIL, N/A
| checkpoint | Miscellaneous
dfb55cbd-16ea-5547-b852-3dbd4829e71d | button | Structural steel | PASS, FAIL, N/A
89747a74-01e4-5a31-ae8b-53ddd773e3d3 | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
53ad6d82-6194-52ff-9f3f-776d647f5d1f | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | PC Beam Stitch |  | PC Beam Stitch | 46028cb7-85ac-4859-9f0b-2f9dc129fc8a
| section | QA
| checkpoint | Delivery/material check
fb177f16-2cb1-548d-b0dc-178b6a3d3eee | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
c8addae6-5cd5-590e-8365-8015a34e0493 | button | Safe | PASS, FAIL, N/A
70cc5ad0-3334-5836-8391-69214ef4845c | button | Starters from protruding from PC Beams as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Longitudinal T/B & sides
a8667408-da45-5b9b-97fc-a9f8651e0414 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
e21f585a-dff1-5651-b86d-f8bdce3df4cd | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
5b55ea7d-f6ee-54a9-9b99-6e5b009a6b2d | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Concrete cover
428cedec-8ffc-5168-a78a-394c67559e09 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
cf07d103-8511-5752-8099-46e628ea92e2 | button | Structural steel | PASS, FAIL, N/A
fe772d93-9041-5ae4-9f71-1ebab5c5d7fc | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Lift Pit |  | Lift Pit | 4a042f6f-e734-4ef4-bff9-c5a44d117244
| section | QA
| checkpoint | Delivery/material check
6ec3c890-f459-5399-bf3b-fa34ed7fe405 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
71b4a2ff-39ac-5772-a13b-dd569b6e7a54 | button | Safe | PASS, FAIL, N/A
20342d89-0494-5bd7-b7c0-23ee8e42a277 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Base slab top & bottom
77ea8334-2d8a-5217-b0b0-deba1fa4998e | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
6963989a-86da-5462-a6fb-c745e517ac9d | button | Links diameter/grade/spacing | PASS, FAIL, N/A
393ad707-8d90-59f4-9e88-fc71f9850c2d | button | Correct laps | PASS, FAIL, N/A
053e45e5-82d3-5b42-a4bb-ccb30b4e4920 | button | Staggered laps | PASS, FAIL, N/A
80ea1c4c-e249-50ef-aa1d-3027ffb11148 | button | Sump detail | PASS, FAIL, N/A
| checkpoint | Ground beams
9b0c8352-555d-5bfb-a1ca-3616f192c240 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
599a83c7-e1a4-569e-b280-31e5513056d3 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrup diameter/grade/spacing
cf22f2ec-90d0-5b38-8b73-8380e432a0d2 | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Sump
2f3cf87d-c63f-5e61-a476-a937716ac7bc | button | Location | PASS, FAIL, N/A
e5779a2c-6754-50ec-9269-4f75551794a7 | button | Trimmers | PASS, FAIL, N/A
| checkpoint | Starters
d96c6728-0cf5-5870-accb-be85b63689a2 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
eb31907c-d0ff-5c36-adaf-b43bbf5f9af8 | button | Sufficient protruding lap | PASS, FAIL, N/A
23de12a1-de03-5b71-80ba-cf65f6c9a19b | button | Starter set out and perpendicular | PASS, FAIL, N/A
0305238a-9f80-5d1f-b6f4-834b47c24204 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
1982ea7d-b9f7-5399-890c-895dd1bafb01 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
0134ac7d-b4e1-5bb1-9ddf-0d04e60db3bf | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
938d9bfa-d9cc-5093-90b5-11c5d0ce215c | button | Structural steel | PASS, FAIL, N/A
7a431c51-3805-5fec-b545-75396a8f4ce0 | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Slab Ground (Bar) |  | Slab Ground (Bar) | 57940321-12e8-41cf-8d5e-63dc47bb7f57
| section | QA
| checkpoint | Delivery/material check
bad05af3-2156-5e2e-b792-a75ef9d9a53c | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
290cc56d-115f-54c9-9994-0ad39eeaeb3f | button | Safe | PASS, FAIL, N/A
b11aaf6d-ecf2-59c3-a4a0-602628e13072 | button | Slab grade RL checked | PASS, FAIL, N/A
0aeb95bd-e8d5-5a24-84bc-c49d0c176c77 | button | Setout | PASS, FAIL, N/A
| checkpoint | Slab reinforcing
107723ab-c033-5f12-8cd2-a5b65306b032 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
61c2cf4c-7fc8-5d29-a8f1-500299226c03 | button | Chairs with height check | PASS, FAIL, N/A
b22681d1-8217-5d47-9341-96bf66a67be5 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
9253ca77-78ae-521e-8bdc-b3d567c69c57 | button | Correct laps | PASS, FAIL, N/A
5509d34a-cffa-5b14-8e49-9aed8d83f3f7 | button | Additional bars | PASS, FAIL, N/A
584e7cc1-c83f-5f15-a4bd-cb5123703133 | button | Saddle bars | PASS, FAIL, N/A
6479884e-e39e-5241-acae-a5893897afbd | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
164d7106-22a9-5687-b0a5-9c66f18becd7 | button | Bend down starters/screw in starters | PASS, FAIL, N/A
a41e3047-1e0b-521d-b012-47237faba494 | button | Starters other e.g., wall, nib, vertical | PASS, FAIL, N/A
| checkpoint | Concrete cover
d0954915-307e-5bb5-b848-f0244a9c05c4 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
212f2221-7759-50d9-8505-233d1c886898 | button | Structural steel | PASS, FAIL, N/A
61882a1b-c5ab-5e6a-826e-4938f06d7be3 | button | Cast-ins | PASS, FAIL, N/A
38da89a9-2613-51dc-b264-a90678ede59c | button | IMBMS | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Stair Landing |  | Stair Landing | 6f49b7e3-1a53-4f4d-a229-bcddc5d533fc
| section | QA
| checkpoint | Delivery/material check
0989d133-6add-5788-b452-f0f7148f0945 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
0060f99f-4c2d-5f10-9622-7dcd4d498bc9 | button | Safe | PASS, FAIL, N/A
a4e8540a-8311-513f-a6c6-d7a2810ece11 | button | Setout | PASS, FAIL, N/A
c6a1c252-294d-5f48-9cab-9854ab5ba616 | button | Starters from panel/slab/wall pre-bent & straight | PASS, FAIL, N/A
4bafa8c4-0693-52ce-b63b-80fa2ad35ee7 | button | Panel/slab/wall coupler inserts have are clean and at correct levels | PASS, FAIL, N/A
93d040dd-0458-562e-ad86-d2441615c31d | button | Correct type/size | PASS, FAIL, N/A
| checkpoint | Stair landing reinforcing
60922427-198e-5416-a89c-a37be4d29b49 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
5cf1d620-982c-5817-84d9-7072e1f378ca | button | Starters screwed/bent down, and epoxied if Reid | PASS, FAIL, N/A
ddd9f091-b827-5f0f-bf21-1c8f54c7b385 | button | Correct laps | PASS, FAIL, N/A
a3b75449-2942-5694-9be3-0f5ba0e02f48 | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
| checkpoint | Concrete cover
c2526227-89ed-5dde-843c-04b83fcf26a7 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Suspended Beams |  | Suspended Beams | 7658adfe-ef9d-49ab-94ad-7da566bbda93
| section | QA
| checkpoint | Delivery/material check
1e92773b-27f2-5d74-b75d-03329bba4bde | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Prestart/area acceptance
447da550-226b-5a75-8681-f0fa06afef4f | button | Safe | PASS, FAIL, N/A
d6bbfaaf-78a9-5bf5-9336-625ffd62ca1c | button | Soffit ready | PASS, FAIL, N/A
3558e354-c072-5f4b-9a0d-d536c5def817 | button | Setout | PASS, FAIL, N/A
| checkpoint | Beam
b2b91e7d-8d07-5277-98be-72b75dad9a12 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
e9e8dd6b-1b1a-5c17-bdda-0730a568da0b | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
b3cdf75d-67a9-5ae9-aec4-870f42df9e52 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
16e2aeca-4d56-53c8-a38d-6a66cfb0e78f | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
9139b6b0-67e0-59f4-b986-c34861db5c70 | button | Development length into pile cap | PASS, FAIL, N/A
692ed756-2bec-53df-87d9-a296e6883579 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
2254703e-7488-5c78-a261-c12d932a27d1 | button | Trimmers/additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
d886aa41-1371-532c-953a-9387958f7ba0 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
cef7dd08-c1e6-5f58-9331-1dda04584a34 | button | Sufficient protruding lap | PASS, FAIL, N/A
7d57a743-03ce-5894-a8c0-ebec31fe7dc7 | button | Starter set out and perpendicular | PASS, FAIL, N/A
5b242023-61e7-518c-ad6b-4077e3930a5a | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
eff115d4-7aa4-5a6b-ae6b-3ee4ad20da17 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
93c39ad5-83a0-5968-8718-a1959f067b18 | button | Structural steel | PASS, FAIL, N/A
4879d863-9ca1-59fc-b19c-6e0e26473895 | button | Cast-ins | PASS, FAIL, N/A
50fa2c99-4f6a-567d-8a9c-f520cf0cdd2f | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Ground Beams |  | Ground Beams | 7b7e0e93-de83-445a-8004-b1cffcb46ffa
| section | QA
| checkpoint | Delivery/material check
830b9316-66e3-5b8b-8a58-1ac37de88715 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
1efe39bc-a881-5c7b-8fa9-8aa7a1601fee | button | Safe | PASS, FAIL, N/A
3656fa32-117a-50ca-a479-1e820f4922d7 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Beam
19225d91-5324-58c5-9069-af8f48ffd0cb | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
a051be16-69b7-58f6-b2d3-0e86a9dcaa34 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
f8f7ab0d-3909-58e0-8dda-0b6364d51336 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
56e8f6e7-9faa-5be6-94b5-738854f80096 | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
37e0d100-8416-5348-ac03-8b38cf8dd321 | button | Development length into pile cap | PASS, FAIL, N/A
c8356685-654b-5433-b41f-5390d9fc32ad | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
631f4669-0ec8-5014-a6d6-f2faaa50f510 | button | Additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
2eb5bde9-73c3-5727-b19d-317b376f746f | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
8c26494e-470f-5b32-9290-83c05c132457 | button | Sufficient protruding lap | PASS, FAIL, N/A
f7ec4882-75b9-5afc-995c-bf16513accd2 | button | Starter set out and perpendicular | PASS, FAIL, N/A
d0f443b9-51aa-57da-956b-08ef49c020a1 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
fc2e63f0-c730-55d6-b2e2-b9c20dded6ab | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
fdb6a8a1-c690-581f-ad40-f74559229c7b | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
e00bca04-3d94-5dc9-a978-00581b1a4f4c | button | Structural steel | PASS, FAIL, N/A
20dd0220-93dd-55ea-8508-8ea57181f023 | button | Cast-ins | PASS, FAIL, N/A
185d46c9-1b65-57b4-a64b-661a7ff80a6d | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Capping Beam |  | Capping Beam | 9e16bf3f-5ad2-4e98-a70a-31455d84ef4b
| section | QA
| checkpoint | Delivery/material check
f27b468d-932b-54b0-97c3-d9c0b1b7beeb | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
1ac8af42-edd5-5bb6-875c-80b57df516d3 | button | Safe | PASS, FAIL, N/A
dcf59b22-2ba5-5af6-baa7-f2997dd74783 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Piles
6f19d8ac-f183-5237-8b1a-c26c6c06f62c | button | Orientation | PASS, FAIL, N/A
42245912-f3ec-5ec8-8662-56f3dfa0da9c | button | Correct height | PASS, FAIL, N/A
4d6d63a8-7de8-5483-8dc7-83a1979cb2ad | button | Hoops bar diameter/grade/spacing | PASS, FAIL, N/A
4318de5d-95da-5269-b6c6-5c476349a334 | button | Hoops welded laps | PASS, FAIL, N/A
71c4e15b-f489-532c-b739-b57046dcbfa6 | button | Footplates on starters - Reid or IMBMS | PASS, FAIL, N/A
| checkpoint | Beam
254b07b4-ecd7-54c3-918d-1340ddd5d924 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
e6329eed-f444-54ff-baab-a28f77a1ab3c | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
4c351f07-ffc4-59d1-b0cc-28c69be29113 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
0118dca6-3505-5de5-a1fb-21211553d82b | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
a2eda2ff-3556-50f3-b7b8-c0da18d710d8 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
4f466fca-594a-5045-ace7-d2b0f19121d8 | button | Additional stirrup at penetration | PASS, FAIL, N/A
07fd8c0e-3c8e-52e8-8fc8-11728d5550ce | button | Anchor details | PASS, FAIL, N/A
| checkpoint | Starters
fd9b4a8a-c760-594e-9580-5ef391fb3c02 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
e6a3311e-8e44-57e0-83d8-e749cfaa397c | button | Sufficient protruding lap | PASS, FAIL, N/A
38df1686-b544-5e56-8323-78ed030c4bcf | button | Starter set out and perpendicular | PASS, FAIL, N/A
6071abb2-3be9-54f8-aff5-93a45f5fc079 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
15e50bcf-8039-58b2-be9d-b35012611a58 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
fa8e20b7-1854-553d-b8f7-08cdcd5a1266 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Miscellaneous |  | Miscellaneous | a5473467-58db-486a-9e28-4f9eee6e5184
| section | QA
| checkpoint | Element/Description
9c32e7ff-e024-514c-9cbd-442ddfe374d6 | button | Element/Description | PASS, FAIL, N/A
| checkpoint | Delivery/material check
a68afb2f-e83e-544a-ae84-4227470cb226 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
0308a893-a4a5-5b55-aa45-f035e34829d9 | button | Safe | PASS, FAIL, N/A
020ba554-daa3-5f0e-bb46-3d4d74f44929 | button | Set out & RL checked before proceeding | PASS, FAIL, N/A
| checkpoint | Top bar/side bar
cbefed87-1a6b-536a-80cd-da358ee2b6ae | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
898ce507-4169-5ea3-8e30-f2ca33e79347 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Bottom bar
85ae1f87-bdc9-5b47-91c5-cb2016df32ca | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
39f5ac33-a1c2-54d8-ac16-04e57dc0c41d | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
e3bc9718-2a77-546f-a8aa-1daeb5131ac1 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
4ac7debb-d79c-5aef-9ee7-6ea53f721c11 | button | Correct dimensions | PASS, FAIL, N/A
0df04347-5c13-5050-9ac8-7641f7ce81ec | button | Additional stirrups at penetrations | PASS, FAIL, N/A
| checkpoint | Vertical
b14e86e2-a338-513c-9eb6-e5135990cbfe | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
1fc6b2c2-80ad-55a8-a8b5-e5c4689ff927 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Horizontal
e7abacfb-76b2-50d5-a05c-0657cf751eae | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
5f16e16b-22d9-561a-a721-62d1ad76c361 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Bottom mat
e170ef8e-24de-561f-93d8-6bdbec2c6f82 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
11c39f3f-ef36-5e73-89e8-b8364d50deab | button | Correct laps | PASS, FAIL, N/A
9e5a6de1-4437-5aed-88c2-ff702fa87949 | button | Support chair height/spacing | PASS, FAIL, N/A
| checkpoint | Top mat
e65e0e71-a3fe-58be-8879-e75a7a6b0bd3 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
7f73d6b0-2f19-5f6d-8dd9-76e3d7014b6a | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Starter bars
c15a5187-513c-5e41-a45f-d53ef07f39a2 | button | Protruding laps vertical/horizontal dimension | PASS, FAIL, N/A
74577f95-bb7a-551a-b094-0ad99a40333f | button | Exit point correct | PASS, FAIL, N/A
ab1609e0-511f-53c2-82e1-2ec612edc22c | button | Secure | PASS, FAIL, N/A
| checkpoint | Concrete cover
e3695d96-95da-5834-8fb0-1d8bc3b9fe78 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Other
b772a2ce-648c-5fb1-8fd6-a0f1a7124b62 | button | Couplers/terminators | PASS, FAIL, N/A
172df749-4fb8-508b-8471-7db1cf73395e | button | Structural steel | PASS, FAIL, N/A
5975cc55-d4d3-5cd0-b048-928e07e3d5fd | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Pile Caps |  | Pile Caps | b2409e06-348b-4839-a91c-4d79956b966d
| section | QA
| checkpoint | Delivery/material check
ed015660-0f23-5cff-baa2-8ca227628f24 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
4f6a328d-afcd-5d4f-ac44-a43e64a5b978 | button | Pile cap reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
0d276863-325f-535f-ad94-d780ef925e62 | button | Safe | PASS, FAIL, N/A
54d5a1ca-30b6-5f3c-9701-43efa9192708 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Pile caps
62d5ccea-eb2c-5bd1-b215-70616f001059 | button | Pile starter orientation is correct | PASS, FAIL, N/A
eadd44c1-5134-54f4-9411-cf413811119c | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
f5eeb1a9-10ef-55cf-acc9-66429c5cfb40 | button | Welded hoops | PASS, FAIL, N/A
b1e69556-1a33-5e4e-9a74-974147e12b61 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
798248b8-c1f9-5972-bfb1-897643636e22 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
a7b7ff6c-afc9-5f22-b30e-a676a318ec85 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
919ad067-7011-5260-a1cb-e6f798f09ce1 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
| checkpoint | Starters from PC
1651b376-4cd4-521a-927f-bba00839415a | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
27923ade-3e06-571f-9573-030f9d862292 | button | Sufficient protruding lap | PASS, FAIL, N/A
31db4e40-11db-59fd-ad3b-319cb3b82d9d | button | Starter set out and perpendicular | PASS, FAIL, N/A
1eb1c3f7-9386-531e-bdd4-e60f1684b9e8 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
15081235-23d5-528d-aa43-00c37654ea79 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
a1ceefcf-9ad0-5cba-9648-5a704ce0a357 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
4c06ddc3-35f9-536e-9a7a-1308403ba747 | button | Structural steel | PASS, FAIL, N/A
572a6fc0-34a1-574b-a883-a00d621d5c42 | button | Cast-ins | PASS, FAIL, N/A
345b85b4-e562-5302-85f5-28a5a067ca36 | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Stitches |  | Stitches | c6b553a1-8d41-43e6-bc61-165c2acce7bb
| section | QA
| checkpoint | Delivery/material check
179dbf08-75f4-5f52-8db9-ef47755b31f6 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
4c2e5a08-eed3-5802-85e5-7de8c5ffea9b | button | Safe | PASS, FAIL, N/A
51d36ed3-d832-509c-a150-bd105e7d3a3d | button | Set out | PASS, FAIL, N/A
8a9002a9-34cc-506b-a890-9170cb272885 | button | Starters from panels protruding from panels as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Bar
fa263c3f-0088-5efe-9ef1-4cd1c9a5d882 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
2f13773a-7927-5a05-b366-457811d65abe | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
eb14cd6f-ca52-5457-8e84-7a5af31bd788 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Concrete cover
dab86557-38e0-5e6b-9e65-7cc0d46c7802 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
8c36811b-235d-587c-b253-9ce736445781 | button | Structural steel | PASS, FAIL, N/A
cc796d1c-9507-54ac-aa4b-7e94d0f52145 | button | Cast-ins | PASS, FAIL, N/A
deb26d2e-4e20-5071-81c8-9d26f59ce6e7 | button | IMBMS/Reid components | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Suspended Slab |  | Suspended Slab | cabaa3ca-ca0a-4649-8d97-61505d8b1d86
| section | QA
| checkpoint | Delivery/material check
d1cb5640-b54e-58c3-826f-ce6b3d69760a | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
540f46a1-f007-5158-bbcc-73ce23bb5b5a | button | Safe | PASS, FAIL, N/A
43cdad11-4c7d-55b4-a645-ac40581b90bc | button | Setout | PASS, FAIL, N/A
| checkpoint | Slab reinforcing
9124cd43-b6eb-580f-986a-5dec662c2905 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
14dbbb46-2221-545b-a838-f1717ace2119 | button | Laps | PASS, FAIL, N/A
ad32e234-3091-52ba-bcfd-bbb2d4a25a67 | button | Saddle bars - Staggered UNO | PASS, FAIL, N/A
0f2ca070-13fb-50be-a78f-fa8d9a904768 | button | Drag bars | PASS, FAIL, N/A
8abb7033-3dff-563d-8f74-7b5aee1c064a | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
b5170b73-c4f7-5c91-bf41-dc382ab9d860 | button | Comflor - fire bar in troth | PASS, FAIL, N/A
89e2f722-b73c-559a-8878-d372b93b36ed | button | Bend down starters/screw in starters | PASS, FAIL, N/A
f6678671-9fe5-5216-8e80-b2a4829f8c5c | button | Starters other e.g., wall, nib, vertical | PASS, FAIL, N/A
| checkpoint | Concrete cover
d35dfa7a-99e0-5f1c-a780-5ddd87a0a368 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
e160c0e4-5689-50b5-af31-9a015c85caef | button | Top cover | PASS, FAIL, N/A
| checkpoint | Miscellaneous
75f5d2d1-4b3f-5064-9bfc-0e8403c27f0b | button | Couplings/fittings/IMBMS/Reid | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Crane Base |  | Crane Base | d547832d-e4eb-4036-bdcd-eab190771b34
| section | QA
| checkpoint | Delivery/material check
b2bd35d4-7e52-562a-9394-a2b4732b44ea | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
237f301b-2eed-5770-a603-8296e96e49a3 | button | Safe | PASS, FAIL, N/A
4607b5f3-51e4-51d9-a477-98fff7a5a7bf | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Piles
bfb8acc5-0a66-5790-a12d-1a1166d8f262 | button | Starters perpendicular | PASS, FAIL, N/A
2126f745-d910-5377-997b-3b59219aec57 | button | Piles - Cut off height & linished | PASS, FAIL, N/A
76659532-e0b4-5d2a-ae08-94c77fab8535 | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
98dd300d-5f74-58c4-82fa-669bae33cef1 | button | Hoops/spiral installed with correct diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Bottom bars
1569b761-1b5f-5790-af3c-3db6569d4151 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
fc506a98-f684-52c9-a8ab-94e64c52ac7b | button | Correct laps | PASS, FAIL, N/A
8fa037bf-840c-5f91-878a-7aeeea0762da | button | Staggered laps | PASS, FAIL, N/A
ca26e1d7-a4b5-56e7-bbe5-e0b558e91755 | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Top bars
880120ae-f355-5b63-960c-c2c685a42a9a | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
7c1a03b8-c1ac-57f9-aecd-d5ce710c6aa8 | button | Correct laps | PASS, FAIL, N/A
729e52b0-fcf3-530f-98e8-f17951c22f6c | button | Staggered laps | PASS, FAIL, N/A
84c7057a-9406-50cd-b5fc-02e52b2f9795 | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Side bars
cdf76422-15ff-5f21-a24a-d0ad33f3e206 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
d301abf8-2b6b-5cdb-ad73-04382351b496 | button | Correct laps | PASS, FAIL, N/A
510b623e-6251-5c74-ad59-f0314b0aa4ef | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Stirrups/links
a2a1a1bb-3c85-54f0-a299-adabbfbe9011 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
e86a991f-df3d-508c-a05a-214aba4770ae | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Starter bars
4468b834-1ca3-56ab-a951-d216d270384d | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
58e3564e-bbbc-549f-b11a-c009eac9869e | button | Sufficient protruding lap | PASS, FAIL, N/A
| checkpoint | Miscellaneous
6cb4a532-eaf7-5c36-bc7b-0b39bffe5c5a | button | Cast-ins/Crane legs | PASS, FAIL, N/A
| checkpoint | Housekeeping
a6297d95-7c20-586a-9257-d1e0172ed772 | button | All loose items removed off workface | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Typ Foundation GB & Pile Cap |  | Typ Foundation GB & Pile Cap | e1973ca6-e198-4cd9-84e0-be64794d71f4
| section | QA
| checkpoint | Delivery/material check
6ea3fd7a-06fe-5e49-acf4-24cf6b8f6f08 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
e24c9985-f22a-57db-b37a-87c07975d899 | button | Safe | PASS, FAIL, N/A
e0388e97-b784-58b9-aca1-3a8ce810410b | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Pile caps
44b949c2-5bf0-5a32-85ad-45082dbd5e15 | button | Pile starter orientation is correct | PASS, FAIL, N/A
bc434283-39e5-5f19-94dc-9b2ce2f40ad5 | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
7ad55a4b-0fef-5a55-9448-987da0945c5b | button | Welded hoops | PASS, FAIL, N/A
4fcacf2a-018b-5ee8-9790-adbca7382f01 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
5457ee52-4bcb-5e16-a48a-a34861f84ffd | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
ac042e88-a67a-56aa-9ea6-e3bfe49c3f24 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
28ccf0ed-a4e8-5e49-9e8f-523379af111f | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
| checkpoint | Beam
6edc75b4-b4e4-599e-88d1-10fee8e0d43d | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
83a96aca-6aa0-595a-8007-cdd4f8a993e7 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
3c47313f-f1cb-580a-adf8-a348c74e4e83 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
61705122-fd5d-5881-9ebc-e4b150262569 | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
409b08d8-1d98-56eb-afd4-9b8bfe336038 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
349f946c-01f9-590e-b4fe-003c3199e1e3 | button | Additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
f4b58b3a-af4e-55e2-8194-3e4f5253158b | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
ff857aa1-ef02-527e-8b10-022152c47f74 | button | Sufficient protruding lap | PASS, FAIL, N/A
67f25ffe-0808-5fae-8dc9-11b09a1d1e71 | button | Starter set out and perpendicular | PASS, FAIL, N/A
b7426a99-9e6a-5c7a-97a6-785da946adc2 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
0900c347-22f7-569f-8584-113baa2785c8 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
2c1fa909-7a79-5bdd-b97a-cefcef207e71 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
b75b7b43-daea-512c-9ae9-02b069495311 | button | Structural steel | PASS, FAIL, N/A
ccc04b0d-3935-5d84-a6bd-4b59b8f135cb | button | Cast-ins | PASS, FAIL, N/A
98ed82ac-6cf5-5fa2-949f-6316d8ee8354 | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Shear Wall |  | Shear Wall | fca7807b-c8b3-4ec4-9fd4-16b47617ccd9
| section | QA
| checkpoint | Delivery/material check
0be003d4-5aa4-5519-9c25-90ae020a92ed | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
95294b12-78ee-5080-b731-04ee8e37dda5 | button | Safe | PASS, FAIL, N/A
620bb75c-beb6-5530-b6f8-7af41e3aa931 | button | Setout | PASS, FAIL, N/A
| checkpoint | Wall verticals
5c438e8a-0eb7-54f6-995d-324a508702a8 | button | Starter height, bar diameter | PASS, FAIL, N/A
1b1c5194-db07-56e8-a685-e1f68a950200 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
4402adcb-e252-5e17-861b-b99d3150d605 | button | Laps | PASS, FAIL, N/A
| checkpoint | Wall horizontals
0bde70ea-b858-5872-90af-2c3c23c01b92 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
3a78137b-cad0-5af1-8659-549a4b42dfcd | button | Laps | PASS, FAIL, N/A
| checkpoint | Stirrups/Links
0f29ab14-aae7-5389-af8b-2000168766b2 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Miscellaneous
4500a8b6-5888-56ac-95f4-d4f97547b3c8 | button | Structural steel | PASS, FAIL, N/A
0776ac64-a480-56f7-8d37-8d973267d125 | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
7c9d76a1-c4df-5f6e-9eac-68fb464d751e | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | 1st handover for cast-ins
aa840340-a04d-50b9-a2da-ada1e17c4cca | button | Reinforcing around cast-ins secure and to spec | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy