## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Slab Ground (Bar) |  | Slab Ground (Bar) | 06df5908-45d6-4b17-9df5-a7e37a25b2cb
| section | QA
| checkpoint | Delivery/material check
7f0b7d29-249c-5d9e-8b61-483872a80b2a | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
c36e994a-04c5-5771-b890-a9ab0211de4a | button | Safe | PASS, FAIL, N/A
fe1cb4f8-cd41-5649-8c6f-c3a31aba7902 | button | Slab grade RL checked | PASS, FAIL, N/A
449f735e-934c-5e26-9ce4-55af4926f5d8 | button | Setout | PASS, FAIL, N/A
| checkpoint | Slab reinforcing
2c4ac251-4696-5c56-a746-c39ae155623b | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
94d971e1-8cda-51ae-9d76-a8f0d325b0ed | button | Chairs with height check | PASS, FAIL, N/A
0110c0d7-06c2-5892-b0b4-984c4ba73994 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
b259f38d-506c-5072-8444-a5c61f4781f7 | button | Correct laps | PASS, FAIL, N/A
f9aa16d0-691a-52bf-8bd9-01984fda36a2 | button | Additional bars | PASS, FAIL, N/A
a38450e5-2e49-5a16-b8f6-7c67b2e2cbf3 | button | Saddle bars | PASS, FAIL, N/A
30b0f019-a9d6-5b56-a066-0c38127c53d5 | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
81b89f69-30fe-56b2-b708-fa5a3d401d02 | button | Bend down starters/screw in starters | PASS, FAIL, N/A
1a7fd198-1e3e-5d28-ba7a-a648f8e9e548 | button | Starters other e.g., wall, nib, vertical | PASS, FAIL, N/A
| checkpoint | Concrete cover
15e75ba8-5cb4-5a25-97f9-f890a342ab96 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
abbc7360-367c-550f-9310-a2a7edc1eb82 | button | Structural steel | PASS, FAIL, N/A
bcd7ad00-21b8-501d-8968-feb61ebeca35 | button | Cast-ins | PASS, FAIL, N/A
c1cbf936-7f89-52f7-9c28-09fc852e8230 | button | IMBMS | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Lift Pit |  | Lift Pit | 0e1f6416-8d0d-4f32-b131-66541e865ce5
| section | QA
| checkpoint | Delivery/material check
eb097bdc-5df6-5386-b901-bb4ba4d84eb8 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
ee9b46d1-9b28-5eee-823c-44fa09f57905 | button | Safe | PASS, FAIL, N/A
ef206c93-1200-5bf3-b648-e515168da0b0 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Base slab top & bottom
7ebae822-d2e8-57fc-be0c-494a29fe807e | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
da7a515c-cbb7-591b-9fcc-318ad23df8d0 | button | Links diameter/grade/spacing | PASS, FAIL, N/A
5b7729fc-14b8-5c7a-bc75-59760a5d1775 | button | Correct laps | PASS, FAIL, N/A
66b4cbc3-4fdf-5543-b4b9-2b78324507f0 | button | Staggered laps | PASS, FAIL, N/A
04254691-dcfd-5225-aa1d-076fdb3460b8 | button | Sump detail | PASS, FAIL, N/A
| checkpoint | Ground beams
94da3082-e99d-572c-aa98-fc9df192113d | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
16d66dd3-ce4b-519c-98a2-5055f415e384 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrup diameter/grade/spacing
ddcc7a3b-04b8-5b29-a37a-edf1c715efc2 | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Sump
11b0f004-ff1d-5588-9c76-5c11b85d681b | button | Location | PASS, FAIL, N/A
6494444f-8db0-5b65-8db7-d35acceee413 | button | Trimmers | PASS, FAIL, N/A
| checkpoint | Starters
96de5a2e-4b5b-581a-b941-8f8667cb649a | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
a1f64442-cf43-519f-841c-f931606ae31f | button | Sufficient protruding lap | PASS, FAIL, N/A
f0615022-99f4-5a1f-823f-7476f9c50117 | button | Starter set out and perpendicular | PASS, FAIL, N/A
fb699667-563a-50b4-803a-f83061c02541 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
2d8d13d2-9b80-525c-9c51-6896fb574d1a | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
f9d733c7-1f45-52be-a7bf-bf87431ca822 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
88de983a-1b2b-5cbf-9093-311bfe91c52e | button | Structural steel | PASS, FAIL, N/A
c7856793-1a06-5085-b801-9a3d7eda0ea9 | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Stair Landing |  | Stair Landing | 1751e2a9-360b-40ba-89f8-17279eeb10fa
| section | QA
| checkpoint | Delivery/material check
c5df0294-0c7e-5e33-9390-38ab3396c6b7 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
ebcc3b25-9e48-5db7-b457-ab968a3ac26c | button | Safe | PASS, FAIL, N/A
bfab2618-8003-575e-a5d9-1b9a4c0b2e62 | button | Setout | PASS, FAIL, N/A
dd772636-b47f-5b7b-a73c-44c48eaa1aa4 | button | Starters from panel/slab/wall pre-bent & straight | PASS, FAIL, N/A
cd78834a-8aec-5dec-85d3-2225ad7aacf6 | button | Panel/slab/wall coupler inserts have are clean and at correct levels | PASS, FAIL, N/A
d1cd2307-0e2e-5840-97d4-8bf3504e99a7 | button | Correct type/size | PASS, FAIL, N/A
| checkpoint | Stair landing reinforcing
6d238e31-71d5-56a5-9f9a-8483872ea0dc | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
93355e12-e857-5313-b8d0-575936fe4628 | button | Starters screwed/bent down, and epoxied if Reid | PASS, FAIL, N/A
cd59a49a-b848-53d7-9f4b-f3af5fe5ca64 | button | Correct laps | PASS, FAIL, N/A
4c6fc1ad-42d8-5d79-90a6-b68ed774b216 | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
| checkpoint | Concrete cover
469d6a3c-0193-50a1-b2ce-1a3c08f402ed | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Ground Beams |  | Ground Beams | 29cab0f7-4eab-4491-98d2-e3a5e1722d13
| section | QA
| checkpoint | Delivery/material check
245fdb95-86b6-5015-99f2-b262ba7267ca | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
9042c685-1299-5bd5-8326-bddeb45a1b53 | button | Safe | PASS, FAIL, N/A
f98ff51d-5174-5955-aca2-65412fc08e9f | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Beam
01cf332d-651e-521f-b459-4e22a7b4dc06 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
fd2ddcab-459e-5f2e-818d-c8d7b5489bb3 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
f39cdc89-6dd9-50eb-9ee5-027200ef45f2 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
08fa7262-7e52-57b7-ac85-ec5206ad1667 | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
963ea71f-b1cc-57c1-8cf7-e8b3c9238b9e | button | Development length into pile cap | PASS, FAIL, N/A
c99ef640-c3fc-5d43-b081-79547bf3f2a1 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
7c69eb39-3175-5560-9d74-3ef066b3fade | button | Additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
fc289efe-936c-5821-895a-b909de76b798 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
3d056ff3-2eac-5f43-b8a9-98f990ccd157 | button | Sufficient protruding lap | PASS, FAIL, N/A
4d3e9186-d9c3-59e9-bb8b-b2a653e24b96 | button | Starter set out and perpendicular | PASS, FAIL, N/A
67ea0caf-4b7d-5d79-b314-1ae3a1e0603f | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
758c61c1-f64a-5b08-9a32-8c2548a94b87 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
9cc278a4-1d59-5d2f-870b-c9f2bf456b8b | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
d9521cbe-eda4-572f-9063-636f60c053e8 | button | Structural steel | PASS, FAIL, N/A
b0d1ec37-b2ff-58eb-acae-40e6b3619779 | button | Cast-ins | PASS, FAIL, N/A
f582c9a7-d483-5bef-adb3-621e389056d0 | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Miscellaneous |  | Miscellaneous | 5521e358-5ce7-4778-81c2-f950a13082ab
| section | QA
| checkpoint | Element/Description
e8f0127b-ee48-5eb0-a82a-51e19b7e5158 | button | Element/Description | PASS, FAIL, N/A
| checkpoint | Delivery/material check
6536b0a7-5bcf-52d3-9251-3abf2c65e924 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
9fa77b4f-e24d-59cc-8a12-e2c517de0a63 | button | Safe | PASS, FAIL, N/A
a2325f1f-5c7f-5e4f-849a-28e88621c457 | button | Set out & RL checked before proceeding | PASS, FAIL, N/A
| checkpoint | Top bar/side bar
4ca611e5-5601-5584-ad4c-f8bf466a2f78 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
c887ce1e-a47e-5a08-b27e-8bd003080025 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Bottom bar
54d047fa-0877-5c2d-b655-ab972ed84c6a | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
202ccbbf-7346-5048-a9a0-cda07e6ab18f | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
4f9c2120-869b-523b-8867-18d745aeac4c | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
0f3d9371-0568-536e-802b-146d49174e9e | button | Correct dimensions | PASS, FAIL, N/A
60d72875-b1c0-5e5d-8541-99cbb53a5e1d | button | Additional stirrups at penetrations | PASS, FAIL, N/A
| checkpoint | Vertical
f554c26b-d707-5a07-99fa-c8946bb19c8b | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
3a696d4c-ae1f-52f1-8177-08ace479c694 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Horizontal
63bac541-014f-57ab-8f7d-c5185ef42503 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
882ed4d8-e10f-531a-a171-a5944d3e1af4 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Bottom mat
8fbf47f4-0075-5624-9cfa-d91a1cf8388c | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
3da37889-e907-5e40-aaff-978ca0c74295 | button | Correct laps | PASS, FAIL, N/A
7d8c1a0c-7f9a-5d77-b67a-77d339cacb81 | button | Support chair height/spacing | PASS, FAIL, N/A
| checkpoint | Top mat
c609c6bd-25cf-5a3f-8a52-1e0568f4d9a3 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
230a87e2-a005-53f6-bf6b-7e122bb6d48e | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Starter bars
c217471a-7d54-581d-8d8a-7c06814e5ec8 | button | Protruding laps vertical/horizontal dimension | PASS, FAIL, N/A
ea20e1ea-7124-5e61-9f83-7d346a4e9c9f | button | Exit point correct | PASS, FAIL, N/A
a968ee5c-09e6-5655-80a4-09d5f93814ee | button | Secure | PASS, FAIL, N/A
| checkpoint | Concrete cover
43887aef-d855-5eed-9455-eaaccc77e015 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Other
9955b0fd-19e6-5494-92d4-5d7e5fd55b5f | button | Couplers/terminators | PASS, FAIL, N/A
fa19d30f-212b-5ad9-a76d-ff1ffeaf7fae | button | Structural steel | PASS, FAIL, N/A
934b12c0-f7dc-5669-9050-beb5836d63de | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Suspended Slab |  | Suspended Slab | 6a4bf108-2853-41bf-9d92-47e030135d25
| section | QA
| checkpoint | Delivery/material check
0b2caa04-1df7-5662-946e-22d97a9a6444 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
707bcbcf-cf7f-572d-9788-340f9c61ab92 | button | Safe | PASS, FAIL, N/A
c084d911-fb14-5273-a9bb-537dbf1e8d55 | button | Setout | PASS, FAIL, N/A
| checkpoint | Slab reinforcing
d47479ab-80f2-5c7f-ae4b-b0573d3d63c4 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
b5eafa69-bcee-5e93-9727-454e9fc0f3bc | button | Laps | PASS, FAIL, N/A
cf88f85f-4ea4-5d9a-982f-727c3f36c52f | button | Saddle bars - Staggered UNO | PASS, FAIL, N/A
66aa28bc-b590-5ac8-aeef-461884d6dcee | button | Drag bars | PASS, FAIL, N/A
4ce38b9c-b432-5a84-93b3-bcce1bf0b2cd | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
53924ad4-9ff8-58f6-bc0e-f884d1fe7234 | button | Comflor - fire bar in troth | PASS, FAIL, N/A
b8c89843-0ca3-5b18-9adf-d9f06ba82cdd | button | Bend down starters/screw in starters | PASS, FAIL, N/A
29a631ea-16b9-584c-bf7b-9d51887ee5a6 | button | Starters other e.g., wall, nib, vertical | PASS, FAIL, N/A
| checkpoint | Concrete cover
70c64933-7aa4-5267-a9cd-ec52fa9883af | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
e149223a-7545-5f5e-8c95-601a3f43daf4 | button | Top cover | PASS, FAIL, N/A
| checkpoint | Miscellaneous
8e05938b-6ba5-5887-a2ba-3033a6d2072f | button | Couplings/fittings/IMBMS/Reid | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Crane Base |  | Crane Base | 81d3b715-3af7-4884-8115-499b9d0ab4da
| section | QA
| checkpoint | Delivery/material check
e4d67ae5-dca4-54ed-a4f7-d915530682a2 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
67672be9-8c35-55df-9de5-30050de55a87 | button | Safe | PASS, FAIL, N/A
ac729d8a-4663-58d7-89bf-6ad70468ea23 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Piles
d9160d83-c77c-5eac-9c7f-453013397ac7 | button | Starters perpendicular | PASS, FAIL, N/A
802ebb15-41d4-561a-b440-dcffeb7d5af1 | button | Piles - Cut off height & linished | PASS, FAIL, N/A
63fe9f55-790d-5f23-ac1b-ef4cd3be9259 | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
baa6ecd4-e375-58c7-a452-78a9edaca06e | button | Hoops/spiral installed with correct diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Bottom bars
643673bf-935c-541e-84a1-bd43c9344914 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
e6bc2791-02e5-5846-9e5e-79ff7a38f44c | button | Correct laps | PASS, FAIL, N/A
890a1e8f-09d8-5350-a426-732f1ea2a7b0 | button | Staggered laps | PASS, FAIL, N/A
2bbf3960-5cfd-5f3c-a766-e1a918ff5646 | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Top bars
ca54932a-b51d-5924-bdf6-552f5a06713b | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
f3e933f9-cdb4-5280-bd80-45f1a6d4b735 | button | Correct laps | PASS, FAIL, N/A
f6fba310-575d-51e9-9a03-663ece5aeffa | button | Staggered laps | PASS, FAIL, N/A
0f0695fd-c63c-51fb-bd8a-0249c9f47add | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Side bars
32316a6f-2825-57a4-b215-3dabc38c9707 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
67a713dd-c864-596e-ae95-b46da9537d6f | button | Correct laps | PASS, FAIL, N/A
22305aee-a745-5126-8c60-201ae9a335fc | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Stirrups/links
c642e290-3a21-5243-9caa-9c2459bcfea8 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
c14e0c1b-ceed-5285-891b-45ca29d58303 | button | All bars adequately tied | PASS, FAIL, N/A
| checkpoint | Starter bars
5be0daa0-7bf1-50d5-a1b7-93aca3ba99d0 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
2198c298-b688-53f3-867c-1014ab8bbd48 | button | Sufficient protruding lap | PASS, FAIL, N/A
| checkpoint | Miscellaneous
b3b76201-f30c-540c-8edf-58f4a59d7391 | button | Cast-ins/Crane legs | PASS, FAIL, N/A
| checkpoint | Housekeeping
9acfc724-5a69-5e13-9664-3b805dfc4e2b | button | All loose items removed off workface | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Suspended Beams |  | Suspended Beams | 8b591611-c869-4caf-96f3-157198654b56
| section | QA
| checkpoint | Delivery/material check
ab786668-dac5-52ff-8fa4-019c9546bed2 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Prestart/area acceptance
1fe53fc0-a8de-5ef9-a210-7a0c18182a2e | button | Safe | PASS, FAIL, N/A
e25166a4-0c27-5092-9303-c5ed47af7220 | button | Soffit ready | PASS, FAIL, N/A
828e724e-ca4c-545d-9914-5dfb81d5d82c | button | Setout | PASS, FAIL, N/A
| checkpoint | Beam
b2eed987-50df-5c1e-8a39-9085fc24c271 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
858d5ec9-84bb-5b1c-ba5d-b57eff0103b4 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
d09a27ba-19e3-5ced-b4e1-d2b4d6d6b801 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
cc15b27f-4657-5baf-ac72-a0d83583d2db | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
79fc7de2-003e-5f6e-ae39-71ccbea6fa43 | button | Development length into pile cap | PASS, FAIL, N/A
a4998372-bf5c-5a47-baef-3024a4b20858 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
55fc0130-a04e-5861-b1ad-c93df614cb64 | button | Trimmers/additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
9e16d0d4-cfd9-5b08-b05f-5c0aba491a8a | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
66bea394-3743-52bc-a858-96f644e2c5e7 | button | Sufficient protruding lap | PASS, FAIL, N/A
a62001b9-31bb-545e-ad76-bb7b7caa080c | button | Starter set out and perpendicular | PASS, FAIL, N/A
b5555471-18c2-52fe-be95-686f7f647dad | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
bbd14e6d-ce40-5345-9868-9d816b00611b | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
284715f8-c73a-5361-82b0-627d7bef5d24 | button | Structural steel | PASS, FAIL, N/A
63889913-ae71-50fd-86f6-6cfaf2a4d0d1 | button | Cast-ins | PASS, FAIL, N/A
0fe7d469-e215-5227-9c75-555a1f9694d4 | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Capping Beam |  | Capping Beam | 94246cd9-8df3-42ca-a568-5402886faac5
| section | QA
| checkpoint | Delivery/material check
e8e8f33e-b834-586f-9186-a3781a5f6be4 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
0fbbfb20-5fe0-5a28-894f-cd4806b45ee1 | button | Safe | PASS, FAIL, N/A
1731c161-7644-5210-b524-b9ccf92c0fdb | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Piles
39bf33a9-56ea-53af-9bb7-57ef17ed063e | button | Orientation | PASS, FAIL, N/A
18e944b7-0b02-5f57-a664-1e34884fe057 | button | Correct height | PASS, FAIL, N/A
35fdc16b-0f29-554d-aeac-61207b5d7578 | button | Hoops bar diameter/grade/spacing | PASS, FAIL, N/A
1b8582da-9260-5f4d-b6db-635a80d452b1 | button | Hoops welded laps | PASS, FAIL, N/A
eb81adeb-719d-55f7-a407-2026ed4d67ae | button | Footplates on starters - Reid or IMBMS | PASS, FAIL, N/A
| checkpoint | Beam
4fce58c2-823f-5e03-aa2f-ae42268b582f | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
8b9e4a67-0ee0-51ff-9bff-bbd38c470871 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
78dad68e-d46b-5232-8754-2ce2bce61a00 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
7c11fc3a-0c4e-575c-a881-852ab8f4a3a5 | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
d17b3230-0980-5459-9e7a-28c22ad9ad14 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
e6e4efd4-b12f-5233-b7a5-45dd4031494d | button | Additional stirrup at penetration | PASS, FAIL, N/A
78b2d77a-2847-5add-b2f3-349ec1cd6a27 | button | Anchor details | PASS, FAIL, N/A
| checkpoint | Starters
b4b52f51-873d-54ce-97b6-7a090e200d23 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
dd225cb2-de53-502d-a50c-06bf3457f1e9 | button | Sufficient protruding lap | PASS, FAIL, N/A
3ef431d9-b9d5-56c7-a2d2-1705a6899674 | button | Starter set out and perpendicular | PASS, FAIL, N/A
87a3f742-23e3-5ccc-9269-1965e2f974d9 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
65f2a671-7259-5fd9-a09f-a94c26e73184 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Typ Foundation GB & Pile Cap |  | Typ Foundation GB & Pile Cap | 955a5f0a-b93b-4a6f-9bd9-7d05cb894c32
| section | QA
| checkpoint | Delivery/material check
b11b0637-798e-5d29-ad8f-252d88873baa | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface Acceptance
eeb7ba2a-ad2e-5bd8-9bcc-f6b543af3b5f | button | Safe | PASS, FAIL, N/A
74dcb744-28f8-500f-a4b9-b02d7c76ed54 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Pile caps
654e74c4-159e-5e97-b1c6-9a1032971c40 | button | Pile starter orientation is correct | PASS, FAIL, N/A
52add566-312c-5293-845f-1d11aad23532 | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
50c37e38-6802-56c8-8599-6884507b130d | button | Welded hoops | PASS, FAIL, N/A
70120683-c7b6-5228-af71-df08dc13236b | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
e58e6d50-5eb7-5e1d-bf66-7ae19f50f5ac | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
039e819c-dc1e-57ce-985d-29605b81df08 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
7ff1d604-dff3-5e67-8fc0-c9775f2db09d | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
| checkpoint | Beam
6d0f2596-c364-55e1-9a71-ad7015e722aa | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
8045ea84-566d-5e11-9ad1-0743cc3415db | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
067258b8-00a3-5966-a7b4-8a0b27177723 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
50ee7f63-dd67-57b2-9acd-5a8f4dda89b6 | button | Correct laps top/bottom/sides | PASS, FAIL, N/A
46b0a187-a161-5ef5-b43c-0bc10b996dbc | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
8aef2cfc-0be7-5b08-9884-b7b52e8f4cc3 | button | Additional stirrup at penetration | PASS, FAIL, N/A
| checkpoint | Starters
1ad13e5e-30e9-5f79-b27f-c3a0cc1f31e6 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
c364782a-695c-5cd6-8f5a-1d874ee538a1 | button | Sufficient protruding lap | PASS, FAIL, N/A
b0af5e6e-a6df-513a-af88-4308daa5d3b7 | button | Starter set out and perpendicular | PASS, FAIL, N/A
b3b6dfae-f515-5a56-8924-4cac2348389b | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
21570de5-2c1e-51b9-b958-9f21dccdd8e9 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
2c1c3759-146d-5b10-9ff4-1d16f5cc7d01 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
92ed763d-9088-52e1-bcc3-494ea626378c | button | Structural steel | PASS, FAIL, N/A
c7f14594-d401-504c-ba01-2a381784ec68 | button | Cast-ins | PASS, FAIL, N/A
9211b2db-a04e-5812-aa65-2385735e6cef | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Pile Caps |  | Pile Caps | a10cb619-6a00-4ad1-a6db-95ac9baa87cd
| section | QA
| checkpoint | Delivery/material check
843c04da-4f9a-5594-a04a-aa5ffcbc9f3b | button | Detail sheet & drawing reference | PASS, FAIL, N/A
adda98fb-c07b-5626-86cf-3637db18445d | button | Pile cap reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
04ce6a23-2cf4-5c39-872a-f8e8fe5b8d8a | button | Safe | PASS, FAIL, N/A
94b4ba9f-d8a0-51d3-82bc-6a52f04526e4 | button | Blinding levels correct/waterproofing/setout | PASS, FAIL, N/A
| checkpoint | Pile caps
a0cde26a-7af4-53e9-9503-6d7679ee421a | button | Pile starter orientation is correct | PASS, FAIL, N/A
c1b7e68f-9f93-57fa-8026-2aea542bbfe7 | button | Footplates on piles - Reid or IMBMS | PASS, FAIL, N/A
2843f2fa-823f-5e92-8feb-c3f0824c8b5d | button | Welded hoops | PASS, FAIL, N/A
56516359-cc19-5d98-ac61-7f43a9145465 | button | Top bar diameter/grade/spacing | PASS, FAIL, N/A
4bd65bc0-4bc7-56f7-a88a-d36b0a657214 | button | Bottom bar diameter/grade/spacing | PASS, FAIL, N/A
e9d134a7-3463-5b7f-be1f-6dd20fe6d6c7 | button | Side bar diameter/grade/spacing | PASS, FAIL, N/A
fdf18502-2674-59c7-a954-e18c1a9fcff4 | button | Stirrups/links diameter/spacing | PASS, FAIL, N/A
| checkpoint | Starters from PC
2a081b7f-8915-533e-b6b8-1d375a4a51f8 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
32a3ef74-983c-5e7d-8800-6dec44d48df9 | button | Sufficient protruding lap | PASS, FAIL, N/A
9f2ab93b-f1a2-5d51-8e1d-f6fb0c20a462 | button | Starter set out and perpendicular | PASS, FAIL, N/A
0e33d7d0-d8bf-536c-a370-4652d6ef5131 | button | Drossbach template installed for panel starters | PASS, FAIL, N/A
cf90aefb-2af7-5c7c-a60d-ae5583e254b6 | button | Couplers in lieu of starters | PASS, FAIL, N/A
| checkpoint | Concrete cover
ad709b1e-a9d4-52d2-b23c-960f0d198c87 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
d18b7058-7568-5108-9801-6fb6d1593e2b | button | Structural steel | PASS, FAIL, N/A
4ad5d563-c990-54b8-ae0d-1e6b5ab3607a | button | Cast-ins | PASS, FAIL, N/A
6ea2c0f0-6dd9-5123-8ed7-727b9610d8b3 | button | Penetration detail | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Stitches |  | Stitches | b99355c7-393e-4d8c-964b-f56859c88921
| section | QA
| checkpoint | Delivery/material check
73d6024e-c16d-5e91-9c9d-f83f2b7a2903 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
f14e7c61-1899-52db-8d52-0dc37988892f | button | Safe | PASS, FAIL, N/A
3edfabe1-de77-5047-bff0-be9211d125ed | button | Set out | PASS, FAIL, N/A
b2eafc11-b6e5-5310-b6e2-57e8da5b7b3e | button | Starters from panels protruding from panels as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Bar
99e4b7d4-50cd-56c1-9c37-48544dd0443e | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
62de54c0-5698-59a7-8884-513d32d507ba | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
735c7f2c-52fb-5628-8ad2-ec2df9cac592 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Concrete cover
a290106f-08d0-5baf-9643-19199812dbb0 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
e9ec73cf-e878-5c4b-8053-ac0b85315999 | button | Structural steel | PASS, FAIL, N/A
003d8372-d2a6-5927-a20f-9d2596e0b194 | button | Cast-ins | PASS, FAIL, N/A
d71e85ea-145a-52f9-b913-7fdfcf1ce5bb | button | IMBMS/Reid components | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Shear Wall |  | Shear Wall | c6de9cb4-56c2-4821-b7d1-30143912445c
| section | QA
| checkpoint | Delivery/material check
b5dfd43e-4e9e-5ba6-9d5c-6ee35026fe7b | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
20823387-db05-535d-aaf3-596328748d78 | button | Safe | PASS, FAIL, N/A
1b54ab96-3d8f-5108-85f4-72dbe23c0a41 | button | Setout | PASS, FAIL, N/A
| checkpoint | Wall verticals
162e9fe6-2270-58ae-a4aa-2438c1f1d7e3 | button | Starter height, bar diameter | PASS, FAIL, N/A
fae242d3-9a46-5603-9ea9-dfe03df8024b | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
9726aea6-f040-5e39-ae13-9b2a546226a2 | button | Laps | PASS, FAIL, N/A
| checkpoint | Wall horizontals
44214537-bd64-50f0-aef2-bf7c553534e5 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
04caf5e9-f565-5d47-aa4e-3b7f461994da | button | Laps | PASS, FAIL, N/A
| checkpoint | Stirrups/Links
93473837-513f-51d3-a1b3-f2609758ccde | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
| checkpoint | Miscellaneous
b014a6f5-f752-550a-b2bb-c0bfce2489a0 | button | Structural steel | PASS, FAIL, N/A
e8b317cc-c534-521a-a48c-8a7c55d0ab60 | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
4bec2b19-947d-5a98-8dc4-9c7e89286cbf | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | 1st handover for cast-ins
8061c7ac-f612-5758-9502-f5c48d05d34a | button | Reinforcing around cast-ins secure and to spec | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Column |  | Column | eb9f2d4c-1e3e-49b8-ab3c-3c4e2892642b
| section | QA
| checkpoint | Delivery/material check
26fd4fc0-079b-5d60-a659-d516d4508a44 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
9026df79-3e07-58b6-9be1-c2830ee3a59b | button | Safe | PASS, FAIL, N/A
57f43319-64f8-5c56-af41-56940a9db452 | button | Set out | PASS, FAIL, N/A
586f94ce-9202-5d51-9b2b-b5e4bcd737a3 | button | Starters perpendicular (not bent by other trades) | PASS, FAIL, N/A
| checkpoint | Column
ef700a8c-767e-59fb-94f1-a02ea2c3f976 | button | Bar diameter/quantity/correct protruding lap | PASS, FAIL, N/A
d811e4dd-2819-5dd7-bb65-9a26b737d52f | button | Laps to starters | PASS, FAIL, N/A
7bc17e9e-eba9-52f8-8607-133471044470 | button | Couplers in lieu of starters. TYPE? | PASS, FAIL, N/A
59ae08c1-c771-5794-8917-9076ca71da61 | button | Vertical and horizontal laps correct | PASS, FAIL, N/A
48c5d9e4-252b-53cd-a1eb-727ad0e22d91 | button | Stirrups/links diameter/grade/spacing | PASS, FAIL, N/A
b1a8542b-ad4f-53bf-b9c6-3bdc5a611b9d | button | Stirrups/links to top of concrete pour | PASS, FAIL, N/A
bc80413e-cca5-5082-b191-3bc2e9a1e2ca | button | Holding stirrup at top of column | PASS, FAIL, N/A
| checkpoint | Miscellaneous
01228351-e383-56a1-ac37-e96a3cef0d39 | button | Structural steel | PASS, FAIL, N/A
6a7e2713-8915-5b1b-ba8f-7e2ec09c336e | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
e12d14f5-9ed0-5e4e-928f-e33358d9c793 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | PC Beam Stitch |  | PC Beam Stitch | f06dc1ce-3b31-4753-90c2-d90d13dcadb3
| section | QA
| checkpoint | Delivery/material check
7bf5e27b-6e4c-5c40-a564-ad525eb5d702 | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
3582a8b7-4e2c-531a-9f64-08be49633158 | button | Safe | PASS, FAIL, N/A
20df2a6f-af43-5277-ac52-6b3e9a42f63e | button | Starters from protruding from PC Beams as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Longitudinal T/B & sides
c8f9ff92-afe5-5e14-8fc7-51e97ff4bb81 | button | Correct laps | PASS, FAIL, N/A
| checkpoint | Stirrups/links
781014ee-e8a8-5dde-a36c-0e57bb8438b8 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
53e373b9-1f17-5ac6-b339-61c22b932945 | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Concrete cover
4b1670a2-fa2a-5f35-a63b-649ae2beb543 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| checkpoint | Miscellaneous
0177dd79-06d8-501c-a9d7-25e27ecdff18 | button | Structural steel | PASS, FAIL, N/A
8b806cb2-3a0a-5270-8a44-db057120f11e | button | Cast-ins | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy
| checklist | Panel Stitches |  | Panel Stitches | f30b48b5-3deb-490f-98f2-bee26c5902c2
| section | QA
| checkpoint | Delivery/material check
14d85771-faf2-50a5-a032-23a6838f01be | button | Detail sheet & drawing reference | PASS, FAIL, N/A
| checkpoint | Workface acceptance
355918dd-2c59-5b95-8b4d-8127cf2627a1 | button | Safe | PASS, FAIL, N/A
8aa4c4b9-eed8-5b99-b755-d81aa44a63e6 | button | Set out | PASS, FAIL, N/A
4c3a6fd4-507b-5c9f-b286-03c50e9269ca | button | Starters from panels protruding from panels as per drawings/no re-bending | PASS, FAIL, N/A
| checkpoint | Verticals
cda7f369-e8f1-55f4-b709-f712f0a89f8c | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
c03c54de-431f-5b4f-9136-e6f8c8bec1eb | button | Correct level at base | PASS, FAIL, N/A
3193f06c-d724-546b-adb9-3bc3b23a322d | button | Correct length | PASS, FAIL, N/A
926b55ea-9321-563c-a094-d77422309b7e | button | Correct laps | PASS, FAIL, N/A
90c6c5e1-554d-5f0f-9581-b7bfd83f7cb6 | button | Sufficient protruding lap | PASS, FAIL, N/A
19d42216-2620-506a-a5d1-25164c115231 | button | Top cover where returns terminate | PASS, FAIL, N/A
6c04e391-7835-5a78-ba81-8ae1f563dee4 | button | Trimmers to penetrations/openings | PASS, FAIL, N/A
| checkpoint | Horizontals/stirrups/links
2a4a3ab2-1b42-5f34-b7ac-44c18d2d1728 | button | Bar diameter/grade/spacing | PASS, FAIL, N/A
f800bcc6-b40c-5dad-8e9e-9335773afdcf | button | Correct dimensions | PASS, FAIL, N/A
| checkpoint | Miscellaneous
e705d57d-b586-52e0-bad1-60bde963d59e | button | Structural steel | PASS, FAIL, N/A
4e8d5986-581d-5ae1-9373-c909700581b3 | button | Cast-ins | PASS, FAIL, N/A
| checkpoint | Concrete cover
02dd55e8-dcae-51b9-a297-605311a98a45 | button | Cover blocks/chairs/spacers correct mm - CRITICAL | PASS, FAIL, N/A
| section | Review & Handover
| checkpoint | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint | Securely tied and braced
| signoff | Request Review
| checkpoint | Area left clean & tidy