## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-017 - Sealing Works - Asphalt Laying Works | itp |  |  |  |  | ITP-017 - Sealing Works - Asphalt Laying Works
section | 1 - Preliminary Works
checkpoint | 1.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval, Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer/Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least
label | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: 407.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.16 Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 2.3 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.23 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 2.6 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.23 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | For layers ≥50mm, if characteristic thickness is:
label | ○ 96.0% or greater Accept lot
label | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
label | REFERENCE DOCUMENTS: Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/FH Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
label | REFERENCE DOCUMENTS: Table 407.232
label | INSPECTION/TEST METHOD: String Sheet
label | RECORD OF CONFORMITY: Survey Conformance
label | SCP
label | RESPONSIBILITY: Site Engineer/Supervisor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: