## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-079-CIV-PSDS-Unbound Flexible Pavement | itp |  |  |  |  | ITP-079-CIV-PSDS-Unbound Flexible Pavement Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-079-CIV PSDS-Unbound Flexible Pavement
label | ITP Description: PSDS-Unbound Flexible Pavement
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 079-CIV
label | Revision Number: 0
label | Revision Date: 2/05/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 Non Dependent
label | Reference: Reference Documents: IFC Drawings
label | 1.2 Non Dependent
label | Reference: VicRoads Section 173 (10/9/2008)
label | 1.3 Non Dependent
label | Reference: VicRoads Section 304 (13/8/13)
label | 1.4 Non Dependent
label | Reference: VicRoads Section 801 (19/07/18)
label | 1.5 Non Dependent
label | Reference: VicRoads Section 812 (13/07/16)
section | Preliminaries-Materials
checkpoint | 2.1 Crushed Rock Mix Design
label | REFERENCE: Section 304.03, Section 304.05, Section 812.04, Table 812.121
label | ○ IFC Drawings
label | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
textbox | Enter: Teambinder Material Approval number
label | METHOD: Document Review
label | FREQUENCY: Material conformance as per Table 812.121
label | CATEGORY: HP
label | RESPONSIBILITY: NA
label | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries-Documentation
checkpoint | 3.1 Subgrade Preparation
label | REFERENCE: 304.04
label | ACCEPTANCE CRITERIA: Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
textbox | Reference: Subgrade Preparation/Type fill Lot Number:
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: Underlying layer Lot number
checkpoint | 3.2 Select Scale
label | REFERENCE: Project Requirement Specifications, IFC Drawings
label | ACCEPTANCE CRITERIA: Specify site specific scale:
textbox | Enter: Site Specific Scale (A, B or C)
label | METHOD: Document Review
label | FREQUENCY: Prior to Commencement, Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: Sign ITP
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out and Lot size
label | REFERENCE: IFC Drawings, Section 304.06
label | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production.
label | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | METHOD: Survey, Document Review, Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE
label | VERIFYING DOCUMENTS: Sign ITP
section | Construction / Installation Activities
checkpoint | 5.1 Crushed Rock Delivery Dockets
label | REFERENCE: 304.04
label | ACCEPTANCE CRITERIA: A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | ATTACH: Delivery Docket(s)
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Attached Docket, Sign ITP
checkpoint | 5.2 Placement of Material
label | REFERENCE: Section 304.03, Section 304.06, Section 304.08
label | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | ○ At no location shall water pond on the surface of any pavement layer.
label | METHOD: Visual and Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Sign ITP
checkpoint | 5.3 Construction - Jointing
label | REFERENCE: Section 304.07
label | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements:
label | (a) material shall be spread in such a manner as to minimize the number of joints;
label | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
label | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | METHOD: Visual and Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Sign ITP
checkpoint | 5.4 Compaction test (Frequency)
label | REFERENCE: 304 .11 (b)
label | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | ○ Scales A and B: 6 samples
label | ○ Scale C: 3 Samples
label | ○ Pass: Tested
label | ○ NA: Not Tested
label | METHOD: Visual
label | FREQUENCY: Each Lot Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Sign ITP
checkpoint | 5.5 Post Compaction Materials Testing (Frequency)
label | REFERENCE: 304.11 (c )
label | ACCEPTANCE CRITERIA: SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | Compaction:
label | ○ Lower Subbase: none
label | ○ Upper Subbase: 1 in 4
label | ○ Base: 1 in 2
label | PI:
label | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
label | ○ Upper Base: 1 (two samples) in 4
label | SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA)
label | METHOD: Visual
label | FREQUENCY: Each Lot Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Sign ITP
checkpoint | 5.6 Proof Roll
label | REFERENCE: Section 304.08
label | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Sign ITP
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.7 Protection of compacted layer
label | REFERENCE: Section 304.09
label | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: Sign ITP
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Compaction Testing (results)
label | REFERENCE: Section 173, Section 304.08, Table 304.081
label | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | – Density Ratio to be based on tests performed with Modified Comp active Effort.
label | Scale A:
label | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | ○ Base Layer CDR ≥ 100%
label | Scale B:
label | ○ Subbase Layer CDR ≥ 97%
label | ○ Base Layer CDR ≥ 98%
label | – 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | Scale C:
label | ○ Mean Value of Density Ratio (3 tests):
label | ○ Subbase Layers >98%
label | ○ Base Layers >100%
label | ATTACH: Compaction Test Results
label | METHOD: Document Review
label | FREQUENCY: Each Lot Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: Compaction Test Rersults
checkpoint | 6.2 Post Compaction Materials Testing (Results)
label | REFERENCE: Section 304.10, Section 304.11, RC 500.02
label | ACCEPTANCE CRITERIA: Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 20mm Class 3:
label | Grading
label | ○ 26.5mm 100%
label | ○ 19.0mm 95-100%
label | ○ 13.2mm 75-95%
label | ○ 9.5mm 60-90%
label | ○ 4.75mm 42-76%
label | ○ 2.36mm 28-61%
label | ○ 0.425mm 14-29%
label | ○ 0.075mm 6-14%
label | – PI between 0 to 10
label | 20mm Class 4:
label | Grading
label | ○ 26.5mm 100%
label | ○ 4.75mm 42-76%
label | ○ 0.425mm 10-28%
label | ○ 0.075mm 2-14%
label | ○ PI between 0 to 20
label | ○ PI x % passing 0.425 mm sieve (max) 450
label | – Scale C: Post compaction material testing is not required (Choose NA)
label | METHOD: Document Review
label | FREQUENCY: Each Lot Where applicable
label | CATEGORY: IP
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: Compaction Test Rersults
checkpoint | 6.3 Survey As-Built - Surface Level
label | REFERENCE: IFC Drawings Section 304.06, Table 304.061, Table 304.062
label | ACCEPTANCE CRITERIA: No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | – Subbase course shall be not < the specified thickness by more than 15 mm.
label | – Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | – The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | Scale A: A minimum of 80 measurements per lot
label | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | Scale B: A minimum of 40 measurements per lot
label | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | Scale C:
label | ○ Lower Subbase (mm) +15/ -25
label | ○ Upper Subbase (mm) +10/ -25
label | ○ Base (mm) +/-15
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: PE/Surveyor
label | VERIFYING DOCUMENTS: Survey Conformance Report
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-084-CIV-PSDS-Kerb Construction | itp |  |  |  |  | ITP-084-CIV-PSDS-Kerb Construction Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-084-CIV-PSDS-Kerb and Channel
label | ITP Description: PSDS-Kerb and Channel
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 084-CIV
label | Revision Number: 0
label | Revision Date: 13/06/2024
label | ITP created by: Anthony Pearson
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
section | Preliminary Works - Materials
checkpoint | 2.2 Mix design
label | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
label | ACCEPTANCE CRITERIA: Kerb and Channel
label | ○ Concrete used in kerb extrusion machines will not be subject to compressive strength requirements but shall have a minimum cementitious material content in the finished concrete as follows:
label | ○ Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
label | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete.
label | ○ Where kerb and channel is placed and compacted with internal vibration between previously placed formwork, concrete shall be:
label | ○ Traffic Routes – N32 portland cement–based concrete or 32 MPa geopolymer concrete standard strength grade; and
label | ○ Local Streets – N25 portland cement–based concrete or 25 MPa geopolymer concrete standard strength grade as specified.
textbox | TeamBinder Material approval number for the Concrete Mix:
label | METHOD: Verify
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
checkpoint | 2.3 Bedding Material
label | REFERENCE: Section 703.21, IFC Drawings
label | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
textbox | TeamBinder Material approval number for Bedding:
label | METHOD: Verify
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY:
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
checkpoint | 2.4 Curing Compound
label | REFERENCE: Section 703.10
label | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
textbox | TeamBinder Material approval number for Curing Compound:
label | METHOD: Verify
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
section | Preliminary Works - Documents
checkpoint | 3.1 Check for correct documentation
label | REFERENCE: Drawing and Drawing Register
label | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | – Using the correct and complete set of drawings
label | – All drawings are the latest version
label | METHOD: Visual inspection
label | FREQUENCY: Prior to commencing any activity
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: ITP Signed
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Setting out
label | REFERENCE: Section 703.17
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | ○ The superintendent will review and confirm set out.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | Attach: Lot Map (Marked up drawing with the location of this Lot) and Survey report
label | METHOD: verify
label | FREQUENCY: Prior to start
label | CATEGORY: HP
label | RESPONSIBILITY: Surveyor
label | VERIFYING DOCUMENTS: ITP signed, Survey Report
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.2 Temporary drainage provisions
label | REFERENCE: Section 703.18
label | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | METHOD: Visual inspection
label | FREQUENCY: If required
label | CATEGORY: WP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
section | Construction / Installation Activities
checkpoint | 5.1 Bedding
label | REFERENCE: Section 703.21
label | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
label | METHOD: Visual Measure
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.2 Formwork
label | REFERENCE: Section 703.12, AS3610
label | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | METHOD: Visual Inspection
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.3 Pre Pour Check
label | REFERENCE: Section 703.09, Section 703.21, Section 610.17a), b) & c)
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | METHOD: Verify
label | FREQUENCY: Each lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
textbox | Ambient temperature |  |  | °C
checkpoint | 5.4 Concrete placement
label | REFERENCE: Section 703.08, Section 703.23
label | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | METHOD: Visual Measure
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
textbox | Concrete Temperature |  |  | °C
checkpoint | 5.5 Transitions
label | REFERENCE: Section 703.24
label | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | METHOD: Site inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP Signed
checkpoint | 5.6 Surface Finish
label | REFERENCE: Section 703.25
label | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Renderings shall be applied within 30 minutes of extrusion.
label | ○ Concrete to have a neat appearance and uniform colour.
label | ○ Class 3 finish required for external surfaces.
label | ○ Class 4 finish required for permanently hidden surfaces.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.7 Formwork Stripping
label | REFERENCE: Section 703.12, AS3610
label | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | – External faces 2 days
label | – Permanently hidden faces 1 day
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.8 Tolerance
label | REFERENCE: Section 703.15
label | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | METHOD: verify
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/surveyor
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.9 Curing
label | REFERENCE: Section 703.10
label | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.10 Joints
label | REFERENCE: Section 703.26
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | METHOD: Verify
label | FREQUENCY: Each joint
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.11 Proteciton of Concrete
label | REFERENCE: Section 703.27
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
section | Post-construction / Post-installation Activities
checkpoint | 4.11 Backfilling
label | REFERENCE: Vic Road spec 703.29
label | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | METHOD: Verify
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 4.13 Cracking of Concrete
label | REFERENCE: Section 703.30
label | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ITP signed
checkpoint | 5.1 Survey Conformance
label | REFERENCE: Section 703.15
label | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | Attach: Survey Report
label | METHOD: Document Review
label | FREQUENCY: Completion of each lot
label | CATEGORY: WP
label | RESPONSIBILITY: PE/Surveyor
label | VERIFYING DOCUMENTS: As-built survey records
checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SPE
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 5.3 Lot Map
label | REFERENCE: MRPA Lot Management Procedure
label | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
label | Attach: Lot Map
label | METHOD: Document Review
label | FREQUENCY: For Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Lot Map
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | ITP-085-CIV-PSDS-Subsoil Drainage | itp |  |  |  |  | ITP-085-CIV-PSDS-Subsoil Drainage Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-085-CIV--PSDS-Subsoil Drainage
label | ITP Description: PSDS-Subsoil Drainage
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 085-CIV
label | Revision Number: 0
label | Revision Date: 13/06/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 702 (May '19)
section | Preliminaries-Material
checkpoint | 2.1 Pipes
label | REFERENCE: IFC Drawiings VR 702.04
label | ACCEPTANCE CRITERIA: All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
textbox | Reference: Material approval in Teambinder:
label | METHOD: Verify, Document Review
label | FREQUENCY: When applicable
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Granular material: Filter Sand
label | REFERENCE: IFC Drawings VR 702.05
label | ACCEPTANCE CRITERIA: Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
textbox | Reference: Material approval in Teambinder:
label | METHOD: Verify, Document Review
label | FREQUENCY: When applicable
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Granular Material: No Fines Concrete
label | REFERENCE: IFC Drawings VR 702.05 (e)
label | ACCEPTANCE CRITERIA: No Fines Concrete: Shall comply with 702.05 e)
textbox | Reference: Material approval in Teambinder:
label | METHOD: Verify, Document Review
label | FREQUENCY: When applicable
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Geo textile
label | REFERENCE: IFC Drawings VR 702.06
label | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with table 702.061
textbox | Reference: Material approval in Teambinder:
label | METHOD: Verify, Document Review
label | FREQUENCY: When applicable
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.5 Subsurface Drain Pits
label | REFERENCE: IFC Drawings Section 702.04, 702.05 CHAR(AMP) 702.06
label | ACCEPTANCE CRITERIA: Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: As per SD 1631
textbox | Reference: Material approval in Teambinder:
label | METHOD: Verify, Document Review
label | FREQUENCY: When applicable
label | CATEGORY: HP
label | RESPONSIBILITY: PE/Nominated Authority
label | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set Out
label | REFERENCE: Section 702.03
label | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
section | Construction / Installation Activities
checkpoint | 4.1 Trench Excavation
label | REFERENCE: IFC Drawings Section 702.08
label | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
label | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
label | METHOD: Visual Inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.2 Trench Excavation
label | REFERENCE: Section 702.08
label | ACCEPTANCE CRITERIA: The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
label | METHOD: Visual Inspection
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/Nominated Authority
label | VERIFYING DOCUMENTS: Nominated Authorith sign off ThisLine
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.3 Placement of bedding
label | REFERENCE: Section 702.09 c)
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.4 Traficable Pavements
label | REFERENCE: IFC Drawings SD 1601, EDCM 201
label | ACCEPTANCE CRITERIA: Choose pass when applicable
label | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and EDCM 201
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.5 Outside trafficable pavement
label | REFERENCE: IFC Drawings SD 1601, EDCM 201
label | ACCEPTANCE CRITERIA: Choose pass when applicable
label | ○ Pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.6 Pipe and Geotextile Installation (if required)
label | REFERENCE: Section 702.03, 702.09
label | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding.
label | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
label | METHOD: Visual inspection
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.7 Backfill Installation (Granular Filter Material)
label | REFERENCE: Section 702.09 (g)
label | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
label | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | METHOD: Visual, Doc. Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, Nominated Authority
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.6 Backfill Installation (No Fines)
label | REFERENCE: Section 702.09 (g)
label | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ATTACH: No Fines Delivery Dockets
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, Nominated Authority
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.7 Install Pits and Flushouts
label | REFERENCE: Section 702.10
label | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
label | METHOD: Visual
label | FREQUENCY: Each lot
label | CATEGORY: WP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.8 Marker Points
label | REFERENCE: Section 702.11
label | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
label | METHOD: Visual
label | FREQUENCY: Each outlet
label | CATEGORY: IP
label | RESPONSIBILITY: SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP
checkpoint | 4.9 Flushing
label | REFERENCE: Section 702.09 (h)
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
label | METHOD: Record Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, Nominated Authority
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.10 CCTV
label | REFERENCE: Section 702.09 (g)
label | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
label | METHOD: Record Review
label | FREQUENCY: Each lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE, Nominated Authority
label | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Post-construction / Post-installation Activities
checkpoint | 5.1 As Built Information
label | REFERENCE: Section 702.03
label | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
label | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
label | METHOD: Document Review
label | FREQUENCY: Each lot
label | CATEGORY: IP
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | VERIFYING DOCUMENTS: Attach Survey Conformance Report
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP