## Resources
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | CC0399 - ITP-003 - Bulk Earthworks | itp | CC0399 - ITP-003 - Bulk Earthworks |  | 05212b0c-bf98-4df2-933e-fe0c94bc9f76
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Determine lot size
6f7fd6bd-b6d6-5dac-98b4-779f6bec324e | note | Ref docs - N/A
aeadbbb8-b6b0-51a0-9635-692a49a625c7 | note | Acceptance criteria - What is the lot size?
ed0b965d-7637-526a-aa2e-0f8c5a6f79cf | textbox | Acceptance |  |  | m2
0e4a9d86-0303-5e66-a40c-aefefb8e7190 | note | Freq - Prior to start of Works
9beaff56-251b-56fb-ab2a-c27b7bade925 | note | Key - S
e8dbe7ed-02c6-53e7-b570-5ceece1710a6 | note | Resp - SE
1af08abd-7422-50b4-b83f-9ea3e2b25d80 | note | SGJV Key - S
9dcd93f1-68c5-5a63-8549-1fd4e891ed42 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
35dea27f-a593-56ca-93ff-6a8b25612e49 | tickbox | Lot Map
| checkpoint | 1.2 - Survey set-out
3dcd4539-8afe-56cb-b7fc-4fb17f81acc5 | note | Ref docs - IFC Dwgs
d5304c0c-0980-5714-b554-aeefc3ba2967 | note | Acceptance criteria - Is the most current survey file what the team is working to and has the work area been set out for line and level?
c5da89cf-e332-53d2-93ec-f24b722867bf | button | Acceptance | Yes,No,N/A
f1a8e7cf-32fe-5278-a3f0-8c6266675a87 | note | Freq - Each lot & Each possession
6193176a-2e0f-5788-90c2-f6a807f29c94 | note | Key - W
92438680-72df-5e53-b925-f090541667a5 | note | Resp - SE
8668f84c-064c-5844-a7e0-1c23daa1bdbe | note | SGJV Key - S
f4ce08ab-0f88-525e-8af4-7d8719877f1c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | 1.3 - Water management
3df4b4f7-ce82-5a32-89af-77d4d1b7f3eb | note | Ref docs - EMP
bc0122c0-56b5-59e5-a21c-96fd9c738a22 | note | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
564bc9f3-a79d-5395-a489-883f4a3bacf4 | button | Acceptance | Yes,No,N/A
788ea033-b3b6-515a-8c0e-bed4c89d7bf5 | note | Freq - Each lot & Each possession
bbf35f56-9600-5d71-a393-9bde29eda858 | note | Key - S
886c9584-666e-5ac8-becf-3b88a26cb5ed | note | Resp - SE
6043c9dd-df6b-5841-9341-5187912ab0bb | note | SGJV Key - S
4beb7c87-bad6-5502-9fec-525b9b6e4100 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | 1.4 - Clearing
9aaac009-6efb-5627-807e-1540bc226e97 | note | Ref docs - CC0399- ITP-002
aa9bfc6d-5d6a-5513-91d7-04f84117dbd4 | note | Acceptance criteria - Has the area been cleared and grubbed in accordance with ITP-002?
f58be78a-b135-5f58-800d-1b20aff1d840 | button | Acceptance | Yes,No,N/A
da78d783-25f4-58d9-84c1-5707cb31c911 | note | Freq - Prior to start of Works
79e71833-2e2a-5418-95de-e9dc6cc25996 | note | Key - W
9c0bede9-3ae2-5635-9b61-d6324743a582 | note | Resp - SE
eea8665a-187f-5e4e-827b-576f61af731e | note | SGJV Key - S
20a4d5bb-6999-5881-8ae0-0607545621bc | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint-no-value | Is the area in cut / fill / both?
b28a0c6a-4e49-5da3-88c7-47c875314656 | note | If in cut proceed to step 2.0 and strike out section 3.0.
96ddbd3f-c876-5b77-833a-42fee6812605 | note | If in fill please strike out section 2.0 and proceed to section 3.0
7981b265-467a-5892-8593-ee4f2abb04e5 | note | If in both proceed to step 2.0 as well as section 3.0
| section | 2.0 Bulk earthworks – Cut
| checkpoint | 2.1 - Excavation material classification
84c1cb61-d661-5530-ab59-537ff2604082 | note | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 rev 3 page 53
64ad3e2f-99b8-59f1-b85f-591108169609 | note | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent? Tick category below:
73dfc5e9-fcfb-5fe9-bf91-9d11bbe7b2d4 | tickbox | Topsoil
3d72d4a0-1ff3-509e-aa3e-9aa9eb65a01f | tickbox | Unsuitable material
3f69db10-f551-51ac-92f7-5ca90e022303 | tickbox | Fill material
8dd9843c-7acb-5bf4-a0fc-ffa7bf765e04 | tickbox | Other
69a0a8f9-d8fd-5e79-b6cd-1e68617ea522 | textbox | Other:
e6b4eb06-e2d0-55b4-8ab6-9c80b06ddcfb | button | Acceptance | Yes,No,N/A
a178cf94-e52f-5f32-ac93-bb497428660a | note | Freq - Prior to start of Works
a0d0e0fc-a7d6-50a0-b41f-f38a1d8a048c | note | Key - W
87d6df94-a354-5aec-bc7a-162f5c6441b0 | note | Resp - SE
0d861bf4-8d90-5c68-aae2-12781beba3b7 | note | SGJV Key - S
50242ebf-029a-5634-8701-995ac4ce05b0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test reports
| checkpoint | 2.2 - Stockpile
0a5d9b9b-3720-5b6a-83ff-6f491518a5ee | note | Ref docs - N/A
8298be41-35e8-5639-82d2-46c5a7cb55db | note | Acceptance criteria - Has the stockpile location been approved by SGJV.
32e016c6-bb1c-5f56-9fe4-e37997cc89e8 | button | Acceptance | Yes,No,N/A
6042e413-0ebf-58c3-b476-b604a5cf20f3 | note | Freq - Prior to start of Works
61a32883-b6f3-56db-8402-786b9fd390aa | note | Key - H
896d7d65-d926-5f0b-8c16-194e6db448ce | note | Resp - SE
dc5e807a-251c-50ee-a6f6-2ac2ece763ec | note | SGJV Key - H
d41d7bed-0d73-53d3-985a-1a153cd780d4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - SGJV approved stockpile plan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Subgrade preparation
769dfbd8-344d-5d35-b0eb-3e7b58749143 | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
4e68c518-d7bc-5e1f-aa98-71520e8cbc60 | note | Acceptance criteria - Has the cut surface been trimmed to an even surface free from lose material?
45f4b3d3-7bb9-54d2-862a-2f27658901b2 | note | ○ Have surface levels been checked to avoid over excavation?
0bd29618-9804-5014-9d6c-6afe7c66c755 | button | Acceptance | Yes,No,N/A
bdd711bf-269f-5da2-9bd2-0e7ea669b5f9 | note | Freq - Each lot & Each possession
8b561c25-480f-5259-9020-3789feed2560 | note | Key - S
c2957022-6b29-5ca7-833d-5727df45f2f7 | note | Resp - SE
a7f0b26b-4851-54b9-986a-259a97563262 | note | SGJV Key - S
36884716-ae9f-5198-b4b8-da896600f29e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test reports/as- built survey
| checkpoint | 2.4 - Lime mix
89b5d342-6543-5e07-a13e-67d4df11ef6d | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
b6e6a826-d72a-5e00-8dbf-217ac63158cb | note | Acceptance criteria - Has lime demand testing been completed and submitted?
eed22b69-bdfa-5056-bef4-367ab23d9c3a | button | Acceptance | Yes,No,N/A
47eaa381-d5b6-5b20-ad33-4d5d44a092eb | note | Freq - Prior to starting
e3d69de6-695d-5477-af49-bdb626cac58a | note | Key - H
3586f2fb-2e2a-5c90-83cd-172d222d40e6 | note | Resp - SE
914d9fbb-d98b-5441-b4c5-79b8d1b36139 | note | SGJV Key - H
252a7eb4-cf8a-58b4-8c0b-84f48b305492 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
eb53d931-b6cc-5841-85cc-4ef786cb6d0b | tickbox | Test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Lime stabilisation
b9b002c1-6f5f-5893-af04-b8d3d4d7e39c | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
be4bdb9b-d634-5514-8535-270e49fa874f | note | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
13627b78-4ffa-51cc-ad53-3f9a44fbdb06 | button | Acceptance | Yes,No,N/A
5568685d-cc61-5448-b434-1c8b7f0de526 | note | Freq - Each lot & Each possession
bcb4b53b-e514-58ff-b223-5f97079853c5 | note | Key - S
4f5e5354-00d8-55a3-b8d3-d84d16622d08 | note | Resp - SE
1957e2cd-9d5b-57a6-a11c-b96691370fe4 | note | SGJV Key - W
27b7b27a-454d-5ddc-87cc-c424ca356520 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/As-built report
| checkpoint | 2.6 - Compaction
c3f22d02-5972-5b36-a1df-7ca8078069ca | note | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
e8dc3c99-f80e-52c9-a14e-0b0d438ce5b1 | note | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2
2cfa6940-ff3f-5b60-8c59-beec33e1880c | note | ○ Has the stabilised subgrade been adequately compacted achieving 100 SDD for subgrade.
a763e330-40d2-5fd6-be23-8cb33a92a890 | note | ○ Is the subgrade material within +/- 2% of the optimum moisture content.
773d268e-879a-5616-99d4-6b33c1e88e98 | note | ○ Has a minimum 3% CBR been achieved?
19743f64-ccbe-5860-ad81-1997755686ed | button | Acceptance | Yes,No,N/A
e39d90bb-0b07-5785-836b-c8018a3674c7 | note | Freq - Each lot & Each possession
6b9add2f-7eed-545d-a10f-08ba4728d329 | note | Key - W
05e052fa-125d-5ff7-972d-6ac3d1cee959 | note | Resp - SE
dce7700c-56d9-53a8-892b-6f986e95857b | note | SGJV Key - S
b27be51b-d62a-5cee-9c7c-94d3ad560175 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
4e9e2178-890f-54ee-8c69-e240fd954c27 | tickbox | Test reports
| checkpoint | 2.7 - Test Rolling
fd0e59f6-71ab-5875-a589-898bce3ee91c | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
7c19406a-7c0d-5571-9ee6-89cdf8e4a3f0 | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
b4504fa3-1196-5ff4-bde1-cd8b481f6514 | textbox | List Attendees:
de2e5468-7420-51f1-86b2-251c2253ae6b | button | Acceptance | Yes,No,N/A
4e7a9ca0-a840-5f11-a9e4-177f6a753ff1 | note | If ‘no’ please see below. If ‘yes’ please proceed.
8911207c-0d70-5dbe-87a7-c85398245075 | note | Freq - Each lot & Each possession
bd43f376-4f26-5051-bf79-aaf9ec55d08d | note | Key - H
ffb933f3-091b-5188-a2da-e5ec6226f356 | note | Resp - SE
6d794d35-6cc7-5219-bd10-171f5606dd21 | note | SGJV Key - H
c0842e9d-02e0-5f56-afc3-10e1063c4e15 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
ccbddcb5-6893-5fa9-aaac-95d5c3630212 | tickbox | Proof Roll Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material
3d5d416b-84f2-5a24-a721-e831c98be901 | note | Ref docs - IFC Dwg
1e15ca83-b51b-5c05-839f-792d33188f7b | note | Acceptance criteria - What quantity of soft, wet, or unstable material is present?
ba64d54d-e504-5a8c-999f-bbd02eb10ee6 | note | Acceptance
520b324f-8664-5582-8a0f-5c7d8c248736 | textbox | m2
23c5201c-7756-52ac-bcab-0925f966d82d | textbox | m3
2991058b-d45b-5749-bc15-e069f7f16914 | note | Freq - As required
2745ed57-bc02-5599-bff9-3a1922973a76 | note | Key - W
ac107c84-caf0-566e-b48c-f507d09ef04c | note | Resp - SE
8564f000-503f-5f09-af38-903054886d0a | note | SGJV Key - S
233b8a6b-06de-5e9d-b906-4304fc1d8917 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | Treatment of unsuitable material
8b9de6b7-3311-5c74-9071-573c16fec9e5 | note | Ref docs - N/A
62b15a90-1dcd-5710-8267-1b52b04ea5f3 | note | Acceptance criteria - Has rectification process been submitted to SGJV for review. What was the rectification process used.
07fc744e-fbd7-52fa-a2e5-441260a234a9 | button | Acceptance | Yes,No,N/A
82831f51-2b96-56fc-803b-d5ab302edc6e | note | Freq - As required
7634feed-3cd1-5304-855b-c278f1a57b50 | note | Key - W
8ba39753-b022-59e3-bb2c-6c8de18fcb61 | note | Resp - SE
993f6093-b83c-5135-b329-96f119ab6d8a | note | SGJV Key - S
5ccb8b78-50a6-539c-beb1-f565438093c9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Aconex Correspondence
| section | 3.0 Bulk earthworks - Fill
| checkpoint | 3.1 - Fill material classification
743a2688-6af4-5685-ab8d-bcf3db1cf5da | note | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 page 53
dffcbeab-f31e-5154-b9b4-b183f3b43f43 | note | Acceptance criteria - Has the material to be used as fill been approved for use?
39514127-27ac-5bb7-bb5e-593c59121dd6 | button | Acceptance | Yes,No,N/A
8d96ba81-61f7-5308-b0ef-36dd69b781d2 | note | Freq - Prior to start of Works
706fbf65-86c1-5d1f-a0bb-128f96ab2070 | note | Key - S
c7fb06e8-99c9-5dcb-a361-f37766b51057 | note | Resp - SE
c6e6f3d5-787d-5fe8-b28d-4fbf89ce7dd2 | note | SGJV Key - H
8469b7ee-642b-5143-9630-0b33d05a9cc2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Material Acceptance correspondence/Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Stripped surface - test rolling (If applicable)
d6d4d227-48ae-5601-b05f-4960ed6cf5ef | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
14aa87a6-105f-57a1-b087-86dc01470e2d | note | Acceptance criteria - Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
fad1bfab-fe21-5461-bd36-24c009d8747d | textbox | List Attendees:
9638444e-a458-53ce-b6dc-425504d55ff9 | button | Acceptance | Yes,No,N/A
74df17e8-4b42-5bf9-9f82-3ac26deaa3fe | note | If ‘no’ please see below. If ‘yes’ please proceed to item 3.2
d1797911-43af-5a20-a65a-78255765af49 | note | Freq - Each lot & Each possession
bba62dde-aef3-51e7-88c0-e87248c8ebb3 | note | Key - H
5e7e341e-fda9-52bf-967b-d26f988646ec | note | Resp - SE
8f350daa-9293-5d20-be8b-cd2640994c9c | note | SGJV Key - H
e9dc21b7-2e4c-5d18-9ce3-6707d02239d6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
69293573-2a25-573f-b2fa-ec4c1e3162c2 | tickbox | Proof roll checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material (1)
0e5bc80c-497d-5094-96f4-b199c623dde6 | note | Ref docs - N/A
5a95519c-b660-58b6-a662-4b614db5549a | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
37caab6a-b8c7-5b20-855c-77c8d3625b74 | note | Acceptance
2e785a7b-49fb-5957-ba6a-d0be68112598 | textbox | m2
f4bee5d6-b137-5311-8ab5-e72d06ae7b86 | textbox | m3
3442865a-3d2d-56b6-989b-f94d44a5d748 | note | Freq - As required
f993b755-881d-5e13-be83-f32c4a88fd8f | note | Key - H
abe1526a-375e-5ab8-9c3f-04099de9d32a | note | Resp - SE
f05a33f5-c331-5ce4-93d8-7ee874ebe249 | note | SGJV Key - S
4dd9e904-69b8-5be0-869b-dd6166f1d878 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos /Visual check
| checkpoint | Treatment of unsuitable material (1)
bfaa1233-2c75-5398-84d5-575960960750 | note | Ref docs - N/A
5fbf06e5-a6c7-59b4-b56b-b27d94b27ee3 | note | Acceptance criteria - What rectification process is to be undertaken
164b096b-ad30-5234-b466-ccf4717cb745 | button | Acceptance | Yes,No,N/A
1ad92a85-c4b3-54dc-9c5f-637eb380b219 | note | Freq - As required
72afb5b0-b936-5d5a-9942-19472bc27c0b | note | Key - S
b1b8bcf6-e974-53a3-b19f-2e3b4f156f11 | note | Resp - SE
a6d9c494-f69c-5740-93b8-8c6518ac74bd | note | SGJV Key - S
e53b8b59-4d14-572a-a92b-23154ae64c56 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Aconex Correspondence/Approval from SGJV
| checkpoint | 3.3 - Preparation of surface
2bc7d884-898a-57b1-8447-60914bb2e780 | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
a7f91ceb-aeb8-5263-9f79-9af6f3849489 | note | Acceptance criteria - Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
47a155d0-5fd3-5ec5-88c2-f230155999b7 | button | Acceptance | Yes,No,N/A
e1e2f089-d3ba-5e4e-b2d5-747ddb8e5238 | note | Freq - Each lot & Each possession
889a0b2b-9ca4-579c-98c8-bcc6d57b587d | note | Key - S
ec6d988e-569b-59e1-89c7-8035c939b934 | note | Resp - SE
45596ff5-07a9-5d8f-9b75-00f59b7cdebe | note | SGJV Key - S
1a94be97-d3ae-50f6-983c-1d24c0643dbc | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | 3.4 - Fill Placement
c620325e-9cbf-585e-abc5-ac9d742b9947 | note | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
e145d812-1e54-5780-9573-56ab4dce33f5 | note | Acceptance criteria - Has fill been placed in maximum 300mm and minimum 100mm compacted layer thickness?
05d18e1c-383d-5eae-a67c-e161fbfa8df5 | note | ○ Rock in the fill should be less than 75 mm.
95768147-dc8a-5785-912f-5e461cf33a5b | note | – Fill should be free of clay and free from organic.
3edc28cf-d817-51f2-9f33-5d820e699286 | button | Acceptance | Yes,No,N/A
f4614980-9298-552c-ab82-84021335b5cc | note | Freq - Each lot & Each possession
7bb1a953-cae5-5f56-bd21-0df0c93249b6 | note | Key - S
4022da30-a234-5053-b963-9c7714a950e5 | note | Resp - SE
44155366-d93e-5838-ab0c-b380ffb35cf4 | note | SGJV Key - S
bd90be1d-5702-5ab3-aadb-70f69c512dac | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | 3.5 - Moisture
65598f9d-4f16-5750-8f23-20171e7fa6c1 | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
4338e789-bb28-509e-ac14-d2743e717e34 | note | Acceptance criteria - Has the material maintained at optimum moisture content (within +/- 2% of optimum moisture), with additional water being added if required during compaction?
cb5baaeb-ffe8-5ed0-9986-ff9b8e27b5e0 | button | Acceptance | Yes,No,N/A
71f5e63b-53c7-542e-ad5a-dea187fe4830 | note | Freq - As required
60b90f6d-baea-5e03-ba9a-089a06098cc9 | note | Key - S
d185218a-a946-5b8f-a673-131e549743bb | note | Resp - SE
03a8a9b9-8923-5118-b165-f089e8c6c894 | note | SGJV Key - S
a7260cdb-9bd9-597b-8287-2fd62720142b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test Reports
| checkpoint | 3.6 - Lime mix
758095c2-296a-59a6-af3d-916fbe2f36b2 | note | Ref docs - IFC Dwgs MRH/A0/B/ 00- CV/DWG/00 40
066a8b38-a29d-54e4-9784-d9db3630ea90 | note | Acceptance criteria - Has mix demand testing been completed and submitted?
84047c5c-d821-58fc-b625-83c87d8035f2 | button | Acceptance | Yes,No,N/A
36769aa2-face-5ca4-9f4d-e3102a90e999 | note | Freq - Once
bc3dc606-9b9b-5b4c-aea7-5d18b4142166 | note | Key - H
5c7ef973-64c9-5d7f-91ed-588bae64416a | note | Resp - SE
2fd44364-80cd-54e3-853a-11fe63908573 | note | SGJV Key - H
3af94acf-024e-5670-ad45-a187a215930b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
10e71cfc-5373-55d7-baef-4e53d4e1d11e | tickbox | Test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Lime stabilisation
fdafece8-01db-577e-a38d-c93fa3d03c45 | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
4206636c-1394-53dd-a334-58397afdb3fe | note | Acceptance criteria - Has the prepared subgrade been lime stabilised as per the IFC design?
70d81f9a-661d-5482-bc3c-81d7e3d4682d | button | Acceptance | Yes,No,N/A
0e2efc5e-f989-5456-96e3-15b8f940e4d7 | note | Freq - Each lot & Each possession
7c9b1fae-7dfa-5d7c-a7aa-35f483bb92b0 | note | Key - S
39481fd1-56c6-5698-b85e-21956406d151 | note | Resp - SE
b26c25aa-2a32-5849-9733-3ee349c31853 | note | SGJV Key - W
f3516aab-4b86-561c-a3c5-e72c9f1ea08c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/As-built report
| checkpoint | 3.8 - Compaction
11ec9792-4b03-5899-8eb2-7791a8d5254d | note | Ref docs - IFC drawing MRH/A0/B0 0- CV/DWG/00 08
8ea1b034-3557-5f35-96ed-e648bc3a5c5d | note | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2
631750d5-262d-5b8d-8d59-76c828471acd | note | ○ Has the stabilised subgrade been adequately compacted achieving 100% SDD for subgrade.
dd14c0ba-3fd5-5e19-babd-63b4f4ac202d | note | ○ Is the subgrade material within +/- 2% of the optimum moisture content.
1e1f94b2-3aec-5782-93e2-6b2a9b0c6033 | note | ○ Has a minimum 3% CBR been achieved?
6fe3cac0-f918-557f-aaae-dc20ddd9d8fb | button | Acceptance | Yes,No,N/A
a3512245-035e-5111-8ddf-3b71d42eca2e | note | Freq - Each lot & Each possession
18881033-de27-5cf1-ae60-0adffc817d46 | note | Key - W
5aa170fe-8bf8-581d-ad8c-154d01356420 | note | Resp - SE
d3ef6163-99ff-572a-938d-a4c51845c6fd | note | SGJV Key - S
1219f012-1c3a-54f0-9c35-332c3ce009f4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
2ba88dc4-5f15-5133-8f02-c300208a1365 | tickbox | Test reports
| checkpoint | 3.9 - Test Rolling
6363422b-7b45-5b7a-8c6e-8f255cee5c30 | note | Ref docs - MRH/A0/B/ 00- CV/DWG/00 40
051a2aa2-33be-5b94-a995-d307219e444c | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
ec364cd1-317b-5573-880d-f0197a7285b6 | textbox | List Attendees:
f605383a-65cb-5ba8-9d79-a94dd25bb547 | button | Acceptance | Yes,No,N/A
b817d861-7544-5043-a8f0-4dc3cbc6b70a | note | If ‘no’ please see below. If ‘yes’ please proceed
d14dba10-5a46-5dcc-97ee-cd7b8fe91d4c | note | Freq - Each lot & Each possession
4e727aab-1741-5aee-aa7b-4bff1f00aff8 | note | Key - H
c491bc65-ea60-59cc-b6f5-0d75d31b999f | note | Resp - SE
a624e8a1-fb2e-557c-bf88-a483b5dc4fe7 | note | SGJV Key - H
127fc8b8-85a7-5c5e-9b7c-99dd33d0e996 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c83e16cd-aa7b-5c5b-a40f-a12e34700f28 | tickbox | Proof Roll Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material (2)
f3f5133c-7e4d-5d12-8cfa-059cb30191a8 | note | Ref docs - IFC Dwgs
eeee47f5-9357-5aff-aa1d-f10cb0f3b396 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
f1688644-8b23-59ff-aed1-68cbfeb836c4 | note | Acceptance
304a0b06-0e26-5557-a734-f96a2860ddaf | textbox | m2
00513c2a-6060-56d5-a42f-6467341496a8 | textbox | m3
389ac575-eee2-570e-8f21-cc083b5d8677 | note | Freq - As required
654c1e04-3014-561e-8f6b-22a141ce95d4 | note | Key - S
4ae4f108-ba29-58ce-b20c-e3b55a28e275 | note | Resp - SE
48153de2-8a92-5c35-9d35-24054c8f4e38 | note | SGJV Key - S
0ed9566c-eb83-5f5b-ae01-32e81c6dc646 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| checkpoint | Treatment of unsuitable material (2)
465d09b0-3220-5017-bc21-58b5d5b273a0 | note | Ref docs - IFC Dwgs
c65000f7-9eab-565c-a938-9cef317bb68a | note | Acceptance criteria - Has rectification process been submitted to SGJV for Review? What was the rectification process used?
bd156bac-7613-5e2d-b971-3707947b93e9 | button | Acceptance | Yes,No,N/A
7446dbdf-5a4f-51dc-bc7b-9efe7cb6b628 | note | Freq - As required
164ed0a8-5984-5830-8ffd-3525e6936606 | note | Key - H
7be3c0a3-15c5-51a6-b8e0-41eb96c05851 | note | Resp - SE
e7831834-ad7b-5a06-abf9-d90a3e8837e8 | note | SGJV Key - S
8da44a35-d62e-5ecb-b55b-f7a08f05a3af | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos
| section | 4.0 Conformance check
| checkpoint | 4.1 - Width and alignment
e3b45b66-a080-5ae5-b345-1825decbf8c0 | note | Ref docs - IFC Dwgs
86275588-c25b-5eab-8150-184e3b7bb3c4 | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
8913fb1f-cb5f-53f8-8940-f8c662a6e04b | button | Acceptance | Yes,No,N/A
cc987cc5-ef6d-57ff-b30a-7415fa1f7c32 | note | Freq - Once
e524a5de-1674-5f64-acc5-ed7d3e4f2962 | note | Key - W
3dc986e4-06c5-55f7-b026-fb6b6017043e | note | Resp - SE
3ee2b23d-75d4-58a5-a95c-485dc7f0fe48 | note | SGJV Key - H
dafcb331-9119-551c-a96d-e1b61944fb45 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d84399e7-f6b0-565c-98ab-d23dcad09d75 | tickbox | As built report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Subgrade level and shape
93f4750c-feb6-566e-ac6d-9545cbda4763 | note | Ref docs - IFC Dwgs
4ffe11bc-1e8e-5b9b-984c-d6adb839b2f5 | note | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
61f283ca-6dc2-5ba9-b486-49376fbcd983 | note | ○ Is the subgrade within +/- 20mm of design surface.
4968baca-5552-517a-82f6-d1dd551f9637 | button | Acceptance | Yes,No,N/A
db73b123-f82f-58c5-8099-d9cd445b61b7 | note | Freq - As required
d6adb3ce-8d0c-5e65-a760-bc80c4f4a9fa | note | Key - W
88e7b147-0770-5286-883e-949c74de617d | note | Resp - SE
d3c8d15d-c9f3-5fd1-a228-fa6efa615749 | note | SGJV Key - H
ebc52483-18cb-5379-a610-1c49046c6996 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9a9368a3-3cc3-5d46-9def-fd56210698a9 | tickbox | As built report
| signoff | AUTHORITY HOLDPOINT
| checklist | CC0408 - ITP-005 - Pavement Construction | itp | CC0408 - ITP-005 - Pavement Construction |  | 3613e95e-7f9d-4e53-8c3a-f5770e5a825b
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Determine Lot Size
1d04c8e2-6896-5b49-93a6-22e51cb8e4a2 | note | Ref docs - N/A
8348f4e1-4955-50a8-b28d-3d650d36008f | note | Acceptance criteria - What is the lot size?
fa1aedbd-b8d9-5208-be3f-9e0fd1b5de40 | textbox | Acceptance - _________ m2
b277fda7-1086-53ab-adec-757d3087012b | note | Freq - N/A
8eefdbf8-2bd9-5e6b-91d3-7477c65667a7 | note | Key - S
0610a643-432f-5416-89ff-a369eb471d75 | note | Resp - SE
57dbb2b5-6286-5900-8364-737ba55d7989 | note | SGJV Key - S
f915b927-f611-5459-a55f-897495043044 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Work Lot Map
| checkpoint | 1.2 - 1. Survey Setout
7a67836f-c72a-566d-9475-534a027012fe | note | Ref docs - N/A
a12b271f-0d11-56fb-b8b6-dbeb423db28d | note | Acceptance criteria - Has the work area been set out for line and level?
5cd51354-b59b-5202-95ef-a863bc6fbf4f | button | Acceptance: | Yes, No, N/A
894e0fcb-2e0b-516f-b90e-34260c331f61 | note | Freq - Prior to start of Works
173cf2f0-83cc-5236-9d19-aa34750a19ac | note | Key - W
33885c9f-c244-5fd3-9274-5d26d2f91b99 | note | Resp - SE
89032d7b-ca27-5295-9ed4-40b297970cae | note | SGJV Key - S
25c9156b-ec5c-55d8-a6df-2bf9f36be4d3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - N/A
| checkpoint | 1.3 - Material Classification & Source
a336cb8a-6077-5726-91d4-7dbd7b584d6d | note | Ref docs - MRH/00/P/00-PM/SPC/0003 Rev 3, Page 55
369554e6-d307-50d5-9bab-6c14699d94d4 | note | Acceptance criteria - Is the correct material being used?
25573492-aeba-5e20-a38c-22066e80f5ed | button | Acceptance: | Yes, No, N/A
4041c88e-98e1-5dc2-a17a-80d06955f69c | note | Please tick appropriate Box:
33913ea8-0bd8-5556-aeb6-75312c96b537 | tickbox | Site Won
538554f8-f0a6-528b-a837-7e22001a1e2f | tickbox | 20mm Class 2
2d7a1b3c-2710-5bf5-a95e-3408f2ec1d12 | tickbox | 20mm Class 3
fde45033-92a3-55a3-9bcd-2d10ad09dd61 | tickbox | 20mm Class 4
243d437f-5fc1-5efd-89ea-e92b98f15085 | tickbox | Other:
e1380653-4057-590b-a375-96252db1fdd4 | note | Freq - Prior to start of Works
07a9d8ae-e437-53b8-a8ae-efd3da57f11f | note | Key - W
67afa776-efd8-597a-af77-e915cf03de21 | note | Resp - SE
e83f4c51-17ff-50df-8411-eb568bf0dfe9 | note | SGJV Key - H
72a56d66-4318-545e-baa8-6ea4d52dfec7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
d98c527c-c9fe-507d-af4e-dfa1e46130fb | tickbox | Test Report/Material certificate
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Previous pavement conformance
| checkpoint | 2.1 - Conformance of Previous Layer
aa9b770c-bd79-596e-97e9-3486bf6a3644 | note | Ref docs - MRH/A0/B/00-CV/DWG0040
7a6b2d4d-a4c9-5a18-9835-2c062da7d159 | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
c5a62a9d-8ed4-5967-9d1e-afedd9e168d3 | button | Acceptance: | Yes, No, N/A
67b1e49c-b33d-5933-bf6a-fffb703a5366 | note | Freq - Each Lot
198398a2-dcef-59c3-96dd-45f02ec3e2b2 | note | Key - W
7edb9960-4274-5f68-a6be-83af67a32681 | note | Resp - SE
e06d26e5-d3a6-5f82-a0fe-3e8477e7f997 | note | SGJV Key - S
b4d779ee-c2bd-5bc7-973a-995073e982d1 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
156557c9-0f0b-5cfe-8a58-2bb00ba81978 | tickbox | Refer to ITP for previous layer
| section | 3.0 Placement of pavement
| checkpoint | 3.1 - Placement
9635761f-6f03-5ee5-a692-ac3910c94ce2 | note | Ref docs - IFC Drawings MRH/A0/B/00-CV/DWG0040
bae1cdbc-98d9-5ca0-92d6-bdd94c5f7201 | note | Acceptance criteria - Has the fill been placed in a maximum compacted layer as outlined below? Maximum Layer Depth: 200mm
4198dc26-de2e-5b37-bab8-c6bf189d14d2 | button | Acceptance: | Yes, No, N/A
a83992f7-56a9-5e01-9878-ec79ab85a2a9 | note | Freq - Each Lot
005be943-9f60-5335-b11f-c4e5657b7245 | note | Key - S
b1589f42-d66a-5737-9bc2-e761e390695c | note | Resp - SE
3e0f9dbe-6d19-5773-b02e-05d43503c27e | note | SGJV Key - S
c03af0a2-4338-5084-8bde-c8e03cbde09f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
799e11bc-4b79-5b27-93c8-b4768b934b73 | tickbox | Photo (if required)
| checkpoint | 3.2 - Moisture
4861ca9d-41f6-5edb-96a2-1d607d6254b2 | note | Ref docs - MRH/A0/B/00-CV/DWG0008
58f3c19d-e0b3-595f-b8d7-d69d85c784c9 | note | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
7c93d2c1-1937-52b8-b5af-d48ba55426e3 | button | Acceptance: | Yes, No, N/A
75e8811b-1e48-5f8d-806e-5c5dc122523b | note | Freq - Each Lot
2532b84d-9a41-5e63-ab13-52f0fb1ebecd | note | Key - S
eccace5d-b0ae-5170-a419-5330c5da9928 | note | Resp - SE
d114156c-4b6b-50ee-bca6-95a9a2bff913 | note | SGJV Key - S
804f348d-ed1d-5c4f-98f3-44fb8efa7de1 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Photo (if required)
| checkpoint | 3.3 - Compaction
e404debb-d974-5eb7-be24-23a683911ed8 | note | Ref docs - MRH/A0/B/00-CV/DWG0008 AS3798 Table 8.1
9d96aabe-fc3a-599d-a8d5-e1dac2f4cea2 | note | Acceptance criteria - Has the layer been adequately compacted achieving a mean value density ratio of: Pavement Type 1: “Granular Surface” Top Layer: 98% MOD Bottom Layer: 97% MOD “Low Permeability Capping Layer” Both Layers: 98% STD Pavement Type 2: “Granular Surface” One Layer: 98% MOD “Low Permeability Capping Layer” Both Layers: 98% STD 3 x tests to be conducted per compacted layer per approved lot map.
315a7ed6-1f84-516e-810f-386329c6cd2a | button | Acceptance: | Yes, No, N/A
e9152f66-00ba-54a3-8857-02f889d6464e | note | Freq - Each Lot
03f4ce17-7c21-5bcf-b41c-cdcb1659ffb9 | note | Key - W
3129c7f2-8632-5250-ae88-0b668d198938 | note | Resp - SE
cbee2bf0-3d08-5c3a-97ac-cfdd30d830d7 | note | SGJV Key - S
b6499ef9-7b17-5ea8-9258-3a008fc93523 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
31f3adc9-7de8-51e3-b89a-aef7b4282cd6 | tickbox | Compaction test results
| checkpoint | 3.4 - Test Rolling
2a77cb09-4e10-5a48-b5e4-e10b170c2882 | note | Ref docs - MRH/A0/B/00-CV/DWG0040
f3bcf04f-84c8-57f4-9b56-5c5abc6eef42 | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation of springing? List attendees:
8bd74116-8458-5422-a3bd-8701bf94cd5f | button | Acceptance - If ‘no’, please see sections 3.5 and 3.6. If ‘yes’, proceed to section 4.0. | Yes, No, N/A
fa1d96a0-8797-5da6-bf8f-f622c0c89e5d | note | Freq - Each Lot
e3f15a9b-5c8f-59fb-a9d8-1b0c6dc7a916 | note | Key - W
c045c857-b16f-53a4-9a93-d0c58c9c2c62 | note | Resp - SE
eb630be8-ff2f-54b4-a4d8-cea8e8a2af96 | note | SGJV Key - H
911e688b-f013-5ca7-821c-556ede6c821a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
011a9fc6-0cf3-5cf6-a441-3dd3b3feb673 | tickbox | Photo (if required)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Identification of soft, wet or unstable material
e6c70c3f-5fe7-5ce5-a81c-75947ade9b88 | note | Ref docs - N/A
a62b42bc-a59f-593c-8de6-e0d23e099f43 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
888f029b-dce6-5a89-ad1e-473514941817 | textbox | Acceptance - _________ m
97d7eda1-c65a-5b14-ad24-76797a8df0b1 | note | Freq - As required
a41c7ed6-7a82-5e31-a8e4-c428608053b1 | note | Key - SE
06af9694-d820-5a17-8d02-ac546704a2ca | note | Resp - S
eb364501-f23f-59d6-af2c-05dad38fda04 | note | SGJV Key
b831ce14-25d3-5d39-8f53-e318cd5e01d6 | tickbox | Photo (if required)
| checkpoint | 3.6 - Treatment of unsuitable material
6968a8a5-889a-5859-bf11-3ba9e8a6db3a | note | Ref docs - IFC Drawings
a6b0d4a7-acd4-58d2-beb6-0a0b8af8f2c6 | note | Acceptance criteria - Has rectification process been submitted for review? What was the rectification process used? SGJV approval acquired before proceeding with the above process?
e86fcd41-96f4-5eb2-b909-adf9f268267d | button | Acceptance: | Yes, No, N/A
83333cce-ad0d-5e09-973a-4b7b4edf7084 | textbox | Process Used:
510cfbcf-749a-55c6-9745-5606418e6484 | note | Freq - As required
cc7808e1-5816-5fc3-9d66-9380cc25edcd | note | Key - S
4ab02ac1-043f-55d6-9259-f4e22bd8e6ae | note | Resp - SE
ec86045a-0605-5f5c-bcd7-bbf16649dab7 | note | SGJV Key - H
7a701c2b-24d8-5146-8b87-465133a6031f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
aa8c7b43-6452-5329-a261-424bb2f81292 | tickbox | Photo (if required)
fdef385e-69c1-5800-807a-0d09d884598b | textbox | Aconex Correspondence:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Pavement conformance
| checkpoint | 4.1 - Pavement Finish
a42d1f27-faba-51cf-a781-8fbf97a28d06 | note | Ref docs - IFC Drawings
08c65344-865b-516d-88d4-0beb0d2302c4 | note | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
99f9c5f9-19a3-5c5e-83ef-eeec6fedea6a | button | Acceptance: | Yes, No, N/A
66fcd787-d5a5-5fbc-b129-8c87e5ddfb98 | note | Freq - Once
1d827d36-ce5e-53d0-a54c-5b1820502f3b | note | Key - W
393c277c-5615-5579-a4ba-233dfde3c3a3 | note | Resp - SE
f55d9a09-1c41-5a45-948f-939133f2aa6c | note | SGJV Key - H
bed84284-2a99-57f0-8a8c-b164f8d29b3c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
33e3e781-a87e-5414-a887-1ac7325040e1 | tickbox | Photo (if required)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Width & Alignment
fd77a674-1dd8-525e-b1a1-aca0820748a3 | note | Ref docs - IFC Drawings
6bdaf715-ee6c-58c3-939c-f729701f054c | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
3097ecc1-876a-5bee-89c1-4f559f3eedc5 | button | Acceptance: | Yes, No, N/A
1142125c-d966-55c2-92f2-5d2521801047 | note | Freq - Each Lot
d201941b-f135-5e29-8590-1dde4283672e | note | Key - W
d71c9a45-b6e4-5dc0-936c-05d7e125d086 | note | Resp - SE
8ca2a47c-5ff8-5395-943d-3ea8f6f1d945 | note | SGJV Key - S
57f6a127-f1df-5428-8185-7269df892e23 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
f005b009-d893-5bd0-b601-05b204e9e142 | tickbox | Photo (if required)
| checkpoint | 4.3 - Surface Level of Pavement Courses
1b326155-1682-5dff-aaaf-b9892bf10b47 | note | Ref docs - IFC Drawings
56795c3c-2a40-5f25-9cf3-4daf9e073d8b | note | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements? All crushed rock layers: Mean Range: +10mm to -10mm
c2b9463f-eb87-502d-aed6-27e520e48a0f | button | Acceptance: | Yes, No, N/A
36016f75-adad-5c56-95b5-fd5eb1d8c19d | note | Freq - Each Lot
c2586d65-324b-56e6-b022-7bf6664e362b | note | Key - H
8493069e-5a24-5021-9abe-0c4de096a541 | note | Resp - SE
d3604d3c-80b0-5a21-b896-fe5e1278f253 | note | SGJV Key - H
8daf5829-6d27-58bb-aaaa-8074b5724386 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ As-Built Reports
| signoff | AUTHORITY HOLDPOINT
| checklist | CC0399 - ITP-005 - Crushed Rock Pavement Construction | itp | CC0399 - ITP-005 - Crushed Rock Pavement Construction |  | 5000e99b-1a3b-4ae8-887a-f44cdac02ad8
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Determine Lot Size
fabe3587-8f25-567a-8324-9e5da1e259ab | note | Ref docs - N/A
142844ce-7c32-580a-8f66-c6a50455d6ed | note | Acceptance criteria - What is the lot size?
592bf7a3-c04b-5d3b-a72a-80d32e2cef33 | textbox | Acceptance |  |  | m2
0298ccab-9884-538f-99e2-e8e65be014d2 | note | Maximum lot size = See pre-approved lot maps
82d9e8f5-cbe7-51d3-be18-1f2157b1d582 | note | Freq - N/A
2a23406e-e5a5-5680-bd25-97199c30098f | note | Key - S
c1db2675-f5c3-5ae7-9e68-f9c8ffda0b7a | note | Resp - SE
021d82b1-4c06-5074-bbf3-6b7a49d6c464 | note | SGJV Key - S
2b3b53b4-cc77-5eda-afb2-12e44fb6f90d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
de70bbdc-70eb-5dba-8705-57be5083e16c | tickbox | Work Lot Map
| checkpoint | 1.2 - Survey Setout
ec1a1258-e3e3-5589-a1a0-dd618f17f4e3 | note | Ref docs - IFC Drawings
4901206e-9837-5252-a17f-b9ba3229531d | note | Acceptance criteria - Has the work area been set out for line and level?
ad11b45e-c9fa-509f-8971-007000cbd269 | button | Acceptance | Yes,No,N/A
403be0ac-e45c-5310-831d-e34d9697ab14 | note | Freq - Prior to start of Works
bbaf5604-b2b2-5681-bf9c-d49af859984a | note | Key - W
061a247c-cc8d-5ccc-8a1a-724fb93bed07 | note | Resp - SE
f7dd3866-2cf5-5440-8acd-a5255058f423 | note | SGJV Key - S
b7aaa1e4-9005-5173-b4db-f65268483d97 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
86fbc0d6-de93-563e-a034-01fdcda69d21 | tickbox | Photo
| checkpoint | 1.3 - Material Classification & Source
aa8ac0fc-10f9-5a50-b644-80a82e9611c6 | note | Ref docs - MRH/00/P/0 0- PM/SPC/00 03 rev 3 page 55
864bbefd-dec7-5b53-962f-baacda4e41a4 | note | Acceptance criteria - Is the correct material being used?
0f0ca78a-71a0-5d62-996c-aa3f52028c18 | button | Acceptance | Yes,No,N/A
cd6726bd-2e82-508f-b9e8-3e2979e75ef8 | radio | Please select appropriate option: | Site Won,20mm Class 2,20mm Class 3,20mm Class 4,Type A – Capping
456a087e-78ca-5ab4-9c8b-b76ca283f9f2 | note | Freq - Prior to start of Works
3d78cdc3-a020-5fc6-89f6-247204f2d268 | note | Key - W
30747d5c-2a91-554e-ac35-a002ecc1dee4 | note | Resp - SE
6cd3104c-99bd-58fb-9f03-506b03813a9f | note | SGJV Key - H
35bc518c-3cbf-55a7-8eb0-6c6498c10cef | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
e6088a5a-9460-56d6-9860-4211d8c9e306 | tickbox | Test Report/Material certificate
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Previous pavement conformance
| checkpoint | 2.1 - Conformance of Previous Layer
df63f4fa-4823-5d4d-9068-ba927ae3f5c4 | note | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
b373ed33-ee3d-5b75-a1c9-3263d02232a0 | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
e787e530-ec11-55b7-8bd6-1ab726753bb5 | button | Acceptance | Yes,No,N/A
3023a75d-2fd4-5612-a320-edc2aab1363c | note | Freq - Each Lot
8a8edecb-f2f3-5dfa-b552-43993636ea46 | note | Key - W
1f98233f-d4fe-58d6-a3d4-1bdd7c14fe1d | note | Resp - SE
26a08951-c940-51e1-b3e7-7d56e89065b2 | note | SGJV Key - S
fc59bb17-2c1e-5e58-9f7b-ea7e797721c9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
fd48314d-82dd-55a0-9625-dcf154bcfe96 | tickbox | Refer to ITP for previous layer
| section | 3.0 Placement of pavement
| checkpoint | 3.1 - Placement
5e4bb51e-eb16-561d-94ff-0089e6be3da9 | note | Ref docs - IFC Drawings MRH/A0/B/0 0- CV/DWG00 40
ccfc9448-1ecb-5eb7-880d-8b4d572f7709 | note | Acceptance criteria - Has the fill been placed in a maximum compacted layer as outlined below?
3c94e771-6260-5e87-9455-d5d7c1b33fc7 | note | ○ Maximum Layer Depth: 200mm
b470546c-e4c2-564a-9668-fb9e6cdedbb9 | button | Acceptance | Yes,No,N/A
adce111f-aad1-5d8b-a07e-9d6109c7ba47 | note | Freq - Each Lot
1b213381-b5aa-5b2f-982e-3035f3486209 | note | Key - S
dbba2cd1-ff78-5c45-80e0-7e050ef4cde5 | note | Resp - SE
85167a0f-c2ed-5e23-af1c-be108fb371bc | note | SGJV Key - S
4348fa41-5f4f-5ad9-8f12-a28f67da0b14 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
8f05948f-1673-55ef-9fb6-d5d25fb8f3be | tickbox | Photo
| checkpoint | 3.2 - Moisture
38929dc3-1dc6-5ace-acc4-cf0ce13809b7 | note | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
b489ab23-9ffd-58fe-b24a-39f15636dfe2 | note | Acceptance criteria - Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
c48b2956-d3c4-5d42-bd0b-23c453973251 | button | Acceptance | Yes,No,N/A
3c39d6a0-1d2b-57eb-be84-7263f2f0625b | note | Freq - Each Lot
81d4a88f-fbc1-547d-ad61-aa95ebd2890a | note | Key - S
ea01eacb-6e42-5705-9b04-8b4cdb1fa91d | note | Resp - SE
15283e05-aab8-57d8-a1a1-62b422ed1ac8 | note | SGJV Key - S
3807201e-e1ee-517b-a080-a5061e6da0ff | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d75342ef-b498-5704-9ca2-985703b0d426 | tickbox | Photo
| checkpoint | 3.3 - Compaction
9fa8206f-2e48-5d2a-894f-0530bb3e4ed9 | note | Ref docs - IFC Drawings MRH/A0/B/0 0- CV/DWG00 40
617c41b7-90cf-5370-992c-1aefcc832614 | note | Acceptance criteria - Has the layer been adequately compacted achieving a mean value density ratio of:
dd0c4203-250a-5ad2-bdd2-eeefe9de02e8 | note | – Lower Subbase: 98% Std
c76c8659-0937-5cb5-aed5-782f5d23d9b3 | note | – Upper Subbase: 95% Mod
8d5983d2-090b-58b2-ab96-35b221049a7b | note | ○ 3 x tests to be conducted per compacted layer per approved lot map.
1fe10556-17c8-5492-a9fa-acabd25a7bc3 | button | Acceptance | Yes,No,N/A
9c28d922-d8b8-5faf-8e0a-d05afafc5568 | note | Freq - Each Lot
15c0377e-6a52-5212-8989-bfcee3a1c44a | note | Key - W
95e321e0-6f5a-5e9b-9bb8-d1ceae45f863 | note | Resp - SE
fd1c857a-3da2-509a-b032-7bbe4bd66ac6 | note | SGJV Key - S
de637f37-6142-568c-8863-55e8ed89b7b0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
f2be83b6-582e-5f11-9ed7-1b5ed3551bce | tickbox | Compaction test results
| checkpoint | 3.4 - Test Rolling
fcb90722-b7a2-5e5c-a433-1e880abf6b8a | note | Ref docs - MRH/A0/B/0 0- CV/DWG00 40
0217240d-8f6c-5bc7-8304-dde6e68f9d77 | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation of springing?
e7a589f7-f45f-53f1-90cb-04dce4313024 | textbox | List attendees:
44a04d0b-4eae-5c72-9ed2-ba5a32979fc0 | button | Acceptance | Yes,No,N/A
ec11b1af-1e09-5355-9b11-7f0802ef9bc9 | note | If ‘no’, please see sections 3.5 and 3.6. If ‘yes’, proceed to section 4.0.
e4b805b2-221e-559c-bda9-3f1f0814743b | note | Freq - Each Lot
03711441-064f-5c89-972f-592b8eb674a7 | note | Key - W
b3186e09-c8f3-56bf-9f37-8ce6182c7cf8 | note | Resp - SE
d065fefd-b05d-5517-a339-60965af18aad | note | SGJV Key - H
98f6b513-de20-594c-8e9f-b4f774361ce7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
07bf8e04-dcc0-5235-82e6-ab92ff24f9f0 | tickbox | Photo
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Identification of soft, wet or unstable material
e6f91614-0324-5983-a5a0-a8f98b3ab5b5 | note | Ref docs - N/A
ceacd760-7f3c-569c-894e-6ce8cf0599f6 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
7e982247-b34f-5cb1-95eb-c060a27233fb | textbox | Acceptance |  |  | m
51fbae31-cb4b-51d7-a0e1-cc7f07eb036b | note | Freq - As required
c63366b6-8566-5ebf-8a40-148d8de41ad9 | note | Resp - SE
0142d955-4c3d-5d9f-9283-77ba7cd1d87d | note | SGJV Key - S
5e37b384-bbed-53e0-a0ac-4d539c0838a9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
f25b69fe-0bd7-5b32-8b9a-e6f068534089 | tickbox | Photo
| checkpoint | 3.6 - Treatment of unsuitable material
38aa6cad-9a35-5066-822b-edbaa7d746d9 | note | Ref docs - IFC Drawings
b4aa9e6b-6cda-513f-9a56-343db27c0ff4 | note | Acceptance criteria - Has rectification process been submitted for review?
9adfbb63-90a8-5da2-a24c-a89826dd0d95 | note | ○ What was the rectification process used?
a5eca0c9-f428-592d-99d9-e03f3e4038e4 | button | Acceptance | Yes,No,N/A
b05643ef-6735-5e9c-86fa-b76468ca64ab | textbox | Process Used:
02d20dc4-1ab2-50c0-9a32-b5ad189fb73b | note | Freq - As required
f2290e9a-fc73-5974-8516-74d5752bb05a | note | Key - S
c7dc35e8-c57d-5709-b56c-71f72ce18773 | note | Resp - SE
7f5ffce3-e161-509e-85ce-b8d915cbc781 | note | SGJV Key - S
d7da5aa8-ab9f-54cd-98b5-39cb3a5e7391 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a8119965-5790-5b2c-9af9-ee61f2c99483 | tickbox | Photo
| section | 4.0 Pavement conformance
| checkpoint | 4.1 - Pavement Finish
4b9457d2-99a9-529e-97e1-6ddf086a33e1 | note | Ref docs - IFC Drawings
46dc9ca1-f794-5774-8bef-ec8f9d4b7461 | note | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
a33c5c63-5f01-59f3-88f7-dfe57073b5b3 | button | Acceptance | Yes,No,N/A
c4bfd35d-9851-53d2-b9a3-dd95a8883630 | note | Freq - Once
8c9af770-38c9-5c9b-b11d-297e86011085 | note | Key - W
3ab96c10-8b8b-592e-abc2-3f7a91001ae8 | note | Resp - SE
5bc57ae6-80c8-5721-8ee4-35783b02a38c | note | SGJV Key - S
866bc4e6-0ab2-5ad0-a0f2-6db145748e60 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
092ba37b-e982-5888-8616-c5d6be40ab90 | tickbox | Photo
| checkpoint | 4.2 - Width & Alignment
f73f51d6-880c-564b-8002-a33b2c7d80ae | note | Ref docs - IFC Drawings
722e5ffb-64cc-5c30-9a9a-38f848da5feb | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
2b5ae12d-ffd8-50b4-bc7e-61dbc4b1854b | button | Acceptance | Yes,No,N/A
cd342790-29c3-5be2-9a21-3436dc98706f | note | Freq - Each Lot
05fdf4e2-3894-548f-b1c2-0f154744ddf4 | note | Key - W
e33d6e1d-8dcc-507c-be6c-22af9d7e51d4 | note | Resp - SE
cfbf9e45-6fa2-5e94-81f4-7cebefcd9d93 | note | SGJV Key - S
5fb5a1bc-d944-59f3-bce2-5e7135cea0b2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
aedba9a5-cc60-58a7-8af1-5a0d4901d5c8 | tickbox | Photo
| checkpoint | 4.3 - Surface Level of Pavement Courses
e3fd8f63-6bd6-542e-834a-fa5593f76b66 | note | Ref docs - IFC Drawings
dfe73c49-8ff2-589f-b7eb-af60b6155e15 | note | Acceptance criteria - Has the prepared layer been surveyed in accordance with and verifying specified requirements?
c75d2b57-bc68-513a-b132-67c9cfd590d2 | note | ○ All crushed rock layers: Mean Range: +10mm to - 10mm
e2c4e313-f125-50fc-973c-57c4d8aae5c1 | button | Acceptance | Yes,No,N/A
0654bd4e-3b57-5067-9592-a1f9bb960eab | note | Freq - Each Lot
a083a307-082d-5e16-962d-d180c5e69336 | note | Key - H
f5e8aa4d-7fdc-5421-a9bd-358ec12ca9ca | note | Resp - SE
feccb9a8-dcdb-58e7-a68a-a0135398c429 | note | SGJV Key - H
b36b5fd9-8cc9-534e-929e-28155b5e9756 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
36b6ae7c-b0b9-5f7c-b812-0f2f4c3e8e70 | tickbox | As-Built Reports
| signoff | AUTHORITY HOLDPOINT
| checklist | CC0408 - ITP-002 - Site Clearing | itp | CC0408 - ITP-002 - Site Clearing |  | 5d42cac3-661d-483f-a5e7-87793f160408
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Determine Lot Size
462f1040-f0c3-5811-9978-c391eff79f0c | note | Ref docs - N/A
56024a19-38d0-5ccb-b1a9-4d8297ea1da2 | note | Acceptance criteria - What is the lot size?
7010f33c-e02c-58e8-8f26-e8e9c2145001 | textbox | Acceptance - _________ m2
b87ddae9-a254-585b-853e-3407ccb538eb | note | Freq - Once
0d165fa0-9979-5a3d-8465-321ad61820c0 | note | Key - S
4d055781-add5-507e-973b-ca15fd71150b | note | Resp - SE
7a039d0e-1b3e-59ed-aeb6-648b71fdb15d | note | SGJV Key - S
49e94bf0-b3a4-5460-a0cd-ac2504d0543e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Work Lot Map
| checkpoint | 1.2 - Safety Ensure that the following items have been actioned:
c27db111-5fcd-5e9f-be50-a73d9af52d28 | note | - SWMS if applicable
48bea335-734d-5114-b6a6-744a158db583 | note | - Plant Pre-start Inspection
d6e02f15-4f62-589d-9e2c-12022a8734ae | note | - Service locations identified
f0e56c53-2219-5adc-9982-8cf1742238ae | note | - Traffic Management Plans (if req’d)
d29aac46-d166-5c11-a42d-6112c8f38220 | note | - All staff inducted
e0270f63-097d-5cbe-bb56-e58665409c66 | note | Ref docs - SWMS TMPS Plant prestart inspection form
848d00ab-9fc9-5e16-a239-9e3b1925caf0 | note | Acceptance criteria - SWMS submitted reviewed and accepted if required. Personnel inducted to SGJV requirements. Plant inspections completed and entered. Pre-work briefings completed. Service diagrams available and services located.
c7693eb2-b076-548e-99f2-b6e190e8d097 | button | Acceptance: | Yes, No, N/A
0864bfeb-8df1-54a8-a14c-6156912c2f27 | note | Freq - Once (Pre-Start)
fb8a09f8-6773-53c2-8a84-9b899cf144e7 | note | Key - W
93b9039b-3459-5adc-b764-e2756a3da801 | note | Resp - SS
87fe9ddc-6a83-5b40-9b24-88ac428997d9 | note | SGJV Key - S
18549c73-078f-548b-93c9-a96352db0a23 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Hard copy of the SWMS (if required)
| checkpoint | 1.3 - Excavation Permit
ff5b4cf3-a611-5ff2-8bf8-fbce03ffeb6a | note | Ref docs - Excavation permit template
1230e542-aafe-5d8a-83dd-f6c3ce84c8d5 | note | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
f8e8723f-1aba-5a1f-9c17-b7b5bbb05dea | button | Acceptance: | Yes, No, N/A
db6d6def-7671-53b4-acb2-47d4c7864c90 | note | Freq - Prior to start of works
b50bbafe-ea47-517b-9f40-de2884d1eab6 | note | Key - H
4fc810a4-919c-5780-909d-48f8f9a91f65 | note | Resp - SS
d79d694c-f649-5631-b4da-0be295083419 | note | SGJV Key - W
cf2dc777-fa8b-53ce-8705-05f4cc600e43 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Signed Excavation Permit (if required)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Check Survey Set-out
c3ae8f67-e151-51f5-9f17-26d2d3206b61 | note | Ref docs - N/A
fd849aa8-0d04-58fc-9675-205b1ef1ae99 | note | Acceptance criteria - Survey setout extend of works
e8ce5e41-d9bb-551d-a778-0236bd77507b | button | Acceptance: | Yes, No, N/A
65e22e5e-a8e3-52f1-bb88-8295450a3514 | note | Freq - Prior to start of Works
b8442198-12ed-5e74-baf3-5cb1cdc414f2 | note | Key - H
5e04d33f-b46a-52f6-9dd6-8bbee7533f43 | note | Resp - SV, SS
fcb62bb4-1c92-5e97-a5ce-50c936f0f77b | note | SGJV Key - W
5f814617-5773-5e44-a6e1-24083db300c3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - N/A
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Clearing And Grubbing
| checkpoint | 2.1 - Clearing and Grubbing
c992ee7b-6099-53a9-925a-f785d74a5587 | note | Ref docs - MRH/00/P/00-PM/SPC/0003 (Rev 3) Page 53
cee7d355-c8ba-5ac2-8a08-f1e1a729f669 | note | Acceptance criteria - Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface? In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed. Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material.
c1fdd0d5-7b98-57d5-a1d8-38997950fe38 | button | Acceptance: | Yes, No, N/A
0b8745ec-9ea5-5468-ad81-8628fbc307a5 | note | Freq - Once
88e2acb0-66fb-5606-a8fa-62e35137031e | note | Key - W
585cc152-8e74-5f32-a03d-e16ea689d377 | note | Resp - SS
0ed10a11-dd94-53df-b73f-cbae90f329af | note | SGJV Key - W
830a9505-032e-5e85-b8a4-f78fa7b5ce65 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Visual Check Photos (if required)
| section | 3.0 Topsoil Stripping
| checkpoint | 3.1 - Stripping
99077738-44d2-5343-b20b-69929d7664ae | note | Ref docs - IFC Construction MRH/A0/B/00-CV/DWG/0008
b068af28-8c72-57f1-927e-55908fba05ae | note | Acceptance criteria - Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free-draining?
541d5992-8bfc-50d8-b174-7be21c41cbb9 | button | Acceptance: | Yes, No, N/A
73b27fc5-9286-5486-9eba-29a9e6342faf | note | Freq - Once
47c28e04-ff16-5130-8536-a341c9aacd6f | note | Key - W
11e96279-fd00-5ef3-9570-89b45da6135a | note | Resp - SS
8b7f49d0-5893-5502-ad34-53d1ee785e24 | note | SGJV Key - H
78763107-cc93-5bc8-9d01-2d4a69b831f3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Visual Check Photos (if required)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Topsoil export / stockpiling
2110f7dc-8dbe-515a-ba31-42654943f3d0 | note | Ref docs - IFC construction drawing MRH/A0/B/00-CV/DWG/0021
83b23d88-618b-5877-97f7-5a8b13ec089d | note | Acceptance criteria - Has the topsoil being stockpiled been approved by SGJV (where applicable) and silt fence around the stockpile present? Have the environmental controls as per CHMP &CEMP and Enviro/Biodiversity Assessment been adhered to. Dispose material as per CHMP and Enviro/Biodiversity requirements
79e7afdd-4b7d-5fb3-8bf1-e83933eb581c | button | Acceptance: | Yes, No, N/A
ab319f2d-e8a3-55f0-80e8-120b057cb84d | note | Freq - Once
5446ffcc-d3bf-5b5c-ab8b-df2da7c89e38 | note | Key - W
263577fb-3b40-537b-8493-353f38af0e89 | note | Resp - SS
f03f3dc7-260d-53a3-987d-ef10ad2e63ff | note | SGJV Key - H
064734dd-65fe-5b53-89cc-985b475eea4a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Stockpile Plan Photos
| signoff | AUTHORITY HOLDPOINT
| checklist | CC0408 - ITP-003 - Bulk Earthworks | itp | CC0408 - ITP-003 - Bulk Earthworks |  | 5e5f8ede-5643-48f9-8d66-2fc499579ba0
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Determine lot size
26a4f566-a113-58a4-898f-e66250304ee0 | note | Ref docs - N/A
bf051afd-526b-5d7b-89c6-170cde50aa14 | note | Acceptance criteria - What is the lot size?
13b37902-3455-5f46-b2d3-d205c6c9862a | textbox | Acceptance - ______________________ m2
0fe3d9a9-1bdf-5a7b-ba0b-eecddd1e4881 | note | Freq - Prior to start of Works
6bc68c0b-b2de-530d-a9ff-0a9828bfbb2d | note | Key - S
765fd910-9f3f-5c68-8cd3-604f6bc609c2 | note | Resp - SE
744eb43d-679d-5c1e-b77a-aca04523398f | note | SGJV Key - S
31633d3e-4dff-52fc-88c2-f346c347b572 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Lot Map
| checkpoint | 1.2 - Survey set-out
2f797d77-1d58-53d8-8e02-4ac8c6c1470e | note | Ref docs - N/A
ab6436ad-a00f-5946-9632-0f38bb545ce0 | note | Acceptance criteria - Is the most current survey file what the team is working to and has the work area been set out for line and level?
94cf3c86-5f86-576e-9d74-781e3eabbbb6 | button | Acceptance: | Yes, No, N/A
14f2a155-b158-5c89-82f8-2bffc125e2f8 | note | Freq - Each lot & Each possession
57f0598a-65a6-5028-8493-8ed6fdd9bbad | note | Key - W
58416a04-90cd-56cf-ab28-ee7e63ade001 | note | Resp - SE
dc7c2872-2313-59e0-9823-79c5b7930c1f | note | SGJV Key - S
53ffdeab-035c-53af-908f-9bc4f3fe4ea0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - N/A
| checkpoint | 1.3 - Water management
25cee85b-1773-5df3-9b67-07187bbaab58 | note | Ref docs - EMP
16f817f6-800d-5e9b-9b0a-54002fe272f3 | note | Acceptance criteria - Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation? Are environmental controls set up as per the site EMP?
e1afd636-bb27-508d-9007-c9a0b3d70d04 | button | Acceptance: | Yes, No, N/A
c51fe832-049d-5bb6-b09f-afe33ac5ff96 | note | Freq - Each lot & Each possession
f3c1f09c-8783-57ff-b48d-ed8670af59c9 | note | Key - S
76a21ca8-00ae-5e4d-92df-1083dad44478 | note | Resp - SE
73f86bcc-f48d-5f6a-9f32-a5445cf6c4fa | note | SGJV Key - S
9de514c7-9cc5-5ebd-9b8f-2c05fa2fcda4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - N/A
| checkpoint | 1.4 - Clearing
ad54f9f7-b13c-5614-ab16-d20680a977a5 | note | Ref docs - CC0408- ITP-002 or MRH00B00-QAITP0001
92b66184-35dc-540a-b7bf-038861f77505 | note | Acceptance criteria - Has the area been cleared and grubbed in accordance with CC0408- ITP-002 or MRH00B00-QAITP0001?
c9960fb8-a694-5d0c-9943-f0b5cfdfb628 | button | Acceptance: | Yes, No, N/A
761616e4-85c1-5d6d-8060-61ce22fd7314 | note | Freq - Prior to start of Works
c0d87e23-fd5c-5e6b-bfa5-b0333c7afed6 | note | Key - W
f06fcd17-d73e-5bdd-a13f-1e23eb49d132 | note | Resp - SE
75509ddb-9139-57f3-af59-fb0a95b24840 | note | SGJV Key - S
23c16c2a-9a5e-567f-bc9d-b2ca2ff8ae9d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - N/A
| section | 2.0 Bulk earthworks - Cut
| checkpoint | 2.1 - Excavation material classification
b998a175-96ff-5098-be2e-ba2d533d3128 | note | Ref docs - MRH/00/P/00-PM/SPC/0003 Rev 3; Page 53
474ae076-3bbe-5a31-8281-e9aa8409474f | note | Acceptance criteria - Has the material being excavated been inspected with category agreed upon by Superintendent? Tick category below:
1f7b6f9f-7e56-5e3e-bf73-636d9e41aca8 | tickbox | Topsoil:
a2cb9777-a0e2-5abe-a1e3-600f2986beaa | tickbox | Unsuitable material:
5584b6d0-49f0-5564-9c8e-c79f3331fe42 | tickbox | Fill material:
06cf10bb-1689-5872-acff-4c0797d233ce | tickbox | Other:
d57d2e7c-7eaa-53f5-90c6-9a9be60d285b | textbox | Other:
e53fd7f0-8441-5bda-a213-c543657e9ea1 | button | Acceptance: | Yes, No, N/A
d91e12c2-37e3-58a8-af55-be3356b012be | note | Freq - Prior to start of Works
c1714027-461f-508d-83bd-884d291a6293 | note | Key - W
ed78048b-d070-5538-8ac3-06ed9341a3a9 | note | Resp - SE
042a2827-58aa-5821-9ffd-718d04d7572c | note | SGJV Key - S
d9201fe8-3e0e-56bc-bfa9-2896c7c717ca | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Test reports
| checkpoint | 2.2 - Stockpile
f9493f30-e631-5998-b609-2e70f189ebf2 | note | Ref docs - N/A
63d6b51e-a1c8-5230-bc53-3bf493b8e29f | note | Acceptance criteria - Has the stockpile location been approved by SGJV.
af94f092-eff4-5109-85ee-7daf0b42ae5c | button | Acceptance: | Yes, No, N/A
293fa4cc-a4c3-5edc-bf28-8e8a5559609e | note | Freq - Prior to start of Works
3e7ad70c-11b7-5e2a-9f9d-b55fdecbe879 | note | Key - H
a8da3258-496d-5b03-b106-3314a60015b2 | note | Resp - SE
5a60a79c-6181-5ce6-9fee-8c5666a29eb7 | note | SGJV Key - H
ff6879b1-131e-583a-ba51-533f959ab3a3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - SGJV approved stockpile plan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Subgrade preparation or scarification
2009a8d8-20ee-53ed-b77e-afc65d3d061f | note | Ref docs - MRH/A0/B/00-CV/DWG/0040
765d2390-70b4-551e-9195-ccf886614ec2 | note | Acceptance criteria - Has the cut surface been trimmed to an even surface free from loose material or scarified/ripped? Have surface levels been checked to avoid over excavation?
05080509-3342-5f93-944b-015f72b26cbb | button | Acceptance: | Yes, No, N/A
1c72a2d8-5077-53e8-a347-ea9399a1eebd | note | Freq - Each lot & Each possession
7096b8d5-cfb9-5191-b8cb-9c310c4766eb | note | Key - S
5ebe7298-3080-5558-bc28-dc3c12fef3c4 | note | Resp - SE
c9df6f59-a0a0-53a0-822e-e1c2ebad3f4f | note | SGJV Key - H
b119a980-aab1-5492-af95-906e7a7f87ca | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test reports/as-built survey
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Compaction
200a1259-60c3-59e8-8742-5452c2ea202f | note | Ref docs - AS3798 Table 8.1 MRH/00/P/00-PM/SPC/0003 MRH/A0/B00-CV/DWG/0008
7899147d-af6b-58a3-a768-3e66697ce046 | note | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2 Has the subgrade been adequately compacted achieving 100% SDD? Is the subgrade material within +/- 2% of the optimum moisture content. Has the layer thickness conformed with Item No. 4.2 ‘Acceptance criteria’ ?
2498aa92-e085-5c1c-92e9-3952ff577007 | button | Acceptance: | Yes, No, N/A
1f779a32-dd69-5048-b586-13aac5726532 | note | Freq - Each lot & Each possession
27f061ea-1eff-524e-b9b8-bca8e62ca501 | note | Key - W
0bd77b74-ef4c-5062-a379-39a41be1132b | note | Resp - SE
7192e4a8-8471-5588-ab3c-a88dd1e4a1b9 | note | SGJV Key - S
47e355f6-2b41-5ebb-a9e7-7775b24c933e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Test reports
| checkpoint | 2.7 - Test Rolling
036f574b-0d62-594f-9719-b088ceab5b74 | note | Ref docs - MRH/A0/B/00-CV/DWG/0040
4a78f542-d1f3-5a74-9ea3-36bf3ef6187d | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
6c2cf820-522b-5dfb-b8b1-63a83cc677bd | textbox | List Attendees:
ffb8b6bd-874e-50ee-b036-f4030366b307 | note | Type of equipment used:
37e64f8b-bc0d-5a92-b2a4-0f04d65e062e | tickbox | Water cart
a7d5afb4-ca10-57c5-bf62-a0dd6a8e1dd2 | tickbox | Tandem
6544ca19-c9d2-53d8-a249-b330649bb132 | tickbox | Other:
020e170a-6beb-5c92-8c4a-ec869b6eeb01 | textbox | Other:
456b6f5f-df73-569f-a83c-3431e58aecf6 | button | Acceptance - If ‘no’ please see below. If ‘yes’ please proceed. | Yes, No, N/A
91c9b267-e100-5726-98f6-3e5205dfbb62 | note | Freq - Each lot & Each possession
dd093ffd-b437-50e7-8928-34ca49cb8e4c | note | Key - H
0ad065ed-6914-56a8-ba30-33a32ca5c60c | note | Resp - SE
31ad3624-3c47-500f-bcb5-34c7c68f05d1 | note | SGJV Key - H
3c668716-5050-5b22-ad2b-d339de66b0a5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Proof Roll Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material
15b1a525-7d3f-53b3-8fe3-c9d177eb617f | note | Ref docs - N/A
177e87c2-a80e-505f-b833-b10b9d07024c | note | Acceptance criteria - What quantity of soft, wet, or unstable material is present?
dcfe4a61-593d-530d-8111-508d4696307b | textbox | Acceptance - …………………. m2
3da9b9f8-6aed-5699-bfba-00a11e26d11c | textbox | Acceptance - ………….……… m3
45c9cc56-f9b4-5053-9603-dcc80f1f550d | note | Freq - As required
075b7434-bab6-5a4b-9871-f6ed39aa508b | note | Key - W
3ce3ce59-3219-5d8a-b6cd-ef7b9da81e4e | note | Resp - SE
2f0ea146-5236-521a-9967-f91a48b398d7 | note | SGJV Key - S
047a6363-6508-5d89-bc8a-c553359ca7d7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos (if required)
| checkpoint | Treatment of unsuitable material
137d316d-072c-5ab4-83a7-4a30f401e5cb | note | Ref docs - N/A
3838ebbf-ecd6-5705-813d-eb86176e6b78 | note | Acceptance criteria - Has rectification process been submitted to SGJV for review. What was the rectification process used.
8b38a62f-3027-5e8a-8119-33c8012ad485 | button | Acceptance: | Yes, No, N/A
e9179781-8a26-5290-8436-9831a51f7a9e | note | Freq - As required
4bbbeb12-8aa2-5cc3-921f-ac17bbce9549 | note | Key - W
d682eccd-4d30-51a7-92a1-29098f03740e | note | Resp - SE
3220720a-79ac-5f58-9246-9402648c26ad | note | SGJV Key - S
0e36b681-0ea9-5df2-977d-0ca867823e27 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
e4748fba-f8c5-5047-9aa8-4d74d20e9f21 | textbox | Aconex Correspondence:
| section | 3.0 Bulk earthworks - Fill
| checkpoint | 3.1 - Fill material classification
41f93ab9-6ae0-5bb0-b0b0-e4bf2f43935b | note | Ref docs - MRH/00/P/00-PM/SPC/0003 page 53
6f37d567-e416-5a5c-a874-593d362742f5 | note | Acceptance criteria - Has the material to be used as fill been approved for use?
2e4c97e5-d021-527d-9c44-bc39d21cc02e | textbox | Material Type:
76b31f1f-a806-598c-9594-4f5ce8c01f3c | button | Acceptance: | Yes, No, N/A
06c640fd-5948-5d95-ab19-8497e876b733 | note | Freq - Prior to start of Works
4102fc11-e747-5146-a766-bb7e64f6ab55 | note | Key - S
a220068b-7341-5607-bcc2-8fc99d6adb8c | note | Resp - SE
8e875835-9688-521e-8d58-9a4e44226863 | note | SGJV Key - H
0d45d52d-a422-5095-902c-f4bfdb4d2e21 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Material Acceptance correspondence/Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Stripped surface - test rolling (If applicable)
5d48487f-3d4b-5095-98f5-bbc9cdb202f4 | note | Ref docs - MRH/A0/B/00-CV/DWG/0040
2f91edbd-7fa9-5ae4-ba80-3b55ef1753aa | note | Acceptance criteria - Does the stripped surface to be filled withstand test rolling without visible deformation or springing? List Attendees:
0b1764ec-52ba-5886-97ea-237314ba95d9 | button | Acceptance - If ‘no’ please see below. If ‘yes’ please proceed to item 3.3 | Yes, No, N/A
513324d2-7cae-506d-ba05-b167ac0288bd | note | Freq - Each lot & Each possession
c231ad22-99e9-55b1-ac5b-00f49d65b6ac | note | Key - H
878fc0ad-4d7e-5cd1-9d8b-92e0f262b790 | note | Resp - SE
29c630f2-8e7d-55f4-9ee4-067d8f628ad3 | note | SGJV Key - H
6358983b-5506-5f7b-809b-f0fd5b1d62d9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Proof roll checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material
1391c6f9-75d9-56ca-aa16-e873936a47ec | note | Ref docs - N/A
c879ff19-992f-51a3-87e3-8997550508ec | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
f9b9bd69-f902-5702-bcef-88d12cee9896 | textbox | Acceptance - …………………. m2
fb3b0ac6-3881-5189-bf2a-52fd42fc11f4 | textbox | Acceptance - ………….……… m3
b4ef1cf4-dc0b-55b7-8400-2f0d37831371 | note | Key - H
9260e5ee-cde4-5c7e-8442-9c678c00cb72 | note | Resp - SE
31fe0798-6caf-5616-8e07-31e62dd64512 | note | SGJV Key - S
d42eb660-bc42-56ac-aa2c-1098a71dcab4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos / Visual inspection
| checkpoint | Treatment of unsuitable material
0caec834-34b2-5a58-abee-141b4cc67b46 | note | Ref docs - N/A
d0fe2c2c-0970-5e05-aba8-16550322eff8 | note | Acceptance criteria - What rectification process is to be undertaken
175e9fca-ecbe-5149-ace0-a64fcbae3d0b | button | Acceptance: | Yes, No, N/A
a33db33c-2773-5183-ad01-f2ef28d2bb5f | note | Freq - As required
fea5030b-e170-551e-a19b-50f9f4758deb | note | Key - S
eea961ee-5326-514a-a292-4f6c0e188c2c | note | Resp - SE
2290ca69-cc16-574c-b9eb-f98b307e9e38 | note | SGJV Key - S
f7874f5b-5f72-54a2-9c86-f910f44d5f61 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Aconex Correspondence /Approval from SGJV
| checkpoint | 3.3 - Preparation of surface
cba37e45-aca8-5d97-b5a2-44eeb2a43714 | note | Ref docs - MRH/A0/B/00-CV/DWG/0040
48a3aa6d-f606-5b4b-ac1a-20c482817bac | note | Acceptance criteria - Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
2e33c197-7ac3-517d-a22c-ddb42dc5a328 | button | Acceptance: | Yes, No, N/A
0cf2dd85-4e16-55c7-9815-5317300c4370 | note | Freq - Each lot & Each possession
daad768d-33c5-5af3-9ed9-4a3624e808ec | note | Key - S
dd872267-5151-5a8e-9e54-24b4f2140ac6 | note | Resp - SE
6d95a5db-948e-5c84-b505-71f8638855ca | note | SGJV Key - S
ccf14204-c15f-51cf-9b30-4e556bb802b4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos (if required)
| checkpoint | 3.4 - Fill Placement
73062c55-1206-598e-8a9f-62bfcb507a65 | note | Ref docs - MRH/00/P/00-PM/SPC/0003 MRH/A0/B00-CV/DWG/0008
15326341-101d-5255-af9b-0ae73fe1274f | note | Acceptance criteria - Has fill been placed in maximum 200mm and minimum 100mm compacted layer thickness? Rock in the fill should be less than 75 mm. Fill should be free of clay and free from organic.
45d2d326-6d7c-59bf-94ee-96868a8b1d69 | button | Acceptance: | Yes, No, N/A
b84c95f6-0dab-588d-9f13-eba8b2678204 | note | Freq - Each lot & Each possession
39c91626-858d-5ceb-8323-1eb526e151a4 | note | Key - S
b519b0f7-dd68-5cef-a5df-296e5167d7b6 | note | Resp - SE
f7730e5a-3658-51fb-9fdf-3dc53b2a6c6b | note | SGJV Key - S
c0984823-5b32-5669-b29e-796a37a4d48d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos (if required)
| checkpoint | 3.5 - Moisture
af001538-17f7-5410-9715-91f211cc188d | note | Ref docs - AS 3798
8f50c88e-c0f6-552a-820d-d11310af1803 | note | Acceptance criteria - Has the material maintained at optimum moisture content (within +/- 2% of optimum moisture), with additional water being added if required during compaction?
a6c65eb6-bb16-5f23-a81f-7bac8383aa59 | button | Acceptance: | Yes, No, N/A
b0288e5f-00ff-5238-a71b-f75772b867d4 | note | Freq - As required
a454672e-3708-5bd8-bcd7-d72020dfe776 | note | Key - S
2f1a027f-214b-58de-b0ca-587efc7ce8c5 | note | Resp - SE
27343771-87d8-5679-aed6-9d71d7e1d723 | note | SGJV Key - S
33d4a47f-821a-500f-a4b0-618b51951932 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Test Reports
| checkpoint | 3.8 - Compaction
01d34351-4c4b-50e5-93a7-9df9ac9148d0 | note | Ref docs - MRH/A0/B00-CV/DWG/0008
df138d38-4a2b-58fd-b76f-ad0aebe18632 | note | Acceptance criteria - Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2 Has the subgrade been adequately compacted achieving 100% SDD? Is the subgrade material within +/- 2% of the optimum moisture content.
2a6eedb7-c7af-51f5-933c-ded1228621a2 | button | Acceptance: | Yes, No, N/A
29df278c-2430-59af-84c7-68b0c59893b5 | note | Freq - Each lot & Each possession
0322dc76-2609-5677-b7b3-f47b6af612f7 | note | Key - W
bf6e2f9e-6395-58c6-87a5-6597997e19b1 | note | Resp - SE
7b128c59-15df-58ab-a81c-5040ba27ea0c | note | SGJV Key - S
1eeb31a6-56da-566f-a248-0c47b98d67f6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc)
b7104403-8001-5a7b-b691-4a4ec772f151 | tickbox | Test reports
| checkpoint | 3.9 - Test Rolling
15248eea-77cc-5259-bea4-464c5afdd4b2 | note | Ref docs - MRH/A0/B/00-CV/DWG/0040
df12c39a-646d-53d4-accf-142c8b5a609f | note | Acceptance criteria - Does the layer withstand test rolling without visible deformation or springing?
65d826df-486a-5b72-aee8-ae0e4642caa9 | textbox | List Attendees:
d31cf1e5-f228-541e-9f59-9e702d1ba05d | note | Type of equipment used:
dfd32ea2-9593-5d52-8f77-de5f4ef7ddae | tickbox | Water cart
9bf5a31f-0be0-56d2-9f6f-fc1358461438 | tickbox | Tandem
94dba609-afae-54ed-abf8-154522d42f33 | tickbox | Other:
eb8e3f37-ed64-5f0c-a2e8-5969fb854588 | textbox | Other:
82f446a5-3f99-502e-8f0d-0ad3c912af0c | button | Acceptance - If ‘no’ please see below. If ‘yes’ please proceed | Yes, No, N/A
931486c0-53fa-59eb-97cc-8417de6e98f2 | note | Freq - Each lot & Each possession
e66e9263-e8fc-55ba-b0c4-7d79abd4130c | note | Key - H
8daebdc5-ad79-5bda-85b8-6870f35e90b3 | note | Resp - SE
b9da4eef-2cdc-58b8-9c10-65f6043c8ad9 | note | SGJV Key - H
d14a40d2-df77-560d-bff8-28b44b6dbbea | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ Proof Roll Inspection Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Identification of soft wet or unstable material
ae56535c-1c62-5c65-8d6f-ed6abd26bf65 | note | Ref docs - N/A
6bbcd298-7dc1-5dc0-b31f-29ba980b59d5 | note | Acceptance criteria - What quantity of soft, wet or unstable material is present?
3611ccb0-db90-5c8b-9166-a5bdfef10bd7 | textbox | Acceptance - …………………. m2
77589da4-f35c-5083-b285-6f1500583155 | textbox | Acceptance - ………….……… m3
b2ee19da-0132-510c-9428-85903b27293e | note | Freq - As required
38207ba9-d511-5fa0-adb1-6325ddf3d61e | note | Key - S
470ccbbf-f806-516c-b305-e18b869f6c6d | note | Resp - SE
f21e9878-2220-5900-91a1-85d22fcf750a | note | SGJV Key - S
a30d4bf0-0066-5e6a-96b7-122b485f7f9a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos (if required)
| checkpoint | Treatment of unsuitable material
414982e8-3bc0-50c5-909b-6b06fd82f8dc | note | Ref docs - N/A
02992eef-fab6-566c-a98a-a148b5127cce | note | Acceptance criteria - Has rectification process been submitted to SGJV for Review? What was the rectification process used?
79622195-498a-5776-a332-eaead75d75e7 | button | Acceptance: | Yes, No, N/A
f1b2e867-ede2-51e4-afff-fa2396920dd5 | note | Freq - As required
21f40852-7d13-5875-aaee-bbea2abde9a6 | note | Key - H
42eccce0-3571-53c7-ac2a-5cc450c37219 | note | Resp - SE
633c0e1a-e0b0-587d-a114-78c98ed538db | note | SGJV Key - S
92a236c7-2a88-5d52-a0f4-e292ee4304d2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - Photos (if required
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Conformance check
| checkpoint | 4.1 - Width and alignment
a488dd04-a089-5904-b9a4-b114aa899527 | note | Ref docs - IFC Drawings
0a10d02e-8c7f-5294-b987-eb9ba9ed0222 | note | Acceptance criteria - Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
046ba36a-ad9b-5ea4-9299-4d205aa59841 | button | Acceptance: | Yes, No, N/A
b665cd1e-463d-5751-a611-1d97567bab7a | note | Freq - Once
36538487-7015-5372-be74-1298732a218f | note | Key - W
e09da5f6-6305-5e85-ae5d-91c5dcdf02b5 | note | Resp - SE
8e25e31d-4dba-5812-9404-0fd6e552dc34 | note | SGJV Key - H
83c50c23-baef-506e-9da5-99b0926a8ba6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ As built report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Subgrade level and shape
02d6b32a-54af-51f5-9686-41f058a563fd | note | Ref docs - IFC Drawings
210ed9ca-5848-5d77-b3a1-70116c12d44c | note | Acceptance criteria - Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Is the subgrade within +/- 20mm of design surface.
d6480777-4ad0-5ea2-b9b8-128f0ffd7efa | button | Acceptance: | Yes, No, N/A
696145b9-e9a8-5f15-b563-4e6c9e329e4e | note | Freq - As required
b65ccbfe-18b2-5284-8986-86aac5b61c94 | note | Key - W
496d5b8e-16fd-5a1f-abb9-c3703bc13dae | note | Resp - SE
47371109-1a89-52e8-b140-810bbb8bf8da | note | SGJV Key - H
f62c5e9e-bb3c-53c0-8be1-fb338fc9228c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - - ☐ As built report
| signoff | AUTHORITY HOLDPOINT
| checklist | CC0399 - ITP-002 - Site Clearing | itp | CC0399 - ITP-002 - Site Clearing |  | b6c9e93b-9449-4246-8eb6-c7c3e8a269d2
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Determine Lot Size
fa6aa0d3-6fbd-5d08-9542-62ff5f9cd6bb | note | Ref docs - NA
37bf5f61-f090-5818-bd59-95a18fa6f3da | note | Acceptance criteria - What is the lot size?
71f90d1b-9938-543f-89d4-609944aaa6cc | textbox | Acceptance |  |  | m2
15f2d5a2-6b74-53d0-9f2a-2d7acba21af9 | note | Maximum lot size = 4,000m2
1dbd2382-9b52-5484-b6a1-f5662dad6610 | note | Freq - Once
2ab2c085-e6ae-5f4b-ace6-cb298a744af3 | note | Key - S
8e4a3194-a1c2-57ab-9aa2-0d6a747699de | note | Resp - SE
49736cf0-23f0-5dd3-9f91-9ff8bb978335 | note | SGJV Key - S
194cbccc-a508-5641-89a8-cdf3458aa84e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
4425d34a-d8db-5bde-894d-152688afa5bd | tickbox | Work Lot Map
| checkpoint | 1.2 - Safety
febc704e-22a1-5671-88b8-dbe14f429ab9 | note | Ensure that the following items have been actioned:
42177035-a4b9-5c52-9e4f-9745922f9e39 | note | – SWMS if applicable
f0a14876-4bfc-5d22-a120-38bcd0ed1ac5 | note | – Plant Pre-start Inspection
992ba954-4216-56ef-98b5-79399260eb38 | note | – Service locations identified
1970e594-e572-5b15-b6e9-00d0f528d6b4 | note | – Traffic Management Plans (if req’d)
6dd59c96-e8ba-5fef-8563-0f0303ce9ec5 | note | – All staff inducted
d510732e-ec28-59af-a8d1-62769051015f | note | Ref docs - SWMS TMPS, Plant prestart inspection form
bd7e84a7-185f-56f6-892e-209d81b7a7ad | note | Acceptance criteria - SWMS submitted reviewed and accepted if required. Personnel inducted to SGJV requirements.
642582fe-fe80-539f-8ed6-59aa8d33382a | note | ○ Plant inspections completed and entered.
db972ec8-cf7b-50fb-bf3a-2c414717f360 | note | ○ Pre-work briefings completed. Service diagrams available and services located.
a7ff4d88-50f9-5451-990b-aedbf8ca467a | note | Freq - Once (Pre-Start)
f8003a9d-330f-57b7-9516-d5963a98c967 | note | Key - W
67ebba56-1d05-5491-bc35-9b9e2e035f87 | note | Resp - SS
f4de7a37-88dd-5aa7-a736-386e9eb55827 | note | SGJV Key - S
ccbe2dae-2403-545a-a821-164e27785cf0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Hard copy of the SWMS, Plant prestart inspections, TMs present onsite at all times
| checkpoint | 1.3 - Excavation Permit
1df18ed3-c86c-5a47-abbd-d7f3ce3ebf9d | note | Ref docs - Excavation permit template
8ceda89d-2c9f-5fd0-a446-f163ca046825 | note | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed.
d9924235-4a0e-51a1-9e72-6366b4df8c81 | note | Freq - Prior to start of works
3a67c339-36b1-56ad-8e7b-bc5c9882525d | note | Key - H
fa4aa198-f8c2-5676-9ec0-694adaa055fa | note | Resp - SS
1fc3da6b-1e5c-5870-8ecc-7520f35b05b2 | note | SGJV Key - W
8adc5746-1f8e-5a02-84dd-1196f08298e9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Signed Excavation Permit
| checkpoint | 1.4 - Check Survey Set-out
07898a6c-310e-5a53-a63b-856e49021209 | note | Ref docs - IFC dwgs
10a81dad-3c54-5925-b917-c752faa9abfc | note | Acceptance criteria - Survey setout extend of works
f9e33d4a-7b24-551e-89ff-df3c3d9eb2e5 | note | Freq - Prior to start of Works
395513d6-6f8d-5ef5-8b25-ac71ccadc927 | note | Key - H
a02e2c82-1d10-5bd3-a3ce-42f017cd2323 | note | Resp - SV, SS
79f8afda-2e7f-5a73-bafb-b6f44b4d716a | note | SGJV Key - W
93e959c7-4708-5a42-944a-6bcf3faaedb3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Not Applicable
| section | 2.0 CLEARING AND GRUBBING
| checkpoint | 2.1 - Clearing and Grubbing
a4e9394b-1b6c-52c1-8d68-e4728e192fdc | note | Ref docs - MRH/00/P/0 0- PM/SPC/000 3 rev 3 page 53
fcba1a12-99c8-56a8-94bb-fbffc19544d4 | note | Acceptance criteria - Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface?
606ae166-f006-50f4-8fc2-60a93fbd15f4 | note | ○ In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed.
e9d9ffbd-a52c-57db-a251-30e264d3cab3 | note | ○ Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material.
b27b6084-b4ea-54dd-a3d4-eb0426eae0dc | note | Freq - Once
e992d33d-9639-5a57-83ac-0218a10256e4 | note | Key - W
291c0969-4f9f-5afa-a927-46f73730f0cd | note | Resp - SS
b8951575-1b12-551e-a162-a3db30ba73c0 | note | SGJV Key - W
4158c971-366e-5818-a443-c7a0e096f95f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Photos/visual check
| section | 3.0 Topsoil Stripping
| checkpoint | 3.1 - Stripping
426db09c-3bd5-5bc8-8e59-7eee36660441 | note | Ref docs - IFC Construction MRH/A0/B/0 0- CV/DWG/00 08
caa89280-eab5-579d-b4be-34612b8189fa | note | Acceptance criteria - Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free-draining?
1291c481-621d-588c-83d8-6d82858c6c0c | note | Freq - Once
5af0061c-ceb7-55a4-90e2-c1ac3711311d | note | Key - W
a7cce5ed-ffff-50ac-aca9-2dba849b3d6f | note | Resp - SS
e77bc4e5-79db-5891-9e40-7a638c3f89ce | note | SGJV Key - W
29e6b550-385c-596b-8bda-898ea62c28ee | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Visual/Daily reports
| checkpoint | 3.2 - Topsoil export / stockpiling
b2d794ca-a585-5622-8de7-71d36acb8111 | note | Ref docs - IFC construction drawing MRH/A0/B/0 0- CV/DWG/00 21
1da56003-c6fe-5dd6-aede-a118563b067e | note | Acceptance criteria - Has the topsoil being stockpiled been approved by SGJV (where applicable) and silt fence around the stockpile present?
f7b9fb80-a14c-571c-b3d1-e6f1cae125fb | note | ○ Have the environmental controls as per CHMP &CEMP and Enviro/Biodiversity Assessment been adhered to.
b95de389-702c-5a47-98d5-085e50b4d64e | note | ○ Dispose material as per CHMP and Enviro/Biodiversity requirements
d4515641-a51d-5e8c-89c5-38aac6103633 | note | Freq - Once
07c2f8bb-a768-536d-ba0d-54f089976a7d | note | Key - W
63303a2a-c233-5568-976e-5d3dd911da95 | note | Resp - SS
c58aa0ec-eee9-56cb-9221-f8130ce6aad8 | note | SGJV Key - S
e1ca632e-80c0-57ac-8196-99fe54f8a331 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Stockpile plan/Photos