## Sheet1
1.1 | Submission CHAR(AMP) approval of concrete mix design prior to commencement of project | Prior to first concrete pour | Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix grade shall be VR 400/40. Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 CHAR(AMP) AS 1379 | DN S002 PCHAR(AMP)S IFC | Verify | Mix Design ITP | HP | FH Engineer / Superintendent | 1.1 Submission CHAR(AMP) approval of concrete mix design prior to commencement of project | FREQUENCY: Prior to first concrete pour | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix grade shall be VR 400/40. Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 CHAR(AMP) AS 1379 | REFERENCE DOCUMENTS: DN S002 PCHAR(AMP)S IFC | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Mix Design ITP | HP | RESPONSIBILITY: FH Engineer / Superintendent | Date Completed: | 1.1 Submission CHAR(AMP) approval of concrete mix design prior to commencement of project
1.2 | Submission CHAR(AMP) approval of epoxy adhesive product prior to commencement of project | Prior to first epoxy pour | Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S004 | DN S004 PCHAR(AMP)S IFC | Verify | Superintendent approval Completed ITP | HP | Site Engineer / Superintendent | 1.2 Submission CHAR(AMP) approval of epoxy adhesive product prior to commencement of project | FREQUENCY: Prior to first epoxy pour | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S004 | REFERENCE DOCUMENTS: DN S004 PCHAR(AMP)S IFC | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Superintendent approval Completed ITP | HP | RESPONSIBILITY: Site Engineer / Superintendent | Date Completed: | FREQUENCY: Prior to first concrete pour
1.2 | Submission CHAR(AMP) approval of high-strength non-shrink mortar prior to commencement of project | Prior to first grout pour | Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S005 | DN S005 PCHAR(AMP)S IFC | Verify | Superintendent approval Completed ITP | HP | Site Engineer / Superintendent | 1.2 Submission CHAR(AMP) approval of high-strength non-shrink mortar prior to commencement of project | FREQUENCY: Prior to first grout pour | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S005 | REFERENCE DOCUMENTS: DN S005 PCHAR(AMP)S IFC | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Superintendent approval Completed ITP | HP | RESPONSIBILITY: Site Engineer / Superintendent | Date Completed: | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix grade shall be VR 400/40. Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 CHAR(AMP) AS 1379
REFERENCE DOCUMENTS: DN S002 PCHAR(AMP)S IFC
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Mix Design ITP
HP
RESPONSIBILITY: FH Engineer / Superintendent
Date Completed:
1.2 Submission CHAR(AMP) approval of epoxy adhesive product prior to commencement of project
FREQUENCY: Prior to first epoxy pour
ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S004
REFERENCE DOCUMENTS: DN S004 PCHAR(AMP)S IFC
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Superintendent approval Completed ITP
HP
RESPONSIBILITY: Site Engineer / Superintendent
Date Completed:
1.2 Submission CHAR(AMP) approval of high-strength non-shrink mortar prior to commencement of project
FREQUENCY: Prior to first grout pour
ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the PCHAR(AMP)S DRG S005
REFERENCE DOCUMENTS: DN S005 PCHAR(AMP)S IFC
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Superintendent approval Completed ITP
HP
RESPONSIBILITY: Site Engineer / Superintendent
Date Completed: