## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-000 - Client Pre-Construction Checklist | itp
section | Design and Submissions
checkpoint | 1.1 Submission & approval of concrete mix design prior to commencement of project
note | FREQUENCY: Prior to first concrete pour
note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
note | ○ Mix grade shall be VR 400/40.
note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 & AS 1379
note | REFERENCE DOCUMENTS: DN S002 P&S IFC
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Mix Design ITP
note | HP
note | RESPONSIBILITY: FH Engineer / Superintendent
date | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.2 Submission & approval of epoxy adhesive product prior to commencement of project
note | FREQUENCY: Prior to first epoxy pour
note | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the P&S DRG S004
note | REFERENCE DOCUMENTS: DN S004 P&S IFC
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
note | HP
note | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | 1.2 Submission & approval of high-strength non-shrink mortar prior to commencement of project
note | FREQUENCY: Prior to first grout pour
note | ACCEPTANCE CRITERIA: Ensure product adheres to notes specified in the P&S DRG S005
note | REFERENCE DOCUMENTS: DN S005 P&S IFC
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: Superintendent approval, Completed ITP
note | HP
note | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
signoff | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: