## Folder Structure
Site QA
Unit Types
Block A
|  | Unit | A01 | Unit Checklist
|  | Unit | A02 | Unit Checklist
|  | Unit | A03 | Unit Checklist
|  | Unit | A04 | Unit Checklist
Block B
|  | Unit | B01 | Unit Checklist
|  | Unit | B02 | Unit Checklist
|  | Unit | B03 | Unit Checklist
|  | Unit | B04 | Unit Checklist
|  | Unit | B05 | Unit Checklist
|  | Unit | B06 | Unit Checklist
|  | Unit | B07 | Unit Checklist
|  | Unit | B08 | Unit Checklist
|  | Unit | B09 | Unit Checklist
|  | Unit | B10 | Unit Checklist
|  | Unit | B11 | Unit Checklist
|  | Unit | B12 | Unit Checklist

## Checklists
Checklist | Bathroom Checklist
Section | Substrate inspection
checkpoint | All prior works done
Tile Slate underlay installed by others and checked if all the nailed in flush
Wall square and plumb
Showerbase installed
Ceiling installed and painted
Section | Waterproofing
checkpoint | Mapeband SA to wall and floor junction/ penetration
Mapeband SA Gasket to floor waste
Specified AquaDefence waterproofing 1st coat
Specified AquaDefence waterproofing 2nd coat
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to a acceptable finish
Section | Completion
checkpoint | Tiling complete
Photo taken of completed area
Sign off and handover
Checklist | Kitchen splashback
Section | Tiling
checkpoint | Setting out tiles according to construction drawing / Site confirmation
Primer applied prior to tiling
Full coverage of tiles with adhesive
Tile lippiness checked and to acceptable standard
Finishing trims & transition bars edge alignment
Section | Grout and silicone
checkpoint | Adhesive fully cured and clean properly
Grout work properly into all joint
Silicone applied to an acceptable finish
Section | Completion
checkpoint | Tiling complete
Photo taken of completed area
Sign off and handover