## project
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
58479811-00df-4750-ae81-f0985e2e0195 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA
c49c3b8a-4197-4061-979d-5d837afa21ad |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs
3bf1bb5a-df6b-41dc-95eb-80a270cd56fe |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3)
6b85dc6f-16f6-4944-98f3-e248af69d077 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1
1e6e1776-5e81-4e27-8ebe-04b94b61b67b |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AE5167 (AE001439) S/E
4fe1a1f3-36cb-4eda-a726-2df7bb24de1d |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AE5167 (AE001439) S/E | AE-ITCX-001 - Temp DB Checklist
dfd4af2b-7f97-4e46-88dd-7669bbf6d548 |  | checklist-sectioned | pass | 43cbec7221431bc53e63051a4660e949334e1f5cd955ebc450ae122009ae65de | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AE5167 (AE001439) S/E | AE-ITCX-002 - Monthly RCD Test Sheet
f27e9fcd-7706-49c3-a8f5-5567e27f3e18 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AE5167 (AE001439) S/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
a2136a29-b45b-45f8-91b2-c4a97048f1a0 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ028 (AE005482) N/E
ccdbb735-8daa-4f31-ac7e-6562ed86c186 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ028 (AE005482) N/E | AE-ITCX-001 - Temp DB Checklist
14a73310-35ba-47dc-89d0-b16b941cd759 |  | checklist-sectioned | pass | b247bedfb082f77200c004e2fcdc7a486b7b361b878a4ba9dedf8ec9d5326372 | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ028 (AE005482) N/E | AE-ITCX-002 - Monthly RCD Test Sheet
661323a4-dd58-48b3-8f77-bf6211692b1a |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ028 (AE005482) N/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
81f36e16-533f-4514-a8b7-c82d99b6f520 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4915 (AE002226) S/W
f3988591-abe7-44a8-8270-bf7dda82cf93 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4915 (AE002226) S/W | AE-ITCX-001 - Temp DB Checklist
6e632bd7-2540-4841-8300-1dece10f44c8 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4915 (AE002226) S/W | AE-ITCX-002 - Monthly RCD Test Sheet
72dc5f5f-b102-4410-91cb-f3ebaa417486 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4915 (AE002226) S/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
34c81446-7d4f-4070-8c78-be342ba107cd |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4214 (AE002785) Crane 2
1a719618-cd76-4a0d-b2b2-75ea1df55f35 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4214 (AE002785) Crane 2 | AE-ITCX-001 - Temp DB Checklist
00600307-7a78-444d-8174-6e8e9169bd2c |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4214 (AE002785) Crane 2 | AE-ITCX-002 - Monthly RCD Test Sheet
eb95b43d-7986-453a-a789-b5f96c86dbc8 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB4214 (AE002785) Crane 2 | AE-ITCX-003 - Mandatory Test for Construction Wiring
f7dce78b-5835-4138-be06-1151e078dc37 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ035 (AE005578) West of N/E core
642641c3-0bd9-405c-a25c-bbf65739160f |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ035 (AE005578) West of N/E core | AE-ITCX-001 - Temp DB Checklist
155d73cb-0b4d-4652-bc33-29d80511ab16 |  | checklist-sectioned | pass | 43cbec7221431bc53e63051a4660e949334e1f5cd955ebc450ae122009ae65de | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ035 (AE005578) West of N/E core | AE-ITCX-002 - Monthly RCD Test Sheet
39064bbe-0195-4db0-86f5-2d48872a0f05 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | AEQ035 (AE005578) West of N/E core | AE-ITCX-003 - Mandatory Test for Construction Wiring
a86b6413-545f-4b58-9362-e1e2d6848d94 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB5041 (AE002825) N/W
978e4171-fe5e-41d5-b800-35b17766e282 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB5041 (AE002825) N/W | AE-ITCX-001 - Temp DB Checklist
616441d9-5ec4-4f20-9020-d766c559ac78 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB5041 (AE002825) N/W | AE-ITCX-002 - Monthly RCD Test Sheet
a04823b0-132b-4e35-88f2-197f7aef8660 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Basement 1 | DB5041 (AE002825) N/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
357afb92-cfd1-4ccd-8ee7-63f72ec4d6e3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground
9e8dee55-5c85-4e14-a878-006d1f012929 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4513 (AE002959) S/E
a422a2dd-bf90-454f-983f-481460515f20 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4513 (AE002959) S/E | AE-ITCX-001 - Temp DB Checklist
9810479f-6c97-40e1-9b15-90163398f251 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4513 (AE002959) S/E | AE-ITCX-002 - Monthly RCD Test Sheet
c9f7130e-3a0c-4554-a4cd-3fdaa59f4e17 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4513 (AE002959) S/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
52a14809-1fb3-4e4a-a538-44d31bf0926b |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4608 (AE002798) N/E
1c7badbe-5e69-49a8-bdad-4e865d08e2ab |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4608 (AE002798) N/E | AE-ITCX-001 - Temp DB Checklist
f487d3d7-321f-446c-95e8-4b89185f34b0 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4608 (AE002798) N/E | AE-ITCX-002 - Monthly RCD Test Sheet
afb2ab7d-30d3-484e-bbfc-231276e01024 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4608 (AE002798) N/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
7fbe4d3b-c0f6-4054-a1fd-9bcf450e1364 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4656 (AE002050) S/W
a6b90861-5770-4056-8d67-1fcd6c109dc2 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4656 (AE002050) S/W | AE-ITCX-001 - Temp DB Checklist
7c591c3a-0a85-4cc9-9803-47229f7ea2f2 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4656 (AE002050) S/W | AE-ITCX-002 - Monthly RCD Test Sheet
d2e1ed2e-96d6-42a9-9cbe-9090ebbfa950 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4656 (AE002050) S/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
547b8cf4-381b-48a7-b154-7a38102fb8b9 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4327 (AE002199) N/W
df655b5d-da08-40ca-8130-5f892e05bd6a |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4327 (AE002199) N/W | AE-ITCX-001 - Temp DB Checklist
63a9905a-da44-4bab-84dc-8181f2a848ce |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4327 (AE002199) N/W | AE-ITCX-002 - Monthly RCD Test Sheet
03bd9cc7-e737-4222-98d8-b4a59b74a5a9 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4327 (AE002199) N/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
8e7377e0-92f6-42c0-bd72-0d348234bb30 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4667 (AE002039) N/W
90a57eea-6e0d-4c62-86d5-9b1c40fc774c |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4667 (AE002039) N/W | AE-ITCX-001 - Temp DB Checklist
4c1b216f-9e83-4261-a60b-fa2b2f2adb8b |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4667 (AE002039) N/W | AE-ITCX-002 - Monthly RCD Test Sheet
d46b26e4-4b81-4b2d-a1b6-96c76f6e06d5 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | DB4667 (AE002039) N/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
1123c74a-3d84-406e-afe2-afc3a296d8e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | AE XXXX
e6d57403-66ee-42cf-bafb-b2c1a2d6f1b0 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a769c506-f8d9-419c-86e6-90e74d694d7e |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
1afd7c0b-aa45-43f3-9044-1cb1265c2022 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Ground | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
16de07af-e9ad-4e8d-a4fc-bf3cfcae4edb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1
d0dc2b6f-5bf8-4ec1-b88a-7e222ee09e78 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AEQ047 (Concourse) East
cdc50833-515d-4d71-9934-f84aaa0f1400 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AEQ047 (Concourse) East | AE-ITCX-001 - Temp DB Checklist
0ecb7046-1126-4800-a078-e2ece615209d |  | checklist-sectioned | work-in-progress | 87f90e51ae340061e20e95dbe0d6ec1a14d4d5e6089d2c90d3329e2535fd4045 | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AEQ047 (Concourse) East | AE-ITCX-002 - Monthly RCD Test Sheet
356385fa-f6c2-490f-9a2b-5d8b634cc3d2 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AEQ047 (Concourse) East | AE-ITCX-003 - Mandatory Test for Construction Wiring
670faf1c-bbac-436d-ba7f-1ad7c37b08c6 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4666 (AE002184) S/E
3900d040-9817-45d1-9098-49c83200c52c |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4666 (AE002184) S/E | AE-ITCX-001 - Temp DB Checklist
8b2fd715-53ff-46bb-a9c0-18310a7a180c |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4666 (AE002184) S/E | AE-ITCX-002 - Monthly RCD Test Sheet
6da797b8-0778-49c0-98c0-02e721bfda8b |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4666 (AE002184) S/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
6cf21aeb-9698-4e8f-9108-7c092c9f070a |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4493 (AE002039) N/E 63A
e09830af-febb-42e1-a36c-2a2106e9ccf2 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4493 (AE002039) N/E 63A | AE-ITCX-001 - Temp DB Checklist
50899baf-d244-482d-8f13-dea99d0858fa |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4493 (AE002039) N/E 63A | AE-ITCX-002 - Monthly RCD Test Sheet
78e6e719-ac0a-49e0-b755-bdc9309e87a3 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4493 (AE002039) N/E 63A | AE-ITCX-003 - Mandatory Test for Construction Wiring
318761ce-15d1-4467-8683-8eb636fa8bf1 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4977 (AE002089) N/W
9c715f47-05bc-4e44-ac0a-0c8722c1fd7d |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4977 (AE002089) N/W | AE-ITCX-001 - Temp DB Checklist
05fbd2df-f1c7-4668-940d-0bf3c518e709 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4977 (AE002089) N/W | AE-ITCX-002 - Monthly RCD Test Sheet
cd1e3e56-c67e-4919-b20e-44fb5a27d023 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB4977 (AE002089) N/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
d9713792-f155-4c01-8524-22dd62762ba1 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB5004 (AE002302) S/W
453eef47-3b42-464c-a34a-6015f8ed3fd8 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB5004 (AE002302) S/W | AE-ITCX-001 - Temp DB Checklist
e2e81ab7-a2f9-4703-8f36-830f4cdcaf22 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB5004 (AE002302) S/W | AE-ITCX-002 - Monthly RCD Test Sheet
9098f66b-6850-43ac-8b8e-d076da644b27 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | DB5004 (AE002302) S/W | AE-ITCX-003 - Mandatory Test for Construction Wiring
ddb6211a-2335-47d5-b990-93c233b67bc2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX
f6eca9f1-2091-49ee-ad33-e3912dfea841 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
6b7b0ecb-d9b9-430d-a842-6a42ec12be52 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
8f05d54d-9395-4205-aeba-ba1eae6272da |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
bf05b52b-3fd9-4444-8619-25a74df62aef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX
f7a03b34-7248-4dad-8319-b15bb82c0f50 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1ff60aaa-08ac-4063-be31-c412b94c7660 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
d6eb2bbb-0b26-4db3-9be8-81eaadc05a61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX
95dabc65-b7cc-418a-9cde-bebb1fd92e7d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
98032787-669a-4837-84e7-9aed0905ffa3 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8f5c9cc0-2df7-4392-a8d9-418a9f1075ec |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
20f43755-4230-4fe4-8606-579a3132376d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 1 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
4ecaee8e-f1e2-4135-9bc6-6a1794b2e856 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2
4ca707a6-4c25-480c-b627-5a971cb1fa0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX
e88d9f4c-257e-4a32-a961-1a4c559efcd3 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d722e62f-b86e-4513-be4b-d33d00e7d4a6 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a80e77a1-2a78-4ff3-a503-0f871a86b163 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
e67716a9-9435-4adc-94bf-55433d1beb5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX
ce4cc63f-601b-4146-b994-2ef311f13fde |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1564b895-01d6-49cd-8477-7d740d763b69 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
b06ae6a0-c1b0-48cc-be0f-dea4eb2ee0ff |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f254b3d4-8eab-45e8-8f51-6a794143ef9b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX
44df81d7-2856-4ac1-9071-8151dbf7ea9c |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
4da5c7bc-4a6d-4055-a0d0-69cf214629ee |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2fc22ff2-2c6a-4b51-94e6-10b2931450fb |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 2 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
56d6204d-ee37-4361-8b6b-14229f655eaf |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3
47f915fd-c5fd-48b9-8afd-befdf7b6d55c |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4466 (AE002250) N/E
771cd40d-3f19-4f35-9817-fdaae87ef870 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4466 (AE002250) N/E | AE-ITCX-001 - Temp DB Checklist
0d270459-f56d-4363-b156-1e9f40f30a29 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4466 (AE002250) N/E | AE-ITCX-002 - Monthly RCD Test Sheet
cdd76057-9da8-4f1b-a58b-9dc54622af33 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4466 (AE002250) N/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
b8040c30-d5ab-450a-9a45-ef358359a2e0 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4603 (AE002585) S/E
ddc2701d-c717-42ab-8e44-2e309fb731dc |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4603 (AE002585) S/E | AE-ITCX-001 - Temp DB Checklist
f0c447b9-5df0-4edc-8cf6-8ecd7d8b182c |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4603 (AE002585) S/E | AE-ITCX-002 - Monthly RCD Test Sheet
c315714e-4d05-4e83-8f8b-cd26024bc824 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | DB4603 (AE002585) S/E | AE-ITCX-003 - Mandatory Test for Construction Wiring
3f50a75c-d2e2-4b24-9240-813b580dd91f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX
fc8a943a-b406-4c45-b68f-a0ddccfd9996 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
82d59e8c-6ab9-4f06-8131-81d3bdd754e2 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
692058ae-3152-49b6-97e1-384c1f3dcaef |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
13c25466-d081-4ca6-b6b2-45aff4970afc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX
e927871e-e52d-4f1f-b9c5-8f7335e31a8c |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
330c2670-0af3-40e4-9a56-507b02c1f549 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
4c98261f-c2e5-4864-aafd-61ae6a707c79 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6aea68e3-d25a-4fa8-b72e-a2c03e822336 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX
dfeeef68-0e5a-4adc-91a3-21db19fec3eb |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
64d97953-dd14-4abd-939b-16054818f0d5 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
50aaf39d-8d1e-401d-81a2-f6dc146c22c1 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
84c880c6-1236-4325-a0c0-2891c695e11d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX
8ab03d58-5dee-4532-bc51-f176bf9e898b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b839681c-cb46-4a46-94da-7a389f9cf4ab |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a7d15bfe-000f-41b2-9140-0fc25d5aff1f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (Basement to Level 3) | Level 3 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
bbf6ee51-db7a-4925-a438-ea6c2877a9db |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2)
edc8ce63-5e44-4816-8565-7df636b5b119 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4
b0725395-ad67-4abb-b6c6-b6a74a620582 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX
03bdd8b5-3c94-4bfe-8e58-385e3111d8a4 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
f56a0168-f7af-415d-b112-9984ba106a3e |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
55537984-d03e-4066-a0f1-651a56a7249b |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
e23bcacd-bf77-4ede-9fb7-b5254b8e1a07 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX
53c88974-1b85-4fc3-b41a-0a74ba04c523 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b0dc0d11-3824-4bb6-815f-cae70f93041b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
f12825b0-d60d-4486-8876-e24fee3cfdaf |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 4 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f2146ef9-4866-4ca8-8b5f-ebf13c34d0f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5
e532e133-c3ff-4395-9254-3bcec5bc639f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX
e0be0e63-3141-4827-b9a7-0ef7a7ae4330 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
fa721d45-3a7d-478f-b1b6-e3aafc1a8ec0 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
db62506a-d800-4cc7-9aca-f83bf34fa108 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
34a2d86b-d6bc-46bc-8947-e9dcec202b59 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX
08f9d7aa-738a-430b-89e9-a87982c25469 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ecc08904-da33-45b1-b50a-e65f5ad55cac |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
baaf34e5-0821-45c1-a452-5e7e2e15c851 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 5 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f62fea59-c1e6-403e-a707-094c88874197 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6
01992a1f-52bd-40b5-a710-d1d75648bb8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX
7b08999e-03ba-4024-978d-a85b96451969 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
c74983a6-aedb-41d3-aea9-4067e6fec2e0 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9ff469eb-c06c-4e80-8805-6a0e881ff4ba |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
4d9c2feb-9a71-402e-870d-aae210f58fde |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX
145e0245-96dc-4492-87e2-b6256395f299 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
3f6001d9-2115-4227-9108-a9aec4f23ac5 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e104aecb-df67-4ab3-ad30-a0fb85ece514 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 6 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
ee39e626-208f-46fe-a659-56b59dbb479c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7
bd2f881b-115b-49dd-bb36-25b1ccb05e3c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX
2fe7345c-c640-49d0-9668-dadedd9bf015 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8a63e88a-c3d2-47b7-9696-5a4c17f1c68a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
48abd597-f776-4c8a-9a87-606753b2a950 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
808408b8-3b08-44c9-aa50-8ef544185c23 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX
53cc63f8-bf93-4f70-86ab-2d5591167187 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b2b188a4-b78c-429f-93cd-0efea8c29f01 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
acf1495d-5d8d-47f2-8e4e-2af0a3d75a6e |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 7 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
adc87a10-826f-40b8-923c-6a395344a690 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8
140e746a-4783-4bd1-a59a-154db7382ba2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX
339a23b1-a1b5-4f01-956e-6ca7a8b2e6b2 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
72d695d2-af1a-4567-8ecf-ca40d9cd1f28 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
63359a12-f215-4aef-93d6-7cf783a178d1 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
3eaf689e-ad68-4162-860c-4eb2cec8d949 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX
695c7a5a-7933-4e8d-814d-ec13b315426e |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
371fe242-b7a9-4b6e-aec0-b1d68dd25608 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
f44f50a5-f9fa-4f6c-abe0-d3e5a9947656 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 8 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
d9c0e255-b693-46a8-978d-1597a99aa423 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9
6c853dc8-6286-49be-83c6-25873e90a96c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX
078b074e-fbd7-489c-901f-e99b79275e94 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
f898bf74-dfe9-46d7-a20e-0e47648365ff |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
60ec7de4-57ec-4464-b075-8c03cfc4ab7c |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
4e118c57-92ad-48dc-990d-b91a602a1190 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX
41fa9341-bb67-410d-9c95-2cdda219bc45 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e1e6b7c5-c61c-442b-9dee-17cc53c282ae |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
1b16cc94-4549-425f-b014-810cf877e6e6 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 9 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
24b45d1e-5a87-47c7-9b1e-5ec666643c86 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10
35f4ecff-2361-471f-8e33-7015b2ebc256 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX
0339a8f8-884c-482c-b061-10d926e8a914 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
4420e62d-4ffc-4c4c-b0dc-0fa5210abec4 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
da5e3d5e-a0a0-41ad-99f5-ddd87dbf3159 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
9ccd517f-c22b-4c0e-970e-7b227af50d2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX
8efada39-d181-4a80-b759-ac0d0b7559a6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
298656a5-3e66-41cf-bd12-184b142b0789 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e4b4ab44-7f8a-4a33-8b10-f25ce3610d80 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 10 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c683a2be-341e-4224-ae0d-b89024200e38 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11
fff2e357-2438-47e6-a098-ca667981a4cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX
3b19232f-93a7-4b53-911e-cec9db0ad8d6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
5b4e6a06-fad9-4b1e-a4c7-78c2df589813 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2a989efa-3be5-4c19-86e1-454cf564be59 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
3bfc9c21-dca2-4386-a0f6-70fa83b685da |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX
7317ad96-5f11-46d3-bebf-2fa8e9469283 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a7e06a2e-4f8a-4043-87c5-8f5ddc0b411d |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
349f3787-ff3f-4874-adee-30ae3b87a77d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 11 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f6b8f311-047f-40e7-bc6b-65a68e6f2663 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12
ef25192a-3def-40da-b827-56daa1edebb5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX
4181c00a-1a69-4c0a-ad3d-fada00308a11 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
c075aa52-b4e7-476e-9e3d-80ac25158632 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
6e71ab6f-c76a-413d-b4aa-3be2eb5728e6 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
51f0cab8-4c20-4f9f-8ac6-f80361e6d53c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX
87d647af-4d69-4112-a07b-b12adbd00d79 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
82f78625-090c-4304-9bd7-bc0df8eab195 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2a7fdae1-98c4-4fe5-b4bf-6eabc6b39f4b |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 12 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c13cd88f-eace-4eae-8bbb-903ec49d3ee8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13
a760bc3f-73c6-45b5-a6c0-9bef1d2407d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX
55767791-8a59-418d-8941-3b4fa2e1a0f4 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
32f3d8e5-d8f5-4c9c-b083-d2dc57a8fce2 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5af5f1cf-09fe-4f5d-9275-d4b1c63ac8c2 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c7746a05-a631-4a15-8826-d779b1a42d5f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX
acbc2933-2297-41f7-9911-181dfe138c61 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1299567a-694c-47af-8bbd-46985ea50226 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
aa1004f7-7932-4930-8c00-6b9712dd902e |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 13 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
dc35aab3-e6a9-48df-9222-0175ceab0a08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14
ae4a6204-fdf2-4baa-9db7-058b2c21542f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX
e0ac69bc-a1df-41e1-bbd3-336b4a550a2f |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
72c1aa9c-68eb-4968-a029-59d230fdf01e |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
616a5f32-4cc7-41e6-8939-2d33f087b7e6 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
9c5ede62-64e6-4b90-8bab-2b031d26c6f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX
bd398b7a-970b-4137-9196-5ff5aaacf0be |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
18558247-427c-4f5d-a48d-c014a7c80f02 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
78b21f27-c337-414f-b05e-21f7064311b0 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 14 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
37f137b6-a111-4004-bd7e-01ba13da348f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15
fbf98911-1fe2-4eb2-affe-cc30a85ac888 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX
e5689afe-5b90-4f49-994d-f2a5648f0767 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
6fb2e8b6-71e7-4da5-ba3d-3dea8e6246de |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2d42007c-3190-4542-abf2-bbef38bcb8e4 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1fbef0ec-bf8b-4532-9952-1239037d335b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX
da8faf80-0f17-4ece-883f-09c99161a404 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
9f1bdc6d-64af-4863-9ff7-c321f160ae70 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
72b44b0e-c6a1-4cef-aa2e-1fa315d476c9 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 15 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
0840d41a-f6a5-465e-b4ff-b1aa3ae91fc0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16
6a150906-74e2-490b-a1ff-b47ba1b56d5f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX
b15d2da8-b4b6-417a-87a6-4f89ab8b48e1 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
78ed43fd-3873-4bed-a6b2-80d002c0a11a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
d2aaf625-906b-443a-bfc0-e80015bf7aaf |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
fa91ea80-e287-4bc5-8127-951bd12f23bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX
4ed56b69-b6da-4831-97da-09d16ab1a9ac |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1edef814-b784-479e-bdec-73f8a89b7002 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
4b73eaf8-315a-430a-b3d1-1be6b7343af7 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 16 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
44dfe232-042f-410c-94e6-5742decd7f3b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17
aa6d39b7-f283-41c6-b6e3-8f09e70f8682 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX
b3f07384-c5ed-42a9-add4-831bf7f19a88 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
004f6497-0a20-4f84-a14a-dfdcc05d5423 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
3ef6b3e5-2854-4ed8-9fae-60402841e463 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
2d75792c-3ef4-4436-99e3-ad240a3bc031 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX
3a3b40b8-d523-4f35-b1ad-66e3e5d908af |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b77dfca4-818f-4402-a22d-1cee56bd48ed |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
3f762030-f7d1-494c-b03a-8757b3d6b22f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 17 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
63d10eb8-4a4f-4ad3-ae60-db713269031a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18
d07c5b29-9ee6-4b6b-b760-52cea7bba605 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX
b03d8bca-6b91-436b-825f-a6fec23cd129 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
6fb29970-90d5-4b7c-b973-8cd1aa71f3fe |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
33b014c5-6770-4b3f-b0fd-245705646c68 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
e1b0adab-dc3a-4a8d-83a8-00cebcffe455 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX
f1f2ebc1-a024-4dd6-8298-6d1f4212d0cf |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8f0cf620-5587-4561-b54f-742d7f481d39 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
077471df-50cc-4dc2-93f6-d474df5be499 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 18 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
9accf915-55fe-4730-9796-02812fd66f2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19
e5cb341f-0974-4ba8-8bc2-f430620c2eb2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX
4877e284-2eb8-47f8-b174-686f89c3dbfd |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
de1fb31e-7ecc-4c5a-9f10-e20436799308 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e2331f31-75f8-40ac-96b9-feb24afd50a0 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
a1511e91-5cc0-40d5-8cf5-8417bebf12b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX
d6aa1d52-a406-4ff7-bdac-67a45d135ffa |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
06e8c2e1-d61d-4ec2-bc6d-dd6ccfcd82a1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9ba881d2-00e4-4bf2-b326-35782faa1107 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 19 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
178e25ca-68ee-493f-915a-764287a344a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20
ef9278ed-e97d-43a8-9d35-7bf134a3d4f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX
436cded1-8c9d-48d1-8170-8a1ce9058968 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ed4b77f5-7a4b-4cd0-99dc-2a6977c741a6 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
6c74742f-4e9d-4a98-babb-1b3f9345bf65 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
7e976941-1ddb-4213-bca7-f636f273ec0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX
54f4097d-a8f1-4b6b-b583-f513219404a1 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
5ef3eab4-1f53-4165-9c0f-2fe7f0b661db |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
f3c05c3b-77cf-4172-839e-48aeefcbb2dd |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 20 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
173fb8fb-b932-41da-bae9-6c6d21a3d3c1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21
32849724-1561-4019-9b68-9d18f1948bdb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX
f011ac0a-e61d-4bd5-b829-232061378f64 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
5d4f4948-f5cf-499f-b0a6-007bba8f733b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9bf828ba-1dd9-4f4b-b505-7f61fa6c2b78 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
258d2cc3-f1cc-4e4c-9a31-e50f06c9ccef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX
69f1c3fb-d212-455a-a352-efed7f61ac5b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ec5fb6d6-7266-44ee-aabe-bbce2abbfaa1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
847c7ce2-87a5-45e5-815e-aee1fa39c4ae |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 21 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
b5dc2281-3699-4c54-b41c-e4dd509bfa13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22
b86d125e-5479-4601-96ab-8a350c017230 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX
241f1847-6a06-4a84-8bcc-7dbcb7a67ca6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e1a25620-048f-4fd0-950c-668c716b680a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a97415c4-5362-410a-bfb3-cf981332dca2 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
22b96e53-4e5d-4e77-99e7-2e80baa1b634 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX
530d21e2-8f49-423a-b14a-17140ebb1ed5 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a9693f09-8bd2-42b8-b3fc-37f7a7479ecc |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
c6a5c19e-27fb-4a95-bc8e-1c41bbc7d2d5 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 22 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
0c0c06cb-fbd2-4f71-ba5d-31a486fc7bd9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23
de7e370e-6783-409b-b75d-02c0d494b35a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX
c5f55a89-b20f-4c24-84e7-10b5ab968830 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
0696f813-9438-4813-9113-e4d8eeda7139 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
cf9200b4-adf6-429a-954d-c479f50ee0bf |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1960931b-615f-4c90-a9f9-e8273c74a7c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX
5677e222-93aa-47e6-9ede-5586b10c39d6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
62982ebe-6ef6-444a-8568-0dd95367f876 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
70d36042-ce04-4a9e-818a-3a54bda46fd2 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 23 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
e6f9986e-76f0-4e63-ac42-3c63f0a09dee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24
a3796f16-2476-4ea8-a423-bb185fc36e10 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX
76167288-9c55-4da2-b9c3-688b26d505b9 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b3cc948a-fa89-44aa-a45f-7136559fc1aa |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
3ca63fec-3197-4665-b6bb-22904fb44f56 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6ddc8d6d-d386-4eef-9439-e0d001d156c5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX
cec32691-9ee7-428c-8694-f639cbf63ccf |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
4b811689-fa64-4748-a98e-e9a8b192e384 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a1f0c150-f2a3-455b-aed0-dd5768a5a6cb |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 24 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
9a258fe2-bd2b-455d-8d59-96e94f7bed80 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25
17ce6f01-5a22-4a99-af83-0f55f3295438 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX
2b995753-ee4f-4085-b046-d2515266fc7a |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
191c6984-3ec3-4d54-a6a4-eedd077b353c |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
166db628-5ab2-4502-ae69-98c76e20cf25 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6786d263-e6e1-456a-be6b-fb95d0f6c91a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX
fd06979d-7b7f-407b-b632-8b49560ba042 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
20608fd9-c5e8-4685-b909-cac1be497eae |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a4a7abbc-3ddb-419b-9c95-458365e8a8c7 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 25 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
7c89f882-4819-4057-a239-1cc959de41a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26
99fbd88f-7f41-4afc-8914-b84c0153c619 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX
0af72445-7312-4d9f-a9cf-8a66f345ea71 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b74fdf6a-b92b-4352-8eb9-3ebcafe519df |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
dafdb5c7-5d90-4894-b267-01d1dd16e35f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
73234e4f-1115-43ec-a4a6-564d10e11aaa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX
de07f154-199a-4f4d-a915-dc62bd8db39d |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
b9cc7622-e0f5-43f3-b87f-15220c3f31e3 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
1868894d-0866-4b95-b4d6-5089774b772e |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 26 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
27d6e9af-627c-4828-88ca-f854cabaea02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27
0ab63de5-563a-4cd7-b616-edc6f2e5e07e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX
021fc149-72dd-400f-a2e5-c5e30fada94e |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ee6c766d-d0be-43da-b022-1d762841fdaf |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
3d49f6a8-4e7f-433b-baed-6d709d689696 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c5534843-2547-440a-93e7-2743e48de2d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX
224b2f42-6522-4156-9575-30d02a2cce7d |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
c2ab468a-7703-4aac-aa53-74089aa7c60b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
7cbf02cf-f225-45ed-bef9-1a051ff53b04 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 27 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
634e0379-e8d8-47bb-ab09-83006da2caa6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28
b6b73372-8414-4f28-8e14-fd43312d1065 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX
77fee928-2b90-4e3d-8163-b4477e887e7e |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
c012abd6-79c1-4634-a114-2e88df849fd2 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
38bf7bb0-cb7d-4029-b5c8-9f27acf677be |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
df149940-da03-4de8-b492-81ddcb349e53 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX
0c304027-9a9f-4f87-a409-400d63480b28 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e5678266-4c2c-4348-bb20-3642ba0c4b3a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
d94c8dc3-c64b-43b1-a5af-fb8e12ebf605 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 28 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
77d7daee-418a-4eb5-80e4-4a7c8f5335e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29
879738cb-9842-4e51-97a5-eeabc04a3c00 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX
87526384-8851-4e64-9efb-9141bc09e52b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
3dfcd88d-17cf-4456-bb7f-f84811542063 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
eaa64304-d507-4946-815b-6d992b4c5ea6 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
3324e45e-bbd8-4fa3-bf26-7b6c5d7de041 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX
5f5dc2c6-f918-455f-9a1f-82d45eb8b5c7 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d2d1bbf4-09dc-4033-b366-99974be44532 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
0adbe4d8-8ff9-4613-bf61-c0128d41a8b1 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 29 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1b3c4ca5-f5e3-4215-9796-3491cbf6321f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30
03279280-077c-4c01-abc6-92ad05f15918 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX
132d3d9e-c217-448e-a91c-c12597f4ba4b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a4684edd-06a5-4718-81de-08e4868c4a49 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
b8aae256-97c0-48ca-b209-0a718336fca4 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c6ee1c98-7013-4141-90f3-0aed850410eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX
82ee61f9-ed3d-4a3e-b66b-63a9917c416e |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
62aa4574-f79e-4b0d-ba0f-5da9299d408a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5a24af25-ba13-4ef2-960a-f089f44ea554 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 30 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
de8d48ad-46de-49ab-aef9-ef28e6277836 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31
cebf7541-9aa0-4ad6-8c62-c424e5597dcf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX
a51e653e-5810-4fb9-b460-91bdd1ca1662 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
545f1799-8985-41e7-a58d-c9c4dc719b6f |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
217e9546-3d32-4cfd-9b87-0e775235367e |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
e482c636-ffba-4e31-b202-ca59d43f39bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX
692b83bf-2a7e-484d-a875-c7187d96fef5 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
3e298a64-ae2e-4fac-854b-ef233a80f199 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
cf34b00a-3692-4752-8bfe-26c023167686 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | Level 31 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
ae494309-e545-4736-ba5f-fe78f8513af8 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 1 (North/East)
5073bb6d-d37b-4e0d-9f01-c753c757aa62 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 1 (North/East) | AEQ050 (AE005843) N/E
2466baac-7a23-492a-8fe9-04129056f4f1 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 1 (North/East) | AEQ050 (AE005843) N/E | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names)
75c50d21-09d0-4c0a-85af-e1177b45ffc4 |  | checklist-sectioned | pass | b247bedfb082f77200c004e2fcdc7a486b7b361b878a4ba9dedf8ec9d5326372 | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 1 (North/East) | AEQ050 (AE005843) N/E | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names)
31abf7eb-e0e8-4355-94ad-c641ea23c562 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 1 (North/East) | AEQ050 (AE005843) N/E | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names)
3bfff8a5-9275-4c58-8d97-e1feec178ee2 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 2 (South/East)
850ab6f8-5376-4638-a1f8-4dbeba666fda |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 2 (South/East) | DB4604
138fd654-3d78-4853-bf12-8e24f3a8a7ff |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 2 (South/East) | DB4604 | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names)
fd515ca7-8c93-49e6-953d-c34aece57b41 |  | checklist-sectioned | pass | 50a87c21342129868180db8841c411de2d4e2eddb09972777818c6a90cdb1907 | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 2 (South/East) | DB4604 | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names)
fbdea607-ffc2-4fd9-ac7a-15fe616183bd |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 2) | T2 Core 2 (South/East) | DB4604 | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names)
17e05a4d-e653-43f2-a3da-606c581bbb88 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1)
6970cf2e-ff06-41d7-901e-df09b0c4aef9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04
5ebae2d5-3bbb-43d4-aa51-cc4befc7cf90 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX
4b167875-246e-4e4f-8621-6e6f692e2052 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e181ca6a-6f19-430f-bf13-324a6edfcdf8 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
4b5c17bd-ccfb-4f9f-9448-9b49ea1cfdc4 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
044b09b9-6c57-4887-9f7c-2493769ea1e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX
bac25e14-5533-4c69-b2eb-1ab7c9711389 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1d3a83a8-ac1c-45de-964a-97632739c1b8 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
dd27914d-ff9b-41f9-ac82-7b7dd4ac168b |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 04 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
905157f2-40e4-498b-88cb-cba5f57d31af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05
b912c7ff-6900-4c7b-9cdf-45b56fb0ee2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX
042a87ae-99dd-4d3c-b17a-a64f63986636 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1dcaff78-65ab-4e14-b8fa-98928e6c285a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
0ac20f69-3de8-4f8c-9a2b-177998014779 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6ca429de-2197-4be2-86de-6ef0ab7f5385 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX
beb33798-5569-4717-bdcb-6f426d0f8078 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1eb65619-e255-46bc-b609-b7d7a616fcb5 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5b747592-b1ef-4b03-bf63-1fa107660801 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 05 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c840db10-45a7-49fe-885c-37654b6bf91d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07
bebafdf1-59f1-47ff-918d-31e2b410932e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX
d7f4367a-cac2-4bee-a1e9-69db8504c37c |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
3540767d-24d8-48e2-a5da-c9367111e7f2 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
110596c5-f10a-4ae1-89b5-cf5d3f2c0579 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
cb33e35c-3a1a-4edf-aa76-af1e0deddb27 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX
b7a80495-c235-43d3-8821-23df5ea1f84c |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
781b5a60-41bb-4164-ac64-e82d50c35564 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a7a67364-a2a7-43e6-b99f-1809c3af2d12 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 07 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
0ce11463-b4ba-42ce-87fb-27f7f73d712d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08
c55530f1-cb07-4423-84a3-7c245ba32617 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX
9d249c41-bfe2-48ed-a8d6-ecbe9e077428 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
523a065f-54c6-45ee-922a-25bc702a3d1f |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
3432c66e-931c-4489-baee-9b608eda2bad |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
55bc0392-dc25-427c-83e3-6c09244935d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX
03f1838e-ff8d-40ab-b7fc-8cd662f0f9ad |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
bd32c87f-3b44-4f31-86ff-1bf7dd2976f4 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9581efde-034e-42da-b162-13d1147ca88e |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 08 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
630e44de-a4c7-4afc-94f7-8543584bee3d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09
d40e07e0-1ccd-4acb-ab37-bc431e8eec80 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX
63536f7f-4e60-491c-bcb9-acddc96967fa |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
13b7467d-54e2-4186-8737-c5ad3a5707d2 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
8633db08-45c5-4aa6-b2be-133c44317c9a |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6dd5c848-09ad-406f-9488-796e4dc709f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX
58841662-2a63-4d77-b38c-9997203aa3b2 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e005b73c-544f-49f2-9f1a-d12f7a6079be |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
93bdd45f-3aa8-43ab-8def-03d238096c1f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 09 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
2af566d0-3a94-4d12-9563-e0380b418a2a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10
64a85973-eb7a-4c49-9e08-3987779aa1d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX
1c9ba46c-13ab-4835-9865-920388511ff2 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8990362c-f7f5-4fa7-a12f-4d7357bba14b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e9d48ad0-6ac8-4188-a09a-6994dff952e4 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
562bcace-ad14-463b-a212-97719cff0c31 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX
2bb99d53-d67a-40be-9976-c6d2bb813f84 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
6b279ece-25b6-48ef-824d-9ecce44bb370 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
23f03611-3206-4379-8509-e81abebb32e9 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 10 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6ef722dd-aa93-45e0-b4ee-4f419c020d7f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11
e3f25944-643c-4b64-be33-80afeb9834e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX
f15f596d-7e29-445a-9264-be0dc0f68daa |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
820a192f-f2a1-4695-b836-014c8cedd934 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
09d30d3e-5ee2-4e22-aca5-f77ae77f8765 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
cfa0d6aa-b618-48bb-a629-d36539abe864 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX
539e3cab-02fd-4bd0-9e98-163c0433f83f |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ef061c99-1b70-4b3c-bbb9-0f254e6509ec |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
72baa708-4032-4c4a-ab2a-c518fb7f36b5 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 11 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
59c5930d-ad40-4e1a-a1c5-2214139c0f1c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12
5452be87-4d46-4cfc-9a55-df110922a078 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX
686b0185-0b59-4d3b-88d9-1b0860fa072c |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d1dc0841-be33-4135-9392-cc3d66e14b39 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
48524224-4174-4cfc-a5eb-c4553becec48 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
d6c7a843-0fe0-4f53-9e2a-114a045f395e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX
e9757037-460c-41c7-af68-8803e561b494 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
170e9a38-12c3-464e-9faf-a861ce2d727d |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
72e1a0b4-f967-4715-ba5c-07582a8543f3 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 12 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1fe43765-689d-46f8-b819-bc8dcfaa0880 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13
b320a9d8-7a8b-41cc-8291-ca0530946fff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX
99249297-68fa-4bab-8451-99cc55a2e767 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
75f9bc44-6583-402c-af04-5ed0566a0a01 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
46519269-4ed7-45f9-b0a6-af27c7f2cfee |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1542b370-3025-4984-b8cb-5c752da7a0c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX
d6a0bdf8-75d5-4fc8-b020-61144fd546f8 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
1a98acbe-e9bb-45b5-9091-20ab50796dbc |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
ed89d86e-753c-49ed-8495-2b8135d564a9 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 13 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
595bbd38-4d81-4994-b856-012e333c3a08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14
9cd06fd9-2864-43df-bc46-a48125deef9a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX
86fe36ea-b19d-4461-8e70-859277670488 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8c22d9d8-4e90-41b9-8009-3ca077d5eb34 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
c43b4e6f-8a6f-4a61-a2ef-5068a7f99e2f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
d743846f-55b3-464c-8166-bcb340aefa5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX
341e2182-bd42-4235-a643-911389fb4318 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
ed646bc2-73b8-49de-9bea-aa306d70dc3b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
cd9ef927-110c-4730-8696-0d63a2ba20f8 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 14 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6494fc4d-ce10-42b9-b301-94aa5a866d13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15
59128f1e-eb41-4a75-9d04-6b864bd28067 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX
0abecf65-89c8-46f2-9b56-c4ff2d3d6e73 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
33f06b8c-abba-4f34-b491-3fce14e2264b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
97f34330-cbd6-497c-9f22-d9889381e816 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
b8e320a4-23cd-4447-893b-f02a3825e6fa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX
99bf489b-f2df-4c25-86f9-65467be07ef1 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
31ee6d0b-4b19-4e61-ac1a-3ed3a4d9b14f |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
b5fc861f-a63f-47e3-a207-6581fa921558 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 15 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
088e0d97-c423-42e0-ad58-8ee887b63e1d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16
3f8968a7-f602-486e-b7ce-974690772390 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX
9dcef922-987f-4c67-b7c0-09e7e7a2e484 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
bb51fe6d-e908-4186-ab98-7c671a7cbe0d |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2fc2170c-d360-4085-b23e-c2945b27708f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
3a490773-da6a-4c38-8764-750e9ac4cfac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX
83e1893d-52f3-4cc7-ab9a-f0b43b66d734 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
78030bfb-c9cb-4b67-9425-84d2374f633b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9c5a4aa3-db0d-4dea-9167-99ba9dcdefd3 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 16 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
7ff94407-62ec-4244-bb9a-92977dd6b544 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17
087ebecc-a2ea-4198-817c-5b6bc942fc80 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX
3a450250-95e1-49a3-93b3-1a828f2e71a4 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a9bf37f9-a17f-490a-b0c5-b58f75653ce7 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
76deee92-2da0-458a-8133-8949eff17551 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
a32aa4ee-f5e6-4d8c-8a12-a761fd3446eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX
5abeb0c0-b4e6-48ef-9d65-e70f0931eb4d |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d1c3ed90-1f3d-457b-93f1-69274ab4a80b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5e4c7ad0-3b8b-4546-aebd-b76a4162d7f8 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 17 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
b31b43d1-68cd-4b16-8555-194d9fefb87a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18
594e72bf-3011-48ca-9933-cc116b3748ba |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX
2c979110-2f8c-45aa-bca1-7c10581941c1 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
0da47c4f-0d82-4313-a879-b65437b59668 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
8e28e7b7-64fb-4d9e-a998-ce47e530de36 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
42599fd8-9fc6-42a4-89c6-8290d8587a49 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX
2ad2e5e3-1ade-4340-af2e-c6fbeab5cee6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
8e435078-a38a-47e2-b1bc-60b53b7d9439 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5c533b9d-c98e-484c-ac45-583a741c980c |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 18 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
c754b2a4-78be-414c-9f3d-5e13e3c8b4b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19
da301b31-cf3c-4074-b5c6-a5c91bc8d856 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX
92e20669-f5ac-462b-b861-c545bb7516c3 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
c2ada325-b821-446a-a9d8-22cbd3b5649c |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a365f456-d39f-4acb-9d26-176c94e6a22d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
58644cb9-e7ce-47f6-821e-79c4e69e2ec9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX
6cbf6e50-0e5c-4378-9ae0-f857ea30db81 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
4c6055e5-bf6d-4d1e-9a4e-b7768647ba48 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
c0542f69-56e3-4fd8-aef7-4990c518990d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 19 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
37dbe648-8e9a-438d-a4bb-f77c7b7ef3bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20
7e82e559-e5cc-43d8-81ee-b2f0e9e19e67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX
b0163034-66bb-4820-bcab-2844184b6c43 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
2afea979-1ac6-4746-a747-a3988f05f2c1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
9e3d85e3-34b9-49ae-979c-bbd6ac80275a |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
3100e913-0e5e-4eec-bebd-ef303af4795c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX
caeb777f-4ee3-48a6-b968-49ce2a904ede |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
f2f3807a-9caa-48fb-b148-b633047afd91 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
eb6ce642-6ac7-46ef-a6ef-77878b97bc49 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 20 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
96498e74-544b-41ec-b463-a37ea4ea11fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21
1fc8e7b1-7002-40e6-80f6-8399eefacee7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX
781a4e5e-193f-4972-a312-431dd8094318 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
70d0c0da-00fd-42f3-ada0-8c6d0c253850 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e8063a04-e473-42fb-8908-cf43ffa9cd63 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
d434c8c8-d619-45b7-8896-590cf2834e6e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX
b8117b5c-58a7-4d9c-b90f-3901addd8150 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
af7ff767-c612-4408-956f-4e4cbb2251bf |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
e1fb4b1f-64fa-493c-8a78-f278b2c535c3 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 21 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
30697f43-1a34-43b9-afba-76581f10e9f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22
9b066d4f-4002-4d34-be8a-d54e2d34e083 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX
1f471318-b69d-4e2a-add8-78fdc637ba69 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
a9bbcbd2-a076-4c08-8429-55cd33f579cb |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
7d90bec0-6bf2-4e8f-abe5-e7975742ee66 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
67ec79c8-ed7f-4a04-8d5d-08c5fb463353 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX
6a2f290a-c490-4ca5-b8cd-764bd2a5f5a6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d63a088f-70e5-4f6a-bc2b-c0e303bb08a6 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
260ca403-f1a2-4782-99bd-da7c30d6d9d0 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 22 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
6be4b0d8-8873-4fc0-a266-194bc5ccae25 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23
afde1105-9fc6-42b7-8855-c78e059ecf8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX
d5b590d2-6f38-43a3-8f45-d14cac5e6ae3 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
19a3e634-e33f-4329-b1f9-d723a4b4750a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
4499ddc2-2504-4e57-bafb-34fcd8340c36 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
bec5873f-f564-4e15-a864-7bc9fd58f868 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX
4c5ff6ef-885e-4e0c-9f22-b98c6fd22008 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
d461d6e5-efe1-49e4-afbc-245b6b26d2b1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
ad0a42fc-ff8b-40e3-8ef6-9c3fc27fb5b3 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 23 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
a8b514ff-6ec2-4a53-ae79-b0015b4cf504 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24
fc79f407-7fff-4818-9b5d-abb36364bd7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX
27473ce5-52e6-42b1-a2ef-cf57ea03a601 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
606f1448-1354-4f0d-b8b3-4c66ebcabecb |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
0a5b8010-bac8-4469-b86f-7e17aefdde22 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f5e54ad2-a676-4c29-849c-1fea38c2f4c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX
594667a2-2e9b-495e-ad88-e796cfa871dc |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
cb6f1679-e583-4d9e-af1a-8932b83d5afa |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
a8aa5c8d-788d-4a76-af78-44fb4a06159f |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 24 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1a5928eb-052e-434b-8fcb-3611c309cede |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25
83efedfb-6abe-40c5-8e27-e1577db25e9b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX
bd216ee4-be53-44bb-8fe2-c18a47be9c25 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
955ac8c1-8671-4c32-bdd7-e8de60b7ccf1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
888e65a7-8e8b-4243-a640-38bc0b468660 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
cf9937db-68f7-403d-8d32-890d4688fad9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX
27a534b4-f31a-4eaf-af64-1d8cbd71b6f6 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
e5a44fd8-ef5f-4d97-8c4b-de47ae982394 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
55f70176-6fee-434e-a79e-5ad51f18287a |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 25 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
086ef779-4017-48b6-85f3-c8d19faf11fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26
629c2c97-b80d-4db4-add2-9ba0676ba829 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX
3472459f-fdbc-45a5-953b-8c6477bd1e56 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
7983050e-4b54-426c-99d1-35eb5e61d8c3 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
1a623327-1b38-433f-bcef-04a175c359ce |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
773bb0b1-74c7-431b-b303-0006a6f9acf6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX
b7c8ddd4-75b5-4c4b-bdcb-a03c3bf4060b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
679c66c5-8f59-4071-b1fa-ce45d6456d41 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
850f95f6-62ec-46e6-bd29-f048eae52279 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 26 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
de518fda-cfb2-4870-a5a8-5565a0093764 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27
5ce84c98-882b-4688-aaa0-3ca20bd228bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX
0f436d13-8332-49e7-90b6-a7804e0e51bb |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
60af97e6-9c43-4336-bfca-151e5a56ac95 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
c3d85176-0ce7-4749-8260-4e4e772ca59d |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
8a32ede0-9aa7-4cc0-8c99-70ca387cb8cc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX
38babb36-f4be-4d0e-a3fa-160c4b501a2a |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
cf5f3875-6adf-4d0b-9762-a3a34062faee |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
afc8d2e2-6f87-4a74-805b-f9e5c4a8fa67 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 27 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
96c264fc-8119-4ce3-94e8-01ac80f3c589 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28
cb0fcc72-5c57-4781-9ec2-017745a08c68 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX
6b78d757-bc28-4e98-8e61-594c4f77930b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
39e6d44e-eb2f-439e-a551-e10fb3d213b7 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
8cf1d329-3135-471a-85ff-c07276b1b706 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
689e3b2e-284d-41f6-8da6-4c20c5058d0c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX
67406714-41c2-485d-bc19-1173aa754676 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
094cbbd0-4789-4848-b8d0-ef14fdef351f |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
d9f2124e-0ffc-42a7-be6e-adec05754087 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 28 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
70e4d265-290e-405b-99ee-a90ea1cffeb6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29
7c199e2e-c5b5-4055-a717-3a398127c3b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX
85ff76b4-d2ac-4853-9a5e-3d631fe9f8fb |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
de75215f-4d90-4360-96ff-a5cbb10a1448 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
c89a9375-980b-422c-8f92-5d0d5ad4a941 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
1e0bb479-81b9-4722-902f-bf3ed0312ba2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX
afa7e378-8ba0-4016-90d5-18858aadf579 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
eb8623c4-7557-440b-9622-4dc8d78b06ae |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
ec09f555-1ede-4e84-a8c9-61de6c33b4c7 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 29 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
88b57a15-79b2-4772-b305-cdb6a25325ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30
0873b565-2984-42af-af0c-c04e34f77a18 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX
3ef4fd9e-124e-41ef-87bd-5b8606e63f00 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
89556a7b-0884-40b0-a639-4527642aed72 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
2c98ee8e-9d71-4fa1-bd1f-87cc01e55317 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
2f9ebc78-d674-4cae-a9fd-70c42c3b7a1d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX
700932d2-28b7-4987-97bd-8de7b3e593ec |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
4f9a5dc0-4102-439e-bc12-108e6dffd64a |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
7869c45c-845b-4557-9405-78f3f9bcbace |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 30 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
39cc9349-0dea-44cd-8c2b-992193c7a698 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31
45d2ae96-0fc8-4aeb-b6ca-5716a203f309 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX
fad6530a-6ec1-4774-869f-51fc74de8b33 |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
85bee8b8-7f11-4c22-9b3d-afe8cd09aca1 |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
5861223b-b5db-4b4b-880d-7e891ec3bbd6 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
f1842e4c-dc94-412b-9a97-5ae076923cfa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX
7e179c95-9954-4e1f-9126-4bd48c9e245b |  | checklist-sectioned | not-started | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-001 - Temp DB Checklist
f76b4e31-a0b7-4873-8f5c-32328156639b |  | checklist-sectioned | not-started | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-002 - Monthly RCD Test Sheet
dcdc0dbe-681d-4551-a8a1-77e2186e1f42 |  | checklist-sectioned | not-started | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | Level 31 | AE XXXX | AE-ITCX-003 - Mandatory Test for Construction Wiring
2b735508-2306-4c3a-87b3-8fd7db5abdef |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 1 (North/West)
f9ceca93-a29e-4b87-92ce-f9c6a2269731 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 1 (North/West) | AEQ036 (AE005541)
55877a3c-f1bb-4517-a9dc-efd8ff997872 |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 1 (North/West) | AEQ036 (AE005541) | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names)
8793c1d5-1b9a-4594-8d9c-8414cf950c3f |  | checklist-sectioned | pass | 5cd22d810171ce23a2c0a5b6de70759ed1e6ab5997204a0fbe2c67bd9a99f390 | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 1 (North/West) | AEQ036 (AE005541) | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names)
c50b8983-2571-4ce7-ad85-e44f346008c2 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 1 (North/West) | AEQ036 (AE005541) | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names)
3572a544-0db5-405b-9b3a-3186f13c80d8 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 2 (South/West)
71626eb4-7eb4-4be8-b806-c569b098b8ef |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 2 (South/West) | DB4939 S/W
ce8ed4f1-b941-454c-bc05-e9b745f58f6f |  | checklist-sectioned | pass | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 2 (South/West) | DB4939 S/W | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names)
a79d9886-67d5-4862-94a0-6d5fdf00ba31 |  | checklist-sectioned | pass | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 2 (South/West) | DB4939 S/W | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names)
0c4a2da4-a878-4754-b406-e186a2090b84 |  | checklist-sectioned | pass | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | MDB TEMPS (TOWER 1) | T1 Core 2 (South/West) | DB4939 S/W | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names)
db824a09-2135-4725-b4b0-31602ffb790c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Temporary DBs | Main Temporary Power Board (Marvel Supply)
e3ea780a-3326-49df-ad52-5561f9ac90d2 |  | checklist-sectioned | work-in-progress | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Temporary DBs | Main Temporary Power Board (Marvel Supply) | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names)
52f9be00-4aab-4c2d-961b-1b180a0da7e5 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Incoming HV/LV Conduits
7aeaf942-1ad8-4195-a8e7-57dd09e24888 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Incoming HV/LV Conduits | Basement - Under Slab
8afcad77-c871-4e7b-8287-e6f967783784 |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Incoming HV/LV Conduits | Basement - Above Slab
19dda7e3-dfe8-47c9-bb7e-bf0796a2c33d |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Incoming HV/LV Conduits | Basement - Above Slab | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names)
0e9b6ae6-28b2-4421-b08d-ecaebfb4a571 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Incoming HV/LV Conduits | Level 1
81e4521c-fd86-48f7-afaa-6d6d8a3d72f9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Conduit
929dd2c2-d60e-43dc-9e51-067ab721f626 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Basement Underground
4d493915-2d2b-4759-87ac-7125489e31e6 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 1
97acf564-2a25-484b-a33c-af745dfae1b7 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 2
bf80be69-62ed-4162-9b74-61a14721bfbc |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 3
91387e04-48c8-4c3e-8368-889c7c84ca82 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 4
96578ebf-8a39-4d6e-a374-eda82931b3bd |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 5
99382849-1d4b-4da5-8c04-f850d67b827a |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement Underground | Pour 6
584a753c-c1b2-4d19-9806-770320b0b60a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Basement 1
ae45fe8b-0e7f-4767-b53c-2ecd36810e3f |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 1
b8d3dc86-0fbb-4cd2-9fbd-107e1927f374 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 2
50605a0c-3318-47b2-808c-84e1eddc79a6 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 3
5020aaa4-1ed8-4733-ba45-20a2ae708609 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 4
53dcda50-03a4-448b-a125-9cec2b2c4f80 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 5
11ea0941-b2c7-4139-a668-0fb247e0fc30 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Basement 1 | Pour 6
1a850ac9-988a-4cae-b634-a0acf8f537ca |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Ground floor
4a8716ef-34cc-4a00-b178-c9b1ad14684f |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 1
1bbf505a-32bb-45ee-b355-3a6d92226f45 |  | checklist-flat | not-applicable | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Ramp
f282e8d5-0af3-4db6-908c-267d8ffa844a |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 2A
9de4bfb4-c23d-48e4-b38a-f6c45d064c73 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 2
239ec75c-48ff-4710-9f1a-afbaac226334 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 3
017ad402-5bf1-4752-aba9-9e046bd12f2d |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 4
d521a545-d9aa-4d21-9cdc-7f19b2062539 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 5
8e1d57ad-ff8d-47a3-acdc-cbaebf6e9e5a |  | folder-normal | pass |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 6
cf8d32d5-9c44-400d-99ed-f5140bb0ca44 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 6 | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names)
12bbb30f-e700-49a6-9927-f472fcc7b37c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 7
f90dc9ca-5ecc-48c7-97c4-135f8ca5b2f5 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 7 | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names)
7e786332-6f32-4ce6-b57b-e228a6a86c4a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 8
3d12d2df-653d-4996-874b-075e76827b39 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Ground floor | Pour 8 | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names)
5abf1c28-826b-4903-9652-ef74243d8f54 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Level 1
140750e6-d83a-4fe8-a5ee-b80a6a418124 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 1
08025175-ec2f-459c-a472-125cfdd6a61d |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 1A
ba433bf5-e5bb-4484-a7db-0628096aa1bf |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 1B
6939c7f1-bde4-42f9-a052-fff46d03d890 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 2
6b589c27-46d9-4904-ab89-a72a1c219b3b |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 3
17687ae6-75ba-4876-853e-cf10711cf09d |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 4
b8e1684e-2cf2-402e-98cb-fcfff54fca05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 5
ec220335-f386-47e3-95ab-75e0a2451627 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 1 | Pour 5 | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names)
4158215f-67e9-47ac-92e9-1d4f1026568e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Level 2
3181f9b3-2f45-4ff4-8cc7-6a98262e5ed5 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 2 | Pour 1
a37bad13-96fe-4499-8340-5fd8b3457ab3 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 2 | Pour 1A
9473d45a-0c34-4008-a91c-23ee7aaffce9 |  | checklist-flat | pass | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 2 | Pour 2
de2360d1-7839-4b1b-912f-9ed7deb1a87e |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 2 | Pour 3
11aaae53-7a7f-4aa4-a5eb-4610671df83d |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 2 | Pour 4
e075f0f9-baf6-4084-afab-42686a1d3ff7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Level 3
d06e0834-41ce-48d0-9de4-75140746f6a9 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 1
3d58063b-6b5a-4cdc-9f98-f03cd71ba8e8 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 2
b8abf213-e36a-40a4-b691-fefd722c35d0 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 3
5ea94df6-a415-4aaf-b3df-4e20d89ca7eb |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 4
f72ba664-bc76-4344-a01f-772b44b8c225 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 5
e151b177-8f59-4a43-b5cc-9c01e2a57f69 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 3 | Pour 6
d0946f6e-913f-4185-8df1-e169c5bf316c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Conduit | Level 29 (Tower 2)
f8000ea0-b472-4eb2-a7f0-6454a93a163c |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 29 (Tower 2) | Pour 1
43803e0d-a50f-4128-9ce4-ec7213f25c94 |  | checklist-flat | not-started | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Conduit | Level 29 (Tower 2) | Pour 2
0c4fcc6e-4181-4518-9c77-5984a1e3ea7d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments
7cec1396-ac51-49c8-a61c-72e711c498a1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1
b44355cb-ddc0-4cbc-8478-cfb83301fdb6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4
276b46d4-7036-4532-b15a-2a2826510757 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401
d3298e8b-96ea-4402-ba55-1909bda997db |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Leadins
74095538-ec18-433e-bb94-0b5d1f9645c3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Roughin
45740855-502e-42ce-8989-af09c00ae010 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Cut out
7b72cc4f-1a3b-4d4a-a36a-3ef3456f3b01 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Fit off
1f153ebc-3c8e-47d3-ba1e-6e96dd193a06 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Commissioning
181862ba-f84a-4ce7-8ef7-8782ad0613d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing
4f9fddaa-cf88-4c23-8829-5e40ad1eb024 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB1
fb8be450-8b71-4bc3-976a-834f7d121acb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB2
d5094311-6bf6-453e-b70d-4b68b342acfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB3
392d3e16-7c9a-4a43-b42e-7b1957ae3c51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB4
44010012-a813-418f-acc8-dc06941057e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB5
78a41758-be2f-4d3a-a3c3-61898113d5c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 401 | Mandatory testing | CB6
4bea9e4e-0096-410d-82b6-1cfcbdb599bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402
1c869178-2db1-4ee9-ae28-72510f3f568a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Leadins
b188c60c-133e-42da-a947-06f5041e6cc2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Roughin
c3d1d218-4cb2-4675-b434-8608305e3e3c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Cut out
bc49cf9e-21c4-461e-84bb-257fea6e7634 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Fit off
e815cfbd-0290-4fb4-9554-36d1781c8a7d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Commissioning
ce3337e0-8a4c-44c9-96fc-26ba461f7d4b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing
58b016f7-dffa-4cf7-b349-a121859e65b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB1
ca56c94a-a6bb-41e9-93eb-d4b8359c09d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB2
ff250df4-0560-4432-af31-26a252ef5ac7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB3
480a1619-8fc4-4096-aa9a-565b9ff73218 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB4
f70d99a5-a63c-48eb-93a9-85ec261413c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB5
70ebc912-1564-42cc-be3f-dab2b3ada0f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 402 | Mandatory testing | CB6
f1e8e662-1e0f-42fd-95bd-7745bda161ab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403
9d1aac8e-088d-4def-9584-9002b24d18bb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Leadins
045f519c-e043-41ba-aa4c-535c0002940c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Roughin
c8211660-bd5f-438f-a369-10c428e75d7b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Cut out
ebb5585d-30fb-4e8a-abcb-cdc9d050b375 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Fit off
25ce86ef-2185-43f5-9915-510eaf83916e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Commissioning
3b946878-8b22-4f48-95dc-b37f087e66b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing
7535d8a3-7ff7-4571-9323-0ca159aa5add |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB1
50a71d8c-05ad-42d4-8257-a2c1501cf8b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB2
5b7e76f4-a178-4c8d-8b89-e4d65799c1dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB3
d4f79f2e-4558-4949-a435-c8beac2c9bcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB4
6041693d-af1b-4466-b349-1b85be854f25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB5
7f509bb9-7d03-49e9-984e-162f376ace3a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 403 | Mandatory testing | CB6
ab75ef16-026d-4f6d-a78f-52addbb88efb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404
dc073dbd-ced7-4632-b90e-367e80a50526 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Leadins
345db02b-00d3-444a-9d5f-d59642baa109 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Roughin
3b2cae5e-d491-41f7-a397-34c0643d03b4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Cut out
acf65ea1-b3ff-4aac-b9b1-c8e5325af745 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Fit off
5d036145-727b-4351-813d-e9b9b9768002 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Commissioning
d0308907-8599-4d62-bdd4-99f83efcfc8e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing
73466c20-0b19-4c1a-b4ee-82396f8514b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB1
78be8ada-0039-4bd2-9480-d4e928e1573f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB2
5b32f2af-d0bd-4fe8-812d-e6b56b97ffa0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB3
2b992331-e5a0-4e09-b062-fdddea14fcd9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB4
bf91b5da-4f79-4590-abce-bbca6516325c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB5
70fca71a-af84-42ca-ac4b-f7a7976c532f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 404 | Mandatory testing | CB6
e6d53ddc-ae79-4012-aa11-3bfcec3bd019 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405
d0c057bb-0a42-42e7-9fb2-315d61c522ab |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Leadins
88719507-137f-45fa-af51-367a5df0edd2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Roughin
fb469fd4-3694-4f3c-855f-71fe5898883b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Cut out
6945a06c-0f33-49d5-b515-9eb4e7a051de |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Fit off
ad59ad98-a3b3-4493-9af2-99f2191851f4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Commissioning
001d5fd4-8cda-4c8b-abd3-4eed2cdba1b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing
e61ab629-a8ca-4a4b-ba61-2ba2683da5be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB1
1c60b0ca-ed04-4406-aedc-ce4fde1fbe9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB2
a49892d2-47ff-45d6-92c3-04acf9b6655b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB3
f526bd5c-d5ba-4cae-a89d-1ecc0d803e9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB4
0d5becec-8e8f-406b-b5f5-bfee5a9fb660 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB5
57fb3461-e025-47c6-81cc-7b271121cc44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 405 | Mandatory testing | CB6
0d97a2ec-e95e-4427-bc58-ffc452f5cbc8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406
c5556835-5592-46fb-9c29-a4dbbbd3d3c7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Leadins
1e464809-5258-4df0-8731-f2afe44409f5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Roughin
7c8e2f4b-09cc-447c-9ae0-ec06d4b7626e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Cut out
99530228-57b4-4eb3-a0bd-03bd22b43b35 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Fit off
d15cb274-340b-4316-97d9-02cccf7fcffb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Commissioning
92bdf42d-815c-4806-9d09-58d2efca2c83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing
2df9636f-dcb8-4f0e-9ee7-2677562f06ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB1
550c3814-9803-477d-86de-e718228c8507 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB2
88b40a0a-ae99-4cca-a9b8-b261963ed57b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB3
1b5a65e0-a503-4aaa-aea9-5df9fd7b0608 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB4
e53d8d46-cb3e-4169-b28e-90fbaaefa3a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB5
bb47f233-8260-42c9-9d8e-c126024bf1ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 406 | Mandatory testing | CB6
31fdff38-362c-49db-9926-a2040f76ba90 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407
c614d342-7e6e-4a91-8f16-f18ce2f8cda5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Leadins
732ab319-13e6-4ebd-8f6d-7fb4a13e25ec |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Roughin
7e1d95cf-6fd9-40e7-84af-e0a18dda736f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Cut out
7f7b8372-8e2d-4e3b-9513-1ae9065cc284 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Fit off
98253438-3bac-47be-a00d-f7070ab840cd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Commissioning
966e880b-d86b-4e91-ab32-e6afafce7e9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing
0dd14d01-b974-484d-a9ae-e62b3b98f953 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB1
4ef62aee-dbd9-46e8-8e76-cf1463d9479b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB2
a4c09db2-e539-49c3-97ca-c39d1eaa9cd4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB3
2e366a2f-bda3-4702-a088-e789106448fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB4
375420fd-4ddd-4199-bfc7-084ba5bb2427 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB5
ccdde565-850f-47f4-917d-4e8609ff94c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 407 | Mandatory testing | CB6
115d403d-28b6-46c9-9ce0-6040889a588c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408
936864a7-0df6-4980-8b88-08dc3d10eaab |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Leadins
79756793-fa1a-47e9-98bf-29f6d0da29d4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Roughin
188e7b3e-3089-4cf4-8a9d-954b39a1f9b6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Cut out
60acb4ec-4380-4ad8-9bb7-224505e626df |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Fit off
466e4163-2426-458b-a138-a25137f3bd4c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Commissioning
6e367d32-7a93-41f3-8422-d45e6f4d9966 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing
f9e908e4-2e28-4731-a925-b25d4cf0848e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB1
07112187-3e4b-4602-a7c7-3de6685f57c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB2
548bad9d-578a-46b2-846a-0a5add918f86 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB3
da06b24a-4970-478d-a2f3-4c7c4e57c3d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB4
3fdaa50d-3e52-48e7-b982-c34ce6df8234 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB5
f6e2ba53-e960-47bc-8b09-e919126153a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 408 | Mandatory testing | CB6
6f667d3d-9b9c-43c9-a5fd-184dff79ff2b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409
2ddd8e7b-b7a3-41d0-b5e2-dd448016fcf1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Leadins
030045b1-d2ac-4bbf-a2e0-8ac8d0f7ea3b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Roughin
a1425ed1-7109-41e1-9336-bb7ca5a2a003 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Cut out
4785b920-eef3-4f9a-a360-af3cbf709e5e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Fit off
bbb472e8-ce49-4367-84be-782ed9dbd383 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Commissioning
1123b621-4b9b-4993-aa1e-31e111d2076c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing
00e6dfd4-a9a1-47b8-a1dd-d6a3d56cd622 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB1
a23f6fcf-f450-4096-b3e5-9b565bf59fce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB2
24a18d12-8ef7-445d-81ed-302a19ea2f96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB3
501e5776-7cdd-4725-acbf-f711c0b79ab3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB4
37c281ee-f93c-4433-8d00-99065a6ee802 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB5
9d01ddd2-5f54-478b-a0fc-bd08ec70a189 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB6
3c0e20ce-e413-4e1f-a7d6-abc7c54d346b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Leadins
9748323b-4d82-4e32-bea3-fff19f2192ac |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Roughin
4f7f0175-ae60-4dfe-b37a-6d4e9bede612 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Cut out
ca230510-6cf4-49c0-a3cc-f2dc3de7d7f6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Fit off
7ec462e2-7a63-416a-bd45-1ca16840d284 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Commissioning
04367797-5b4c-44f1-b682-aac61fb7d2fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing
72b8a3b0-0ee0-482f-a7a5-f916b19fc096 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB1
25b8f6d4-0240-4f80-94b3-4bf3f2a4b81c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB2
ddfe3de8-45c3-42b3-b113-83a1e93746bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB3
a67af3d1-1de0-4d87-9d14-55a637fdb32e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB4
a0776692-bf9a-423f-8e2b-4a4a39931e96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB5
b1e64b2a-c7df-4930-a014-d4b1c8cf20e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 409 | Mandatory testing | CB6
953b094d-0380-4643-8af2-64aa9ed4a08e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411
12a04c66-1712-4338-afc6-3ea4f6edd930 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Leadins
90d75b80-3bf0-45a2-b04d-44cf12e8c78e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Roughin
d86b6911-42c9-4109-8ae1-b710f664c0f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Cut out
9462e728-478a-4c0d-b712-e3e9282c7595 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Fit off
e5845852-e9a5-4daa-8ac6-8725ba8054ad |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Commissioning
59666182-ab38-4af0-b906-1bf6bdb5977a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing
8d64fbe9-2e47-49b3-84b3-482e246c38e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB1
00f950a6-7fcc-4732-894f-a47db1f52a09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB2
f4710d92-a843-4a01-8a0b-f13100772350 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB3
585d2c4e-83b8-4819-9647-c5efd659de18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB4
3584284c-d8e5-479a-a33a-10aa8a4ac94c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB5
b302af8e-b57f-4093-a61e-9b8633a56bb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 411 | Mandatory testing | CB6
1d6ca1fb-da62-479c-9d2b-4255a85103e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412
4413ffbe-ad7d-4b4b-bd1e-4008e8606a9d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Leadins
71b94e40-48ec-43e1-bc41-32435a9df63a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Roughin
30ef3bbd-4d7a-422b-ab40-594ab1040667 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Cut out
5972edf7-aaa2-4365-a163-b9b066bbd4d2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Fit off
d079a995-8cc5-4ab8-b76a-30ac73541431 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Commissioning
31421bda-791f-4f54-b142-3f1e2466d5bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing
a05e2080-2791-40b6-9c7f-354afa568b25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB1
362f07a0-3509-4c92-a941-d433399544d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB2
2249f880-ac1b-4aec-bf31-d9b652a381f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB3
6ac9925e-890d-40e4-9444-51f57d827ff4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB4
7b71ab90-3992-4ea0-8612-f7bf4e28ad61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB5
23f1e9b1-fc7f-4b0e-81e1-ad7279a4ff8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 412 | Mandatory testing | CB6
65c3d80f-abeb-4bd0-b455-4f357248b9cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413
b1a3f716-b724-46e5-8396-f87da493edb8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Leadins
c185681a-bdeb-4295-bd59-b8334b1ab6f9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Roughin
05196862-bdef-409f-94ee-637b8e5004cc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Cut out
877fa9cc-fcaa-4927-87d6-4c18fc275690 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Fit off
4cb748a5-07d1-4fe7-8db0-73caa66a380e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Commissioning
486eaa92-15a1-41dc-a89b-67b95cc3db67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing
d1e600e1-bc0d-4e7f-81db-549351a1deb5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB1
73953ed0-4ea2-4251-8c87-d738ee715d95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB2
527f016d-3e46-4f13-abf8-3982cc28e4f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB3
ff935d16-af96-4280-8768-b4171fdaf4a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB4
0ea7cd07-800a-4d90-bf24-b7543dd35fa2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB5
bad9873c-f06e-4661-afbb-cf9b4342e824 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 4 | Apartment 413 | Mandatory testing | CB6
d6623f03-7b39-441a-8f96-b76502dbae26 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5
cdf157d7-a496-4547-861c-e7ed0e679c3f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501
b25b2e26-2617-46b4-8a53-005b9572585d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Leadins
31966017-11e6-49e7-a448-b5ca39582224 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Roughin
6e85d799-9855-4d0d-96f0-66bac20e3694 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Cut out
01cd0234-a40c-4295-b5c5-f6001070d910 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Fit off
050cda39-1b68-4e89-9e63-f183fbda930f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Commissioning
c6170df0-b573-4cad-be87-633fdda972b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing
f115005b-ce96-4e21-a74e-52d42cec37af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB1
230f89a9-a4d8-4d7e-8b18-b9c43befc962 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB2
9076b81b-1000-4874-9c38-043d2fdefb12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB3
198e37f6-a116-40b5-a5d4-18ba9b3392d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB4
dbb903d7-e109-4d68-9a9d-c886aa148b0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB5
5f05e28c-fc9d-443a-b715-f0c02aa3e80e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 501 | Mandatory testing | CB6
60f14ce1-06af-42c3-abf9-6725b7a7eb9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502
11bd8982-7847-4f6d-978c-1c2cd985ecf0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Leadins
537ad7c2-047c-4cb9-9ebf-aef87615acc5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Roughin
a3f59f17-5d36-4be4-a7f2-dcb623555e20 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Cut out
a0fabf6e-df8b-48d6-a2f5-59a6bd34a452 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Fit off
9e391f27-df2e-4fef-929d-103788cd481a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Commissioning
f9b01509-76b2-4e7f-a81f-f8b5467110a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing
0928f637-7379-4d2f-823a-28d4e9ec6a32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB1
ba594f52-59b9-492f-a20b-546b1ee741bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB2
eef88332-21a1-4f6f-81fc-704721f3e577 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB3
bef92d67-548b-4bb8-91d5-833591b86487 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB4
b3bb3544-73cc-4a16-9d7c-74528ae56e02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB5
6434e4d4-afcb-443f-b441-67b6764c4c69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 502 | Mandatory testing | CB6
629119fa-db87-4fd1-9026-ffde5e6cb997 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503
1e62174b-b318-4d48-baea-79b981c0c918 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Leadins
0b2d710b-b4ed-4c78-8752-d5913d2902b4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Roughin
775ad481-0dc3-41d8-970f-5fc7a8df2c6f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Cut out
37a8b090-189d-4910-ad1f-dc36c3cbdfd9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Fit off
4782931e-cf5b-4082-b926-89335f3c557f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Commissioning
31aa3adb-cfa8-4d87-a034-21960ee4d81b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing
7d87040d-1cd0-4ffc-947c-0c335b42b75b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB1
c0d6a93b-f5ab-4f8f-ad8b-9ee14e0b708d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB2
c400741d-3852-495b-9664-a141494af789 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB3
34367f83-421e-40fc-881a-772491f4ac41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB4
1b3917b6-e9b6-495c-aee0-eed070974534 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB5
1be577d2-9762-474e-91d9-4ce41b572a76 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 503 | Mandatory testing | CB6
ca6f9611-b545-4e42-b662-a6e3e2e9a053 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504
7a002b95-55ce-4637-a90a-fb75b391a2f0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Leadins
d31a3358-7317-4612-81fc-3034523b51ae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Roughin
1285c605-fc9d-4ccc-8d02-2d2b8f40f752 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Cut out
c3f642ce-3dbf-469f-bfae-388cdb009e86 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Fit off
15073e37-08b3-4df4-a445-af181026eab7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Commissioning
f129420c-a57e-439b-9850-75a04caa13bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing
b08ab4e4-401e-4edf-88cc-1be8659fd79f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB1
73aee1dc-e400-44a7-b4ab-a5300ddb90d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB2
241e5d0a-389c-4056-bf90-fb73286a30d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB3
f00ade17-49af-4a07-be75-3f551886cf39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB4
7c6a0b7d-3061-4035-88eb-9d4ea9727a13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB5
c781be5d-3ed1-4c77-afbf-3cc02fd8fcc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 504 | Mandatory testing | CB6
4e4dc567-01a2-43d3-b666-ea71fff5fe30 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505
2e117993-e002-47f9-a3f0-0261ee365ae1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Leadins
fd4d0ff8-86e9-46e0-9773-0076fc494b6e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Roughin
e694adaf-c19b-48eb-adb8-8ad5f9e2314c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Cut out
f1b9f34c-634f-4580-bbfe-35314f8f88ea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Fit off
a3b0bcd7-c227-44b9-b59f-49e19570b47b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Commissioning
c78f2af9-2ade-4c0b-9b27-0c923c88612f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing
b99ffed3-1c39-4297-b69d-aa08f3c1a524 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB1
fccd5040-7d5f-492e-bfd1-e65f0007985f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB2
8b0baf4d-eb1d-4116-906e-89d6e2a2f368 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB3
01b0ad22-d7a5-4941-8fa4-18a032fc32e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB4
4d4cdda7-174e-4ea2-859d-22de062d027c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB5
855ed181-747c-4fc6-959b-cfd58e4e0fd8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 505 | Mandatory testing | CB6
635abd31-abdb-4409-9d53-fdefd8ca0d9e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506
b6acde3c-ded1-4687-a4e6-153c4eb6cf58 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Leadins
d0fb8da0-1365-4dd8-83ae-92f3877dd15d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Roughin
7dae9a08-4b67-4736-816e-6b03934e159d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Cut out
fdcc1891-c886-462c-a8ff-d1536e8eea15 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Fit off
6e1a894f-57e5-49ea-be99-36b6f10daf85 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Commissioning
0b0e6e76-8093-4ec4-9778-a66063f59e9d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing
57bb8d2b-7326-4ab3-af87-895b2ee28938 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB1
076ff20c-f233-4f23-bb4d-57c406126aab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB2
2dbeecf2-1b98-424c-bb34-b49d569d5e59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB3
5d468ef4-64d4-466d-9c9d-09e1406f14c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB4
ce19cabe-5af3-4718-aeec-3e6086fe86d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB5
1f4b7bf5-a6ce-41e3-904d-5bf1114f50e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 506 | Mandatory testing | CB6
c6d4737f-40af-43cd-afb6-9f0a3bda720f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507
e8ae0ba7-2007-424f-960a-24424ff3e2bc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Leadins
819f5ef8-ec95-492f-a6b8-e9e4ee7cadc8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Roughin
2da13d89-fd1e-4962-bfd9-b82a2d608def |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Cut out
f9a66551-bb04-486c-9bae-03106cd6a888 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Fit off
ac1b3d98-a912-4552-9e0a-61db9ef30bc3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Commissioning
9cd6433c-d8c8-42af-8e4e-5cfe4e6ad4d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing
89fe6143-3c15-4a45-a7b7-4a32ed1423e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB1
35ba71c9-7d2b-4e43-afe6-529abd9ed7db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB2
ed9b524f-8875-4712-b881-a2c803abd218 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB3
91d8c7bd-9886-4726-9688-bd90d83b8189 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB4
fd90b70e-09e5-44c5-866a-52e87ac17639 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB5
702c03d4-b372-4ef5-8fd3-9307177ef869 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 507 | Mandatory testing | CB6
22d4333e-41a8-4f1c-b3ff-a4303f53924b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508
ff57ffdb-8aec-433c-9876-7b3369be29b8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Leadins
328964a0-73ba-49e3-a363-be0750587052 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Roughin
53ab988e-d1ff-4fbd-b130-3017cf135212 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Cut out
56604267-35e8-4e0a-b6be-a4f330956f8b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Fit off
1847888c-793d-43cc-965d-3f31ba62a165 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Commissioning
f8dd081c-46b4-4d9b-aed3-39119ea37ee1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing
e2a620ed-5427-4e3a-b934-9104112cdff0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB1
59a5350e-98ed-448c-bfd5-ffc676a480ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB2
da63b923-1f69-4d1a-be5d-d0dfadd49567 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB3
5031370f-4c8d-48e6-98c5-a263fabd5ae6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB4
0d66f453-eb9c-4b60-aa88-c01b4c769eb7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB5
2135ced8-c59b-4742-bd59-b72e387f580f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 508 | Mandatory testing | CB6
6bfe0a4b-4649-4033-b2b6-7c2bff363eaa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509
d4a81cd0-97ea-47a4-9984-3d728d5d0627 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Leadins
fbf0a55a-ab11-4655-a2b8-8ed78e27c507 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Roughin
005b2256-c8f5-4e36-9b99-7f7be7461cfd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Cut out
2c40db5d-10db-4512-9c94-039dd22aae5f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Fit off
e4069843-62ad-47a0-8ec9-36f40bd91ff0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Commissioning
11755230-3feb-49be-bba6-17dc43c3bc45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing
9470cb49-2738-40f2-9e34-d840eb64ddc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB1
12645abc-7b34-4789-8911-836da4d10fb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB2
e77f1c33-26b5-4f8d-b6d6-007555816a4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB3
da0f8a94-d3e3-4326-839c-146b95274228 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB4
3e36c2f5-5995-41b9-b85b-ceffa8b72762 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB5
b633e715-a619-4663-bba8-e9b8a2d347a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 509 | Mandatory testing | CB6
17eb3afd-5056-49b4-921a-6d953dfcb6ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510
edf6497f-9768-4cd4-9617-b7f48a08a892 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Leadins
e83fae4c-29d9-45a6-b49d-d7c7e41108ef |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Roughin
55140f53-a83e-45e5-a825-996215b2aa2a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Cut out
06777b68-118f-40e7-8772-bfcd87c20578 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Fit off
d2925e56-dcb7-430e-ac08-d7a6bda59b18 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Commissioning
10ef5f9c-de6a-400c-8f1d-2bb959176f0e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing
57ed1069-2c2b-48e2-82c8-2f5cce71f744 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB1
42e156e5-a3a5-47dd-8430-25b9ff23bed3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB2
6f51a1a7-de43-4d58-a172-54c64d554318 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB3
d8944ee9-be65-4784-ab5b-e81c72b73b04 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB4
a437215c-5860-47ae-8916-ea9a81534d4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB5
2db27224-8467-4c36-b3b7-c95ddf8556d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 510 | Mandatory testing | CB6
a66d6d27-dbfe-4c8a-9030-e67b368306b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511
a4b51caf-7ae5-40b3-a4f9-7b3c8115ecfd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Leadins
80f7c900-3722-46ed-ba65-7de71d467bdc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Roughin
59cc9e12-1458-4254-a7d1-a732e1e7b22a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Cut out
e2b3b0c3-2250-4f79-a146-af23acb3bafa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Fit off
21ddc21a-adbf-430e-a071-5c53bfe50939 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Commissioning
5939d2c3-880d-44f6-a784-16598d04c94c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing
6b84fe11-8e67-4c1f-94bf-6e0b353bb1c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB1
e0b75543-2148-478c-bd45-4ec45b0445b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB2
1b9da348-3269-45a5-89b5-8d1e76f9044c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB3
ebad164c-95d4-410a-84a3-c26f19ab552b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB4
38ef4be9-da10-4737-9c79-764ff177f03f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB5
1df3a40a-e286-419a-bcda-e6d38a9cadf1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 511 | Mandatory testing | CB6
39d6da4f-8750-441e-a084-641dc659dc0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512
bba38ea7-73fa-44ea-975f-0320b236753e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Leadins
b08e1c8f-3e98-4d45-9c22-51c3022d7868 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Roughin
d1cd4db0-65ca-4d72-b659-ebe804978c71 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Cut out
03f48163-2f37-4ce8-b17d-56ea1b9c69b7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Fit off
5284a7c9-3bd0-4a49-b0b9-74d177ef1866 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Commissioning
a5212077-2cf7-4211-beea-5ab7fad13526 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing
90f3f4e6-6118-4ba0-8f41-8bc78f229bde |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB1
d440c487-c6a0-42c3-a485-6740eb6a002f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB2
6b96eaa6-2257-41c5-8cc7-16708314a39c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB3
944a583f-e78a-43b2-8eba-77b09260dcb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB4
66aa0f51-2bf6-4dbc-96e6-8c9d487f9664 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB5
6aa3c3a8-2a6c-4f76-802b-cf145c0db208 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 512 | Mandatory testing | CB6
33987252-0524-4eac-a99e-515320a9a860 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513
69b1c118-bb0e-4bd9-958f-8bf2f558658b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Leadins
cfc4d5d0-49e1-4b1d-bcfc-b55e75f6b0f1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Roughin
c5ab3620-779b-4e02-a76d-4064f001db3b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Cut out
59efe84c-52b7-40d8-8b93-09d0eb438a74 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Fit off
28424c61-d79e-4b63-9cee-9e51a1508ba3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Commissioning
9c24cc8b-2263-4d71-affa-504bf25d8a45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing
2803a547-5d69-4843-b990-41041af09152 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB1
a051f63c-48cd-4f24-ab94-298e89f32d45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB2
0d4f552d-6d6a-4439-b26d-d81b199f0a8f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB3
295036c4-e505-4533-94ed-df9e2b4e483a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB4
9982043b-eb83-48e4-affc-eae581905ee9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB5
014bf168-e955-4d91-8f3d-622ad50df44b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 5 | Apartment 513 | Mandatory testing | CB6
f06f6f45-2ca1-44f3-b32a-75257ff717cd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6
eb56c921-e9e0-4773-9e0a-ec44de84ef21 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601
13d0fd63-9841-427b-b6f4-e4daf9445e13 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Leadins
4e642d3f-e664-4067-b8ce-6fd5be0bb9ce |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Roughin
93c4168a-545a-4f6d-8483-4df914fd16d5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Cut out
26344581-b12f-4801-bc26-5342bb0fe4b0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Fit off
b232a4f6-43ef-44ce-b968-08bbc5b12948 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Commissioning
42015a9e-d09e-498b-8f4b-ed5e838cd777 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing
3b55dccd-2a8d-42d2-a143-e6810e016fdd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB1
c7dfaa19-84d3-434b-a4be-e6c885114601 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB2
c8d781c3-6b1f-4fdf-b670-5aeb1fa85010 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB3
ba0ae689-44c0-4eda-b2f6-a4f76e4ab05f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB4
6793e2f9-6da1-458e-b3c4-e79ba023242b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB5
2d55bb23-fda0-4c52-9ac6-e129c00a113b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 601 | Mandatory testing | CB6
90e39629-b082-46bc-98e3-befe8b09b4c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602
9d17f949-3f47-4faa-a0fe-855786e75e58 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Leadins
a3802c21-0b36-4439-bd03-222a5d7df52e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Roughin
eafc6722-b321-4217-86b8-362104d70a2b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Cut out
e3d7bafa-2399-45d8-9340-61d3f1361760 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Fit off
76b21178-eb1b-4440-b163-bbd5a83be4ff |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Commissioning
5d5896c1-e99f-4973-8764-d480cb8c5db0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing
ffdd4180-671f-4454-8de4-0280471016f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB1
b2f00872-2147-450b-957b-2d94d9ab1117 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB2
70071a97-04e9-43e8-8e41-c0d58f7a21c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB3
0275a2e3-5e46-4e5d-8d4f-ff850c60d06e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB4
e91e7ae1-a474-406b-98a4-7e8beeb0f234 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB5
dc817ee5-2881-4a54-9623-ee4201fa06b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 602 | Mandatory testing | CB6
c10dd8fa-e2f7-49fb-b9e9-5a66b9815f5a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603
afde0337-ed0a-4b72-bf29-63518e013fff |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Leadins
d67f7367-2867-4dbf-a324-528bca1622aa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Roughin
e1ea02ad-49b9-4925-b5fe-39b498744d1e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Cut out
5473cabc-06be-48a1-86f3-e14918244c5b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Fit off
2191419f-df33-492f-9b88-5a37be8f4f3d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Commissioning
1bc1dab8-69b5-4dff-af7b-aa45d797a4f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing
19549291-e341-48a1-acf6-85ab17c58935 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB1
67604d5f-2837-45e0-8ab1-6b6040511ab7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB2
24e0fd58-74df-4843-9674-9cfe4cfbc346 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB3
8f112103-d33a-4171-8047-87c575ad9ab9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB4
d58375e7-636d-450d-8414-0b4210545c8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB5
d6693770-a62a-4006-adab-e696a7ff155d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 603 | Mandatory testing | CB6
5e6a86d3-8b97-4fd1-9e37-3ae472be76d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604
f4cbd892-5b35-4855-a1b0-10c6453ec8f7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Leadins
a85ef602-832c-404b-8c03-245ddc6e2d19 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Roughin
b8e73005-023b-47d9-9448-1daa384e4e8a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Cut out
db1ec7f0-f74b-4483-8b5a-0f4e4df59f02 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Fit off
8e92d244-59b5-4395-8ed0-ccbb4b66dfe6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Commissioning
8850659c-f3b5-4323-bddd-82c858cf94eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing
0a8655a6-8231-4036-a30d-491f223cbfb6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB1
d6309b95-80d6-4a6f-812c-4643c1a85d41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB2
410b0410-f77c-4c84-8025-70a3f762a36e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB3
9fcf69f7-39d8-4607-bcec-ae606c0df06e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB4
5c983622-6b99-4d5e-9b77-fbd922048558 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB5
5625a015-d2f3-4143-8321-e905e8bfc672 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 604 | Mandatory testing | CB6
530c475d-e837-421e-a323-db193bafd96a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605
77032f3f-e9a5-4dde-b905-6cd21985b57e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Leadins
b74f415c-51b4-4454-be02-c6a5bb848143 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Roughin
0db2b163-a4fa-4908-88c4-22dfda2a5417 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Cut out
e43ff3a6-7770-4967-9577-1b471af65e04 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Fit off
db685657-7d0e-4e09-82c1-b46745984b87 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Commissioning
5fe02d71-c4d6-4177-a81c-00c943ec719e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing
4366bcd3-693d-42fd-8c3a-e15b3635e14c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB1
72298867-bd1a-48da-ad38-d08b24fe4140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB2
31fc3f8f-7669-41f1-8497-c57e3e703a10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB3
2b8a7a5d-679e-4a71-bcb2-559e32b0a97e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB4
6f79144d-8fd7-495b-aaf1-accd8dbaf7c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB5
2bf155de-5a35-4730-b085-85189e1182f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 605 | Mandatory testing | CB6
25102c72-4df1-4e23-a6fc-7291628f9540 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606
1b3b5457-109a-4c2a-87db-652fc463cef1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Leadins
2189f3b0-2922-49fc-bac6-27adb13b8dca |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Roughin
29680431-a178-47c3-95bc-6fa92a172b45 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Cut out
30499a88-e00e-4f45-98a1-da9012d33c54 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Fit off
b3208b13-2808-4153-a128-e1c7e5029257 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Commissioning
ac186116-dcba-435c-bf1a-582cc3118a04 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing
427c32d2-c9a5-47ed-8a2f-6da705278c2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB1
4aa97d3e-4f9b-4df4-a92d-f18f843a78ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB2
5e2e6412-840f-416a-9610-f5f05f1db7c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB3
2ba5d3ce-0ff9-419f-bc8c-c4c91e2c939c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB4
b02400ff-9b23-4fbc-a3be-83cca0ea604e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB5
7c5d68de-ffaf-4c46-96a6-f5b21367a16a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 606 | Mandatory testing | CB6
db7108d0-ea62-445a-a3f5-7b6fb2035f56 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607
10d4c4a3-67ed-4853-92c0-caa1c1e1ec4e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Leadins
c7229cc1-150c-4547-9dc3-35bc8ee65b42 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Roughin
5b185f48-58d8-4b73-9bbb-997e5fcaf4f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Cut out
630fc862-097a-4455-a76d-41c8b38c84aa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Fit off
b24ef70f-59d0-47d2-8998-95988fc59d47 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Commissioning
c8d723f0-794d-47d9-b877-f513c1ae63b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing
c553fab2-e9d1-49ce-8f4a-e217ecaf34a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB1
bb86d3bf-95a3-4dc4-875c-b3253f88c528 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB2
3d872bcd-65a4-434d-bb91-cc58eae72bd4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB3
fdeef9c9-ccbf-4d01-961e-f45acc127d6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB4
d7fd8370-a66d-42f4-ad72-c8807e673cdb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB5
14a67602-6ffc-4f3e-9565-50b2f55cf79a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 607 | Mandatory testing | CB6
5ffb0d11-2344-4ca6-aac7-2b0dd957dfac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608
c54dcdfd-00ac-41dc-bdb9-0513d2e2042a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Leadins
d322dc27-9c7e-40d2-83fc-aba406ad6cd6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Roughin
1575790a-5030-497a-b042-4bbba53619ac |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Cut out
822ed167-15b5-4b75-bc7f-0dd4a90715ca |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Fit off
ee3e418a-6cad-4ffa-84df-5a322b208b85 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Commissioning
2f23dfa1-4fe4-44aa-9018-3429c78a7a30 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing
88f19534-36f8-4caf-ada9-6c823f7f72cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB1
0161ef9c-5fc5-4a0e-8ad4-f187e5568237 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB2
fa5e8542-831c-4b85-bb44-b41a24146c30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB3
f1f9b03d-6b19-410a-8595-7e5204648e1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB4
e19e851e-1149-45ea-875e-850fb788c36c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB5
177b36e5-0f7d-4f73-8a16-8d225ccdb9b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 608 | Mandatory testing | CB6
5fd5c568-5a55-4a89-b019-73f05a0fdbb4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609
c930805e-582e-4f4a-a8e5-71df63a58027 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Leadins
293525ff-9d53-4a43-a4a3-d464e11c9778 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Roughin
e27dc50f-b5cd-46a8-9a79-2ca575835829 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Cut out
3558963a-606d-4676-9823-bd2765d74229 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Fit off
e8483ea4-0a84-43e3-b56c-19fc75ea694b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Commissioning
12128974-52ed-43b5-83c4-f432de5c1255 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing
e2a7607b-8b31-4a72-9a60-376dac0ecf2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB1
2c326aad-49b2-455a-81db-04e1ecbb21c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB2
4e5cc511-d683-4136-8d17-3ec793ac2926 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB3
92e391d9-b50c-4a62-934e-d057574d437b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB4
f929dbb7-7bc9-4793-86de-8291ce6cbd15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB5
3f1e3f7f-569c-4256-8ce6-d71493f6358a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 609 | Mandatory testing | CB6
21fec869-4ef1-41f9-a42d-1d3359720a82 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610
c74b3ef3-91b2-4ba4-8a0c-c97def797daf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Leadins
f0fb376c-4844-4ac9-9161-9b447e02fd83 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Roughin
41650eef-ef95-4fb1-be78-71248a575c2c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Cut out
54612ecb-6ac0-441f-b90f-3acf94c193cb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Fit off
db0bc270-eb98-4e8f-9073-30383f879eba |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Commissioning
31af4d9e-9f10-4664-912d-e910d844d85c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing
a61cf99d-34bb-4728-a59f-6cb5ca26b249 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB1
0b47450d-03bb-4326-9116-8ae7b9f95f9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB2
c7198d13-1ccf-495f-b114-47f4b64c3e1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB3
ff44648c-7028-4df4-b677-c20bab33a951 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB4
13957d16-09ff-49d4-ac3b-896fca8196f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB5
4fbc8ef9-a87e-4b6f-8cff-7673ca327063 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 610 | Mandatory testing | CB6
037d8572-350c-4da9-9d28-69688569db0e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611
0033c9e4-0a02-45ce-8594-5805c0a3e4be |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Leadins
65c811d8-3e27-44fb-8f53-17c51b77ced3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Roughin
e6631050-357b-464f-b712-f60bf8eb1ff1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Cut out
90ac09fb-506b-4228-9912-2d177eb3b054 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Fit off
ae191dc4-f416-4e3e-b123-8a8500b2a066 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Commissioning
d89d36eb-2d2a-46db-b0cf-eb6f50dded55 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing
455df0fe-0d38-4c47-b1ad-85039826cd50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB1
817cb311-77a1-40c9-89f2-25a0e99edaea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB2
f6063c39-cef6-430f-b67f-151c4f471d70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB3
11d7d907-ecb2-4654-9882-56a8e3e7e559 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB4
7d6f0f27-f597-42b5-8bbe-2e43d7a26f46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB5
b9f858fd-96d1-49c6-aa38-f1f36785a0b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 611 | Mandatory testing | CB6
b95c63c1-5b97-4979-a874-f290246d3ef9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612
ce8233ea-a63f-44a3-afc1-344834628bd1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Leadins
dae906dc-b62a-4838-9ad7-5e4102aa58bc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Roughin
60142be8-e890-4e99-b1b6-d37325707b11 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Cut out
1d5cda45-3f4c-4937-9595-06ec3fcc9fc0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Fit off
d2eab4d3-d1e0-45a3-aad1-e8ba42f0aafc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Commissioning
f2531525-88ec-4bd7-8587-d26cc8fc80c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing
e3a13a74-8fa8-4e58-b7e9-94664deaa6e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB1
01967ccd-47df-4b23-8af4-66f34f8ee7f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB2
bd4be15c-6fcf-4083-be51-5fc5f992d413 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB3
e1bbfb27-1ff8-4a5b-bffb-bee707a78364 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB4
86d96ef1-f909-40fd-b57f-1841194a9404 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB5
8fa0ad2d-48e7-477a-bbe0-334aab138a4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 612 | Mandatory testing | CB6
2390ebb4-c585-44b9-a92c-0bffcd678d1e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613
0e4dbf5d-befd-4a5e-8c4c-c278cf99d58d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Leadins
fb231280-0054-44f8-ae8b-756f45f0c997 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Roughin
2a3847ae-a0d9-4e3e-a4f5-e15d29e8515f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Cut out
6a56165f-f36f-4ebd-8157-8bf8e29bad9b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Fit off
70744f32-a504-4c29-abb0-3056330eabdd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Commissioning
517751ba-a37e-4655-b396-892d0c4e0361 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing
3b044c04-11fe-497c-a664-7370455df089 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB1
67be5259-37bd-4b4b-be4a-265d01436abc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB2
3e1b7a46-e9b6-4d04-a52f-1e626808f179 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB3
9ee01cd9-55ae-4a1f-b8b1-2687698a297e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB4
3a716f55-2b4b-4dad-9797-89df38a12eca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB5
54ad3d81-32c4-4883-9c69-985973918fe2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 6 | Apartment 613 | Mandatory testing | CB6
16b904c6-bff7-4c8f-b131-d4c0c500916f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7
269f7734-8d32-407a-bbf0-7409fe9cd320 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701
061c6951-7512-493a-ab1d-9de0009e9cdc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Leadins
49b970a2-2bd4-41e8-9133-07fb8d17f964 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Roughin
19d660f1-a172-4e2a-8de2-6577e5d970db |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Cut out
bde1c0eb-d76a-47c8-97a8-1c1f52b2b4d8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Fit off
2b263c33-b6f1-4728-a698-b87642fff057 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Commissioning
751ffd4a-7d82-4071-9d68-1d50277a3fa7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing
1f7143ae-070f-4581-befe-f4286af5ff9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB1
a735ff7c-070d-4999-9467-db28c357bda2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB2
d2720237-2352-4ed2-a205-c413ab216565 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB3
621451c6-145d-473f-b11a-771afedcf8ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB4
f22c7b74-8740-4728-b2a1-8dae6731ffe9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB5
227bb80e-3d72-4c1b-8e3b-9b61a127cdf0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 701 | Mandatory testing | CB6
cc597fc8-179a-47d5-9af6-f2b20f0b0d57 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702
02269afc-1e6c-4d91-8592-dfd56b0f0ce7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Leadins
e8c8fc07-fb3c-4c6f-bf05-d5252a214ab6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Roughin
ab9a1bba-f087-4a37-87c7-ae16b64e74f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Cut out
26659dfa-ecff-4819-97c9-4e8aefcc8d73 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Fit off
ea89d76d-7cc1-469f-a5c1-dd549c6ca00d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Commissioning
075d7ee0-aa40-40c3-a5d5-97269abb1c41 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing
a303dcc5-da0d-4259-9691-c1c618070dd2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB1
ed7dbc6f-71f7-4be2-868b-a439bc0a5004 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB2
0dee849e-3cff-41f7-8569-aeaab4b83f0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB3
291839c6-9578-4331-b49b-eda46f9e2a35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB4
67cd8a0e-a53f-4550-8f84-1d558bed9b06 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB5
6936b96d-2605-4340-a832-c16f8eb860e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 702 | Mandatory testing | CB6
53710d29-1894-4442-814f-9894a73c7a4f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703
9240a476-93f5-46a9-b697-4f4b2850ec90 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Leadins
6341ba3d-7e95-4489-8dda-69aa805f22be |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Roughin
4e8b5f25-0522-478f-911d-d949e915da79 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Cut out
6df8bab3-dce8-40a2-be21-cc31d66b8fc4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Fit off
d2979ea0-5e2c-4176-bc49-1ed250bccb3a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Commissioning
03971eab-d879-4af8-8a67-f10d1b6dc3bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing
37da1c97-69f1-4807-8373-7237cf18abdc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB1
eae5cc56-6ddc-4c9d-ab1a-a90cea9452ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB2
f6504b67-6669-4dd2-9f49-7f9be1c48ab5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB3
c655ac9f-1631-4655-ab53-addfc8953b06 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB4
c7d0e730-56fc-4146-ad9d-88bf011bad2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB5
13f0ef8a-1585-4705-897e-59debf41ff05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 703 | Mandatory testing | CB6
fe234e92-ad86-4853-af8b-4be5ae24d6c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704
c2ac413f-1f7f-4ae0-8424-fafada056197 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Leadins
f55b1f6b-c610-46e3-92f6-6344becec5fb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Roughin
abd39799-8628-425f-9052-179911faaf88 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Cut out
950127ab-3959-4785-96dd-0920909af412 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Fit off
4bc2ff8d-9fbf-4f73-a2b4-29aa9d166157 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Commissioning
9846c686-ffb8-41a9-bc1a-7b48cc1e22f3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing
53a01402-bcf4-447b-b121-2c8c6d124029 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB1
8a5df90a-c304-4b3b-af53-21f7801c5b57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB2
ca0feec6-1824-4370-93e9-4bb0ce0708f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB3
20fd2346-4cde-41ca-94bd-50bfe605694c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB4
74a35b4b-e306-43fe-9558-8661d673f805 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB5
c170369b-980d-401e-a497-0ec1f57b6166 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 704 | Mandatory testing | CB6
44733c95-b4d3-4ad5-9436-932cd55c8e98 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705
b908f259-fb49-488a-9a18-a98d0f2f4a3c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Leadins
f828b6bd-0dd4-49d7-bd26-31f6e6a6962e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Roughin
54d4497c-f6e9-41e2-a456-f46274c503d5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Cut out
9ef88ed3-d5b1-4e75-af38-c10715e16a9c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Fit off
3388b4c7-62c6-470c-a323-65af1e3e4ae7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Commissioning
a9540a87-0043-4ea1-ae48-2b8e4f9be8b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing
619d5c6f-56a2-4ca4-bf29-de8772826674 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB1
cde5010c-589f-4530-9ad5-6864f79f6fc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB2
e788b8a7-d85c-4d8f-a314-b9ac03dc4e1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB3
7699ddfc-ad5b-49d4-8ee1-0c3d607cae64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB4
a6c6f8ec-5ac9-4c27-9df3-d0a6ef8099f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB5
dcad6817-0d74-4672-9952-cbdbf877cd66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 705 | Mandatory testing | CB6
4f1030e2-462b-442b-92ce-15c5a8b86329 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706
012afd4f-8ec6-4ab3-8256-d818957bbfc3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Leadins
7f594dea-69bb-4293-a11a-631fc8c93ab4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Roughin
f2adabd0-abbe-42f5-a1e4-57f5bf481863 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Cut out
748b0dc8-498b-44be-ab9e-bcef9581899d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Fit off
410014fc-84ef-4568-b436-47c2b6f24444 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Commissioning
36e6d118-a969-46d3-942c-ccb138635369 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing
d4098190-6ebe-46b2-a216-348ace7371ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB1
de01e572-82dd-4ee0-b293-3888bf9ceec0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB2
e4e9ef21-7a82-4682-a574-138cf4ee8f42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB3
c494c3d9-7921-47d2-a4ff-686aa32d59ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB4
0a0809c5-dc3e-4bd4-931a-99fb6bcaf0be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB5
342dfa7e-678f-459d-b3c8-240bd6ff4c86 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 706 | Mandatory testing | CB6
bf0f675c-87d1-4261-b3e5-809d26ea5075 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707
5b998a0c-3a8f-43cf-a92d-07f505072a74 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Leadins
5586d617-8291-49ed-9c04-e57be194365d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Roughin
6e3a84fe-067b-4c69-8792-b3e9f15be4ff |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Cut out
ccaf5619-4d16-4bb4-b2c5-c0bced7878c1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Fit off
33ec6401-b56a-4ed3-ace9-9856eb2b3222 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Commissioning
be00f549-09f6-4f07-9d6c-70d1e9016d3c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing
909a15ff-618a-44dd-b3bc-095a6ec5d5c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB1
163bc059-3afd-4e7a-b9e5-9cc64878e19d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB2
d64d479c-bcfd-4fc3-81b2-f1b309b2fd5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB3
6e0bdcb3-e6b9-4069-b9b4-db95fb063131 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB4
8ab764cf-cf10-4f43-9245-8e140778cf2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB5
c6c891d1-2482-43c6-b3eb-1017422416ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 707 | Mandatory testing | CB6
bcaf7ae7-d45a-4ae1-addd-9d6ca6eebb63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708
560cb202-0356-4f6c-bd85-1b4a2b28eacd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Leadins
339b76b4-7b34-4fa8-9505-2828ea04c356 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Roughin
7f9024c6-5599-4bfe-a2e5-b6db1b74589e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Cut out
dceeeed7-9890-4599-ba8c-bb8979f7be33 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Fit off
49e64619-c95a-4a46-8ee5-ed5b4f267c80 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Commissioning
64ad135c-f2bc-452f-8f9e-58f532016d7e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing
5671cbfc-68d9-4114-8f48-017343af6daf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB1
3d0a2df6-9cf6-4594-b51e-8ef04737aa07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB2
0b6bff21-3f0a-480e-bfc5-d9e9330239fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB3
ca72e383-5fd6-438e-8072-510fb980d4e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB4
21ebcf82-51ef-4ef6-89b4-99bffe8cd53c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB5
5158fb01-23d1-4364-9c54-9d0f83c2b5bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 708 | Mandatory testing | CB6
a47f2071-e38d-4b68-b5cb-68d2002ef2a5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709
34aba69e-35fc-4310-b1ef-9e6be9daf3f9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Leadins
cf47e1d2-c0a2-4037-8c6d-301a0a701349 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Roughin
0499641c-e80d-4dc5-a21d-617b3ebec55a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Cut out
6b848495-8134-479c-a870-0601f2857254 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Fit off
8ab01c43-2ae3-493c-9d1e-f8eeafa0c772 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Commissioning
0da84dc3-b8d8-45aa-aa6c-77d540752c35 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing
fbcaa42b-d15b-4c65-bbd0-1131964403c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB1
24379db0-538a-41a5-a607-f77c236c5ba9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB2
0cc92b26-0c15-427e-89ba-937e449e6c74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB3
4a991f46-0636-4998-93aa-0245b4fd5929 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB4
e810cef6-de28-4c89-875e-2582a47ffe71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB5
58e9b60e-60a2-4ef1-b224-48687faf396e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 709 | Mandatory testing | CB6
1f3e23ad-9d57-4117-be93-2813bf049948 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710
43fe1702-0422-4724-931d-7ef79e4e2794 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Leadins
b006ed51-88bc-4d97-b0fb-62b77080ca82 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Roughin
ead11aff-a0b7-4be2-bc90-7805044a5de4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Cut out
e363d7c5-85df-4432-bba8-d5667bf9b121 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Fit off
cdefeb43-2df8-44d3-8d2e-53008789688f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Commissioning
3bfbae51-eba9-498d-b002-0fb6b05f4df0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing
b906ab2d-f326-4299-945b-4716888cd67c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB1
475f77dd-dba8-44cc-bc66-389010b89e13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB2
561c7398-8eef-40fa-8f11-af764b99f8df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB3
1b811442-407b-455d-87ee-8c32cc415b23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB4
fcda3939-ec6f-44fd-8f29-e548a04ac18c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB5
c145f7f0-76e0-445e-a350-bc0f78516986 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 710 | Mandatory testing | CB6
61873205-f305-4c26-9837-7fc8d98bf247 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711
0cb404f2-f3ac-4539-ad38-579f3a8fcb9c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Leadins
52a69025-3a82-4f69-9336-179dfe664952 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Roughin
f2d9eaa5-a8b6-43d0-866a-3af51a9439dd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Cut out
abc35c63-cf3d-4df9-bf86-37473020c6ca |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Fit off
30e715a3-7796-41ba-9747-eba466888575 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Commissioning
ad72181d-84ad-425d-8e75-43bfd3360b9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing
37c55ac1-9a2d-4766-b069-799e888d33a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB1
40cee82b-9333-495b-825a-6d72f2e20876 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB2
8d1f7612-abe4-4d3b-a5b8-8a28febbf7c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB3
db750b76-45e1-4cf7-9d7d-3195f0cde7fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB4
b3be964c-e061-49f2-8ece-71e1f0d86301 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB5
03c4ab74-8d4f-40d6-ac8b-50e26a2b336e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 711 | Mandatory testing | CB6
37c97347-22f2-4be1-96c2-219fae18d12a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712
a425b300-1e44-4cc2-bd5e-735a53965c0c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Leadins
bb1de83d-2b36-4760-a08e-ae3cd82c4b57 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Roughin
8ca3bc87-d02d-4c10-8396-102c4976e8e5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Cut out
1b3728a2-64ac-415b-be49-b8d5649cbf10 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Fit off
c7066bfd-f2b2-41ce-912d-f076394771a3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Commissioning
fe5963c7-8348-4c32-9c7d-32ce6ef641df |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing
34af360d-b219-421f-b23a-54987dfc8f94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB1
2692f6d7-746b-4a79-adc4-88515ee295c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB2
1ae512b3-08c6-45a6-955b-237ee1ae861e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB3
85a4cb93-3c66-4738-8be4-f53ad3beb8e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB4
6ac4afd8-7ce3-40f8-8f6a-ed91c691a29e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB5
14080a36-fe30-4030-928e-7e0300cc2220 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 712 | Mandatory testing | CB6
4ea472b7-e32c-410b-ba35-f54bbb9834b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713
84f0e749-dc07-4341-83c5-e9b9301d9f9d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Leadins
ef695d54-eb20-4ddb-abc3-5c1e9b3437a3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Roughin
a41d3960-c397-4790-b768-014bee7b15cb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Cut out
f477080f-6b35-4e5a-89f2-ed76c8a1dc1c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Fit off
6a9b8097-764e-453b-9fdb-eaa2da35403b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Commissioning
7942a2ff-9948-460f-a81f-53b5c50e5ff7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing
02a3e0f9-e1e4-4ef2-894b-4579a877a0ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB1
ba951a8f-0fc3-4241-a16d-ae431efeb0e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB2
ffa443db-046a-4c46-905d-eb371ced68c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB3
2b609132-08d6-425a-a4fc-a62498437584 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB4
2524e1e6-030d-483e-8d7d-99e9f198a9f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB5
e03a3d56-5a8e-4304-befe-21864552c9ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 7 | Apartment 713 | Mandatory testing | CB6
6bbf7014-64f7-4b56-a8a7-18d8de5eb7f4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8
974132ef-1949-409b-b2e0-e834c6df6932 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801
298cae3b-6d7d-48e3-af5d-e7262565adc2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Leadins
d5ad355f-ca45-40ce-8076-95a1c65641ab |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Roughin
147cd659-0ce2-4042-a56a-e629e49c6d67 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Cut out
b9e55008-3cb8-4612-98e6-9f642dfa8991 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Fit off
6f816986-79c9-4e7a-bdf6-fbc64ccfbefa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Commissioning
15888120-3982-42b7-82c3-d1d27d32529c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing
68c368c1-6c2f-4463-9d63-cdda896d239a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB1
30ad08e7-c5c6-4f06-b0c6-1a904b1cd1cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB2
424f73ee-a0ed-42d3-8333-28040ae8e1aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB3
34115618-93e3-4a4a-a1ae-e167e69065a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB4
858bfbe9-aa68-4f4d-9673-e01e0508b606 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB5
736fb5ec-dadd-416e-9a41-24cf2a6ef57c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 801 | Mandatory testing | CB6
eec0fce7-097b-4866-ab88-fea00cc369b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802
ac17438e-55dc-4381-be7f-1fc55a940d14 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Leadins
910dfc6a-43db-4cf9-b303-b6eb36218986 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Roughin
a0689d9b-b5a8-4249-b540-2546c908d29a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Cut out
3a017660-4fa0-4174-917c-75c648be44c2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Fit off
dcd8daf6-7525-4c51-bac9-f5a734152746 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Commissioning
11ec6901-5b5a-4f7e-b572-7d2ad7f49f75 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing
bf77a966-1f4c-4ee8-9855-90047afd7cc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB1
07fc2581-81fd-4556-9cd5-70bb54ca8db4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB2
604fa771-abe7-4e9e-bd8d-c32215af7bb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB3
9e2117bd-2566-46fa-987b-667f212c4621 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB4
23337c7c-7c45-4fa6-bb5d-4e358f2c7369 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB5
6cc68f50-2561-48f0-9528-5d648cf0eba9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 802 | Mandatory testing | CB6
a2407ad7-fd42-4b75-aaeb-b934310b96e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803
db55ad8d-9cb6-4516-93b0-03eb5b1b738d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Leadins
a31f2432-12e6-46da-b8e2-fca64d7d70cd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Roughin
db3e7c73-12d2-45c0-99ab-a5a0d934b21b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Cut out
d33aeaeb-cb8f-4ec4-a076-2acbb6b2a9e2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Fit off
7c621168-0da9-4bc1-94c6-e03d4ae535f2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Commissioning
068a4111-cf08-4adc-b339-fbee79f4d7f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing
db92f71a-5ade-4da9-94cb-19029a41eead |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB1
b06f1512-23cb-4c3c-a686-397824a848c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB2
bc2dd91b-14cd-4d6d-a014-ae735c317205 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB3
e953a010-dd29-43f4-95b7-0b3279e5ae93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB4
bd2cf7a2-0c3a-4d29-9df8-b04a17f0f22e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB5
d111bf26-c85d-4743-9417-bb2c060c2d38 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 803 | Mandatory testing | CB6
3cbc10c4-6bb2-435a-aa1e-f08c32b06f6e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804
8efff641-e7d7-4a50-8adb-85e90bd8ed97 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Leadins
416d0091-9ff1-40f8-b16a-bce1d82e3fea |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Roughin
4ae4e603-d3ff-4ee1-812b-4a51508bf802 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Cut out
82d43274-33fa-41f9-a3cd-9d70842f6d10 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Fit off
9b31af50-0c73-4b2e-a21f-1c0794b36e6c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Commissioning
e4dd9b84-4c08-41cf-95d7-9a34060847fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing
ac2b9794-bcb1-4c0e-984e-2f4d7fd290c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB1
feb9e522-f3c0-442b-848c-511531f0d186 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB2
dcf22daa-8917-4340-9b24-0c2f560c9830 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB3
c4109e82-31fc-4b58-a806-9cecd589ef1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB4
04cbbe9e-066e-49f6-9fb5-0bf291814ec3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB5
ee09dcf6-7ee4-4321-945b-8d75f11f9483 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 804 | Mandatory testing | CB6
bdd9eb80-81fe-43e5-89d9-a7350eef522d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805
9cd07b0d-7a39-47f7-bae2-426543a5eafc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Leadins
9bd18f82-60b2-4ffb-90e9-c2589c6f5f64 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Roughin
90d6ed8c-c76b-4348-84fb-b41d7827e0ad |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Cut out
df9bab1a-9428-412a-87bd-c6a2da924784 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Fit off
729cbed6-5490-4447-a489-bebff55fe63a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Commissioning
f5cdfbb7-1bb2-49d5-9c65-dabbbed00112 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing
3aaf026c-0603-49be-86f1-efbd52c37fec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB1
b0cd04c2-5ba6-4f71-9a51-a03fceafbdc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB2
11cd4c45-c931-4f45-886c-092bd9975411 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB3
af3165cb-7342-4bb5-9ac6-3bd603542c14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB4
939b6412-d3a8-415a-9c8b-2d707483a863 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB5
843bdbcd-83e6-482f-bc79-93dfbe14f3b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 805 | Mandatory testing | CB6
28386a44-c4c9-4779-b28e-eed7020e24df |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806
e5d38203-3902-420f-aad0-43eac249489a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Leadins
ab1a5506-7872-44d6-a0ff-830d7f12aec0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Roughin
abb3d192-6de5-4ee8-9cac-9fd4b555298b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Cut out
d612a966-8b4b-4dc4-a6fe-4926b556d45f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Fit off
fa65a0ad-8853-4e8a-a4a4-29d764bdf0e5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Commissioning
42af1cc8-392f-4a9e-abb2-930c6d106923 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing
db038877-dc67-478f-bfb3-3a8fd6fce0b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB1
d5a1434e-0a9b-42c2-bd80-c5e29d833c09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB2
b475b777-366b-4712-ba4f-f69bf495f7ae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB3
2194dd40-9544-4536-924a-264976e26330 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB4
cb3efa7f-3498-4c2a-bff8-08815781a8a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB5
365b6fae-484e-4cff-b399-d683dbdcee8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 806 | Mandatory testing | CB6
d8598acb-eb8e-4a61-a3bb-5d8fe8251be8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807
f56ccaf7-e32c-4346-af15-92251e2b6fcc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Leadins
ce21f391-3788-4f10-a209-c17ae70b9882 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Roughin
b4113b71-835e-4475-8bbd-b4113fa6462e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Cut out
c5bf1783-1661-40bc-86ef-94cc574f102c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Fit off
c0407d75-9d17-4817-9b5a-38b1f047aa7d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Commissioning
74c88526-5140-4e4f-a4c3-2ad0324fd97c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing
e34b9aa4-7adf-4130-845f-903f336490ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB1
0a6b11a3-27a9-432b-83aa-c9194dce472c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB2
223859c6-4e9b-4e8b-8c84-bedd968efefa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB3
9b7cc838-f510-46cf-9dc1-a7a282af2d95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB4
a97754cd-6249-425e-a656-85e6e45e1650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB5
e27e2c0f-be36-4e98-9a9c-a8f6f98d15d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 807 | Mandatory testing | CB6
fe0aa9c1-209e-4c70-a2a7-d5464eef7589 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808
241ec241-f25c-4161-ae9f-ea652bac8da4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Leadins
f3d4cdcd-c53f-412c-a8e7-bacd7117c65b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Roughin
ddfd7430-1cff-4bb9-9478-b212196455cd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Cut out
01ab3a3b-ee87-4278-b12e-75e9537e7ee8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Fit off
3a85b8be-3487-4a53-8705-c2ac290b87aa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Commissioning
2051aff8-19d1-4f82-ae44-f6b4f9416e17 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing
26219ab7-7fac-4b08-810b-2e9fc8e2aeb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB1
801f6e76-7927-4224-9712-2aadca5f5c8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB2
98b02310-c9d3-45c1-a7d7-58a8267a3d1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB3
1f0d091b-cde9-4c72-8059-72eac2f93638 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB4
0af8434e-9e00-41d2-af8f-47125b045a3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB5
258a02f9-ce80-4cd4-b4ea-0cf4a4bb142b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 808 | Mandatory testing | CB6
9ba53cb7-a4eb-4ea5-9e32-7bb592af216f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809
d38a8da1-85f3-420f-ab33-bfcfef4140bd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Leadins
1158def5-aae8-4ba2-b643-626ad41766b9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Roughin
8c6f9271-1af0-4778-8dfa-b657c0fb4c05 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Cut out
97f44812-f4ae-4fc9-940b-b77eed03c34d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Fit off
62e90144-26b4-44f2-b8b0-78a0b81a4df0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Commissioning
5bb9234c-a871-4bfd-bcc6-40d6c3dda737 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing
da6e5f72-2b62-4889-b8ea-163661072b49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB1
b0e60c28-87c9-4704-a2f5-8cdf6a244d02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB2
e4ed8d91-f9c8-407f-9da9-6508b1f22cda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB3
a688307a-cc2b-4d3c-9ff9-bde0f3b67d56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB4
cc1b6044-e92a-4e18-87bc-91c54a0d658b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB5
b6f9658c-17d2-497e-8335-03bf038eaf8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 809 | Mandatory testing | CB6
b2a4583e-95a7-4506-bec2-3dc1e9521d0a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810
dc4ea6b2-285c-4dc8-9f51-2a4dd1716236 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Leadins
32ad6ead-0910-4f4e-ba54-ed2fb5662e63 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Roughin
f61940f7-2cab-4cd8-b697-792325008951 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Cut out
8982a963-2669-426b-8ae7-f3a39c464af8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Fit off
9946183a-a63f-4254-846d-dbe1033f8ce1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Commissioning
d601e4d0-f935-4806-8c54-e473ab716f2b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing
2ecefb52-b63e-4e31-a329-768d2f104c05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB1
bc0ed202-9393-4b89-9cf4-6c4416d5f8d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB2
db839f1f-b582-402e-9a78-0eff02e298cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB3
877024c4-1691-4ff1-b7f1-fc7565878e33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB4
08958004-ff52-4220-925a-1da8defae40c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB5
4bc9787c-f676-4171-aff8-266b63503771 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 810 | Mandatory testing | CB6
a07b21e9-0998-4611-85ad-467640717cae |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811
c4752e16-55aa-4533-bb0f-95de3ae8c395 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Leadins
5b83fcf5-030a-49e5-a3ff-1a7c30287af1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Roughin
7ee87614-625f-4194-bbf2-17fc383884d2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Cut out
4cbbed4d-5344-4d7e-b84b-bbc7943290f4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Fit off
c998ef0a-b4fb-4667-a400-bc4dbd889c82 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Commissioning
036ac310-f08c-4e1d-9f3c-d453d7f9292b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing
5772e93b-27d5-4208-bfc1-5376292a3e34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB1
e5b23c7c-ce7c-493c-9d54-aae2f999ac6c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB2
4150d5f1-0629-4c08-a04f-f0002fa61a03 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB3
6adcb767-2141-40eb-8fe2-02537cedd48f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB4
77c4a904-4b6d-45f9-9937-13f31c609a54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB5
14c32429-66e7-45d5-9d26-c873914b8aeb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 811 | Mandatory testing | CB6
926d7f05-0b6d-418c-aeec-9637d0c7e3dd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812
718b4c36-c961-4a0b-ba72-ac828f99a89e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Leadins
c9f941a3-2452-488a-9166-42dcba062393 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Roughin
a117b64a-7055-40ad-a85e-859ba39cb8be |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Cut out
5df4bf73-59c1-4a6c-8f8b-e5c7e51ebf7a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Fit off
018b15f3-f729-4fb5-9e33-c0859af7e92f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Commissioning
d73b94db-5d2e-433e-90b0-93c864cbc4e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing
a9eab218-28eb-4c4e-a296-b7360b54f314 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB1
ea9fca42-ce24-4844-b227-eccb58f9a9c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB2
63b8adeb-5dad-4907-af65-4229323436a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB3
bc9d0f0d-2bdb-47d2-bbb7-32c75dce6d7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB4
25f0e413-004d-47e6-bb52-953c52956a89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB5
d06c06de-0679-43da-9d03-d9aaa200beaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 812 | Mandatory testing | CB6
df4191a1-6b2c-4191-be29-0c55c1f6f007 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813
d90d3283-f4e3-45f4-8c29-c39df456367c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Leadins
2e572db7-5f19-45d9-9b24-51000e7ba111 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Roughin
3358d9ff-5cdf-4db5-ad37-a5eaa642dc78 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Cut out
46553703-8d7c-4415-a618-277c96b17603 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Fit off
ad1cf917-3c14-412c-b2b0-b79830b43e06 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Commissioning
69c7773d-ef36-4960-a2b4-621dbef50e42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing
0b8ca3e9-7798-47e6-abd7-6d173e352813 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB1
6f74a452-5d9f-4951-b63a-cf57e8d70349 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB2
13270a69-9b0c-47b5-a84e-bb4963587a46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB3
25dd3f1c-f7cc-4739-80c7-7afcbf7b8b0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB4
eef0e4ea-5f11-4364-9c20-83a501b77968 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB5
160ec0e9-1fd2-4198-9ea4-0bedcb72ff84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 8 | Apartment 813 | Mandatory testing | CB6
ab0a6ab9-1b7b-4066-b6c6-d2e1f0f0c059 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9
eee14b0a-05eb-49d8-8d3e-462b5db1a311 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901
eb56aa17-a5f1-4aec-81c7-ba0e7f4b5d98 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Leadins
ce302454-186a-4c64-afe7-24cbd3ae9e1a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Roughin
4d69cdd2-6617-40c3-a310-751903daa792 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Cut out
7577e0be-08ac-4efd-bb6d-b6fc48f24ecf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Fit off
dc036e35-a40c-4ab4-8133-da442d2cef8f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Commissioning
39aa45f9-58fb-4f30-b44d-96edfc0d16ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing
df3d1fa8-7435-46e0-8f36-f1501a9b195d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB1
5dbf5fa7-2a19-4a19-802b-c62ccb2d8ae5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB2
2ed375f5-fd01-47b2-b8f3-ad52ffd09ee9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB3
5b400a55-7802-4fab-bad6-6fa00e8f69c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB4
7018477d-8d28-47c9-997c-7ae0493e1508 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB5
3c8e8c2a-59ec-4c7d-b853-864dd2c25a35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 901 | Mandatory testing | CB6
f4f228a1-0434-4fe0-b451-422bddc11181 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902
0833742d-db98-4dd3-abe4-8cd55eec54f9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Leadins
781ff609-cf93-4b2e-ad9d-7f7abf5342cc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Roughin
90952c38-a8fd-4d83-b927-85042218f70c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Cut out
f6b76c0a-2e17-48a2-b584-1dc339117ffd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Fit off
a23f0286-6a78-4f3a-9d67-9578269f8f53 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Commissioning
1181feb7-d131-4e10-b8f5-9c04ae9c841a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing
b5b209bf-e8ed-4425-a024-ec47c0e1c5ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB1
4dcf9ece-1044-416e-8a05-49f007ed643e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB2
368d9dde-e558-4db3-900b-a39d13163980 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB3
b372849c-3233-4604-9b77-dd2738054aea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB4
8e5a7bb2-ea0a-4d91-9067-8a41971ce278 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB5
855525b0-ed88-40fe-80e5-5dc4ae3b435b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 902 | Mandatory testing | CB6
0d4e198e-f82f-4e18-a96e-eaf81dad19f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903
43d833a4-15b3-432b-a832-929e1157759f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Leadins
c1f40328-7893-43de-909a-8aedb6687ee4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Roughin
c76a3ac6-5d7c-476d-b7f4-d5cc9c6cbecb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Cut out
b50dde9d-459c-45ff-a7b5-f81e4197a78c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Fit off
ee810bb3-8ccc-4251-a499-72c4963e2914 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Commissioning
493289fa-b302-4554-ae6e-dfd1eb4dec29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing
12b14c0f-ff60-4aeb-a546-95dcafa75f9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB1
e0f9e38d-3151-4277-bde8-2ab64c283e14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB2
1b5a3efe-c584-4c5e-bdea-5038d9f5a22d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB3
2239d048-3037-47b4-997e-82322a6b5d9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB4
42f8ee63-fab8-4d0e-a4d8-b0d4b658097c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB5
04248d68-8ede-4f7d-a3cc-934adf495512 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 903 | Mandatory testing | CB6
af153423-2592-470f-a7ad-25460b7de945 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904
92281ef4-b5bb-442f-b4b1-d7c2ed7890a9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Leadins
1508a0cb-4283-4f1d-82d9-9fb7c529338d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Roughin
c34618f5-24b5-4ea9-bdeb-f91dc84e00ac |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Cut out
0e5c8faf-d40c-4cd4-8cf2-10a576c87782 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Fit off
3c44a297-55f5-4e97-8976-c472c12f894b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Commissioning
5d8e0183-544f-4dbf-b398-db0d5701b9cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing
6ed83ebe-2409-40c7-8c90-adbaf84bbe25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB1
036d0824-abf3-4bef-8e70-94243bd44b75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB2
560ac915-ba8a-4405-bac7-c5e5d799b9a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB3
3dd39d00-4367-4931-b224-4ce6f34da629 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB4
a4e2c032-cc40-4abf-a690-513fb4fe2929 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB5
87e27f41-4908-4e90-9245-fcf44c75db4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 904 | Mandatory testing | CB6
75823469-4bb7-4c9e-ad87-05035bb2c65a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905
528c2310-97c9-40b1-a837-d05f3c89742f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Leadins
6ed8a8ca-36e8-4870-80c2-be2805c8eb78 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Roughin
30f1cbad-b4e0-4497-9687-fd74ff26d31f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Cut out
67c4f842-0ae7-4ed2-b59c-730c957f626a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Fit off
b3c800f5-ce35-4263-bbf3-c05394226d32 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Commissioning
a72c47e5-baf7-4747-9c5f-ef2228a4df4d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing
57f6dca4-466e-4064-a39e-8297bf870d60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB1
0c9a13c4-0a19-4471-af94-529c444c6d9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB2
e8f2e412-a500-4abc-bbc3-56afc9ed4035 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB3
4b6faf49-7bfd-4ce5-9a1a-597224ba2f3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB4
f2cd1911-1ba1-4d0c-8fcd-92dbe639b95c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB5
b2222f85-ab86-42b3-8b59-490304c7240b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 905 | Mandatory testing | CB6
e36b1612-8204-4601-ab63-69b7bd440dee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906
6f0e2d95-5edb-43d5-8eb6-dc8902ea2f48 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Leadins
a11b73c7-23f9-4537-a17c-a27f5018766c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Roughin
3d354557-f3e9-4499-9a0e-c98ec820b54f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Cut out
70b25116-74d6-482c-9ab5-b9c3fb58097a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Fit off
7e983ff5-4c9f-4e5b-8fdd-5e6ea0331da0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Commissioning
61a9ee75-4232-40e0-8630-5ba8469d90a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing
e2c0c379-7e91-42b5-b56c-97755d206284 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB1
112e3783-6c65-42d6-8b08-107dd5afa678 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB2
c0e3dcbf-1032-4bdb-9418-513906e1cb86 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB3
f0668fd0-9ff9-4fc8-b2c5-2e240c4c9d71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB4
c84aa4c7-9c03-4fff-a913-386d1d96964d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB5
f1b360d1-ca0d-4af8-9517-874b7ded23b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 906 | Mandatory testing | CB6
2ab8fd54-89cc-4aaf-9f92-68f26019b288 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907
e2f4c03f-5c8f-4540-8a5c-b0818cdad040 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Leadins
026048e8-412e-47af-a5e8-8505050f47b0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Roughin
a7767c15-6280-4063-9c25-99aab3016133 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Cut out
c7d1c59f-6f38-4669-97b3-b9114b6a607e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Fit off
0e7f3354-7d0a-47e9-be40-c14b46dc1074 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Commissioning
d482708b-c91a-4beb-9529-5f874646e5ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing
e912b766-1e6a-4cde-9b96-671078c4b672 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB1
d8b35a69-a5b9-417e-9f47-d1ff249f27dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB2
ef682294-6acd-4372-ac2c-b5f8ecc658ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB3
cc311789-f249-4d4e-93ca-095ee670139d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB4
444ea8a1-7587-482e-8ab0-de83f9724944 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB5
f8a5a9d4-fbf4-46a5-95a4-4a2e231f9d94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 907 | Mandatory testing | CB6
241dfd52-5589-4305-9fad-b65a7362d6a1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908
3b5bea90-443f-487f-a3e8-609976dd1a7f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Leadins
29c8dea3-3d12-4548-b99f-8a922773270c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Roughin
99d1d2dc-6c66-4f97-b1df-7605b16add5a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Cut out
2b69394b-b729-450d-b7ef-6438771c24a0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Fit off
c8ccf931-fe76-4c41-8949-4c2df9861033 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Commissioning
703a9557-f74d-4c4f-961d-416bc7b7dbfd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing
54992d96-ee9b-4477-82fc-abdad2069eb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB1
41674cb9-494e-487d-9586-578ea14dfbd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB2
21988c93-463e-4d99-8f37-dceb17e081c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB3
5b9abd6e-b479-4f39-8470-fecba0e6af18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB4
21b88f0a-dbc4-42cb-89e0-b39fce795106 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB5
97a91ad1-b64c-432c-b76d-c2df12584332 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 908 | Mandatory testing | CB6
c862dcbd-88b1-4db8-8dc7-07db7678fe7a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909
64221f89-0752-4dbc-8938-b3a040d22fe2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Leadins
66f2a333-465d-4089-90d6-a474b28b1d54 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Roughin
f5f37698-1bfb-4d99-86bf-00ec4e953036 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Cut out
39bd4f15-4b8b-48f8-9a11-96dc0e310ad5 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Fit off
1d0bbf92-8366-44af-bec4-3e011f2eadea |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Commissioning
86dae070-27f4-4c62-9640-5e05dbe889b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing
2e5ca1a9-6caf-4b7d-8f28-ddc84ca83e76 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB1
ee0c1d88-63f8-4d8d-b3b9-94e81174963e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB2
5df5c767-90c3-488a-8519-2a791e382c74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB3
340e4841-6ae1-4cfc-a1ac-a97ae75839e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB4
9bf7b076-1e42-4054-b966-ef76d5f31972 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB5
6b82e162-cd16-49c1-8f9d-58c31ec86a7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 909 | Mandatory testing | CB6
0b31caef-69d4-4f33-98fd-b97ef346a30d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910
c65f6460-cbc1-45f5-87d7-fe87f3e442bc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Leadins
4c822944-c6f9-4f28-9e5a-351145531eab |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Roughin
b196ba39-82ae-4a89-b526-be2b88473401 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Cut out
3017c8cd-45e8-43b9-80c5-ae15ffb220c1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Fit off
3b373146-4033-47f0-b62f-4cad75b4a62a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Commissioning
50e6c07f-ae55-4c73-8b4d-447bc5b27092 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing
6bc940f0-6525-4f01-b54d-bdc4c9895eb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB1
500c91c8-97c4-4050-ba1b-b1bec7abaa1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB2
8e9c253d-26ef-4fab-98ea-1a9dd9c39cd0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB3
84012b95-14b4-4454-abdb-a20e32182813 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB4
f9d0daa4-933d-4b43-9d86-f24df1ca1f20 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB5
72832c08-0829-4bf3-b537-159e027e1dc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 910 | Mandatory testing | CB6
8b13c57e-c619-44dc-b50f-fc30f6687f60 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911
43b429b9-8558-4fef-bd2f-2fb35eb3611a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Leadins
f5eb3d02-b0c2-47aa-bdbb-90e2543a6bb5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Roughin
3f04d672-e619-4189-a3bf-4421ddbad2ad |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Cut out
bd391c8f-83c5-4005-bf0c-41fd19357ad3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Fit off
5d65deda-9d73-4d48-85f1-751251b4f253 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Commissioning
deac9fc9-2472-4d1e-9287-9c32222e6268 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing
cf83534f-6f0e-42fe-a9d6-d109b5e1b0f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB1
312cf3c7-4749-4f07-81f9-aadb8949659f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB2
40744c37-860c-4955-83a0-2dd447a7da10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB3
0e61d3ab-c363-49b6-bf30-9716e002e320 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB4
e4d84a27-7365-4d44-ab62-d09402aadb21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB5
7bab2e03-fb45-4ab8-97ff-6490cb244c66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 911 | Mandatory testing | CB6
759c629e-0578-4e77-8238-a20d0b024830 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912
8364d510-2a18-4522-9780-5c90687b2790 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Leadins
8b2a46aa-f9d2-494a-8b2d-efeef8fb0e3a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Roughin
09040cb7-1df9-4cd2-838a-846a1e9a0485 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Cut out
bf379b3c-e994-4a7c-b9dc-bc1f5627b27c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Fit off
1eb384fa-dffc-4eba-8987-8019b274a8bd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Commissioning
5b83c196-fba9-4378-ae47-0a5515baf183 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing
285de17e-f781-4ba5-a3e7-d90e4b7deb99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB1
37ab6924-30db-451b-ac38-f7c9dad006b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB2
7dd6c1d2-4f9b-48f5-ba14-9985c87fd9eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB3
038478d8-de78-40b1-9d2d-e26c5dda73d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB4
d7d23e86-c840-4c63-959c-e0b8e6576c72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB5
ea085698-0482-49b8-a693-32735595558a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 912 | Mandatory testing | CB6
5ed55ae5-d51f-49e3-8a47-fc0d36ea155d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913
a62b8869-ef53-4fe9-a084-7e464c451d2b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Leadins
a7bbe07a-aca0-4c5a-81d1-277cbee0b690 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Roughin
d9f395f9-3700-44a7-b483-570d073b605c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Cut out
2824e99b-1c98-43d9-90a8-51a2371eefbf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Fit off
acd003ce-849a-435e-9b60-bb5dfbae33e5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Commissioning
a373c300-aeb5-42ac-8d70-5c22e727569d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing
b5b645c1-f5c7-41fe-9e47-49a7ed9cf322 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB1
87d0ff69-8413-4e75-8ef8-e9ce1c8144e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB2
418cc72e-d395-4da7-a1b1-e2c0419818fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB3
931904af-cb50-4037-851e-2c64f722e242 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB4
f241b5d6-e424-4d0e-9149-06fcf03f536a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB5
92f1ec62-3cda-4c04-b3ef-4b626bbd0f32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 9 | Apartment 913 | Mandatory testing | CB6
954dacf9-92e1-4bf7-9a2d-026a3e5f28f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10
4fb9bf9f-4b06-4a47-bce3-7c6ef2a11e1e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001
0642d87b-8ee3-40b5-9e66-11d2c18b82a6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Leadins
fdf7d19b-e16e-492f-a194-b294b59b18a6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Roughin
b5d357ba-8ccc-4528-ac52-a6973c3d8d17 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Cut out
e49185f3-47ec-41e4-b875-c8a9f7d34929 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Fit off
0304b03e-6fbe-4522-b07c-36910e14a99a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Commissioning
7ee901e7-4e80-4446-b83d-196766dc964d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing
cb4c5e57-577d-497c-b83b-120deed8f38e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB1
5ec9edaa-c717-4d79-a6e5-2a6fba1732b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB2
f81c2d28-a694-431e-ba10-a240a4f0d9af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB3
f76ccd24-3395-40ae-b577-2c7592e0ff6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB4
63bc6f0f-0b5a-4f1c-8bef-a9a3149cf045 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB5
ea95c819-9dd7-475e-9aaf-a2d589452166 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1001 | Mandatory testing | CB6
8faed333-5c25-4f9a-9cf9-e98cd0f03f83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002
6b92728f-cb68-4f89-932b-a688a5d1b09e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Leadins
437c2dda-97b5-4b64-9fc8-91f3939d126c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Roughin
36c9de44-df98-4007-b690-b48296383d87 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Cut out
128227af-c085-4def-92b3-6c31cae494ce |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Fit off
63fc4979-823e-497c-ade3-48b1e367d814 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Commissioning
ace61887-1aef-4a80-8b1d-e3fbcb4b1956 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing
d6d3d9c2-8b30-425d-ac18-ea14202f02ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB1
c22dc42a-319b-4d83-a1e6-47b6350f580d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB2
bd8ff094-6a1f-4384-98d3-24be13ab92c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB3
7d0dd8ee-1ffb-4984-b002-476a0020c81f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB4
d66d304b-649a-49f2-aa1c-2b254b862cec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB5
99421d35-e50c-407e-881d-4206b7e02aba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1002 | Mandatory testing | CB6
6d685b3d-44a0-4d82-b4ec-e1b498c8a939 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003
17109867-293e-4ba9-96b0-bd05b607ceef |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Leadins
fab18d46-a7bd-4a4b-b7bc-bb1ab8ea77c0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Roughin
3c73d916-871f-4992-9ec8-897aa1521dbb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Cut out
2e77fadd-665d-484e-9435-d8f163ff72f9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Fit off
e6f0ae12-319d-45cd-a555-47cebe70ed6a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Commissioning
fc04bf21-34db-4fbe-b987-35a9e0fe5294 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing
18da53c5-4b62-4d81-9516-2a69673e8d2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB1
79579c19-79eb-48b5-b2a5-c8134e26573b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB2
0278dec2-25cf-44aa-ad2f-d7e0b8455bac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB3
2157ffb5-8163-4831-9ce4-0cb17891c96a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB4
12307b8b-52f5-4641-90c2-4ff3d5d6be52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB5
d5207062-38fb-4695-8d6b-6a13a04680b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1003 | Mandatory testing | CB6
0231e292-f901-434d-aa30-dfdf80720d43 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004
8ccc6c97-3bc0-4280-a6b9-7daa5057a7eb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Leadins
724fd2f5-5582-4297-9d4e-9d0755523638 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Roughin
7e1e9966-251b-4014-aa67-c78ae8942394 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Cut out
64250dec-3dae-45dc-8c87-2f12f861be36 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Fit off
03fc6dcb-329a-4203-8535-10cb7c2dbb5e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Commissioning
e09a6dca-f9c6-415e-8316-5fc858b77e37 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing
0fb4ac00-fa62-4b4f-b649-34f63b45fea1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB1
f4d13386-84e8-4623-ab8c-bd38837b32e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB2
d40d555f-15f1-4f82-a2ea-6da602bf0ba5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB3
d9063c16-327b-4b87-a7fa-259048d2fc2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB4
50717f7b-7e40-46e9-9f19-0cf2af624d3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB5
1ad9a9bf-7351-4f37-8853-b2a350c9db7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1004 | Mandatory testing | CB6
5afb4b9c-4ae1-41ba-b6af-9ead61e1f906 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005
3be6cc9d-1cbd-4ba6-bca2-b903a3f834ae |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Leadins
3215a37b-b5fc-47e2-8ef0-5f46d9197959 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Roughin
402397b9-c294-4331-8c66-01003b89d723 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Cut out
ad38375d-a543-4d89-be17-3813c79249e1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Fit off
7bde158e-28fc-4d3e-84e8-1ae0fd825609 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Commissioning
1baa4c87-38a3-4a32-a71b-72d905b51b63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing
394826f4-0fe3-469b-b4f3-f64be85ee81a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB1
77f0b8c3-e97d-4ca8-a0e1-4bc46df0b934 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB2
708c4e0a-51d3-4c3b-acd7-894fa18f2560 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB3
d6674f79-81f8-4523-8e8a-d54863e20781 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB4
631d2537-207d-4caa-9411-68fcb56f3cfd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB5
4bcc0aeb-a440-457e-8da6-3a5c658d10d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1005 | Mandatory testing | CB6
0d8ccb21-7888-4148-9e36-5ee8095a86e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006
1c4c07c0-f2c0-46a5-9488-57246288f4cb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Leadins
8d8c765f-306d-4542-a85d-821d299803ea |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Roughin
fc7224b0-e64a-462c-893f-11e891c7c678 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Cut out
40f7b71b-a35f-4fa7-bde2-134876e7c77b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Fit off
bcffd69d-f572-40c7-8143-30156da0deb2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Commissioning
f227bd00-5b9d-4410-ad67-278e6c08845c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing
90caf17d-6371-4eeb-97cf-d0dcf437fada |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB1
4a1ec01a-ec3c-450e-b95a-edf660bec636 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB2
d934d2e7-fe76-4fa5-9c68-9d14af62dd47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB3
9f37119c-c373-4048-85f3-e4e610a4779b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB4
730c044d-3810-4794-a68f-ca703f1ee111 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB5
ef480668-7d4e-49f8-bec7-1d6d68c26306 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1006 | Mandatory testing | CB6
153369ce-53a8-4b1b-b980-c3a5a2eb4cc0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007
b189cc46-5dd9-4817-b647-811a454a734f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Leadins
ab6caa74-6b76-4e20-8582-b66dffa74ffe |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Roughin
bb5344bb-2c61-4915-9bc4-c31a0e0d37d5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Cut out
1d530a01-9d7a-4afb-ab02-be87be7b3e66 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Fit off
8609c1dc-1104-4b44-8959-02b074d5a40b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Commissioning
8e66a599-f625-49c5-85a2-f70fc36a98b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing
cb68481e-3d76-4ac4-ada8-4634ef10921a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB1
cd7ce285-fa94-4960-925d-ff51f0da4dd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB2
5a8cf400-96bb-4185-b9d3-b663eb3694b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB3
46b48882-36da-4d3f-a8a4-c3acde1650ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB4
f01e81ed-efc2-4a27-b2fe-75afa95060ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB5
4516dfc6-6f7e-40aa-929c-a8be25a2b197 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1007 | Mandatory testing | CB6
b3206251-a56e-4c0d-91f6-1037618ffeb0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008
2ec062b6-834e-46c7-a8af-5fe29e0bcf32 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Leadins
052ecc83-c965-4b3d-945e-fd5e0c664161 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Roughin
12addeea-ca18-4d44-bb1e-51aa5045fc46 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Cut out
33ec53d6-b3c7-4cf5-beb9-801f0b11c70f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Fit off
3438b21b-e5e8-4225-995a-b212edea01cf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Commissioning
73563110-0191-4a8c-b870-42f27f83cbdd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing
7af309f0-b355-4261-9ad5-d77c5a4b7728 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB1
a8039d42-d1b6-45b8-8844-343154ae68e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB2
19095333-677c-4a64-b675-bca6fa77d32b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB3
5f000b83-5761-4465-8da6-489a5c79d542 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB4
7fa16050-1d76-463b-9989-73509c4ced1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB5
f2b661b9-200d-4d89-9449-91db7c563467 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1008 | Mandatory testing | CB6
5acd4cea-5dc5-4157-91f3-425c3ef878ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009
1108fbc4-1e1e-4655-b30a-8408d80deb46 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Leadins
1164acb7-de50-491f-9b27-e6862e90b539 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Roughin
ea3543c7-fb8b-4e1a-a791-bbe33d15a1a3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Cut out
b90f7928-4f8f-453d-8109-6012a9e63dcf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Fit off
e7affe64-81f3-4220-b89a-683fb1f4d0b0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Commissioning
487c6f5f-b9de-4a5a-8858-f1df5ae2b14f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing
4cf88072-806a-47e4-a415-aa19aba99df5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB1
792e1924-042b-46f1-a541-ad13f1b1ecdc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB2
45dcc990-6c7b-4960-99d4-932d40ca210c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB3
b4ac62b3-c95a-432c-ad90-12fb804d1915 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB4
1e2a9669-6762-4462-a780-e40598cc8ffb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB5
96fae588-c0f9-4c1a-91d1-944d89a9d2fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1009 | Mandatory testing | CB6
c0d7cf13-afc6-4139-bae0-2cf73069a56f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010
804d9090-af9a-4f8f-864c-e4c306b99876 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Leadins
494cd947-0c7f-465d-abc9-40a38662260b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Roughin
259e88bc-af26-44a4-a29e-96a774ab18c1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Cut out
2be3fdfc-b751-493d-a203-b88885b28399 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Fit off
14b1b5a2-16a2-4853-b8e9-cec0f7c76773 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Commissioning
d7ca25d5-60a3-4574-b22e-d01540a94c12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing
27d342d3-e9c1-4734-838b-1ba4b8e80b92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB1
f650b15e-3b35-44ff-a86d-1494c75e0dba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB2
22bfc851-a9dd-4b47-89a9-0e0162cec9d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB3
73de2673-314c-4521-9ca1-9cf41dded6f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB4
562e1c35-ff6c-4c2f-b674-bee53e06e05b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB5
a538b5cc-750d-4b49-a10e-f469de8b39c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1010 | Mandatory testing | CB6
09684e7d-33fe-43d4-9d03-dc01fba10ad0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011
7b401f36-72e6-4709-94d2-67bb262469b6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Leadins
f03eab05-9e7d-46ac-988f-d9b7c03bfe04 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Roughin
af800303-f11c-4e86-bbc6-cac3579908e9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Cut out
2c5a0c0b-83ef-42a2-ab5b-9e46cc568209 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Fit off
63178560-fd5e-48a7-a515-a106c0576933 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Commissioning
90c824c3-221b-4932-a989-62f41e639687 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing
c8d13a11-d478-4db8-aa1c-bbba829058fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB1
bfb8e2a8-bcca-4827-80ff-0abbe9487fd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB2
28bbcb4d-f3c8-4bb7-964a-0d31e1693309 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB3
8196e821-5509-42ba-800c-b5f5018ad579 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB4
d4f45c12-f4b6-48c9-8180-340562e29952 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB5
ebd018e8-3d48-455c-921c-7ebce48ff50d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1011 | Mandatory testing | CB6
99610b51-888c-4eae-8e3c-be9da0c45e76 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012
bf027c75-4fbb-4378-8d2f-b6858213485b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Leadins
650e1fe4-0d67-4f22-862f-8ae110c51514 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Roughin
e4df6895-86b5-43ad-bdd6-c3f7ebfa94c5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Cut out
1071cb3b-7381-4d43-ad95-9e84b6ae8add |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Fit off
b66f4e43-7db4-4570-8f7c-d05e42cf4413 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Commissioning
dbe54361-c240-4369-8982-bf9569fd18e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing
467fcf8f-18ad-4235-b8c6-12f7ca6d1a8a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB1
07158565-27e2-454c-b01e-c9ec10590ac6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB2
503baf41-cb79-4257-8324-5569cfe05c39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB3
aef857e9-560a-4674-b1e0-276af370b9c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB4
287f12e8-35ba-4119-af93-f194a4015add |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB5
a87d00bb-f86b-4506-8f13-becae17b8b2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1012 | Mandatory testing | CB6
efab5aa5-e421-4e55-bd76-8fdcac303531 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013
318f9393-809f-483e-807a-549d01d05888 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Leadins
6bee1ea1-0a84-42aa-b875-c376dbd5c2db |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Roughin
abaec2d3-7604-4dfe-b30b-9f336f1b011c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Cut out
2344f23b-7f0e-4d8c-8525-56bd17be9820 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Fit off
6f77afec-734f-408e-9af3-2d57b3da6f0f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Commissioning
b8e69fdf-f6fd-4413-9ef7-5f14d67f4c5c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing
b4f8fc43-1355-48d1-b6c3-b59b6c3d3336 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB1
f69abde9-6f8b-4ee2-836e-2676ec56f062 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB2
feb9893a-f6de-426f-9bc2-2afcb5844eb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB3
2cde026c-cc0e-4dc5-b1e7-22e07599fd50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB4
f4effdb1-0ef4-4a9b-8786-1ad2fc32d25f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB5
ee4345ac-1aa9-45b4-9f76-bc8afc12f1db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 10 | Apartment 1013 | Mandatory testing | CB6
76dee3d7-c41e-4529-b771-7c560d7f9b1a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11
525f398a-b88b-4248-b091-a29c0ba46a4b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101
9021b7cb-571f-45ad-bbcb-38b1a711b992 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Leadins
01eb285e-4f18-4ef3-8c8b-8c3512980cb8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Roughin
af2119fa-0f4d-46ea-a0ce-16dd63b56f90 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Cut out
cc3565fd-66ea-44a4-9e42-04d8dd40a98e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Fit off
af90a540-af15-4638-90ea-86a042d115bf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Commissioning
4a370601-cd7a-4f74-bb89-d64d09e05045 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing
ab7f2798-a6a2-4683-896e-f39e1a6dde30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB1
0781f156-e956-40be-9a4d-a243422c742a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB2
a3fe3eda-a9a0-4c0e-9ff9-3ad7f07e8b78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB3
202c8344-b79e-49cd-bfca-8d5f3599c303 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB4
685f4364-1b6a-44e1-87c2-149ade16949d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB5
4690533a-5786-4c57-8dca-e3fa41b3a147 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1101 | Mandatory testing | CB6
6caf4fe4-58ae-490f-8e7d-a51a09834ee4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102
0524e3ef-f701-485b-8afb-a6d6932566a8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Leadins
be8a775d-0d81-474d-8227-8192315b6ad3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Roughin
b6595411-e9b5-4a32-ad48-cd3b2e329e7c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Cut out
c9ccb70c-be37-4cb9-b5ec-b38892fe5025 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Fit off
bc0bb271-c2d0-45de-9a0f-a5f52dcfc69e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Commissioning
3bfa53e8-3f3e-4314-a8f1-3d6e2a3cd4f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing
7e4daa4f-fbd5-41de-91df-07fbe4d3312d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB1
508c7f30-c3c9-454f-9d1a-664ca16bc33c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB2
3e036085-2f12-4a5d-a6dc-3bc5a61f716e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB3
8a892366-70c6-45e3-b040-b77fd18f7146 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB4
9c198853-f69c-4e70-bb5e-4e81b73fab57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB5
e372ea73-ce2d-488b-a781-c571de2e949b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1102 | Mandatory testing | CB6
cfffc8fe-a6ec-4775-9af0-7e32b663983a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103
b4586c95-30eb-41e3-9d7a-f7d308d32c60 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Leadins
bb578a54-3df4-426b-bd3b-6db3cb0aa85f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Roughin
c2b01cd1-00fc-4b9e-9cc2-29f63d257f45 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Cut out
d1488c04-2527-4001-8943-1a6fb4c94db7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Fit off
06511001-c9e9-4e71-9a50-4824ebb14579 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Commissioning
1f58990a-c425-4dc7-84a2-6c2383a60671 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing
227677f8-34e5-45d5-8d2e-0fc3e6911ebe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB1
2f71ab2c-c8ab-4254-b0e2-f486d8cdaf4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB2
033b615a-17e1-4741-8d88-6505e4cdd84b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB3
a94d9280-623e-4ae1-aacc-131f341decc8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB4
ab6bc597-e527-4933-b0b3-a4218e1b397f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB5
af3be5b6-95b0-4f90-ad24-45c3fc42467d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1103 | Mandatory testing | CB6
929b6c2d-f00e-4337-af74-de5864e9a99b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104
376c82dc-c40d-463e-b810-7cb02e3c9325 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Leadins
b908e17d-5841-4afc-84d0-5918587ef64c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Roughin
b7372d84-9860-4c94-92fe-3235f3b5c58f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Cut out
7d2d4667-e494-4216-8af2-daf545cc6ecc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Fit off
b5481b10-a757-45cb-beb8-2dd6654db095 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Commissioning
e6b01ad1-117c-4b7c-96f5-d40004a031d9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing
18c63f39-bb7b-46de-a709-508d48b329ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB1
1aac25d6-2f30-4ddf-86e8-cec755c158a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB2
40bf2250-8d07-4e35-a2f5-bb53445a7ed0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB3
ea0aa4f6-8fa0-4170-a38f-2c4096ea329d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB4
0e587997-9900-451b-a2aa-635e0f384e8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB5
d6fb8219-440f-4838-877e-d24a75ba10a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1104 | Mandatory testing | CB6
0bb3b9e2-2296-433e-a906-3ffb54f1e8c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105
1fa104f4-578e-4f8f-931b-2260fe758ea4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Leadins
a081332a-0e9b-4f70-a8ad-550f255a5649 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Roughin
9d89ef5c-d36f-4443-9f92-062a4a0b6462 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Cut out
9ec85ffc-c64c-4756-8e47-470f5efc4f96 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Fit off
db836ad2-df06-4258-8009-db3985412eb7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Commissioning
0577830c-5368-4103-81c3-7c7cb757aeb0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing
6bebd2ee-8c8e-45f9-9656-ab72277c0cab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB1
091ff27c-5963-4373-940e-d7e5e7b74ee9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB2
322a3c12-5e41-4f9f-b086-036ac160216c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB3
53e43d13-9a83-4971-b7d6-9caf734ca7f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB4
6ed8f45a-afee-496c-811b-35da21d2721f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB5
50f6a657-a2db-4758-b1bc-fdf01e8c7f78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1105 | Mandatory testing | CB6
b2ba1e84-bd2c-4ce7-bb50-1b9a607d24fa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106
9db6a0bb-b93d-434f-b5b5-303daf5a7398 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Leadins
7f2013f1-9f24-4d62-a472-3c664eca7cf1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Roughin
2132fdc2-6971-415e-9673-ccf2aee03ec5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Cut out
db3a018f-9be5-450f-b33b-61ab0f72968e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Fit off
8d6a8e00-6a8d-4888-90ac-6f997330ebba |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Commissioning
c5835bef-3cf0-4bed-bd9f-753bf8ceebeb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing
ddfbd436-1553-4f26-8097-b7bcc12af12b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB1
cca1e6c9-d9dc-4264-b156-b661f8dabfa0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB2
0f0fc389-a10a-410f-818b-3ab3f76cb0b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB3
4a9e74ab-5903-477e-871e-391920e9785a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB4
350bd207-19cf-44f1-874f-45bd14caa7f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB5
61822f58-b902-4308-87aa-a788531e2ebe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1106 | Mandatory testing | CB6
f478e339-526d-4fff-9a41-ff6757ca7fc0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107
67af16ad-c482-4788-bc43-7d01471d7403 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Leadins
b8517a7f-f32a-4e23-ba5e-ebd3ee86fd65 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Roughin
678a83b9-4e08-408a-9d46-681880ced7d4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Cut out
939766da-4718-4a2f-b56f-4afc40b1b55c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Fit off
76411417-b19c-4c0c-b98f-391ea076be95 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Commissioning
a732b0ee-1ba1-45f0-a16c-5e1dbf07b3f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing
203e2cec-1564-46f2-aeae-c4510fac5b42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB1
3f094dcf-5c2d-4b87-a5d0-40f1b00c9f05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB2
ca83165c-e74d-4e39-b3cf-7731d734ea0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB3
e44d33bd-1370-4e83-8235-b94fb9063998 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB4
095cac97-7295-4be8-a5c3-07de3fa7287f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB5
3322e597-4474-457f-91ad-ae754118277b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1107 | Mandatory testing | CB6
34ae0263-e999-4ade-8ce3-58ddbd6af30d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108
b497a16f-7087-43ab-836c-efe0675b9ec6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Leadins
0ce11b12-a860-4753-8744-96f75d8d6079 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Roughin
7e0aab02-612f-4a59-90a9-b4b81c580063 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Cut out
4846b1fe-80cf-4da7-98bc-be115953ab7b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Fit off
303aba56-e723-4991-bd2c-d3acbde17cb4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Commissioning
56a0e7f1-bef9-4271-bfa0-6e757acd0b48 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing
2430435c-a1c9-482b-9d72-f69e81d234a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB1
da978cb2-1ac1-44b3-8bb5-77b3c4e7570f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB2
407d0f1b-5cf6-435f-964b-fded32f2c884 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB3
74fb2679-8f2d-4943-a155-8a77a02e6b5c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB4
2bd45840-a19c-4a89-ad1a-411afa702246 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB5
c3a2c0ec-e27b-4361-a8ff-c2fade1125c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1108 | Mandatory testing | CB6
e1da6536-c00c-466e-8b5e-38a38aa6ee5b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109
05c1ffb0-a717-4679-b63c-f11e9bdf235a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Leadins
c1a8e1f9-2ef8-4677-bc5e-013c01860daf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Roughin
4ba55486-3554-4033-9b67-4218418ef06d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Cut out
66f14add-f42c-4e98-9f81-9cea14b280c2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Fit off
40c2313e-c4ca-4686-9f2d-b85f8f426310 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Commissioning
106dd983-0575-42cf-ba9d-932345ff90bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing
d63edb1d-fc2b-4deb-81c3-7af7ddd5127a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB1
9a75a0ee-c51d-4bdf-96eb-9ab7e8eed5a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB2
594ce53e-a42c-4aa2-9289-6b76439fd3d4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB3
5e438a76-2c97-4e0b-a3fb-d1dcc9a85e31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB4
d21d8f9f-799f-42ac-a14e-e48717acdb53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB5
da6294f6-4571-4b08-9693-fa1881db9dbc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1109 | Mandatory testing | CB6
fec35ea6-6b22-494e-8831-d09f8b66a255 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110
e2d4b6a9-a16b-4722-af15-91a9f2549d70 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Leadins
c0910101-eb68-4ba6-8fb7-45451bed595c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Roughin
bab774fc-afdd-48a1-8f27-cbf709b6c96e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Cut out
97450537-51d9-44f0-a5e3-16afe8fc89e7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Fit off
98cacc1f-db2d-493a-bd81-4840a044ae9b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Commissioning
85bf1109-fe9d-4dda-9f85-f88d3c5c416d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing
dd80fdc6-909b-48cc-9caa-8e778b4f85b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB1
9f3f9cf9-c2c6-4299-9342-bca12ef6e61a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB2
67c53e8d-b460-4ac9-83a5-88e30ba9ea9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB3
e88f6ebe-8f65-4f2c-86fe-4d987d45d47f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB4
c37a3d5c-e6bf-4452-a38a-bb00924ba189 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB5
294323ef-0e2d-4e18-95b0-150d4b1bd649 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1110 | Mandatory testing | CB6
d2555b96-61e4-41e0-8778-c493a0f86238 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111
bcc6af19-27d7-477f-92fe-2a350f80c5d2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Leadins
4df3330c-a520-4f38-a120-83afebe2185d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Roughin
b6b443d3-8788-4bf1-be02-002305bfb731 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Cut out
6b718eed-8eb2-4b91-b684-3ab0c11c524c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Fit off
70fc47a3-99b2-41b5-b826-1cfe0d02df6f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Commissioning
eefd2776-54c2-442d-8431-df67a81f63f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing
a028c5fd-4d99-4266-92ce-7f8579ef7753 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB1
df48a37e-b0b0-4cda-a9df-0504c7f76568 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB2
2897f033-30cf-445e-ac79-e688cf5d4431 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB3
1bc6a98f-1e75-44c1-93e1-a825a79ee54e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB4
cc7be62a-e521-4234-93db-111c0e339471 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB5
4fd6adb8-6796-473d-b041-6d9154efcf3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1111 | Mandatory testing | CB6
8d7a7f53-bfd5-4f87-8a2c-a892666730cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112
2952685e-fd40-46cc-9fa0-606cee1ccf82 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Leadins
16164fa3-34dc-46c9-8591-4fb2dac2a747 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Roughin
cb433d26-35fb-45c8-857e-2924652d908d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Cut out
87ec4888-9ba6-4ebb-8e9f-4882198971e8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Fit off
48006ee7-ec7b-467b-9fb5-b424eb33f52c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Commissioning
f25a75e2-5828-4dde-bfba-371a9600f81e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing
819306ab-ac19-41f6-9f1a-2e27933e71f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB1
78d495b3-4e10-497c-9155-f8ae77966422 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB2
134391bf-7a90-4d71-aec0-2807a09a62bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB3
bef21e09-fc5f-4f8d-8d14-1a99d1c5119f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB4
4c20624d-f9c4-4b71-be2b-ba24999526d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB5
7122dfe6-f5e6-452f-89ef-871d29435c81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1112 | Mandatory testing | CB6
8eac3ed7-f4c6-4ac9-a338-e903bd3bcd01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113
69fb4203-d03d-4367-bfcd-c748ad2e3902 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Leadins
149f3358-12b6-4a3d-87bc-58b5b3306fb9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Roughin
10b3b001-1801-4c96-a4c0-6a209ec72dd6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Cut out
07ce88a1-55ee-448b-b05c-2b7c2c29accc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Fit off
4e6f5b6b-79e3-4176-9d55-2c704ad2456a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Commissioning
c13f0b59-c8b3-480e-a8b4-082e56e3b2cd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing
da4fd60f-134d-4e5f-b92f-7db3a3f3833b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB1
feadc981-ee34-4ec4-802c-320752ba39d4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB2
0ae3ff43-5653-43f0-b723-903e4e7355ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB3
fa78dce7-8390-4d4a-8218-b5f6cab02e8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB4
1fd48398-6d76-4605-b355-d45135ba1295 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB5
f4e2cb68-eead-4c52-ab15-81c8d9ad1cd8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 11 | Apartment 1113 | Mandatory testing | CB6
be0fe318-e95a-436f-b4db-126e667eaf45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12
380c01e2-33d8-4e61-870b-f67ea1164ceb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201
78d6ea85-11e0-43eb-8261-9ba0552a6197 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Leadins
5ef509a2-c3e6-4dac-a6dc-5b4e25d3bae2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Roughin
f2f24387-e006-4215-ad0a-f4df26f28e72 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Cut out
7517b287-b395-4108-952d-a170c7415570 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Fit off
0d5cf1d2-7e14-415f-ab46-a3874f1a4f47 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Commissioning
d8fa3393-84a1-4da2-82f1-73edc78a7d87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing
2f6c3a98-5b00-49b4-a4db-ccd75dc37aa7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB1
f8ba6550-1a2a-497f-855d-94004e0b63d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB2
6e4118ab-5b91-4ac7-b0c8-08ffee0ceffe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB3
a66c4130-df66-46b0-a219-2004f9878f35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB4
9b6b2d0a-2cbe-4356-bef1-00c4ed23b516 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB5
ab1031e4-3c62-4330-bbe4-64bf20996c0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1201 | Mandatory testing | CB6
bb7c23c7-c525-4a55-9936-6d3274394669 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202
c1cc9e93-e0f8-43d8-9d6b-4f7ccbc0c54f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Leadins
a354214d-fc9a-420b-82ba-48352fb6ea88 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Roughin
597bf330-2a93-466f-a482-f5cd54aa2236 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Cut out
d6403e43-ae0b-419d-968a-aee5e8eea15b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Fit off
64f383a4-6ade-4015-bdcc-b34d4e50d0b7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Commissioning
ca31cfd7-0849-4a06-94aa-49971ad99723 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing
3128a148-0d1c-4bd5-94b3-ae5d3c548108 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB1
aba64018-4656-45a4-bc37-8b555b447b4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB2
1df41138-970b-4bda-803f-7acf3e50aebe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB3
ae07b3ae-e505-4a29-8971-518760fcc39a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB4
a56050f9-ef7a-431b-99d2-6a9eae543d89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB5
8ccfac5b-922a-411b-be26-7140528eade7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1202 | Mandatory testing | CB6
87147a31-afad-477b-9d9c-2250468dc0ef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203
73009703-422a-4bb0-a725-ce6f62f4ddaf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Leadins
bec8282f-12ca-4ed9-97eb-0f1709567b75 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Roughin
62b6c2b6-b00c-4231-9f22-407ae9e99cda |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Cut out
95b1158c-f324-478d-92e3-ef13d0e4bb92 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Fit off
831405a6-1ae6-40a7-ba45-054b4f1b3151 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Commissioning
b00f49ff-ac39-4a3d-8996-92115ab22926 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing
161f98ff-6898-4df8-99e0-4891a699f06a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB1
304d522e-27f9-45fe-9175-2e00e05c315b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB2
038ec1d4-115a-4502-ba38-38bc2f2403e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB3
c5bc2103-df8b-4337-ac04-5179d761c105 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB4
c4aee5f3-52d6-4367-bb76-1e64917c233b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB5
844059e5-cb62-4e7c-b3fb-202ba44ca5aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1203 | Mandatory testing | CB6
ed824913-4957-4afc-922d-8dca595b7bf2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204
1747d9aa-9e4c-4e7f-b1a7-18955f2f4fe5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Leadins
bdc67fbe-2129-43b4-b429-276e6a90fc4a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Roughin
71a3e55b-7e1e-4c6c-97b9-5bc12a3fe6cf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Cut out
0171d0f5-92f6-4e23-b139-315215c4d8e0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Fit off
8382ce89-fbeb-42f1-8f1f-9fdecfe57863 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Commissioning
ec0a660d-a155-4fe2-ae36-f0bdec0ce14a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing
227ff31e-847f-440d-b51a-283cd02276a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB1
490baba9-30e2-439b-a944-71569e4561e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB2
576fd318-2199-4121-bb11-28b42466c29c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB3
1e43501a-bb69-43db-a383-372027d421b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB4
9054931f-1162-459f-a294-16545b0c10ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB5
ef3c34cb-b540-4239-821f-29d0bbf2a088 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1204 | Mandatory testing | CB6
b49b6df1-691e-4672-8585-4100f6724705 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205
b626d4bc-09ab-4a20-8059-4e3047c1d6d3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Leadins
cf929b07-37a1-4289-82e1-a38db1b9f922 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Roughin
e40dbcc5-da70-46c7-802c-eb15dfe1ff24 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Cut out
fb6ed406-5a88-4246-b675-20d075650a62 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Fit off
76a960e7-a1db-4059-ad62-bbe621dff5de |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Commissioning
ac3df617-d359-4248-9c12-a6c42c6fdeb0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing
1f1a5059-b96e-41c9-8e2e-31cf813012ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB1
db67b7fd-9f43-416f-9ba2-7579c33edbb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB2
49cb58be-bbef-49d1-8d87-5c8ab41c7ffd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB3
99f0eb48-ca5a-4e35-b069-3a6afb62d085 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB4
1d9e7934-b26a-4724-851a-15402557b79d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB5
cb3eabd5-c66c-412c-b33a-daadebd614fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1205 | Mandatory testing | CB6
87fde445-85dc-46df-b1f9-3d1eb83b3bad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206
a3f3a934-2889-40df-8586-16a5e9fc5cde |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Leadins
bd087c8a-a884-4c86-848c-519724214875 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Roughin
958a76eb-3b53-4a5d-9909-6abf121bf24a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Cut out
c6d7e4d4-b499-4606-98de-cd77c02579e8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Fit off
3854af5b-a6f9-40b8-9ffb-02add7f719fa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Commissioning
9a08dd3d-dfbb-4f53-966b-8c4ec45f301a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing
3f81ec6b-1fc9-4ee8-abde-e5d98b9a2825 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB1
52854005-58b5-4a8a-9939-0261224aee12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB2
f88c61a8-0c7a-4d61-b060-6eca6c355abf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB3
dfe2c7ad-5284-4301-9477-61b141959a52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB4
a1ac6753-33cd-4402-b39d-bc4ea43a284a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB5
001c4000-28a8-4f29-9ac1-051068c7ba08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1206 | Mandatory testing | CB6
319e7d88-441c-4bec-a2e3-cc3f4ce58487 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207
9939dc31-7858-4a9c-a910-15cc3018fd91 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Leadins
0ba891e4-c019-4fa6-9f07-31e0f1b00828 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Roughin
34cf42b1-5e4f-46cd-83ab-b2e4a0463d18 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Cut out
9c0f789f-a078-424d-9ab2-71e0e1138691 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Fit off
02dd0f7b-7ad6-4d91-809f-5b7d0bd57acc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Commissioning
c8938e82-6055-440f-bff5-03730dc57c87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing
96a18ac0-b438-4e25-916e-2954cfdc164d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB1
912e7c4d-253a-4eac-b14b-40a2efd602a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB2
b5b368e1-8ab9-4598-bfee-39dc4cc1544d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB3
7d9e2dc4-b968-41bc-9ea7-7fe3257f5fd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB4
3d229d53-1dac-4b2b-a063-19eac6703a0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB5
75a36efa-4cb0-44db-8320-8c52f1ee6dd0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1207 | Mandatory testing | CB6
89659349-0e50-4611-a72f-ad0bd225f8f4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208
5f8afd78-116f-4ef6-902f-fc4eca8aa4ec |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Leadins
cc83b093-ba99-4ccb-bdd5-d0acc4d0f985 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Roughin
189f3338-3537-422b-8410-9967478ee137 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Cut out
1263d0cb-7a66-4572-a1f0-8bb2ad4130e3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Fit off
bc821522-3b7a-445c-bf61-89fcf7a985e8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Commissioning
ac2eb30b-2627-48b3-81d9-316310f6d210 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing
00b6cce3-c112-465a-9207-dfbf2050f31e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB1
4f3e255f-b3da-4940-b992-9eaf04186c31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB2
9a12c110-8a4c-4b2d-abc1-44e00277d270 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB3
2fbf3cd2-a22c-4f8e-9d35-4403a2149f2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB4
0ba60c84-e53d-4ca4-8e5f-78930f75f967 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB5
a49c04a1-354f-4269-a4e8-06ebdfc6f927 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1208 | Mandatory testing | CB6
f34a3fb8-55a9-4854-a337-e022631058fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209
3baee92a-8c96-4eb2-b098-726686cad882 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Leadins
b5fbb87b-eabb-4d58-b07a-a2ecd28d6453 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Roughin
24edaf39-4a71-4a05-a314-5137da1b2e62 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Cut out
3651a481-df2d-4ae0-a3e5-f8aaaef606a2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Fit off
b68a9d70-9fec-4e82-8ee4-fdc44571f3c0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Commissioning
136e4472-1b1e-442b-bf11-5fea56e27fbf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing
13c9f642-9034-405e-a7ff-f7a509980a23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB1
fc3c2cc0-9b2f-42d3-88ec-4448ea707e6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB2
84fa6297-bd23-413e-98d0-7aaffca51ff6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB3
2e00150b-eb76-4d1e-af23-694001b0274a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB4
4ac40b26-798f-49a0-b1dd-85521ae77ef7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB5
b301ca01-73dc-4200-af71-2b4a3a454790 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1209 | Mandatory testing | CB6
1983612c-58f2-47e5-b766-d6f765dbb2e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210
025761f3-e852-4388-8477-498022a16a6d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Leadins
a725b157-4d80-44b3-8465-0129952fc819 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Roughin
d7a37a80-6e7e-4162-a4f6-85704dbe633a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Cut out
4c232ed8-ff08-4fb3-ae5c-17b12d435a92 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Fit off
30329453-cb43-45db-b461-28d9abc17b39 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Commissioning
f878f223-ce6e-40f8-bcd8-d2af1924c0f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing
8c5dfee9-bd44-4fa4-8be6-4280b8fd1aec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB1
e878b9e9-2063-4b56-8fea-24c5340899c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB2
7723feaf-49f4-48f3-bec6-844c40c6f768 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB3
f2967a33-599e-48e0-b525-32e8264a6902 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB4
692d6258-9cfd-446f-985c-063ba5f5f341 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB5
b8feb59b-164c-44a3-8ed4-0daf7350af1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1210 | Mandatory testing | CB6
d7aca7ee-f9c5-411f-a442-4aedab5f3775 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211
18de405c-8826-4c37-8b80-6c9a3ce90b0b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Leadins
a331c97a-4117-46d8-a883-5025db2f606c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Roughin
7bc0bb71-5d45-4469-a045-394463671955 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Cut out
7ee919f1-4761-42c1-b977-739ee0845401 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Fit off
f4cc3f20-28d6-4d14-8893-0f4279edc18c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Commissioning
488ce674-16f2-4434-94b9-280a8bed95b1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing
915f73d5-1aff-478a-8748-be882672ff7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB1
3d0f471b-7919-4be0-9e4a-abbb961a296a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB2
5065fe47-0968-434d-a911-7483168d5666 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB3
19749f79-3390-4c0c-8d05-0544d460340d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB4
83abd245-2d62-4356-a074-200d78111d52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB5
ba5b73e9-577e-4f33-94d1-e86563852ea1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1211 | Mandatory testing | CB6
803b3a01-76da-44c2-8062-08ad3b6c36b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212
256f26d1-3b4a-4a9f-9cee-16fed8b6042d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Leadins
f5358363-2b48-44b5-b436-3b85966507fa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Roughin
7b9910a6-62ab-4cf1-889c-36131f5d6b5d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Cut out
c475f286-66fa-4e2f-92c0-19c43ed25be8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Fit off
95a860eb-dfbd-470e-a139-16fe6b29ef3f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Commissioning
74c5c91f-be35-4e41-a738-e0f65e1a2098 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing
134c5313-e9fd-4a66-be7f-1e1409c64fe9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB1
80f9ee90-bbdb-46a2-9aec-66c838a3c086 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB2
a18217f5-4605-46ff-bb8a-5709e51d4168 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB3
60289672-578e-4c84-a6bc-a2ab10a06acd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB4
fe241539-870a-4204-89c2-b6c9240b5e9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB5
697ea68f-5f5a-4c32-9f02-d64b47e006c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1212 | Mandatory testing | CB6
8bdb00f4-ac38-4968-8a4b-2c8793d43d6b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213
657534e5-547a-4de7-b0e2-265c2deb9114 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Leadins
1aa214a2-5146-471d-88df-2045ab4a1461 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Roughin
2ca143f4-3cbc-4dfe-9536-15eda8f6a7e0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Cut out
fb304d99-da6c-4632-bbe1-f8c263c46272 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Fit off
ad72b29c-5e54-4f53-a91b-6a72d2f75df5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Commissioning
88d5e5a2-1f21-4433-b818-0fa29bc16df5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing
05663890-e8aa-40df-bc35-092e65de1045 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB1
5579a429-393c-4b52-a06f-b44ac9125fe7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB2
c88cc0f9-1eb3-44e9-838b-151497003327 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB3
c9778a3b-2c44-43ad-8fca-418f7a2dda4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB4
6d2fbc2a-4762-40f9-8790-a0042f8ea622 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB5
0a873148-c39e-4898-8ca6-040b9fc2b3c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 12 | Apartment 1213 | Mandatory testing | CB6
49cec1d4-1e06-4c88-b66b-9171ea3be204 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13
da6f6a3f-d05b-4df3-9ed4-2da47ba826ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301
9cb0a6e6-e254-4697-b9ed-ba4d4428ed24 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Leadins
de0cb3df-5813-47e2-9762-710f3a9cfec3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Roughin
bea0b0a8-6a3c-492e-8ccf-9e7c4723949b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Cut out
d6f8fcd2-5f87-467f-93f8-1b71b6e8a881 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Fit off
0a890ae2-b98f-4665-bb63-de9d2010e239 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Commissioning
ec5cbe48-ccfc-4fd9-91d0-745be7aeb21c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing
08fda779-86d5-4cfe-861d-f808f6865d1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB1
86bcba7d-7025-4f11-b5f3-0aca23df40d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB2
a0a87e55-387c-4ccd-8b3c-dbb5b596cff1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB3
4d59ada8-f0f4-4617-b471-57aeb2195781 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB4
49da83ac-488f-4703-81e0-94c118d1e94b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB5
0f7f7ce4-a77a-45ad-a9f3-240a90973244 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1301 | Mandatory testing | CB6
00787deb-613f-48af-b892-1986b61866e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302
0b020ad4-77c4-4be4-bfe3-26abbc54634d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Leadins
51e17670-04ae-426c-bcfc-e0b4da671238 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Roughin
5d685c29-545b-40b0-8592-a37920d10652 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Cut out
6d7074e8-bfce-4878-a825-12248db54f43 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Fit off
d1b3d914-2668-4b63-90cd-63af4ffb81e3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Commissioning
9ecfadde-d124-41be-8601-8ae2a0aebe46 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing
1bbe5383-57bd-4752-ad8f-7e4d0e7b5b34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB1
12fe911a-fcc3-408a-b3b8-fdb6edaf584d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB2
4044ecea-1107-47a1-9e27-72a8c6af8366 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB3
bb339b0f-566f-430b-9b76-5764d3078175 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB4
f8673a8f-28f6-44bd-887d-0a91a5952b0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB5
a5222019-f494-4a1c-a126-9aa01a502f43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1302 | Mandatory testing | CB6
b93ad315-f91d-4410-9e5d-d97ef4a845e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303
5ae0574f-5114-4268-878a-237ddcaca72f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Leadins
8e2dc604-8ba8-479a-ac4f-5fef9007f715 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Roughin
dc2bf92a-424f-4240-96e7-77d7966a5711 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Cut out
581d1251-2a71-4472-901f-1e75f09a9d91 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Fit off
c5422051-b443-4e4d-be46-64c61d43d63c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Commissioning
80dc7d94-a7ec-4e30-8b32-65ba045010ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing
06b4ef36-ab19-4d1e-8005-2bca74970dda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB1
ba5fbf66-9406-4aa6-b0bf-d37697b44066 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB2
38daa7f3-1c70-44c4-be0f-aeaccfa9d1a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB3
6dab1b9e-5711-4ffd-a40a-f867bf872d42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB4
e7e7a446-a20f-4cfa-8e3f-f917412b4c16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB5
27a05634-6516-4a7b-99e4-f2662783147b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1303 | Mandatory testing | CB6
f3d566df-8e06-4cb1-a544-175897e616a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304
1a5b810b-d6d2-4320-83a2-7963575eba2b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Leadins
56e0c8bf-76b4-4beb-a9d7-a868bd1bda95 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Roughin
49787580-862b-4034-8f7f-067bd78658dc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Cut out
c8cff056-4a35-45c3-abdc-a7b6c91ab3f9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Fit off
76d4f6c4-54f4-4403-9b98-ac2c82d199ac |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Commissioning
163ba738-2958-4a51-b045-64d21126b151 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing
c88188d0-e40b-4ea6-b494-b518edae9b94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB1
926a96cf-97d7-478d-a836-a70a70310a3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB2
a5fcaad9-7087-43fe-ac99-f0b9c5f1e397 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB3
b87964d1-99b7-4cbd-904b-a399bc64208a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB4
157927e3-7849-4908-8fd6-c4309f4a9a5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB5
0dd3bb47-d305-4aab-9688-604128db2975 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1304 | Mandatory testing | CB6
275a3898-a091-45f1-b7cf-c9119a003917 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305
3faa4a10-6f12-4ca1-8b0e-3304bdf17692 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Leadins
5bd9b5c4-f9b5-4c1a-a5f8-e3186a66b595 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Roughin
e1af8536-2aa8-4765-b2cc-ca25aeacdf99 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Cut out
155182da-5437-4e8a-afff-d25f13dd3ec3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Fit off
50a7dbf9-65fa-468a-8a25-ede88291e67c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Commissioning
f726fd4a-3295-46fd-8d3c-8e2072ef5e33 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing
1f4322e6-5fdd-485d-8e57-ef08b63efb16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB1
1d19a2c5-1258-4904-9928-cd6906f6a568 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB2
9294dea4-6cfd-4298-ba99-c9412ecfefed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB3
9591898e-2519-4765-aea8-7a410b4e727f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB4
9c74ed76-48ba-4cdb-ae93-ab36c3a372b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB5
122ed110-65e3-489c-92ec-da90b934e34e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1305 | Mandatory testing | CB6
c51bebe3-1347-474c-ba9c-fd307509bc61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306
bfc799e1-7bca-454a-8e81-abcee89ac0cc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Leadins
6bee6925-4074-437a-8651-1205eac15b7e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Roughin
fd51b41c-c939-4abb-baf8-85ba41caa221 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Cut out
db9b7ea6-3934-4938-99b8-f398d2fa38ff |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Fit off
fbb7d8b0-357c-4538-b2c0-63cf28bedcf4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Commissioning
70c33069-806b-42d8-a2ff-49f8bf17a8d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing
5698da41-4e98-4982-9061-9b03b0ff367b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB1
8d8ca85b-f3d2-41ec-af64-b7ebdde7b3c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB2
cbeccdb1-c740-42ce-adbd-f113ab11636b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB3
efb4bebf-06d1-4e07-8fbe-20a851b1cc7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB4
e113c8f1-0b59-47af-9d4a-e65de48371fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB5
5c70b09f-86ba-439d-a856-0c3c0a919278 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1306 | Mandatory testing | CB6
98558966-96c5-41aa-babf-76f43018b965 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307
0ff9d451-5056-4db7-9696-41367cb21d23 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Leadins
9a6cd92d-be29-496b-99af-a53d06946977 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Roughin
65a5a9b2-28ff-49dc-bfb6-1eb56657a4cf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Cut out
c83943af-a0bb-488b-b9f7-3ca381c25c1e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Fit off
a4f4e942-efa9-44aa-8bbc-51fc0c20e352 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Commissioning
5161c8fe-9add-4f8e-8728-aeaa3f15a5a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing
7f6efb22-11a3-49c8-beb0-4f6ce01f0ad9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB1
ebbde03a-675a-4f3e-b455-13001604ddfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB2
d296aa34-bf1e-40f9-a008-482d81b767fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB3
683a932e-7fcf-4a4e-88bd-c1c04d5b6587 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB4
3f7ce533-0b24-4d64-a6ce-945db002f033 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB5
958b1647-1e01-47e4-b300-da11498f7fd2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1307 | Mandatory testing | CB6
8377810e-10fb-4f31-bfb1-29670471655f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308
2c6c9bce-cc23-4349-bc74-1ed5d03a8cb9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Leadins
b1ae196b-f259-4aa9-9a70-0004c18f752c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Roughin
ab47f914-fc06-4282-8e7c-3ee84672af24 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Cut out
128a32c5-a5a9-46c1-9921-03000c2bae86 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Fit off
7180fd62-6b5a-47ea-8857-ad12f61f7c80 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Commissioning
9df646b7-a061-481d-ab09-8a4596e9756e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing
33605005-625c-42e9-8a08-3b36b85c2000 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB1
f019b286-dc3b-4937-b1ac-5cbbbdafb1a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB2
0ba7adcf-72ba-4e82-8f89-b8c6236b6306 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB3
14c814d3-8cca-40d4-a0ab-e92afb7dcaae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB4
5335e122-5766-4745-bc8e-18125127e91a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB5
f85f2f03-c9a0-4d50-be61-0126ef2eac14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1308 | Mandatory testing | CB6
18fbf38f-c3a2-4892-a941-282fa46061fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309
a3395728-7a99-40ee-9a43-e056495557f9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Leadins
612ae4cf-d302-414f-acd7-b1dec9afe896 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Roughin
490bfeed-8075-458f-b774-544cdf541b7a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Cut out
7505e515-c2c4-403f-9a2e-1a0d4f7b5e0e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Fit off
7fe0cee9-da4e-488d-bc28-8e6e449dbd8c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Commissioning
e41b2d85-3b97-458a-b911-95f6f91af15e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing
3ef6a5a1-7c5a-4bed-9d5a-95aee08548ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB1
b9d5e4fe-43f8-49cd-ba3d-caf953b6e366 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB2
afcd3c97-11d6-48a1-86a7-1c844b54d9f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB3
f9846a27-e52e-4ed1-be4f-0ade30b03442 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB4
a7480133-583c-4d23-bdc5-de9b1954c28e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB5
b9fa4235-0ad4-4bf4-a5df-9cc111ea8b49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1309 | Mandatory testing | CB6
be2549ae-b795-433c-81d4-ab231833ff63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310
6836e7d1-b28e-4307-b7d6-9c1e72b6ea06 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Leadins
fc65869d-1166-45ee-aedf-fc5be5fab55b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Roughin
b9c7e847-81f3-4a62-b2f2-f72977460deb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Cut out
1c1a64b7-d8b7-444c-9e81-c51b2237784f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Fit off
4e04741e-2da5-466f-934a-da33dcf1bd7a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Commissioning
528047e6-a762-4f57-b839-ec6eb9915ac9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing
99910b57-7e84-4736-954c-dd3db9472aaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB1
3754678b-b601-4e21-9d56-2b87f711900d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB2
aec5b80b-b88d-4d10-afb9-03c346e13749 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB3
6458cb3a-e43a-410e-bc82-deef8d99bba9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB4
2ecff374-0966-4e7d-89cf-38c3d8bef60d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB5
2de8edb3-e9d7-48e1-af08-d8514c19775c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1310 | Mandatory testing | CB6
2f49cf16-05fe-42a6-b3c1-524d52c127aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311
719e2ff4-e3d6-49bf-8c87-545563c73b25 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Leadins
587ef82f-0fb5-4b45-9f1c-5394831237ef |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Roughin
296fd856-2fed-45e4-83b2-622382272b64 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Cut out
95aece65-9996-4b24-aebd-00e323aa5094 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Fit off
200bf135-4138-4e46-b0b4-4c1f2e25f260 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Commissioning
812dbd96-7c8f-451d-82fa-cf41f8848422 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing
839c8dee-d429-4fe6-8b7b-6f3212f09797 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB1
86457039-7e9f-472f-a913-ed6f5ee83eef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB2
b24d616a-2eeb-4a69-b46a-9e5b59f073bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB3
408c8583-22c5-4155-a16e-acf8cf740c3a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB4
aecce75c-31aa-4979-a4bb-3d6bbbc44435 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB5
964a3756-80c9-4c74-9022-c8940d1f448c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1311 | Mandatory testing | CB6
6b941659-d7b5-49c9-8354-50ce2946068a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312
fdd77311-e783-451f-8702-6461a6b45b0f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Leadins
aa293f1b-6578-4ad0-afd7-93536f415377 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Roughin
4f9ea8f5-9695-4dde-a5d5-179273061e61 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Cut out
7f5cfb10-78d9-4724-9b72-00c1246b1e71 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Fit off
9b541389-4ab1-4926-be13-7339e0b2bb0d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Commissioning
11dd73ab-e547-4d0b-9036-930e636ba0cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing
3755d886-0715-45a2-be16-0b248f0ae221 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB1
06a85b52-c12a-46ca-a069-e3580770d2cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB2
2f9104ce-0381-483b-a266-9a6ba48a076d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB3
8c4b9dd8-8b4f-40d6-8298-b54f92d057d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB4
590722b0-395f-405f-b3ba-2cc82a1e6650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB5
8166ca1d-467f-4a80-a532-50f0c0b0ee93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1312 | Mandatory testing | CB6
484a9dcc-8617-49b1-b13d-1257b9009820 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313
26d8b07b-026e-4d7f-8c92-62a1f5207123 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Leadins
fa4e6fda-a054-4d1a-bac9-26abadd46ec8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Roughin
1f02288c-675d-4ca0-a57a-36a040e95f7d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Cut out
9781ee79-eb2c-4c87-bec7-3c47f23c340e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Fit off
93d33325-b8da-4b8c-9061-08beb00b6989 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Commissioning
8a54a0b9-230c-433b-ab7a-c3ee2a0316cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing
fe2e52d8-e572-44a1-87d5-ae644aa8c96d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB1
92aee3cf-3aea-44fa-8616-5fc9f277a114 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB2
ce4d3cfb-0de5-4a5c-a606-8d6462f01384 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB3
0d6e8d6c-3ce9-4e4c-9d47-fdb2c4b51af2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB4
a4db87ad-ec6c-40f7-a978-bd9ee52f2da4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB5
58bfc1dc-2ce5-4bb4-a195-052bad9dcee2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 13 | Apartment 1313 | Mandatory testing | CB6
514cf01f-6be8-4eec-8883-1049fcbd38b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14
8784a4ea-e546-4ad5-8e88-09c24ac3cd22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401
01385ab1-58fe-4bd3-b4d7-243782c839b4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Leadins
dc33095f-2c79-458f-9855-fbb45d23b798 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Roughin
3f1c7d96-9bd4-4a84-8862-053846614669 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Cut out
46cb0a74-67e5-4c6a-b414-dd84dad5d3de |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Fit off
14ca84fb-7e30-4994-869c-21ffeea9e48d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Commissioning
fc02cfb4-d347-488c-b7d3-f6f1bcfc46b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing
70e0f23f-04ee-4c39-b05d-9e891917e451 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB1
c8299190-948b-4a9a-b9d0-e22dd15f175d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB2
c2543c1f-56b2-43b7-8768-e2ebb896d316 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB3
70ff32c2-5070-41ee-973b-2ec83e814d96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB4
4e8956d1-0092-47c1-8c01-b6ff2c6b1e75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB5
bfc66996-a0fd-47d0-a2d3-559c629321dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1401 | Mandatory testing | CB6
1442d0b7-d849-48bf-9296-5cd0e6b5c5ae |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402
dfa069aa-349a-4383-accc-464d9997e752 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Leadins
269e8db9-22f0-444f-b15e-5310c1aac113 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Roughin
3e29b59a-1a7e-4468-8a38-4a92443fa65b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Cut out
574810aa-de29-4e08-b003-16101fe095ce |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Fit off
b66df1ed-c0bf-4edd-8e6a-953f1f6427d2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Commissioning
85449589-c5cb-4661-88ea-2eb2f87a4b74 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing
fa6c5022-56c3-46fe-8c35-db888b2ecc0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB1
d04d31b7-b42b-466e-a7be-56d3a456dde2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB2
97a2396a-41b2-4206-9cd6-5886a3083414 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB3
0328981f-02ec-44f7-9485-b39f294ac7af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB4
ad23adc8-2b44-40d3-98b6-eb131230af6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB5
19305445-f7e2-45ca-a378-f2a6ad626d6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1402 | Mandatory testing | CB6
b654e5eb-6c21-4bde-bedf-59e841e7d743 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403
ffa113d8-eb33-40df-a55a-af8a0770190e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Leadins
bb48aee7-86fc-4c69-8a00-ee7be063c9ae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Roughin
5cafd3f9-2013-42dc-8a1b-6d1172cf7bd3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Cut out
d6bbec28-7843-477d-baff-68745d1bdd1a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Fit off
6804e7cb-3640-42ee-8c3a-1aa3170b5147 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Commissioning
5d97b4ec-271f-4dfb-90bf-ed7ff931d8e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing
08809fec-5def-4f6e-80b4-0445806db27e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB1
0d52271b-3c30-4aa6-baef-dcb4295199be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB2
69b8766b-a5df-40ac-9e81-a021097cb9e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB3
675c1287-d45c-4bb9-be02-ffd4d8415d0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB4
be55c259-7b98-4923-ba9c-6c58680074b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB5
9fe64124-6354-45d3-9064-2b8ce56d46a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1403 | Mandatory testing | CB6
e6788121-ac04-4172-ad89-5c111a28879f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404
4b00815d-16f7-4bad-a788-55b1d0bba8ca |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Leadins
43c48138-08cf-455f-bfa7-d0e7db54f7f3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Roughin
60a304a7-ed39-4e81-bff8-274e42f74f1f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Cut out
fd4cf870-66ea-4ea5-880f-e7d3a456bdec |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Fit off
558730e4-c193-4c8d-b437-706d1c23f85c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Commissioning
734c4fd9-d436-4b71-a85e-527568f30d61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing
0e6fdfd4-c890-4e7b-9ec3-a51c6b792e1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB1
ced17890-3e30-46d3-94e5-2713acf53158 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB2
3ed0130e-c2a8-48b9-98d6-89c72f40c818 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB3
2bb69be6-4c9e-4e36-8ae4-2ba5981204f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB4
e61597cc-0381-4894-9214-32115bf0a75b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB5
90bd8531-25e8-4fb9-a2f7-a3efabc40dda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1404 | Mandatory testing | CB6
bdaa8acc-92a3-44d3-9bb9-77739c79b9fa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405
0532cd21-de6b-4ee6-8e10-86d0883cbac7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Leadins
e53f2060-70ac-4644-b999-a1faff4435c5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Roughin
8938692d-fad0-4503-9ab2-154a48392023 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Cut out
16e5e5a4-7b8e-4be4-bb50-9f271244e57c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Fit off
928514d4-d02f-4125-a834-3614a7418b62 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Commissioning
b268f559-b05d-460d-a5d2-010a8ace42b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing
71d03c89-53fa-4788-a942-80b87a3b1e08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB1
b8d32140-745c-4bbe-aae4-ba5556e12d5b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB2
91eac76e-bdda-448d-aa66-eeb1a1d8431e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB3
a591fe16-616f-410f-8cc3-6f5302f4d3b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB4
2aff2698-1d85-4736-b596-e154e936bd0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB5
24ee0069-1ddd-4368-9a86-bd05bd59d6c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1405 | Mandatory testing | CB6
8af6ac04-3b56-4dc7-abd7-780a15a9ea09 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406
2cc320ee-4105-41f8-96c9-fe3f77bcf785 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Leadins
ba19a905-6857-4546-97e6-ecbb72120215 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Roughin
530209e2-2117-4998-bc48-5277d755d42e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Cut out
3619afab-3dd6-4328-8ec8-b1b6e56c2264 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Fit off
2f5d26ab-d829-49b7-ba17-d72f569cd12d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Commissioning
5206b483-f745-4f50-8832-62b61458a0a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing
d0f0d691-7eb7-45f2-b53b-d1aa57205858 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB1
aef02c4f-12fe-448d-b5c9-359f8f9a68f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB2
73d2371f-1de8-4c8a-aaf8-f0e11967f26f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB3
20d2295c-d31a-4bfe-98f9-afa6b194450a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB4
682ecc77-4875-4ca6-b533-f779fb18cd77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB5
fbdaabc5-6d84-4e54-a8d9-3a1bbe59777a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1406 | Mandatory testing | CB6
31824fdd-bdd0-44a5-81d9-49bf854e6b86 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407
bde283f5-9953-4550-a261-e2ca5d40fc5c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Leadins
b48bc5ae-0b36-457e-979d-9d3559b7d9d6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Roughin
7f7f3f1c-720f-4a31-9bf4-f472ec38ee33 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Cut out
f94822d9-2ff5-40f2-8fd2-801bf19ac842 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Fit off
b5280dc0-05af-4890-9c6d-03dcd03f0b05 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Commissioning
a9aa0a6f-360b-415d-b4ea-55b94e1346bb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing
267ef060-04d2-4ec9-841a-8712cc370a92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB1
425e000b-99be-4856-a87b-3cbcf76880ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB2
ba217d8d-36ad-4b62-975e-90331b3542c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB3
8dac57f7-a4c4-4dd7-a443-37bdef0df6ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB4
05737da3-4418-41b3-b0ce-7fb04c95461d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB5
351128d3-f8d3-478a-98b8-2156f38082a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1407 | Mandatory testing | CB6
46375ede-4247-4d33-863e-3aeef9e33c03 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408
e535a475-93f3-4a58-8a70-77042fcbbe16 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Leadins
0ba16109-843f-4f06-95af-5f0e3c0499da |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Roughin
3b5c2848-9fc4-448a-a9b1-55f92fd6ea53 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Cut out
a51e9c0b-9092-4342-9345-cf05f363a41a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Fit off
f36f4dc5-9101-48c0-a1ca-12ca9144f05d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Commissioning
e05cce02-5847-41ea-b722-b2d4b47c1493 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing
d414650a-b099-4e21-8b70-f77335367a37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB1
20f56867-ff25-4997-8836-f84b6d40dbd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB2
d89ab4cf-b0aa-4c36-ae75-1d715452c70a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB3
60214277-275d-4fb8-852f-f1a253ba1daa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB4
17401b34-36e0-4c31-9974-baea114ecf6c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB5
2539136a-407c-4f07-8952-7100c5b48c00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1408 | Mandatory testing | CB6
f22811d6-4cbf-4173-8800-f571b5c0c10d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409
ae6e4584-b1cc-479b-9090-05b60b568cb3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Leadins
c83d0a43-004a-4818-85e3-5e094a8a617c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Roughin
59ac2b12-9f2f-49c8-a862-7aac8ee5c612 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Cut out
62be3b43-7d20-4835-a7ff-c3507a18e056 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Fit off
c94e559c-dea8-41fd-b301-662cf76b540e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Commissioning
2c3e032e-c88f-42ac-9481-5d0b0af416c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing
968e40c2-6c82-4676-a162-0628cb584ea7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB1
59a5e7d9-68fb-41bf-b572-64951601989c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB2
2e0aa2c4-5f99-43ce-aaa7-a61b857c3348 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB3
0b67dfaa-f5ff-4511-af89-b3788a3dcc9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB4
166b13fd-d2ce-4b52-a2c8-a1c26b257eba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB5
0fef0c10-a4f9-47de-bf1e-ed60f7d52cdc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1409 | Mandatory testing | CB6
0ced9f5d-357a-4bde-bea5-8af36f4459b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410
535cc8a5-bafb-4fd3-9f4a-0a668f24d6d7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Leadins
fcc44b89-f663-4ea1-86d8-7f811c327285 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Roughin
d4f58a90-5d85-4020-8a9a-363bcbc7308e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Cut out
11271432-92d7-482c-97ec-b47cbc5702e1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Fit off
704a4b55-89f4-4f20-87b8-cf2669c96676 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Commissioning
9fd02e60-e58d-4687-9163-476ca10bb06c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing
6cd45245-2554-4df5-8e90-cd25451f4c87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB1
e48f162b-e8dd-411e-838e-f722f3baa9e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB2
56c74f78-c637-49b4-aa03-f8b7ee308957 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB3
cd06dbeb-ee25-47e1-8096-e6b566a50add |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB4
76d1e55e-a9b1-4fa7-95e4-e43516f8fa5c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB5
8654ef73-c388-4ed2-90de-cfe70bcf68f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1410 | Mandatory testing | CB6
ee07f364-0dbb-46dc-a396-f0018f234d5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411
ce37df5d-ba72-4343-88de-f78d7e0ad839 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Leadins
f6e7d311-a33a-4544-a3d3-94a2898cc116 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Roughin
9e7fe1e9-44a5-404f-8625-1ffc95c72dc8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Cut out
ec7d5332-30ff-4f70-9f68-245b424560c7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Fit off
3f9df84d-fadb-441e-b270-d818415b4eaa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Commissioning
72292109-f239-4dd1-9203-faafe84ea403 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing
d1efc880-dfc6-4987-8914-e8a37c0ff5c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB1
54b3e9c0-eb96-4ae8-a49e-a938ce12bef5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB2
fe53ef83-c018-43d7-95a3-9c647f644538 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB3
7cf52e1b-2214-48c7-a952-176c5e8ad6e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB4
4c14bc89-fed3-43c7-a36e-78192878d5c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB5
a2445fcc-3314-4692-92fc-a800dc7a7016 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1411 | Mandatory testing | CB6
0f958599-7803-4839-8995-8be2b2178087 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412
06afffe0-27f4-45a0-9b4c-31c32545740e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Leadins
e12954fb-b6c2-4cda-97a9-03b53f120904 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Roughin
bcfa70d0-11fa-4820-9468-6bed15e9f3b5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Cut out
ac8df8ea-25e2-4a95-8601-a1a202c9338c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Fit off
16453004-e2a2-41a6-b152-850fbf7e5d43 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Commissioning
d6907438-fbb5-4b96-92db-765f81434a6c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing
30582c73-122b-45cd-9090-79d9fe1ba246 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB1
90923e48-6dca-4214-9839-fbcb9a823892 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB2
e27b790d-0ef0-4d91-81ad-f06133994b85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB3
15632a9a-4efe-414c-a4d1-b0994fb3cdc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB4
fd12affe-e1d1-4674-ab44-4721b379bd36 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB5
0f2b7f2d-0826-4e57-b501-ba31b57a4ad5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1412 | Mandatory testing | CB6
f2817a7c-4705-4e82-a59c-dac94629e335 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413
99a4bd8e-a6e0-4cb7-ac0c-cbc8cb231552 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Leadins
d3bb0d83-5e7c-48f7-893b-197cf7113d58 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Roughin
0b957513-9bfe-497c-b80d-748c4d0da96f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Cut out
e2f94f09-7220-44c3-8ef5-6035503204bb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Fit off
765775e2-b759-43a8-856a-ff4f6db1cdec |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Commissioning
72144102-af89-45f8-bea7-f2dc2bb79e20 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing
a26abc60-1324-45ae-9dd9-5dd00e275e7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB1
6253d1d0-9638-4e6b-b077-f41e8a17686b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB2
13888b1d-de3d-4e59-90b2-580675171a9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB3
01aded23-f08d-4a60-bd8d-ba902bc7d01b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB4
e399e62e-a581-487b-ad9e-fc81fa7b084b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB5
24e2f1a6-4f80-407a-87ab-3389656e8db0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 14 | Apartment 1413 | Mandatory testing | CB6
ba883cac-dfdb-42bf-a4e5-f2cc46afd16b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15
0053d31c-fafe-48b6-acf0-8ac402d8b0f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501
a4ef3816-1770-4fc1-8b84-3bf27275e74a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Leadins
5300d582-f059-4612-ae8a-19e09ed32f68 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Roughin
57634772-6e64-4894-a3b2-012c6d670c29 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Cut out
e81f8f56-4007-4b87-8c0d-4fb69eabcf72 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Fit off
cc219130-cc7d-46f0-bc87-a3142b632f1b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Commissioning
a0a13e2f-a188-4d98-bd11-14fb9bc94c93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing
2f03c9f4-a803-4398-b565-732b0277526f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB1
bd3a4f9b-388c-4907-bcd6-082246d341a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB2
b4f50e60-f6d8-4882-9299-7daaf48f920b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB3
acedc8b8-9fb7-425a-8f14-c4bac59bad6b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB4
7809b28b-daf4-4cf6-97b9-d73d0418924b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB5
5d97f7bb-bb1b-471b-9c27-34d08e59c57b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1501 | Mandatory testing | CB6
268386ae-9618-483b-b703-7574eaf08993 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502
8c7540e6-cb46-4936-9de0-caa51ca3e6fe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Leadins
54b08af0-677d-4c03-9139-4f66c6598e44 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Roughin
f8812186-7699-4d0d-8bab-1a3ed658641f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Cut out
34855e9b-1f14-415e-a3bc-f4484e42c064 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Fit off
74661688-f7d0-4d26-bceb-324a5972bc69 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Commissioning
2b44a350-f97e-448e-8e80-7d05faba326c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing
30a99f2a-0f4c-4f0a-81e6-7e176750f280 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB1
6c4b21d2-0cb1-447d-9de6-216a1262031f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB2
b5b72f65-2604-45e4-92cf-d2247a6b8c88 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB3
2900ef18-dea2-4b5d-b6b0-2c0b83fd142c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB4
c901b325-47d8-485b-ac0b-b605cbb7ed0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB5
54c0b928-09a0-4818-bbcd-89a42259c31f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1502 | Mandatory testing | CB6
86990370-fc3b-40d0-9c2d-c2fe01c95889 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503
b4dfdf5f-4dbb-4572-b04c-c3140ce2e698 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Leadins
e0a5f49e-997a-49c5-83bb-4081c7cd62f1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Roughin
a2cfee49-008a-4385-80c8-10767dbd9cc3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Cut out
99bd60d2-7cdd-4592-8eba-afef7fd72393 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Fit off
0fead4bc-7745-4b7a-a25d-0ec09b5ac284 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Commissioning
40ca3e79-7c5e-453c-b2b4-a1c2a2297909 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing
4fbd3d89-5eaf-47f7-ad30-168edde96853 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB1
31f9b61a-e79f-4380-b46c-2a67869e0b16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB2
ac9c26d8-7804-4cae-a44f-c571d17019da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB3
bbcb592c-cb2f-4a98-8bfd-bac5260f2a02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB4
525483d5-a897-4c10-a2ea-ba6519423f6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB5
e15c91d9-6f92-4361-85df-dd22d195e304 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1503 | Mandatory testing | CB6
10137e9b-16c1-4d77-9dd3-e404e2c9de63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504
93d35196-d18f-47f3-a0fc-43e10f0ab8ce |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Leadins
7aaddc22-9470-47e5-8681-dd448065036f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Roughin
2fa5ed12-6fbb-4dfb-a4ff-8b2fcd2f9160 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Cut out
b9825ac9-423a-4785-b17d-53890f622c97 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Fit off
505e584d-b2af-4d5b-88ee-44f7a53e7914 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Commissioning
bfa7483e-7a9e-421d-a5b9-9d3a70366574 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing
fb910b67-677c-49ec-ac0c-4a5cb38d6475 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB1
045543d4-c171-46fa-85be-fe238bf80b0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB2
1e57f64e-7dd0-4983-b5c1-4ad86146bb54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB3
10f5dc73-bd45-417e-9c3a-3fd1814f5531 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB4
a7c69d46-506a-4b68-a826-3a4bc39f6e02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB5
49e79bef-a61b-49fa-8481-2c455d81c645 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1504 | Mandatory testing | CB6
f379a2f1-4ae9-4cf9-b4c7-d68f4c961c8d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505
6f3c24c7-5091-4173-914f-7029899bb658 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Leadins
775157bd-6fd8-400d-805c-29aa8c5a8052 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Roughin
07273bd8-f5dd-4de3-83ea-93af6cacc8c5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Cut out
d25540aa-0e83-4904-ab8a-39a4cf9b84ce |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Fit off
34eaf521-75cf-4fa4-a944-ab71822925db |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Commissioning
22bdf6af-aec2-430d-9c5e-a6cacae585d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing
10c6cb62-7ec4-428b-822e-0d42c377cd23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB1
050012ae-650c-4cec-8013-f8fceaf940cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB2
f0b749ca-4236-42fa-801b-4342c8b8a738 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB3
da455c76-b088-4dc8-82e7-8386a4d73ff2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB4
f6577c74-63f8-4ddc-a111-e922a27c4fe8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB5
c06db8fb-e5a9-4897-84cf-56f3c1b356a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1505 | Mandatory testing | CB6
2cd543a7-3f25-41fd-8f79-8827ea1b7af5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506
f784d853-e648-4b0a-81bd-ece7cf64041f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Leadins
1b2c0afe-ffc8-4716-bf7b-96871e16d6a2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Roughin
3d45a8e5-9f15-477e-8178-8294152029d5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Cut out
4c9a7d2e-cdbd-4280-b5ea-8b67e3e3278a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Fit off
5096cbe4-827d-4971-a943-b1fe2b382b99 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Commissioning
b0dd6841-85bb-4c02-bf8d-018764e0a135 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing
0786c9bf-369b-437d-9f8d-36cd58bca305 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB1
abdf7e75-cc6a-47dd-9919-e6839e3fd4b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB2
dff63301-2251-441d-beed-13b5e55a3db9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB3
07b9aa4e-566b-46f5-883f-04d651d9a509 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB4
7cf2a4bc-c311-4f9d-b353-98588158ec1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB5
c07f0e3b-ded4-42b7-9d9c-d642e52923a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1506 | Mandatory testing | CB6
33fe889b-51ff-42fc-bd4e-4354f1e16438 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507
ce224e6a-675b-44d5-a130-90506e762aee |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Leadins
fa2e4482-ec38-43a0-a50e-3bfcacdac6c3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Roughin
95c21fb4-7bf9-40eb-a5e3-0b7c34f32ee7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Cut out
9f681868-c57f-4fe6-9e6e-be41962cd032 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Fit off
858ca309-c44c-49ff-8e83-8615cfc89d71 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Commissioning
e2bc97ca-2234-4538-b68f-55b19b7f90e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing
9dc36956-0cf5-4a42-b022-d68f50db644e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB1
67b37f3b-3c06-4ce1-9f79-a7e648c030ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB2
42168673-b4e8-4f25-9042-cb0d16738387 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB3
c1876261-528f-48f9-bb79-9138751e8697 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB4
7058a48b-b552-46a8-a974-5901ba54e32c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB5
ee2a1167-1283-4705-874d-e44316ad52bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1507 | Mandatory testing | CB6
0093cafa-d870-456e-a94d-64ac95ff7e4d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508
5e9c6a10-8609-4d54-bbfe-4daae622d981 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Leadins
b855d520-8a47-4194-9510-911ec3451ef4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Roughin
b60bbf6f-0ba6-4124-ac58-9f053cbe8df7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Cut out
67e63987-33fc-4983-9644-0d7658ef3555 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Fit off
27d66628-07d3-492f-9444-c8d107129d17 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Commissioning
bd58b106-1588-424a-baf0-2e52ebeb2b1f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing
291a0b8e-7003-4460-816d-355f329157f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB1
f85b2a9b-e95a-47df-9e41-af48ead26f17 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB2
85ac8b8e-96fb-4df3-bb60-e02557fb790d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB3
9b696cbb-483e-4e09-973d-f0f55614c1c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB4
24fefb1d-e9c4-43f9-bca9-a5219c583ecc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB5
8abb9257-97ae-48b2-a757-b3d70464924e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1508 | Mandatory testing | CB6
f3d18b42-9ff4-4e2e-a954-74498d77d7b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509
7c7b5437-f099-4e0a-8307-b7e2d0e08092 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Leadins
15bfa6cc-6587-49a0-bfec-f585416e9e16 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Roughin
cb081ede-76ad-48e2-b538-9476b576a52b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Cut out
7f8bbcf6-e151-4b13-a717-ecbaa6d0ec7e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Fit off
76d7b4e0-c2c4-4993-9703-d2c92e4d4967 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Commissioning
d6ca2c59-b554-435a-8fd3-c7dd0beb5ffb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing
7403e5c6-dce0-4c74-83a7-4cbc5e368d6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB1
127f7995-7e3d-4a9e-b2f6-d4af1fd3b159 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB2
ac34908f-b3b0-468a-b271-ee6976899f83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB3
f9102b64-0cbd-4a0b-8ad9-b2e0691baca8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB4
b33c30ed-a998-426a-9818-e54d499b89b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB5
ec100e7b-0a95-4dcc-a85a-ac8baa91913a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1509 | Mandatory testing | CB6
d8dd5467-0163-4738-aa10-aff3a6e0a603 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510
fbd18bb1-2a33-4358-a9f9-ed1c70df89ce |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Leadins
aa7b8ed8-b5c9-4795-85bb-8def11ca1a17 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Roughin
828de2dd-ce0b-4c0f-a49a-47d3d19c2c7e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Cut out
06fcacc6-4540-4846-9668-205204dc36da |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Fit off
3b7f7321-4874-49c4-8b51-7153f96c8d99 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Commissioning
0e0d19ec-1c77-48f4-a0a3-db166b0d6cf9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing
c97fbac6-d555-4230-8925-6aed0667b6a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB1
4639acd2-ddb1-4cc5-bd98-46188da65cf2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB2
6fde8dc6-ac57-463c-b4e4-adcf51798a74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB3
9367a21f-94dc-4478-bc5d-611c781be5a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB4
b2f2e4c0-9a20-49c3-8e4e-7d6b05a1053a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB5
7b0dd653-3610-4a7a-ba43-a43308cc8cfd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1510 | Mandatory testing | CB6
26eaecde-1dba-4141-9636-b27e525fbea6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511
7d6fc310-2b68-4561-8b91-e162ab4bd5e8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Leadins
d4f09780-c894-4b92-bbdf-a807ae096c8f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Roughin
0aeed3a2-ee18-4e0b-b9aa-c84b72dca829 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Cut out
a75e03d6-97b8-4cb8-9a99-531bdd2e395b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Fit off
1f3888d4-c4bc-4e0f-9611-ddecc9e16bda |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Commissioning
e2ddba25-1119-41c5-bbb3-3a6cda96ec8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing
4077c9b3-e67d-4155-9d00-ff236f857315 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB1
e56fe12d-429f-40d7-bf87-38fde7e458ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB2
f80ea12e-af1a-4624-a1e1-3cbf69849e15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB3
69036562-cf5b-4ffb-9c39-f7acbb9a97b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB4
bfbbde10-5975-4855-b38a-51db3f3b1e87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB5
5f4e4a42-01cf-4818-96a5-eae005b6829c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1511 | Mandatory testing | CB6
e3eeb18d-d4da-4b50-aeba-17f04f4ee223 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512
44dbdff2-e79f-4a8b-b7b2-fea45673466a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Leadins
6bb5ecaf-f1b5-4cbc-9a3b-5bf343808e6e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Roughin
2fe980f9-c3dc-4d58-994e-270ad7ce0a64 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Cut out
0adbe299-cd2a-41f0-9fce-e645e3b1dc12 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Fit off
7532aacf-6777-4516-b4a8-fca367c31566 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Commissioning
b6f56c9c-f94a-4d8e-84f1-6a1ca8bc742c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing
ac9cc552-292e-4e3b-a8c5-d7f1c6f1c480 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB1
01552a62-693c-4a10-82bc-a2ecc4a0295c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB2
7e183d38-61c7-41ef-b583-3b2df7ab8569 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB3
b96214c4-07c3-42f8-bdbb-88108add14d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB4
d4196fb4-84ff-4e6e-9b58-9ee5df7a2a18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB5
f9aa840b-7cec-4ca6-99c0-85594841e825 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1512 | Mandatory testing | CB6
3b042b81-ead1-411e-a007-f8be982106f6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513
8448236e-377b-41bd-93cf-2796d02671cb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Leadins
85f3162a-e575-416d-9226-87f661fcf205 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Roughin
d87b64a6-66c3-48e3-be3e-543757fa12dc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Cut out
d0bcaf90-deac-4ef6-9055-b553b3f2f91e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Fit off
b0feb841-a795-4852-b375-d04b3583bb50 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Commissioning
f2e3e083-460e-4d4d-a7f5-62c1b3cc0805 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing
b1ec6279-8e9c-4098-a4f5-02a1cc674224 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB1
dc3f5b42-3048-42a9-b8c1-f3284953c9ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB2
cff2f146-5bab-424e-8624-1354763d673e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB3
0ad4bfee-3358-4195-8a67-775135c60aec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB4
4d01373d-b066-4717-9b4a-0bf47a0efa89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB5
7906fda2-03dc-4675-8f7d-6e0faa7338c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 15 | Apartment 1513 | Mandatory testing | CB6
56fb8cf7-8dd6-4fdc-8b75-3fb0086ee06b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16
14748353-add9-47ef-9544-25c993511807 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601
1e0c34ae-637a-43ac-a8fa-ef1e51957130 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Leadins
a6955941-f824-48a9-a117-28c7a8e1d5b1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Roughin
1fa2650c-1745-4bf8-90d5-01e79ef9ceb2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Cut out
f3fa6f73-2c4c-4378-bad2-c8e637dc3460 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Fit off
817b4afb-ea76-4d06-9281-00f8bddf0b9c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Commissioning
4aa9391b-11e9-4ae6-9b66-6e2f845f7054 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing
0f91abf1-5425-4c6e-9c7b-e043e77f729d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB1
3666bcf0-be17-40e5-92b9-55eed67467a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB2
fddd1004-c648-4385-8c9c-63595fd17254 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB3
3d15907b-ec02-43c4-8579-2cb2ee579019 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB4
48f31586-5ff3-4620-8706-40ee42a26a42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB5
82137385-e52c-4a43-a044-cc4841e3e661 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1601 | Mandatory testing | CB6
6eb73c91-9060-4905-b873-e1cbd2d72fa5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602
58fdf557-4a6c-48b6-9a38-f85fd36e73ea |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Leadins
1f7a526d-4272-4962-8085-3fd0c5bf561d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Roughin
fd595813-e7c5-408b-83d5-892ee8c5f20a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Cut out
2e86346e-2059-4718-ad46-2aabb14e6676 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Fit off
dfa4985b-f16a-440a-bb5c-d01d2b19f65f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Commissioning
e893ed9b-9407-4fa1-9009-e55ce074b7eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing
ec912f2d-b3d5-48c5-9c4f-13719169cccf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB1
e7cda926-7092-4f09-9340-b810552f9e90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB2
1686bd0c-6fa5-40bb-a5e6-b076dd8dbbb7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB3
41458af0-6baf-482e-b3a1-052cdd659363 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB4
7e55c6cf-cdd8-4ac7-8efc-3b53081ec554 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB5
c21a9b3c-0361-4c2d-b995-ab2639b05cc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1602 | Mandatory testing | CB6
a5735809-e8c2-4cd6-95d9-5bec52ee4648 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603
a1cbdc0a-99fd-47c4-bafd-5c79b188dd01 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Leadins
8917f210-26a4-4f2b-83aa-a4869d38454c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Roughin
2444c4d2-e7a3-4fb1-bb6a-926a035179f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Cut out
0cd7f04e-79d2-4d16-8064-04b44be78c40 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Fit off
1e6e304b-d460-45be-bdde-a9d7754eecad |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Commissioning
997a2a53-2ffb-4876-aa37-cb4613e57d19 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing
f0c8bcb3-7a5f-4575-8974-0b3f8d21f54a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB1
4c4c097c-488d-4efc-82e8-ba4543cfe926 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB2
4fbea661-78c3-4dc4-98ab-ad078ac24ca0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB3
25d9feab-68f0-4aac-8f56-35b5bd4f43b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB4
386a88a8-7b63-4306-90f9-8bb54e0b39de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB5
56dde5f8-8873-465e-8a6d-7ed17912d765 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1603 | Mandatory testing | CB6
376fa33e-ab73-4c8a-b381-2615cda3e0ab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604
8392ef0a-4a58-4949-bee4-146c65b68224 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Leadins
96e57506-0eaa-4ed9-829d-71969f8aedba |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Roughin
bb38dd05-916b-4069-884b-d3ad109c0afc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Cut out
b905b319-20b9-43b4-894b-33ed827087d1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Fit off
ea558618-44b0-43b2-adab-7fba517a43b2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Commissioning
d263dce8-5d55-4b11-8dcf-a470d7401e2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing
7749ac20-1670-4623-88d4-1089277d0e59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB1
009ee935-1aea-463b-81f2-314dc0985fa7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB2
4093ba72-3d33-43c1-ab18-0cd41d5ec46e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB3
897eda28-33fa-4cd3-9a72-fc0f846cb881 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB4
d6d7e9a3-ef02-4ad4-b464-26e1b15a1ceb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB5
80255007-f532-48ed-af80-c3e441a93eae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1604 | Mandatory testing | CB6
764d36a7-bba9-4d8d-a9ee-ce36d6343b0f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605
88a60a7a-adfd-4ecc-a50f-71e56707de51 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Leadins
fe623dcd-0023-444c-a5fe-03169a8875be |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Roughin
7431bed0-bf7f-43db-b3d1-d567e5371939 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Cut out
174f58fb-d9da-4425-a32a-139c991d5562 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Fit off
7c1a1184-fb2d-4574-ac0b-65883825409c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Commissioning
133b3495-ebe6-4da4-926e-977115cd54f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing
210e7163-e871-4a60-8281-819c61834e6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB1
08fed6e8-3a53-4517-81bc-72683f8a911d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB2
67070a40-5315-463e-b777-c9ae3427b2db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB3
a5e8a465-4460-4ee5-90e4-a4fca5af3925 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB4
531c1339-2e4a-47f3-a96c-82bc9b7fed55 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB5
fa5cf536-9c13-46a3-be8a-1decd778052e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1605 | Mandatory testing | CB6
071fd4c9-0d65-4ed3-9520-14e805f58ba4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606
a3f42715-42b6-46a2-8b38-e88634cc6f63 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Leadins
2aaf8f4f-aa04-496c-ad87-3bf1d41fa3eb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Roughin
e503c19e-0bcf-48cc-8e79-65f859b0cf67 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Cut out
ecf4a7f3-ee8c-4943-8f66-5205702ef94c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Fit off
28a5ecb0-fada-4341-968a-426a97126552 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Commissioning
5b163efb-4dd9-4de1-a430-c6b60cb701d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing
d0fd6fa0-cfe0-4def-8b9d-cc72d9d8d0c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB1
55161b84-4479-4d60-844d-8ff5f29f579c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB2
a017a366-b4be-4b65-98fd-9fbd5bd737f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB3
77217263-3a05-40c5-93e2-d537a95ce52e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB4
278a0cdf-b256-4de6-9f49-a0d494ca5e4b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB5
c080dac4-8e64-4d00-b1ce-f879c412dad4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1606 | Mandatory testing | CB6
6cea521b-7b10-4e21-b5e4-4ba8fda89943 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607
54158cfb-2e3b-4a83-a21b-f6a17d7ad25e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Leadins
2e24d5dd-66f0-4406-8dc2-7cd0c69c9820 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Roughin
43a34bb5-8817-4de9-b3ba-344c0a680d47 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Cut out
6abc1d67-97f2-45c3-a94c-75860750f4ee |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Fit off
755c2f86-47fc-4f05-a900-662ee03eeb4b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Commissioning
0a7ed963-a21a-4e3e-9d4d-0d8f1637efd2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing
b9d45f49-56cf-419d-a4f4-fd68de0237ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB1
9c805fa5-28cc-43fb-9dbc-92073356b5e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB2
beb2ea63-8d67-4eec-81cd-d80c147fd400 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB3
a37d1df7-8fe4-4241-b00e-6ce620e95a20 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB4
6a1486cf-dd73-4d50-b90b-c692424923b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB5
54bbda6a-36e0-4132-8338-483425ef421f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1607 | Mandatory testing | CB6
a9b0fb70-d7a6-4110-83f1-960c29b4a7f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608
40ab3649-ac7a-49cb-8484-290189770e5f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Leadins
5659f636-a310-4e00-873f-c5ee5c227f5d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Roughin
317472a4-2af1-41f4-ba40-66c811a9d4d8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Cut out
1c9c291e-06a6-4177-8c72-0ccb6eb9900f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Fit off
71c591e8-b6e7-4bfe-9fa4-22899e48c33d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Commissioning
a5280e1f-d28c-47f3-b1eb-a38348f85854 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing
9074c149-1dc9-4e39-a52f-0b488db584fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB1
b302c220-e20c-4070-96ea-4d21f1e2b698 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB2
3ceaaaa3-ae91-4053-af3d-b3e0b5efc351 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB3
e02e5520-d1e6-4799-b358-7da36241bf57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB4
c5358abc-b0fc-41d0-ad6c-5e1274d5f0c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB5
083a3f54-23ff-4476-b28b-e176e7f6f115 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1608 | Mandatory testing | CB6
92e251f0-85d7-43ae-8776-b3cec4b3eb97 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609
7d9921af-faa6-4346-b9cf-ac67ce379ea1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Leadins
13ee6fa4-2e95-4187-990e-dfe28bcf41b3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Roughin
94c41e65-e2df-4f1c-bf03-00c3bfa05e6f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Cut out
eac7cf43-ab51-458b-bcbd-4ca8d21e2045 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Fit off
f59cc670-433f-4095-96d8-ef8edcbee99b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Commissioning
ce17dea1-662c-41fe-9f6d-508cc600d8d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing
0fda0188-6bf0-4f78-8325-83516e68183f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB1
a44ce08a-7760-4afe-9cca-3df2e5b1f294 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB2
f8841bc0-b3a2-40ae-aaef-1e52f67a3e73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB3
7ec4d435-bc20-4f46-8ce5-087d527d1654 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB4
eb8ab008-dc8b-408c-bf5a-5c61063a772c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB5
31c37251-efcf-4f56-ab24-b6f28f415af4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1609 | Mandatory testing | CB6
42e470e7-0558-47b2-b3ae-092487152d80 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610
c545a148-2080-4c33-a4dd-ff2216248882 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Leadins
2f95012d-160c-4c11-9827-19baf099a60a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Roughin
ebc2b83e-69bd-41e5-b7b1-568d286d7663 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Cut out
d42f3cc6-512b-406f-b196-4776c2887c5f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Fit off
461dbd67-3be8-4898-99c5-c0895d68ea69 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Commissioning
a6b4dd5a-334b-43b0-8643-a5f981bc8ecd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing
4c59ca13-7ca5-4a5a-99e3-54e8ec4bcb4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB1
d2ae5459-bdc9-4ec1-8559-a28688130ac3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB2
10cdf725-97e1-41be-be7c-88971c74b18b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB3
a6175dd3-ea73-47de-aa51-85364f3bc73f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB4
c8340a2f-9f73-4963-aad9-9d01f0144ade |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB5
9eb74432-13ab-433d-8a8f-2ab84cf273d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1610 | Mandatory testing | CB6
530b078b-69fe-4020-8683-300d1562e177 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611
a0f0d85e-fcc6-4860-81f4-b7385180ae58 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Leadins
674c9db0-ee6f-4051-b16a-b4787c200b69 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Roughin
307e2e39-24a4-4364-8a8f-955adcdd2602 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Cut out
03c56507-91d3-4a6e-8cc5-bed5bb3223af |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Fit off
262c5be5-9187-420a-bdfc-c4785593bcab |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Commissioning
2df0c7b2-f6d8-4b51-a712-3e5b94f4f4cc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing
75dc6759-e807-42ee-a09e-a117b67d5744 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB1
c585ecd3-64aa-4289-8d9e-bd96716b9419 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB2
4569b78d-fbd7-4ef2-bb0c-a330cc3ee3d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB3
c102bdca-a976-4e58-92f3-189df42eb1cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB4
0fee8a0a-302a-4594-bbde-9bb19ea655c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB5
ff94d702-192f-4faa-8108-5433789461a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1611 | Mandatory testing | CB6
526d1139-854d-4bf3-9e44-cdc89e9be21d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612
9d9d6c93-29f9-422f-ae5d-a1cd4017f06b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Leadins
97edebe3-41d7-4b99-acd1-6b9ededbc11a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Roughin
a8dff3ba-ae1c-4075-96e3-33ddb7e1c6d0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Cut out
96987594-72b7-4286-9cb8-84d07cbf55c9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Fit off
e23190aa-97fb-476d-a875-e1d6ad3f840b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Commissioning
279a4f7b-f894-4e37-bd2a-32d430afd25b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing
c2a2c18d-1f46-4dcc-8ac9-9d7029e400ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB1
a8e71bf2-eed8-44fc-8931-7ccdca180b66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB2
2e49d506-5601-4725-a0e3-879fbac8158a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB3
94df6e78-2378-49c4-b0a1-44e5179cc346 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB4
2a6c03c9-2560-4c93-adcd-50554d204594 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB5
bc3566bd-6d8c-440a-b610-0fa040336436 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1612 | Mandatory testing | CB6
9da984ea-7ab0-45f9-a04a-8c5c82b4da82 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613
d1a3ecda-06e2-4825-b84b-4eebb1ebb484 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Leadins
75f28fde-6762-413f-8af1-ff6ee795b644 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Roughin
32de6652-c665-49bc-ad13-2124af94e9e9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Cut out
28b001f5-68df-4c74-a88a-06fb0db34c86 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Fit off
a5123e98-5c8d-45b3-a353-2f146739752e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Commissioning
2d4c87f1-e8d2-4c4f-b441-37e5f5efa723 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing
883195c2-4341-4d4b-a7eb-76a7e27a1ecf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB1
07ace791-0f54-4f49-9751-123279ef17cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB2
a99bf0aa-9a2e-4e1f-9b43-d6fef1340e63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB3
8e528a65-e5bf-4939-9b52-3892429ba196 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB4
1db10b06-fb5f-4434-a71b-75ecde85c9c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB5
39e83f53-304a-4be4-ac2e-2f472bcdef09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 16 | Apartment 1613 | Mandatory testing | CB6
950bccb9-faac-4e76-812b-2640995cb9a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17
698d4c25-24c5-482f-b82d-8c99d37a7db6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701
6a790a38-ef52-4aa5-a046-f5dc47cb70fb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Leadins
16500584-04db-4962-b65c-7c5402037364 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Roughin
a31eb415-fa69-4185-9a79-97c7d3d0e17a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Cut out
7d3802ca-6796-447b-b991-67e8821e44a6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Fit off
63d23b33-dcfa-4133-a77a-803f926bbb97 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Commissioning
c7440a5a-5224-4b39-948c-66835987b4be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing
2aaf484f-5c6b-4e28-811a-ea2c5f5d7f06 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB1
20a445b6-c8c8-4a23-908f-dc1c50ef3684 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB2
d9f62602-09cf-4177-ac72-2f109d79a338 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB3
ca1a80bd-2e34-4d4f-b698-db5ca5b00288 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB4
ca9f6b2a-d4de-4193-b782-ae7775a40f4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB5
b4fab763-51fc-4d24-a622-dfc5bf65b1bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1701 | Mandatory testing | CB6
dcd25012-6024-4df4-96cd-ce973fc77b50 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702
1bdc6e55-ef66-4799-812e-9a628a70d33e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Leadins
30936056-48c3-4cec-9c9d-4ea9b109b3ec |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Roughin
ffe0704f-64fd-4e50-8f02-1fd6c7e4a6ad |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Cut out
c6be674d-1782-4340-9e66-2f3685af22a8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Fit off
e2a03767-2300-4165-9ec1-1f9b4ed84ffc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Commissioning
42ef4378-a20b-4a7c-a2f7-f76bf120de46 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing
c4988cc5-c6c0-4fef-95e7-4c377a384862 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB1
85aaf380-069a-475d-bdfc-9784151f9fb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB2
63fcb205-b30f-4361-b29b-08c20ee4a175 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB3
189579ca-2c5c-4b3e-b7df-621b5cb7921f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB4
4ee362ae-b4bc-43c0-b1ce-3b34e0aeac2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB5
6cd32ab6-4a4f-479e-9bf5-767ac8a52649 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1702 | Mandatory testing | CB6
5f1112c5-550a-4596-8bb0-4ae178ff82ba |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703
17ee5157-4093-4772-834a-900e4b6669d6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Leadins
c0aa6dbd-43fd-490c-af59-bdda433009be |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Roughin
2ca0f2ec-624f-4421-84d4-42f5eed88e14 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Cut out
a88be4b7-0172-4925-9776-6d63610793a3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Fit off
1fff6f30-1820-4430-8f95-8ef2a8981761 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Commissioning
5c2ee967-1555-4fcb-94bb-642c6c18f27d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing
ddd8fd2e-097f-4e92-ba97-09f37f5e3cce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB1
5ae32ee3-9de0-49f6-911c-e64c67d25097 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB2
3afbcb11-81d8-4ed2-9be2-e3ab80d0aa0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB3
9a00a2d2-cb76-48e7-8d7d-f1c6b8f9b6d4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB4
71c30224-6e07-4fcd-8be4-514ca2c5c0ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB5
67c72c89-66a2-4ca6-a3a9-a58a5fb35828 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1703 | Mandatory testing | CB6
2da56483-8d90-4ace-b601-3e15da4576c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704
391fdcd6-bc93-458b-8359-b1744932299f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Leadins
c267a84e-322a-4ecd-be25-54081b71a34d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Roughin
5b5b02e3-0fe6-4b1c-af02-b1dfd4b8483b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Cut out
dbb88cdc-9fb4-4d20-88d9-f9e944607ba7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Fit off
22adb744-d508-4b60-881d-073f4ce45591 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Commissioning
dc494986-5c0f-4ebf-b5bb-77fcdd2188aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing
2b4b5845-9058-489e-a5b9-cd3d5e3a4371 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB1
cd73cbf2-4490-4711-8a8c-87e32641a64a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB2
4dd827e1-aca9-454a-b197-3dc91e1e6b71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB3
0cf321ea-1e45-4034-889e-411056fd8863 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB4
e85182c6-4137-4019-9f1e-a9452ea66dcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB5
9931dbf9-41a9-4d7e-91ad-5706b0da017f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1704 | Mandatory testing | CB6
534d2776-1161-4502-aaf0-41d3734ee02e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705
2bbaf40a-3e26-4ae4-b111-59d2662cf8ec |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Leadins
fb625f10-eace-4eea-9ca4-b76a2d742f8d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Roughin
981b7020-0819-4320-a6c7-cc92fef72418 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Cut out
86746148-0dd7-402e-b151-47b041f31ea7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Fit off
b4d6c7e0-8456-4bc3-96c8-f4ebd7296b8a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Commissioning
c79ac414-ff71-4734-95a9-363725f5ea32 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing
7c9adb0d-4134-4d00-93fa-3e7deb2abf40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB1
8ed6add2-fddb-4ab2-9d0d-754cb09683b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB2
c1adf2ef-565f-4a63-9565-15cf5fe89dac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB3
adccca39-5247-4af4-9d4a-e9836ce108ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB4
1e6e1fb7-6379-4542-9780-c88eb1532ac2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB5
ff601dd3-59de-460a-a847-b68d7a358f6b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1705 | Mandatory testing | CB6
53a11eb5-106e-4d18-b23d-a243fafd3fd8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706
60e3513b-a42c-4238-8a01-c67eb1dcd67a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Leadins
0c4d8c94-1361-40f8-bfe9-7121eb67fe2d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Roughin
d9f35d95-16a3-418e-984a-23bc57698409 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Cut out
1f9dce45-04be-4e2b-a7d3-f2f29f18fa94 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Fit off
9eb22c24-0c84-44db-b398-fc223afc56b4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Commissioning
d943b13b-30c1-43a5-8b77-be9df70d4ffb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing
c7e1259e-60d2-4eee-8c88-e066d831fad9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB1
ec691bbb-d62e-4f9b-a9f5-caa0346ce250 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB2
807f215e-7a50-4347-a505-7352d17249d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB3
25acc80f-acdf-43d0-a124-78418ae2f877 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB4
e6dbea26-593c-432a-a751-899a99589789 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB5
873c05a9-8f12-4faf-9de3-ad44c73bf610 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1706 | Mandatory testing | CB6
3b769859-6af4-4cf0-95ae-f7cbb0caed4d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707
e04a51ee-217b-4cdb-b2fb-b01d9bc1b549 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Leadins
7c321a08-e1d3-4836-be2f-60659b84b26b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Roughin
4062d6b5-21a6-4a38-a94a-8ec44677339f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Cut out
cc7454f2-efec-44c0-a962-6ac59f4f12d6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Fit off
1328f81f-f65d-4f64-af42-52e4e2e0130b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Commissioning
19252414-f925-4ca9-a0be-0058a64faf69 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing
4822a8dc-7cfd-4fd0-b86d-7c99e48fb6be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB1
a060c7fc-6048-40fd-87db-e883ab8b3248 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB2
fe79d890-7f88-4f59-833e-093a5a0dfb1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB3
04750cc6-441c-408e-8418-f0ff905c9139 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB4
155f15e8-cfbd-4ba2-911b-e3dfe22fb3cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB5
b9f0f2de-a8d9-4de6-8be7-ceacea6477bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1707 | Mandatory testing | CB6
ade0a76f-e152-4863-9820-33fdf40de9ed |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708
200d2a9b-45e3-4ab1-9291-a784e9c3fc5c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Leadins
f56f9196-89b3-4bab-a583-a1cfcf57f4c8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Roughin
5ac2d6d4-1409-4d3f-a26a-ae248c9f073b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Cut out
2f0e601e-c182-49e9-8731-608ebf4b52da |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Fit off
b795f3cd-26d5-4e0f-b941-2cb4212f8432 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Commissioning
afeafd0c-3c6e-438a-8b4f-3d5beb59e966 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing
e4aeb9f8-4a46-4590-86a9-3fc898b226e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB1
df17fdf6-aa67-46a2-8467-91363b1d5fb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB2
225451a3-86c3-4670-91b4-1a17c15baa4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB3
cb21d34e-d331-4048-960f-8e452d825801 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB4
f2da5e3c-1bf9-4baf-81a7-9a921cbd81f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB5
d5570734-c6f0-4596-b1af-6030a4c513ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1708 | Mandatory testing | CB6
cc865756-c2f9-4852-ab97-5955a01545c7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709
775ee0b8-60f8-46fb-8def-9783f739b412 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Leadins
51a6fb79-2331-4575-8239-fd38489e144e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Roughin
8178e1e4-0a17-4018-8803-8d676dc9e9f5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Cut out
13c9dee4-16de-4639-b1e0-4f36c5515331 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Fit off
e970a3f4-b41a-4a55-9b22-0952d6d109ea |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Commissioning
501ca6cd-054b-404d-a561-baa04c2e492b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing
e0400355-907e-4c2f-a62f-a8f4f4058d5b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB1
f31a1159-4322-4edf-b95d-0044e012c9e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB2
2b023509-874a-4514-8efb-4a9a097f88f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB3
3c95f656-84b0-48fe-ba6d-09fb040bb040 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB4
6f093dee-1d6b-4dff-9b4c-0dfd92b70d3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB5
2f734d47-b685-498b-9944-3e40a9f69e27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1709 | Mandatory testing | CB6
3f0b2be1-0bbd-4cbc-998b-6e572e65283d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710
670b3012-c99a-4271-bb76-4b424a3e86fb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Leadins
c195d9e4-4764-490f-a885-21a6087d3a48 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Roughin
afc5f56c-8bb1-431f-929f-2bf4027eb842 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Cut out
7b80f59f-0a8e-45d9-8c60-e8f0eb8ed691 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Fit off
7c73c081-71b3-4d4b-b120-eaa33b51a8f4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Commissioning
399d3d83-7dca-4b38-919f-7ad90bbd92cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing
a44d44c2-9d4a-484d-a792-5f0334018a62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB1
0120d3cb-dda2-4f87-af76-1dc4101c79a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB2
25866fdb-9ebe-48c5-92fb-854e77cf1f9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB3
2a228a8d-4199-416b-8dd7-f64f76f67b5f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB4
61a42823-7fe5-4fa1-a789-fbc3d63bf2f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB5
dabf2774-2805-4861-905a-b1b5b571647d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1710 | Mandatory testing | CB6
6a6d2853-5016-4580-ad64-4a150102142b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711
20136148-df8a-47a3-a5d1-481b9d48e32d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Leadins
a1e50bd3-10e0-4da1-aac0-f2347f14c872 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Roughin
2e27f898-6a63-4dd0-aa18-8b9d23667228 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Cut out
1a0dfed7-d880-4005-95b7-00eb818f69bd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Fit off
85917af1-ec1a-4cf9-91cd-d8959dfc4a82 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Commissioning
cb302990-8875-427d-beb0-92a3236fc342 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing
cd0d63fc-f0be-418b-8300-43d068415351 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB1
8dfcd62f-6a21-4396-a5e4-ec30f71dc2f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB2
bd231ef3-abf4-4724-9d85-bcfc3a4e46b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB3
cac31e04-63c3-42af-b507-bcf008987323 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB4
0e6a89d9-264d-452c-8eb3-2ad75b521207 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB5
1d26bb1c-7efa-4812-94ae-3149db9bff1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1711 | Mandatory testing | CB6
1c3b574e-efe7-4c41-b1aa-9814602c29b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712
a904f8ae-5fb0-4f23-869b-becf6573318e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Leadins
f9e0cd23-ee82-478f-87f9-4f7300b82e2f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Roughin
22bd901e-10ed-49ea-ab71-ebf9b81f62a5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Cut out
20334b9a-e50b-4ec1-94b5-877ea5601cf0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Fit off
46a93330-16a9-4b58-97de-f483ddb07ae4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Commissioning
28b1f984-97cc-4285-9233-fbe9dc58c855 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing
f6348ebf-32b0-4d5a-a586-6192dbe86704 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB1
46f08789-fabd-4d96-a76a-1e58616e7e0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB2
7af2dd02-fdeb-469e-a29f-261a13eb264d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB3
f5003fae-b196-4307-993d-7c8bb382375f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB4
36536766-7fea-4280-9faf-fa83fbf96e9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB5
ff578fdb-513a-4953-bbc8-1384b3f9eb2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1712 | Mandatory testing | CB6
15f20c03-6b2e-4e56-8f37-e6bb87b647c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713
bc7736d2-c045-4430-b92f-1f5905fcb9dc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Leadins
b6a0c578-a924-47f1-ba3b-37887789833e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Roughin
f5d8a151-f5f8-4f6c-9e46-66981f80d061 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Cut out
ea76d085-bbd7-4560-9d48-bfb77fb22900 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Fit off
9c05e684-815c-4961-9f1c-ed8d4fe31e6f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Commissioning
1d2467b5-7b17-4d26-912c-812427ee170c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing
fdc20afd-3528-4df1-81f5-c6ce9e42ad41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB1
5fbd5013-f257-44f9-a2c3-aa218cfeed1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB2
b0966617-1ff0-47a3-b962-8c1775d82e09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB3
e47efcb6-1bac-482b-b284-0566d3e87958 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB4
869ad522-f15b-438e-96a0-ad2d55dd0083 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB5
86509c4f-8a6b-4f33-8613-6e67d7ea2f82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 17 | Apartment 1713 | Mandatory testing | CB6
f9f9c46b-12e1-4acd-870e-ffda9412656b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18
0e4ca869-eb12-4c70-9998-50bb3a374636 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801
724573be-63d7-41de-a2f7-692a85c29e7a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Leadins
1b6107f9-a545-45a5-9fa7-ede2d394becf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Roughin
739a0ad8-a84d-4311-b74a-2435fdab6d1d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Cut out
d4dff57b-4c37-421a-9f85-1c02e5eddaa0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Fit off
141bcd3d-46c9-425d-a89a-bf35a2d24e3a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Commissioning
ce3d59b3-dd2d-47db-886f-d3b90fcc58c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing
f07a1f5c-5a7b-4503-8921-588f7348d061 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB1
3bb49910-9f58-4a88-ba49-b1724a14dde6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB2
edc90d56-b221-463b-8b44-4fdcd4722730 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB3
aa68356d-df21-4f62-a06b-7fd639be24eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB4
4c82d5ff-3853-4af7-9a70-06e05db8e236 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB5
dea02be5-63a2-41b1-94bc-260ccc4bdbc9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1801 | Mandatory testing | CB6
f9eb4304-40af-4c76-a415-3bb22bf7e9f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802
5c88fc4a-388c-4ee7-8f67-5142f8d95b8c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Leadins
a73d7490-195d-465f-8e96-bd1bd32039c8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Roughin
0e6fbb1e-1a65-45f1-860c-d38bf9ef02e3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Cut out
ae8e4c2e-f0fb-43de-8541-dfb9aaecb2f7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Fit off
a17ff9ee-9df9-4a39-a174-a2925af7b293 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Commissioning
d1603a3a-bf34-4b9f-a667-3768696f36a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing
6c963d33-8787-457c-966e-e3dc4948547a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB1
8fbaa2ec-81de-49da-b8d0-248b556f5ed5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB2
d2c31e32-3d6c-41f0-a80b-b8453ec0fbe9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB3
cfba2578-903b-4057-a253-c4802bd87242 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB4
3b8d7b4b-97f9-455d-9718-24d41920d368 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB5
71fb7dd2-0098-4971-a0db-b0ddd2115b85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1802 | Mandatory testing | CB6
81fdba8d-d45e-458f-b315-32a5ea22570d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803
7b46dd92-a687-4a38-b825-d39a77b2b0a4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Leadins
6652a671-1894-456b-8d92-440c43d877f4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Roughin
1e518516-cdc2-44c9-9a1d-872eff40831d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Cut out
e2138133-f7b6-4427-b017-ab2b7e684089 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Fit off
15f13e41-b30c-4196-9230-2d769a0cbdc0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Commissioning
20688f41-a9ec-423a-bac4-f5ba2a9f7c6f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing
3cb3f443-126c-4440-b120-0b7c41de3369 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB1
4689866d-fa3f-4074-86b3-6d21ad76a2ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB2
fa7582b9-abd1-4ab3-9a4a-ed31ea38afb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB3
6e95dbec-7a56-4df0-ae8f-672215091354 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB4
a672cead-a028-4f99-ad8d-9fda345e67cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB5
a2d4f073-8c23-4ff0-b532-938a91b51a11 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1803 | Mandatory testing | CB6
bc3e63a0-a118-49f3-ad4f-5712a653aed3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804
6e23100f-41ee-4268-be96-62a390d1a889 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Leadins
a4864014-6aed-4391-bee8-3107b764c273 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Roughin
7fc82b24-b86b-455e-bffc-315c17e3d5d0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Cut out
76e32284-d5a2-4c4b-8641-01b0857cd234 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Fit off
46763e38-22e8-46a1-965b-83bb251afc4e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Commissioning
5aaa5210-88d9-4124-b0ae-98c152e380b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing
34e820a3-0c45-4e80-866f-a39c02626cc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB1
f3c84b9c-39c4-4778-9971-5cb7e735cb93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB2
62fd8bda-5626-43f2-abed-7cdc41569b7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB3
12008af8-9c1e-4837-a4fb-19bc4de531d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB4
b4cfad35-fbc6-4f01-85e7-be3a5f664d24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB5
9823822e-a1dd-4bdf-b0ef-c17169006df7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1804 | Mandatory testing | CB6
c33c2aef-dcc8-467a-a7db-9dcef139e6dd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805
7a9389b7-6421-4efb-88cc-559908dfa3b2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Leadins
bfd4eee4-53a4-4542-b323-8c212a8efe64 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Roughin
650939fc-4246-4b69-8619-ac3374195512 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Cut out
0ac457ae-8b8e-472a-aa0f-41b33eb4fac1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Fit off
c64854d5-0308-4ba1-b155-2553f4a12474 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Commissioning
f2759883-595f-419e-94cd-2538050ac196 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing
1b9a726d-a144-4d22-a145-b7e7dc88045f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB1
db3cb794-ba5b-4ff7-acb6-6a01de542678 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB2
4e9cb6be-0634-4c93-989c-97803ce14b62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB3
df87cdbb-cfd2-4bb8-b1d0-64f936bf1ba9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB4
e7c30764-77a1-44f9-89e3-474a490f2603 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB5
e01ecc7b-6ff6-4c11-8b6d-df164bf5bb67 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1805 | Mandatory testing | CB6
531b37d7-7662-428e-97b5-c7058da455fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806
26b76b9b-8433-4416-b3e6-e0523c178074 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Leadins
fa181894-81d5-4c76-841b-2087c2645c1c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Roughin
80ea59ae-846a-4cf5-bbda-3d89827f02cc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Cut out
d7328e2c-3e30-419e-9ef0-9314438af306 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Fit off
6f0eff9f-d96b-40db-8396-9b849368ef59 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Commissioning
1e789981-8b2c-4b5f-be74-5605a4024a04 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing
07db8765-7ebf-49be-b7e6-60d87f81b4b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB1
2ff44b6a-0032-4bc6-9132-5ec16c68b450 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB2
642b102a-3e9b-4c5a-b8f6-3d35c189ddb1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB3
36fd1ed4-5da7-4259-b548-d46a7e977b9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB4
c4d162b0-8293-4cd4-8c14-b58bc62b44a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB5
b3e71d1a-cdca-4562-a17a-178825fe28c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1806 | Mandatory testing | CB6
2b5ad7e6-7337-456f-8f43-55d70f37b286 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807
2763fb29-3c13-49d0-bfb1-2e24b3c1241b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Leadins
51d36ccf-8bc9-4ed6-8a23-1399b8014431 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Roughin
223916f7-1929-4e27-89c1-619fd0c6229c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Cut out
bfe3be0c-077b-44d4-bb8d-236548a991ef |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Fit off
a4abc91e-2f03-4138-91f9-082d3b81513f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Commissioning
3c8f4f7d-8da5-4623-8684-63b95767e9bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing
5d3ca0c5-7b3f-411c-860e-fa27c907d837 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB1
90ffa0dd-eb4d-4ca6-ae72-f87879d4e60b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB2
f9007ce5-6e01-4d55-b2f1-ad064f5901f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB3
126964a6-09e7-49e0-b3af-f617affe6880 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB4
b0c91912-039f-4c50-9d38-54ca736a541f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB5
0752490e-cad3-455a-9ff2-1bc27c149a14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1807 | Mandatory testing | CB6
cd975a92-5453-451f-910a-8c2b826aa5dd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808
9aa5511e-9848-447e-8287-faef286421a3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Leadins
0dddbe79-9faf-4d59-b165-b9579c530970 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Roughin
e55571c5-6784-4677-9969-1e00cfb2a806 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Cut out
b7afaf0b-f114-4e3e-99fd-e549e39b55cd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Fit off
7dcdfbdd-20f6-4088-bfbc-d3791bd6cc9b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Commissioning
a607a549-6d1a-46bf-95d0-93ed5b4e8988 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing
1eb3f0dd-90f9-49b8-a955-4a6ac8fdf8f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB1
3c0e3f59-a798-4767-b43a-788d27831e9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB2
7ee41d5d-a544-4b8c-9a0a-383f62e4976c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB3
e89ba3dd-eebc-42e0-a593-47fee32b0324 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB4
65d47a40-d311-48c3-8003-7fb9fbcb9153 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB5
000c69ae-ed90-4a60-acec-5344075a9a79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1808 | Mandatory testing | CB6
3ca3d5e6-16e5-4c91-9d71-b218b7a47e06 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809
c979ad54-9334-4e56-89ed-0b62be0cd86c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Leadins
93dda3d4-65ba-4784-afa1-499bb4bba57a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Roughin
3d99ccc9-c1e7-4cc5-97d9-50cbb9258c61 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Cut out
68599209-2c13-4cdf-ab3e-76f53332c34a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Fit off
27ed6782-572a-43cc-9713-05e005ab5444 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Commissioning
ddc6c9e8-abd4-4fa3-87ad-0988a5358cf2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing
2cff1ebf-876e-4969-84be-2f23cd500ef6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB1
0320a016-40dc-451a-b02b-92a9efd44844 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB2
9c01f219-5201-4744-acf9-c85bdbf75221 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB3
bc6f63e3-4978-4aac-92f9-8dca628c204f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB4
5e152044-4ea1-479f-8e14-412602891064 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB5
bc19c4dc-1d58-4b4b-8add-a03ca3e60f28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1809 | Mandatory testing | CB6
ae978a82-6077-48e6-ac26-1bcaf37213b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810
ea9253f9-e0d6-44f2-925a-cc041b451533 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Leadins
dd0e3123-a32d-47cb-80d9-aae6c1f94549 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Roughin
48e74d68-7e00-422d-b4ed-8713a664b72b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Cut out
eefca956-589a-4005-8479-4f5b73247daa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Fit off
d8484380-cbb1-48d9-8060-f53e4583752e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Commissioning
8af4afd3-b6a0-4619-92d5-dcfe01db3d78 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing
ec4b7804-c4f7-4449-a2eb-b7f1d573773e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB1
57229f41-97c7-4861-b3c9-0c719ffc52ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB2
e49167be-d477-49aa-84a5-1e8d0bbb7530 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB3
f62da5d2-3349-433a-a979-29342d49b1dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB4
3918d411-78a4-49cd-8514-6073dee03c27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB5
155d03b6-9a1e-467b-b43a-d044352fef8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1810 | Mandatory testing | CB6
6a5ef37e-3b7a-48a1-a782-414c9449d099 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811
4a2f2ef9-7e3c-407b-b42f-1d06abfad64f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Leadins
b8761688-7423-42ca-b455-6ee2d3c6cfac |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Roughin
6f677bc9-f4dc-4ac5-b410-3ab78390c915 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Cut out
4074b6dd-5edc-4b85-91dd-1cfe2f2afda4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Fit off
718a71a5-c281-4edd-b4f1-837bb859055c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Commissioning
1951d8f1-b54b-4c1f-aa0b-05efb6815384 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing
2c292eba-1106-4f55-9d88-2d31af233f9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB1
087e7db1-9518-444b-964d-18f701ed7e5d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB2
9475f25e-f794-44e0-aeaa-b901f6569560 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB3
40d5d4e6-c35e-486c-b2ca-976a2f8ca3f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB4
4715264f-313b-473d-b191-96af9c16882f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB5
09860e48-5aa5-4323-b6b5-1a0ce8b4ebc8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1811 | Mandatory testing | CB6
c3195572-b445-4b66-9232-8bfa2c60797b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812
4009d059-9864-46cc-84e1-0e8e52416a07 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Leadins
4458f327-41fa-4e9f-a66b-0e731c73c2c6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Roughin
61a169fb-1d20-4531-92c0-73bc66905fc2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Cut out
a3c63504-86a9-443a-b796-9038ee8128aa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Fit off
01f6bfc3-7b79-423e-936b-a276c09168e3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Commissioning
f36359bd-583f-4278-a85c-189c0112e87b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing
ff209080-db45-4407-8993-3299b0ecffc7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB1
ff69a263-fa6b-4d39-8677-4a03edea4d87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB2
9a0c6d70-3462-4677-af6f-1ca77e6e0b2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB3
b353c5ca-8df9-4963-8ce4-734cabfaf609 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB4
7d84cb28-3579-4bc3-8ef5-cd0689b4ffc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB5
e19494b6-5f7c-4e0f-bcd4-47d5657d8fda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1812 | Mandatory testing | CB6
b5149919-651c-46c4-a9fa-dd210efc528e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813
a8f0f9ae-af2e-4199-8a85-48894009e9b5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Leadins
59db8197-d9be-4c3c-a17e-f113581ed14e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Roughin
d511d18e-65ca-4a90-abe7-17913b13cfcd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Cut out
9ee22b7e-cd15-4c03-b81e-1be9e304c512 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Fit off
6c138a2b-eeb8-47ba-83ee-6af8018380ae |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Commissioning
68fd4203-15c8-47d5-9492-77ed3385d3a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing
1667bed9-f09a-4e1b-b481-362fad3f66cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB1
5984597e-489e-40af-b4b8-ad2428eeaf4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB2
fd6ec800-e557-4ba1-8ce5-5439c3505272 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB3
c8af5684-2c6e-435c-84a3-1c21940af606 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB4
80efc28f-fefc-472d-97c2-0cc0cb00835f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB5
6a6e81f6-1d51-4c73-afc8-c47439ddbae9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 18 | Apartment 1813 | Mandatory testing | CB6
d279d932-cfdc-4973-9ae8-9eb9beed57b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19
a93ce47d-a96b-4079-b6ff-ee4487dd6393 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901
d1b841c9-bc82-477a-93cd-fec3e6b6b4fe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Leadins
cae9d87e-4fa9-4af6-acb6-eed5874a983c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Roughin
193f1600-0e38-482a-9c84-bf604036d92e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Cut out
ab6c4b29-d0de-4608-ae79-37c413c12d7f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Fit off
aed08a50-5fbf-427a-b951-db3c8d100add |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Commissioning
99319114-e9bb-4aed-9698-e377436f6f87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing
73feb628-f58f-40b1-86a1-fc7ce95e4b1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB1
64f3d74c-7a79-4c71-8471-b4abe2e7ae52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB2
6f567aa6-e3fd-41c1-ba23-f8c193f7f7ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB3
cbab7de2-7457-4df7-9fad-ef5bab673652 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB4
d25bbdb5-01e6-48a1-9bc8-5fc7c98e513c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB5
6136f37d-c5de-4dd2-90b3-c71832187efa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1901 | Mandatory testing | CB6
23702f54-2026-42b2-892a-4a47412bd058 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902
5d018638-d8d4-4197-873f-e9708dcc801b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Leadins
29f4defd-e1f9-4f53-b282-040855ac2a4d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Roughin
7ba9dcc4-8a16-4c73-8a53-65e84954e840 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Cut out
3e7fd198-7de3-484f-bfc9-dab7a6451bd3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Fit off
b201e50d-4d20-4532-9ef5-038cf7f3963c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Commissioning
e40bd3ad-e4cc-4d1f-b837-e8bdaff12727 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing
bb6df017-227d-4e63-9c50-31954b5384a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB1
93efd23f-c970-43cf-9917-c32f7ddc35d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB2
80138a22-fd3b-497a-af35-89e7fb8df362 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB3
b8497a20-e72f-4bd6-b00b-95c098c0d387 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB4
bc1ab8e1-2219-4e4e-b147-c2069c94cc39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB5
de068c18-1927-45eb-8e29-733a57fee460 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1902 | Mandatory testing | CB6
4af2bfda-01d8-49c5-aead-813ac8e8e24c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903
035bf28b-cc23-4d37-ba5a-a9d54582deb0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Leadins
6aee0113-b641-4be6-bb49-ff0b867ea855 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Roughin
13302d0c-32f4-4c38-b4dc-5ec3751b8557 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Cut out
6707ffb4-a94d-4eba-8eee-c08c4dc444bd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Fit off
cc559b77-709f-4bd8-acf7-2c00a45d6200 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Commissioning
da5612a9-72fc-4c32-8e47-f6985a10939f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing
b12cd779-fc7a-4e3d-8936-c88c022ff300 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB1
92c26fe6-6fa8-455a-883d-dc89a256314a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB2
af80cfef-8333-4bd8-9486-5992ecba0f3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB3
9012b8e0-d58b-4f1f-bed0-1a31c057cdff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB4
dcf81f76-7a30-4573-b38d-eedd46c7b97b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB5
c01787b3-a3f7-4cb3-b4b5-c21b33ee2aee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1903 | Mandatory testing | CB6
3cbb3ee3-44e4-4f80-a6e5-33f1bb1c294b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904
e0595aac-f8c5-42bf-bca9-5dea8460755a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Leadins
b8f04155-38cf-43f0-b7c8-623f477a4a0d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Roughin
dbca9df0-7788-459b-b71a-a9d7be89a990 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Cut out
a7f98211-78b9-4eb5-a21f-d9334a9db286 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Fit off
a1e8d82a-8b48-4fb2-8900-6140e1cc22af |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Commissioning
236765a0-fe04-4bbc-b935-7a57ce29625c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing
a8166281-5470-4808-acdc-6b37a57b4fcf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB1
4984adb5-71e5-4e8c-922a-815d32521492 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB2
a6d50229-7900-4593-956c-4996807e6bd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB3
0ea9c4a9-eade-4551-806b-4713cbd76630 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB4
cac3a897-af66-4be0-8da9-90ebabcded62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB5
830b19c8-8929-46d0-a9db-7efdc1c60508 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1904 | Mandatory testing | CB6
4c1633f0-bf90-4cda-97c5-a52e7b5388ff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905
342dd6aa-078d-4432-bbcc-019dae68fc3b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Leadins
1b1babe7-46d4-4d80-a9c3-70e68048e733 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Roughin
2921e279-ca6f-46c6-bdff-30b5b8e85924 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Cut out
bd08b20f-24a9-4e0e-a5cd-192552d25c94 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Fit off
ec0a69ea-ceb4-4bc0-ad3f-127d209b64c9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Commissioning
fe7dc1fe-b279-45d7-b7e7-2e5dcda210a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing
bd58ea66-0f3f-47e1-aa00-a681ae203397 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB1
dc5cb41c-5196-4902-9ae5-e0907546391a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB2
1f70ac4c-1de9-4a84-aea5-1110bf78de25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB3
a61151d2-b0ea-476c-a900-1d334483d20e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB4
7345bcd7-f879-4d77-ab27-1b5dff7f21fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB5
b4f7c278-0232-4954-bd13-634d73ef6817 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1905 | Mandatory testing | CB6
0b735d4a-6cff-4405-af93-14a8110d32bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906
8bcebc9d-8671-4f76-9d9f-5ce42feee52b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Leadins
0dc7c738-3449-4c91-85fd-3cf527a6e3d6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Roughin
e730e1d1-3c7d-4b97-bc09-adc7078211b3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Cut out
da8087e4-a0c7-418d-bc87-a2a7ccfce3b7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Fit off
ab57c9e9-2bae-4b0f-85c8-c1117dced2b9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Commissioning
11aad31f-27ec-4456-95ce-b442bd138260 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing
1ee1c0ec-cb64-41d2-b241-b745d80323b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB1
9fa77777-2041-4fcd-89c1-b987322c3d71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB2
33948e50-56c3-45af-9758-08135eb12e28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB3
ffa4377e-47c0-4642-8bb0-18e80bb5ca7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB4
4df7b0b3-948c-4cea-8a23-f071539d23d4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB5
c711f70b-1b76-4867-a98f-b271a8d7377a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1906 | Mandatory testing | CB6
89328b9d-b5d2-4bf2-a9c7-0e8ff81a4d00 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907
d5515141-25a0-4913-9423-54cd1c9cc38a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Leadins
c185ab52-3202-4dae-b83a-5cf69d5b9e07 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Roughin
b02e6057-16ce-4837-aaf5-12ba72699b2c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Cut out
efad8452-2dbe-4555-83d7-a35c0ad34054 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Fit off
34c3be60-93d4-46b2-aba9-7465b9dad742 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Commissioning
c1f6c474-3f46-4fb0-a6c3-aabdc921502c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing
22a641cc-fe1a-40cf-a13e-ae0eeb7772d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB1
09e0bf83-1fb5-4ea0-9421-85317e37bddf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB2
4ea3bf7d-0785-4b71-803b-7837a8f23ebc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB3
3f8f6919-5829-4e76-84d9-6424367b17bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB4
895e35b4-f8e8-4258-9798-20344ea4f9e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB5
25ed6b1f-91c0-4adf-b7df-e4a479b0cc45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1907 | Mandatory testing | CB6
d3b7d255-65b5-48b0-b378-04ad022f0fca |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908
152845a1-15b2-4afd-8e18-c38e0f846fc6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Leadins
d25cfba9-d078-417e-9a71-19df5cca645d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Roughin
214da34d-7ac1-41ff-a7e7-46c4b73ed11f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Cut out
05681ea8-5d95-4e68-8c71-cebdd085edfc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Fit off
5c14f4d3-231c-4831-9cfa-094aa5237aae |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Commissioning
13b499aa-a951-4fe0-b834-1ef6f529d9c5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing
d4dc40d3-7d9c-44f7-a81e-2c724d7b2f47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB1
9a857066-e4a5-42cc-b9ad-b2d364fcf1eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB2
42e277d6-17e4-4c45-b200-28f7958f9fe7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB3
0698b216-55cb-4309-80ba-50272f9e8a2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB4
168b9517-b89a-4b42-b22b-ffc8f655b959 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB5
0028a92c-d244-4fe1-afaa-ec27f31fd31e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1908 | Mandatory testing | CB6
945ebe8e-6263-40c0-bcb1-6cf75112e1a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909
cdbc39c3-ae82-4fe0-8a1f-8e09c5f4a160 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Leadins
026ce8ee-9a9d-4c8a-88bc-8cda668ecd6d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Roughin
2e0c4867-ff27-42fc-9f64-57ed19add859 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Cut out
ce297b70-ac01-4666-a25d-29904cff1740 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Fit off
2579908d-786a-48fe-a979-b86a94c581f2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Commissioning
bbcb0142-c4f3-4a8d-9c20-8e92936adf7a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing
ba900cfb-d99a-4979-b574-af794fa7482f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB1
608f7df8-e012-483c-b3ca-fdcc877d2e33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB2
6a4835db-9175-4058-a67b-73e26acb9bd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB3
68c96dfb-823f-4b08-9e4d-b62fba9ae0ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB4
4eec77c8-6d17-4313-871d-d6fbc2b8b51c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB5
d4b1341c-4e9f-4efd-a99d-910d1c288f8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1909 | Mandatory testing | CB6
9b072285-b5e6-41df-8289-13405c622e2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910
a5f2c8a3-3188-4a1e-b0b6-48f145ab01dc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Leadins
44b863cb-dc85-4bf5-8060-62be8fdbe011 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Roughin
45bcfd59-6029-4010-9beb-ec4129752e7d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Cut out
c51979c1-de4e-4563-979f-bb6da3eebff0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Fit off
f2018552-9958-4eda-a66e-b0f67dc245c8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Commissioning
e07a79ab-d40e-4fd8-9d37-e48c116626dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing
5c8756a1-6629-4468-8f6a-4653010021aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB1
58058da8-679d-4078-a5ae-1db3763756f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB2
5279e6ff-2584-442b-a04b-f386c0bdd980 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB3
de947981-7f1c-4108-8532-bcf089d6aaec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB4
97473c50-4922-4b76-9f4d-0b3b3286056e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB5
f6035dc3-4470-4b05-880d-e55c85b470d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1910 | Mandatory testing | CB6
d13c226a-f6fc-4bc3-b8d1-4c725aa5e312 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911
f577968a-6402-4c97-92cd-11de0aa23f4d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Leadins
1ca28919-0f4a-4c56-86c8-bf2e72a5299c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Roughin
9ef5df38-d0e4-4ebe-856e-b78f2d2b48c4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Cut out
632d0d40-e285-471c-a9c7-e51d240e0e20 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Fit off
79a9b620-fa2a-4bd6-bf4a-996a2bccf7d7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Commissioning
9209bd47-0dcf-453d-a015-121865adaeec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing
2a05507d-7c61-4b5b-99bf-fb6e09b3aef5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB1
92171067-0137-44ec-96f7-6d3b26cf9c1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB2
660c238b-0482-4b6c-aeed-5d50457f8baf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB3
69eaa6de-3996-42d7-b00d-f58cfe7e64a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB4
10833537-e5d3-45f8-9c1d-79a86a67d499 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB5
43e48d9c-c4b2-4fb1-8f7d-084e3faa1ca5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1911 | Mandatory testing | CB6
872e9cc9-b781-4d72-a936-349c81118bef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912
c0295fa7-759f-4fe2-95a2-608503337a9a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Leadins
ccf7dd04-9f58-4dc0-8fee-c857e3987128 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Roughin
abb7b8bb-896b-4af4-8501-2061977d8876 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Cut out
98ce732f-40d5-4572-a221-e3b3834566ee |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Fit off
fa86e0da-f19f-4f38-8f9f-33a088146dfc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Commissioning
4696ce8e-ad50-47f3-8d46-96aebffcba22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing
0ff49ff6-05c5-4c84-abc9-53f1780c155a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB1
6fda278c-af3e-48a9-a8e7-968a93ae88aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB2
624f3157-6277-4ec4-beaf-00a76ec6d0ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB3
46e13a3f-46fc-444d-b1d4-44a62a448511 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB4
f77470ad-b2d0-4c15-92d0-e7bf0cae6157 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB5
7dba4fea-23e1-498b-a582-f5bbd625f275 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1912 | Mandatory testing | CB6
9fd881ae-c86f-488b-a365-feb1f7ce0772 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913
a19531db-0dff-490d-b80d-94468215b6e8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Leadins
9c207af8-fafe-4ef9-bdfb-3e136a10e21f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Roughin
35e42577-295d-4886-80fc-e1a61a87a1f3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Cut out
aa4ce9ac-5eea-4c41-a8ed-7d49a75f2555 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Fit off
fa04952d-1b47-4d49-b489-9c5af2c434e9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Commissioning
9353fb3e-d7a9-4753-88ff-c198d4b4ea7c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing
b05b23d1-0e72-42b8-b8cd-4e5faa8c123d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB1
f54bde7d-5448-4e75-b9c0-21e62b83cd99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB2
2568c5d4-6452-4a59-859e-6c337ce5e12f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB3
e4b52b49-35b8-4ffb-b7ec-c9c69e166e69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB4
677ab973-ebf2-426a-be62-233dcd1436f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB5
fcede70a-7b61-46b6-b862-8fe4762cde41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 19 | Apartment 1913 | Mandatory testing | CB6
f44f84e2-6dbe-4aa0-9466-c94e4aff5c37 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20
b220ed87-d69c-44e4-a15f-0433da648f78 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001
9eb31372-9c5a-46bd-932a-de1f0c10268c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Leadins
061ed056-230b-4e54-a4c8-869a3c1ef9a1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Roughin
505d797b-8bc6-4046-a590-8d311d6fdb9e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Cut out
ab2a40a9-e6c1-4b29-b94d-296cd70dbb99 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Fit off
a1ea1d16-f1f6-407f-ba80-6f5e198fe41d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Commissioning
146be6f2-6dad-4836-9650-bc41dd2ef78d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing
0ed8ff41-6f58-43eb-b88e-9faccd2463e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB1
06dffc64-25e7-42f2-97e2-f53ce648b555 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB2
77cbb8f4-58db-4deb-a659-04ff65c60f9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB3
24c229e0-9c97-4910-89d5-18aca03fa27f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB4
a073e2b5-847a-4eb4-b4ac-a454beefe5ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB5
37c2e8ae-9991-46a8-a375-1b599ce2d767 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2001 | Mandatory testing | CB6
d441d105-ba0c-4e4e-8ecf-b2229dd9ac6f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002
23d53900-294a-4010-9876-d2b59ce90181 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Leadins
71a48393-8b50-41cc-990d-eb323ca84856 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Roughin
a95587e2-a0f8-440d-a569-f9e251fed9a2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Cut out
6c808d47-7b40-4086-b6d5-5ab1c881d6e7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Fit off
18ce6442-c5b6-49aa-aed9-5c9fbab963a2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Commissioning
c5755b63-b412-4c32-be49-f3a37c0978a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing
b83c92a7-0fb7-449d-89ad-dfdfacb72bfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB1
74c89db1-357d-49c5-b262-6c51ae50dfd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB2
ec79fb1e-379c-4353-afbf-9c802daca1fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB3
7e397174-8437-4245-9c9b-6e7420334a22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB4
30706d3e-69db-4c4f-aabd-89377c911101 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB5
82ffd5dd-2b21-4bc7-87ef-03551cbd1dbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2002 | Mandatory testing | CB6
513189be-6881-4ef6-950a-c58f2254f490 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003
8106aea7-48fe-4dd2-b3b1-8e7aed833772 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Leadins
000319e3-a5b2-4be7-bf17-7eccf5134a58 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Roughin
be68be8f-5735-4031-9589-8260976e9441 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Cut out
edcafb69-4452-4ac2-be72-4e6151352a87 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Fit off
1e1bde31-ae93-4d37-838e-3671a5f43709 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Commissioning
237067d7-e9b9-446a-a45f-d6025b9e3630 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing
f3fc7679-ae3f-49de-8cbd-c46be27ef9db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB1
5eddb081-1a20-493c-9e25-3b4e7d642135 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB2
9aafb8b7-e959-4a5c-9afa-dc4ceafe1f45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB3
22a7906a-c2cd-419e-99ce-0c19dbb93cf1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB4
bb8cdb05-340d-4fc4-8f0c-1125c74a5872 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB5
b33bb5dc-3a87-4cca-aba3-22a0f5e44586 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2003 | Mandatory testing | CB6
f63e3b55-b176-4402-95bb-5cb9088f0554 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004
cbeb158d-3d10-486a-b369-39f3d0250b82 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Leadins
f8d7cbd4-9687-4834-b234-37ece85861e3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Roughin
f4ac1ef6-8405-4cbb-936d-24dc46bd8f42 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Cut out
63e8f7df-4642-414d-9442-0fbba62c031d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Fit off
3eef5991-508f-4ae3-a1f0-92d6adb02f99 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Commissioning
e45f8ce3-ddcb-4719-9087-a5160d46d8c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing
0cdfbf31-9156-4c99-911c-42d87afc0d0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB1
7ecd961c-a25d-4527-88d2-28f78bf7a1f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB2
a513e41a-7ca0-4333-a99c-366898615bf7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB3
0753c3b8-33e3-4451-9354-3b32aefc6e37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB4
ea97e238-2d1a-4296-89be-6b44fdc61824 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB5
f773aec5-f7a9-4086-ba35-535416de918b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2004 | Mandatory testing | CB6
025102a8-06c9-4363-99cc-587d805abbce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005
c2c6d0a2-7ad4-4b11-911d-254ed451fb22 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Leadins
f944bb42-cc85-4ffb-ac33-745455da3216 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Roughin
a066a4ec-1a95-4774-b2d4-266737e49619 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Cut out
e9a3a759-2d13-408b-9f88-88e9a5abae06 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Fit off
c3de69d5-d1f9-41a0-89e0-f3700684be11 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Commissioning
96460d9e-02c1-401a-96de-38328b621d70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing
bc08dc0a-1b7b-47dc-b413-797db134ac81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB1
0cd893f2-2c7d-4ff4-82c9-8a625230c0bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB2
2c669185-8d58-4a78-93f9-478788da5fe3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB3
ab313b4d-8500-4abe-9cd8-9969b84876cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB4
f6e8c52b-e64f-461e-aaf2-2c48aa80f1b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB5
48a615e0-a76c-4975-92e1-156ac36205b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2005 | Mandatory testing | CB6
9c6caf41-367f-423a-9fb8-55f7bf0d25aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006
e0961f0a-6b70-4080-81d3-0bfed3f8ba55 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Leadins
6793eaf3-ec3b-42b2-8068-d7e67308ef95 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Roughin
4d980fcf-4eb0-4ec4-b10f-09d268685deb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Cut out
6ddf5f02-61df-4286-ab84-c3616d0f658f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Fit off
1ade6f2b-a237-4f89-ac7d-c129af798a64 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Commissioning
0d37fd14-9f74-4760-b7e0-0cebe0bc6f1b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing
d32384d0-7053-4517-806d-e56cd91612a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB1
f806444c-b02e-4a24-a8c9-ad7e95a95706 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB2
a11f86b5-0e35-48f0-98de-8ed2d866ee60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB3
2da9d733-c196-4643-9568-5612576abce9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB4
4ba2cb41-e64f-457d-a7b5-9908a8a0037e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB5
8244ce16-1865-4e87-9915-ad925e0b5ed1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2006 | Mandatory testing | CB6
c91451a1-12cf-41e0-8e75-f998ca149f52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007
4880d3b7-fa9f-4058-8c33-a6539879a869 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Leadins
fa726816-df95-4887-a8ac-d033d87c1ecf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Roughin
b091a0f3-81ae-43a5-8875-24f0c2b61795 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Cut out
c834e48a-17ed-4bb3-b028-29acdab22239 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Fit off
9a0642b2-3e0b-434e-9db0-d0ca48c2f8a1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Commissioning
4a66ea00-7083-41af-af5e-2016fe55cbed |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing
2c927cc2-dd49-4a12-a529-fdd4f23a0062 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB1
6c7ee70c-afbe-458e-964e-4c115ef07f7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB2
bc3bbc07-1366-4a3a-a913-5222279a56ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB3
a6ae65d3-5bc2-4740-add3-6155e75563a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB4
49a4fe90-8f70-4d03-89d1-96538df03610 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB5
f6b6309f-918a-4f1f-a838-ef617a572745 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2007 | Mandatory testing | CB6
5e9d6ef1-49da-48ef-ae47-9ed15bff2f9a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008
3ac7aa9e-1788-414c-8cda-38e41edb3497 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Leadins
6aefc557-99d0-4a05-9f00-044ec8bb3295 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Roughin
d47879df-da98-468b-83cc-b12574dd699b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Cut out
cde3e82f-518f-4667-b796-af94ea44f3e5 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Fit off
0b8d9723-582a-4cb5-b6e7-69dfdeab11a4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Commissioning
efbeadaf-47b4-4311-985a-f9470b4645b1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing
c6599ffe-4406-4769-9ce6-67113719611d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB1
f73ee9be-426f-4b0f-b555-51b3d5d4a837 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB2
1966ab4b-b413-41a4-8608-408a179638fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB3
8ffc92a6-6947-4732-9e9d-ac6de0df9838 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB4
136ea73b-b2d6-4996-b8e2-1d15c7042204 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB5
8f8151f0-f4dc-4131-b539-28b0140c72ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2008 | Mandatory testing | CB6
011fd00f-6a23-4fdb-94a9-32d3ad55ae95 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009
53151b46-0ef5-4a74-9e6e-fcb762a891d9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Leadins
c7e28f78-decd-4dc7-a693-5c324c99f48e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Roughin
c4134ebc-cf54-44ee-96e4-710c313509f5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Cut out
30905f0e-6ecd-4778-ae5e-82296fd233a8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Fit off
d43e34f5-ca4b-4bc7-9ecd-20cadfe398eb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Commissioning
8c206844-57eb-42dc-b263-701df291e2d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing
c68380c8-f58e-4ce1-a676-47629f211dea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB1
de39004f-7641-4f58-ace3-aab214e1a5a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB2
5fa06832-3ca8-4185-a133-caa313a54ac1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB3
c65e7414-a954-4344-ac60-40619d023fdf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB4
b1a79538-1012-4343-bab5-ec2926e2a902 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB5
5325c7b1-5d89-4f30-9bf8-eaffa5591417 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2009 | Mandatory testing | CB6
0c3b1ac7-58dd-4aaf-8de9-e0bca537d7e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010
3707894f-0441-4294-ab0d-643badd6eff2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Leadins
12f233bf-206a-470e-950b-328a6157e6d6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Roughin
98a24604-9325-4281-9e13-9af83cf80022 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Cut out
f628df88-8357-48ed-a71f-17fecc9425f4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Fit off
f51c6e1d-f729-4705-8bc5-6d0da08ef73c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Commissioning
be71cf4a-901c-4d3e-9ecd-fb7d34a5a8ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing
c046f680-c985-4152-9172-4c48c745a8d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB1
d7ea1fe1-68fc-41ee-a5ce-031bca044c67 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB2
b66b74fd-99f2-460e-8029-9199e13046f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB3
045f08d1-e9b5-491a-9072-077a608bcb09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB4
80ca5b85-597d-4f30-901d-958b5cadb1ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB5
035f50f7-f04f-4bb3-836c-cb992e8c09ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2010 | Mandatory testing | CB6
2ad86b5a-3988-4fde-ba3c-76a7e5cce913 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011
d2637dec-0626-48be-8a86-04385995133c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Leadins
c31b6612-3afa-4660-abec-0d1dcc085970 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Roughin
adf1430b-5133-41bb-ba14-e8ba5ff123ac |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Cut out
46cfb560-3c03-47f7-a167-872a3d4c7745 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Fit off
64669d92-2550-4447-a6b6-2465fc797a81 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Commissioning
f7d2a4b8-e3b0-4f37-afde-bbd393d38ed6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing
20f4f55a-1e4a-4a85-bf1e-fb39e3995324 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB1
79de883f-6b4a-4722-ba0b-8b95fa86100e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB2
3a10eb25-4382-4a86-8312-9c34171a1471 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB3
623daa59-ca02-4e26-a639-ba416d7a1d17 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB4
d76fd347-2af1-444e-9132-37fe71dc6c1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB5
1aa5196a-20d3-466b-8188-6f5bf795426d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2011 | Mandatory testing | CB6
f43057e0-31af-4288-b498-7ba9aff10e8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012
08a884fc-9764-446d-8b3d-7a4dccf35973 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Leadins
0567f9f6-b3ce-4ad2-9158-8aca8302ce15 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Roughin
ad9d63b0-d524-48b2-b9b2-3a0add9853d3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Cut out
508efb5a-00ec-4e37-abf2-b30869a43032 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Fit off
c96d0a7e-b605-41ea-b3e0-6982873f135e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Commissioning
d6282a1b-8ebb-4a79-9a51-147257ff2e22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing
9e3538d4-7ba6-4cc6-9658-aece8b3508af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB1
eb25fdef-76ab-45e0-90af-e2c05cff0421 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB2
60ead744-1857-4817-b0e1-52dcbe543df7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB3
c336b017-abe0-4c69-abc3-5bcd33305646 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB4
f346ee2c-7dbf-4622-9252-8dd55665e260 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB5
1fa7128a-cc80-4956-a8e6-e041bfcf30cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2012 | Mandatory testing | CB6
de5f3b51-ac48-4c64-836f-6e40e2128071 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013
c31aaa9e-9029-4c8d-bc43-546f8878c15a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Leadins
1947ed78-2fc6-43eb-ba50-19abf239f1c7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Roughin
8b9637c8-a428-4c2f-a4a6-dabfa660cd7c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Cut out
9bb0c492-5f75-4995-88c4-02283ece57e3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Fit off
3ac62d70-5af8-4d48-ab00-4ba392d96421 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Commissioning
2ded9974-1b52-4456-ac0b-01114457da97 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing
790c3058-8499-4f2b-9a86-eacf2cce1958 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB1
a677ad44-b833-4a71-ac73-82bf93725705 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB2
02f8d24a-f91f-43a9-9248-efca0a5e9423 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB3
f9293adc-e10b-49cd-a0b5-d493bea8d5fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB4
910f48d4-292b-4f06-8734-23e2ce1cf45c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB5
163a3f77-076e-41e7-af11-2c9e44c57bb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 20 | Apartment 2013 | Mandatory testing | CB6
e72f7790-7b6d-4f15-9b58-a5c1b9c55ab0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21
89b2516a-345b-4500-af62-9c381d23a803 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101
9d7a960c-0692-4990-916b-10c666bd65a6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Leadins
bacece50-52b5-40c4-92f6-abb9088e206e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Roughin
29a5e74f-99f8-4775-af1b-81cd626f98ee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Cut out
ff0689d6-1029-4bf7-a57c-ec99c0d36b75 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Fit off
bf707a86-5195-4094-a4ef-550988372ef9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Commissioning
90c63282-b7ac-4784-916c-ac658c438b54 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing
89ad8f0f-10ef-4686-a8de-77721ce9df2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB1
ce01b1f9-eef0-473b-867d-624f9105845c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB2
2acf29d5-da60-45a3-8b9c-ddb2d2b18be5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB3
0eaa729e-9e72-4939-8c2f-677f8d6945a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB4
b6613a30-7c9a-4b96-b2f4-68481865bfc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB5
f8ae5b14-4253-4474-9bf9-bc45c5e96b3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2101 | Mandatory testing | CB6
e9a24745-5369-4e42-b886-a693c84f7f49 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102
cd73bc7c-c5a3-4358-909f-8e00d5024cdc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Leadins
a0d6f3f9-c959-4c0b-ab48-1dfab5e1d89a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Roughin
141a3355-e839-461c-bf2a-1d70b9c21ae0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Cut out
8626a7a7-3a56-4489-93df-7411e9635839 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Fit off
6dde0549-f123-47da-b732-446c58f43e59 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Commissioning
c7e24182-7182-4cf7-8b29-3e329c0a8f42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing
42f89618-2227-4da7-8180-f52c0ee80ca3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB1
3dc91579-a399-46b0-a95b-5f3935b508d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB2
be709487-0db9-43c1-94a3-9e462363cf3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB3
9e17e5c4-e731-4ecb-956a-ae90b22e1f7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB4
1a064416-8432-4737-8a35-ce17947ee2a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB5
e371cd45-4734-45ec-902a-306c5e6204ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2102 | Mandatory testing | CB6
deeb5075-36f0-456f-a68f-cb62ddf70275 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103
531a573b-48f5-45f5-a0d0-177b3305ddf0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Leadins
3b885503-1d33-4ca5-9f7a-434a5ee708b2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Roughin
206b2b08-c1d0-4c9d-ae46-8a23d0bf8f6d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Cut out
105c9fcd-ed68-469b-8103-27ef98bf6ce1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Fit off
755c4be4-78c3-41ca-a0b0-7725c54b5e11 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Commissioning
5f29c8b2-fb7c-4294-a3f4-e83505ff842a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing
c93c43d3-bca8-496e-b5fa-9d078c265d9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB1
ffaf2b61-2b57-4c87-97ba-078097664321 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB2
c7b96a51-50da-4fee-bff6-b5df9cfe00f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB3
d86b9af1-27d5-475d-a04e-d32949f56ce1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB4
62d6001c-c955-49df-af21-5846ac6bdae6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB5
e10a98ed-e567-445d-b906-d011ecdd70dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2103 | Mandatory testing | CB6
2f07076d-74a9-4bd8-8d25-fb6cba40adc1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104
e79f72cd-1d4a-4df0-842a-a461658c34c0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Leadins
75689a7d-30d9-4d58-bead-54cda63e9881 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Roughin
eabe201e-95fa-44d0-a1ca-9f803d5a9936 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Cut out
b6248252-44bb-4fba-97f7-e24039032f51 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Fit off
470eacf6-e446-43d8-903c-103164233beb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Commissioning
ec0f4fd9-22dd-45e4-86cd-26e55d19a7a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing
9927630f-2abc-47a3-8953-723efd4d9282 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB1
e987493d-a818-4b46-a497-28084425a5b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB2
79e7e708-ecc3-4f43-b3a1-4ca9f87a8f7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB3
4ae7e076-847f-4eb0-8760-7509e2c1725f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB4
65472b24-7082-4b14-b028-dbdfc9e150a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB5
b383fe22-b650-4789-b007-31bfa067d2b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2104 | Mandatory testing | CB6
c11de57a-515a-4ff0-bc3b-be477f80cf9e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105
72145d8e-e6d1-4a4e-99a1-abb0af5ccaca |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Leadins
31eece86-c4b0-4e92-8eb3-6fe97904549d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Roughin
0ac398a7-4097-4a2d-a2e4-72fd105d9fd8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Cut out
67bffe86-25a0-4ae5-8d50-47e704d8827f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Fit off
dc8f75a6-e7bc-43d7-ba30-3d5af62a492c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Commissioning
d43bcf3a-fd4c-4a54-ae05-62c289e8af35 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing
46e1f2de-1594-44c5-a589-ddfbba5fd9c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB1
59a0c2a2-210a-4848-93fe-86a97f18bd40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB2
814abaa1-695b-4989-9e81-62af973618fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB3
b9fc1de7-2a8f-4a24-aab2-b4e96d2b0afa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB4
788fd9e7-109a-4a65-b19b-978922723c72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB5
8bbf62e3-3f27-4758-af2f-068fbbfb45c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2105 | Mandatory testing | CB6
c56ac3fb-727d-4885-9dc4-2a0cd7e0934e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106
fbe035a0-6433-4d51-b9c8-a5ebcabc09ef |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Leadins
92ace790-c6cd-447f-b40a-e0b478f081d4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Roughin
afa82560-6fcc-4fdb-8b45-beabdf812214 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Cut out
7772febe-5f88-467f-bac3-91457e47466a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Fit off
dba01cb5-8859-4dfa-904b-7b102a849293 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Commissioning
60dfc96d-0b41-4f7a-a6a0-dfa5ef4375c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing
3da8f8dd-bf0b-40c8-a83d-fc7665cf97d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB1
fb2f063c-237e-4da7-808d-d32d272e2429 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB2
09689f91-5025-4df2-903b-3703d9f5bfbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB3
c541a1c9-3462-47fb-a795-1d019c48e53d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB4
d2db408c-e50b-4f55-bf47-ae1bf8af2432 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB5
effa2b81-60f8-4c89-b45b-3f92ceed5180 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2106 | Mandatory testing | CB6
8527a57e-1af7-40b0-a595-225e66d1d5fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107
42ec0d63-8ed2-4cb6-b636-cd4003c99012 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Leadins
62dc5dbc-aef6-4f33-b38c-121338971598 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Roughin
1a0f4562-6113-424a-b54c-c230c79e600c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Cut out
6cd8ce66-b25d-4d44-8589-a1d49bf3be26 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Fit off
19e00828-cdb5-4574-9eac-a9a5ca74a047 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Commissioning
f08f4c5f-22f8-4e28-99a0-f5087fb374ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing
e047fdbf-22b2-441f-b71a-e4492bf9c0ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB1
21ed549e-865c-459b-838e-d80abb9ab4cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB2
7ba9c790-3e31-4228-b73e-9280e174a590 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB3
8bc05ecc-97e3-483b-9b85-f9ed89d94727 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB4
6073e820-e92c-465b-b7bf-8b2576a0fde5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB5
41a84752-e212-4cde-a86a-f8fc122e2c7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2107 | Mandatory testing | CB6
33d2ba25-4f37-4515-8f3d-e1a6e923e7ec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108
dae44f35-99ed-4fba-969b-34befb465c34 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Leadins
5684c5cc-419e-4cd3-b5f2-90b7ec90c45e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Roughin
8560aade-15d1-4254-82c2-cb1bfd3076ef |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Cut out
0298c03e-4b02-45c8-b1b5-41ee7569e27d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Fit off
a7638d31-81f1-4508-86af-20b36e075d88 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Commissioning
7126529d-591b-4d4e-9a00-fa57ca3908bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing
43acd2fb-02be-4b84-88f1-8f78de3dd9f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB1
830cae98-8292-43bc-92e4-238a1146a657 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB2
f9210846-6bcc-4f05-981b-5814619ee335 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB3
7186e144-b225-416a-aae8-418c7631aba2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB4
96012449-0b86-4406-8ddb-363d46322555 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB5
424ba494-afa8-4ed8-aaaf-81e1bfb82525 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2108 | Mandatory testing | CB6
4efba96d-ec70-46ea-8122-bdbb0d47844c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109
7aac07a3-5288-4116-bda5-95b0d5156d8d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Leadins
20aad709-bfa1-47e5-9851-ca02f51be4da |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Roughin
d1857770-f40d-450e-967c-f7dd99338389 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Cut out
06740354-85b8-4d2a-85eb-28c2c1755aea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Fit off
bb05e860-85b9-437f-a39f-fc74320138c9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Commissioning
8cc99b21-1448-42e0-bfd7-467f1bdd178a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing
f03b22ab-224f-40d0-800d-48c55fd26c72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB1
29007c55-1051-4beb-869d-713178f045d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB2
b1549e6f-3117-4ada-b53b-c8031a929d30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB3
81699ffb-4ca3-45a1-8c67-d90f6f13ad45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB4
bf176e7d-b586-43fb-9c50-eddb5bc6bc24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB5
c1e82ffc-12ce-4b45-8414-e5116bbeab87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2109 | Mandatory testing | CB6
77cf144f-448f-49b7-ba93-7837307a093b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110
22ed41db-b77a-45e5-b7ef-085aaca4424e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Leadins
c2b561df-ae58-4110-aee8-92bb134e3102 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Roughin
ba774085-2786-49f6-b7e5-0680a1f29107 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Cut out
b2a41c52-0237-40e4-947e-2a0992983471 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Fit off
c569d72d-7b51-4514-85cb-01e02fe5a339 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Commissioning
05bc1451-1878-4434-ae07-14be23e8d1af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing
ffb0965a-ee39-4af7-a8a1-fc424e12714e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB1
896bb2e5-2d74-4d90-a5d1-9dc670f3231b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB2
8c46bfd0-8b03-43d1-8001-9a744ac08326 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB3
15368188-affb-4f22-8ad8-eefc7eb69768 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB4
80f36f9a-920d-4d12-a2c1-320ec67e3c84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB5
7c586f66-203b-42a3-a43b-65336804e92b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2110 | Mandatory testing | CB6
e57bfa8a-a3ba-4789-ba35-4788e864f1ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111
20190a37-1701-4262-b829-d9e42d680e55 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Leadins
147c5b36-b8e2-4992-9fc6-3ab758598f8a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Roughin
9064e74e-afe1-4749-a042-d01b0d7473fe |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Cut out
01dd6f56-ea54-4303-9b94-eec2c452c561 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Fit off
85fc77fe-42d3-4a41-8ea8-ea5c225d3187 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Commissioning
fcbcf19c-c17b-4945-9f63-3c4e07a98f13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing
0af36b54-4c78-4e08-ac50-8aab157e5c1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB1
7376b394-6eea-4006-acd4-256f31d78fa5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB2
7665c443-a919-4336-bf7f-94814c6a304f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB3
98873cd1-988a-46a5-a467-2deb98c3478d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB4
c546bc33-7072-42bc-91b6-287f95dbc525 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB5
a6243d0d-9bf6-46d3-b360-7f51ec2b776d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2111 | Mandatory testing | CB6
239fffb6-070a-4ed9-be56-cc90ac91d0e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112
fda00aa0-ed9e-48e0-92b5-d0323e49e0d7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Leadins
94fd921d-2d05-47f7-a0c2-5fec9de26ee0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Roughin
627746dc-0c05-45fb-9f6b-2a2c248f3926 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Cut out
3d90b147-2eea-4d27-962f-f9f1acafec4e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Fit off
d169ef6d-bc84-4d4e-b412-0598ad6cff2e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Commissioning
834f3afa-4e55-443c-a598-e083c187cb9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing
8a78bddb-46c2-42d8-81b5-d0c1c349cf6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB1
cd66b57b-52e2-4bfb-b3fc-3478be882441 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB2
5ce598b8-e219-45a9-a9de-f239c5ca9a88 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB3
655c7065-b606-45a2-9801-97c29f0c9088 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB4
81006180-10f8-44d3-aa3b-b3195156e998 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB5
78bf1a25-e348-4ffe-be42-4dd38a4a5843 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2112 | Mandatory testing | CB6
31f3af21-1034-4baf-b6be-f9612c54196e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113
1a0b5892-06bf-485a-8c97-792474aadefe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Leadins
0e6a1eb2-4f7c-4e1a-b20e-36b57b5372f6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Roughin
63bb16da-bf60-42d0-a38b-ff22e3c9a445 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Cut out
43e9a0d3-54f8-42e8-9501-5c870e91cf26 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Fit off
426af1e5-e226-4acc-9440-859dcc70215c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Commissioning
6f156fc9-4645-40dd-9741-8ccdd4cc2521 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing
8fca9493-2eb6-498b-a585-65cabc932ef8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB1
1ff4b275-2f07-40b5-ae39-b2ade86809ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB2
5d2306be-16cd-466d-a341-346392658f0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB3
3056f590-ee3a-4225-9163-65a91ecfa24a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB4
6e2dfc26-bf36-4724-9ff2-dae72a659c36 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB5
b05e01f1-0d46-401e-a99c-ffc4af1ca7cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 21 | Apartment 2113 | Mandatory testing | CB6
3bf16de2-6609-43b7-b922-6835a4a61cf7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22
3596b2a8-4f45-4d9e-8637-49392c1fbf0f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201
f76015ed-9c1b-4abd-b44e-8e3cc4bdf577 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Leadins
cabb8114-729c-414f-91a9-742d7d7ecd0a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Roughin
f2bf99a8-691b-4cfe-b127-ea33fb964a33 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Cut out
a59e9149-4e24-4325-a127-c8a7f7efa037 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Fit off
f673f39a-d6e6-460c-a4eb-b1a4d57e45b5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Commissioning
a72f1c91-27f5-4a5f-b3d6-1418b6a08f34 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing
7fdb3ca1-4c57-4f8c-bbe2-b2eff2786bb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB1
44dad133-13e3-443d-b7be-25bc7c730ca0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB2
1677ae65-8324-4514-a716-c8a34f5cc67f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB3
01dc7205-2742-4876-a3d2-64fc0ba6921e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB4
2e4fd9c7-8fa4-4d32-8bd9-4eb5e3a478bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB5
0ee247ab-4ca0-4420-9bee-ad2afd1b52ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2201 | Mandatory testing | CB6
b8bd4732-a4c2-4ae3-b1ea-a866c3713983 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202
02ebc8fe-5fe1-4bca-b73a-34565e5c2786 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Leadins
4bd8b1d8-1024-4bf5-9795-2c4e1be37a4f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Roughin
29fba6a4-0772-4dbf-8c29-180040c99295 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Cut out
03750bb3-8470-457f-8955-a9da085b1b89 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Fit off
1cd1c5af-0054-4c11-9be2-9b27d2aca4b8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Commissioning
a4d36684-7678-4257-b95b-28d14d9bba46 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing
ee42107a-2faf-4bdb-8059-6e5335fc841f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB1
6138eb19-0247-46ab-9898-287f58ecc697 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB2
f0913434-af3a-4765-98c9-db71fdaff74f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB3
4ee47633-0213-43d6-8139-acd58323a05b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB4
187add74-eb95-40d2-82ec-4937f7bdd3d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB5
781704e3-9371-4b47-b383-b282fac22b78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2202 | Mandatory testing | CB6
d2eb4d88-13d7-4c81-9716-28318542d7d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203
abe697c9-a752-4fb9-a941-69e6ef881842 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Leadins
5c0352d9-8e25-42ea-8d33-e41f6e032727 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Roughin
095f70e1-c0f8-44db-afa2-d2d6a1f9e33c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Cut out
f130bb24-b3c8-4f43-9055-44e7f4d054b6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Fit off
25c693b9-71d2-45d7-8cd3-0b968ca77a0f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Commissioning
4a70d5a1-d3e4-4dc0-9fe7-9c381a944644 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing
2f8be43a-ec0f-4ac7-9337-735561c5e3e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB1
017e8c83-dc32-4e50-be2b-f85f8fc71434 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB2
3b3d0218-cf0d-40b3-b415-3367f3922929 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB3
0bca6335-3c8d-4154-ac78-c6556d4a6b2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB4
c74c1d76-8a9d-4bf5-9957-ee691c73abde |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB5
57da3829-961e-44ad-82b2-04e7b6f2506a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2203 | Mandatory testing | CB6
97f7f974-fa46-44c3-b029-6a38cb11b9fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204
2d369ba5-ca38-48e6-8932-c4dbf28976af |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Leadins
a98068b1-c68e-4415-a794-ff5a56204c61 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Roughin
b2bcd8e8-6f5d-456c-82d2-c7689b9b0a34 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Cut out
1e19ba73-fa27-4e54-abea-400578b6e91c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Fit off
c58daf39-6fdd-4171-a2c8-aaf79d3e35f0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Commissioning
7733dad6-1d3b-436d-9fc1-01423b648a69 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing
b97f9599-41ef-4eb7-94b1-c40ca3e5887c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB1
d51c7c7a-03e4-4cbf-9c09-4bc822771a01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB2
b6b6099d-61b3-4386-9d7b-e8e2b36133da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB3
2a1b9903-1c1f-427b-86fe-e4f961e02dba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB4
b0f43c49-b249-4840-b15e-6af33d62c501 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB5
59f8f36c-c6ee-4dc1-8b50-ea53eae74899 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2204 | Mandatory testing | CB6
f05d9bf6-566d-4403-85e2-9aed9439a283 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205
768c1b4a-16c0-47e1-80c6-a442b51045c1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Leadins
0ce6e3c4-2194-4cb9-96c9-d097f4266140 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Roughin
386dcdd0-2d3d-4d24-9c2d-0845a0bc95fd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Cut out
a75100d0-0f74-4294-95cc-cae98715a5b1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Fit off
7ba44182-3737-40bd-9fe5-d6ea286272f7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Commissioning
1357390f-8231-4c59-8704-602576205e79 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing
470f9b8b-294e-42e4-8548-a23964791e40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB1
b3ed10c5-f446-402d-a9ce-43b24103b45c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB2
929b7f3e-bb14-424c-ab72-c8a59c6dc275 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB3
1867df26-4692-4486-b943-c04f713e9a51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB4
b73f8cbf-bf60-4e67-88db-2a076aca2d68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB5
a2c07fa6-5ec1-4f83-8f7a-ea912dc5afe4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2205 | Mandatory testing | CB6
d97a6e4e-8687-4c44-aa77-987d61b19007 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206
a0b5de15-5c65-486d-ab29-7622b6230286 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Leadins
de483f32-b7eb-4a6d-984d-d4357dbf05f8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Roughin
b0adf6c0-0dfb-4f3b-9278-461204d36e4b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Cut out
7b731027-d6c1-41e5-b577-5fb71f2575c6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Fit off
5c372f4d-c4f6-4d72-b6d9-82c4ddd5cc14 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Commissioning
11ae3640-6f9a-4d29-bce4-0f528986b5d7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing
4312eaa2-8cd9-461a-828f-7522cf5a52a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB1
7150b2c6-c867-44b9-b2c2-68b1af409df4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB2
5b57e788-7e3d-4d0e-bde1-fb65240ce027 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB3
8892432d-fb60-4bfd-be86-b3e2da04b0c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB4
8a30fb42-6f25-44d2-a46e-13d486e09995 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB5
5e25921b-4b18-4fc2-ae81-8fb4a70da43d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2206 | Mandatory testing | CB6
efc772a5-1ff3-43fd-9cdb-97820f91eaa7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207
5fff74ab-2005-409e-a45c-36c07da5f231 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Leadins
2db0bf22-1764-4231-8cb9-9916a63f3608 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Roughin
d092f7f2-cc9a-4130-8e18-48100ef7000e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Cut out
df813665-2b46-4bd2-b349-5765791a7ce4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Fit off
d410e927-31ec-438a-9b43-0c53d86a95c7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Commissioning
9fbc2951-e1b0-449c-87b2-9a4a425dbfd8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing
5de56390-3ccc-4569-84e7-4c74dc328af2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB1
b5cf82c6-c9f7-4ea7-ad1b-6b216e1dbf21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB2
cbcf276e-62ea-4fa0-aa33-e92e302845b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB3
ac8d7d31-130e-41e7-ac37-71d416a5b895 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB4
7506b2d2-370d-49d8-ad0f-37dd92734e16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB5
4ac8dcd3-d747-449e-839a-e0de927d08d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2207 | Mandatory testing | CB6
2fa22d1a-1d3f-4362-a24d-1d3163a7d31c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208
b4398a2d-6789-48fc-9a29-1a387cf57e14 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Leadins
1500cae1-c438-4f0e-bab6-154af09ca173 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Roughin
6ca26f04-55be-4d8d-8021-6644ff6e82e9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Cut out
5c85fffd-edbb-43e1-b18f-b1ac6f1e89b3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Fit off
fed0bca5-10dc-4b5e-9695-109e12b3eb87 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Commissioning
ddd799f0-f35d-4562-af93-6071f2189d25 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing
4cf8847f-e5a6-4aec-8893-97fe97b081f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB1
cbbf6afb-5d08-4cc1-bd0c-2572befc0a6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB2
e8fb6d6e-3b50-48a2-b4da-ccb419d25595 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB3
3922eb90-8da1-4d50-ad94-4fc6abc16712 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB4
2e5a1db1-c9c4-4221-a81e-2614b0dc740c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB5
99dc32a7-6a86-4760-98ea-7c8904d9699b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2208 | Mandatory testing | CB6
6871f19c-e412-4765-949d-0614035b8f78 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209
09a5a03e-41df-4f5a-9d97-97b00edf0d4c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Leadins
3121e885-ce4c-46e3-a836-53cedb49827f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Roughin
88eb42b5-8cc9-426f-87fa-25fb608eacbd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Cut out
3b54ec24-d815-4373-9452-e6e3d9ac37c6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Fit off
4856b6eb-59a0-46e5-821e-d9a080d4ab97 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Commissioning
e9cbcd28-bfb9-46c1-9ff2-e60df560e23b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing
49badd72-3968-4dd6-85b9-a81e848c3c25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB1
7825a354-f519-42f7-9462-a062b9b8b446 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB2
840a9ff5-3af9-477c-87ab-9c8e18025da5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB3
7e602cbc-cbaf-4ed8-8953-43225da12281 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB4
bffc773d-4759-4b53-b4b8-f3bfa418014c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB5
b264934d-bf02-46af-b45c-87f08f09b9cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2209 | Mandatory testing | CB6
83ef5a1b-c955-4a16-ae0a-175c4368ff01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210
bb0cd871-a6e2-4428-be3f-234dc3f485a7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Leadins
8da3be43-7c82-4d62-ad39-90f74dcbdb3d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Roughin
d7f44cb0-3c04-4fbe-918e-91d6b305b898 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Cut out
e25ff77b-f4fd-4601-8138-594fd2975e9d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Fit off
1ff5b5b7-0bc7-4306-a3f0-4de6784fa3d4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Commissioning
3a19d54c-4dc0-42b9-b7e1-f5d07575c183 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing
b6014200-082b-407c-8a89-9b1fbbe50271 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB1
5b06b29b-94cd-4157-8b19-efb1ae2a00b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB2
7f82c1c8-efbe-4a64-86b5-f218e5cf1f95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB3
ab254dde-0f29-466e-9303-a3239453ad6b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB4
aa4c4997-bd11-4fbc-bf5e-9bcc4fcbe5fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB5
ae84eb9e-ec58-444f-be04-b9bc9f24590d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2210 | Mandatory testing | CB6
33d10b68-17d0-46b7-8b8a-bb0c6a696814 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211
27e1f7c6-371c-4379-b085-1d8fc6e6d42f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Leadins
8326506c-ff37-432b-b183-fa28600a60e6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Roughin
000b1722-2730-4071-bf2a-a3e001658fa7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Cut out
254b97e8-7793-4d8f-9c4a-9b4d9ee3aff1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Fit off
2248ed55-7410-40f8-8875-9bcbe1b962a0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Commissioning
9b520747-d30c-436f-93ad-005fde04f248 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing
aeedbdd3-d5e2-47dc-9e34-9aa076eaf22b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB1
f3c365cf-fe13-4071-aea9-89a95f6b1216 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB2
a85f6fcb-b85e-49f0-9fd6-54602fe13f00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB3
30fddb06-dea1-4353-804a-53c339d00ff2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB4
32c1a155-77a2-4f1b-9ac6-fcf94be80e8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB5
47c8a5ee-e0df-4b16-a3a3-bdffc4218d1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2211 | Mandatory testing | CB6
2e0e04b2-f298-4004-b02c-c26fa470660b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212
bd2c66c5-b9ec-4e00-9f64-26bfe9f6f9e6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Leadins
47dab1de-28f0-49e1-a99d-d5390c70ecad |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Roughin
e1dfab0c-e6ae-4a22-8cef-d2629e1400cf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Cut out
0d953a24-d8f6-47cc-96f3-c8a542bfd71d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Fit off
bbad8c35-edbb-47bd-af69-df6bb42bb133 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Commissioning
69eba297-2a3d-423e-a294-438fa9105cc8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing
97313392-5b8f-40c5-ba95-cb95ac4950af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB1
f8f77ab4-882b-409f-a89f-922e8a308442 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB2
8bb63a96-ac2b-4074-a03c-062e29b7cd6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB3
be43e372-b871-46b5-8190-1a13e2db72cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB4
21153d86-053f-4ac5-a0ae-dd41ea9b3342 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB5
1e7c09de-a863-4b9a-bf88-181edc0252b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2212 | Mandatory testing | CB6
94758d55-0a66-4eaf-a0d6-d738b9d67a6c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213
b2f23320-5770-4c92-9259-d869a93cb057 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Leadins
2c1b89a0-b590-4df4-b503-553d0beb9e37 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Roughin
a60f8b63-3df4-4c90-bca3-fd2a50fc850a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Cut out
3425bb90-cf03-4ca4-9bf7-061a7a414f6c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Fit off
0ed5cd20-9a3f-4492-a474-8b9a54243ec5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Commissioning
b2c1950c-48aa-4e09-9778-a86e74bcd471 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing
323fcdb7-0508-4274-9334-8d8a7c5f0094 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB1
d27f3798-ff47-478e-befd-cddc5b91ebc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB2
30c7aa65-2bd9-47bc-b496-7f76c2d150d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB3
8b186f3f-925e-4064-9722-7654204dcfec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB4
adc7e440-bb65-4e7e-a496-112a45738140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB5
e788b503-b416-4c83-8afe-6556150d1f5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 22 | Apartment 2213 | Mandatory testing | CB6
7b704869-36d2-470f-a5c1-270b91e6c7fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23
3b64d8b0-bc2f-4eaa-8d7c-09bbf080c95b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301
a1efce69-b465-4a78-aad4-0120a533b222 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Leadins
98657133-c56c-426e-86bc-03a680ec4caf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Roughin
808376ac-0851-4b0f-8382-7221804720d8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Cut out
477bf3ec-0c91-4ae9-b7ae-d86f879878d1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Fit off
bb547d2b-e916-4fbe-be81-09aeef6f4c5d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Commissioning
35f6690c-91d7-46be-aee1-ca500e916dfa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing
5fd200fd-414a-4df0-98b8-a8df764adbf9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB1
81738fde-4f01-40e4-9386-7d1f96cae358 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB2
6948441b-672b-4771-a458-8e18ef99fa0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB3
887efeb0-aa2d-477c-bd04-a7a996635c18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB4
63c202d4-0df5-4310-94a3-3f96a5da8092 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB5
ed4f6cbc-fb24-44d3-9c4e-ebcb81f563a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2301 | Mandatory testing | CB6
96e1fd74-3b1e-4e07-8574-00f4d3e2b1ef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302
1cbd599d-a775-45c9-bb21-a98b6efa9197 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Leadins
eb47c18c-d88f-47d8-8c2e-730f127521f4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Roughin
1d3a81f7-b27f-46a4-abb6-20254dd13696 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Cut out
2b99d131-0cbd-45c3-9ceb-9c4dc3e71bbc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Fit off
b7bdfa22-c003-4e3e-8b6a-4757fbcd8579 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Commissioning
cd1f402a-6c8d-4bd3-90e0-389d29e234dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing
e262a25d-5d53-45f4-9e4c-af6da22a0ca4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB1
01194dfc-ef40-477f-933b-a1fba70259e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB2
e57ba7db-39ed-4652-bca7-fb0f161db571 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB3
35b96e20-d3a8-4e08-8e02-55d5d5ae183c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB4
c39259a3-964e-477d-b6f5-871c990a5d15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB5
12cb02b1-c99a-4f70-9caf-c4773ff4eb5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2302 | Mandatory testing | CB6
36906441-7d35-44b1-b21e-e0f1d2b24a82 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303
60bb57e1-85a8-41f3-b0bc-4a552055fcab |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Leadins
2332692e-fe81-4d4c-8dd1-143c5391e4e7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Roughin
02589c37-ce9c-4289-b6ff-26205996467c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Cut out
d5b5c83b-02d9-4573-beff-379c8c85d313 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Fit off
c98a91b9-0653-45d2-8455-3fc915b7c058 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Commissioning
0e339235-9389-4ac9-9b38-06d7a3413ea7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing
920ef3fc-a970-4925-97ac-c64b4126dac5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB1
392f0f48-d3c2-447f-bb89-800941c600d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB2
dda73c3d-0107-4298-bb8f-f188d1cd07fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB3
f2d088f6-5786-4ccd-98e2-394c7608271c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB4
aa107b84-c986-4f34-a43b-0900f39128fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB5
677281ad-8e77-47bd-b86f-db0cf3e65727 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2303 | Mandatory testing | CB6
996fe333-e657-4d5c-bcad-1a1c45c239eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304
12df1adb-cfa8-4253-acdf-dec57bf47788 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Leadins
f250f623-02e3-42ab-80b9-b51cc4f7ae9e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Roughin
e7512a94-ecbe-4d9e-8d2d-2dde66f03cf5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Cut out
be8b2d1e-9896-4ea7-b329-790734c9d431 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Fit off
0b80f869-33d5-40d6-be9b-6ec427409e3f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Commissioning
bc9a0163-d4ff-4e7a-b1a8-fad95712cb44 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing
37160b2a-6b4a-434c-80a0-4a5577633e5b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB1
489d7509-37ab-48ca-95eb-fbffeb307e27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB2
0096ef90-a8b0-4ee6-9e1f-9ea66db9e7f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB3
89865a36-f5d6-49c2-bde5-b4864b42af9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB4
b6a5d3a4-c513-4719-9769-83ed60a1e15e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB5
eccf6160-3cd0-439b-badd-06b0680e04a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2304 | Mandatory testing | CB6
31ace8c8-e980-4eec-a2c0-b2562d456b1b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305
e9ec29c8-1114-431b-9403-c48e64f1358e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Leadins
9300954f-51d3-446a-9147-8fa39fd1da34 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Roughin
d63ed45b-5193-439b-98db-564475cacec8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Cut out
0bc072b5-4213-4d52-8764-9c6f938836ec |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Fit off
82e6d696-1454-4393-b559-fe023bb39ad5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Commissioning
e93b9a5f-cfc2-4475-b02b-370655401fe4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing
ef9ca110-a134-4ca9-80d9-c0189f018572 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB1
683be6d4-fc1b-4fac-9877-31256a1ca6e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB2
5ac32fd1-63b4-4f72-9f86-652e0df1c917 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB3
98b9a113-449f-4772-bc16-2b0c102b3fbc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB4
7cae9e76-4606-4615-8044-83f9744f71e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB5
f414f08d-e726-474a-8720-db5cc8a393e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2305 | Mandatory testing | CB6
e5e11287-8d5b-4054-9cab-70fc3d63e025 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306
665b9647-44eb-44c6-8167-18603e240fbc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Leadins
6ca6449b-6585-4c6b-a095-8bd15a68d44e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Roughin
7d19f4a6-d627-4f92-87ec-0b97838d611a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Cut out
76f7760e-4043-4317-8f70-84a785d0155d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Fit off
89b13644-0bbe-4a3a-8742-030429cf2500 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Commissioning
b546f38b-df23-4e12-bd5c-9e68900905b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing
4509d303-2ea8-468c-9052-e44fd1101ff0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB1
0915fa49-a832-46b9-ae59-ab37f5a1cf88 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB2
7f22281b-9748-4e0f-bc56-4fad1dc87a2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB3
6a71d4c4-d29c-41e8-9ca1-c1e6de54e6e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB4
7b38a3b1-029b-4de3-825e-3b908ae9d617 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB5
5c4173e9-0dea-48db-ac4e-de26e5fc0ff7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2306 | Mandatory testing | CB6
bfca7d77-d95c-441f-8fe9-ce96ce4f2ec3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307
b7d9e0fb-3e70-40c0-b92d-7f531d9aaefe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Leadins
a83220fe-082b-4d16-88de-69d06d2a273c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Roughin
f6d410da-cace-4b1e-a142-58d02615e749 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Cut out
40c6a2f8-7666-4dce-b324-06c8a6c8b090 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Fit off
a93913b8-46f6-40cd-9b66-175206f94d6a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Commissioning
b6b07db6-9a86-4408-8b01-56f4a5d652d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing
b457f799-f1aa-45c5-9b54-de2fdee31a09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB1
fb3990f4-c05b-4036-b799-a2b45fed7d64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB2
be6114f4-6636-4215-a701-4bab2bc94db3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB3
d17310ea-ddf5-4dc1-95ac-7d6f2686618b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB4
eceb9e81-c910-4b22-80e4-147b62477e59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB5
24d240fa-6fdc-443a-8040-f8287994370e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2307 | Mandatory testing | CB6
7a024aba-f3c1-44ae-825c-bbfdac9778e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308
82736112-4815-44ff-b176-44d22d8f7e60 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Leadins
a37aa58f-7dca-488f-aaf6-f82153f3fcca |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Roughin
72021144-5062-4b0c-809e-443a34da1ea7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Cut out
b56b29ef-d927-4abb-aa3b-6f331f696c3b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Fit off
c7e49c07-b34a-4c1a-ac9c-58c098fb0be8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Commissioning
7bd3d180-c672-45bf-9e24-1639c227fc53 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing
faab6a7b-216f-49e2-a0b4-432f8f6f6bcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB1
d1608d73-118c-4d95-b9e8-cc65ea806c3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB2
b4e483b9-7be2-4033-9cc3-750d1c763187 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB3
47c0d3b5-72ca-4ced-bc38-9d5f06ae6767 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB4
3753d9f7-d1b6-47a7-b689-fccfd5f1934d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB5
2d605f1e-6365-4023-8318-8e63aa9a36a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2308 | Mandatory testing | CB6
04335f7c-0555-4d00-893e-035bca8510e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309
135fd496-bba6-4b6a-b8fe-3061f61fb670 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Leadins
7d53620c-baaa-4135-a1ad-e8138cadd12b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Roughin
adb553ea-12ca-461e-aae8-33b5b3f60cfd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Cut out
673d439f-3e18-496e-a6a0-2d5c00dc6476 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Fit off
95910698-2cc2-4206-9ad7-b18b065c5bc1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Commissioning
1000f4c5-eb55-47ae-95a9-aecb46d2167a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing
bc42f971-f711-426c-aa7f-4bf88d0f94b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB1
85eea6e6-89c5-4e5c-8feb-7f2fc3429dc8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB2
017506eb-4e65-4e76-b5f7-4d6aed57fd22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB3
1483a8ea-fb81-4bc1-acd6-987c0599dc6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB4
8aca28bc-ed06-403e-8e97-20cfa40c6874 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB5
ced33da0-076a-42d9-a0ee-cc57ae90fe3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2309 | Mandatory testing | CB6
c9eade38-85dc-4ffa-846f-f4e75439cf74 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310
b36258dc-88f6-446a-86b6-e0a3859b87b8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Leadins
073c6f48-87ff-40da-b2c7-49b95c1b430e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Roughin
6c7df334-a16b-4912-8061-6c771ee51ed4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Cut out
76d45108-f0fd-4f07-bf0f-63898725f1cc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Fit off
0ef3fe98-dcbf-4a2d-924b-53f1bac31d8f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Commissioning
2221f25c-9316-46ff-a5b1-2ff205435c60 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing
08e9bc66-3e24-442c-96e1-ca390d3e0415 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB1
a5fb6148-1a05-4adc-ab48-26bdfc27cfba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB2
3171d108-e20c-41ac-ac8d-6936686461e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB3
01fb082a-4f51-4c21-a2bb-9c926405b6d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB4
a3c289d3-1aec-4ad7-a755-3c2c8bf2a8ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB5
d6e33fe7-61cf-4a08-97b6-1c89a9a3e005 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2310 | Mandatory testing | CB6
8a2c7229-28ac-40fe-a737-d66878e680ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311
fd5d0bf8-81d1-4751-8fa6-bdf8192a85bb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Leadins
599c25fb-0f02-4b3c-9614-5c4bb2de6557 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Roughin
afde7da2-908a-4732-9b1f-eed4729f09a5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Cut out
2cf3616a-7701-4191-81ba-631ce6485f6b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Fit off
ac48f35b-0162-4d9a-8e9b-f83b4e049252 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Commissioning
1b25576d-0dea-475e-8a31-3990bcac830c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing
e670d2e9-9c0a-4499-b778-838733053279 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB1
444036db-add7-4bde-95ae-9626954f8540 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB2
0da30870-e251-4472-becf-55fa6fd76591 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB3
63c9939c-34c5-4ffd-91a6-276fc5455a4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB4
27f05606-758b-45c7-bd02-a719f95752f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB5
74e22bcf-b519-4801-8c50-0e7776ffcea4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2311 | Mandatory testing | CB6
9c12321b-f6d0-454c-8588-4432b24063f4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312
6e2c2fa5-8d6c-4a7e-b5b3-fd56daba5538 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Leadins
24d1bc93-547f-497b-a5b1-a1a42e56004d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Roughin
fcbd321e-f6cb-43e8-a7c7-a5e6a0634eb7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Cut out
e72b07fc-d27a-4c3a-bcfb-a70590c8eebd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Fit off
42f7ef8f-f1bf-4867-9bde-02ede8100f08 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Commissioning
c14ee094-18a2-408d-a98f-2f731f44ac8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing
b2f441f0-8d00-4177-b4a8-c3d5f43e4afd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB1
d5e00f49-3524-4c37-8e2d-e050ba190cb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB2
3d40671c-5343-480e-8ca3-1ee60c1ef9cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB3
e09240ea-970b-48cf-b87b-b6985cecc19b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB4
80447341-f527-448a-8c30-dd214fa4ee35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB5
1ff3c9b8-f507-4808-bdb9-a637b9bfe37b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2312 | Mandatory testing | CB6
bf7ec216-29b7-4adc-bd8c-289f48456b39 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313
3c8b9cc0-af7b-4ca3-b209-fe124f8b6380 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Leadins
e7a69600-eba2-4bc5-88b2-5f07eb5bec85 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Roughin
9c11c4f7-93a8-4613-a561-6ef11ce95998 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Cut out
3e8846c1-48bc-44a1-8cdf-c1ba710043f6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Fit off
5ff66613-7142-4bf9-9470-e33e520729a4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Commissioning
1bae21fa-5062-4df7-9edd-c38caf104055 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing
ca17370c-c9d7-42d3-9c92-c0e3109de021 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB1
5423f2f1-e264-4196-a58c-8a59f78efbea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB2
842a2377-2fcf-46f0-a9d5-f18e96014eda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB3
5a0ced0c-95f4-49aa-81ea-e9be7c84f345 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB4
b7d93a67-0992-4f77-8e61-5944d771634e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB5
91745d85-e3be-4c8f-b9b6-fccf5567df83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 23 | Apartment 2313 | Mandatory testing | CB6
a5227660-2b8c-441a-a070-e08a34faefbd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24
a5aa424b-7b29-4397-a545-69e46da661ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401
9b524067-6f56-4256-b41f-5712291c5bb4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Leadins
debab2ab-8654-4fee-8c49-75a4c866f8f1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Roughin
b2f9838f-5f40-45ec-b994-0620c68eda59 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Cut out
c8768275-24e1-462e-8cfc-3cc9acf06961 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Fit off
8bb4fba5-bea7-450d-902a-acf4ad2dbb5c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Commissioning
455f8336-304b-4725-862d-3d2ab3d8fbdc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing
d638a228-51bd-4594-bb4a-5b987c46a9f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB1
a21bf161-2f75-4875-b861-af7dd220a4df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB2
e0ab2b5c-8c1b-4183-9229-39d6040eaba6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB3
3cd4000f-f0ec-4bc1-adbe-abe5ef7e9544 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB4
3667fb8e-8aa2-4cf1-a1cb-f82ab1dfb1d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB5
105e9d24-f7ad-420e-b013-031feddfc63b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2401 | Mandatory testing | CB6
499e8385-0e22-4ee2-8065-6ec51970b7bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402
b25f60e9-533c-4b6b-bfa2-b25d220ac21f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Leadins
d7dfa3cd-0070-4c2f-8f50-9da6ccc9d700 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Roughin
b1dd69e7-a26b-4ff8-9726-88a291722532 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Cut out
fc972e21-5162-4d98-bd89-4d071d812cfa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Fit off
5e23a9f9-8ec4-45b7-a6d8-543488411c97 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Commissioning
6045cba7-1409-4c6d-b1c4-28b80be70058 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing
e4250496-1bc5-445a-893e-8e982319016b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB1
fa5411f0-d6ac-4de7-b204-b3a6a383942d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB2
55476ee9-d567-4e70-aee7-649e31311070 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB3
0af9fe14-fe52-4e48-8dc1-4e9436e836a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB4
cba10e4c-bb8d-4ab0-8590-cfb82c023fae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB5
c8cde15f-cd83-49a2-8be0-5abfa4427ef0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2402 | Mandatory testing | CB6
acdb77b1-701a-48e4-98c1-d7032e435cb7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403
a0e45a5f-ae71-4b6c-a580-50cd932d0af7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Leadins
2576bbb4-bcbe-4173-adea-03e52fc9f5ae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Roughin
c75d2aca-90ad-4842-9cc5-987fd8754b7a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Cut out
cc8e35d5-0926-4300-83d2-b222dfc74499 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Fit off
99833e70-cc7d-41ae-ab2b-fdbb497c63fb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Commissioning
4e1f64fd-aa7b-4e75-9afa-854889aa4a1b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing
f073a9a6-9194-490c-93f5-2bccad21b8ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB1
2bfae656-f64c-45a3-961c-fca09c2576e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB2
7f471c20-6cfd-478d-97dd-4c8ab0cb6ac6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB3
5af8a0ed-a98b-466a-bf5b-29d0a8823eaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB4
c4211d43-9da3-4ca1-8c51-bfac787cb991 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB5
3aa85be3-24fd-45ec-832c-be14d0487f90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2403 | Mandatory testing | CB6
ba894bcf-3ec7-4246-b4f8-e9fa9d78c3bb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404
135e425f-a304-4b33-9182-c796f2a281fd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Leadins
c766ed20-1a49-4787-89a7-9bdae4cd5c84 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Roughin
7aa0c0b8-673c-45ac-804b-fb8e2ded99d9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Cut out
5c77ff2d-468f-48a0-b912-e3a7524474d6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Fit off
aca33a65-fe63-4e99-9613-109ec857328a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Commissioning
2a9776ae-99e7-45ac-a476-88f025c9b53c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing
2c66fe82-d9ac-492c-b81d-f0328b984b24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB1
df82be90-7707-42db-a329-65954857a495 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB2
2891eed1-21fb-42e0-ae62-5a22e7b1b6de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB3
311c35f6-c791-4cbf-9ef2-471fc2f217bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB4
b2e43ccc-2d87-495a-8f7f-04b445c1af3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB5
6ed754d6-4cdd-463a-8c6a-7b2e1c55e76f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2404 | Mandatory testing | CB6
fec82d16-1035-49f0-adc6-5e3e672a280e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405
a6d4c047-733a-467d-a776-39507f00bc29 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Leadins
92910b0d-6033-41c6-ac26-5f2242cbabdd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Roughin
579636cb-5e86-47ee-aca7-a16da851f9e4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Cut out
10bacdd2-66c5-4d91-ae88-5e7ba7c98e3f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Fit off
4da5dd60-e6f8-4050-a70d-c100520a350e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Commissioning
aad99bbe-2391-4d3b-a312-6d2103865895 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing
744a250a-6e26-44a2-a71e-67f1b9959a92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB1
1923ed5b-8726-4360-a3de-7edb85479bf6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB2
bf99897e-d38f-4cb8-834e-2097c484508e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB3
0857b6ac-c9de-439d-ada1-b13c183d6ad2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB4
1f899deb-d6b7-433e-9cd3-55dc8cadb77d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB5
1be361da-5cb0-436b-a960-02dc17361fac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2405 | Mandatory testing | CB6
5b692ccb-55c9-4fc4-b91a-04668a993c56 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406
8b8a2fcc-a7ab-4447-954a-3d655b5b683d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Leadins
e6634a57-d563-4104-8264-3303fdc24e34 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Roughin
f976cd81-ef8f-44df-ac5c-2319a887d38e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Cut out
52e000a2-ffa3-4abf-a3e6-4265827260a8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Fit off
52bbbbd1-23a3-49b4-a714-2cc7263453b4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Commissioning
7afc054d-0914-434c-a441-c445a4b054c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing
0866b7d6-08f7-48b4-8f37-812c794b2e53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB1
ad1fd7ff-8bb8-43da-9aee-301baa738acb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB2
15729500-c47e-4c3b-b2dd-264ca6163cbe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB3
6be12d94-4910-4ba6-904e-5bd45a28d02b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB4
3a5babb5-b464-4466-b2ee-f4a3d55281e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB5
eb83904c-e409-47cc-b697-0f7309526808 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2406 | Mandatory testing | CB6
4f6fcfde-2c0c-4c27-a36a-53f77697a796 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407
544cead8-8ff2-473f-88f1-dc4e29edfe4d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Leadins
2ad988f8-e31e-425a-8fb2-0630d8ff53f3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Roughin
addea2db-c648-4030-8f5b-1b6b3532b2e5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Cut out
adb54bc1-54e4-4ae6-a82d-4b43c933dc55 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Fit off
187ab8f3-94eb-4495-b0f1-01a8aa0e1eb6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Commissioning
09f66377-6cf7-4a10-b1fa-4c25a078064b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing
2330dbfa-6225-426a-9038-291a50c4144f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB1
085a7d8b-f582-4e65-be75-a8a265696cef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB2
0e506ee2-768f-4e8b-a63d-d7c45cc219fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB3
14bb5bd3-0119-4070-ada0-3e149bb619cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB4
d8145954-4647-47ae-89ef-5ae6606e29c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB5
cbb35c14-b91f-4d42-92bb-4657b514c0d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2407 | Mandatory testing | CB6
0cb9b73b-fe0f-4c9f-97b9-006f7185e7e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408
8c983a9e-3b70-499d-8f4d-b60ee5289522 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Leadins
dde365d2-b842-4cf4-a439-4f775a0422a2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Roughin
d36f32b7-f5f6-48e0-bc1f-345db1a2170b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Cut out
1cbd8fd2-8db7-45ba-ae9a-a24950ac9a5a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Fit off
37e43c44-db92-4034-a075-22d6f9b3e154 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Commissioning
56a68c87-cc7a-4420-8172-29db8919e9cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing
6b7523f6-7213-4e76-90c7-45f1605a7941 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB1
87dae04e-38db-44f4-b8d4-d7e4c1bb2d80 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB2
b4d667e7-5195-4941-879c-ac6b1d853ab8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB3
5a3fd3a0-03c8-458d-bafc-ecdb3aa29ead |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB4
7e0ce647-9c0f-4c40-92c2-fff4be370001 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB5
108daebb-80a9-4c94-b8b9-e4a3f71e8ea2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2408 | Mandatory testing | CB6
77aca0c2-28fb-4348-9ec4-130e7054d78c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409
f3754c27-4599-43ff-baee-f0623b414bf1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Leadins
ab96eaf2-48ea-4f95-9caf-e9a873802026 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Roughin
99640a75-9ea5-449d-bd56-5960cb8ff74c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Cut out
ef7ba2af-c50a-46ca-ac18-c3aee77cdc1f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Fit off
2e2f81c9-f36a-437f-8489-29152e8428fa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Commissioning
838f9239-dd89-423c-bfdb-a922c914f2ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing
f35387a8-df90-438c-b6bd-ca1586b426dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB1
69853aff-238f-4f58-995c-b6bd058fec65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB2
1c6df7e8-6e34-4d3d-8465-eb4ca340a1f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB3
b36c2205-fc88-4938-b53a-bf7b7934c8a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB4
4436c82f-7ecb-4ba9-8941-5a006f97f923 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB5
31517547-2c09-412c-93a0-eede100596f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2409 | Mandatory testing | CB6
fff0b414-9a7c-4c3e-bbcb-0eb959d650e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410
8da40b10-8661-4b21-9652-3402ee15d42c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Leadins
659ffec9-c443-4063-ac29-08f4cf7a5bce |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Roughin
72463d6c-a574-479d-9b8c-ef4b3ad89200 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Cut out
583dd33c-07b0-4b51-b62e-665f9f05b753 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Fit off
cd9d1670-304e-4415-a781-a5635120faa7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Commissioning
0d5b2b1c-5a86-4e13-9f61-eb3ced485dda |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing
f68a92fb-771d-4369-9367-778bcc0ed4f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB1
7476fa54-d650-4bea-b4b7-10f34a5c3d4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB2
0f82f1f5-b45e-4e04-86d2-be836638c515 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB3
bc0ac679-537b-412d-9d43-d9804b15a474 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB4
96b59ba4-9067-42dd-8481-03dd1a07abab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB5
56212af6-ee2c-43ed-b195-44e00a8842ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2410 | Mandatory testing | CB6
b8a764df-2ae5-4930-af9b-5cd20b3d3e87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411
7f099a17-b9f8-4f53-8416-bc3e0521701c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Leadins
5131694f-2059-413f-8f7f-c67d923a4806 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Roughin
09a1a026-3cb8-4eef-9128-46de52bb220f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Cut out
8bed5fb0-a269-42a4-8da6-095b5734a4eb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Fit off
0af2604c-6bdb-4860-818e-6d85ab8636ee |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Commissioning
251daa90-14d4-4e01-b27b-55a8e0653c82 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing
bdc72295-ac43-471c-8635-9d7f20bb68a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB1
b38316df-b4f6-4068-aa3f-c5e48859c7be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB2
3e98ad93-1e7f-45bf-8523-e79a38f3b853 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB3
c3cd88bc-cf67-4fce-8c1b-6e2675af15cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB4
62e41441-e3f5-4107-a165-d49442677f7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB5
d32a596d-bb32-4b39-9b1f-a6186e73f570 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2411 | Mandatory testing | CB6
52844d76-a2ca-4027-8d69-47c027189594 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412
0d76e4b6-7dcd-43c3-ad94-91883ad4f647 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Leadins
dc2a2fab-b00a-4ba8-9ffe-3f8026a8fbb3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Roughin
79f5e0f0-efc8-4c5b-8875-0b5885c300ac |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Cut out
b7e0da4d-dc40-4fc9-9e0e-3be93908dd63 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Fit off
f6a587ba-777c-4cab-99a0-3329831e99fd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Commissioning
728a3039-14c5-4688-9529-0a0db8c84bb1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing
c23f3fe1-f2e0-44aa-8ee3-fedf5182522f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB1
6f06679a-19df-478c-b010-006761a8604d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB2
046313fd-1fcc-4adc-aa62-a3c04d822a33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB3
1bf79b64-5ab3-48b8-89e5-681b5f3859a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB4
87224e54-ac1e-409e-8e29-89b5988e41b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB5
7fde4815-526f-40dd-8df3-ea4819272c90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2412 | Mandatory testing | CB6
9b9d9e3a-f8f5-4638-9295-a7ca73834f93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413
1b1f70c9-9dfe-4406-8ce6-2b64c33b7aa9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Leadins
fb338e68-9a75-48cb-9d13-7c81d71754d7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Roughin
891d324f-3f08-4b7e-b82f-3a743eaaa2bc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Cut out
dd48462f-98fb-4298-bfa8-e2acabcbb5ab |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Fit off
3ee900e0-dd95-4b2f-b1a4-9a7055f4b896 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Commissioning
ab221fae-dca4-4864-908f-7a7faa36e1b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing
6d815166-87c2-426d-b344-bba4d9d7f2b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB1
d7db3895-7f88-4354-a4cb-67762360572d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB2
3dbd11a6-2d8a-4569-9a4a-7c948b7365e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB3
d8f7d084-d4b6-45b8-8281-eef788ff0295 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB4
7e20c02d-e294-43cd-b4d5-ecf131fa6941 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB5
c837cbe7-cd3c-4667-b9b7-ff65b4866659 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 24 | Apartment 2413 | Mandatory testing | CB6
e19f5cd7-2ea7-4d9d-be79-33a3c500f921 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25
f0cd2604-d780-4a2c-9cdc-0df285292925 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501
718f299e-c0bc-4e9c-a175-7e7107a43dcb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Leadins
4330d413-148e-456e-ad44-d8e527082973 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Roughin
dd4e2726-936d-4688-bc50-8178a7978951 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Cut out
e6f27e90-9b00-41e0-b26c-45ba611f8d2a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Fit off
79625d8c-c635-4185-add0-3330a9d865d2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Commissioning
4a5a8b1d-3b1c-4256-ba96-539f022de4e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing
0c021aaf-1942-4c1e-af3b-75a8b875e218 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB1
7ed57031-7740-4686-b566-9f6363689040 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB2
e561eab5-8ac9-4c8e-a3a7-f1a325457f71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB3
0046d3fe-e170-475c-a343-17cd4af4703e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB4
37f97c99-d12f-4c4d-8429-e8dc040b197b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB5
b2ad762d-71e2-4f13-ad7d-29cbcaced8a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2501 | Mandatory testing | CB6
a4e81458-d24a-40d2-a608-be13681a600c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502
87833f8c-8a26-4387-9c84-385d9c0ac569 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Leadins
9073d566-5075-4119-96ae-0921598727be |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Roughin
e4caad2e-834e-4753-9118-f3c4b8e6e8a2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Cut out
fe0ba20b-bb7b-4628-b0b2-cfce8d2f0478 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Fit off
fb6bb248-bb2d-40c0-861a-92936e6dbf7b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Commissioning
8d76fa67-558b-44ff-917f-6be6775812dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing
eeaa1e42-cdbc-4373-9602-637b7226e704 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB1
4def2074-7a93-4c7c-8aad-5dc444934e65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB2
c6255dfd-292a-4fe3-8d8a-90e8d50f17d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB3
17d4a1fa-2a95-4aa9-8ad2-c4c49996c33b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB4
1c31251c-1572-4948-ade9-77c065fc0fa5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB5
70af2e17-332d-462e-9acd-72545fa68174 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2502 | Mandatory testing | CB6
86d8021d-246f-46e3-8833-6a4c142c4e12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503
432f9376-e485-4919-9b88-d09e253f1ff7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Leadins
35fdbeca-befe-45aa-af64-3f003f816c2b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Roughin
fc61c9e3-93e4-4cd7-bfb0-c51e456c3bc3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Cut out
04e951d1-272e-4eb9-9ba9-7720a4ac9538 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Fit off
441d5543-3a05-4aca-8dcb-f3e2e41b3b3e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Commissioning
82bca66a-9bb0-48f2-abfa-79431adccd36 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing
105b996e-4f16-4baf-a1a2-d37e0215f4e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB1
348705fe-399e-4c29-ac5d-ced67704d817 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB2
6d69d1cd-e4c3-44b7-abbf-c89fddd76e5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB3
0bcc2dd9-dea6-43e3-981a-0addf96a3383 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB4
3f08dfd6-12c4-4de9-84ec-4a41c96dafd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB5
79d52855-1d86-47f9-a56c-710d96d781c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2503 | Mandatory testing | CB6
6b1f5cfb-27e8-4738-93bc-ac70ca5a6972 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504
8d672e25-27b7-4776-896d-6ab13f2f55ee |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Leadins
fbb7be2e-3e25-4011-80c5-f3d7f0294c04 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Roughin
ddb9b36c-25c6-4892-9078-adf66b4f5ad3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Cut out
0d280ba0-08c2-450e-ab46-14367f01c436 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Fit off
ecf6d93e-5e06-4793-bd92-b50e03aff08a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Commissioning
28a67cd0-6f9a-4121-aca5-e49a0dbcdbbe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing
aa2eefa8-b631-456e-8cad-54d56eb572d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB1
91d0a297-7850-4d47-b6e8-6d94fb46cfad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB2
f99ce236-8795-4fc2-8128-89b28660479a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB3
d6a19e24-43b3-44cc-9515-13c3eb1a863d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB4
8d1318a2-b03e-48f0-aa55-6932a83a6937 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB5
3c49465d-d7f7-4215-ad7f-4c6446c9c160 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2504 | Mandatory testing | CB6
c620f636-ac7e-4055-9599-d35810e3c0fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505
a88f73aa-dc8d-4800-9e30-8c87ddfe66dd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Leadins
1a4cc118-09ed-4644-8233-9be270d7d12b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Roughin
4a1fc8a0-82da-4d5d-ae25-837732e977dc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Cut out
ce739025-0a0b-4b6e-9b4d-21a53e155051 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Fit off
0d69d0e6-5399-436e-9b91-cbd6178866cf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Commissioning
cb526bf2-6b0e-4329-a29b-3f2936c0ae5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing
b9296b49-498b-418a-81e9-a47eb9d72a08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB1
af36934a-cb86-46dd-a00f-db09590607d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB2
7520933a-2d04-4bee-9ac7-56b174378734 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB3
980d66ce-0f81-4752-bf71-f6bbb0cf9dab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB4
20458e16-8bf3-483d-9900-2d5ad7e65791 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB5
cdd5ec59-1052-4ab4-968e-c7333d01d987 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2505 | Mandatory testing | CB6
ed7a83fa-c824-456c-82c2-4935ff06225b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506
d6ac76b4-8086-4921-a260-c082abbe309d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Leadins
e63d3920-3fa8-4826-9e91-0be3e1ba0539 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Roughin
7b2e8d19-3a7e-4d26-8d44-89d428dcb9c6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Cut out
95571c33-b9bf-443d-9b32-d0e74dc56155 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Fit off
8031c291-f38f-416d-87ca-d5b3049920eb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Commissioning
2b327b60-1958-4618-aaf0-a0eaa42f372e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing
be9ac3b3-8a41-49c2-a617-db084fb68964 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB1
c4fd23c0-0796-4682-914e-7ad819d598af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB2
7fbca50f-cf12-4657-be90-d905f46db22b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB3
a3752d81-d83f-477e-bcb2-50108a68751f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB4
c4eadcca-366c-4be1-806f-d97132ca4454 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB5
1b64d81a-a605-4bf2-b5be-e9b72376b603 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2506 | Mandatory testing | CB6
edcbf18c-e2c6-4d2c-b2c5-2f86a832bda7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507
0b578845-8e98-4254-8351-fbe1e8c6cd1e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Leadins
493e4746-c2e6-4ced-b5be-a1dd81d126c2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Roughin
d6cd35bf-05e6-45a7-bcdd-53d681fdebf5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Cut out
b6647f6a-2307-4b30-ad88-6a1d74660f27 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Fit off
f9cb01cb-fa15-47af-a90d-930ed6405810 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Commissioning
051109df-b3ca-43c0-b64d-72e4a9e8cc05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing
d3f36f2c-9809-4d3e-90b9-b7141cea4d5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB1
4b79827b-1e4c-4d29-9707-7664c5d93cf7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB2
bee504c6-039c-43b5-b9c6-17e016df9427 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB3
8db92b39-4027-489d-995c-81df22871055 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB4
118fd2a4-3d70-4778-adbe-ffee159e451f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB5
76b4964d-67e1-4bc2-a767-e1f8f86954e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2507 | Mandatory testing | CB6
fcca1f4e-82c2-4b91-8e77-c8ff282db099 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508
d28beee4-91ba-4198-a6e0-2c1722f1887f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Leadins
052e7228-e229-40e0-a18b-92025e9c37c5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Roughin
1c90b177-6c05-4b2f-903b-b0d6dcf43e14 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Cut out
be85e5e3-d1fe-4ee4-ab27-addce3e5fbae |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Fit off
22046a08-fb76-479f-99c4-7563f725a276 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Commissioning
07f95cc6-4124-48f4-b69f-6a45a303295a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing
41266a80-3cae-4cd4-b087-6fa18a02fd78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB1
8c5e2a4a-5af9-4185-8e50-fa77c6e4f307 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB2
aa18ebd9-c92f-4abe-a621-439f22c5f4be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB3
ff5cf5df-cf79-4bac-84fd-bea0fc0a4402 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB4
dcaf9f22-219f-4b8e-8557-93e0bee8140a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB5
f9eff7ad-0b3c-4c16-ab5c-6639152db159 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2508 | Mandatory testing | CB6
1e7494ab-e595-4452-bd33-48884aa05b84 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509
9ed1fdaa-cfe1-462e-8eb9-2a28bc8eb7df |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Leadins
d89d1dc8-073e-42fe-a55d-4e8957280e01 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Roughin
08330b97-0404-4a4a-ba1e-2a5907e21b0d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Cut out
805bb578-c697-4ec5-8fa7-dc810da18eea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Fit off
deb95198-3c4d-467b-a329-38a235888a15 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Commissioning
e0a0e445-1e8f-4358-8dc7-d55f1a7e1f12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing
e830790b-9cbd-4547-b3a3-4a9796772d4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB1
6ad16bd5-c0ea-4987-9ce3-8c0ea3a35a41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB2
7048348d-23ac-4924-8f9a-508ec4876f27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB3
6cc4e69d-d9e2-4c99-a330-d0851f7bbdf2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB4
d5a1cf71-8be7-456d-a8b1-9cbebcd54cd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB5
869c9948-c02c-4211-9bb0-e6be44f9b48d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2509 | Mandatory testing | CB6
19525adf-1ab1-44bc-8620-c2f36fb8c84e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510
26a41501-71ca-42c1-b746-98613ed4bffe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Leadins
5e1513ef-3906-4e87-82c4-8e27b096a61a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Roughin
6f490e29-79a4-4af9-8263-1aa623d41616 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Cut out
3550e44b-7bfa-42c0-a87b-1f1ce26aa4cf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Fit off
54d8f5b7-15c6-40fb-9bb3-779bcf794e1f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Commissioning
92490c8e-9419-4f27-b88f-2d51afe456ff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing
4ced4696-d4fd-417d-bb5b-e841e7bf3e81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB1
8db468ab-7d9c-4b6a-9df1-035a54bd533f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB2
4c4111e2-d21a-4e9b-9d4c-e8348ebbbb0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB3
f83b5cee-a7ef-447a-9d3a-078e0e2aeb2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB4
8c7fd480-2093-43bf-8470-7bb3f4119393 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB5
8d691d2b-a5e7-41d9-90df-e372c16e1d42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2510 | Mandatory testing | CB6
52a79b86-2053-4752-b8a1-8db80096eee3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511
eb8fa848-1d37-4082-8677-0f3d624a9019 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Leadins
534b6b3f-01d0-46be-8939-629a78e2c156 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Roughin
9bba2890-a52f-47ed-bf2f-80235dacff37 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Cut out
def99c93-c9bd-4e24-8293-043d7c685a60 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Fit off
11b13aed-9511-4bb9-88ec-02e9af6d42b6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Commissioning
796f0acc-e37a-4135-afe7-641e0965b72c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing
4783fb01-0ca8-4113-8562-39babd25f696 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB1
04ece4e9-da4f-48a1-be1d-1dec39acfc4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB2
681c78de-0d87-42c9-bb13-75a735e5eee5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB3
b0552216-c76c-42cc-837f-ce12de82b511 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB4
ad741ec6-cb3e-4b8b-9b53-7872b4068d2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB5
f5f77a3c-41cf-4bbf-8230-6d37b41c0356 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2511 | Mandatory testing | CB6
a13b8e23-f5a1-423f-80ce-e0ddb9eb6b01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512
c0da4594-80ac-45e9-921b-917d3b4c9ad4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Leadins
2bb908b2-9a9f-474c-97c1-f75ccb8e3903 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Roughin
b3f8d719-6fa4-426e-ae4a-59a8e353aa1a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Cut out
56238412-d7be-432d-ab8c-ac9f79ada1fa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Fit off
6c9fdd0b-516b-429d-8b17-46279691e3ea |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Commissioning
7ffb2792-445b-4f22-9768-aafef996d4a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing
7ea526cc-a70c-4414-bb6d-329162a48786 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB1
2f49ba10-f43e-4242-9a58-6ba30f38baa0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB2
895bafa5-e8b6-40d7-b26f-d946500ac81a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB3
e4601026-ffb7-4643-8ccb-a9e89641ff9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB4
3a98f82c-9bcf-45bf-b2b5-bcbf189a90ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB5
8c566b48-f823-4cd4-9899-5284cf64a000 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2512 | Mandatory testing | CB6
ee175b36-5b73-4d0d-ac87-2ba021c59a3f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513
52c9ec21-35e0-4b9f-9dbe-fa120304198b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Leadins
1a991b31-8bb7-4f16-83ec-3cf6824c1c11 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Roughin
d9e91ef2-7cf2-4370-9961-a678f5ab653e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Cut out
fab6aefe-36f6-47de-bfff-b9717bce150f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Fit off
fdd7283b-f14a-4323-ae1b-e89ea3985455 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Commissioning
9bf5baf6-dba5-4862-a33d-baa4d0ae8264 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing
0425d9b4-a508-48ce-8352-7a17fde5a4ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB1
8eac2fb5-a954-43d2-a450-c59cecc1806b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB2
b3fb6ddc-cf48-4070-9818-232985f0049e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB3
99d5b37c-4ecf-4c39-b97b-9fd8540c9230 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB4
d2c73b4b-1880-4bd4-a1bf-22e390402b2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB5
2b30ed9c-b9e9-482b-8aa9-bffbadda48b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 25 | Apartment 2513 | Mandatory testing | CB6
e4e2592f-9724-4cef-92b2-1a64cc5b7c6e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26
3dd6c2d0-ccf1-46f6-8dfa-56c3f01e6e4f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601
db974e73-5d1c-4394-9e18-5a5906299055 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Leadins
48ea1191-859b-4be7-b5ba-6061684ff978 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Roughin
fba524a7-8f65-4efd-aea9-79c9b58f9195 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Cut out
a87e417f-99ff-4758-b4b3-56228b0f8b2a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Fit off
15026c97-9137-44aa-a7f3-755d61e50e6a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Commissioning
66c87a9c-a25e-4d84-a6e1-8cfae3bd4e19 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing
af4d8519-052d-44c1-9a97-3300831680df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB1
36e58e9f-e1d6-4182-96d4-ef9785e1c501 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB2
9f1c8b45-5507-4653-8d5a-4bcb95e52401 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB3
0240b8ec-1afc-47b8-a3fb-a286e855e53a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB4
8ee92822-a16a-41a2-a1eb-5002e6d8445d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB5
52d3ce7d-f27a-46c5-a4fe-9d22139ebabd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2601 | Mandatory testing | CB6
73f76886-d1a5-4695-b56d-0f4db7b8b2d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602
494b36c8-e7a9-43b6-974e-fc93d271474d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Leadins
1c6d3e05-2286-47c8-94f3-e24453ecd692 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Roughin
7418d37d-1ca2-42b3-8169-75190a9e68c8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Cut out
a910b676-da25-4621-a2ed-b9eedb40c297 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Fit off
380b05b7-d63e-45e2-9ac7-c8d8665988af |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Commissioning
fbee813a-2768-409c-90af-36e208dd0684 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing
317bfb88-7458-432b-9634-15138ee049f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB1
205e1254-9da5-4a9a-8519-8098247641b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB2
fdbebf0a-aef8-4765-b69f-117d09cf7fb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB3
bedaae29-20e9-4c4f-93f5-310f4a6945d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB4
e590b85a-d005-46f2-bfe2-7a59edd22b73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB5
13c693c8-4809-46cf-91f9-7dff1d40cd5c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2602 | Mandatory testing | CB6
5c712cd7-9384-4bbe-931b-1fbb84f6c478 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603
a414ac81-50d5-4a68-8f1b-655f665a034f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Leadins
05f5603b-e611-4cec-987e-48978b834ba8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Roughin
da235833-a9f0-46d2-91bd-1615a6a604ab |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Cut out
6b141e4c-7b6e-4c28-a6ed-9871b0175639 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Fit off
0dc1e923-3777-4130-9fcb-f5f43e83308a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Commissioning
d1f86341-4cc4-4245-9e21-f807c8c8ed86 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing
2212e4c1-600e-492f-8371-8139cf5ab4f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB1
0c775ea2-3fd3-464d-b99b-901e5a5d8e5f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB2
a9128e30-dbc6-4b0e-a28a-e732a514c6cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB3
f73473c6-1be2-4b15-ab52-238b104d21ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB4
12011cfc-e3b4-4387-a48e-abfe1d149d29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB5
7571e619-39c8-4802-b226-40ab188539ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2603 | Mandatory testing | CB6
93052119-665f-4386-aaed-7abc9b3a2100 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604
830bb037-a4d0-4596-a9c3-aaed56d8d04a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Leadins
839806e3-0fce-413b-9c75-15a455b9ffbd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Roughin
2750a48c-c62c-4c18-850a-df78aa5f045b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Cut out
4ce54229-e640-4d6d-a1cc-eb1d571c1e75 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Fit off
8a0bc3f2-f35b-4753-9dea-ae2207ceebc4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Commissioning
91f70619-ec47-42af-84e8-234625ae09db |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing
1bb32a67-4d03-4ee6-acff-5263c07141bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB1
bc567f59-9e9a-43ab-9fe6-6d94da091b6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB2
537d9d98-e0fe-4ce4-8ae7-557bcbcaf5f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB3
50abb466-7b1b-477c-a997-9d52dc89ed19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB4
5d79ce20-5e1c-4211-808b-d6700a5702bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB5
a55bc801-e6fa-4842-8034-42edabc6b6fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2604 | Mandatory testing | CB6
0d845ab0-8c5e-4368-a82f-c19682f60eb5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605
d7a1d300-7cd1-4b6c-a0cc-11909d397236 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Leadins
f93fda43-f53a-4f65-b37b-6c139a3aafd5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Roughin
4cbe5c31-c621-43f0-bc43-3df11a1d12ae |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Cut out
1c5af61b-7b9a-452e-ba90-ffd4e1d4458a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Fit off
9d99b883-e812-4f98-81a9-87ebf048160e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Commissioning
f5598013-96ad-45bb-8db5-fcd7e486836f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing
f5c989c4-bb70-49cb-a523-c09a1100bba7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB1
a3937147-1942-43b8-b074-3a31c2d13615 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB2
4aa60fd1-70e9-4620-90e4-7083e0220591 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB3
a37c17ee-719e-4ba4-b277-0cb1b92c0eb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB4
856ef371-6caf-4408-9635-5fcf3676c20e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB5
b9c94b3c-104f-4e85-8d95-8bc05de067ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2605 | Mandatory testing | CB6
8267b3d3-03ad-4bbe-aca5-72f922876549 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606
193d028d-57c5-4b44-a79c-72a818a778be |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Leadins
3190d49c-e60b-4b64-96bd-f270ecda2681 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Roughin
f18838bb-5309-4297-ab7b-540810671fc8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Cut out
2f078106-861b-4163-8ffc-a41a06316aa9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Fit off
2f6943e9-63d4-4235-91a0-625dad8d5220 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Commissioning
bb30f88f-4e53-4aa1-9b5e-6d10ace4e640 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing
c6b2aae0-86b2-4950-b9c9-c8a80f46fb87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB1
967543b3-3c84-4c18-8199-cf9938da1140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB2
723d1775-ff58-4dc1-a0fa-9fea0f924dcf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB3
69914318-68da-4270-a669-4f66a4ec08e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB4
e57f3168-10ff-4e18-aeb0-725fb6c4e3ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB5
2e822001-23b4-4edf-951a-c83b29827d92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2606 | Mandatory testing | CB6
046ddec1-c358-4149-b34b-8dc37368d6e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607
268ff755-bd81-43ee-81db-a82871a5e59b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Leadins
b18fe36c-c157-4e50-baaf-da31a7c6bd44 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Roughin
001a7b00-a12e-41c7-a6d2-dbd18e5d1e9e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Cut out
02a1bfa8-9649-4250-b9a5-017c52dbfcf3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Fit off
3b3ff188-583e-4f3a-8fb0-8b680332165b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Commissioning
61359b0d-eafc-49f1-8eac-60e2774da441 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing
5d13e9a5-a404-4231-a345-be196cb9e228 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB1
e73aa2da-8d26-40a3-9dc9-b4137c9c9bd0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB2
d47e9663-6fba-4674-a080-a2640cc9ac70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB3
037b0e31-1cec-4e50-a8b5-55b8db8d048f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB4
1d88790c-1cea-474b-972a-fcc4141837f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB5
e88b0e3e-4eb0-476c-8540-e2deea588b2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2607 | Mandatory testing | CB6
e3a9d3fd-e9a6-4a6e-9dff-142263d5830d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608
a5f7d8ad-4fbb-42b6-8685-152318e7cabf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Leadins
51c933bc-1937-4149-84d3-d5ce7ede422a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Roughin
f54c93ef-d500-44bd-a7c8-18742bbf8989 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Cut out
31235859-56e9-4dec-bda1-aa56135578f0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Fit off
5e32d372-a91b-4448-889b-36d78bf66795 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Commissioning
adee2a3b-64c4-4302-bbf7-1d78e93fe769 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing
b93a69a4-0a10-4401-8fd1-971da0350575 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB1
cc186d57-e85b-4e24-bef8-11db0b1c5d38 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB2
ac16142a-f834-407b-bb94-cb894ccbe9d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB3
c1a06b6d-c085-4f21-8344-92bde574d8ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB4
1d3c1505-2db8-4b46-a2e0-5260bd420f65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB5
ccba4ffc-2c26-4a3a-bc0b-b793a4b494fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2608 | Mandatory testing | CB6
7e46a3de-3d8c-4fb6-97fd-aaccff5bcd81 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609
6331b43a-7c7a-4c28-ad95-ce32c3197208 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Leadins
f02a4af5-92e3-4a9f-838a-630ee435fa8d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Roughin
e646c4af-b77e-47d4-a24a-cc32929e5c31 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Cut out
1cd9f81b-08f1-4f27-ba63-61c4adf7ae60 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Fit off
d125f3d9-984f-4d2a-9f3c-49e35b5e85d1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Commissioning
7a5fef63-8b4f-40eb-ab12-6b40d6a13100 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing
62a1f98f-94fb-4023-882e-81d7debd0647 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB1
ba6ee102-64b7-446e-a276-25a1a334da1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB2
daf1b561-9952-47e2-824c-cc3c2d9f2b90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB3
7650bf49-2429-4b20-8ee0-c42e0a5c33c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB4
d9b23f22-3d0e-4c79-9653-58c47d1d5bdb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB5
6cf8521b-421e-4981-8864-84fb433ca4cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2609 | Mandatory testing | CB6
f72d4f15-00d1-41ef-8417-bb32e5abe116 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610
94a8917f-b851-4274-a456-fd6ed63b5799 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Leadins
33d1b6b7-a16d-4b42-a563-95f6c5bc4884 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Roughin
4d3aa721-78d4-4761-b6a3-9e35338691c5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Cut out
688a9de6-70a9-4f92-985c-9606182ab45c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Fit off
f7abd3d3-17da-40e8-b0b4-8ba5706f3ce3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Commissioning
8e414764-7e58-4d04-9475-6c2b81884eb5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing
efd10a50-00b4-4f76-b6e6-7f7a95b15fa9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB1
1d0454bf-78e6-40be-bd5e-44bef0176d39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB2
040d8804-c1a4-4a03-adc4-1601df72a15d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB3
7be257fc-305f-43c6-9fab-bf9b82ce194e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB4
9b638c3b-6b7e-4e1d-8bd6-9358258acbcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB5
be6a7edb-b8fb-471d-868e-02c2d210be8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2610 | Mandatory testing | CB6
d1d7994b-258b-438c-98a2-1414f6664a53 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611
8b02a385-b328-41e2-8fc2-8a8b494409e0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Leadins
11cc36f4-4d23-4c9e-84cb-7c723312588d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Roughin
5ca9f02f-bbb3-45ea-bfbd-1c35368e211a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Cut out
8f540761-64f2-4704-94d3-58f709645f0b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Fit off
49e0b6f2-fc87-4857-8305-45493441201a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Commissioning
b9639e82-c7a7-4654-9dd1-42580f74e776 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing
3fa0d4fa-cb94-480d-88be-589458f02505 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB1
d185a396-7afc-4eb1-8762-3ee748a3305c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB2
be8954a1-947a-479c-a214-afc7b8e4cf30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB3
fc547a03-dab8-4020-8c65-bc1afc19a34b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB4
df1f246e-6453-4d4f-9eaa-d278015a9feb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB5
cd6890ee-e19d-4127-bf5c-832c673b5e2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2611 | Mandatory testing | CB6
2ce43dca-809a-40bb-a3c7-d8ea57d9c150 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612
3bc86eb4-bc47-4b0a-9792-b54e03a6eacc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Leadins
7e4aed0d-cbfc-45ef-9e98-741c10d5071a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Roughin
4ec388af-0f1a-4e13-bde7-d8992b6003a4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Cut out
a4b5423a-e5de-4c0e-b7de-c59f4f1a5775 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Fit off
57414e8a-ce72-4010-a88d-d37d37053149 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Commissioning
18d91f0d-4405-44b7-b187-96bd698fcb63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing
61cf597a-cce1-4d3b-a50c-5d2317617b77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB1
a40968da-e0ae-4d04-9f2b-117c1f14a795 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB2
25cb79a9-353c-4d5b-9024-713bea328b82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB3
8cf11de4-4bba-4d8e-81a1-c077c74c9e25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB4
01aab10a-04dc-4701-97c6-44caa18b3551 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB5
97af3413-48cc-4e3f-bc25-7f9b40d3541f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2612 | Mandatory testing | CB6
0eda137f-8c6b-41c5-94a8-0a1b254ff922 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613
3b89596b-ac7e-45dd-b095-442ebe504592 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Leadins
11e7290c-c9f3-4c4f-a3cb-2597713cc3a2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Roughin
f625a741-ad55-426e-aa1a-3b4012ec1cd5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Cut out
e9b1256d-bf86-4acd-963b-9615960afe4a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Fit off
19e545fc-d8a1-4758-8fdf-bb93ea00c39b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Commissioning
4622cec2-90ef-441d-8728-d886de01f8fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing
a0ac1167-a33e-4600-8a73-d79bc7215960 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB1
d8b20c69-35d5-44a7-8062-910aa6cef8c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB2
bf077a4c-b532-4eb5-a43e-90a37c5739bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB3
1d35ffde-3217-4fe7-8924-445bc092e742 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB4
70c2ec9d-5cd2-457e-b7a6-3c2a5c3b83ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB5
84ee51a8-d7af-4eea-92f2-e92b69a8eb83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 26 | Apartment 2613 | Mandatory testing | CB6
b0da9075-3138-436e-a119-55de754fb123 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27
cfda8e95-1447-4bc9-84bd-9b10769489b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701
773ca62a-3db3-459e-90a4-907b043e0088 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Leadins
8d3c2291-1c6c-4fd0-9dea-672c12d48bba |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Roughin
cb0df846-258d-4958-9df4-a250ea10ec15 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Cut out
d439b6d2-7306-4e3e-95f7-39233e7b55b7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Fit off
ab88179e-bf5a-4617-a716-0a6ae2831d1e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Commissioning
2a1b510a-bc3a-4c3d-be8d-32124d055c39 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing
6306871d-81f0-47fb-ac38-cbf02d3fc7b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB1
6890d7b8-db56-483c-b3d1-562b7f35bf2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB2
9f97f2b9-06f2-4e1c-95b4-a1eb1447cd93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB3
19ab69df-7ec7-41dd-b860-fb331bed0e22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB4
eb95745c-cbad-49fd-831b-869da591c96a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB5
e236c6e8-3209-4202-b758-c674b69d1bb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2701 | Mandatory testing | CB6
e6b7aef8-0ae6-4f89-af0e-60682b7b18c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702
be8fa63f-9636-4b71-97c5-1e109d0569cc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Leadins
95e0ba47-acc7-47a9-bc9f-cf901242ba91 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Roughin
a6f64cdf-ac1e-46fc-8dba-23048264ff34 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Cut out
895e12e7-146e-4306-a37f-74da655bcec2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Fit off
b2fca448-eef8-49bc-9673-60646ab767bb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Commissioning
da5aae76-b411-49d5-bb75-54dcd73600ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing
de1f1f0b-1eeb-42ee-a8d4-8bce65c14118 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB1
690f1c41-e860-464f-bcb4-0eb481230353 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB2
a50e2e0b-6d9b-414a-989d-176e95058a20 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB3
fed28601-39f3-4d5d-8b7c-ae4efb59b1bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB4
0003d2fe-0a94-4b9c-ac32-e0f0a97d321f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB5
9f36b852-1498-489b-a48d-ab1bb8679800 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2702 | Mandatory testing | CB6
fe4b3d2a-9981-4073-9ff6-57cda0dfb306 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703
ed884bca-7d0f-42f2-9378-46d1bacbdc89 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Leadins
2ee2821d-88ad-456f-974f-0ca259c9c0f8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Roughin
3d5e5309-0796-42ed-9905-f69d0bc8fd8d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Cut out
01b82fdc-81d4-42c0-8441-4c1928227e6d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Fit off
e5c91a24-7a3a-4b14-9369-8c3e64c54f31 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Commissioning
b9a542e5-58b1-4810-89a9-a2124ccef03a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing
f8580305-d1e6-44a0-a700-02ceafeee54d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB1
417c5d44-55b8-4349-b1c5-09812bc8df50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB2
2eedce4b-e8cf-4028-888d-5deff26c10c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB3
f341b15b-ba19-49ca-9064-5ccab142f856 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB4
280a70f9-6a11-4dbf-a83f-46e8ac71098f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB5
c03c5b6e-a16f-44af-9d54-89126ead7fe7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2703 | Mandatory testing | CB6
397fa26f-04c7-4370-83cb-b57a1761da36 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704
a81acc2b-0fa1-4786-9daf-61bddfc9bf11 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Leadins
09d7dc66-acd6-4c4c-8aaa-bf9570c9b77a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Roughin
2e797954-6d87-415f-9236-fb31d285826d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Cut out
390e30f1-c36a-4043-864c-d20da84e0179 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Fit off
12aa4c6c-3364-4fd0-9ea7-dc06a70dee0f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Commissioning
5d327cdf-b331-40c6-99eb-4400cb83cd3d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing
e1656e67-4738-4d51-a795-8a2c496a791d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB1
b67e670d-f2ce-40ae-b8dc-a40bf9c9ea7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB2
725c2c12-9d93-4c0c-8dfe-e000bffbf30f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB3
aa555fcd-63c3-4c9f-8300-3ab4b248e5b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB4
266039cc-8fa1-477b-b020-248df4bdda2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB5
fd8bceda-7de8-47a7-a39e-24aa6312ff3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2704 | Mandatory testing | CB6
dcfb0815-6d36-4464-aad5-da96b896d6e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705
5aec9b21-9d89-490f-b5d9-9c7d6e154762 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Leadins
9f05f704-00a0-450b-a938-1f602ff36ce7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Roughin
869b83b1-b97e-4411-b275-e8eee54991fd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Cut out
c4843606-274e-47e0-8cd9-80962fe2d5cd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Fit off
de0feeee-fec5-45eb-b919-328d9f9c11f8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Commissioning
3b4d3bf4-8dcf-4b45-9f62-ee8c884a137a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing
544be125-3aa0-4ac6-ad89-d4ef9171b699 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB1
c96bb063-c6e3-4145-9c6e-f77817baf779 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB2
32f39d91-58e4-468a-9bfb-9ca6f66311bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB3
dd4bcf92-0c03-4dd2-ae36-6c2c8930b726 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB4
87a67216-ca7e-4539-878c-0ab6bd7be212 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB5
0a65b7ef-93de-4eb1-88b4-81d0ff3e5bb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2705 | Mandatory testing | CB6
96eab2e3-9af0-4792-9502-ccc527467711 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706
8f6ef717-0c9b-448c-959c-b5013870bc0c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Leadins
1053efe3-b587-4df9-83ae-c940270e4681 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Roughin
4a93c511-a032-40bd-9f70-e409b3faf010 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Cut out
e5b14db5-d7b4-4925-a99e-afe982b0e6b4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Fit off
908bac2c-10c0-4064-a1b5-47a0682e7bc3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Commissioning
87060335-b397-4893-a26e-1594c4221178 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing
aa8c0c9e-8611-4e8f-a6fb-448ec780b009 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB1
df022c65-6b81-4347-8772-b9e5738b34d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB2
d45e55b2-4d83-41de-83cf-c65f78577862 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB3
e9dbadd6-47ea-4ccc-b049-8f4523523988 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB4
ad11a588-8dbc-4106-bce0-35b0d9b9c0b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB5
61bb5486-5b9d-40ea-a775-843fc5e6a166 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2706 | Mandatory testing | CB6
2a7dee05-d955-42e3-b22b-9fc257afa9d9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708
5f76b4de-8816-4633-9372-b4a55a4e5ff7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Leadins
d267f354-fd8a-4b49-b5b8-fe24ac01cbff |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Roughin
4cdd53a4-75cd-4936-8e53-4bfae254b4bf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Cut out
2a267959-e2a7-4ed2-a50b-7078c6ded3ba |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Fit off
c8762176-84cd-47ef-9a93-2ba977d62596 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Commissioning
b8a96b56-11b5-4e8c-8d06-24a729c3536a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing
37dc742a-cecb-4247-812d-072e88a17af6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB1
473df085-7ab5-421b-9195-4bcf99f427a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB2
e5326fce-8b11-4635-9d89-c7bb734d9235 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB3
ac7eba3f-bc18-4885-9b1c-45e5e9f85b0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB4
d0b2c6bc-532c-4dc0-9078-9a89a064ca36 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB5
3eaa7101-9664-4550-882b-31b9d530ea14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2708 | Mandatory testing | CB6
55e4a6e9-7abb-4712-bb8f-ea1b6d54e1f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709
a3cb442a-031e-4eac-bb28-4867581d4abb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Leadins
495fe766-634f-4ef5-8d32-fe5af0dbafc5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Roughin
03b8e5ee-787b-40c9-ac79-3134f699a147 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Cut out
303c4f7e-d409-4c65-a9cd-e63b424a99cf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Fit off
fe58d84c-fb35-43b1-97b1-edf127beb72d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Commissioning
76addb98-68d0-443f-b496-d42d5b397c5f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing
61c7c62f-f1e4-4059-86ce-cdb0f0736e6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB1
8b141882-8aaa-481e-95eb-65c342863cfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB2
890e1f29-f0fc-4616-8e43-2f013701f4e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB3
9f2d3389-b4e5-4cff-8697-bf6e720a0654 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB4
47aba9d0-9b62-438a-a030-ccd9defa6dfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB5
ad70867d-3683-4d4b-96c5-3b8b3b1b2ec0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2709 | Mandatory testing | CB6
52e34eda-c4d8-40eb-8a6b-bd077cafeff2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710
e045e42a-0052-4d39-bb31-d34bb19cada9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Leadins
f0e0b6b0-ece8-4a53-95b7-b7ae27152763 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Roughin
6b9e9c29-c2d6-42ad-a96d-aec8aecb742c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Cut out
0c6224a9-e1ce-41c6-9920-9250a3eb05f9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Fit off
a0f12465-7862-4384-9661-da6f5d817129 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Commissioning
5329dbe3-2691-44ad-83b1-b92ef48edac1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing
4fd9d699-ee89-43ce-a420-50deb35380ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB1
5af7d285-073b-4c1f-b96f-699953030d92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB2
3a8a9605-b86a-4c6b-a6dd-b36ed471e9e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB3
e465e721-dd30-469b-b101-1cb9e0b5b87e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB4
bd019386-1511-46d6-ac78-1c7039246d4b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB5
acab25da-f50a-46be-9908-eacbf227bb2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 27 | Apartment 2710 | Mandatory testing | CB6
842e8baf-9128-4fce-b8c2-9e6073a806ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28
f1931aca-4e5e-44dc-8a47-82be47d1bb2f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801
99e1b674-1286-4a5d-af74-3aab6556fe40 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Leadins
531defb6-a2bf-42ca-b678-3d81b5dc9496 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Roughin
85e6b4d4-668b-4ad1-8214-268b73359646 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Cut out
c669bfde-85f3-4e7d-b441-fd1f39e76843 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Fit off
796d0806-edf1-4ae4-a907-63a5a283afb3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Commissioning
800b7372-805a-4ac6-9900-411233c29783 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing
229dc68e-0b58-4fdb-9527-0d9434d34762 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB1
cfa52b0c-7fdf-4f42-908d-12f3ba7c553c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB2
bf720294-25c9-49b9-98e5-d99efc3c7df3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB3
da26601c-f021-4507-946f-0334cf097c30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB4
6bb641d6-8127-44fa-903f-e10bb9a16e42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB5
a53a37f0-c966-438b-b007-21ddb708615b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2801 | Mandatory testing | CB6
76491f10-1dd9-4340-b2ef-cba98a1cead1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802
0e17f26c-58c4-4d10-a648-d03244898a30 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Leadins
30648d1b-3644-4b21-a061-93aa68b3ac57 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Roughin
b401c9f8-b114-4969-9a0a-f32902f5318b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Cut out
ca494044-b190-46b5-a8eb-db010ea8f0d9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Fit off
6e7be542-24a2-4794-9166-baf9603323b7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Commissioning
b2e3490e-42b1-4d6b-8ba1-6043fc393619 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing
a1449884-5e2b-4b17-905e-bcb8de1214ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB1
442b74a2-cf9a-4627-914d-385565101ff3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB2
9473fc0f-4bd2-4bff-9078-be8779d6d98f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB3
c1ceebe5-079f-4785-ae64-86cb5add9312 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB4
f088dc05-1de3-4b18-95e3-8bb4d90e07dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB5
03792899-1b86-4657-b85e-a14881f61c64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2802 | Mandatory testing | CB6
85c82735-c52c-4343-ac42-c0bf924b0557 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803
011714c5-ca8d-4c18-a57e-a1da5c95d6cf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Leadins
20aa16eb-95ff-49c3-9432-121ae9bea821 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Roughin
9e663a3b-b5d5-43bd-8520-430a660b6475 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Cut out
b4c798b2-ca0d-44e8-b85b-68d1c2489df4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Fit off
1d6e9b44-2163-4cef-914a-524f38192e6f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Commissioning
c93d7dd1-01f9-4ff1-b472-163a615381c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing
e5a99bdc-24b1-471a-b7b2-72350f3084ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB1
521505f3-c684-409d-9db4-21844de586c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB2
5be8157b-8088-4bc0-a198-ceb0bab6038e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB3
826f8539-d632-49d7-9627-6615db626b8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB4
333238dd-9503-4de6-bd96-c30dcf0127f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB5
911f2900-0142-4fc9-8abe-18c6159034bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2803 | Mandatory testing | CB6
308b57ab-5e85-45d1-909b-ccfbdd964bcc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804
abd1c2bc-d8b7-4386-b621-1435cadf670e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Leadins
13fd874b-257e-412c-88d4-08108447fc07 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Roughin
80d9a432-5d93-430a-af02-a5ec56641ced |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Cut out
d86aa6f6-2e72-4ab9-9b5b-eb8bcd10942d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Fit off
dee48e50-2136-4bf9-8f5d-0e6fe145740b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Commissioning
6ffbe570-6f0c-4fff-a5e6-6f57360e0482 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing
bc0ab2bc-ec77-4bc3-b865-e224a7c22e60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB1
481c438c-72e7-44a9-aae4-2bea8e71fe27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB2
2ea6bf27-40a9-40b5-af65-601444dd40aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB3
83c8c9d9-f32c-42c5-9157-9ff284cb26bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB4
1548de16-38e5-4e81-b459-51dd26c6baaf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB5
5035acb6-f384-48ff-92c8-0b3853378aa2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2804 | Mandatory testing | CB6
b0a1d7c6-88c6-4e3a-a9d1-fe190ba9390e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805
61bebdb9-4895-4c75-af64-2d165557eb86 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Leadins
df1c6627-b4e4-4998-b173-2f541d1bb532 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Roughin
a66164a3-e9fa-45a6-aac4-ec1b22cf2b67 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Cut out
e96d236d-f40b-4459-be93-53c74ff6aaa3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Fit off
3a7bf818-7e59-4b52-b170-fd46b187e31a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Commissioning
45fa56ef-a494-4585-a89a-cf0a87cc8647 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing
5abe2485-57dc-412d-b23b-cf535ba2732e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB1
13ccaed6-e454-4eed-8051-b77015ea44fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB2
59fe5fac-f8fd-4833-bbf2-ad5922f82145 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB3
c3fe79dc-6676-472a-a9cb-ad5e5e7aa5c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB4
3f15a147-aaa5-49e7-b7e6-f36aa2f26a91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB5
c11eafa7-70a3-458e-b6fb-574ded6891d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2805 | Mandatory testing | CB6
781a8c85-d0a9-47c2-8c4e-494a1b12b1cd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806
51b6b801-31b5-412a-8b10-c8572d20926c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Leadins
17e6c858-e803-456e-badb-a26e36147501 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Roughin
9172e07c-546f-47b0-a042-e2d9e567e463 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Cut out
67eb0dc0-ee26-4144-af7e-a21190dd8afb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Fit off
11a42ce5-8528-4869-af97-4fccb44b17ae |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Commissioning
065d9cf9-8a4e-47a1-a9b9-3643b4c7c1bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing
970a540f-05cc-4c42-aadb-3992f4cb0012 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB1
ee222798-44a0-4b5c-95c7-1f85e1c20e7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB2
17ec842e-016a-4ab1-92cd-aa453a8386c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB3
024c6fca-7da2-4848-bc6a-231c1a2b4cba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB4
d9594fe0-0ce7-486a-924a-654ec0c20b1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB5
239d278d-5d54-4a74-92ed-1cc2783256b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2806 | Mandatory testing | CB6
35243d55-4a9b-4bfb-b43c-eaf45f74f588 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807
961471cf-f0e5-4e9a-a30e-732ce55aa126 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Leadins
7ad7ded8-55b1-4954-9b01-c3c1ccb89892 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Roughin
f728bf50-9375-4f4f-a480-a77e5e801cdf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Cut out
ca90d213-4969-413b-949c-7e02ca382ce7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Fit off
848ae448-8e31-4d7a-9945-16ed82b665ca |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Commissioning
a8b14e6b-a8dd-45dd-ae59-572c3954c690 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing
ed18239d-9319-4941-a28b-df25e4ed4c07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB1
43499482-d9cc-4436-80be-f95179864641 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB2
a4135600-9eb6-48b5-879d-7d6fb9b194af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB3
a5061736-8c86-4481-afc6-dd2aa421745b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB4
557cfb12-65f0-4b57-8f6a-fc3dc98a20f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB5
01e6fe7c-18ed-4e14-a728-fbccbf4d2770 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2807 | Mandatory testing | CB6
ac4e0012-1e57-4c2a-b05d-a93863fbde89 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808
632a2320-224c-4b61-a581-3139e30d7df2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Leadins
77dd2a54-f100-4814-a8ce-c83688df1368 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Roughin
282bae55-191b-49a6-87ae-447f3ac5e84b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Cut out
57c3f925-9384-4c7a-bdcd-224c0cc4f535 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Fit off
e23a1d0c-4397-4156-9208-9623a33a81af |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Commissioning
b9a9bb80-45cb-4dcf-801f-5f6b8cd7b525 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing
ebccb469-c19c-4db0-80a3-8de1b0026f85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB1
15201ef2-ad81-412b-9aa7-beb8a67caa30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB2
aa0d22fd-91b9-482f-b0b5-239b3ade0740 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB3
049f3e19-5e96-40ce-a2cb-f249769592ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB4
53c1cf77-f2ad-4bac-bf86-d0feef6e46ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB5
acf32123-7bdb-4185-bc37-f62f1af9bb16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 28 | Apartment 2808 | Mandatory testing | CB6
9fc470f3-02b5-4844-86ca-a54c5fbaeefe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29
3a5f15fe-d37e-477f-bc3a-0d3befd5e330 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901
67a387cb-4913-40d8-983b-40363d806653 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Leadins
ad6eec9c-0814-4360-9483-9409a2f1de2d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Roughin
55fb08b4-760e-4990-a1e7-26812a368c2b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Cut out
2c103819-ff56-4cb8-81eb-d94f1c352c5c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Fit off
72211522-238e-4527-b63c-b904ca5e799f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Commissioning
4482fcfc-0ed4-4a41-92ca-74cd47b0c287 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing
7982243d-fac7-42cb-94ec-11fbb98f57cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB1
acbc7488-1fc1-4cfb-9d31-5d03cd5b7d4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB2
6acdb67a-5cc9-4292-9163-2b5e9de19ba1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB3
7d4e7675-fea1-49ae-813f-18b4de3bfd9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB4
7d603be5-0df2-42f9-81ee-f3d6afd2ff87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB5
32da2e4c-db62-4de0-8a50-4dbe07571d49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2901 | Mandatory testing | CB6
33b407c9-9caa-4e23-a154-acd15ce4ac5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902
86647f5e-0796-44fe-b4cc-1af3330b62aa |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Leadins
bcfc5656-03c2-4d59-93a9-712f4c6bcde0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Roughin
fd8f2677-b3dc-4750-a4ad-a36262eff1cc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Cut out
37108a32-e441-4a44-910f-77288f0f94bb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Fit off
388f0a99-c6d1-4ca1-826f-84a618877b2f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Commissioning
86e3a464-2f62-494d-8fa8-15c538fc3364 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing
060d865b-e2bc-44bc-91a4-ab0122208f9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB1
77f429a5-c014-457b-bddb-74556d01ba49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB2
7702dd07-cd11-4933-8c67-1eff8aa52dc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB3
6441098a-401f-4e08-a210-662bee7338f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB4
ef431264-025a-46d8-a04d-8543ebbb961d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB5
0b0d3707-32b7-40de-8095-3996e139c51c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2902 | Mandatory testing | CB6
f8f6548b-5282-4356-9a9f-f50f9ab4700c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903
4f4d3dd4-095f-44d5-9cc9-01eb5304ffba |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Leadins
fd56eeb1-1fbe-417b-96b3-b31a81978268 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Roughin
939bd54a-a239-4288-9a7e-909279e76269 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Cut out
3a014977-63af-4edf-a13c-3647e2115b5c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Fit off
d710bd91-6433-49e7-9a63-ffbf3fb9f4f8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Commissioning
fccdc823-19e9-40d2-a504-04de171c726c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing
2ac0af94-0a9f-406d-b109-a2cda2294fd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB1
33824518-53e2-422e-bce3-d970c2687647 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB2
9bc81903-1b16-45b3-8a1e-843cc5ad4236 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB3
cee572fd-1021-4530-bbe0-e729f730c48f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB4
0aeeb424-7cb6-4bc3-be81-5bf5119f0606 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB5
f3d88a0f-738f-4c84-a91c-70023339824d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2903 | Mandatory testing | CB6
d2a16724-5f27-423d-a977-b9c34f69c27d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904
9644b956-fa78-45e8-88f6-cbe9c8f99a13 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Leadins
a77498b9-7e36-4771-a711-afde21ff5845 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Roughin
fbd569c4-916b-4f0e-bb1a-7aafacb79da4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Cut out
5c9af7aa-2cb4-4fb1-a7c7-6a7504e3dc34 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Fit off
588a3a7b-d325-4afa-9493-2c0d73d94fc5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Commissioning
9a02997b-e2ef-48ab-93b1-e3aee07f0371 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing
2239f1d5-270a-4551-a731-3358a80e1c48 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB1
7ec269ea-88a4-4063-b432-b26153703268 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB2
dcd88697-03e3-4e29-ad89-2b42dafac111 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB3
80cc5c04-bbe0-4a6c-bf60-f47d66c915eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB4
6997788b-58b4-43f1-a206-2df3ce636eb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB5
f7e95d5b-f1a3-4619-a906-453569de3eec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2904 | Mandatory testing | CB6
278b8a14-21c1-4f30-8ff7-174f10253c93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905
4fe410f7-a6ad-4e38-b222-d0206983e425 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Leadins
b9e49011-29c1-458e-936e-0c9214903ea5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Roughin
4fc6c5cd-f7af-4067-b3ef-e6fd91c6716c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Cut out
f5aaa16e-1c87-47bb-87ef-ad3190ae9c30 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Fit off
1884705e-4cc4-4080-bfb4-591bff60f030 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Commissioning
bfb9829f-0c38-46d2-8862-f7c9987a17ae |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing
01f1d35d-b7e0-436b-875b-28caec53f8c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB1
53d1426d-d597-430d-9fd5-2f35075c4f2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB2
2a69e78f-cabc-4d24-80fa-0ce918d31ce9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB3
21b10f2c-dab4-4f6c-b7b6-82127738ba10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB4
88745502-3b48-4fab-a16d-2e582414c42d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB5
1dab0bcf-7a75-4dd2-87b4-195a160a8916 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2905 | Mandatory testing | CB6
8ee38034-4a08-41a7-8085-48673cf381d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906
963b0a9f-cc28-45f3-82b7-544cb3f77bb8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Leadins
daf033ba-5113-411d-b378-81a0db336bae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Roughin
d8a7547f-05ad-4177-bb45-d92ae43d7f51 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Cut out
84fb8c7e-b327-4cfa-962e-9fde17963291 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Fit off
e3978416-28ac-493b-af45-ed5127aedbcc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Commissioning
07aa1309-129b-4483-8b37-73a31287bbdf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing
f48ce3a8-8e6a-4758-b856-2cf31357fca1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB1
ca5b8195-740a-4113-84e3-6632d6b50b23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB2
9eca7e23-d736-4a04-879a-47f76370a553 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB3
e1c6c391-dcf3-4ce3-b95f-95a554f5cbc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB4
bb018396-e58d-49a4-8d1a-4826f4299d1c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB5
10d37fcc-c8f6-42f4-b6ce-2131ac1af1b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 29 | Apartment 2906 | Mandatory testing | CB6
5c58e2cf-cda6-4f63-8f85-2ad9ad9fdbcd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30
896cc385-be64-477d-b51b-33f1e6a58604 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001
530463d1-96e5-49d1-8fce-22fc9a39381b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Leadins
a8defd01-be79-4678-ae6d-dd4c4920f5ad |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Roughin
9969ad4e-620a-4e57-9e0d-498e030c957a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Cut out
8a65cc26-beca-4ad3-b089-e22cdcd9acb5 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Fit off
bd3a9867-3957-489c-92a6-5803b7994caa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Commissioning
33cf9703-90b5-4bb3-917a-3c1b4a5713c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing
f2550c5e-21e7-4965-9382-eef0e38d6999 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB1
358a9e67-7a4c-49b0-885b-b53ab9a32516 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB2
2194215b-def7-4f27-a4d0-01a626f85ffc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB3
f70e7c3c-3a98-4f1d-81be-c00211a2c2c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB4
d176befb-3b9e-4187-8ccc-758dc77d00d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB5
0e4f7cf8-279e-4b86-b903-6a9891b0d36b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3001 | Mandatory testing | CB6
f7a07e38-eace-4d0f-82fd-3de3ef5b68e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002
33ed1fc4-80f8-4602-916b-0b5260be8bce |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Leadins
2dcc04d9-139e-462c-afbc-1db65aec9ee3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Roughin
6373febc-662e-4830-9dcc-0a4ed5d016b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Cut out
ec5e6194-4c64-4bbf-bc47-82ccd25c7f01 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Fit off
4cc15c56-0120-4b4d-9d0d-c6e8031af429 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Commissioning
6389aec2-0609-4d96-9d4b-fd2cdd078c44 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing
d20e05f3-e526-4f2b-87b7-147953cde17e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB1
05bcadaf-66b7-4595-bc9f-1d8356da72a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB2
e33ae985-d510-4b52-aa6b-f39de469750a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB3
7c78ae72-3c4b-44c0-a1c5-6cc81324469a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB4
a8f49dda-070d-4b91-8e8a-721d8b3f62f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB5
256a4096-d124-4185-bdb6-4940ead34ba9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3002 | Mandatory testing | CB6
24637aa6-1774-4ed2-82c4-895c8f583f22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003
a4440485-28dd-4a92-ab6b-0b55395c38e5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Leadins
da8bbb97-9cc1-42d7-b084-719d28285a7f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Roughin
718637f6-92c2-41ae-9c80-20d518e5b5f2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Cut out
cbd92d2c-f7cb-4e85-a7eb-2728edee896d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Fit off
b02be723-b3c1-4bc1-a50a-a9f0705ce84a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Commissioning
a6946dbc-ff6d-47e9-9319-394461232565 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing
b76feaa4-3de2-45a3-b999-44b5ad1e4758 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB1
b2237e08-7dcd-4a0e-a744-57aa2f0cc4c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB2
fa7e06dc-705b-480e-a4b0-c6caf51af397 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB3
e0917166-7a29-4ba4-b76e-78a3c735d945 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB4
d04d538a-e78f-402c-ae17-59a68502c01b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB5
469e4461-c546-4e50-82ca-c987359b0688 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3003 | Mandatory testing | CB6
9993f8a1-7548-4f65-845c-734644d59e87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004
61773ee0-f8b6-45d1-af3a-9b02f6b52ed1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Leadins
397a65e4-d1b7-44ec-a1c4-14b8ea17c4ee |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Roughin
bcd13e43-5076-41f3-8b26-cf447ce5a5cd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Cut out
dad9a173-8131-4d5e-b6d4-3374f9d94972 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Fit off
374a8371-9719-4aaf-9f19-f4356a6b7e35 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Commissioning
7d9215e5-387f-4a85-aecd-0d654dba7a01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing
301667ca-af11-42fd-9780-b0c114de4bce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB1
4c6f25c8-a940-4d57-bc94-e2fedf5ec7e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB2
d664d42c-9b37-4318-a41d-4e0dcf29dcf1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB3
30c365c3-17ee-4888-9d1b-81d12ad9b345 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB4
7f078521-909c-43f3-aeec-73b8800139bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB5
5aa2850d-71e2-4513-8eaa-881e18b69859 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3004 | Mandatory testing | CB6
41f27b75-1918-4e14-85f7-76912157a385 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005
10a843d8-5f9e-4f54-a29b-20ab3db3dfa4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Leadins
41dc0cfc-1ec3-4bdc-b66c-361549f5957d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Roughin
b60f4046-56df-4bb9-b4c1-529db1bf63da |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Cut out
ccd8231b-8b0f-438e-b785-a99437e35c92 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Fit off
15e80dc9-ab3e-4579-b6cf-89a104ed543d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Commissioning
8a84fd64-70f5-4633-810e-b5a47d538b24 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing
f4a7f0bb-a458-4561-8480-7c1e492ff589 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB1
be0e3217-549f-42a6-970b-7a4275fc0386 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB2
a265799f-e814-4d7f-848f-75ab33e6f719 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB3
1bc35d90-c6fb-4800-b7b9-e81de7756b20 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB4
7cd206ca-5d88-45fb-9215-e1efc7a48687 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB5
43ff83f2-f9ea-42a8-b81b-91aa625d6b89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 1 | Level 30 | Apartment 3005 | Mandatory testing | CB6
aef943bd-d685-42f4-b791-b286c46a7f3c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2
72b4a271-a814-466b-b91b-a592558a154a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4
7fedf0c7-1ab5-4cba-9212-be5d88920cf3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401
ee138420-f6b4-4fc8-a462-2590246a814f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Leadins
2dadffc2-22f1-4289-9610-1083c58188d7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Roughin
28bcbbfb-2c7c-476f-9502-0d103fb12dd1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Cut out
ee5674ae-8a07-416c-af6d-b1b30c795a97 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Fit off
5491ceb0-5256-4a2f-9e6a-93f39436dcfb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Commissioning
bc1c2f73-236e-4f3e-a3d7-ffe396333ecd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing
568c2fc9-d8ab-4fec-8e5e-4eab29aadb65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB1
1e54360d-9001-4464-8f70-ccd642f994f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB2
431a2875-8058-488f-958a-5acbc16fbc18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB3
4e2b9b20-37f8-46ed-97d0-56551c659eac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB4
c7205f8d-fe7e-4d86-91ab-8153625e168a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB5
3c8a6b13-c8b8-41c9-b080-bf9545c0ccc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 401 | Mandatory testing | CB6
7c90189c-7cf6-402d-8920-e9c3ff0690e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402
8f515dc6-b065-4156-b1a7-f3070dccdf22 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Leadins
11e6bfe9-899e-4e72-9f73-16679f9ff7ae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Roughin
57ea5c1c-f881-45c0-95af-4e08f1e7e47f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Cut out
cf793d38-1a84-4e16-bf75-35b0b6795b10 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Fit off
a6f4ef71-1b55-4142-a33e-f565a92c990d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Commissioning
5db13f9e-0450-4138-88fe-c42e4f6475b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing
bc500c21-61ed-407c-b2c7-409029e20015 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB1
801be510-97f5-453a-b9f9-a449c7b977dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB2
b1c7b4d7-d87c-4042-b179-07de403c1aea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB3
2215f7eb-d7e7-416d-86ed-2425c7fb963c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB4
90ce6491-b072-40df-9f14-55538af3dd59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB5
677df2a9-f3cc-40c3-abec-c58d8e5c273c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 402 | Mandatory testing | CB6
225e2698-4833-41c5-8885-b263bbd365e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403
5e00ea53-f9ec-48d8-8bca-fc7548c5f553 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Leadins
cec71812-ade4-4970-b2ab-75127870efce |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Roughin
27dca940-1565-404a-a2e4-7a528f2eb121 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Cut out
551a891c-41dd-4546-9a9d-d7f78ffc47ea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Fit off
36d3ee73-adca-4b41-b091-5efa56c823ac |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Commissioning
d04076cc-ec75-4720-8df6-be7dbd3e31fc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing
6e36a4f7-e101-4a18-9922-d2f8410eed64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB1
9bdabbb6-cb5f-417e-b38a-49f3bf7cb207 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB2
5bac65c2-e26f-46c9-ae8d-a64caf0a7c8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB3
cffa1f7a-ec32-4166-b4df-dd0bc862b13d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB4
7a3b567d-2fca-4e0e-908c-bc7042c341b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB5
98516243-2eee-4f6d-8432-eed2808f0d23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 403 | Mandatory testing | CB6
e85ea44f-b8df-4405-8812-0d28ff867587 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404
688ab395-8137-4b66-b073-542095442db9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Leadins
473bac72-2637-4e98-9244-287c9bdd13e1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Roughin
abfde32f-4b92-4787-9430-146d7424b13c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Cut out
5850810b-c036-4502-b691-1ac4f1164daa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Fit off
881b6bc2-43f4-4403-8da5-a50611c434b7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Commissioning
7a7d3c97-6868-402a-bcdc-b1ef14613b60 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing
4bcc0cd1-1463-4aed-8414-fb7f90070d6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB1
aab5fb88-c753-4e5f-8a63-6bf8e321b1b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB2
71c41f47-058a-4ea4-bade-f4b482124d92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB3
f5d196cf-056a-44e0-a594-39d89ffb08ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB4
65c98810-d54c-4369-a20a-4673e610748b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB5
608fb968-1059-49b7-acf9-c28ba8279092 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 404 | Mandatory testing | CB6
ed3e2523-5274-4d70-804d-543a7e0debc0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405
f1dce13a-9315-49c9-9ed6-784ddceb5673 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Leadins
801e30f2-2242-467b-9bef-50ef9459d7bf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Roughin
014cf080-6d83-43f3-b74b-1c7d3877b257 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Cut out
0fe4d633-1364-43b6-97b2-0472874e4c5b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Fit off
81480caa-4bf8-492f-ac53-8052004bb02b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Commissioning
d85ecd18-d539-45a6-8ced-6a9a1ec07bc5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing
aa45c316-4a5b-49c0-964d-1c16663bd1b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB1
85e3e81b-bff4-4339-b433-9d12e832acde |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB2
13e16fc6-49e1-4ab5-b7b8-88b3010c689d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB3
c389966d-cd87-42e1-9cfd-a2ba7bed6812 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB4
d33bf074-e348-4622-a73c-7543f571e71a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB5
f8932818-308d-4ffc-85c1-897491fd048b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 405 | Mandatory testing | CB6
ccdcd355-d7a4-463f-aa02-969cbe51289d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406
53518b88-240d-48d0-a6ab-08e9ec299a22 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Leadins
2dd84047-939a-43fd-a87e-366f7bd6a34c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Roughin
3fdacc2e-1f85-43e2-9d06-d1724707eeb9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Cut out
537c7161-cdef-4678-b9ca-b984ce75a3be |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Fit off
68275aea-e4e4-44a0-98f4-4342ca86c423 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Commissioning
1433183d-5d90-438b-8d7c-1f12a01afcdb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing
6485b0d2-ebac-4f92-a454-b3411f7457d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB1
f71a3dab-f26e-44c1-a10c-770dd3d3cbb7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB2
628823bf-9b08-49bd-8afa-d2edd7ec6140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB3
a1ade6cd-2e99-4423-84a8-406b69950c00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB4
f411f38c-6774-4da3-8085-886cfe2eccea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB5
0afab277-bf41-4a0d-921b-a75e8265729d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 406 | Mandatory testing | CB6
eae972a9-0177-42e6-a99b-391c1fd9dcfb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407
ead4c35c-c366-4a19-b877-404f184b827a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Leadins
ff67b5ec-7e4d-4f31-a4cd-c8f00ed24cd2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Roughin
d09f3504-83ec-4bc6-b70c-dd91bff3d968 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Cut out
882036bc-dd5c-4ca0-bcdf-2bd25e4ad8ea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Fit off
bdcc4a64-4a23-4aab-b622-cf32fa3f6cff |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Commissioning
9f11fb6e-f177-45c1-ae12-384b714dd4e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing
1d1dd833-34c2-4524-a0c7-a48d0ad1155b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB1
0b755219-760f-43d0-b436-56e9145f6391 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB2
6f773410-6ac2-4607-800f-08decb3c3464 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB3
bb9b1617-a1d9-40ab-b846-64e403d2c35d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB4
c0687250-cf8b-4345-8d3d-bb2ee9785ea9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB5
7b8ef7df-2eba-414f-a157-0f6a13342532 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 407 | Mandatory testing | CB6
80ab9294-0411-42b1-a58c-9024f10dc6ab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408
217c705a-f5c8-4f1c-8821-4ce34ff52df3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Leadins
ae767ea8-4578-4973-9972-33d5b9be43b7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Roughin
2ba80a55-3ad1-43c7-bd76-77476d4124c0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Cut out
207b1a91-c285-42e9-9e65-de017760727c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Fit off
0c1fb771-51cf-47e5-b6c4-fd305e6f251e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Commissioning
7910b9f1-a5c5-4b54-b2cf-57b14c5b0a3d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing
618e39c8-0dc1-4ec0-924b-75b2b579f603 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB1
115fb3ed-b7bf-4d3b-b655-2d0d90b7cd7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB2
300e0154-c566-4c59-a0c2-469ba23ea653 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB3
a17ce694-da87-4d68-8b24-c21753e8075d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB4
63fb50c7-aade-4845-8f0a-be97e5d6f8a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB5
def21249-5f47-4759-a6ed-7e0b6698dacc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 408 | Mandatory testing | CB6
b61808d2-136b-47f2-825f-57184a4f82e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409
fd652333-6b06-4b65-9949-481477038178 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Leadins
c7421038-4980-49db-a4ed-a612f1a67576 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Roughin
624545fc-39de-4921-af17-72e3fc008278 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Cut out
8067a48e-c923-4153-9e38-65344c81a459 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Fit off
90517ccc-81db-4a85-b3ff-d4277ef5765d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Commissioning
09da5c8d-0f7e-4a4c-b966-544339e8fdaa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing
65163580-9636-41cd-98fb-6055ab506801 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB1
3bb591fe-03f9-492c-8757-56796ccc2303 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB2
64c0cc7a-4537-428f-b5ab-5e774ab1c4b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB3
158b75e1-b54d-4cd3-93e9-6a63d19345c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB4
e82f7396-0f19-43f6-b0e8-9f238cbb96ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB5
536c08b5-0dd5-4f8a-b0fa-20c1b50c7b34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 409 | Mandatory testing | CB6
dd4fa937-95d7-4f34-88e5-e818dec6ffa2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410
4fe9bcb3-27b3-404b-8b34-b2f2a4bc5648 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Leadins
1d137ceb-d83b-455b-8657-34a02ef2e3a7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Roughin
03e616f5-a83d-4b21-a912-d8edf5a74948 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Cut out
d86484fc-647a-4ae2-b521-8a1023c5d73d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Fit off
c04cb49f-e9e9-4fe6-bdcc-f43419ac99d7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Commissioning
e3bfdf2c-c3c2-433b-932a-1eb97b93804b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing
6e37546d-898d-4fd9-be1b-9c83b978c841 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing
1efb91b6-ef8a-412c-ae3e-9d6c1c77a781 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB1
02298a9a-780b-4860-99f1-5d6c77e25232 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB2
0a93e2e7-5779-4d8e-a057-36414d4efe57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB3
fc58e2b7-1210-4536-b3f6-9aee92978db4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB4
665525db-f972-438b-8f58-d2e2bc0807fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB5
9e3e2eb1-b968-4ff0-976f-c203af662176 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 410 | Mandatory testing | CB6
990dfa5b-ced9-42d4-adb0-bf93fda855fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411
3cb9b110-a945-4fe8-934d-0461ab2ae809 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Leadins
47e27ecc-2775-4902-b54d-db2ee7ffbd8f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Roughin
446463ac-a035-4827-9027-5d3acb1fc75a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Cut out
f701ccd5-ebc1-49f5-8063-093203acf1ff |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Fit off
01e7565d-0f46-4914-b5cd-6a033c4389a3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Commissioning
37f316c7-3a53-4deb-93a8-5d283fba3855 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing
45034320-2bac-4a1a-8841-2675f391609f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB1
f1300b8d-b016-40e1-92d4-636c7f544b42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB2
d10d962a-1251-44ec-adff-40e579c3656d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB3
ac307a47-f0c5-44a9-91be-fac50e5adbff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB4
5747e622-5da2-4e23-b90e-f03dc4025856 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB5
e1a9cbc9-6f5c-4d72-9cda-7d12e2d5bf96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 411 | Mandatory testing | CB6
2143d07b-75ba-4825-9a8d-697f5eb6e859 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412
57f0ec21-047c-4d81-b83c-787c2198e089 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Leadins
9a4158ee-68fe-49cd-b6af-a0321c939d4b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Roughin
ace233d1-7d70-4212-bf4c-5d24b9ad6858 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Cut out
d4aeeda6-ffd5-4ad1-9cb8-4510e24b9227 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Fit off
ec7ba218-0c49-431e-b68e-b4fee5470ccb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Commissioning
c703d504-149f-44cf-aa02-55bffff5bb68 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing
2b5a82c0-d6ea-4f2a-8d8c-1e1659566760 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB1
36842ec9-43ea-4506-816b-cf6fd981d861 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB2
cd55ae40-2885-437c-884c-0f6310559736 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB3
d628aa03-a2d7-467c-a041-6d4f4b37b573 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB4
49fb05ce-6dc8-4fad-af57-52c645e42bb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB5
2c9ac268-a545-48d8-8e08-387a600c012b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 412 | Mandatory testing | CB6
69cc4267-eedd-4df0-aaa7-b32f3a1f1951 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413
d95ade42-ddab-46e0-b12f-d516a2a0d550 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Leadins
79e55208-349d-4f15-be57-e6e64ad2a1e1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Roughin
ee13c09a-75ac-4349-9484-d418bfa48898 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Cut out
d81325de-6969-4ce7-81ec-c57acf73d4bc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Fit off
79ae62f6-93ec-4704-87c7-ffd43469a5f8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Commissioning
fd2e79b4-ff4c-4583-81bc-45e49143f7db |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing
9e2e989e-a0b5-4f57-8d78-b7f33ecfdaf0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB1
2f9d518f-3d51-4803-8d88-68e31c25e5c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB2
a69b53b1-4598-429b-b72a-887e46bbf9cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB3
ff60b4c9-fca5-4803-a2b2-6f5000df2f20 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB4
fac18868-87d6-4ec4-af93-315186132b50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB5
3f9ffea5-e935-4144-a83f-71a5f7cfa206 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 413 | Mandatory testing | CB6
ec6285a0-8030-48c6-81e5-99d6f8fb7044 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414
0a99cd57-7a38-4839-b0f0-f7d43e9df9e7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Leadins
d0c7cf2c-fcfc-45d6-8019-8639bc3b5e00 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Roughin
7470e5c1-61c3-4574-802e-48712d60bd88 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Cut out
ef570bb1-783d-4392-ac01-63a3487a6993 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Fit off
dcd7bb27-6d31-40b1-95d7-0fa7fd1a6871 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Commissioning
b5cb998d-204a-4d6a-8868-e5ce0de4de5c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing
0b98e8c7-de4a-4f9b-aa4d-9029382ff811 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB1
9629b365-015d-496b-9416-f4424d99eaef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB2
082044b9-1736-4cc0-9ea6-52a67883ff10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB3
401defd2-4784-4e62-827a-4c6032d0c9e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB4
40180ca5-25ad-45be-b9aa-6c6c15c44303 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB5
043f705e-1e9f-4cee-b333-f28bdd0bdecf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 414 | Mandatory testing | CB6
19e8ed5b-5a1b-4b02-9cf6-ee71c143223c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415
1ae3bca1-62ad-489c-b0c2-949aefb64aba |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Leadins
1f2fd623-6bdd-4dc9-b233-694ae60d4c93 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Roughin
5899e248-d91e-408a-aa6a-e6a08f666c49 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Cut out
00b140b0-c6a1-490d-9db8-b2f9f651cba6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Fit off
b28f36f1-a58e-4edc-8660-f2ff378fa3c7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Commissioning
76e3c063-7d16-4dcf-aaa9-27ca64b2b8ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing
a0d3370f-8e1a-47ab-956f-474c2b7ab183 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB1
197f4e5c-efa5-4595-b66a-0dd565baed59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB2
3b388ac4-3f29-40bd-9a7e-b1745fac7ada |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB3
851276db-3348-437b-b4b6-fb1ba2db85cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB4
48f03ee1-7d2d-470a-ab58-1d48a1c8d7c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB5
94bb616f-3385-4eb2-b1d5-33d1d4a367a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 4 | Apartment 415 | Mandatory testing | CB6
03e250c1-7876-417c-a7fb-8e5561364f5e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5
3694cf92-adcd-4af5-a917-dff15f63ea1c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601
8c27b721-f45e-417b-8424-649b37a7e1b0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Leadins
32d8e53a-29e4-434d-8808-2c2617434622 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Roughin
4560f75e-2cb3-40e0-b38d-d4a14aa53e0f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Cut out
e9678c7f-1594-4332-bd53-34df6bbeb6e1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Fit off
0ad0d660-3dbe-4e64-b2c3-8972587c11b3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Commissioning
ed032c02-2851-43ad-b3a5-0499d90db346 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing
7a783c9b-65f2-4333-a7be-f832fb127645 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB1
3c7572c7-d99c-45be-8f43-fdb6c2fb3195 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB2
6249c9a5-bf6d-44ce-82e2-ba26b1756e62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB3
86aee553-1292-452d-9ef9-151dfc1c98c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB4
1a27bf5f-8e6d-4e1a-a1f3-d644881ca9f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB5
21e67cf2-2b23-4614-a161-04421e14eadc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 601 | Mandatory testing | CB6
eca32e87-bac8-494a-995b-12301c7d3b8b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602
7f12e7f8-dd84-49af-83a0-342c109d964b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Leadins
79eafa25-df7d-424d-a3be-e02aaff891fc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Roughin
db0106fb-b666-48f0-8fe1-4b878c955718 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Cut out
87cebf8c-118f-4b27-a7f1-cdfa73efcb35 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Fit off
8f3cd39b-f185-4fd1-89a7-c8cb47e5e829 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Commissioning
3f0bb4da-6477-4930-92a3-9cf796825959 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing
72fcd06b-ffd8-4cab-9c7f-3398ec7ad292 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB1
80f185a4-5208-4393-b1c7-be2f56aac3e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB2
b762e6c9-3ba0-4c81-b315-49b281061940 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB3
b4018388-b94b-45af-8d2b-1aa07051a022 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB4
050a8348-2322-4ad1-b739-fd96df318213 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB5
824a0e57-da8c-47bb-a8bf-3f75bde7ee4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 602 | Mandatory testing | CB6
abeac1fd-ced5-4797-8baf-9c2ff730bb21 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603
5b3ba59c-2af5-4f23-bd06-98b676012588 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Leadins
0ea381cd-9a29-4646-8d60-89eeba32534f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Roughin
cb475c66-8767-49a8-808e-5046d0da1def |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Cut out
fe63b812-39ef-47d5-a8e1-81c5d3ed63b4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Fit off
9011eebd-cd24-473a-b2fd-52bcac0adafe |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Commissioning
3eed46d0-4022-43a5-922f-e495770c22e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing
776bb8cc-ea3e-4438-acf9-d41feaf39fc5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB1
7fcf040a-bf13-4583-8b71-fda177f1ef58 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB2
c808f70e-16f8-4f49-af8f-d1512bfa18fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB3
e1806f19-4e27-4bea-8e72-60b01687f6d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB4
764d8d9a-3518-422f-8f18-1d51e786f7a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB5
acea23da-0ddf-4e54-ad27-f3bfe463b0c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 603 | Mandatory testing | CB6
3a5b2d0c-a7f6-4f56-96fa-11b649142bc6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604
6ad1cdb9-6e31-4cd5-a755-a8ac03a82454 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Leadins
f34a9843-4047-43fe-a043-5f1689f2c585 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Roughin
b3bac6de-2404-4700-8cae-69a9fe601dfe |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Cut out
dc4fc75c-79ce-415f-9cef-606714a77fe3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Fit off
10bf4bbe-1dd9-4bf2-963a-b9137b388573 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Commissioning
e8088337-6543-42c6-b96f-4c55ec964aa3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing
85a795d2-551a-4293-9bb7-f91151f64620 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB1
fd123120-a341-4a1f-baf5-fa05c0c1ffb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB2
644e1cd9-c90e-48b0-a145-4542e7999e76 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB3
040265d1-48a1-4555-9540-79c3ba06db82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB4
a8bcc916-468b-4007-b9fd-d3bbe0d8c840 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB5
6e2efd77-bad0-444b-8c9e-92b1870e7f91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 604 | Mandatory testing | CB6
26322f7e-960d-4ffa-bd22-e5e993ab00fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605
dd218f63-b974-4f53-9ac5-517ce8e03f36 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Leadins
0b1eb007-61af-4846-bc20-6b923970aa09 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Roughin
edc87111-388f-4f89-bd64-636d1ffe1f5c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Cut out
4db55b5f-b355-45e5-aa78-88e60add8466 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Fit off
81c3c1ad-a6aa-4280-a805-2c46cbccb432 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Commissioning
e03ae24a-bc12-49a6-a4b9-ae3e20b4fa27 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing
e6a2c6f1-c75b-4d6f-a9f5-2f5e31973cfb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB1
7635b493-6668-4430-aa38-ce152bea0994 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB2
8648a6fe-e30f-42bb-a62f-02f983c2d9c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB3
5a0e5a79-c867-4b67-b56c-2341b78336f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB4
a4503ee8-fb36-4839-bf8c-baf08767b374 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB5
8f4918a5-7e2a-4e55-8cde-b6f49850dc59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 605 | Mandatory testing | CB6
930a933a-216c-4521-9aee-0c8eabfc6fa1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606
1f15d743-c399-43e3-9736-75e719e423cf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Leadins
bb4034e1-20a8-4e35-af1e-413596370c81 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Roughin
df0ace88-e8ba-4517-8cae-f5cd02115caa |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Cut out
440ed96b-f12f-4e58-9ca6-2217a3ddc71d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Fit off
22c2d2ef-2b3e-4dc8-a8f4-da4fdfb40684 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Commissioning
3cdfe2cc-a76c-49ad-970d-b6ec2f6543c0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing
f3d410ba-bbaf-404c-94e1-8bed1b126969 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB1
34096a28-7311-4982-a5b5-e358f3c80f5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB2
f762b256-b9b6-4929-b114-3250c163143b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB3
9b0349d3-908c-476d-b14f-fcd7382c5677 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB4
1b9686df-dfbc-4477-ac50-6a36333f3d12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB5
19290bda-6cf6-40a2-99de-6972ac2a701f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 606 | Mandatory testing | CB6
9899ab59-8a17-4d19-9359-26c59d11375e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607
9b751c1c-c7d8-4893-a7ff-119a3096cd4f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Leadins
687b6604-14e7-4c78-a6a6-d075ffea2304 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Roughin
cea99578-22f4-44f7-b909-6f34251112cb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Cut out
1e616d2d-c1e4-44ba-8220-6afddded2635 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Fit off
3970afcc-2da9-4750-aae4-3c1439202a33 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Commissioning
ab8df369-7a3d-42b3-8cc4-eb9af251f854 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing
1c9d0321-43b7-478c-ae2f-baf47b118627 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB1
039a8726-779a-41ab-b892-8778eb66f9bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB2
9be098e4-a4a6-4a88-9325-19526c4d5996 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB3
b32e3de3-48ae-405c-b6ce-354684ef2b98 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB4
61618b82-0bfe-486c-9545-cbcda8b96c55 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB5
64fc7444-e217-4396-b70f-8692875bd42e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 607 | Mandatory testing | CB6
e07633ce-e432-4efb-a894-4567d291f4a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608
d0c207f4-01a4-4183-bfaa-eaa155f33a1f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Leadins
7c7ae943-a8d4-469f-a314-3c4072855ed0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Roughin
2809e6ea-7c58-430e-871f-8bdb8a6e81a9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Cut out
535e6c46-0368-45fd-9c0b-e572cb2012fe |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Fit off
069f492c-a1ce-4413-8e8e-d7cb7dfa2f5b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Commissioning
c3688ec6-e176-4ae7-8807-e9720158a7df |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing
f97bacdc-82b1-4a40-b412-e81c6a576283 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB1
d392c377-4eb0-4067-ac52-fb5e6599bcf8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB2
3909d2a8-dba5-4f9e-b6d6-f2f0bda92f1c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB3
f1af5eb4-8207-4cfb-b84a-b148b31d1e56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB4
c3daf407-86c4-450e-8b03-305318eb4e94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB5
04426f36-848e-4a1e-88eb-34742adb2c40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 608 | Mandatory testing | CB6
60fd2179-da70-4371-980b-3004ce9a6865 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609
8b8cf5a7-a3d4-491e-9eda-9c4be9aba9f4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Leadins
ced1bea9-3b01-4e1b-a99f-2fea1d6b3481 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Roughin
ee8095f7-a1c5-4660-93d3-46448db216ca |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Cut out
bf1a251e-1eac-4e65-8f06-6f773cac99b6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Fit off
89241a10-a204-4a67-94a4-0468cf85158f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Commissioning
832146be-10b5-40c1-acf8-f138d39f7544 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing
d62a91b0-a69b-41a0-9dca-258e0ee46533 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB1
008108d9-52e6-450c-a476-0cf80c2b86b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB2
96b73880-cd19-4524-b544-bede5380033a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB3
ed18028d-191a-4032-8935-447f899b38b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB4
22c765c8-1d83-45a5-8530-3bacb962e7c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB5
f95266f4-706c-4927-933b-116e2d0d1a01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 609 | Mandatory testing | CB6
20d7b6f6-42a3-4c1a-a2f9-cc64040dd04a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610
3db435f1-75ff-4110-a55e-efd83a974bf0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Leadins
11c05105-27e1-4552-b7bd-cc9280f57a80 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Roughin
255f3021-bda5-44de-a5b5-cab5aa5e59df |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Cut out
bda34d4b-f246-4c6a-a54b-2b836368139f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Fit off
0c7fbb6c-1f00-45c7-a7e5-2d8865a4ab92 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Commissioning
c2540c01-66ff-4234-8cd3-eab12c21b692 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing
6f258ea2-f71c-4fd9-a47a-86d153814cd1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing
032027b7-e6c9-4896-ae38-dd49e88453ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB1
c5256339-b4b6-49f7-8410-a61793780cf5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB2
ab2e521f-32a1-408b-a620-c459b10f28a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB3
f34b214d-b5be-4ba0-8546-7f517390fef1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB4
b7ae465f-429e-4196-be29-396508202bad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB5
9b8e8dfe-a540-47d8-8a11-baf8b7d1a173 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 610 | Mandatory testing | CB6
827e7af4-5519-4b8c-9fc2-b5a5488aaa97 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611
e7fb296b-5971-411a-a9c9-c64ca92ed92d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Leadins
ed864f67-b1de-449d-860e-81d38c827035 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Roughin
cd7c55bc-2bb6-4a6a-9a30-92a3848d5594 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Cut out
7bb6b138-0d4f-4031-aca1-4ac7309f0d66 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Fit off
0267e7c8-3091-4697-b248-de7d16ace575 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Commissioning
8196e09a-2f21-438d-85af-fb9cbfe752cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing
1f7af10c-02ec-47c5-97a5-26f31599fe0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB1
de8b8085-a160-429e-9a17-68c359eaea48 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB2
ee74cf1c-ba7a-4f6f-ab2f-d5f283270ef0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB3
30f557f2-7350-4ca7-9e2a-cb351184bd7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB4
604adec8-f4b2-48bc-b012-043199091f99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB5
25001478-1db0-4032-bc7f-94063b2e877f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 611 | Mandatory testing | CB6
dbbb5b9d-4131-428f-8193-25145a1cb91c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612
d9f26570-5166-4fdd-b0b6-23f7c5207e2c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Leadins
1f797682-9b73-4731-8bf4-2532caa246c2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Roughin
83997374-b23a-4c02-8821-b1bd8c5e3a0d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Cut out
90eec156-de01-4ee2-8f39-267d3fd7d225 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Fit off
6f6ed20c-58da-4f19-a2f7-3d79023ab1d5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Commissioning
b2530929-9950-4406-b953-c48344326b47 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing
799be5cb-328c-4c6f-b402-eddcee5c4e6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB1
c0748b56-2f91-4d52-b1f9-81382194d79c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB2
d73b75c9-d49f-4e18-a1f1-ee5c6be6542b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB3
6e5d9880-2f61-4b31-91d5-f1022f113d5f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB4
ca63149d-e2ac-4485-ad55-4f2008538800 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB5
e71899ab-de98-415c-9d35-a7d9fc502afa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 612 | Mandatory testing | CB6
5ae5dbd8-902c-45bc-b484-1bb4a03dfdd7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613
4cf609a0-4f3e-4db4-afe4-fa70d5ff2e68 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Leadins
1a08636a-fdf5-4625-bda0-2c796f782722 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Roughin
d6005f21-c0b5-4645-a8a3-e07e6c8de2e6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Cut out
f542ca4c-d2bd-4a18-a382-e5824751662f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Fit off
1b2a8048-0362-4c25-9f8d-601b65a2695b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Commissioning
02ac0ca5-3f45-47d0-be7c-e8622eba897b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing
f2db5f84-0ff9-4fac-9e0e-3a7264d8a3d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB1
dbd4fe97-f1ed-40f2-93e0-9e4340330ce8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB2
c9ee74fe-b968-4252-9401-565ec7311561 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB3
b839bb83-142b-4b2a-82a5-5a9d8c201354 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB4
a131c0a2-8b1e-4cde-b6a0-ff74a544ddc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB5
734640e0-9190-4769-ab17-afff5f77c267 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 613 | Mandatory testing | CB6
623b8fe9-3883-47b1-b140-f2076a63255b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614
8f562a89-44d9-4b94-8c58-b1415e195191 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Leadins
fb5c7075-6faa-4a09-af5a-e3fa7371d6af |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Roughin
45cb2ff5-71a8-44b1-932c-e7eb5cc87e64 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Cut out
46159aa5-afe9-4b6c-9382-8bbacd4bcb66 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Fit off
a93a7b84-f31e-40e1-a375-38ffe60031fd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Commissioning
0a05db54-6d41-406a-8051-8f03e22ff93e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing
8189e1ef-f317-4381-a830-f71a155b9013 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB1
5a892411-00a4-409a-8c52-f838e5f22efd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB2
5145b1d1-cc49-4c98-be56-badca7200f7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB3
aa455ff0-5a60-4c1d-a1d2-4d67d16fa44b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB4
dbc63beb-32c2-4782-9d03-d34ab45ade7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB5
fdd78a73-c8c5-4551-8efa-65b9f330c179 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 614 | Mandatory testing | CB6
2465c7e3-71f8-4228-8f85-5f0633a8fcec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615
fd70a296-b721-4864-948a-1814af804a35 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Leadins
f63dd4c3-f0e4-4e95-9851-6a23226a8618 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Roughin
659c02d7-2477-432f-ae9f-6842849b08a4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Cut out
fb18bf17-2fa2-480e-b5f3-f5225b294f5c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Fit off
60fde049-e868-4879-98e6-e28e0e635d7b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Commissioning
0b61d55b-3e49-4ec7-8b11-f95da779f0b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing
5ac86c5e-f394-4f9e-9553-23914af78aad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB1
41fe642a-8697-45f6-b3c0-28df3330b140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB2
257da8ec-3fee-4e91-8382-8e4e8602fc93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB3
491007b1-6b06-4326-8782-ca6cb7f6fb33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB4
68bf57f4-9c83-42bf-bbc6-5cffa6b13834 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB5
73da9f7a-0ee5-4636-ac37-2d10acf65a1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 5 | Apartment 615 | Mandatory testing | CB6
e9a73605-f31f-4c57-8403-dec3f0dd619a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6
d4fe1d25-9525-4aaf-b647-85b6d7c43e11 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701
bc0b6888-3839-4994-8938-22c93b521cdb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Leadins
b751e606-5c44-48a5-96d6-555c1acd2a81 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Roughin
dca1f586-dd8d-4869-bb32-bd4c79c6b24c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Cut out
b3873981-2f87-4406-9474-20e7e64955e6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Fit off
59b906e3-cd57-47c3-8cac-8635d4357297 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Commissioning
cc9ccbe2-693a-40e5-9e01-e6fa864aab5b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing
a26ed7f9-eadc-41f9-b28d-7c6e4c78cf7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB1
de4717d3-fb3c-4a01-a217-c47f552ae045 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB2
05164588-4a40-49f1-990f-6389c7b2bd2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB3
0499dbec-e629-4a2d-b51a-6fedd5b556d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB4
668a3a0e-ae04-4bfc-be32-84d120d471c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB5
f9cc5398-1d1e-4eae-a226-9cf01ebe4e7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 701 | Mandatory testing | CB6
0d14be13-2f57-4300-9022-f81b3696c2cc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702
f23e672b-6c7f-4397-bc9c-aec7867f9985 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Leadins
b4d0836d-5c3e-4a5e-8703-02f5c0ac0437 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Roughin
8d503341-4833-4012-8b65-4f130e8a1566 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Cut out
50eb88bc-fe15-43a3-9402-4d38102c68fc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Fit off
2601fe73-4895-41cf-a17f-2389be10cc56 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Commissioning
a60d2d17-b6d3-490d-8c7c-f12cb8b424c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing
5709d70b-6b6c-4166-8b89-ec65b2a40661 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB1
1f97c8a5-3db2-4971-99f5-11d52c4753bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB2
b8144d3b-7e49-4847-8906-2f0c03be52b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB3
254bef42-3d27-4d4b-8aa7-e2d8a806f259 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB4
e45d02f3-6d78-4b7d-ba4d-d8258459b078 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB5
6850126b-b96f-4738-ba46-7280b5db316b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 702 | Mandatory testing | CB6
17db2f3f-709a-457a-9d5c-ed4214def9d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703
f46fc8dd-6fb3-412f-b930-b89af6fd4836 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Leadins
c29be639-d53f-4aa8-b753-3c8fb3f67c0b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Roughin
695bf715-950a-4ea1-9b57-fb724adeb445 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Cut out
84cf092b-429b-40cc-9fdf-073687427582 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Fit off
ce1edf7d-feee-4fd2-a70a-1e4cb7e651e3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Commissioning
ee1c9aac-68cd-47ea-bda2-dbd457dc2714 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing
573cecc2-b68b-456b-a5a9-7ac63ca63179 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB1
774e9fe2-fb55-470f-a730-cdc8b58e096e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB2
93c9cf59-f87a-4d2f-8cc2-fa0bef80fe66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB3
1e087569-f2b6-4717-aa44-cc5c3b90b578 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB4
5ff08aa5-bb44-4a79-911b-e09c731d98df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB5
902e3752-7a43-47fd-9570-948fc8a9aaaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 703 | Mandatory testing | CB6
79f73678-aa50-4bf3-bc54-d6ca27de8989 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704
401c7acd-0c76-403c-bc3c-dde701716e24 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Leadins
6be4eb5f-2ad5-4e3c-89a7-02387be8ce5d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Roughin
b56c2a0e-9470-4475-a984-7c72c07a3511 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Cut out
32f52315-23ff-4431-bf00-eec0b1db10d7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Fit off
57c2d1f1-d749-418d-80d4-f46965f50d20 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Commissioning
d09ab789-10be-457b-9018-103b8e9588c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing
9794fecf-e722-41f6-acfe-d02342cb9299 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB1
d4f7b83b-04f4-4544-8c5c-29ec20fc7419 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB2
fde61cee-73c3-402d-b8ea-a42946fbfe44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB3
34bd5cb5-7505-4e45-bcb5-1294878548af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB4
e9a2c4b8-e7f3-4a45-83b6-104b3541163c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB5
22c37311-fd17-4707-bc96-ea67b4970c24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 704 | Mandatory testing | CB6
0c73dbdf-7c49-49a6-a687-49e9bd9d8c7f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705
20d847cc-41a9-451e-9d24-08555791b1be |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Leadins
ac34e073-b9fa-42b0-9d5e-549f642d1003 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Roughin
9f22b825-617c-4cda-8fbd-29dcdc11f1b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Cut out
dafc9581-94ca-437a-99ca-e9a2c611b300 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Fit off
12a43146-6f1f-40d8-b286-67f56b374b27 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Commissioning
c2d0be90-e1dc-4a5b-b42d-794ada701a0e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing
c79fe98a-985d-41ef-b005-dada401ea337 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB1
ae59a27f-5bb2-4ea8-89d7-c9e97061e4c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB2
0fc6023f-3526-4b0f-afd7-311bac591568 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB3
78137577-2d94-4a6c-a1ef-84453fa719cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB4
3694d298-65b8-4591-8c69-f7f24e756dfc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB5
bb6984eb-99d6-4265-b355-76284a102080 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 705 | Mandatory testing | CB6
565a7f60-d94a-4c43-8e77-ac5034ea4c05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706
2ac133ae-8004-4b06-bf74-a5fdd3fadc51 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Leadins
0a442d31-8eac-4bbe-9bd5-316877c8cfae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Roughin
68a3230a-070a-443f-81fc-060b2919613f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Cut out
54f3116d-e9bf-470f-bfbf-de78b4fe65a4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Fit off
9d673da0-7332-47d2-baa7-051a064cf964 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Commissioning
ef16ecac-36cc-452a-9118-cef38e5734fa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing
fa5d2435-3ae5-48fa-ad26-5f8b8016c3de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB1
658e7dc4-ece0-4f42-9896-840152acfabb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB2
ee3681fc-c3a6-40e5-8deb-98cf7387666b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB3
fbb6e926-7a48-44a0-a878-c952d3c54185 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB4
26d4ccfb-ddca-4e0e-8a79-63f3aa324fc9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB5
3b5be681-1cfc-404a-a2f9-8123d8c0629f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 706 | Mandatory testing | CB6
61c229f2-8d3d-4747-8fd1-c903d5553e63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707
e0edbdfa-51b7-4e22-9204-e03a17c595a9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Leadins
975b3c23-c631-4b1a-97a6-523b11010b31 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Roughin
67514732-6cd6-4bf9-bef7-611b15529e77 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Cut out
390bfe3b-d847-4cc5-b715-59852a07fb33 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Fit off
0e9256b8-82a0-48ef-b721-9ae72973dd7c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Commissioning
3bdab0dd-49b4-4441-8455-bc0f4e4f9da9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing
2d3398f5-247f-437e-a5d1-1f6c00376834 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB1
71a84271-dbed-4126-a7df-246fff5555c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB2
e137920b-a1a4-4bfd-b112-83a3f41e8060 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB3
13a27722-db62-430d-8885-0c583646b927 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB4
46746004-d234-4c18-a71b-36c30389584a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB5
962155ed-14f1-41da-9a36-19bf5e79966d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 707 | Mandatory testing | CB6
2c90f8bb-2318-47d7-8dde-e5b254e67ee2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708
9101ae6b-a0e9-4954-95b7-ccfa4c3a1784 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Leadins
e8a8667a-d18a-4176-bf5c-2bb8d9576c11 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Roughin
21047b54-a015-44a6-b379-d6c213e484b4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Cut out
b9c678fa-e90f-4aad-be05-227d716c0a5f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Fit off
096c148b-98b0-45d4-945e-a1447517098e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Commissioning
c27b2145-333b-4e5b-a3aa-340cba0e08e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing
6803c666-22ac-41be-982e-4be724e07b5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB1
251501be-724b-49e8-9560-d7394ca9ed96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB2
c67a6340-4ccb-40c0-b9d4-63e2c57b3102 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB3
c4d02711-9272-4742-9719-ac1dfc66fdb5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB4
31e40562-d75a-42dd-9360-a5a9e25b16c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB5
fc8cbbe1-edeb-4b53-a078-358e386d6c8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 708 | Mandatory testing | CB6
fb9242d0-d0c1-4a51-b92e-b99902b385d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709
09d0f129-804f-440b-877a-4ee2831e50d0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Leadins
b425dffb-e2c9-4c6f-99d2-d83899e4ec02 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Roughin
05923f35-ba28-4b09-89c3-28e5bac73bcd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Cut out
fa386d0a-24dc-4732-a198-eaa5db3d2a2d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Fit off
eb265f7f-f481-4e80-9385-8dab9f803ef7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Commissioning
5b995633-0c47-46c8-9182-ea615efee954 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing
4e14f95d-d619-40ff-815b-9d9f3e27ba78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB1
f6be327a-1eb1-430c-b047-c4c1aee0a0ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB2
2395d770-e81d-4f77-a741-e1a213b9002f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB3
c28dee4a-e8bb-4ec3-86be-df37a5db4e32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB4
16f6b95e-a254-4ada-8454-2564634fb846 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB5
9122e336-b364-4668-a04f-6793c2b9201a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 709 | Mandatory testing | CB6
55ca05a7-df1d-42ca-b2a0-ad53863f1109 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710
3e629dbb-05b4-4dcd-9293-3052699fd0b0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Leadins
aa4c8e49-6f21-4a69-98e4-217f0a4021e5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Roughin
ad7b47ef-bd66-4625-91bc-98ab09249b02 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Cut out
31069796-2b98-4721-bf96-61bb3ac86071 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Fit off
9bf7ae28-38b1-42ec-8417-7e5722b578aa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Commissioning
e9305415-8bb4-4c3f-b633-08b6e37bf521 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing
4640b225-ecb5-457a-ad75-5270df77b223 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing
68206e77-dfac-4a0d-94ae-b4960a0a19fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB1
0aeebe90-87f7-460f-91ea-806f51cdbabf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB2
f4493de7-00cc-4637-b8c3-ba2d83f072e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB3
f58fcd47-3cb9-456a-ada2-40ff8c52a949 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB4
dd6dba11-2137-40c1-836f-63e2e03da401 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB5
ba20a921-d53b-49c5-abdf-0190ea8120e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 710 | Mandatory testing | CB6
7cdab34b-5cb3-4d97-ae00-bdfe7842b143 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711
522a3b93-ed89-4e48-9af5-c98a829d40a7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Leadins
58084e28-51df-4a8b-9852-66127c396359 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Roughin
3710c06c-a185-425b-ada4-84ec46bb0925 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Cut out
67e20f77-ff66-4ae4-b9a5-2c3cbad6f0bf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Fit off
dd405f78-35ee-4afa-af80-00921da32b93 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Commissioning
d5e618ca-3154-4e9c-9d27-0375a4a0905b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing
d83bc9ca-56d8-4a2a-b1b1-a23051966698 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB1
f8e9aa57-4ff2-4270-9f30-55b7e7742696 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB2
63065e52-6929-44c3-a3e3-bbd24e757440 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB3
2441e0f3-3eee-4e90-bb9b-946be4e87d3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB4
4665c2f1-bf7a-4412-beb9-616d6c2cbe14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB5
4b7f4f2c-141b-42a4-8058-5cceccc0a401 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 711 | Mandatory testing | CB6
4e6a98a2-04d6-4ca0-8b42-4b5de7e82daf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712
38c6476a-d88e-428c-96c5-bed4a57a5467 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Leadins
eb9b2e58-478f-41af-b16d-908922969cd6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Roughin
14d22efc-e83c-4c14-a285-a3b74eef0910 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Cut out
9251191a-daa2-4c92-aa02-df590fab48cf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Fit off
7566ff41-59f2-46d7-b94e-0f8807bd5143 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Commissioning
7f03152a-d8ce-484a-b3d8-d88dd40cbb78 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing
6507ef6f-5695-41a3-9540-16d7fb7b5a13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB1
49c9e7da-7485-43e2-9a4b-eac79f976be0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB2
c8ba32ac-c0fa-4f94-b4aa-d4f0b07263f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB3
964be3bf-c9ba-4cbe-9bec-caa9ae6ce3e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB4
e1cd7038-b600-456d-87a4-b34395998426 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB5
a62cdf91-a9de-4a6c-8bd2-0b5277905f0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 712 | Mandatory testing | CB6
f3910b23-8540-4592-92e7-2e6beff0d44b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713
fa896218-f03e-4554-99fc-e3b0e99f26fb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Leadins
945fb7f1-3136-4fdc-982a-a77303a29066 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Roughin
6573ed62-9bb4-4efb-b94d-b2b0c3a916b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Cut out
5b4fe7d4-5a6d-4331-baaf-497715156c0d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Fit off
6bfabd89-035b-4043-979c-30c161e16a63 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Commissioning
84566e58-4f43-4af2-96d7-ae591ff8d708 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing
e2315d6e-ea54-4e4d-8754-4290053469b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB1
d79d4692-5193-4a75-a618-514448e70914 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB2
30e15373-2f01-44a3-abfd-7aa6195d1967 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB3
e78b5543-509a-460b-8f34-a31544664960 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB4
48d58905-449c-41dc-977d-6dc78a11e57f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB5
6e851ca9-5139-4b6f-84fc-be8d58dc1da7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 713 | Mandatory testing | CB6
d266f255-8acb-4c85-931e-35c911deb457 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714
5e3fb3ed-2f7e-4d0d-845f-505654706797 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Leadins
87bc0b95-29a6-4862-bb19-d933f9bfe95d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Roughin
66bc8149-7fe3-4c79-b247-bf574388b21d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Cut out
0cf08e47-fd37-4712-988b-f9a724ee0a9b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Fit off
5db8822f-8751-4c60-a5e1-978eba6064be |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Commissioning
acf02dc0-8ccf-48a8-9b19-7c3c9e9772e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing
14c839c0-ff10-4c76-9070-14ebc7f3fb81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB1
b39f4509-3b09-4040-98de-a0141753b381 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB2
628bd0e9-04e7-4277-bec4-9cc9d3a2e70b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB3
676607f2-e5f3-4cfc-b59c-edc5caa4f2f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB4
ce374121-274e-4364-aa56-e79697b9c56b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB5
ad3ef506-3c3c-44ec-a64b-d6aa66ea36e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 714 | Mandatory testing | CB6
87e5f4cb-6463-471f-89ce-67881d4d2944 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715
b5ed0c51-54b1-4d4f-bd4e-c0cba0aa4173 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Leadins
1dbd10fc-9648-40f6-a3f2-4ab9b889346e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Roughin
62861801-cad9-4fbc-9966-898df2273d95 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Cut out
2545fdfb-8126-4306-9969-52eada6791c4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Fit off
3ea9aa7b-b687-4e15-bacc-18a2d28831b9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Commissioning
7618739a-7554-425c-9ec8-776ef066cf7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing
3a1ff60b-63f2-4e99-98cb-a40d05747684 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB1
2e58b2aa-049b-4cd2-8839-bdc5c25b7e9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB2
2795b639-cbbc-4fc5-ba62-e2d5e40219db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB3
0d8d3199-7862-4d44-845a-189c1e0358bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB4
4afc14b5-0e31-4c7f-a116-7b969558d6ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB5
5f1dec62-a61b-4184-ba22-cfcbcb43146c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 6 | Apartment 715 | Mandatory testing | CB6
c46d7b85-2c8c-4055-b528-41be4435c9e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7
ad1a3947-b9e1-459e-980c-56deada82265 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801
590306ec-3b50-475a-afb7-dddffe1a8271 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Leadins
2b46afc2-eaf0-4c38-85e9-2e1f7e98dc7f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Roughin
a8ec1c19-3575-4f2d-9e29-ae2ee2868e48 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Cut out
25ec55d7-0959-4a2e-817b-ff7cfb9ce4c7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Fit off
1c10884e-22e4-40b4-91e3-066308060495 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Commissioning
f23feb57-dcdd-41e5-b801-0872767b5a2f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing
8048ae66-eafb-4ed7-a112-9ccb2dec59be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB1
17d16176-9c60-4b53-8139-a3a761a857ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB2
ba38ee1f-648f-472c-a764-171ccf9ed8c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB3
6326db9c-f483-4e87-9b4e-101fbc27cd43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB4
5f39eb7f-63f6-457c-a58f-97d4ace7ab43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB5
4bde96c3-cc8d-48ba-b1a9-b1a4e2ca7999 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 801 | Mandatory testing | CB6
901d0d0a-bf93-4031-a887-ad37f3679b7f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802
03dc90a1-9778-45c4-b88f-4c17e5ccdd89 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Leadins
cfbf6251-6171-4457-a1b4-dea39c0f869f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Roughin
4a4a5de1-8630-41b5-b336-cadd4ba622ca |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Cut out
603141e7-fa5c-4625-b768-a39cfda4b9d3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Fit off
abf4dd50-a5e9-421b-bc67-deec98b19a82 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Commissioning
a36068ae-279f-44fe-b9ef-07dbd32749d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing
1f1dfdbb-a662-4784-a418-674ad6d6ecc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB1
cd070d0f-e6b8-4adc-b0a8-f28a8da4d307 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB2
a15d2c8e-0a80-44ab-bc72-3f9dc7ab6298 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB3
4787b2dd-0662-46ec-ae8d-4fd98dcfea5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB4
c8410e5f-b866-4f45-85fc-dd4e66015126 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB5
c9e53e07-7663-4eb4-b2d0-bcbb4ccc54aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 802 | Mandatory testing | CB6
5471589f-45d6-4500-9232-7b7219bba251 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803
8167b558-42d8-4302-a157-8a09e06f4b11 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Leadins
9e3f75a7-1e6a-46c3-a748-904069eee5e6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Roughin
4e4502b4-ed9f-411b-b708-552d6b77bc7c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Cut out
e0fec508-14eb-42ef-a20a-b0b7b1cf1e52 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Fit off
7fad64f5-6be2-4b3d-9179-b2452354f954 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Commissioning
4e70cb0c-737c-45b5-ba0c-84163918b9f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing
77bb00bc-375f-4d4f-bf2b-9a566e5341d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB1
1d8f6e0c-483a-4ecf-bc66-f10abf662e63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB2
af64166d-a962-41c0-b8dd-1eb3b5f9d726 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB3
ff2d5e89-a58c-44fa-9fa6-5fc67a155ee2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB4
14a75af5-69dd-4420-b6f3-e924f8e2faaf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB5
eedf061d-201b-41ea-9365-009451626d2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 803 | Mandatory testing | CB6
05ec52d6-8923-4ca2-b2ca-1275e02b9049 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804
ed4a314a-f485-4447-9a7b-ce36aa52faf0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Leadins
072b5359-3ddc-4f34-a3d7-151a42357b63 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Roughin
3f39feab-5407-4392-a269-dba434d8fd78 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Cut out
921824c0-0109-43bc-ab09-b51836c5b4ef |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Fit off
43283d84-b43a-4fa5-bec8-ef2dc931f90e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Commissioning
91d4d3bd-0bff-4b9a-9401-5926d09112eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing
320dbacb-7c8e-47c1-a7ba-b1d5ae058a59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB1
661a4bd6-c852-4a21-b266-5fbec2fb3ff1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB2
3f3b120d-12d9-49a9-9066-3525b45db295 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB3
7178a61d-ddd0-41a0-843e-a705843b0f15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB4
fe87fb24-8be0-4bf0-85bc-6412d69212e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB5
d883ef5f-d139-4621-a731-9ab1692b987e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 804 | Mandatory testing | CB6
9f3cf23e-4ed5-4903-bd9a-eaa4a7558e08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805
20b6963f-d8c6-428b-9276-93125cc6b8c7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Leadins
acd8e2ae-d235-4e23-a7c2-77ffdc45ebe5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Roughin
173d1d5b-b5d1-4951-a10d-46e067ab67eb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Cut out
e5889f8d-3ba6-419b-8e0b-2c64ed6a9da0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Fit off
b13b62ef-f026-43a8-b075-b5aa8950c05d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Commissioning
486ec982-cd06-417c-81a1-331f0fdc07a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing
0891184d-1070-4d5c-b293-8459543eb4ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB1
e7181251-8318-4125-ae1f-64a8532b3543 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB2
43b1db7b-fe1c-40b9-a6fc-a4e2a96fb6a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB3
8620d5c6-3ed7-4fe9-98ee-433578197b85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB4
70967831-954c-4ad5-8d45-d6cdebf0e8fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB5
a0918c96-e3f3-485c-ae96-7b7c8f13ca85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 805 | Mandatory testing | CB6
ee8c80c5-5c8a-41b8-8f75-726be4ce79b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806
c0d87e96-d694-4608-89a0-9f21b0b3cf54 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Leadins
5a16724d-ec57-4e0d-909e-3e88902c9bd9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Roughin
994a8460-526b-40c6-943b-5edf71162c9b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Cut out
b55143af-e527-4684-9489-875e67fe89e1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Fit off
f55d2a41-cadc-467f-a774-120cbb2449ef |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Commissioning
7be2bb00-040a-43ef-8630-3f674fafa324 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing
a9faba7c-e049-4977-be46-4052045e4d2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB1
79050a02-c4bf-4598-80a9-99bcecf4db90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB2
c469e4ed-e4e1-4e70-b39e-148f06511e92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB3
fa245a38-194f-4feb-bf5f-68293a81de9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB4
aaec4091-7ca8-4868-be15-623c0a17fcb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB5
f1f68fcf-c5e2-4c68-9bf0-ec9c8aba090c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 806 | Mandatory testing | CB6
44330e28-cc6d-495b-b310-bf832078bed5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807
42afc28b-05e5-42c3-b961-cc803e007396 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Leadins
9529b074-d6e6-4a85-9251-fc9c23497685 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Roughin
e2e64845-eb15-45c8-9ed9-22942a4bd61f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Cut out
694b4275-6543-462d-8e0c-4d77406037fa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Fit off
31ef6ddd-ec40-416f-80c5-654dd08cea61 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Commissioning
409bef01-afd8-4e58-a2f3-ad9434a55177 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing
f4af2616-ab57-4c8c-b4e8-f24f72129cb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB1
292723d5-b030-40a2-991e-fdbc3a1e0c9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB2
78ca1893-d560-4111-a1aa-97e8795331e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB3
91abb855-04e7-4391-91a6-dd43935a0784 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB4
0dc63dd3-048f-4b85-9e99-32a1f8ea9703 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB5
3340e956-422b-47b4-b969-cc09f0525a21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 807 | Mandatory testing | CB6
318dcf44-5b3c-4dd1-b416-db1522f6e725 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808
f6f3f68c-00ff-434f-a970-f3adfe1c4c0a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Leadins
31a05d80-646a-4de9-a7cb-e6f58e3dde24 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Roughin
9484c2c5-3eb9-4f61-87e7-6be74eeb352e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Cut out
2dc43886-59b7-403d-8979-8c4fae1994c2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Fit off
5872fffc-b126-44ed-95bb-ec8be822ecc2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Commissioning
6c6ee2c3-af4f-414d-8ee4-f6e2300479cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing
6afcd7b3-42de-4f8c-9ad0-d28679d1692f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB1
64a8b135-dfdf-4e53-95b6-0857446444c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB2
470ba164-17d3-4a2b-a035-b808f44d9d3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB3
eb0e4735-8aba-4c5c-a94d-8f13a5469894 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB4
77decf35-479d-4df9-ae81-f0a1d7e41b60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB5
f91430d5-b9b3-44b4-8055-670706a93abf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 808 | Mandatory testing | CB6
442f23c8-78eb-49c3-94cc-236ce9319d4b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809
0e115747-0215-4b2b-b460-03e752263114 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Leadins
0b1255d7-02ce-479e-8dd2-28b127bb9a11 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Roughin
ce70a163-e4af-4ce3-80ca-99c9924d5201 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Cut out
1fc08a86-6149-4bc7-802f-8d79d7a4e74e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Fit off
45216608-c4e0-47ad-9c01-6507c5d7d7ba |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Commissioning
3d099b0e-6d6c-4c7a-988e-316de3c27f85 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing
a829fd0e-3683-411c-8e8a-5c2c67789c7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB1
6d25881a-4a3b-422f-b8a3-6abd5dbcfc59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB2
bfe1fa9e-cce0-4465-9d16-835e481d3bef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB3
e1a0f88b-05b7-4760-8030-18f31c1f9cb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB4
84b47f28-e7f1-40e4-a1a1-df4417d55da3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB5
6842f90f-5731-4e4d-97fd-eccdbdee48c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 809 | Mandatory testing | CB6
a081cac9-a02b-4bf3-8dd2-01afba12310a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810
fef78868-7933-4a41-b2b8-8959d0d28980 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Leadins
bb7f191b-275c-4790-bec5-d1293f15ff07 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Roughin
0b413061-4e99-4190-b6ac-dd8c340a0343 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Cut out
9a817079-36b3-4a0c-ae62-5f368df49a1e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Fit off
36a9e40d-ae97-4c24-9972-c9fbfeeb347b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Commissioning
944a0ce1-176b-4ded-a1d5-8bbd8f8a773c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing
fb7d0097-c4b1-4525-bcf5-871f05e92a02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing
88ab66df-3d65-4d29-aa8d-16c144d3bef2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB1
37aea2d9-04f6-4979-b958-84668dd8ee7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB2
a0ae0247-17ac-416d-9c3f-9d197b7c8a05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB3
d683266b-2667-4e94-8092-3ddbe7652497 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB4
7dda221f-9b29-408e-b225-75547ca8d5be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB5
383d2ff7-8e67-4efb-aa54-55efc8f0115f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 810 | Mandatory testing | CB6
83945dc6-77d3-4002-8e61-0792909bac50 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811
64af680d-500a-4ce8-8b86-bc59ae864e17 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Leadins
871c3961-444d-4dc3-9bc5-7052e1934508 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Roughin
61e0350c-5615-4943-9b01-5af4dba1792c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Cut out
3d5f4a86-10a7-4b6c-96e5-f0a57cd0ed23 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Fit off
dfe54152-d667-4872-a282-fb78f3d81256 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Commissioning
6df67216-9e32-40cd-9754-1466ab61ae13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing
04bf71f2-6bff-4702-b9da-2d7d0285075f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB1
f99f279f-c277-46a0-a22b-a70b1a8d2aec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB2
1f1adea6-1b06-4703-98f4-06d036cf662e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB3
e304ef6f-bbcd-4dea-a4d3-4513153bda84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB4
0d5d9600-d351-47c7-8b31-ca5ab9af6ae4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB5
8963f938-b9a9-4e01-991d-2bef2ecbd737 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 811 | Mandatory testing | CB6
d3873591-6538-4499-8edf-986b24ef4f11 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812
4aae35f2-6f1e-4a6a-94c0-f8597135d022 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Leadins
d24c14df-72f5-42d5-8c66-efcb7dc54e97 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Roughin
9bfa6582-c764-4ea0-96de-bb69c85f5af0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Cut out
aa645367-cc7d-410b-b089-a27ce8e48edd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Fit off
ae79ee1b-163f-45b1-963a-9d4baf12ed13 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Commissioning
1eab5378-4b4b-49a3-8f68-e447e47f2eeb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing
8933eaf7-d1d1-481c-aca3-ed6422375424 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB1
ecd781b0-8c40-4f02-b405-a4b21847f5f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB2
34cb0a00-baad-4fad-bc72-e93213270e95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB3
ea2b1b20-1dad-485c-94ad-f77c35500e31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB4
230a2294-3858-4748-a5c5-4eed1bbb915f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB5
56e3e6ce-c571-4b28-b0a6-ed7caf8a01ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 812 | Mandatory testing | CB6
4eeb02af-ddf9-4c7a-b0de-3a27e5a59c08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813
35d1b67e-87cc-4bcc-9d30-4069f1c32814 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Leadins
5a6fd68d-3520-4ae3-af1c-dbb0b5dd7d8a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Roughin
2c0f4533-90de-407a-b2c5-638dc06ca181 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Cut out
e54041a3-904a-4df0-93c5-12ce6911d348 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Fit off
a7049c7b-0bfa-4f4a-add4-ce81b59dedfa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Commissioning
dead55db-b167-444b-a94d-1428cb6c78f1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing
cb880aeb-e0ff-4c2c-957c-2664991bd292 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB1
690e8ebb-9eb7-48c9-992e-93d3aa3eba9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB2
43dd1cca-baac-4eb1-b0f2-52b51eff7d68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB3
2980a4cd-578f-4ddd-86dd-9c83045e4768 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB4
6791c20e-7934-4906-b971-ed894bcf50e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB5
aac320fb-c748-42d4-a577-ac983deb0937 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 813 | Mandatory testing | CB6
79fa01c5-db28-4ea0-a67a-260a956eef45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814
5141b9ee-eb50-4c38-a19d-17539c6abde4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Leadins
173b8021-e3f0-4aac-ae11-ab9c9cb0c379 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Roughin
5d94c479-2903-4a05-a4ae-428c1d388a44 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Cut out
7a4f42bf-d919-4662-a15f-a0987ec0e47f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Fit off
86666f9e-b7b2-4c0e-b8e5-b4c98d9e57c7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Commissioning
3f3093ea-dbfc-41f5-8d15-f41e8f18ae2e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing
1bcc9db1-e05b-406b-97e0-e4b20cf0b0da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB1
a4257e0f-011c-4c7f-941a-361e77ffb43e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB2
1d4903e6-68ad-42f3-80f2-3e1ca25620dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB3
ec3413c9-6964-47f9-ae25-97a9bd3e9306 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB4
97126518-ead1-454d-9618-71146f6499e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB5
c3f982f6-4632-4113-a236-51ed85f55bc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 814 | Mandatory testing | CB6
57d0c2b2-2fff-4031-b791-9b49098b1306 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815
3389ad66-6ece-4060-b923-f106541a651f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Leadins
513e5d3b-0831-45fa-8c42-d8cbd4425a43 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Roughin
5079a371-9aa7-4108-b53f-b6fcf9b0da83 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Cut out
058d7ec6-f78b-4cdd-9b9d-4094102d0317 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Fit off
8a783344-c1c2-4de7-99b0-723b804f2c69 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Commissioning
6f563181-11f6-47ef-8a48-99f266d0c162 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing
ea1c4dfb-09a4-44c7-ac20-729b4184de74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB1
2b5bcdab-5da5-493a-b6ed-31d243d8c8b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB2
d2eba460-3a8e-4a6b-82cd-f98597784281 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB3
ca9b5712-285d-40f1-8739-dab596002223 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB4
ee6d472e-f9fd-47ba-ab66-b30ea1cc63f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB5
059c5353-2a24-4ef4-b118-a4b78958c1a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 7 | Apartment 815 | Mandatory testing | CB6
e59fc6b5-dc47-4d25-8d25-b917c2990287 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8
8f6186cb-485c-47dd-9525-0af6ea757348 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901
ae60135d-6cf1-4511-88bf-f593b1c65d23 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Leadins
c2c9b275-52c9-44f8-a3ae-0e79f0c30292 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Roughin
88964be5-7fbe-48a6-ae2c-67fe58ce2021 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Cut out
02196ea5-e9d2-4b55-a46b-4d9a06ff7dd0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Fit off
1feda9e5-cfef-4cf8-91ed-59271c3586e2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Commissioning
08bec60b-adc0-42c2-bf3a-efa54ed6095c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing
9e7e675c-8a47-4825-838a-c588d6f1028c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB1
e647a32c-8dfd-4194-bb58-ad96d10cf83b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB2
5e02b63b-d356-4bd9-8584-a25f7a0952c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB3
beaebc8d-9422-4eef-a04e-270e6ee76a5c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB4
b44c69bc-dce7-4fdf-88ab-d452fdfa8d26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB5
65026f9a-d8b2-4a58-af59-6f50b39c76e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 901 | Mandatory testing | CB6
7f304b7a-91f5-495a-8f62-8c3242bacbd9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902
ddd9d1f7-0250-40a4-8276-cd3d8229e8a0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Leadins
aa30c734-8ad4-4a5a-979f-ab03d95a02fe |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Roughin
139e89ce-d02f-478a-a620-aac7b725f5c3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Cut out
e202bfc4-63af-46c7-ba3c-9e07744f6aab |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Fit off
394aa412-ca0c-4c0e-a310-9135ba0990d6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Commissioning
320723a6-f7b5-40ce-8613-02c1426ccabf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing
51082abd-caf9-4998-9eea-5c7da78e7081 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB1
345858b4-e769-43f1-9ec7-67a29a0b4f54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB2
3a904285-c44f-46a8-8016-3f8882880eac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB3
18a8a1d7-e640-4a54-9f6b-fad444863370 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB4
69d470ae-5f7e-4769-ac7f-0370464c4977 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB5
b0874357-d4db-4e9f-81ea-c07e5acd6106 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 902 | Mandatory testing | CB6
a598bb60-58cf-47fd-869d-d625ad1ed73d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903
7b7610eb-56a9-458e-82a5-9fe0de3eb114 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Leadins
e1bf7603-b6a5-45db-a9d6-789c69132f7e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Roughin
d9968c06-a5a2-4af0-a2ba-5113e749ed0e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Cut out
be347072-8d86-4da0-ae9d-d77ce976ed1e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Fit off
041b1668-4284-455a-bc32-e5199aacb54d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Commissioning
277ec2be-f3da-4eb0-be0c-67b75b8f8f93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing
1ec6070f-a2ec-4029-8210-8ef8eeaf9ebc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB1
a411c3b3-4306-45b2-a362-3fd8c9be1656 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB2
81ebfdf1-a71e-445d-938a-0f795b5ffb6b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB3
4a9b0e13-5503-4f6e-ae95-4b3059a61302 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB4
62b56eee-9290-4adb-8f3a-38a974fbc7f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB5
2c569c4b-62ae-4ecd-b17d-0d4e07a9b0e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 903 | Mandatory testing | CB6
ce99c7f2-873d-420f-b811-e31cb4b7fee9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904
5c46448d-364e-4750-a3a7-b513b429d788 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Leadins
8df3031a-8775-49db-b69b-00665fc4d5c9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Roughin
4d1043df-9301-4bb9-80e8-b2e1a5fde6e3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Cut out
91f0bf66-4435-42d8-8dd3-a075c976bb89 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Fit off
66dc0489-3742-407d-81fa-9a1a372829a3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Commissioning
ecc4ab63-0bd2-405b-af09-8839ddf98ad6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing
014412fd-2a2c-4c4d-adab-6facb4e8c1ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB1
a55f8b1b-2495-408b-ab82-de8e40c2bdcc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB2
7e26f44a-1305-4720-9194-701dedb4211c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB3
a91ca51e-3a00-4dd8-ae94-aa244c786b0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB4
56b41edf-5fcf-4c6c-9c75-f246c93ae83d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB5
e818f145-12ab-4d77-9f30-3619f004b4ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 904 | Mandatory testing | CB6
4d404696-d690-4074-8bd3-a5cbacdde737 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905
b7422d83-0494-493f-9156-35a7641ba625 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Leadins
7f10504f-f628-46bf-a6ac-0d81f735932b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Roughin
6cb9c64f-3dbf-4bab-83b3-5679a920b818 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Cut out
47f46a2b-3cd4-4e7c-b48c-2575495bb50f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Fit off
e042dc3e-b86a-497f-bb1f-99788464e759 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Commissioning
2dbdce02-751a-494d-ae18-2a7b046b5e62 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing
8533ebcc-584f-4e5e-8abc-ee7a961a8228 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB1
63a4375b-afba-4c68-a0ca-121df6df0d13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB2
d49af348-8639-423f-9f89-b69cf4c7fe83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB3
9f30e974-5ff0-4934-aa76-9b98689f675b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB4
30739430-faa0-42ed-8e46-7c5015df9d32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB5
73c7a69d-9385-4dbf-bdd8-8e4b6d2d780a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 905 | Mandatory testing | CB6
075b3ca2-fdcb-45c7-87d2-ec19d299addf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906
28868e50-0bc8-4272-ae03-43d606e16104 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Leadins
2f6e38a8-5391-40bf-8539-4df7963dae7a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Roughin
eb41719d-e132-49f0-9c30-e5e4bf8acdff |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Cut out
3d1f5f7c-3e6a-4b40-9b77-af5341a63492 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Fit off
883dd924-b721-473b-a7e7-e35dfc87de4c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Commissioning
4656d5ea-81b0-41e7-aac8-84137bfbc4d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing
0ecc77b8-ec71-4391-b8ff-5976fdecc61e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB1
0f167f71-0292-4077-93b7-8962fbba82b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB2
64a42936-f1c0-4295-961e-2f5bb90ae6f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB3
86a3c157-3116-44b2-8962-3c7008876467 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB4
b0e6b8d4-5c76-4098-8f36-faaa10471150 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB5
4bbe509d-aec2-4226-9ec0-475007486245 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 906 | Mandatory testing | CB6
8e6c5867-4201-4db1-95a7-f2d4460cd6c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907
a52a1641-24c3-4c25-8a16-093b6bd80cdb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Leadins
2001d5a5-be47-49e7-96a0-688cc35dcd0c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Roughin
d18528e2-35f5-42a3-8525-c3efb10a87b2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Cut out
9467a82a-64a5-4457-aeea-ffccfacfd077 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Fit off
75d58268-f341-4733-86ba-11138b3fcae5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Commissioning
91bce3f2-60a9-4bec-bc4a-dce6749b01af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing
81dce178-3a40-443b-8592-18dcd608e6ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB1
53ca5710-5747-4fa1-b893-a8685dd2cd1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB2
2ae33471-84e3-4f3e-bbf8-348c121e40d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB3
455dd57e-f413-42f6-931f-165eb31ea820 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB4
7a97de9b-8692-4b15-ab2e-85f42ce1b673 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB5
0b40e3fe-f6b9-4340-bda1-6468deb4b674 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 907 | Mandatory testing | CB6
8b0c3e78-1955-4122-a4cd-1adda3bec1eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908
7e1ee27f-1dd4-4739-8460-db27131602db |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Leadins
a248294d-f7b6-486c-ac0a-073368b2cc3b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Roughin
322d2185-cdac-4c51-a339-cc8cfc73061e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Cut out
4afd277c-cba4-4902-84f2-5a9e7952de18 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Fit off
e233d9c2-ea18-4c9c-bd08-7a0dad448c32 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Commissioning
7b917718-91a0-41af-a448-171a4076cab2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing
51696344-072d-4d4c-95ff-5007dd1f738f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB1
603a2b9a-0cce-4c2c-bd83-c8087ce34a2c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB2
43c8cbba-1d28-43ff-b558-b2e73c433bef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB3
1a5767bf-0f75-47d2-923d-0011b8a61848 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB4
322d1d9a-5c9a-47bb-a533-01957537551c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB5
eaada10b-fe31-4460-b7c0-8710fda6aead |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 908 | Mandatory testing | CB6
95f73516-67eb-4458-be4f-201c5ee3c79b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909
c876b649-3db2-4b7e-bfb9-3347c64b3933 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Leadins
ca413d4e-34c5-4de6-876b-fb3251b8d6b9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Roughin
efa3d7ac-230a-485c-a7ea-b9f7fce1038a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Cut out
e3a1ec8d-c575-4c2f-ac75-b0e307ef3c5e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Fit off
3547ee5f-42d7-4cbb-b0ca-fbb492f34022 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Commissioning
182bb123-b09e-4039-a9c1-14823b1927be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing
709e6143-afde-4a44-adc2-4e0af63af781 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB1
286d8209-cb43-47bc-b19f-31e4682530b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB2
ca8b17ad-acb2-425e-ad4a-26a37be1c6d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB3
2805aed4-1bf4-4477-bf8a-edfac81d6d6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB4
65d19891-db27-40cf-bd91-586ffb6eb0f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB5
40fded7e-2f29-423f-9ce1-48d61e54821f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 909 | Mandatory testing | CB6
7e956b31-376f-4fa3-b84f-25d569b01ae2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910
82b1ed2a-64a4-48e3-bd98-f85590aa3aa7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Leadins
d6004e11-cf6d-426e-967f-8e94f9ce86be |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Roughin
b9e833b9-6b18-4591-af7a-67bb69821cbf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Cut out
c36d30ef-0fd2-4615-a465-5d196b548002 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Fit off
b52e83a7-a64d-48fc-8df4-871d179c5dd1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Commissioning
7d9079d1-2993-40e7-a173-bc0f9a426329 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing
6fec2279-84b2-41d8-b9cb-8ccb2bb25563 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing
cafed88b-8318-4adc-85bd-bbded5d9e95c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB1
18e2ca35-dd0f-4170-9f22-edb01fb452f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB2
04070e93-4c24-4a9f-9122-98c7388a458c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB3
5b9acc4d-6343-4815-aa2b-afd292d26a7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB4
ff9c0b10-30e3-4c66-a5e1-401557c9c76f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB5
932bb106-117a-4c37-83a2-fdb8bdbdf48f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 910 | Mandatory testing | CB6
742dbb25-59be-4243-a68d-f7497ce9585e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911
abdcbfd9-1718-49ce-8ca8-e6d4165e8207 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Leadins
4b92e31b-303c-4378-b74c-6588abacbdc7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Roughin
3dea56a6-3d61-40ec-8363-7b8c29853ee2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Cut out
0f95eecf-782e-4a9c-bb15-d0a0aa9033f8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Fit off
9400af15-6e30-4f9e-a0de-5e6005a52903 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Commissioning
e101c073-7290-4561-befc-c375118064fa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing
01cf2ace-06a1-45de-b60c-d3240673d407 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB1
018ecfdd-b13d-40c5-9b51-32b4ef14720d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB2
c0a5a281-85ab-4481-a3ad-09cc46383db6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB3
621c09ee-e442-40be-b61d-419b92a47824 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB4
8f20e24a-2175-411a-8b8c-dc8ebfebfae4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB5
38ba4398-82e9-46e4-978d-35434d3490e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 911 | Mandatory testing | CB6
76e8d1c9-bfa4-44d4-9a29-953ca574c2a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912
2fdde9a1-2cba-4fd5-b9dd-c96a9bdb31f3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Leadins
840f6d95-d827-40bb-8dbb-c02d1c3c95b8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Roughin
c01e0b4a-0438-4610-b4ad-6f33680e1230 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Cut out
b875e115-053a-4068-a6ae-249cc50744b9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Fit off
6017744e-2e1e-4c9f-bbd2-a4d381bd6c6d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Commissioning
dbef54aa-6485-4cc0-bf45-b389dfff74fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing
1181e4d9-7254-42b5-add6-0a5f1ad3f7de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB1
6a0e2a94-36c9-4a2e-a95c-704cb03faa0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB2
53c176d7-3430-4188-acbf-ab453223b91c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB3
4fb4b38b-893e-45dd-8fb8-f90a38ceb031 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB4
6584d0cb-e1ee-44b6-9222-3305e9e18a8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB5
bf8584bc-5633-46f1-9e23-dae949b9ba87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 912 | Mandatory testing | CB6
48b9187c-55a1-480b-a9f3-a39097e22b72 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913
e88c9a4f-b654-4183-ad29-06cd75b35fb9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Leadins
62c7df9d-09e3-48c9-82b5-8accd3417f69 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Roughin
9181ba41-231d-4cc0-92a6-9a41d5e0f01e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Cut out
772145da-380f-4470-af1c-adf79b9ddf70 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Fit off
8136714b-ab8f-43e0-916c-e3b2ef4dad73 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Commissioning
ccdbe91d-f60b-49e8-8618-87c024f93a8d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing
ba1633cb-1685-4b60-b200-ddf16e17bda6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB1
d226a2a3-750b-4d72-b277-f55c2f8290de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB2
45eba450-7e71-4014-a150-49afb87a0581 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB3
fdcbc429-66c5-4c67-b1a2-23ec6bbd040a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB4
d3c54b80-2bb3-42c4-8143-86ad04c031d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB5
0fc048c6-75e4-465a-9ff5-66f1b089a6c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 913 | Mandatory testing | CB6
875c28ac-6a20-4249-af12-4a16abe300a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914
9872b45f-6eaf-4544-863e-dc79e0eca198 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Leadins
585bddaa-5a3b-44e1-92c0-40356a5d78c7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Roughin
2395f5da-bd54-44f5-beef-10dbba925d2b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Cut out
223c5404-8e54-499f-9a5e-6accc495ddd4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Fit off
8127e48e-0b7e-482b-9628-7781044459bb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Commissioning
1970bbef-0097-4e20-9c26-2bc4949ed71a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing
7d199231-a372-4a18-9a16-375963d29522 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB1
8d21c833-f9c5-4c6d-ac3a-14295b0b9022 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB2
b5e7ef23-634d-488b-b921-3136310b0d1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB3
cbb801c6-1360-4cf3-8458-10cef27e187f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB4
283d0aab-ee0e-45fc-888b-236b0b2d56d4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB5
6e9320ea-4bea-4754-830d-78feafd3f566 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 914 | Mandatory testing | CB6
1c00e773-b596-43c5-9acd-c793f31d4773 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915
33927bc7-3f13-43ee-8ebb-916e929496fd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Leadins
b9ce03cc-7090-4297-ad29-29e7aac7e0ba |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Roughin
f169b568-f8da-46b3-9f4f-675c74300e0d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Cut out
ed8068ab-46cb-48d0-a374-8f7a9eca88ea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Fit off
f9fd0f79-cece-4642-bab3-c6c6597e192e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Commissioning
b3213d66-d417-4d4c-ab6e-b4278bbb2b31 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing
2c3071b7-7dee-4c4a-ac74-98e2a54f48cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB1
3bd89a16-3273-48f3-9b9e-9afc63ec49b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB2
f7efd52d-2776-45ca-a890-bea7334a8ae4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB3
5aa3a780-470e-43a4-8379-1fea1772d452 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB4
0b9b85cc-6309-4e8d-b3fb-7f280a9abc81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB5
80349bae-24cc-40a8-aa34-9ba98871cc77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 8 | Apartment 915 | Mandatory testing | CB6
c74269c9-33b1-40a6-bda1-85c103df4f32 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9
659098e4-1510-4157-a2af-dc8cfbd79785 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001
115f2624-ae8b-405f-bb40-6a8b078fd32f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Leadins
ade2e2c8-b30a-429f-8b91-938b203ac19e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Roughin
633b72db-aa05-48f8-9785-57a5231a85c3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Cut out
9a7be8a3-55c1-4e3a-b85e-91d735adde8c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Fit off
a0bb2ba8-0a65-459f-b552-3fa02602d301 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Commissioning
cac2cd6d-c33e-4df3-a527-03de9e7d2aa3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing
55042637-938d-4fb9-b7d4-310148c95787 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB1
26ff2341-7e9f-4068-8a8c-c303b6b74dfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB2
75b2a284-9d77-4337-93c4-5bc8df64ea7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB3
1850cd9b-d2cc-46e9-9659-9384015342b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB4
c9322d69-7b92-4d87-85ba-e0799668cdda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB5
788ba54f-8746-4abd-aac8-a98ec4de8358 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1001 | Mandatory testing | CB6
f27f3129-1500-4cea-b94f-645487c572b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002
72e0ef1a-7995-4867-bb1b-b46bf4f57e13 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Leadins
42ceb6e6-6d4a-466a-a07d-e2186286ca4e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Roughin
b3f6e8af-143e-4dbb-bff6-51d752145d9a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Cut out
c33eb12e-0f73-43c9-b2cf-07d23bd503ba |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Fit off
5537ca06-0596-4f27-adc6-32dfa04c6a98 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Commissioning
e17b591d-4c91-4538-81fb-fa09fd1d4156 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing
ed3038c2-6161-4c0c-94cb-e56ad8c808fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB1
06e7fec2-a633-4db4-ab34-73deac2d1c23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB2
df946ef5-d55c-4345-be54-6ee3673360d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB3
18399b98-ba34-4f5b-9045-f488e745537f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB4
e56d6fc4-41e3-4752-b06b-766020e9f162 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB5
b57a4d2a-71f7-4c08-a49f-61048fcd68da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1002 | Mandatory testing | CB6
a897ebee-0398-4dae-9972-47df7a8d8764 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003
d3861af5-98a0-44c1-9411-2729448cefc4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Leadins
7a72f8a4-6de3-4bcf-a73d-a03bc89ac422 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Roughin
bfa0db55-f4e2-49ed-a2db-5b7dda5f22ee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Cut out
8237abee-8dc9-49f8-ba58-270b87ab2d66 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Fit off
a4a3b5bd-df12-4eab-9a0e-013e97b0c5f0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Commissioning
7dd49127-a117-44b7-b42a-9adbf4e7d410 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing
4b1925ca-7caa-4397-b933-696e7c82e68e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB1
01d186c8-4702-4a74-8a75-733ca797622f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB2
467b8666-4b3c-4184-a23d-577e46f777a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB3
0fd95bc0-9faf-45d4-8d56-82fd541fc9c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB4
2a7dbf01-7fea-4d8c-99b8-2452df6d3df5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB5
60685db1-b49e-49b6-92dd-5b148a2a0818 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1003 | Mandatory testing | CB6
8be55111-4279-4635-afc8-4bded36618d7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004
562c4d87-b877-4ad1-8c9d-81ead79962bc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Leadins
44ed48cf-888f-4e96-9e5a-4fe3c37e8aef |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Roughin
bac88824-2b48-4f9b-9687-72377db7965c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Cut out
a9dc976c-ee55-44da-82bd-7cfed7d1018e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Fit off
dfbb385a-ef6b-4e73-882f-e0fa54dc0d92 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Commissioning
f4113497-237f-482e-b5b8-47bc260f1da7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing
f3c2d6f6-9e92-41aa-ab60-7dde4fd80804 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB1
4d80866e-2643-42f4-b036-ff2846eb5844 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB2
5cbccbb4-da24-4012-9491-d30e8763fab0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB3
a4365ff1-8891-4493-be4d-a5f8cfa674f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB4
d25968b6-fc20-4d21-ae12-d979e21586b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB5
5f57c7cc-2bc2-4349-bd4a-768d5d8deff0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1004 | Mandatory testing | CB6
5d13277a-5ea4-40a3-820f-7d65168ddcd3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005
c547e978-087e-4062-a31e-94ce5e8ce07c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Leadins
67c4767b-e853-45eb-9aec-08f9cef67764 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Roughin
ee74c779-331d-4d35-8386-91378b830d2c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Cut out
20450025-e4d2-4333-9783-3d89c5362c97 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Fit off
796cc1ec-ade5-4711-a1b4-570fa827422e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Commissioning
842bfe6b-234a-4912-8bb8-2fb682d812cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing
cc30bc48-eb2f-4f1c-9f04-007de027d22e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB1
361441e6-7cd8-465e-8800-0c2da4f4e097 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB2
83877141-e05a-4041-8ea0-9582dc121596 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB3
c47c06d4-7f01-4446-88cb-d78baba27c1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB4
a986c6ae-ca6b-41bd-9dbd-f06471b6239d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB5
c353753e-7c02-46e4-bcfa-4bab83be38aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1005 | Mandatory testing | CB6
b410a1f6-5335-44a1-8734-4a0f0fe32da5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006
15a5f158-fa01-42f6-b17b-82d1c6493d66 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Leadins
3af293fc-5aa5-45e2-86e4-7feffa98d709 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Roughin
79b31bfa-2bcf-41b3-abee-785a5cce64c9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Cut out
31e82273-acc4-4f52-8adb-0abcdc7ce6ba |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Fit off
395dd8c9-2c06-415c-a157-0a1b60658c2a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Commissioning
1c08a668-3d17-4c06-8ec3-3005ced6e54d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing
dec8fde8-98ff-4a73-afbc-31df933616dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB1
77706eb5-7d28-4b6a-85dd-3bc29fff293a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB2
bc479029-8b90-4ed3-b909-e51f42bf29bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB3
e5b51a17-dbf5-4eeb-b539-12f12d33eeef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB4
9ce170e0-9604-47cd-8a83-b83fb6177c96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB5
5a90f237-011c-485e-81b6-8809c34283af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1006 | Mandatory testing | CB6
1b739c2d-1eaf-4031-9bd0-515f579646da |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007
dc40f701-2fe8-46f9-bb3c-f95078df6431 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Leadins
2b3e6472-dfe2-4670-9070-1e019db1d82e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Roughin
ec3fb526-8010-4560-b92b-9f7f1371301b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Cut out
e247e931-319c-4c66-a5b8-a9320c44bb07 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Fit off
0f9efc72-d8b4-49a7-833c-a4ad4151cf13 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Commissioning
9947223a-6c31-44cb-97f1-ab39449b376a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing
685a2543-3106-482f-b726-a34baf73e320 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB1
6cbbabf1-b222-47d7-bff3-73504b4985da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB2
7470cdf7-c847-4c4f-b668-b39d06da3a4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB3
0ef5d6b7-a307-4397-ba33-5f6c8e5daddc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB4
8f61f3a8-4f84-48fe-b1f0-dc28994fdf3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB5
5f02fd86-076a-446c-84aa-0b503965909b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1007 | Mandatory testing | CB6
0f40ff51-1e83-4e41-bfe1-99527e0c5c11 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008
52530159-1d5d-433e-8d08-28b75727ac0c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Leadins
51af4d93-2ce2-428c-8ebf-f75f709a789a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Roughin
2f5ed34e-6be8-4176-bffa-aa32b67ce95d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Cut out
7ab8de57-4b06-4745-9284-de0560a0c42f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Fit off
b83bea48-43ea-4a81-b63d-ef78be20bbde |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Commissioning
7db9d251-5f03-472b-99be-f1e05667bd25 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing
046ad95c-cf07-4a93-9ca2-3e26c020eb1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB1
ecb38529-e41a-4701-9900-e48fd3d0ce43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB2
f3f5ce9b-f534-467a-afb3-ed22f4189f5c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB3
e645414f-806e-47e0-abbc-e0dd3cf84a7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB4
96f77822-60c6-4f84-8bf2-f275d00af6dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB5
c0baca2e-4853-4051-96a8-5bd2abf18f74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1008 | Mandatory testing | CB6
f2709147-fca7-46e8-86e5-b286d5e13420 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009
f3038e6b-6ac5-4de1-8cee-baf9bb0e7258 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Leadins
abaf0fe5-9759-416d-b7a8-65d75d0e97a8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Roughin
6e1dfdfd-1d4c-4333-9293-d82c897eb371 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Cut out
a1d61415-65a0-43ba-ba90-7a2982d341de |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Fit off
7fa3b4c2-9e58-4a6d-97ad-2d2972d7c513 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Commissioning
6c703035-5e9f-42b8-b266-f0598fe711db |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing
960cda15-210b-46a8-bcc8-67fa54562bcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB1
5549e48e-1e11-4898-ab09-54fb1ecdd2e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB2
ee0df586-0d72-43bb-a56e-fc98f5a5cd84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB3
8f5e1b9f-f722-4044-a152-e364962552cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB4
5951541e-9afb-4df2-bd23-e63809fb3ca5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB5
42a48d04-9ca3-4314-ae64-f6b394dd4ac7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1009 | Mandatory testing | CB6
d86a9d9a-02fd-4d3f-b6a3-8956847663d9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010
4f39b82b-cfbb-4c62-b3c2-2898d85976f9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Leadins
103291d4-cabb-4a59-8520-22e1ddb44d41 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Roughin
baa12ab1-c742-4492-a4dc-db640f779e31 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Cut out
67ccea93-66fa-4a17-bfd9-042907640d90 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Fit off
500248d9-e14a-409c-98f7-6854c8120082 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Commissioning
a2b16fc7-9815-404c-acb2-79ed5141a088 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing
2297a7a1-9219-4eb9-8727-4019652d26d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing
0b83f1b5-fa62-4e2a-9967-21b8839fd36f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB1
559de03c-eb49-46e6-905d-471d1e63a32e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB2
05d054bd-dd35-4c9c-a935-ba6bad58ae0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB3
13b4832f-8420-4a5c-847a-a83850044ec7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB4
a4fdc728-eb69-4bb7-81ae-c89d4c616c83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB5
39e32617-9f22-4924-866f-aea26b6c5acc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1010 | Mandatory testing | CB6
8d750a61-2723-4fdd-817d-192f46038a47 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011
8fc30cb3-e4ba-4a2b-bc91-cff27c4a2e82 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Leadins
67b8e23d-95b6-4eea-b77a-64a55deed85f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Roughin
b016e195-79a8-448f-a41d-09368fee5eb0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Cut out
51146712-eb73-438d-b4a4-c7e1b133b95e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Fit off
0bfbdc48-c160-40f3-995d-efece02f0e7f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Commissioning
5b8bfaff-ae5a-4955-8224-753f52356c54 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing
dab37d78-76c1-4565-8e92-56d8ed84b563 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB1
1425822b-89cb-437e-a2bb-1bddd9937f3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB2
288f8894-5e6d-482b-8ddf-7749f9d33e61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB3
12f3f9bb-35d8-4c7f-9622-63dfd0316b1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB4
d77f5333-fddb-4acb-99a2-ec7217ca3ba2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB5
61a58d2a-2fe8-437c-97fc-5d85f12216f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1011 | Mandatory testing | CB6
69f18fd8-3453-43c9-a5fd-6a8eab158c8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012
0c41ef9f-2865-4d8a-96a1-5afac11f6117 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Leadins
2c329cfb-63e5-4f3a-b3c2-e5ad36336383 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Roughin
9444b6f1-4400-4bf1-bab8-c3b5b864159a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Cut out
0df736bd-f504-41c0-8402-38eae1dd4009 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Fit off
f93a2835-5887-404a-a768-108427dc2616 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Commissioning
1c3308c1-f88d-4429-a532-6bb1b0929450 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing
61d7cb57-a30b-4c7a-80a7-03867002e891 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB1
d5b8b7cb-457c-4e13-ad6f-7591e686cd01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB2
60f191fb-f1d9-4568-b3c1-bd7c2d32b9af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB3
d523a857-5a42-413d-8caf-f39a0f21c99a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB4
4e270579-4218-47d0-acba-aa711e98fceb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB5
f5671cba-655e-462e-a67c-592e5f7a90c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1012 | Mandatory testing | CB6
71f1cabf-12b0-4176-9324-b623a4a0bf5a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013
46f54a19-0447-40b4-a2d7-553fdee58a41 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Leadins
6e380d52-ff3d-4ee1-862a-5618d9b840ba |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Roughin
8912082d-1967-4407-8794-b46092ccb5e7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Cut out
bb89f5f1-ac34-467b-8b49-23ca55d99660 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Fit off
59636616-4565-420f-b530-ee7e0b4212c1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Commissioning
b4325f1b-9795-451b-a3ff-f72f8c595a9d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing
040df0de-a671-4902-b6b5-953f0de5ebf9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB1
1d50b53a-f6e2-484d-b702-ec967cdde58c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB2
e06610e0-be5e-4c0c-9c5a-0481c8b160ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB3
569610f1-a166-41a0-aaf9-4d0b21dc1c23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB4
d1895c63-8050-40d6-8b10-d5cc5d03357f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB5
843fc747-9a86-422e-841f-5de3b0ba3756 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1013 | Mandatory testing | CB6
91dfad2a-81b4-4237-acc6-d94d6d80566b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014
86e22fef-8bfd-4a80-991f-38ff925bd352 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Leadins
151c1521-810b-4113-a56a-7c433a088d72 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Roughin
ee8eee3b-2b65-41e2-9e47-52a1047f2597 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Cut out
13bb7e32-94d6-4897-9311-d5d653cae0d4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Fit off
93567b46-7d50-4457-a071-ccb20e9b2952 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Commissioning
c3672c4d-c546-4bfe-a73d-8b4e9253331e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing
7dcc3f4e-a655-4fc4-9d24-f76feb40808d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB1
22000338-f4e7-4fbc-b5cc-443e6cc6f20f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB2
25510c16-3ccc-4a61-9573-a54cc6e58fdb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB3
5378f7b6-a8f7-4828-aba8-ca589baddb6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB4
5a78ebe1-80c8-48c1-b3eb-dc4c7eaa257b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB5
bfb18968-f4f8-4c2b-b5b4-605b9ebcd1f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1014 | Mandatory testing | CB6
e1d851f6-4d95-4272-97b9-7b91cc9017d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015
21665133-1730-4be1-ac4c-e236069a9e18 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Leadins
19cf404a-4d23-4084-bc58-fb8f532706ad |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Roughin
96d6206f-ba6b-4d6e-a5ab-b1fcf0408b40 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Cut out
edf1a47f-ddaa-4c62-80ab-2c704fc64928 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Fit off
2869788d-7ed2-4c0d-97ad-6e8836818f50 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Commissioning
ca5d9921-61fc-4d42-8372-257210f0883d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing
e05c4032-ac4f-4e7c-b5f0-69c2ccf519a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB1
b4e921d2-d475-49c7-982f-0f6e4cd784f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB2
a3c358c9-8af9-4835-93bb-96590794f3ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB3
ad8414cb-9a8f-47be-af82-67c2b0eb8667 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB4
e77be0b0-e825-4e54-9deb-84c98a9197b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB5
e8926ed9-1442-499e-b3b2-eb2f490c8ac2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 9 | Apartment 1015 | Mandatory testing | CB6
8654f993-a135-4283-877e-d1a1d3b9c685 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10
20d6d167-ac9f-4f82-bff8-c4433f746b5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101
c0488815-853c-4ba3-a47d-bd175c05ba6e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Leadins
4b83804b-e408-42d1-81b8-cd0b0cd58c5d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Roughin
9655d67a-23f0-45c8-b141-c929b4cb3dcb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Cut out
0495b3ad-a00c-4222-9967-108f8a62c931 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Fit off
3807d62a-2eb6-46d0-91ff-a4dbb2b50c30 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Commissioning
284bdec3-d31c-4ce5-ae7a-e8e21aa4ca12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing
d40f4aa9-2b16-4416-864d-3a6d79f2d2a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB1
89a5925f-c0ee-48f1-8a1a-2b865652faa2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB2
b7991aff-7f69-4bf4-aa78-1559878ed1ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB3
19bf26ad-b5ed-455a-beb7-fcfca546c145 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB4
c0752a07-51de-4051-b9e9-ac21ae47e4ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB5
4ed0160d-efaf-4ec9-9ba1-665e9c2d369c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1101 | Mandatory testing | CB6
1296fbde-b1e5-4e39-8133-9d1be2080943 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102
d170905c-0db9-48dc-a7db-cf7b6e7b2c12 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Leadins
375e057f-fa50-4941-87d4-2f03b03de0b3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Roughin
89de5ce6-bced-4e52-bf34-49d2db5f6161 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Cut out
244b69db-033b-4200-841c-0e6324860ad4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Fit off
3767b076-66e1-4301-9e36-5d2317ddf1cf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Commissioning
4a3220c8-98e7-47c4-a346-de04a895932b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing
982e7825-3dbf-4716-9cdb-0f761f288eaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB1
84f7e7da-e91d-4d95-a774-8aa758c4842e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB2
b239eafa-c854-42f1-8cfa-f30095f0c43e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB3
8d0e2c78-85cb-4398-84c6-7df5131f2c35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB4
a6f96e00-e5c1-4f16-889f-e1d1647bf64a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB5
f699b8fa-1a03-43c4-a313-d7cfc2e59532 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1102 | Mandatory testing | CB6
a0f98527-a8d9-4e3b-be8d-2fab88dd14fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103
18e2dbef-c2e1-4bb1-9ce8-6cc779c3290e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Leadins
1c4ef6ed-9a75-4297-8d39-bc253ac98915 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Roughin
b54ca1ba-f0a4-4659-b0d6-f66c9d112695 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Cut out
4e533262-2467-4fe6-9635-840d93c2d159 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Fit off
13976b30-738f-449d-9768-e5f9ec63b594 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Commissioning
1e762820-ca94-48d3-9e68-7ffd335c3567 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing
d01843c0-d532-4697-828d-7ec7e182d456 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB1
4cf300c9-2aac-41b2-8fae-fcfd7472dfb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB2
89825e7a-e3a3-48b2-ab35-7c982264dd6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB3
d60b118d-f543-455d-881a-217d21640e21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB4
19d4a534-ddf2-48af-ac2f-a1bc3d791307 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB5
0d49a090-56c1-47b5-b874-2d835e6e7cb6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1103 | Mandatory testing | CB6
cb273e1c-7320-4496-bea1-9831ba3b641b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104
cf2b5644-0c2b-4314-aba5-b246c5e46139 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Leadins
7a7e9d19-1988-4545-9de7-d4383cf774e9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Roughin
be527ae4-870e-4ec1-8651-8521c6ff8cee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Cut out
8f9be27f-b68b-45f3-a45e-e087096f307c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Fit off
f9ddb368-078d-4451-af98-f13e640160f8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Commissioning
bda76e0a-31de-4e07-bb02-4fc0b35713fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing
a7fcd7af-7021-4020-ad49-ddf0c581949d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB1
3a6a6f96-fabc-4d9e-9133-11f9abeb65ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB2
3bbeab70-3c7a-4a8c-b359-1cea8215b944 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB3
949bd0a5-f94f-423d-9885-8931486a3842 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB4
a5180545-5915-40cb-a891-a2421d7709a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB5
b55e82a7-b29a-4882-9e96-0549b612bcab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1104 | Mandatory testing | CB6
bfedd429-e5df-4339-a1f1-6b9e4d1286ec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105
09116658-4d44-4311-97e5-d722dd445eb7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Leadins
a045a2e9-2992-4448-9478-c01bf1398111 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Roughin
390e23c6-1f08-4825-8ffe-7dcd11e973c2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Cut out
6828a55a-fd20-4fb0-8e27-eb47560398cd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Fit off
8decdb18-99c2-4f02-ba3e-423f2183e17a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Commissioning
bf9bc3ae-427f-455f-928c-9af03c60ba7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing
e734d5ef-d72a-4972-a3b9-2a20eea3ec13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB1
ff174c70-1864-46f6-9a8d-e123e1aa50ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB2
d1e1ed45-3c90-4ed7-a611-1f773197a9af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB3
abf57a87-9827-45e6-b380-e65c7a0b19f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB4
ba442e8d-4104-404d-b843-07e9a34a658b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB5
3b39a7a5-7c8a-4f80-9265-b12d34e03973 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1105 | Mandatory testing | CB6
43cc5cd7-e467-498c-ba82-2c1601499f66 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106
5ca2724b-300a-4f33-a3d5-3e76257c01ff |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Leadins
2c8c1f64-3b37-44cf-ac00-f322247f2e0d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Roughin
1f7764b8-5940-45a1-b141-b4cfc0a7c21f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Cut out
c065791f-4dce-49b3-a437-bbf3c9a5385e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Fit off
6c54702c-b883-44bc-a6f3-76a2e44a9e20 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Commissioning
1caba2aa-b22a-4a9d-b707-790ec987dcfd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing
7df601d2-d38b-4147-9336-2a6f9e0b7f00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB1
ebe0d931-64ff-4f3e-b90b-cf1b19e2c26f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB2
267e228d-bc61-437b-8ce1-d9ff7437448a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB3
5851c1e4-4cfd-41fc-95ea-bcd3b468284b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB4
bc92f526-b145-4074-a784-0f2626c64484 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB5
ae18ac8d-16ad-42f5-b5cd-d876ed22828c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1106 | Mandatory testing | CB6
37d2d0d6-4021-47c7-8958-74286ff6253f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107
c52e0db6-6d4d-463f-917f-3384e723fcaa |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Leadins
d4375b03-9798-4ffa-bced-b4f1a1017406 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Roughin
89ba5451-bdd7-42ae-94fe-678ffde59af0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Cut out
581e0ba9-8d50-4cc0-a0e5-e6aa62e464ac |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Fit off
0197746d-bbef-4aaf-bd50-11e0a3dbcace |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Commissioning
92d95e3a-86bb-44c4-b62b-f371de4d7395 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing
fc8678b9-a8d1-4d97-9dc2-4dfc8b3dcb23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB1
dbaec1d6-7398-422d-928d-a85e6ba0dd75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB2
4f1254e3-363a-4ff4-8e81-17f125acbf35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB3
d73db220-5839-43a9-bc40-07ce48d6e99a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB4
8ed510b0-36e3-49f7-aca3-098d7e87d218 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB5
692fd58f-277c-49c3-931f-9105f2d4bc54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1107 | Mandatory testing | CB6
8539eb3d-5144-4847-8e23-3b29688cee10 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108
2209ce60-d087-4bac-b336-299d2d592590 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Leadins
419159a5-509d-481b-a519-d6d00ac93f66 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Roughin
758f9203-8af3-4f07-a310-d4a06853418c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Cut out
8e5cc235-c824-4d01-9e0a-09174dda3aed |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Fit off
ae792c41-3f1d-450b-934c-54607e637420 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Commissioning
8dd3ede1-3feb-43ce-9069-d2dea373fcd1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing
63a7d62b-5d9b-4a20-9b91-88f31d74aa8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB1
79912a88-118f-41ba-9ae1-0a6d684dc1a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB2
4ea8a479-39f5-475b-bba8-2f241629bc1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB3
d7084025-60d2-42d9-a883-6bf1e1d1c7dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB4
71bed704-cc19-46c0-90a1-06689c9e7d0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB5
b186baa5-1235-4377-9496-48db139b69a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1108 | Mandatory testing | CB6
70d18973-df34-4692-954c-c7caeb307f90 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109
cb2b722d-a3a5-45d7-ae0e-068454f059c7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Leadins
464a58eb-222d-4a09-9a78-24b52bc74630 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Roughin
e6d56280-fef4-492f-b51d-1df0a7b3bc6d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Cut out
9ffe5620-b8c8-4dc1-9769-5a12d9961499 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Fit off
ee3b0444-602e-4972-938a-160db0b9f9a6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Commissioning
e428aa93-b316-46c0-b1ba-ac57a9c637fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing
a7ac5711-faca-431a-894d-25e91bbe6e75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB1
387f9208-62b0-4b33-9429-2540c2628c28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB2
eafb23ac-f5c2-490b-a58b-44dbccf66bbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB3
02f3bb36-011a-44ca-b2d5-4f80f3f74b98 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB4
2be20439-d88e-4e53-b31f-bd331389da3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB5
25327dc1-3f39-40ea-82c5-b3139f0a1a28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1109 | Mandatory testing | CB6
33c393a0-4c35-49d1-92d3-cf489f831a36 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110
b3cd087e-fa5f-4906-9a7f-2e9fa73804ca |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Leadins
6d4330e9-49b4-4fae-9ec5-341e8575a92a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Roughin
bb37a000-68ab-4ef4-b8eb-614a88ffd7d2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Cut out
984b0b26-f085-4c89-862d-f65b368d4e56 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Fit off
86cf74bb-4f7c-4294-8dc9-b01370f6bba5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Commissioning
3a671693-0d26-4f77-a5a5-b75b1704bf24 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing
11d77a70-238c-43b7-8f36-f1d810a9c52f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing
244408a4-70d1-4985-92c0-c07a28b8ed43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB1
0f376930-646a-48af-8a17-7fa1b18be925 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB2
4b592cb7-9aa8-45c7-9aff-7b37e7d0bc05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB3
e24c644e-7a44-417a-804e-7cf46656cc5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB4
37a0dd57-97b7-46e4-9f93-df0578b91397 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB5
0711a293-afcc-4144-a186-178657493726 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1110 | Mandatory testing | CB6
1c37e081-ec39-4690-800c-86aa37b01721 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111
dced3c91-d08d-4333-80ba-c12d3612e0fc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Leadins
09a4aba3-c87a-4181-a343-66cb03372b83 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Roughin
15cd0285-4b43-426d-b8ee-0500298caad4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Cut out
01fff5a5-6d8a-4fba-8b45-c25033e6eec0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Fit off
9fd75d15-1187-4860-8778-c9fea19f5670 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Commissioning
dc166915-1f33-4e96-9842-71509253be2b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing
e684dcae-35f3-4b8a-ba84-8d23e0e767a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB1
3b2d8e07-1c73-4284-a2d7-9714edef1c5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB2
b4083af7-b3c3-43ca-8fd1-4908ff80e33b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB3
0ef54d0c-0292-4773-b871-104b6b8a2f0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB4
b96b3a52-4f9d-4fda-a501-a267201c782e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB5
8b8fe19a-398c-445f-829a-a21b98a7ab79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1111 | Mandatory testing | CB6
da4c1b0d-84ca-4b27-b5b9-a71165065dd3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112
3b304c62-d22f-4fa0-9b29-b8bed16f224d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Leadins
67388558-d869-49ff-8b28-bb7c3f892081 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Roughin
a85bcdc5-6a55-4ea7-a641-dd80e9605a46 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Cut out
71dda668-8319-4d34-b914-084fc8252a14 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Fit off
a1b38aeb-a591-47e9-a36e-ac5a837c1ea5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Commissioning
efae57e9-8810-4ccb-aa4a-a8e5b5a3261c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing
ccd47ece-11c2-4a26-8b84-c7eec24c6b72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB1
d256fa56-2b03-4145-9490-e9004dc18de3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB2
a8411d83-b2bd-480d-ac9d-82b79cff6332 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB3
563d8973-243a-4cf7-b51f-efa227e42211 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB4
10b263c1-63d7-4978-a9c9-1c0fa1ffabb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB5
7c7376cf-d8ca-4381-9786-12a9f4debc1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1112 | Mandatory testing | CB6
431845ce-0801-4444-b1a0-f45b67c836be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113
57284421-607b-4bdb-b97a-14c70c3605d9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Leadins
9d4b2942-1794-40c1-bc30-d005ba3eac23 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Roughin
77da13ce-529a-431c-8c8b-e7641da2668b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Cut out
35aeff40-5206-48f0-8566-d8adb79ca209 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Fit off
66934333-a9fa-44e8-bd21-1421d58951ed |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Commissioning
e2cdf602-7651-4c64-8bc9-25465c0ec1b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing
881f5efd-b3f7-4acf-9c9f-6b1b22eaac74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB1
7b95f877-5e90-4f57-bc07-383b5a5499e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB2
5a6c41e5-bb7f-497b-a5b6-f31fb06f8eb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB3
de1f2bb3-61a8-4787-92a3-f7653152c385 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB4
5bb68b4c-8fb4-4407-a961-38897be848f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB5
cce820f2-7368-4ed2-a771-5c9a782f3957 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1113 | Mandatory testing | CB6
0e435e70-b0f8-422c-9712-e30094823a04 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114
d0347cda-2ca5-4792-b2a5-033ea32bff13 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Leadins
55e5755e-d2ed-4e06-8821-5187e8983226 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Roughin
4e9c52ab-91d1-4212-9ab9-d37ee9377326 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Cut out
2844e99d-3e0c-454f-9739-c95044652818 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Fit off
52e1a04c-b3aa-463a-a9d4-1ad4eade4ec4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Commissioning
229e6205-f61f-499b-8aae-a79106051680 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing
5b7e267b-1951-48f1-8486-78b6127b069a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB1
bff97616-af36-4edc-a70b-658cc2bdc730 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB2
faf3499e-f247-4144-b994-3bd7f756c225 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB3
e1f33c10-ea2f-4fd0-b5dd-7fc362460449 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB4
c70d22db-9e1c-4d56-8760-82e7e6af5669 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB5
e30615ad-4544-4caf-8986-ae168708074e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1114 | Mandatory testing | CB6
242d8af1-c95c-43a2-acd2-7b400fa17b11 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115
9dcb8e18-cf13-45d5-8ffd-68bc7ef1ac09 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Leadins
7f46d518-ea75-432c-8291-29516f5a0273 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Roughin
fe8a0689-bc66-4e3b-91d0-bafc54fb10a4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Cut out
4b78fb98-acad-479a-aef3-0d0aa9efe4f4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Fit off
4a9e5ec0-9b1a-4d9e-9873-f2756dacb75a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Commissioning
18f32a69-75af-4342-8450-a7db42ec23a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing
6f508b7c-2956-4305-9a14-83a2778fca64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB1
763fdb00-e66e-4351-b529-8e24adcfbb9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB2
8cf429d4-4dba-4f3b-923e-10b1425c0845 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB3
feb97b61-3ec2-4e79-83a0-40eb851be032 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB4
7e30cd2b-855e-49f4-a854-8a1184bb93d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB5
0aff41f7-e7dc-4548-b8c1-f4ceb51de2fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 10 | Apartment 1115 | Mandatory testing | CB6
a00706df-0d34-4bb8-878a-74c0c1af4b11 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11
a1f822f7-1949-4303-a451-54d95b9fd80e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201
7cdc07e9-2402-42fa-990a-bc6b9a6f7122 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Leadins
5c601d56-5bce-46c7-a12b-4c0e3acf1d1a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Roughin
979107c6-b047-4abb-877a-1a2e16f40e60 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Cut out
b8f786e8-5b5f-4c71-810b-4a66670bceda |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Fit off
af39e1cf-eeeb-490a-bbc7-ba4b2c9c7e68 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Commissioning
87273549-c784-4b2f-811d-16a1b0695f3e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing
cc5dc690-d7d6-42ba-92b3-b58ec5be8141 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB1
faaef19d-727d-44e4-85e7-659d13af175d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB2
9eb83e23-a4bf-4c78-a214-26f8e24afc53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB3
02555d8e-1e14-4ab3-90bf-de44506a3299 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB4
a0be0c0d-ad60-45d8-9a12-a8743ae330e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB5
f6dd8c3b-b5e6-4c9a-a03c-e87632ed62e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1201 | Mandatory testing | CB6
74dd6dd7-70d7-48ac-8996-0c27a063c21a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202
d0dadc90-8951-42b0-a68f-b283fb3244e4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Leadins
090f0dcd-c865-4792-96c0-d10f56e74935 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Roughin
fd9ecf22-e1ec-4675-9de6-c6fa1847ae1d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Cut out
7065d8c0-0445-48a9-b197-c8b9904433fe |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Fit off
29765a8e-757a-436c-bb04-25ad741424bf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Commissioning
3a7a8e16-e1ed-4641-bcda-d1756ec03a14 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing
62e75763-d94a-4dd3-987d-62cd6b64ba10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB1
3dcdfaa2-fd12-4e29-b492-210c12895512 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB2
72a50c47-43af-42d4-a23f-9f5d593431b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB3
e93d181c-1b64-42a0-bf94-2873e07ebd82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB4
bcce94fd-d53a-4086-818a-8337447aca4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB5
92e81055-c38f-4d99-b442-aa459fcc7d5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1202 | Mandatory testing | CB6
c8a50591-e757-440e-aaf3-2ec4e2a6721c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203
b7af2a00-9cad-4eef-af7e-145083f6dec5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Leadins
1956ee9e-c6f6-4fdb-97de-9faafd7e9410 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Roughin
03d9847a-d4a4-431e-8915-ed5e98a8506c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Cut out
6953866d-04f0-48eb-b254-a12bc8740d6e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Fit off
713c73c8-24ae-4128-bd9c-ab7ce0359d73 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Commissioning
c5ac7f4a-13a3-467e-96f3-8e0bd2257c22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing
f5fc49cc-7213-4d43-a86c-fd4d5295bc23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB1
5d0cf7a2-8626-466f-adbd-46ee76464dcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB2
251e987a-a9b4-4364-b0ee-191b9f95882d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB3
07ca16d0-0374-459c-8cc7-0a53e05869da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB4
fcc56df6-3fa1-4ad0-9ccd-c9ce01107d9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB5
7f112da4-dddf-4a7d-99f2-e16398ad6e3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1203 | Mandatory testing | CB6
bdca170f-f32b-4057-82f1-03941c054e61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204
27137871-c9df-4ba8-8bac-df62bc9933de |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Leadins
3261254b-7d84-46d0-9f8e-ce67b1b99804 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Roughin
7ffe58f2-2bc9-49fd-a547-dae41c7d603d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Cut out
389cb9cf-79c1-4fbf-aa53-39ee8cceb5d7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Fit off
dfd96f3b-f9b2-4aee-9aa2-7455a1bba8e6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Commissioning
8b7f2577-142a-4881-aca7-09ccdfd4118a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing
95d5cbb5-0053-4adb-9b6d-d58c20e83152 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB1
c299814d-7d3c-4375-8c0d-a5a63f715e16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB2
b06796fa-f90d-4eaa-abd6-7be9372952e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB3
6abc6865-8428-4604-a776-5ff4d49e7a38 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB4
c137ebcd-c1f5-436a-b1e0-8119e81bb5c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB5
ac170acc-83ed-495e-8898-82373cd09c3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1204 | Mandatory testing | CB6
193a7b56-4203-47ba-abcf-994e0e0f73ec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205
6ab15b42-b519-4127-b5f6-a6dc8147f53f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Leadins
f28dbf44-1673-4150-9145-fa08b1f9ab47 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Roughin
bd66cb60-99a7-43a9-a9c1-5e54a38fd107 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Cut out
c44432ca-908f-4a76-8b4a-f2644c469169 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Fit off
85f32819-8664-4b69-bcdd-ba9bb6fba3fd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Commissioning
35ff7dcf-bcee-4373-a6ce-cbd243acde91 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing
14e90372-931e-492f-b50c-4a038659e17f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB1
67c64e98-77d7-4d49-a7bd-b9b7c875f5bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB2
e0472db5-d9e4-4c18-bd59-028045dafabd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB3
433a4de6-9cb0-4724-b27b-da25ab47003f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB4
4e9320bd-b370-48ee-8cf3-7ddac91a08f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB5
2b0c0952-01a8-4d69-9dcc-a3975194733a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1205 | Mandatory testing | CB6
245a5c01-9520-4f08-bd59-a4efb9f54d02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206
3075861a-5d53-4366-a98d-7f4438621469 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Leadins
342c8fa1-14d8-4d69-83d5-4745e7de90ec |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Roughin
bf2ff907-1ab7-4e4c-88ad-f8c95046f961 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Cut out
3ef91b81-b587-4e0d-9547-61902eec22fa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Fit off
a288a7b4-a7ea-47d5-b9e1-95defba5ddf9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Commissioning
79108fb7-69ce-464b-8973-55e57627c105 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing
dfb8e177-11f8-4208-9014-a46273c2b1eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB1
0399b89f-5aae-42ad-848c-0334eef1a5ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB2
afacf010-94a6-4630-aa33-0fa71370ee93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB3
a23334c7-cef8-4fe4-a5f9-28872805b0ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB4
b4e37d11-461f-498d-9cfc-1833cd088cda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB5
0e24db49-4979-4f48-9779-50e0dd3ee923 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1206 | Mandatory testing | CB6
468991de-cdd2-44f5-9195-095140ff55fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207
afe1d6b5-1bc5-4957-9c89-964d22de40f2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Leadins
3c892c19-7f3e-4a27-b0d2-4d87272e43fe |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Roughin
9b8e25d6-61d6-4edc-a607-d44048fc7528 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Cut out
427528da-c546-4db5-a83d-4e4cf3472379 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Fit off
bdea00ec-e795-475a-8da1-ddd74e4085f3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Commissioning
28daffc1-d26c-4bcb-91e7-4c45c940baa3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing
caaaafc8-7d94-4438-8278-cf3fa19b9bde |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB1
6ba97be0-32ef-4dde-855b-288e0d2a0974 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB2
2843d4e9-60d5-4ef3-a420-73dbfa4ee201 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB3
40c79fac-a37b-4d32-a454-79432b0c9659 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB4
7c1c5c5c-eb08-4057-a45d-24762c5e9d68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB5
3159864e-18fb-446a-a367-85cddd3e9775 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1207 | Mandatory testing | CB6
1f60355d-344a-4145-bda4-59c5def92a8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208
80e6120a-91ab-44c7-93c5-c77d76b64453 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Leadins
cb30700d-8e9b-4aae-898e-1889a737e0d6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Roughin
6caeef48-c8a5-4f3b-ae68-75ec2938e1ed |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Cut out
ab447ebf-5dd7-44a4-8b6c-7a65ca1db713 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Fit off
7e04ef40-7115-454c-a42f-0554d32fc559 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Commissioning
cc911862-a6c1-4193-855f-07265196aba6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing
c0cb0a2c-a709-4565-9e88-2a568c08ccfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB1
53e4ff7e-1e4b-4ab3-9984-3a8d8479d529 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB2
810fc4ff-a4a6-4613-989a-f56bc83ca782 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB3
849642e8-4736-43e9-a86a-9eb43d906de9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB4
6c62d2b8-c793-49f4-ac0e-67ac7ba05da3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB5
a79f1e87-4d3d-46e0-8f06-c885bb93a2eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1208 | Mandatory testing | CB6
bbd7ab76-36fa-4d4b-9032-9bb7b1d82318 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209
0797e491-cfee-4211-984e-0980d933654d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Leadins
2216f6fb-b535-418f-a20e-f74c4abf021c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Roughin
c340732b-801e-4778-8421-1951169490f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Cut out
bb1c81c9-4c2a-4697-b458-21fe449cb168 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Fit off
4b02edea-cece-43d0-bea5-41b0405e769c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Commissioning
be05597c-c1ad-4d67-a0a6-7a5e52bcf5ff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing
69dae57e-30a0-4562-a7e5-f8ab8ba64e68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB1
7d716401-db5d-4422-8bac-ba07880bb6e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB2
c1d6c741-f91d-43d4-92bc-d10fc96cb017 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB3
58839d60-3d73-492b-a972-0095d0bebfc7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB4
cdd26e76-a341-4e4d-b9cf-a2c42cb048bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB5
732bc4a0-26ec-4301-8789-f82c9055af66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1209 | Mandatory testing | CB6
6ce354fe-0c52-4b2f-83d1-35b2fcda0726 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210
1eeced6e-11da-4a11-af08-68cfca745242 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Leadins
ea73edea-f40b-4e4d-b2e2-a93d3a8d8e6d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Roughin
5cdb40cb-bd18-43d0-ab4b-645d5859cc3e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Cut out
213416a1-32f0-480e-9aa1-6e1ff7823dc8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Fit off
2ce6360f-84fe-4769-8b22-59fa0eb1632e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Commissioning
a0145615-6012-4bba-8d47-fabce975a247 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing
a6de70e3-67de-45c3-b474-e99c104870c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing
ebbe6df4-54b0-4fd9-9d0e-3aef7928ffae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB1
d932532d-200f-43c3-8e55-3e51360010ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB2
907b8606-9aa1-4ae2-9c2e-ea818f4d4c7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB3
82462fed-e40a-4228-bb18-653fd9b4093e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB4
e91f05d7-0d58-44af-b38e-9626f50a6a4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB5
d3a4860b-0827-4135-a5e6-e3220a3b0594 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1210 | Mandatory testing | CB6
824adc10-327e-4ae9-90e2-85758fed450b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211
6c6a6abd-58dc-4805-b415-039260888fc6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Leadins
a180ebbc-28be-4c27-84cd-d09a9369c9d8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Roughin
251e2abf-be63-4d59-b596-9042d4735d83 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Cut out
509bec0c-6265-4dc3-8740-04f6ab364367 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Fit off
21ffbcb2-c3d1-4c74-80e0-85947a1a246b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Commissioning
aeeb6ceb-66af-497d-80dd-44b245d20abd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing
63849429-88f1-43b5-943e-a68b45861fe3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB1
f13c0eac-84f6-427b-878e-5c10f94ae1db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB2
c6b08a58-a46c-4f5c-8811-e2fc8470da07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB3
bc13f07b-2609-4504-b749-b039c4c52c29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB4
98fc90c3-6333-4a4d-b08f-0b60977c358b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB5
1cfb0d15-bc41-4946-9b62-5a9b9782ec8f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1211 | Mandatory testing | CB6
1c3db388-a21a-41ff-a3ab-80dfcb38ecbe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212
d0205bd7-7565-4944-ac64-220c06d80a39 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Leadins
ef382905-fedd-4820-b910-d75cfe6e9d59 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Roughin
aedf25d0-3b18-498b-b83d-66ea82198384 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Cut out
ed5564c4-b05a-43cf-b6cc-8bce6ffa172c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Fit off
70d276e4-7231-46a7-a88f-4aed59740b7a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Commissioning
f054a5e6-a7d2-42c3-9746-5e558fffde71 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing
c866ee1a-df83-42c2-b6cb-82d386804bd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB1
c7adba45-c068-4e52-95d2-9e3bbdd66d7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB2
bd633e95-6ad0-470b-8129-0a62bfcb14b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB3
13dbb69a-a004-47b5-ada9-d25826585afa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB4
02ca7646-b058-4c0e-9bad-eb4a50f57e04 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB5
9ed88a7a-b338-4bdc-9a9b-c61522d44ead |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1212 | Mandatory testing | CB6
2dee4803-458f-4895-9286-f0e699e4c13e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213
c69fa978-9aa2-4e36-8cee-c5f2fe779203 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Leadins
14981eb8-8d9c-4843-88b7-0546e7726758 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Roughin
e3db54b3-fe21-4f66-aff0-abdd38c9c173 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Cut out
59a89e6f-85ef-40e3-b36d-3d4701a03863 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Fit off
f8b0c542-5731-424c-bc55-11c0d2465163 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Commissioning
6e235f09-a624-4af0-943a-1925770ea1c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing
d012f4a4-c423-4d03-b3da-e137b1559f92 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB1
1e42df4a-d5a2-4227-bd58-58ffcb2a8df7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB2
d2b66625-2049-4fc3-822e-9864343404c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB3
40abc1d3-47b7-44df-9958-334017927764 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB4
9be495ba-8ae8-45c6-930f-0ac53e3e8577 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB5
54cdc0f6-6328-4c4e-a2c7-e537235f95cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1213 | Mandatory testing | CB6
8a877075-19ee-4406-82bd-85cc0b77a0c1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214
6d239dda-ab0e-4b6a-8d8a-f7751476a96c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Leadins
1390cda3-8052-41ef-b95f-22c3244665a8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Roughin
430c7a68-3e8b-4ca8-9951-342e3d45342b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Cut out
8b211178-4b44-4692-8462-317759b784d4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Fit off
ae9e2995-cf45-4426-a393-fe66ea2ffd2f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Commissioning
863c5649-9811-45c5-9cb7-f59efa32f567 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing
076a9d5f-03d0-4ad7-bc7f-7180c5c2ff12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB1
a1f8e371-b6b3-434d-ba1c-fd519ab2536b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB2
399fabf4-b359-4a71-b168-48936a6915f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB3
d611ff2a-4af3-45ec-a4a6-8fbfdd2b9051 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB4
14df2780-4236-4938-b8ed-7e5cc4d5aaec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB5
5fa68bfd-d757-4b33-a1c3-7e9f5e912b7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1214 | Mandatory testing | CB6
b3f82b48-6604-4628-af34-e90d139b3928 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215
52810549-ea1c-438e-8e35-d6ca173d98ba |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Leadins
0abf223f-6d6a-4435-b449-22a69b48b548 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Roughin
2ca7e71b-182f-45c9-be93-afa6afb2f688 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Cut out
6856aea6-7527-4d0b-ae27-739855273ccf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Fit off
29496847-7486-4136-bdb2-f4d421bd7f41 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Commissioning
7cb04870-3a88-46c2-8268-500181f25999 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing
70ae198b-0ab3-43c1-99d6-a9a19971df07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB1
ff5638ce-0491-4aad-973b-19b070fc7e33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB2
7abf435f-a152-4d67-84a0-36f7041f6ee6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB3
56d75e26-e17d-4472-9c11-1cbee1e8aa71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB4
3fa421fb-dcbc-4091-8c67-00ade5038faf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB5
8bb559bf-de56-4f5d-96dc-f1824f57306d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 11 | Apartment 1215 | Mandatory testing | CB6
74afa6b4-3791-4825-ab04-6b7d7c768ece |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12
2269ab9c-7993-4aec-a94c-a50ebf5a1f5c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301
c2ebcf05-8332-494d-a972-2d94ab30786e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Leadins
82952f67-211d-4c99-b45c-d8b2bcd5dbf7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Roughin
d8955cf6-b99d-431e-ad09-ea3a93dc6a92 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Cut out
f080431a-86d5-4887-8cf1-546c6001456f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Fit off
cc6578c1-0d94-42e0-968f-22cac70cbb59 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Commissioning
f4f0ab06-a32e-4842-9207-eb277b92fc59 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing
235772a3-22f2-4d20-be58-a5c7ec1c6a07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB1
58e574d8-59dd-458c-b8e7-c7ba237cf816 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB2
5982ceef-ad07-4aeb-8012-391ea39cbafa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB3
2371c025-186d-46e9-95a5-92e5121d4477 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB4
516c3f77-3b6a-43c6-9af4-a91da42de22b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB5
9f40c1bf-f3bf-479d-88a6-f9696fc29d9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1301 | Mandatory testing | CB6
85ac5ae6-94ca-4280-92f6-d4ee845fbcc7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302
5ff66de5-5ded-409b-a540-bb3bb1ef7e62 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Leadins
f4af542d-c452-4698-9520-9f838e5b73d0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Roughin
52850211-dedc-46d8-b6ea-5a4941c868df |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Cut out
425dabec-15f5-4704-b7b9-b7592c7397ea |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Fit off
ea23892f-354b-470f-aa08-6b5e10bddaef |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Commissioning
ac16304d-ff41-4446-9448-78fd170ab23b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing
d26763ff-23f1-4594-9d95-15628d7784dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB1
ed4cd4f1-3c30-4432-96cf-677c45419193 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB2
e68bda3f-059c-47ea-80ff-3905e8a2adb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB3
7a6d9592-7dd5-46c0-bb23-483f95507946 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB4
97550312-acbf-4c14-97cc-26530794dbf5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB5
fc094dfd-a9cc-41bf-a1a4-f246127f0043 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1302 | Mandatory testing | CB6
f6e8ff99-62db-4e05-8f82-0dcde124f759 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303
c73f90b5-dcdc-4b5f-b63c-a9e9ff9566dc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Leadins
58a1109c-bba7-48d8-97ca-6219926f7e40 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Roughin
fce32f72-71e4-4ceb-85f3-34460048b3a5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Cut out
73756a82-c4bd-43db-ad66-a3d747bfb889 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Fit off
7ffb3ae7-a2f4-4a9a-96c6-eeb147ef3a61 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Commissioning
4941faa4-6721-4162-9deb-6a6632123277 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing
1d6a87b4-af98-47ec-b3d8-23d7d30495cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB1
7c4a93e3-ca9c-408f-8af1-4344983ff204 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB2
a4dcea56-8aa4-4f51-9d4d-c17e962b44a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB3
dfe66b93-e9db-4738-9fa5-679c101c02ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB4
208231da-8bcd-48e0-8821-ded2c92e1fcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB5
c4fea182-57d2-4fba-a4f0-3ffdb62d9994 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1303 | Mandatory testing | CB6
40a79d4a-7cf1-4249-9df1-0ac15a4666e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304
054eba64-144a-4633-8a82-4ccab70940c2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Leadins
706ac0d1-480a-4ad2-9b35-189842798a45 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Roughin
a04f4985-627e-415c-8bee-689bece49f53 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Cut out
b72aa4b8-c038-4e38-9d28-bd0e0007ad50 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Fit off
e2992641-d200-4f18-907d-4aea6413f229 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Commissioning
94f0ad94-d8b2-4415-aeff-2681cb815ced |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing
bfa57d49-519b-430a-a9ed-a3c629f0e516 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB1
152a6808-1bbe-4904-b682-06adea2a5e37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB2
8e54cc00-ed4f-43f7-915e-2c16b6051d6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB3
46932d79-996b-4010-bc95-635d9ef962a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB4
141b2a73-f8d6-412b-9f3e-054a2540de58 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB5
f93c0827-adfe-4914-9b10-232856379c44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1304 | Mandatory testing | CB6
d925ebeb-c557-4cb1-979b-08555052c182 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305
699117d2-9401-4194-910e-2895da580e1a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Leadins
34f202e5-556f-4c8f-9a44-bb8c0d70f2fc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Roughin
ea8eb068-09e9-4571-a855-41f3e3261acf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Cut out
a2ca3dcd-3f29-4697-87bb-ea4c073a1d24 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Fit off
d3ca6bf5-9148-4ba1-8754-30437dd10e61 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Commissioning
5794472b-d257-4c2f-ac82-99a1f0b2d4e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing
059edc06-646a-4727-81f0-2efe0121c52c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB1
f886a49b-d76b-4be6-a318-2eb7f3ba3741 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB2
0c48b383-3bb5-479c-8f21-7bf5673c2edb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB3
39066f9e-a814-4a0d-887d-e9571719eb87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB4
423f3ce3-d77b-4fa8-8cb0-256d873076ae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB5
5d462863-370a-4e84-958a-bba097ca2391 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1305 | Mandatory testing | CB6
a78268a1-d796-4065-a7a9-bcd1e57ff6a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306
6ad43f72-be29-48fe-9336-51cfe39582b5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Leadins
9472b60b-f7b7-44e6-b0cf-d54418ee458c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Roughin
4f86ad12-9ab3-4a61-948d-992e4005641e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Cut out
fc88e5bb-1f4b-4608-bf57-91a7d93fa0fb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Fit off
3f505e05-402d-4455-be27-28350a6203e0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Commissioning
4fe320c0-a329-4f29-89ca-6e818a937683 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing
6c1ee563-1d74-405a-871c-f2d16bccc49c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB1
18fbb78e-16e6-4b50-86d1-1064cdc0bc2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB2
f408ec7a-8e51-4da7-97ec-c6a038f89cd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB3
202a16e1-75e9-4e3b-aaf9-a168dcd0080d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB4
0ba01378-c282-438f-ad42-5b32da9ed6b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB5
f6935662-203f-40ed-a8bf-dcc626d1c22f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1306 | Mandatory testing | CB6
26ee332b-8887-40d7-b661-1a5ec3f6f89d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307
6ea1f858-851f-41bb-9441-1782c7320c4e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Leadins
87f50b22-782c-484c-8989-4d3a89b47e56 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Roughin
e0788629-5870-4d98-8a91-efb08c1c6da8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Cut out
ebe60e0c-b89f-4dbb-bc33-20eb4baee2ed |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Fit off
e4bf17fe-5849-45e6-b893-6ff0acac8ec9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Commissioning
720edd7a-35e2-4b5e-b6ca-87dea66314d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing
38b2fc1f-0bc8-40dd-bcc8-232e04b48a49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB1
e8abe740-c61e-43c4-a240-587cd7cbae04 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB2
c947fe4a-56a9-4e65-9878-7c25d9bd084a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB3
cd77aaf6-bbc5-4c58-aad5-b078dae7cc7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB4
bb991e28-6087-4563-aaf5-58933d9ef54a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB5
1071fb8d-f32d-471f-a573-ebc657f9f29f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1307 | Mandatory testing | CB6
9959f1f6-7f78-450d-a3f4-496c6f8fea8f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308
d816050f-72cd-4f09-a63b-4a2532393490 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Leadins
f9a3ef81-1f34-4d98-996f-95f7150d7281 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Roughin
aaad84af-5343-4e46-a5e0-39bb4d5c27ca |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Cut out
d3f0523e-4f9c-4f33-9d08-0e5010da9a34 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Fit off
7693f875-4e80-4335-a270-031f0074eca3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Commissioning
8ab08a72-d4a6-44ce-82f6-522ad26d6b59 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing
3243ea1c-f679-4ea2-97ed-913c1e76739a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB1
7671c932-e3ce-4fde-a7b1-fd9226707870 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB2
ae568a7e-fcd3-462b-8cd1-96dc3ee69003 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB3
6805aa90-21a6-4c99-8132-e0092db1e218 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB4
d9cb7ffc-3b71-42c0-9c8a-b719affe1b1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB5
c1418418-2bcd-4d34-b48b-2a6897aa12e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1308 | Mandatory testing | CB6
a10f51af-a63b-4ca9-a2fb-cfe5d945ecef |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309
85c7973c-df33-4635-ac6b-4f3671ecf2f6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Leadins
aaff5497-b5d1-439a-ae31-6323116bb0ae |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Roughin
0098f2c4-ae44-44e0-9348-b23fabd2ddd4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Cut out
d16267f6-ecdb-4097-8ef0-508d0352c9e8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Fit off
1d9cecc1-df25-4653-9316-d1af0b3c612d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Commissioning
31a6a07c-fde4-4d89-83bb-66cbc45d6198 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing
fb2a3673-027f-4c42-b4d9-a1384b503a3a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB1
abcdf988-fe90-4ef4-866d-825c01897f8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB2
0930f9d6-4665-40a1-9c85-7c99cc6c1878 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB3
f06f2fbc-1f19-4174-bb40-d5f2024561ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB4
395dc68b-9d9a-4c61-a7b9-c042cfeb62c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB5
169d4ecf-ed40-451b-ae16-09c2abd6b5bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1309 | Mandatory testing | CB6
978fcf92-433c-490d-b9c8-5a193a7c8a36 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310
58c073bc-bbfd-4b20-92d4-15ae8a5727b0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Leadins
e809fd6b-faec-4d9f-9645-3202ee590e4c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Roughin
a18b0bf7-73a1-4726-960d-51ab70abc968 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Cut out
689d1096-4ad7-46c5-8ff1-302cbe5d3334 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Fit off
f5ce7c8c-0e4d-41b3-bd50-f60e37f59749 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Commissioning
34b749f5-9005-4280-9853-5040b3015c91 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing
4acf5288-167c-4af4-b595-da55219820dd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing
8a9ec41a-effb-44ec-b32a-2c66eaea995f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB1
26da808f-dcf0-4770-b8c8-1409f78fd590 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB2
d424252a-338b-48fd-8c7e-cfe1cfb4b953 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB3
4dc3f29f-41a9-4f43-9335-80f6bf208d47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB4
5b75df5b-7ed1-4bf9-92ec-41b66a3f9402 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB5
330b9be9-5525-4c88-b5c8-249f9edc1f62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1310 | Mandatory testing | CB6
44fe63a9-39af-456d-bedc-240cc659d3a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311
6596117f-9988-4a8a-9bcc-53e790ac3979 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Leadins
182570d8-17d9-49db-a1b9-20e64f9421cf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Roughin
79e1b92b-65fa-4448-a8c2-85ea80475b7b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Cut out
6239271e-4e18-411d-895e-b006551adb33 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Fit off
002ff372-c161-4ee1-9160-002d25054c0b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Commissioning
e4761d11-5bef-4cde-8e2d-7660d25b8046 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing
28a705c3-2182-46ed-8081-60386b3e2484 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB1
d7b2c4d0-9f0b-400d-901c-1b1e5655674a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB2
72391add-a0e9-4e41-874d-885a3b9a1c97 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB3
6ea5329c-ef7a-4796-a110-6a4d94814512 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB4
5b03b25a-3af3-4c45-9365-cf0b07d56df7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB5
2374b7e1-b8e4-4eb6-80c9-31525ddf4c4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1311 | Mandatory testing | CB6
8a619497-4659-40d3-bd3c-486aac38f128 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312
4d437edb-36b2-43c3-a482-5f982ebc9ed2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Leadins
6ecd3764-4304-465d-984b-61d0003478e6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Roughin
f7d55e3d-64aa-4bb2-9f75-d646ce7ecc2c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Cut out
dd76eb42-84cb-4243-bba9-05664859e560 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Fit off
b977bd2a-4590-4f10-a77a-c38e338391d1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Commissioning
7ab76442-57c3-43c7-8f43-98e42cd43771 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing
bd249ea6-3ddc-47a1-a100-1645ab1b5b93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB1
6cd9bccd-a252-42d0-8389-3b42a7858170 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB2
f621771a-ed63-4bbc-a1b1-cd445b3a23a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB3
a63edc02-c70b-438c-afcc-a4f419f3ceac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB4
06a79197-65dd-46f3-bd32-fd147ea4f0b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB5
cd672935-524a-4d3f-9e9b-102120a9cc50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1312 | Mandatory testing | CB6
07089509-c76c-45bf-ae65-f9aa86687d0d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313
2e2b140f-9270-44a6-9ea2-92fab252356d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Leadins
81daf5a1-c6ed-485e-ab42-a7ce22ace4aa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Roughin
acbbbecc-3b06-41f8-aefc-556a9d53b1f6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Cut out
efef9489-bd08-4797-ba33-09241d969bb5 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Fit off
41637e2c-7048-4f5e-aba5-acfabbdbc911 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Commissioning
ce4bc6ac-2aee-47c6-a1ec-028d8fff4fc0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing
0a79ca14-5c70-4296-8a26-c54556262117 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB1
f2d706c8-3936-4843-980e-baebd6a761d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB2
b62645f4-1e63-4584-b091-c11ed142ebe8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB3
de338e53-ea2f-4b3e-9e61-7f87ecda948c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB4
70078dca-72b1-4f3c-ba71-f6fbb51f3bbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB5
e82372af-a9e4-4178-881e-0b5e55b7b780 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1313 | Mandatory testing | CB6
8640ba16-6d94-43c9-9b0c-9c5e41cb68b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314
87c79279-2f3c-4669-a32b-63bdffd396b2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Leadins
d689b321-4186-44b7-b555-dc680ab04b68 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Roughin
ea74fe95-1b2d-4cea-a28f-d5519d2a4cc9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Cut out
09e35750-36f5-4560-86fa-e6ce277873a8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Fit off
2577008d-f672-4fcb-8363-e256f48bda9e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Commissioning
8bbeca0d-a688-4bb5-9b91-3524057bd2e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing
73fe7ba1-28fd-4c38-9cea-f7711523e25c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB1
f6dbf8f4-beb1-4c7f-bc71-3a82adc3386f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB2
70657d69-97ea-4539-84fc-4d4c32ceaaff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB3
a0d276d2-5155-46fd-a9e8-1cf1b06ccc2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB4
e367987f-ede1-46e8-9d0e-65f9dd4870ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB5
fcd01054-99e0-4c21-8e81-aaae96a964d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1314 | Mandatory testing | CB6
9ddd3006-0a40-4bf9-953e-bfae8332bf28 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315
279803ac-81c2-44a5-bad9-c4db9012ae4a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Leadins
7f463fd9-b13a-4b1a-adae-38e165e5fe5c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Roughin
1608d40c-1843-48b7-9855-47452d3107a1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Cut out
15e3b29f-4445-47d4-a2cb-dd7ff83c2753 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Fit off
df6d1d87-fb9c-4973-8e5b-8e254c851683 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Commissioning
00f32fbc-1c84-4cb8-9544-0265f83b2cb5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing
c2c07802-d077-4ce3-888c-8f2083d5d931 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB1
c968ed8a-8730-4aad-a91a-fc587eb50b0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB2
3851ea36-0f37-44c7-8c99-8ea4a25ffd32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB3
88429a68-b14b-4cdb-9639-2e00c264948f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB4
65de4382-230d-433f-a12a-c232c59a6c19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB5
0a3b32dc-9dce-4ad3-ae85-c03dea04f125 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 12 | Apartment 1315 | Mandatory testing | CB6
2561f0c6-07d9-45a1-a886-6744fec69f06 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13
7583de0e-9b43-450c-bad4-e6bc4f2659d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401
ccfe3e83-50dc-4cfb-b8e6-ea634ff1f968 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Leadins
ba0d5ed9-97fe-4876-bf99-515acef0f9d7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Roughin
ee519ed1-37d5-4321-af7e-1dbecc977055 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Cut out
a152630f-8fda-4971-bfa4-e0d87afa9b4a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Fit off
4205eec3-a094-41c2-b27a-6426c33f4bd5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Commissioning
12fad368-e151-4822-b087-a406a56ce057 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing
77a3267e-cbb4-43d4-b720-e5453f783886 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB1
a404830c-e956-4d70-ba77-9c0284771b60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB2
6e2554f7-cf6a-42f9-bdd8-c1373b6659c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB3
db8b1bef-2ec7-407f-a480-3138fdb30fff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB4
fd550bdb-7a63-4495-b742-cd4aaac515b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB5
a6f65913-c847-4a87-a567-236e6c3758b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1401 | Mandatory testing | CB6
ba7a769d-f0ed-40f9-8ec2-8f7df5efe1d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402
5a6cfc60-2c68-46df-b0a2-7fb45b0be2ab |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Leadins
87c0fde2-ea7e-48d9-9f58-2af26ed8bd96 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Roughin
e7eb9312-d195-4e68-b8d5-414eacc7cf8a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Cut out
d10a867c-f003-4fe0-a2bb-7c7c4cc9796e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Fit off
20620927-d760-4579-a152-4d1e879bfa98 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Commissioning
eda0939e-8aca-4a27-b74d-835c290c1034 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing
468e9d95-9831-4abf-a5e1-e0d636b5ab8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB1
fbc40661-e014-455a-ad91-4c2a8da1dc46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB2
752c3c0a-f55a-4568-9f58-7e630edf885c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB3
8693dda5-9c94-469a-a964-d8b1bb261650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB4
198b271c-02df-43ce-b7a1-c96b511488b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB5
f999774d-9eb3-45f4-8582-0b9528d2b8bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1402 | Mandatory testing | CB6
d6f4b9ad-1b6e-4b81-8e5f-00fcc6d4cfc6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403
854b038d-e8b0-4938-8e6f-490aa4f010e6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Leadins
1ccda07e-32df-4205-894e-ae9f70dd3bab |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Roughin
9114bfc5-cc0c-4d87-b709-67eca3104133 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Cut out
fad83ace-6c84-4396-8e1a-fe0a8e6d8cc1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Fit off
3b7bbbcc-d7c1-480e-8512-005bad71264b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Commissioning
89dcbf06-ece7-4fc6-a808-5a1e7265b9dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing
b906c013-1deb-4a97-9d89-5e87d2d9afe4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB1
761c619a-e0e5-4411-8107-52cc43522fda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB2
d82af698-66f1-41db-a7ce-8c44827db757 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB3
151827f0-7f27-4178-8b81-bb99699867c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB4
ec639d20-d2ba-4aef-a8ba-6bc9b13a0611 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB5
b4a79774-19e1-4b0f-ad69-d99c063e571d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1403 | Mandatory testing | CB6
93f8bdf5-d2cf-4bb6-918d-e25d1feadf3b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404
20ae2163-8481-44d6-a709-783f94b73be9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Leadins
9b102f83-c9bb-461d-90ad-eba99a8ec4af |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Roughin
9a836935-a33c-44e5-ae17-eaf4671f003c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Cut out
50716f0e-d788-438c-93ec-43f740bb6c39 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Fit off
00fedc0d-9084-4ebf-a361-225950059618 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Commissioning
d757affd-3e7b-4af5-b430-2d6bb4efd8f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing
133f386c-31a8-4efd-b612-aac7d025e19c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB1
d9e4a82a-9b27-469f-ae99-e3d74c18383d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB2
d9d7cac8-4171-43ee-acf4-71efae666acb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB3
b8e4e86e-f716-4308-b0fc-57b0019af067 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB4
ee2720b7-8cfe-428f-b89c-4a73e645e6e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB5
a62ae39a-d81f-4ab8-a484-a41e37c89ba8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1404 | Mandatory testing | CB6
d6c00a97-48af-4d44-8e88-85775e96caa2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405
ee49d3d5-8be0-4a2e-871e-e7a21508ed78 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Leadins
6c63e5bb-d3d8-4a74-911c-5ae9ea60ad52 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Roughin
47d05d5f-9839-4e3f-bf78-407ced1fbf77 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Cut out
90b9e1c8-0cb2-492b-84e1-fc6c78c15082 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Fit off
0af29a48-399c-40c9-a713-a130bd0907b9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Commissioning
b931dd66-f8e4-45d4-be6b-bbca6500fa42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing
3f3624f3-05f7-4429-9148-4ea73c21970a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB1
af1fa354-a07f-4b54-801d-885a5627c825 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB2
2a15b617-0f8b-48df-9f57-b020eb80601d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB3
79c973ec-7bb5-4761-ba83-870aeb8e4467 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB4
ef2d2db0-11f8-4097-a7bf-f07b5f591087 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB5
74836d00-051d-4de0-8656-edd724da492f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1405 | Mandatory testing | CB6
6acc2433-80e2-45dd-9693-1f5ba7fb2306 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406
5b68da07-a094-4acc-a2dd-d79c5bcfa1b2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Leadins
ede0f27a-b565-4963-99af-8c0dd0d8602b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Roughin
f7614afd-7c5b-4b95-958b-1a69c031050b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Cut out
06d5d0ad-dfcd-4541-8158-c3503c8f971c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Fit off
d0f794b3-629c-4d81-b421-150faa28b28f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Commissioning
36746df2-81e0-4dd1-9c2c-242543454e13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing
ba9bd259-7976-4b41-bf0d-d7c7ec894bfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB1
7523c753-c44d-452e-a858-472d5fe5d2a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB2
185f5156-1ecb-4c20-b33a-e734e74a75d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB3
6342d881-b150-4ce9-a6a2-2197c5dfde30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB4
b55fe391-cca4-44a0-863d-e1566f6f718d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB5
bdc284fe-6e48-46ad-8599-aa3b831ab4b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1406 | Mandatory testing | CB6
5bf93e36-6402-4679-a49f-d3438e3c6c66 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407
34f35d9b-df10-455c-88cb-8feef83dc372 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Leadins
774b5897-aaef-467a-a4ba-3428009365f1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Roughin
5095037e-ad9d-4861-a3f2-cc94af4bdcf5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Cut out
f1ff4492-084a-4e8d-ba2c-e3a3e385550a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Fit off
5eafa533-e682-4bac-9be0-675c3eada722 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Commissioning
f866fa90-1e05-4c11-ad10-e7c8fea6e22f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing
9623c8d7-0647-4f60-8084-bb610e4e3ac7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB1
81c5fce0-c1c5-4a75-a33c-ededc0e2ac3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB2
c5a36753-41c9-45e3-93e1-a2e1bdc35c56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB3
1846c8cc-b5b4-47ea-abdc-71096eb9ea26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB4
e9f59943-d43d-4f9d-99d4-d9fd08a6f4a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB5
6bacf0b5-b1f2-4a64-918c-749011a3473d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1407 | Mandatory testing | CB6
270c7362-d025-4a38-baee-de1a0ca1a552 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408
71c483b7-533d-4161-b4d3-9fc0870c0ae5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Leadins
88b0a7b6-f6a1-4dba-897e-109017619045 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Roughin
c402a1f2-3a06-4404-b2b9-504673e569df |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Cut out
4aae4e53-be84-401d-9880-bb5a0c17af1f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Fit off
30018ccb-fcb5-4e54-98a3-824c049c0bb6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Commissioning
587b4f5d-4a73-402a-80c2-292198d6a06c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing
b067672f-b7fb-4e97-b8ea-5a50505b2a0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB1
59b05040-a767-4425-a5ea-751d70a41569 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB2
600d9dac-e5b9-463f-8adf-eb0ce376d2d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB3
58994dc3-7fb1-40c2-9ac5-7c1dddbd23ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB4
4aef92ce-804f-44a6-910e-3ac149a00dcc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB5
c20ad6df-2871-4b2a-8a69-5256ff193e47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1408 | Mandatory testing | CB6
3c41f76f-fc37-4c23-990b-1505817db2c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409
c5a2d5a5-d9d8-496d-a88b-3e029436d77d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Leadins
025f35be-6790-4318-b65a-47148de404da |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Roughin
ff7fcb8a-2dd7-46fc-85bb-bb3631442852 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Cut out
0cdf3006-db90-4060-a7d5-4c8e379e5737 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Fit off
40459113-1f25-4e9f-848c-97e94f3c0a98 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Commissioning
004788bb-bafc-467c-9008-44eb1b2bfbb9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing
a886cc5c-9173-456c-8ebc-acdc0ec57847 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB1
e98ea56c-c0eb-482e-a21d-e5bc6f357e8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB2
60a86798-7db4-4306-bc2f-2ae8133c70c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB3
04993020-fcc3-462b-9952-fa1eb35499ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB4
0f8a3c34-4925-4a77-8330-c0d1dbd05902 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB5
4cf67798-84f8-4462-aea2-1176e4782519 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1409 | Mandatory testing | CB6
68d0e8c7-6532-4890-bd0c-cc2772b9e9e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410
2aee3f1e-3ab2-4985-b64a-a10b2bb55813 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Leadins
564d7496-9085-492a-9d5e-4d0d32c2a3f0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Roughin
e6a064a7-227f-4355-a0a0-fa6cff2b70b9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Cut out
ad8d1457-94ab-4eca-a9ed-94406bffbb55 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Fit off
e3912043-0176-46e2-8243-331f7153c9b6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Commissioning
697b9587-5c21-4c47-987f-ff960f084c5f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing
796049e6-7d9f-46ee-aa60-6b84ea2dcf57 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing
fba89901-77cb-4e21-9d00-25696457e9db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB1
09f40b95-f944-4974-8add-25c24c7727f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB2
947e0a4a-2400-4bac-97f1-3dcd501c7819 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB3
587c37af-accd-4cad-ad27-15cd9582401e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB4
1228ca0b-3bf4-44a2-9ca8-565efa741868 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB5
28c1caff-57e1-4621-9265-7eb42d8b9aee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1410 | Mandatory testing | CB6
046c811b-f91d-493c-9970-dbe3259a7d71 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411
2af784fd-f37a-4132-b85d-d8724ce15aa2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Leadins
95ed8fb9-bf7c-4858-b3dc-2484e16d5db6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Roughin
c7c24c39-947c-4c8b-a182-d9386c366022 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Cut out
073203b3-ca0f-4e7f-9e9f-fc76b0d78496 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Fit off
0f3dbabd-c023-466a-80bf-c04d4765e3bb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Commissioning
db47cc1b-d3aa-46e4-af8c-b6f85d1e0cbf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing
905c6f1d-b668-4a14-95aa-2eeca27b88df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB1
acda8a87-4552-4fba-98ec-263abb33e097 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB2
393cca1a-4ed2-43bf-ae49-769c72e59151 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB3
c7ba7221-ebe8-485a-98c4-2d0f09e93da2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB4
51983b13-1d68-45c5-b362-8d8d6a8bb825 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB5
4091d841-7214-419b-9d84-b1f3ecefd829 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1411 | Mandatory testing | CB6
3890f864-8429-4085-847a-8d5bd004dbe1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412
fde9e8e0-35ca-4263-9e1d-7194c6d11ad4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Leadins
7a00e6be-8d78-4cb7-8ac5-205c9b87fde7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Roughin
0c1be825-cab6-47c6-b97a-5e66bd9330ff |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Cut out
defc046c-ba46-4a97-b6ef-5c644d46ef0e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Fit off
3737c8fc-4302-4dd2-97c3-e115578a5543 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Commissioning
d6b51050-53eb-49a2-b851-0a7765786ca2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing
420be99c-2da4-4357-b0d7-4e17249a12fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB1
0786149c-ea1c-453c-b546-924f015cfd18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB2
0b44abd8-de44-4079-9ffb-6c9fc9c0864a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB3
27b82e53-4601-40e4-aeea-91df54f90ff1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB4
4e8ce74a-f1a0-4fc1-8c50-e13b36161b2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB5
6338956c-16f6-418e-abe5-af3751d5a5f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1412 | Mandatory testing | CB6
3509f621-274b-4eb0-a272-a4cbd7a7520f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413
22d1ced0-b409-47a9-82af-84af8f61ee44 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Leadins
73d3f935-602b-4520-aae2-2bdddaab6db6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Roughin
af6a9fb7-8602-4fbd-ae63-514f8c2a52f7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Cut out
8b71c071-3d30-4b1e-9fd0-7d7306d59844 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Fit off
6c52c188-5327-47cf-85bc-ee166a375eab |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Commissioning
869f67aa-dc85-444e-9ba6-798102047837 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing
c7479153-a27c-4ff6-85bd-c196bad3c43a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB1
c42b56ff-a856-48e0-b027-925d91e4a465 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB2
91dca821-c613-4825-9f9e-24b7f8350d4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB3
7035c8d0-ec22-4dfa-bb89-4f92be053fcf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB4
c876cb9d-b950-4f09-ac2a-815c6e59a590 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB5
bc798e4b-745e-4784-9892-7d6bbdbb3528 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1413 | Mandatory testing | CB6
58c20e78-75e0-4bbd-a5da-4eb55aafb3c7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414
46cc243a-fea8-4a57-a9a7-bb838076cdf6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Leadins
88c8807c-fc1a-4d12-ae4e-6b777ce80d1f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Roughin
ba50c898-f883-4fd0-b375-c97d02200fcf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Cut out
55f1d131-4b1a-47d1-9b9f-1076c94ba07a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Fit off
ee4e2c35-e51c-448b-bdac-fe23afcf31db |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Commissioning
903fe42b-8864-45ee-bf9f-49d2c764b1ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing
2bf60e2b-074b-4669-8fe8-e16b7b0b6653 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB1
4e886288-cbb0-4e7d-aa00-399ea7081c3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB2
705db742-e25d-4239-ba1a-d2153b2bd1dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB3
70ec655d-b63d-4bdf-bb21-9c268ebf6242 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB4
c3dce2a5-3f36-4fe9-9f5a-4a51bec5ee01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB5
bc9c41ba-10c3-4611-986d-b6e9eb971fb7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1414 | Mandatory testing | CB6
67a096d8-47bc-467b-8190-494467660294 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415
af7dc90f-28fa-4d3d-aaeb-bb44068ed3ed |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Leadins
a106b827-9c3a-480a-9a50-a7e0ee4996e1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Roughin
ede17db2-b838-44c5-b321-e570bca50287 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Cut out
08f3d729-eb02-43ac-80b9-da04f10999d1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Fit off
e287385e-5a92-4ef2-8b9a-a4570836970f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Commissioning
489e19e1-4000-4dfb-b2b9-355ecf5e5bd6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing
39abb403-e17f-4b3d-bff2-583fc7d9478b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB1
901e7ed1-f045-42d3-8810-df0b3352eec9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB2
fcbd72d8-cbfb-44a4-a889-dc8af330dfc9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB3
467c2191-d4a6-4c40-a66d-e943f97fe19b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB4
0dd1d563-7aa2-43b3-b1ae-971804705073 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB5
c464f2eb-91e6-46f7-9300-2705f9ee9c00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 13 | Apartment 1415 | Mandatory testing | CB6
4b4786f1-e61f-4746-8528-2ccf4e02dc83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14
96516d1b-3de2-42ef-8086-f50f1efb96dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501
33e03774-0bc6-4fd8-9f82-c14287766a09 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Leadins
5be94909-3318-4f7e-b64a-b8055ddfbe0e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Roughin
e3f2bd28-29a2-40e9-9d8b-a1c69056f11f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Cut out
d564487e-eda0-4d7f-ab8c-744aa983c422 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Fit off
4ad3a0a2-52d4-4578-a7d8-f58768770aff |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Commissioning
bcff3dcf-5303-41d7-89bf-465cda25f319 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing
0d19fba0-55a3-4c92-b482-b3d7f0240d2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB1
e37d99a9-1310-4746-8deb-c48a221c0d69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB2
9b03bfb6-e03b-4b03-adb2-c41f86269048 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB3
175e98be-bb90-46c7-a4b5-b68a00fba20a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB4
1b6706ca-717f-44bf-ac44-5daa582c148b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB5
af15eea0-ea49-4b4f-8116-890794f16e01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1501 | Mandatory testing | CB6
edf7d4f4-3119-4dfa-b52a-b22f48eb0da0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502
603dc1ed-3805-453b-a348-3d04f091dd9d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Leadins
c056b2a9-6754-45e9-a900-16c4c0a42297 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Roughin
3fd8a76e-946a-4eef-a0fe-5825fe906b8c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Cut out
2c33d747-e6d4-4cf6-b88b-38e5815c1186 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Fit off
d18dd7b6-0ffb-42c4-ba75-1c59e3df64ae |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Commissioning
a3501cf8-f150-409c-8979-2b43f25071f1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing
134331be-74bf-41aa-927e-4379f4405863 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB1
8acee5f2-b72c-4ec0-bc26-b62be4de0d8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB2
6407a49f-6273-4713-b5fb-96d4960d747a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB3
16a8e2cc-773b-431c-b038-fd61f818fc18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB4
5d3aa3cf-04c4-4924-91ec-3bb07b0d1380 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB5
9320aa9d-f764-4d76-97c2-38b41513fe89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1502 | Mandatory testing | CB6
39443b4c-0423-4da8-a5c9-2209627a5e2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503
55251f8f-e5ae-4c74-867c-1efe2064078e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Leadins
9f24c555-c5e5-49fd-977f-06b18eba316c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Roughin
94bcadf1-faaf-4fd8-840b-c93f4ee2cc29 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Cut out
0ea7d787-1c05-40c0-aa1f-2f8955ab0299 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Fit off
f70b5e3e-e6a3-4d0b-bad0-716bcde7e82b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Commissioning
958d669d-edf8-43ad-855d-28bf72695374 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing
eff57e85-93e2-4e48-bb3d-8542f36bab4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB1
924ceec2-bc90-48a7-9291-af69ac113c60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB2
b9360880-4564-48d7-af03-9a72435c452e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB3
de9c72d3-5f15-438d-bf90-6e510f41fe3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB4
52384c12-7841-495d-8408-dfdcf89118cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB5
9cc48218-6e14-41a7-83de-67650c40e215 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1503 | Mandatory testing | CB6
0e78311a-a5b6-4d3b-9f43-e27e29b683ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504
f4174ff2-23d7-4ff5-8d27-7dd32f441119 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Leadins
f60672a8-5896-4438-8d41-659bf304b475 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Roughin
92acf2af-11b7-40ad-a21f-be3fac3b4102 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Cut out
e20706ef-56f9-4eff-bf56-0efbcc997599 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Fit off
46025269-d13b-40b1-8fce-f76bf2443331 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Commissioning
74911335-7359-4854-9122-40bf3278ba4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing
c57e534d-6d8e-4025-8fec-6e49903fef4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB1
af7c744d-8dff-4446-bcd4-f7ba66cef7c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB2
03f0a313-ed99-4870-bd9b-562a1cb15b65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB3
0bbb593e-2681-4a9d-a48d-6eb5b5d3052f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB4
327692bc-526a-452a-935e-31be0b0ea91e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB5
0e0d3d8f-173c-4a2f-9b99-9354d94893d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1504 | Mandatory testing | CB6
810164e2-d2d6-4a4e-a477-11bc7b2961aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505
14822a8d-cb00-41e6-98ae-fc20c8a1df4a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Leadins
f9e90e86-fab8-4ac8-8bb8-7c7d3b80dec2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Roughin
44c9e2ca-958f-4826-a8d6-d2cb6fdd457d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Cut out
4104495f-d28a-406e-9fe8-2586ea1d601f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Fit off
c94b10e3-68b9-4764-9ecf-9390a27c0d02 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Commissioning
55527210-b487-48e1-810f-e675f45c9132 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing
1468e2e1-d47c-497e-8646-5f70c3dce70b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB1
d39cb158-e6de-498e-86ff-096e76a7ed4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB2
c5277f70-a7bc-484d-90da-bd592d1f23ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB3
c080cd6a-d3db-4480-95e2-5790e4a46ddb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB4
dd59f98b-d8c6-4816-8ddd-cdf7a51ce384 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB5
e682c70b-14e8-4165-a9b2-86d9cc17c01d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1505 | Mandatory testing | CB6
fe62c1ea-8e21-4a9d-be8a-bacf217f5f7d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506
8e88dda7-9254-4f88-9402-94ac80a475ec |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Leadins
b6005ee2-5014-4d47-85f5-663e571a95df |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Roughin
081cb69d-5020-4137-98ea-6f0d4ec7e2d7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Cut out
d7d83220-6fb0-4a9c-8192-1a3be51eb498 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Fit off
7caac265-01a7-4079-a5bd-8a8dd2b4337e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Commissioning
ecbe2ffb-66db-490d-a348-5c7a71aab50e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing
aa421125-e845-452e-b61a-711862ab394c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB1
dbbea5fd-a8dd-4277-939b-0f454f58a7bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB2
8fb2a9d0-a695-458e-938c-08ee6eb70841 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB3
b5dfe78f-7c26-4fa5-b880-ccaf5d859a02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB4
4a7e8a3e-98e9-4cec-adf0-e13f6e04db01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB5
8c11b04f-fa00-4ebc-ae00-03275b6c2d1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1506 | Mandatory testing | CB6
9520884f-c861-45fb-8d05-4485d221e62a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507
6d3bf7f0-6186-4fa4-a9b6-a9ad80d8b75a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Leadins
8e128a46-b330-4dd7-bc5b-3089ab728b9e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Roughin
c3c8c9ee-6e4b-42dc-90cf-9d6c6107465d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Cut out
e1361d90-19f3-46f0-8a82-257f7a2804bf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Fit off
630a2414-df17-4461-99e7-218998fd2087 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Commissioning
9b05f0ff-833c-4dbb-a8be-3d30893bf073 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing
d4be5d29-e8b2-450e-8f39-bc06c41e86d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB1
61aa4db3-8376-4b9d-9379-563621c42b4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB2
85dacbdf-f768-47ce-b3b7-e8007113d333 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB3
6aebc3ac-2a97-4313-a02f-cb5c2c8854da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB4
1a541753-1a84-4746-9afc-de1422460a96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB5
a14cf3ac-6ddb-4700-b8e6-6b0f68316507 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1507 | Mandatory testing | CB6
73abd72d-5332-443d-a84b-d7fb8f9a66ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508
350dcfbe-4c37-47e0-8aac-575ff11b7852 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Leadins
8ae3687e-f0e9-4c37-b736-842c4923197a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Roughin
07994542-b443-4cee-ad20-bd213c7ddcd5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Cut out
42601f81-5752-497d-945e-d53adff1d374 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Fit off
5f8e0a25-ac07-4001-b43a-187a60309749 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Commissioning
976af37c-98d7-4390-b9c4-17154e5b1cf1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing
de8b4328-3b02-433a-abaf-1cc706931b11 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB1
90b88344-2fb3-4791-8c9e-38dea2b5b479 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB2
2373ed71-f225-49da-83b2-94277c983d1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB3
c38721b6-fd0d-4063-80ff-8326b846ac4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB4
2accb5d1-0f6e-4a31-9fa2-e9a6577795c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB5
36cb1c91-ce0d-48e3-b32b-3e55d40a8ce9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1508 | Mandatory testing | CB6
1e14ea0d-8d08-4808-901f-9121086e7e3c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509
381ae93d-efc9-48ae-b34b-6038fbd4e1a1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Leadins
f7d0194c-069f-4d55-86e5-af3ebc3fa5cd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Roughin
c8f5b5a6-8bda-40ef-8f87-d8061a4d5a31 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Cut out
93e260cb-c178-4fd2-bb01-868718f0b0f3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Fit off
7ae89d54-57dc-4267-a6d0-4be3e785c2e1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Commissioning
d656b1a1-62f5-4d39-b2b7-5d43ad61dda0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing
397dd322-d3b4-44eb-ad79-c06d8963fe10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB1
c97e7c8a-3a89-4dd6-a689-1ee21fb13a0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB2
2af0aaff-ba50-4dda-9b6e-57f56fefe1f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB3
5bc125b1-0345-4a3a-a58a-7349907c3b50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB4
d857a74b-90fd-4994-8cc6-ec0750c60624 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB5
1da5e8da-c62b-4a24-a5c2-af51ef3122d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1509 | Mandatory testing | CB6
58df1bd7-d39b-4ee8-94d1-8f77558bd205 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510
8702f00a-348f-4390-8690-81aa19e30807 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Leadins
86510e33-4f09-46f2-9ee1-065b83a3d193 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Roughin
8aaa7e6f-98bd-4428-9b39-80601b34ac7b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Cut out
c64bf5e4-8aab-4550-b191-e9c9656b746c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Fit off
116e2edf-3b17-40e4-824d-4cf7a82bf788 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Commissioning
23ee052b-47e9-4463-ad28-68127a159446 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing
a3606e45-3f84-4348-a4b3-693de64d67b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing
ca3cd6b3-f762-4128-9867-88722c4c2683 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB1
827567b5-2084-4198-b019-b8599f1a9234 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB2
0b87cec9-5958-4a2d-a9b9-f85431f2e70b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB3
680d9ec2-78fb-4f50-a81a-c9ee44a4ed93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB4
30de6c0e-e37e-49bd-8610-8fe2980057dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB5
a2b81c36-56af-408c-97a9-dae9769e9616 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1510 | Mandatory testing | CB6
7df63aac-b549-45d4-8258-f8d6fbbd22c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511
6359e117-5845-4f41-a191-9638d8932517 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Leadins
72ac7f60-b268-4aa8-97e7-4460d81971b1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Roughin
b4a53725-412c-4843-add2-69c0ac097437 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Cut out
d53d4739-fc35-4d08-a9de-25476eac6ed4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Fit off
65d4db3e-ffe0-4c09-b53e-fcc8a3610efb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Commissioning
1ce9f6fc-5db4-4742-a225-5099114cc6ff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing
57eb8adc-a698-430f-9502-28a68ace4cff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB1
28e4af8a-2aaa-4081-bdd6-7378b6c91f0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB2
6a7c321d-1c37-4a69-a171-ae90d05a536b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB3
d9be0984-ee53-40cd-a3e1-e17dc00214df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB4
86d19cdc-a591-4046-a981-b8c90ecf71e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB5
aba8eb62-c63f-4193-9838-ed61cfaf57f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1511 | Mandatory testing | CB6
06bb4f3b-6c68-4fb6-a0d7-7047aaf7e5d0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512
f4a8c8a3-f25d-4df9-a3e6-027ab9ed33b0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Leadins
b4c1b48f-d937-40b9-afda-a3742c73bcb9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Roughin
9413f559-70af-4390-995c-e365142068bc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Cut out
c00e98cc-d982-41d0-8500-6bb5c5dcd302 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Fit off
d1f5aa9e-d3a1-4116-8114-142daf6bc931 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Commissioning
81b854d4-3b77-4d77-9aa6-d55609a4a5a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing
7c691744-e4ab-4c80-b277-9b5d22e75bca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB1
7a899a9c-1b5b-4975-ac33-b37ba7dcef77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB2
664ff2aa-8656-4d91-afed-191ceb991b75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB3
cafe82f6-4764-4a96-87d1-b0ac1abeed46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB4
0c3e1dd0-4b8b-412f-b934-1a851abfd6d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB5
13ebfa69-2c00-4620-b876-6306570de7f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1512 | Mandatory testing | CB6
2eff339a-e3f9-4abb-956d-b2b624fc38d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513
56a7b6d2-1b60-45bf-be58-65755162478d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Leadins
984cf551-0a8a-49fb-88b4-7238e0f64192 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Roughin
273d6381-eb7a-469a-abf9-e2dd1c285a26 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Cut out
99714b9e-4f07-4be7-a0bc-74a4d0f97c6f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Fit off
f904fbe8-1c74-47d9-9a36-b9485f483d7e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Commissioning
78b3e9af-fd34-4758-8ff0-2b7ab6ab2e85 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing
9168f8fe-9e09-4dc1-8766-8ab3f3431fcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB1
0ebf1962-8f28-4f0d-8e58-871e10e08949 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB2
19fa759d-f5a3-4b3d-a284-51d39795df8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB3
bf3d3b41-4aa4-4593-9dfd-16d50405b163 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB4
8b2ef80a-b7b9-4a1c-aeeb-e6c536db1df3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB5
c326d773-f3da-432c-8772-aef388632050 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1513 | Mandatory testing | CB6
dd22fd8f-677c-4f44-8a05-381532434899 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514
fde70291-e595-4b3c-9de8-59a6f5ca8312 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Leadins
ffa80706-650c-4e7c-8843-e938818d4cf0 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Roughin
82841521-0046-48ae-b6e5-2589c6598da2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Cut out
065ccd27-df93-4abc-8942-22d873ae3d61 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Fit off
b566264d-0a9c-4304-9846-9554d33ef851 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Commissioning
10d95b65-2458-4f38-aba0-21ff9dad87a1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing
762fbeb8-c7ce-464d-b2b0-2d2f2677b975 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB1
51804d63-b1ef-47b9-9c96-725913b795f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB2
e3b32d0f-0c19-4a51-819e-aea28fc90aaf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB3
2296b61e-ffc9-414e-86db-b126df2788f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB4
333627da-fa3f-4c62-82cc-44f41446ac39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB5
9df44177-c877-4924-8add-ba597cb6cc14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1514 | Mandatory testing | CB6
9d442c04-fc59-452f-8887-7915b7e541fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515
b8a48341-a491-456b-b0f5-b668f9a80df7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Leadins
acc93276-09bb-4a4f-b437-9fe68b70e2df |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Roughin
ba7d956c-6a49-47d2-810d-eef188d1e72e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Cut out
3d54104e-2811-4319-98c6-9b975bc186fb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Fit off
2092a1d5-6a28-47d3-86c1-a88ecc9a99a8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Commissioning
8abb5427-ae82-444e-9514-57469e3d684c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing
9a2f67b6-82a5-4dfe-a4c6-73d433061a5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB1
d98389fa-4dc2-475a-a83d-cd88404a1045 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB2
85c071bb-94b8-4b9d-906c-0c2e6646f170 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB3
05359213-f931-4fc1-b328-bd28daa14d63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB4
55cd3021-8eab-4c3f-b44b-7ea95e7730f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB5
ba47d111-4f00-4e5c-a67e-868b4d228d00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 14 | Apartment 1515 | Mandatory testing | CB6
a8407c52-26a8-4bc1-a0d2-a3de81d5f80e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15
78e58dc7-d9c3-4b91-8ffb-fbcdfd295749 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601
6aa90f35-a484-49b5-8c6b-4b2213cbb928 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Leadins
35abfa7f-9654-46d2-98b1-3c46bd25d509 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Roughin
a10c5b6b-2529-488f-9d1e-4490bdf23d09 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Cut out
30f48f47-15d0-43e4-a1a1-c5156af10cc1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Fit off
4482cad6-b54f-4e85-8827-4e6b9a7078cb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Commissioning
76ddae9d-997b-43e0-a571-79a15716a062 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing
b68c42a8-84ec-4c58-b749-8f2e70b59765 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB1
87381a7c-b0cb-4ef0-93c5-ea54bec0935b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB2
e2a353e7-4e37-4ce1-941b-3f4180be67de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB3
96e0a4ad-ded7-4c80-90f7-21c7fac7b113 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB4
0822cad5-5767-4dfb-8836-d74a9048776b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB5
f36c0d00-0c86-4d0b-8e8f-c3b68e96043a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1601 | Mandatory testing | CB6
a1252651-77e1-4a60-8845-e675bc46582d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602
a636ea08-2a8b-45b5-8ed8-daf7030124ba |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Leadins
fbc119e9-dcd7-4d46-86e1-8ab3d0fe8a19 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Roughin
c83268dc-b4b3-46d5-8546-c7bdb7729761 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Cut out
e2eea7da-b905-4409-bb3b-51acdb63c846 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Fit off
6c7f9f18-d515-4453-90ac-70c2ce755dd4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Commissioning
081153ce-031f-4f9c-af43-7fc7a0fda724 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing
0c79fd1b-d9e9-4192-8cde-ccf085ce6e6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB1
c16c3c17-ae59-427f-800d-0a43ef063cc9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB2
6625e1c7-84f8-4a62-a204-6dd5b36fd93e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB3
84e447ab-4634-4398-bc5e-e8a75ab2358f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB4
2f4d9551-21c0-45cc-bdce-dc689d632bc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB5
8c475371-45ee-4fe5-aa9d-c6291159b72a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1602 | Mandatory testing | CB6
127a1419-6146-418b-ba8c-9d60024e7bfe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603
5f17b4d8-5257-4bd8-bf30-c7f00c09fe27 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Leadins
503ca87f-c3ec-4abf-9221-78d46398757c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Roughin
b13946ae-bd0f-4ae8-8cf3-c48b1a0ad6e7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Cut out
3d1c79c9-b904-4190-8449-4b8e35a37071 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Fit off
1ab55976-e216-4193-b19e-6787ef696e48 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Commissioning
129df7a0-71de-4d83-b0f9-1d717e3f180d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing
9fa8181d-1be7-41e3-9f3e-65c7d9036cb2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB1
16edc315-f41b-49a1-852d-16ad4bd64b9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB2
aa0aadaf-4310-480b-a933-d705678720de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB3
8ad08afb-4682-484a-9354-b0166c6df895 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB4
92de644d-0e0b-4055-a750-a928e3b5e6a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB5
0955719e-db7a-4aff-bf34-ef5b4c9cd679 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1603 | Mandatory testing | CB6
e7562877-f290-4911-a0be-26749f928441 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604
493cd789-b812-4182-af47-b69567f17688 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Leadins
c07bfa6e-bb2f-421d-a7d8-a4e4d55f75c3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Roughin
22d9b419-e70f-432c-a95e-c0428ed43954 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Cut out
fab73774-556f-40e0-b4c3-f030d08c8e95 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Fit off
a9e3a0ab-bd07-4868-864c-947ce646aed8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Commissioning
46e7e6e4-7f42-493d-a36e-bc66d4c8cb02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing
74ffb72c-80e6-4420-aa20-5dc55b25cbd6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB1
823a8982-bda5-4dd2-a6ed-b08359aa066a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB2
56acb43a-864e-446c-8af1-fb8e4365f792 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB3
058b3f73-5683-43ae-b92b-3b975fd0ecb5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB4
d5eb9dfa-8e09-4949-a36a-ef6862d7a5fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB5
ae19e0a5-6e0b-41f1-8c3e-0ac493169e41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1604 | Mandatory testing | CB6
a373b455-b877-4496-b551-b30880c8a234 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605
cf3d782e-f2c2-4723-b93c-fe13e6bd36b1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Leadins
484ddfaf-e601-40de-8664-ba5459b7875a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Roughin
5259a49c-530e-4f10-8625-1dc45ca5ae1b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Cut out
0baa826f-276f-4fdd-af65-cdaf997b2635 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Fit off
84bd2cc9-0be8-420c-9cee-e6d32eb2da5d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Commissioning
6dae4939-52b7-409e-bf91-6bd61eb36a27 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing
ad384ebb-ca9a-420e-ac34-ae181fb9c276 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB1
c9f7e976-0834-4f06-b36f-fcc2602a70fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB2
7e65408d-6355-4afd-8ac9-2d813a2caf08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB3
1da4d579-cc29-4f67-971a-3e5fb6747c7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB4
f7f9ac41-e753-42ee-a867-aeb0abdc6397 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB5
b2e04fe9-bc48-47f0-bdc2-c9fb52daa325 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1605 | Mandatory testing | CB6
092111fb-ac17-45c6-8d9a-cf025e83a7b3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606
4747e750-9274-4bde-8de8-a41936b9d7d2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Leadins
849306b2-9ea3-4d32-bfb3-d1a0e1eb2bcc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Roughin
718bad55-d4af-479e-8dd5-9eca2016d370 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Cut out
457f340b-cf93-4668-892a-6ea8457d25ad |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Fit off
0464c0aa-4e43-42d3-9706-71828033590d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Commissioning
1c5af6be-8e7b-4e62-ae9c-8f6438ee1a67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing
d3b01130-1897-4fb5-b14b-65eab3da49f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB1
5493404a-0825-4ce1-a1a2-56e5f8b32cfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB2
9d3cc2bb-16cc-444d-8444-e6e3609878a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB3
080e6665-86f8-4a95-9fb3-cb935df06d5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB4
0d665a45-480b-453b-90de-765fb353fcb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB5
5c8f5aa6-d07a-4805-85cb-8c46f31038b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1606 | Mandatory testing | CB6
57c265ed-bb35-44f6-bb1b-d8c97b6cace5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607
a28434a2-e039-481d-8872-d6b99b806c19 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Leadins
1e43a49c-c9a4-4354-930d-93dc937ea985 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Roughin
a2fe9128-bb13-4c2e-98cb-a8235a99d583 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Cut out
34a126b9-7d75-4fb8-b41f-085f79f72f28 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Fit off
14bbff3e-3bc1-4a6b-b3ae-5d3383ebf542 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Commissioning
581048b6-0565-4c53-917f-6fd74c50381b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing
56b4b861-59d6-4c25-ad11-6323b1401e17 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB1
f1142cc3-6d62-4a04-a270-3ece1af86001 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB2
4eab9fd4-adec-48e4-97b3-a0dbfae9e7fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB3
d36ade2e-d927-4b3f-9f66-e51d7d17113e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB4
174794be-3ec0-41e2-a6bd-675f5f67dfd8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB5
d0ae48b9-1d8e-4e55-832b-dc5eb1dd7552 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1607 | Mandatory testing | CB6
478b3621-5d6a-439e-849c-b49aa2572dbf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608
756287da-cf89-4e6e-b87e-772790417546 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Leadins
ed6d31fc-018e-4f92-8df4-44eb1b836250 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Roughin
fbe6ad4e-b80f-4eca-98b9-c7cef543df11 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Cut out
6f909016-9876-4432-830f-cc82c9f9b431 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Fit off
460df845-d8ec-4e2a-8a02-ee5814008370 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Commissioning
f2ad378d-351e-4c08-897a-937fbe24479e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing
a25741c8-4a3a-41f0-ad3e-bf1902599bd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB1
a2d8dd3c-6fc3-4f87-a197-5a1597ac2f0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB2
8bac9a4f-2d70-4dc9-81e7-13dfd1dc4172 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB3
26d4ff51-0afe-480c-998b-2dc850d3831e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB4
7bdcc2fd-8997-4dd1-94bc-820425492abd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB5
a08331c7-7300-4e44-8d51-4090de8be1dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1608 | Mandatory testing | CB6
5aafcf2f-cb20-43dc-b85b-96c9f24890cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609
5e288c69-b409-4b61-81ef-60e4a787402c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Leadins
8062f1ef-deb1-4d36-964e-3228be7030a9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Roughin
5c1e7f8a-4265-4570-aede-5bcfd0ea8696 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Cut out
4283a7cc-379b-4419-9e5a-aab920c0026f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Fit off
763122ca-0ae6-4c5a-b811-6c2e5cafa9e9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Commissioning
63640ccb-f904-4eb3-ab70-355304dc3912 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing
ec9fa309-a11c-438b-bba4-95912cfe9696 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB1
3380f952-f208-4d54-86a0-a1f8bc90b283 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB2
d4bacc14-41e9-49ee-a6f4-bf744672016d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB3
6a307016-46cf-4fe8-ac76-4a8269b79113 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB4
8a510e93-e573-41a5-b015-1b961848178b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB5
7543068f-b3ad-4575-b7a3-6576b40aa37a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1609 | Mandatory testing | CB6
e715c1af-8c8d-4cfb-aa23-3e60355eff1f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610
6c974e9e-fa9a-48e9-b14b-9afd933f8927 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Leadins
e6ee93dd-055c-4ada-a943-de9223a982fe |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Roughin
4b014acc-e882-40ba-a093-fb25d539a282 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Cut out
5858450e-2e40-4b57-a890-0305c8e1e72b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Fit off
4740a0d9-fb36-4b67-a778-fde190fba1bd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Commissioning
36222977-8336-405e-bd78-34c5320e7a62 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing
b6647990-8f95-4c1f-89f2-745bc6c0f263 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing
04cd81da-cd8f-4ae8-b58f-4c0f755620c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB1
30ecac13-cf48-42c3-8b97-3a75d6e9ed11 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB2
97e8a008-50de-4c77-bb8c-23b8b763b9ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB3
b5df9284-2321-4e5c-9726-0af35b5d3d10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB4
2680e88e-fbb3-4f17-8049-69612c66e568 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB5
3944412e-3c30-425b-aaf9-202ae3b72549 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1610 | Mandatory testing | CB6
c19d5412-1353-4c4e-8ad1-c103ba1f43a7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611
14b63ded-4278-4490-8553-abeffdafc152 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Leadins
1876d194-44ab-439d-90de-a9bb5d9889b7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Roughin
9d7c8517-e230-4273-8436-da6bfa9d5e86 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Cut out
24bbe8a3-cb8a-447d-8b98-92fff55aba23 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Fit off
6d8556fe-56df-4014-8286-6b2b1dc8c3cc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Commissioning
cda40dde-ef3b-4e5e-b1a1-de8c5c42727d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing
52091e17-44fe-4f98-bf97-d09b3b73dc88 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB1
5c162271-c565-4923-9cce-e5282abbd8ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB2
dd62078f-55f8-45a7-b1d4-70288d31056c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB3
0f7f231c-2dfa-409f-808f-2173b09a9df3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB4
a2304e7c-f0f9-401f-8b7c-700bb5a1fd30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB5
671f69da-95eb-410c-9e54-18051bdbb215 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1611 | Mandatory testing | CB6
6c100ef9-54a1-44d2-9277-59af4d51f71c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612
053c983e-cdba-4841-af3a-a2e1a1802d8e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Leadins
80c6a0b3-afdd-487c-9f49-12ec19393b39 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Roughin
90486e40-f4cd-40ba-935b-dbc57aa3154e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Cut out
0bd15445-662a-488f-9034-a9ceba49249c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Fit off
39179125-e3ce-4b61-ac9f-561c901ed673 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Commissioning
3fc94133-3c2d-4ed0-8d1e-917a8ed22b79 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing
a4490bcb-3377-4064-83df-7c09d108be55 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB1
cdc04454-bbee-4bfd-8b00-5adc4d13c411 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB2
e88c7dd4-1922-4a8e-b169-c2eee7f8b4b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB3
f0b5d23d-4b82-4fa1-9704-304eec9016b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB4
58b5d6b1-d5ff-4c6e-8572-a3aefb55ae8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB5
69082cde-7d76-48c1-8c2b-6ee48f7e44e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1612 | Mandatory testing | CB6
acfac3ad-44c6-44d7-be60-e3de1e9ee020 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613
8463fe19-8836-4007-aeb4-8a8117680b3f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Leadins
d89baf2e-a3c5-4c81-846a-b422395d0823 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Roughin
50baefab-ecbc-46a2-ae32-f960f6b28fd9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Cut out
69d6d916-099c-4bb7-83a8-ea8139451690 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Fit off
da47733d-55fd-4f9e-af4e-0bb30d9c9e93 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Commissioning
966eae65-bc5f-423a-aaa5-cc4705ded460 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing
95f86adf-80b7-440e-b2dd-539bad42e6b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB1
4ca34ea8-c243-4c3b-9357-80d1d12ffa7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB2
c58a344d-663f-42c4-a02c-0541affa9380 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB3
efff7e98-2d1d-41fa-99cd-86a0a6e27057 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB4
b442cd30-92b3-4b8c-a229-da9b7a7c0777 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB5
83d60434-0d55-45f5-b6ba-b46b4054e2ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1613 | Mandatory testing | CB6
bf61d9db-8fa5-491d-8b43-49e3908b4f41 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614
de26c7eb-cfa8-4706-8128-d914e7e3dcae |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Leadins
35f76ca8-248a-4bd6-8e24-42a245432a14 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Roughin
04d94488-6c3a-495f-809b-0c720f95b4c6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Cut out
6487d6f1-2562-48fe-b653-50eac54ab4bd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Fit off
c230e96d-2d8b-4534-bce3-9eaaff25662a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Commissioning
8a409241-cafa-4683-8526-385bbf790957 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing
9c6b0ddb-76b8-4270-8cff-770819730236 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB1
e3c65738-b22e-42b7-816e-0f4e48d36a75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB2
07f477d5-e9be-4cb5-a1b4-34e63ccdbdb6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB3
060aa057-5a96-4dba-bacc-736c631f20ae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB4
69fd5140-9682-4514-bf06-6004486c91df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB5
8584030e-ce77-4d74-b421-00e51b7221b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1614 | Mandatory testing | CB6
b6c2def7-d040-42b5-8e19-15af528bd34c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615
15f8c29b-cbc9-4430-92d4-5ff1ea69c303 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Leadins
8c86d258-dd27-4915-a7cf-fd718e628a91 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Roughin
a1df67a7-abd7-46b8-a4db-7eb91f85405a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Cut out
be950c1a-8600-41e1-9902-f645188d026e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Fit off
3e706f4f-222c-4687-aeb1-e58c9fc07110 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Commissioning
f2b89b50-5e0b-4321-9d69-bc9e150632b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing
e05bfe7e-9e6c-420a-8ca6-b0866e186739 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB1
629f9110-e01c-4022-92de-ce5ba18cf8e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB2
2d265c9a-3e20-4877-842a-ad5b22248ca3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB3
7c7a74de-c826-46d8-884c-fb0c20b79419 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB4
4182788e-4a90-4d40-8819-f634d8d3d7e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB5
35784e8e-0649-48dc-be6b-4708a2cda2fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 15 | Apartment 1615 | Mandatory testing | CB6
5e5d2953-9089-411b-b7cf-b9ec07064ac8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16
674a34f9-b9db-45a5-846e-735162b572d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701
1677fe8e-2bcd-47a4-a435-f714ade5b040 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Leadins
a875e45a-bad4-4ccc-8184-6235999584fb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Roughin
5bbe4b79-e56f-4cfb-b010-06c33dfe2999 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Cut out
004cdfa3-f0dc-481b-b0af-8003b6ee8b25 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Fit off
822d5fe0-c67a-4c17-acfc-63aec0989ba5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Commissioning
b22fc4e3-8e8c-4381-b6ad-cb5df0ab8ddd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing
13bc3910-b32d-4c6c-af17-313026753c01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB1
98b6a19c-913e-4ca9-a074-aa144afdb9f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB2
105e9144-3005-450c-945c-20f7e714a852 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB3
802f57f9-3356-4e22-8b27-61da37b8ba4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB4
8829a1a5-b40b-4f66-b7f2-ac6654f38cce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB5
e312d060-7ed7-4f2e-b74f-ab257f400e11 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1701 | Mandatory testing | CB6
09fb162d-d448-4aeb-9e07-7c0203ae9a8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702
e7688cfd-2a9d-48a2-935f-d57d6cad19e6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Leadins
a42e9116-8459-4f55-94df-75e515bac864 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Roughin
cf80bd7e-4aa6-479e-9eb2-317194d095b8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Cut out
0883f474-bf61-41b4-9eb8-916f285758b1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Fit off
98bbb781-e173-4d3f-8583-ac5143e7fda5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Commissioning
3ac6e664-e4ed-4d17-88d2-0505e0cb4e83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing
34265697-7efb-4aba-9c17-69e09b557a1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB1
b2f6aba4-ebcb-4b03-9535-6a684c2bb37d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB2
fda773b3-ddc3-46e1-9e16-63c85e4847ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB3
3c7896ed-3648-43e9-b935-ffc6e0e2eb47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB4
4a0693fc-e495-4f49-8577-ad83f591337e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB5
9d384699-11be-4958-b2f2-5e7d85036ecf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1702 | Mandatory testing | CB6
5380746f-cd1f-4fa3-a9d7-389112b8d2b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703
be12a575-f691-4229-8f25-3cde2e703461 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Leadins
157721c8-79e1-408d-9bdd-1b111319cf81 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Roughin
42557b3e-8c74-4d82-8899-a2a18ab6f50b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Cut out
1de31859-5cde-4c04-b227-6623b8573d5a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Fit off
202f2910-8ebf-4e1c-aac8-bc7e4f770709 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Commissioning
7a2e8436-0a08-48ed-8665-b7edc02936f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing
0cb68083-e3b7-4174-908d-7a4c4bf594f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB1
b7ba0f07-81f1-4816-bc13-7a7f67d3433e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB2
66d0d468-b726-4485-8d55-de0317b7af7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB3
c669ba81-f360-4a03-be6a-bdb1e4e314ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB4
15582ae8-5fb4-4360-ba4a-9c64a2789a6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB5
c0614a12-ddb4-421e-b680-72ea603974df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1703 | Mandatory testing | CB6
841b8f31-e90a-44b9-9c80-07a575c34125 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704
a2d68ad7-ebaa-4563-bed4-79b2caecee52 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Leadins
44730f9e-5e26-4ae9-940c-011abac0bfa1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Roughin
d2c8c64f-a48e-461d-badd-156e4c6556b6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Cut out
ed59675e-c83c-4e46-86c2-e30c5eef9048 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Fit off
158fcd34-0a22-4ae8-9bdf-98b3c3addef3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Commissioning
8af6aa6a-ffc0-42f6-b53e-07e1eae97401 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing
e0aa29e0-b2b2-4326-a5f5-041e9e515a08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB1
3c9c464d-e66d-4cc1-b2e8-b8d4ac53caf0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB2
ac230f9b-2d7c-4845-b677-142bbc2ebe3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB3
5477d54a-38c6-4326-a278-8c5d40154fd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB4
89b38d9c-1e90-4a4a-a269-6c8839aae5ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB5
9bd502ed-4077-4e80-b35c-ef93b33aa577 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1704 | Mandatory testing | CB6
108862c5-7e3e-4f61-a270-9fcd3c5f3d56 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705
b2ad8ad2-f276-4494-a90a-56bd6cad19bf |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Leadins
957ed71b-baf5-4bf5-92dc-7ca33b7155ca |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Roughin
c753a321-673e-464c-aa79-7292d65079a9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Cut out
acd4c950-e896-4f85-921f-13d626733a96 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Fit off
73f429ba-d48d-47cc-b81f-a4452e73526b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Commissioning
739239a7-e0cb-4cf4-9860-21217ee51d4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing
43112189-7211-4f55-9fc2-ab6f35e4b070 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB1
fc5dfc34-ba38-4180-863f-22ed06fcb3b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB2
b084bc3e-1ffa-4e14-bdb4-72f8ecf322c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB3
bde97716-1490-4913-99c9-89227b29ed9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB4
e7e60f0f-1cee-4eb6-a313-b9c865a4a34a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB5
d0b00c54-a147-432d-a2dd-6ca6f64f315b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1705 | Mandatory testing | CB6
2055a492-3472-4ba4-bbde-52694465ae89 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706
7758406e-683c-4b44-899a-25a8362c6fd8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Leadins
42e9a4e8-ba53-4fd0-a1ab-dca199ee6d61 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Roughin
314c087d-1bc0-43a7-863f-380e9abc5306 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Cut out
a839883f-fa4b-4dc7-b605-a863466e9778 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Fit off
acf5bce6-658a-483c-8ab3-128037e502bc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Commissioning
711a21fb-5eb5-464f-aa97-29316b375376 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing
337829bb-8dfb-4205-a929-17c5cb8f4635 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB1
5e9a0424-e40a-4386-941c-2a8e3cf1a560 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB2
29aa1380-7275-47a3-8273-dd5a60566097 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB3
5692230d-6b7a-46f9-8017-92b2f8b145d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB4
169873cb-6e29-4c1b-a764-95a8c171063f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB5
85166f2a-1dc8-483a-8362-9c05c39d1e89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1706 | Mandatory testing | CB6
1be41d7a-2629-4315-b7ff-ec8c53f40f29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707
3e1bf20a-b49e-4a95-b7d7-1430cd9a8c37 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Leadins
03fe8f63-6ad8-4407-952d-864ba219ba2c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Roughin
6db357fc-f26f-42c2-b0d4-b83cfb2335da |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Cut out
cda25446-b517-487d-880a-cf4cad6682db |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Fit off
248daa67-f200-4e12-82c6-57157c88b810 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Commissioning
c1f5c269-bb55-42e4-97f7-4a1ddaed3ebb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing
4911fbd5-cd3a-49e0-af9d-6447a3048309 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB1
731178e3-3383-4f34-b8ee-31af2d730785 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB2
c438e05e-3144-45a8-8bdf-1f654d55aef4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB3
d6b3091d-2d63-44a6-a2bf-5d632390e932 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB4
66ac845a-9367-47e5-ae34-1e6743fdcc05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB5
4f989fa0-5872-4750-847b-df847fa7cfd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1707 | Mandatory testing | CB6
73726b3f-7a7c-4a04-b62f-a46f83c2f0cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708
cb20a33c-4669-435e-8439-88588390bcff |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Leadins
a84d5abe-91d9-4615-8f9e-7a7dd91d3c13 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Roughin
960bfea5-dd00-4796-9205-bf2fd38c440b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Cut out
716a2e79-c3da-4b79-b6dd-81e5d61c6d07 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Fit off
07dc8356-bba9-4712-8fc9-f6c5a14b3bc8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Commissioning
43f628c8-649e-4c53-98d0-c46b80618d99 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing
5dfea902-5e56-4eec-a4b6-6e49ebae269b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB1
0d4d963b-956e-4b91-939f-7d9e6fe33712 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB2
f9e75917-aee2-4b78-be8f-606ef6b3ef47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB3
2f80f6dc-2aba-4579-8a5e-16a31e2bb417 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB4
32e1ace9-1c3c-4fe7-906c-52076ce3f34c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB5
332e7e19-f8e4-4d15-9b9c-57c3bf6dd1bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1708 | Mandatory testing | CB6
cfe179ee-8101-4dd9-b606-fbae7f7b335a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709
e2330dbe-aef8-474d-bb6c-25d1c918769d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Leadins
98fe00ed-0de9-43bb-908b-379c835a6843 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Roughin
096da195-6f7a-4869-8e92-d6fd844d01f9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Cut out
89bff8c8-912d-480b-9a8d-776b73038028 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Fit off
a7d206f5-d6a0-40a8-ab34-6836abb3360d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Commissioning
8e68bb9a-81b5-4c6c-9c41-56ac8694143c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing
ebe7f6a0-badf-48ee-90e0-5d1853277b8f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB1
aac9cfbe-4536-4eff-ad11-15039d7104af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB2
5b4ac8ce-3f1d-40dd-9945-f139ed77860a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB3
a0856d9f-461b-4cad-a782-a01e4d655271 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB4
592390bb-a54f-4c92-a34f-765f8a61e0ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB5
9cf05d14-2e04-4b77-8c4b-29d353d14366 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1709 | Mandatory testing | CB6
c5984c14-a93e-4892-bfdb-5700e0323d9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710
3a260960-436e-4b0c-ba05-589450393317 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Leadins
203aa204-0bee-444c-8d05-4fc2099869bc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Roughin
e49d6ba7-ed1e-4813-95fe-0608a3f54c4b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Cut out
4772b1a0-0dbc-45fe-a30d-f411f8bb8b39 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Fit off
589eabed-8ecd-468b-8ae2-e3a142a184a9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Commissioning
0893296f-4b94-4fe1-bad5-da31b8e19739 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing
0ee1ed41-8b9c-422a-bb6e-5ced51b4d940 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing
49585a5d-8b7d-4542-8449-d1569b1d3405 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB1
e6888de7-29b3-4275-8583-4c3467a3a1f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB2
5e473af3-fad4-4224-b9f1-7e71a685786c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB3
cb465cca-2e54-494f-8320-71e064a998dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB4
d9d0716b-4294-481d-b3cc-bd0b2ff5f388 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB5
36e01a03-073a-4b0e-bc57-03c8ba3d95bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1710 | Mandatory testing | CB6
3f6ad29f-7d62-4b1a-9b2b-13e49152028a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711
d4a94c92-c434-4a50-919e-c3e38964269a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Leadins
159e221d-5c4c-491a-adf1-398bd83437fb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Roughin
f35459f6-7c86-49da-a0be-d4ef990c5ae2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Cut out
4c313dd2-2adc-4d53-8d81-d56be1394eaf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Fit off
cefaf761-467a-450e-9c59-405cc06b5417 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Commissioning
4014aff6-ef76-4e51-ad21-b85ba62d07d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing
f60a72c2-4533-4963-9b16-71a53f5aa276 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB1
17f0200b-b741-484c-aad1-61e9018ce369 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB2
d705342d-0bae-4d0a-9008-8ba77ef0031c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB3
ade2d68c-0d92-44a3-bae8-e3f63b77e895 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB4
b0990990-6bbd-4812-98a4-835d979bf436 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB5
dbd29ffa-396e-4af6-b0c4-e56e41642dc2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1711 | Mandatory testing | CB6
70a14678-73da-431c-a162-b8baab9a811e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712
0d59a288-1010-4d42-87ed-49dbcfd4d91a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Leadins
7e3ac2b6-850e-447c-a94f-af6ac0f879bc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Roughin
b7a9e209-9987-45b9-9805-661a4e728e6b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Cut out
c1d456be-b7b3-4915-bdbe-438f75e014fa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Fit off
cd8367bd-cb91-4eb3-97fa-170b47d2d49d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Commissioning
1fbb1b7e-7c98-43ce-b18b-fe3917fb3290 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing
5fa2b7c1-3cd8-42cb-bdda-36817e8540a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB1
718c037a-38f7-433d-9495-96a56f52c97c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB2
04098ca0-d5b3-47a4-b1cf-1845a49989c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB3
c0856ba2-2ebc-4daa-a1ee-e8e93c1bf7df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB4
ccde9abe-629d-4e1e-82b8-0bfe8ce17430 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB5
76106ea3-f07e-462a-ae60-20a7636848a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1712 | Mandatory testing | CB6
0c53db26-2917-48e1-9aa5-45f91729b143 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713
ba370542-4185-4384-83e9-0d7edea53d39 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Leadins
073e5b01-130d-49c2-b9c5-6adf827086b9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Roughin
c1450281-809f-4acb-b6b9-b94a06d168e3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Cut out
0670b4f8-df90-4076-8936-f2985f434cb8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Fit off
c5afba56-e86f-4c1e-a8e3-3f53207c86b5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Commissioning
abd6f241-06a3-48dd-a6ea-a187d333013e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing
53c5a886-5984-4cb6-b51f-addc9e0125db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB1
f0acc1ec-9865-4e2d-b19f-bd4e3d172192 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB2
906a0eaf-298b-4803-ab63-c5bcac5ef7a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB3
10427fbb-e5c7-4e35-a45e-be5b5a323a6c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB4
4a9816ec-1f24-4e8f-a802-93f2620b82bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB5
767f5098-cd49-4b92-a594-5e2270f41148 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1713 | Mandatory testing | CB6
ba6ef610-f0ff-4c28-bd01-1efb04ea9b2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714
28d7645a-2c72-47d7-9618-a17af3198b39 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Leadins
c9b27bb4-be47-4404-a73c-6ec590b969e7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Roughin
b60336c6-0785-45ac-9ca1-ee2f67ce16ec |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Cut out
56e82542-b2a8-496c-920a-ec862f9ad267 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Fit off
0df97843-6d4b-496f-a5b3-4fadb18bd477 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Commissioning
03eccc1b-d816-4640-9cf5-b45643a7c8f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing
4e08f816-8ad3-45aa-86fb-bf35a438ef0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB1
f0659952-b4f3-4923-95dc-54c3ee8c656c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB2
f1f1cb9e-28f4-4dda-9644-6035f3fd647f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB3
1d32b5d3-afbd-4331-8fdb-60e634f11b24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB4
1ea0ce39-a4a6-4cf1-af69-c22905f968b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB5
2dbc4c00-72bd-4639-9d4b-e2a21111e740 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1714 | Mandatory testing | CB6
c7743852-bfba-49b0-baa5-3150b533c177 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715
2877f448-1ad0-4f34-b015-fffe3ecfa3cd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Leadins
a0e0c7c4-9abe-4646-8378-517b10c151aa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Roughin
1e674818-6372-41e1-bfbf-7cb6a7c6c564 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Cut out
fa6687e0-e683-46a8-9a52-1b9e1d818216 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Fit off
76a64875-a541-4241-ba19-a4ab95672465 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Commissioning
729d5adf-0d6b-4d02-8fb7-690f7cee944f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing
f0262dda-bb5f-455e-a8b0-7d8e400c73f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB1
3b42465e-3b45-4922-a692-42e1f8164ccf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB2
c1c3326a-49e0-405b-99ad-4245483386f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB3
82932aff-d252-46d4-b7d4-a8eded2dd5c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB4
6f88fe9b-e31e-4569-af83-4b071cb63277 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB5
8cd56155-033b-4232-b101-d68fdbe90985 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 16 | Apartment 1715 | Mandatory testing | CB6
44ff8911-edea-4d7d-a973-241d16e36d5e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17
f0f819e2-f914-40a4-8b13-e355bf556f05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801
0e585af0-4581-4da9-9697-7c2e7314a773 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Leadins
238bd0be-c71e-458c-88e5-ba5c8d38391a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Roughin
f90b337b-4e8a-46b4-bfa2-b7554e3e216d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Cut out
88576ef3-9d9a-4bfd-9d13-395e5ac5465a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Fit off
e8684e39-cfd4-4113-b666-f780ef0bc6ba |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Commissioning
145e122e-5c03-437e-bffc-235c50081bea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing
1edf0287-edfe-4909-bc42-e372169838da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB1
37136433-acfc-40cb-93df-00359aaae44c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB2
8f3622f9-4d31-428e-ba75-5a7db28d4cc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB3
82f8e8a2-38b4-456d-857f-fe2f5bba9e3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB4
f330ecbf-44e6-43d8-8110-2bc2853ce248 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB5
2e1c984e-a616-4238-83de-31f766237c3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1801 | Mandatory testing | CB6
f3cb0f0b-e41f-45b0-bb0b-d7c0a7bd4d08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802
fbbe1192-6def-4afe-a159-634ca592cec0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Leadins
ac1efc37-9ee0-41c6-b835-70dfd72e471a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Roughin
ee4b7b14-c168-4035-805c-1247c45cc754 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Cut out
cc016321-ad46-4256-8ea4-90547080fc69 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Fit off
d024f5ef-3519-4128-b96a-e631abdd1c5b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Commissioning
3cf3319e-ab87-4bf2-a677-5216e149dcc7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing
684f6d1d-26eb-451b-b6a1-5a51ca554665 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB1
e3101a50-a5ae-4fa6-98a6-beaa23d58d51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB2
de68aee5-5df9-42b6-8371-b8c4ec08559f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB3
17a64ea5-0a2a-4114-aea6-0eef65642354 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB4
ee5b7173-f05a-47d3-a12a-9af64cca5f61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB5
7223dc25-b1d9-486c-aa69-04b67ae66f12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1802 | Mandatory testing | CB6
248ff8c3-2546-46d4-abf2-f7e5af2b1515 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803
659c45b7-32b8-4f1a-b57c-164113e4db38 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Leadins
d232d484-8f13-4e95-8871-5bf63ff4bf7e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Roughin
8e43af52-8c78-4ca0-b2b1-bbd9414cc27d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Cut out
918ffdda-8b93-4184-8e04-556ee5d9b64e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Fit off
c1db5022-2be1-41af-b22e-5cb624bf1ac7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Commissioning
6218b287-6b78-47a4-b3d7-26614fd0c41b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing
f5c79a78-1b08-4af1-aab9-f2c09cb01758 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB1
ce6bc922-84b3-4641-8da5-dc434276669d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB2
cf084ea5-8d80-41c3-8b82-3dd2eecad0a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB3
f856e92c-90d4-439f-93bc-e78d6db6d7c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB4
a164424c-e3f8-4cbb-b090-516f13544dbd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB5
00957e9d-b866-47eb-be3c-2488fe910653 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1803 | Mandatory testing | CB6
c1f325ff-62b0-4fa8-97a0-cb79a2fa1a50 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804
e6c2de27-7bda-4821-a66e-d0c948ae75f1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Leadins
c6621c6a-eb00-42af-a37c-7279887dec4c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Roughin
3b49a70f-9111-4697-8f18-2f5bf0ea5c9b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Cut out
2c3dda81-b9a3-4545-8289-2883267d1f64 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Fit off
37d28ff0-c62f-4896-9842-c2af06cd8069 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Commissioning
95679ab8-ad26-4386-bca6-4349407e68d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing
df2a1c77-19b4-469a-b2c1-5f9542335084 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB1
a6a89190-19d6-4c96-a3cc-283e07236db4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB2
aaff2894-9e34-4538-8c75-8f63aff8baaf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB3
28e6de2b-fd79-4120-bb92-a8ae0fb149b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB4
700c724e-60b2-4957-9d07-4ee7fe082329 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB5
31d9e276-75e6-40c4-afae-d220a30e131c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1804 | Mandatory testing | CB6
a3b46194-566a-4557-a76c-45c4d6f7a763 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805
0bd90e54-3c6c-4c11-b7e8-6f441595205d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Leadins
d0be52d5-6d5b-48fe-a6f3-5395aa40f7aa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Roughin
d5379f3a-a54a-4d7a-a82a-448c31f3803f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Cut out
86a55fe6-78c5-44b4-8917-4cb159b49466 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Fit off
e7d77f61-a661-402c-a481-bc14c21d3540 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Commissioning
bf02a2a9-9508-4e17-9feb-03feccdd48a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing
d0a1fbb2-31aa-4101-864b-47be5cefd185 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB1
6626fe7b-fe9f-4549-b56d-38934a028c7a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB2
1824ca3a-29e3-43af-9525-26d73a4571ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB3
2e01830a-3816-438b-b66c-cf583973241e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB4
60130409-4121-4732-ace1-128619fad711 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB5
f629941b-1514-40b7-acbd-0bde2b044fc7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1805 | Mandatory testing | CB6
8b78e00c-f9aa-45b2-826e-4b59edb44add |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806
33e9b054-a275-49d1-b2ae-d8f90c2f3535 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Leadins
bf6ae36a-7efb-4ac4-8068-55490cbef33a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Roughin
b27e6403-6239-4e1b-95f2-39ebec48b5e8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Cut out
3156f98b-039a-4c15-bcee-7b7d33f804d1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Fit off
25c74fb4-70fd-461d-9523-1aaab1873afa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Commissioning
57083e35-7530-4f8d-b51c-e9fbc8f3f346 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing
d98a1061-7443-4ef8-a428-1cc1c1a2afef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB1
554cfb1b-238b-4f21-b4f9-61db2ae202d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB2
2b31d2e1-a2e7-4aab-a514-4bc2dbbae646 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB3
7c01d011-4ed0-4f97-b84c-d214578615b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB4
26dc81d0-73e5-4adc-9234-d67ef17e082f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB5
72b4af55-ad97-4ec6-aca0-66b42572b9e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1806 | Mandatory testing | CB6
8aa55c02-c8e2-4dd2-b432-c0e1107e381a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807
d8192901-e710-4111-981a-af1273ac3dfe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Leadins
1fb96c4b-e6a0-4460-bd5a-d8705bd1e5a8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Roughin
aff5ce1a-4daf-4af5-a9bf-bea8b11a4703 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Cut out
a73c7919-2713-442e-a469-2ed77f7b9bce |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Fit off
518e1a0c-db20-491b-b45b-554714327adf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Commissioning
b3879596-926a-47fa-9b21-06e9e3f65ff2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing
d18abe68-69c6-4f35-a394-c1cfedc747bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB1
390c368f-23c6-4a06-b330-af77385442fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB2
9de86d5b-3b65-4275-b19d-6690fc57e47a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB3
78d211aa-4feb-48ca-b28e-69e9a185e8c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB4
98771706-da5e-4dfd-b28e-93874832b361 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB5
c0694c1b-af6a-4139-9c0e-e896965c3da5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1807 | Mandatory testing | CB6
71ec4016-1516-4df0-8c41-c33eabaf9b15 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808
54f5458b-5b3d-4844-af63-8caa42ec9ee5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Leadins
66e34f1a-6991-4034-867a-b95341e20dc9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Roughin
3857abe7-6e94-40cf-8349-5705dae70e0f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Cut out
2dbb6eb0-d171-4d75-a351-c0561b34d59d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Fit off
97ff0cdf-995a-4857-80f3-ee1e9df76cfa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Commissioning
1b1d3c41-6873-4e75-a681-d7b1ffc220f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing
70a19ea1-4af4-4547-8210-2ca0f30a8e9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB1
6fc4280d-605a-49e5-b3c2-865e8507605b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB2
25850294-7888-4542-83c4-f37eeaf142cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB3
55bf6873-8337-4400-973b-1711b1ca3f77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB4
4eecaa52-579b-4d84-a161-ceae27947cf3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB5
ab8bb962-788b-485e-88fc-11d29e82fd31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1808 | Mandatory testing | CB6
d1ef541b-abcd-4eec-88a3-dfe751c9886f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809
d39e3727-c858-47dc-b533-5d4b2856176f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Leadins
175c5b47-b792-4220-b283-0af21606b1cd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Roughin
cda001b8-9a13-4fee-9a38-5aab1552967d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Cut out
ccc61c02-501d-475b-a0a6-ab6cd02e71f3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Fit off
16642580-e1bf-40fa-93c1-6b9b435e9431 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Commissioning
f6981b05-d260-4221-8353-7e8dee99dcb2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing
e2ab44e1-4894-44d5-9cf8-bb377359655c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB1
52f1c28a-988e-4324-802f-12533326907c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB2
0e8490da-669b-485e-a122-fe3cfed4b935 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB3
4fe69c9a-e67e-4bc8-a53f-3699e9c547e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB4
02a39611-7523-49d0-9ac1-1718646df9f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB5
944171ec-d3e2-4264-9024-f30c944af915 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1809 | Mandatory testing | CB6
45a2c98e-c236-454f-8947-60045061406b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810
3bd61a96-f630-4448-8250-f04092dcb130 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Leadins
d05f9926-82b0-4b2e-8e48-0943f2bd48a7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Roughin
849ba763-dd3f-4d9f-9d7b-ca80f3399a3a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Cut out
79772402-244c-44c7-b49c-f669f3716d50 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Fit off
7c27134d-d4b6-493e-ae7e-687f242b4bfa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Commissioning
89841706-2d86-48e5-845a-7e5863fc79aa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing
5307d9b6-b81c-4049-a9e5-b666fe849618 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing
e2e217c8-cd81-45db-9ebd-6b62edba84fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB1
79917705-ca06-4869-b1ad-e6d4899b4de2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB2
818d706a-7375-4116-a418-fe391e4a9dee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB3
b55ea6fd-c269-4c55-aac6-155e56ac7e1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB4
bd814ed5-230c-4e78-a6b6-f01ad1404ab4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB5
df0c60eb-8742-4423-99b0-134283800562 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1810 | Mandatory testing | CB6
335fe47b-186d-4303-8b9b-52008ae6f32d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811
adcfb103-941a-4c51-b297-de00376f69a1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Leadins
eaacb00c-7475-403f-a675-5fe9eda36a06 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Roughin
9f2c93e4-afd3-42d5-902c-a35ce3f3ce5a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Cut out
025af53c-0b9b-49d0-942c-bb3b20a244de |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Fit off
66acfff2-c30a-4546-804b-5f444a918145 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Commissioning
563eaf5c-d15f-4a04-b6ac-e2c83cd0fe95 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing
1d4345bb-afc3-43e0-a1a4-44f6b1719ec6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB1
f9c467df-f791-4d2c-b2ef-a263d9c657ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB2
191c84d8-d5f7-43e3-9bad-14e9e5bf9b0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB3
0c5cbb34-74aa-49b9-a127-b229b0f2d947 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB4
68c813a5-7539-4a95-85db-1951bec1c8dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB5
a8330cbb-2fce-4310-b353-384bad60adf4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1811 | Mandatory testing | CB6
8d5cffe6-8549-4928-91ee-f861cbcd0e86 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812
84d6fbab-2abc-43e5-93a7-9296890d3678 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Leadins
5cae58c1-932a-428b-b8fb-6afc21f69e7a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Roughin
425d27b5-74e7-4287-a061-32ae4a70e824 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Cut out
6041a81d-7146-46b9-9a66-f7606745bbdd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Fit off
cbf738ad-b217-4338-a849-86829403a0c3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Commissioning
07d5d890-9663-402a-84fc-01ee5fa05e14 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing
9bf86c9a-8d4e-4cf3-ad5f-6b4a0f67124a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB1
5063080b-b30d-4bed-90df-e994defd86ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB2
8aa0ec5b-c619-4813-945e-96ae012c22e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB3
5615120b-8b08-4404-8ccc-752e96c507e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB4
ea29e2be-0d93-4545-85e6-b3fd81a4a8fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB5
108bec6e-47e4-4570-b13d-89a5a4bd61de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1812 | Mandatory testing | CB6
d49f3a31-4b3f-4b4f-870a-9d4e031afcc2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813
d3a6dba6-5ccf-4ab1-aed7-073e027cfa67 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Leadins
c47d3f69-4eca-4251-ba53-c8dc29fa0984 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Roughin
0131b3b9-9221-4098-9677-08c66954bde5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Cut out
36822609-d68a-4591-8145-462f6fded48d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Fit off
2d1ae552-ba37-4a05-80f1-58f5fa3960f3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Commissioning
8a60f7fd-f42d-49e1-8326-b211119d4a62 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing
88783bb3-96f0-4fd4-a338-71e43fa801d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB1
856f1073-ad31-43ab-b64f-1ee03c9fabd6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB2
71769a3c-192b-4576-ba02-d950b27cb6ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB3
e8622e56-e7dc-4a51-b168-9c5c4b3a21e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB4
f8510f18-e0fb-4661-bf96-d335f07bbfc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB5
7e86e53a-3184-4112-a0ff-ec1042ac8166 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1813 | Mandatory testing | CB6
7c6dd43a-c043-413d-a701-f92473a40b85 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814
8544e603-eab1-4291-8307-ab2d428db063 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Leadins
fd79e461-7364-4196-95df-c8601be3205b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Roughin
1f813157-b6df-4a1e-a8eb-0640ac90e8cc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Cut out
8629e8d7-0ee9-49e2-89c3-95a629ab7fcd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Fit off
9647474f-b397-4a78-b61b-938c38e92453 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Commissioning
3d49a579-9546-40d7-b112-92f8b492339b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing
c56742ae-e236-4a08-bf19-acef5c6df287 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB1
faf65ac9-9519-4b6d-81d2-7d82b112ca95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB2
73c3a2a0-9fd3-4b72-80b6-007d48b27650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB3
1e91f400-adb0-4363-a8a5-8790a2ea9661 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB4
d4c62494-b1f6-4e26-b3f6-89f2868d88d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB5
b7052425-246c-42f8-aa4a-92a1a97b5e8f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1814 | Mandatory testing | CB6
f1a2da20-ebe7-4d94-a71c-9f4427ea73eb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815
0ef0c2cc-f95b-4d54-b063-15a45cf13cd6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Leadins
9fc7a58b-cfcf-415a-83a8-39e67f9fc070 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Roughin
6b25fd9f-512f-4f64-85b3-71c9a05c78b2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Cut out
4f078c45-65a5-4661-9ae9-9e615a4ebce4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Fit off
16dfaa47-c68f-417f-8ba6-f7380b78aff6 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Commissioning
f7e7c4bf-3dd2-4b01-b5d6-341a7c95c2e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing
2758cbfc-991a-429c-aa4a-1a1c8f88c3c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB1
24f0c6f7-782e-4e14-abbc-6121c52c6519 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB2
529fcb88-3f42-4877-b8f2-ccdbd12b021d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB3
ae6b2fdf-acca-4312-ba55-e75bc16da709 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB4
5d1f7fdd-c323-42b5-83c7-bcc91e5d4d70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB5
1436084e-cf75-4382-8717-097ae77b2870 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 17 | Apartment 1815 | Mandatory testing | CB6
69307f04-d192-40ec-b1bc-6901d6758895 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18
a12a759b-c593-4af8-8a25-75e9cef9a486 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901
20aa845e-0a2f-4975-94d1-00be57782e79 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Leadins
b7e36cb7-b609-489d-9234-39c061b8592d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Roughin
ff83c3e4-3ec7-41c4-8d11-cd4e9660c712 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Cut out
5fd00970-bfc7-4dac-aab5-ae40c64dffad |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Fit off
0131e33c-d11a-402e-a041-c40e38707099 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Commissioning
048e58d1-2063-4430-a878-c8bbd7f62e0d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing
5f3a5706-45de-4c09-81ab-20b2908551f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB1
0ce496a1-364b-4da7-b4fb-4ff693b4905e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB2
47882d61-3715-494e-9357-a2a96d8042f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB3
7044a4f2-2cd8-48ff-9ccb-8692a9615d09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB4
5e72da3d-4500-4637-86a0-19b4e158cdef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB5
7c586b38-1038-4d92-9cc6-e4b3e42e1dca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1901 | Mandatory testing | CB6
5820a9a4-e252-4560-8f4c-0f5a5f502c95 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902
0a378844-5f33-4735-8165-ea3a6e5700bc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Leadins
707b072e-78ac-4647-ad09-8c827a19a286 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Roughin
383f8fc4-b771-4ae1-a593-8c74a17eb0ca |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Cut out
21747901-98cc-4dda-8b53-8674cf66cdd0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Fit off
85f72dbf-4976-453a-b16e-1c0b8c9161dd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Commissioning
47bcba7d-9126-4ef0-af45-33161bb5fbae |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing
45faa0ba-3922-42de-9b76-8b91a4778cd8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB1
04e0e12e-b600-49a8-8db9-bb2f6cc7c6a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB2
6840a158-2d85-438e-bcb8-249542ecb716 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB3
d7383d57-a7ed-4d8d-9fda-244588e28187 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB4
c83fbebf-b201-4479-a562-73361ab2557a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB5
ed3fd158-a327-46cd-bae8-01ca2fb9f842 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1902 | Mandatory testing | CB6
e1ceabe2-654e-4200-8983-fd41f5a41fdb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903
a449e27f-f9e2-401d-a888-93b7cd04268a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Leadins
05bb7ddd-fcba-49de-a9e0-464e5f7fc21e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Roughin
c8764da8-4454-4e9e-9e8f-0f5dcdb48039 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Cut out
df769b8a-1fb7-4633-a1f9-edc02accda51 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Fit off
863a0b23-71ba-46af-b8b9-5b1b1023f3eb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Commissioning
fe93b35b-82e6-45bd-bac7-33f314715a2f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing
ecccbc8e-c799-4284-b3a6-177039886c60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB1
c589ce57-e0ca-43e1-bf51-2293c7d8c18c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB2
2d95c92a-99ef-4afc-bbea-7223fbeed31c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB3
b892f2ed-dd21-4220-ba54-82d11ee70200 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB4
6fe9f64d-bde6-4953-aeba-16a3e5bc41c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB5
2198ce8e-412c-4d22-a7fd-28b2cc642b30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1903 | Mandatory testing | CB6
72695abb-1cfe-4e60-8336-08b740bac584 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904
075b9ad6-e1ef-4431-838f-5e4fe195d126 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Leadins
785d97db-accc-455b-a1a1-f9f1a770ec0d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Roughin
770ee2ab-10e4-4f6f-ad7e-03a1ecc54f7a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Cut out
23882c59-dd7c-4e24-9653-8e0b568059c1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Fit off
9aa2f62b-ff12-48ad-b1a3-dbe07d16ae3b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Commissioning
bda7a0de-b65a-4093-a1a0-7449c1101c0e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing
3c75f921-150f-406e-81d7-25f99753ad62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB1
41062e3a-2763-439f-a655-3eed91760b19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB2
eb3a5b66-847a-4ebd-ab11-fb9f3d720320 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB3
88841668-37a1-4d73-ab02-2d9880cb8444 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB4
99f32948-fe09-4df1-bca9-0e41adddc623 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB5
3bc3b397-340e-4bbd-abbb-4f961d3ef190 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1904 | Mandatory testing | CB6
58686157-5671-462a-b9c8-68b78b245aab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905
7ca50423-427a-4dce-8705-10338cefacb0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Leadins
8e99e0de-6486-4f1b-8875-e7a334320eb6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Roughin
0e6f07c7-183e-4d55-b4f0-94ba0726f0b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Cut out
a21af116-f7dd-4acb-983b-61c8724df93e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Fit off
6691512a-aa30-4db7-be68-dcc26b16e802 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Commissioning
da2ab614-e18c-4ff9-9da9-6c020ef186fc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing
9eef3803-a172-4c01-9d8f-6e135c6018cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB1
5714d4fe-82cf-49e2-a6cf-75a881f7d76d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB2
ab8407c6-487a-4eed-ae38-3777c6782e09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB3
08aaf06a-13b3-4b55-a79f-41c6e23fab15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB4
5a32c7c3-3ee5-46b4-9c07-4b80e085ffd4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB5
22c92b4e-8d9c-401e-a1b8-151446d9cea3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1905 | Mandatory testing | CB6
3cae2b49-28b8-4646-95b4-d1f247e866bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906
6484d83b-4c20-49ca-9a14-7773796f7ed4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Leadins
470ba540-88f4-45f1-acb7-95b6aa38c54b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Roughin
ec3474bd-7bd0-4100-a6d7-17f7a083887a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Cut out
0f6a3042-006c-468a-892e-74abc6bf84e7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Fit off
30497f48-a14c-4877-b2df-6e410cc80f3a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Commissioning
1dd25e59-dd64-4063-981b-b9b0fc5fdbb7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing
c06e031a-44be-4a61-ba57-31348d96993b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB1
9ea8adac-be37-4aa0-b2a4-5d02d24da2ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB2
ce0c671f-d612-4b26-b9f8-305c2561d9f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB3
14cc3148-c5dc-49be-8834-4e6e94e904dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB4
4619c24c-c517-4a70-abcf-81c52c965a39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB5
7a7a5491-74d7-412a-a757-5dbc8018149a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1906 | Mandatory testing | CB6
410b4da3-74a3-41ed-b5db-f1197f72eadd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907
ae133c74-41b4-4673-a145-a757fa94ca1b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Leadins
45f06ce2-43c9-418f-8d77-daa934e37b84 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Roughin
f97f6374-c300-4d0a-83a3-4fd402316810 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Cut out
a60b4837-cc10-4a52-a0f7-90d31c0a7c8b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Fit off
61d5cd8e-a264-4275-9020-a0ebe088c5a0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Commissioning
d3602ac7-b727-4ebc-8099-3955260105e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing
9ee4181b-3cdd-4916-a1bd-9838c7cdebc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB1
f0eaa934-826e-4d29-89ec-f0e8a8aab8e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB2
b6d8dbc6-4b4e-411f-83b5-ac3dc69dafae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB3
f2872253-dd34-4d4b-a790-2225abef717e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB4
cfd2232b-f309-4a88-91ac-459630defa8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB5
b8497093-0fd9-45e7-8a09-a45b75b22578 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1907 | Mandatory testing | CB6
9357b3dc-0325-4ee7-a827-ad5f6a3dd9b1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908
3dc3e295-5757-42f9-9b7e-e04823454d6e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Leadins
e5e153db-5f8a-4e10-a073-ee419dcab043 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Roughin
c3f0be6e-4cb6-4068-bb4c-aeea435acdc8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Cut out
625bb8cb-b4f4-48d0-8377-1a8e4881a86e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Fit off
53956d45-75b7-47fa-b881-7148303080eb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Commissioning
c1331eb1-4590-4954-bbd0-adf86dccc276 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing
b173317d-c5ad-4f21-a7bf-e538309829b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB1
8f7a46dd-c576-42ac-8145-c3c19e0d5f0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB2
5e9cbba5-1052-4a27-9512-83c803762471 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB3
330bd710-3cdd-4223-acb7-08f29411289d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB4
ea4022d0-211f-4f35-a8af-0ec8ce5eae0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB5
fe9cd1c1-6d94-45c8-bea4-7de80c45aedf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1908 | Mandatory testing | CB6
c71bf69a-86e6-4e6d-8b87-4268a9592fbe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909
e5ca2ef4-6b81-4e77-afbb-3f5977eac26d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Leadins
b984aee9-3fb0-445d-a234-5560a72328b3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Roughin
8fd17b00-31d6-4a31-9067-b2e0546532b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Cut out
b4c74494-adc6-4a87-a332-4a8d97ecd776 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Fit off
8a63c114-0c0f-4985-a4ad-9e384ada8a9f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Commissioning
fd233f5a-33fa-4e92-a604-060e1646aa99 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing
92126a06-cf49-4dfa-90e6-ac56071e84d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB1
040e100f-19d9-48c9-afa7-16574f7d64fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB2
50b6e2cd-23b5-4798-9625-917fe85ef26c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB3
0cebce15-8dbe-43c9-a0bb-0bd341ad93d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB4
f07f5349-6a79-470c-815a-3b420199a3d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB5
d770aa91-9b23-4fee-8906-b9cd31e9ef15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1909 | Mandatory testing | CB6
47fd4992-785c-4705-9a13-4d760bfce769 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910
ab2d22eb-658d-4f5b-96c9-362ef2951fe7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Leadins
dd8d0cce-6e8c-4c05-87b6-751d2b3fa34c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Roughin
87addc82-0787-4358-a660-584afe392aee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Cut out
997f8d2e-f54b-485f-b754-67eecc051c30 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Fit off
a40ceced-5048-4290-ad6e-eb82873f535c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Commissioning
54d9ecf3-3634-4e19-83ca-955268b9dc80 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing
7df0bb07-11a5-4a4d-ad14-83f393f3b223 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing
585594bb-b720-406a-907a-b5fa369161eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB1
26bbf5f3-1729-4cbd-9c87-943910ee576d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB2
b5f68162-7b64-4775-8354-a15aa478a006 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB3
d17bce7e-82e7-4801-b5d4-e8e713a36bc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB4
26ee0ae7-d9e2-48c3-8911-1880111fca7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB5
a247d974-c4d1-4ffb-9cbf-915f90879ab0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1910 | Mandatory testing | CB6
3cd2e72d-0b35-4946-b0ce-f94226f2a24d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911
e8cb8f1a-ef8d-4ff0-9b95-999afb2eb15e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Leadins
46fd4e5b-778b-4e36-981e-1182d49a7eb6 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Roughin
6e834ad7-d901-40db-9351-0340d671782b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Cut out
33ce2537-2c18-4558-9d29-b4b8c81d4e78 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Fit off
e9105991-8b6f-4b8e-a4d0-a2778511b6dc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Commissioning
0ac35f83-0c45-4925-86ec-a09cce2fb933 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing
b2b88ee2-2fa6-4105-b710-767e574a3874 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB1
788dbc33-25d1-4fca-9c7b-bd9f295fde6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB2
67ceeb18-d329-43c2-b9d6-f600a856bf3f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB3
fa1233ef-1149-471f-9795-0334c55133b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB4
e70a580d-660a-4f7c-a084-345c8fd01dfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB5
d746f42f-e9d5-4d47-b627-e72764cc6fd2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1911 | Mandatory testing | CB6
0e3307cf-f973-4445-b173-65f34e31b6cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912
c55ea522-85cb-4e8b-a23e-11d7e657a2e7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Leadins
b7caaadf-a7a9-47d9-ab4e-9a5b53f3702c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Roughin
28d7715d-c20a-49c8-8ade-c4639e0572e4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Cut out
9b8bd10f-a4ee-4420-82df-6684e094185b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Fit off
1f97f939-2b83-44f9-86c2-35d9c8495e28 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Commissioning
103f861c-8025-42c5-960b-77a26b6e8f98 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing
2ff16e87-9b0e-4414-a7f6-c3d74d131e61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB1
a780f649-0110-49e0-9dcf-618e7a1d9639 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB2
73e9ebe9-fe0b-4b65-af86-72999d34add5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB3
75bb0e1a-eb62-448e-9a0b-70e1835d0d8f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB4
99d837cc-589d-47d9-8886-8df8a2e28d43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB5
c59ecc0e-d62f-4ac4-a03d-48ae46e4b625 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1912 | Mandatory testing | CB6
4a92d8d9-509b-447e-baf2-fed6c97952c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913
bbc6a0a0-85f2-4ab4-94a1-95ce455cfe9d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Leadins
72136766-a3a2-4ef7-89a5-cd88f49686ec |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Roughin
9cd190d7-50c2-434f-95db-d90759c44cec |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Cut out
4851ce48-0bdb-459a-b837-af9a599ee6c6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Fit off
409c66b4-16a7-4a8b-8272-37109be556f4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Commissioning
54c7030b-9ec7-4c13-aadc-55fc3c9a1438 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing
3b7ec126-ca77-49da-85c7-d313eb591e5f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB1
42b117eb-d299-4cd7-9741-ca8e452638d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB2
ce0127e4-1be8-4c13-a3dc-50976289b86f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB3
d0dce90b-8318-49d5-9cf2-f68ba486df57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB4
2ca81e12-e49d-41ff-bfbe-b7aab15fde13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB5
f8451080-b3df-4711-bf2b-0c4f02333865 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1913 | Mandatory testing | CB6
e453c01b-ae5d-4223-b7a0-b3c8bd31d5e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914
d481a140-edad-476f-9110-d9dce55549f5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Leadins
ee7ec448-8c10-42f1-9b71-aa76767529ff |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Roughin
39128739-ed15-4b74-9172-f8b366a81dba |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Cut out
d6ba1d75-764a-488b-8559-ecb268eb8a59 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Fit off
32a5f10b-2ee9-42ea-a346-f5c6c126e0fa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Commissioning
7297b34f-a406-4733-9934-8350e9efc3e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing
f1d8742c-f84e-4c24-bf6d-f4a7897571c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB1
6d8f5501-b16d-49aa-9d93-d8b670630a0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB2
48f03560-c2ca-47e7-8171-35549367b651 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB3
9a33153e-1a85-4fb6-8382-ed6e2ec15747 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB4
e2b24bce-dd47-493a-a3d2-bb62f1313560 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB5
71a25ae8-9564-4217-99a5-3b9ff127e28f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1914 | Mandatory testing | CB6
3c695c05-c336-4ef8-8370-851b0f553363 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915
12e2e891-c491-4ef8-b943-7b96200cf794 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Leadins
66e4d8fb-5483-41db-bf15-f88dfe4acc0f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Roughin
9d914266-9061-444b-9d3f-10acffa6f5a8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Cut out
1654ff6c-d263-4156-a0b4-1cb54354db81 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Fit off
9d12b54f-b453-4966-b85d-25e3c4edad7c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Commissioning
e985c3e8-18e7-4941-b365-f45b1b63263f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing
b04894eb-aa46-49a0-9e05-5b3e532e1519 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB1
6941e221-8466-4573-a22d-637cfab727dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB2
ce5f537c-a4e4-4077-a3c4-232d8c4f87d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB3
41a8b6c4-5c64-4e29-ade5-13ce7bda15cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB4
b649c32a-0554-4ee0-a686-f99accdd0e10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB5
49a18439-d5f3-42d2-ae82-bacd2ed8e9d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 18 | Apartment 1915 | Mandatory testing | CB6
2c944492-9594-4f80-9ee6-9021a1350295 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19
a30413bf-591b-40f3-a95e-dd6e8b47e0a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001
d9a11f6d-4481-41f9-a318-ef5c9a9ce459 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Leadins
0a9d01fb-0b27-42fa-b14a-855d6ca629bb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Roughin
06917458-9ad5-4c10-a8f9-3a47e7bd2555 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Cut out
a17632bd-70e8-4f71-85a5-6bf5287b0b43 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Fit off
4248e95e-0f09-4af1-b27e-171b798bd1ab |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Commissioning
905ec56f-afb4-4153-b4d3-edcdea193d40 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing
486c2610-eb7f-4f4b-8208-4523af3474a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB1
bb8011fb-174d-4c18-8d4a-e9c20a006fac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB2
f8446aad-4351-4c66-8cae-90cd3fc30e7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB3
818d9772-f98b-4eb6-9268-3715b08cae6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB4
7bfff67c-d21e-4673-af1a-3bbf2966815c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB5
27eee74a-8fbe-4f88-8f52-f07e033141de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2001 | Mandatory testing | CB6
ab92e176-16fa-4d3a-9c73-4ec3f7e48642 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002
51324155-f31a-4367-b136-7652c074fdb4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Leadins
2206bb06-63a2-4ff4-b00c-4fae112dcb25 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Roughin
c0afe24f-d506-4535-ba0d-d005cf280ccd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Cut out
86b8f992-7dbe-4a6b-9e13-4b3da8abbf14 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Fit off
de170969-ca7a-4518-ab59-20e29d36dd0b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Commissioning
758dbc25-cfcd-4c48-bb0d-cb7bdcbb5a42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing
4f273dd0-c809-4660-a0a7-9cba3b509ae8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB1
9e5364fe-4bfe-4cde-8d4b-5ed511f5f111 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB2
c9e1726e-32a7-407a-906e-6030923345c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB3
de5b90b8-c04f-49c0-b6c7-00fdb8801340 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB4
2b695909-d923-431a-a9d0-c6e3b140eb89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB5
42eafa84-a9a1-434c-be16-fb86f25d5485 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2002 | Mandatory testing | CB6
94b463d1-211c-4757-9391-6afe73cf9dff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003
9241010d-220d-4630-91c1-5b6f71004abe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Leadins
948eb007-0d15-46a9-b824-2cd520479b1f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Roughin
83ef740e-e247-45fa-9cef-c4501bea2d3b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Cut out
5e16b4d2-f321-4d6a-b157-7ad3e3feaa27 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Fit off
b93b7470-79c8-4d87-b7af-b254e6eec40d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Commissioning
6adb8e14-1b4b-4e2e-8069-3c56a7130a63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing
5651ec1c-9a08-4608-99b3-c22c2fac3dc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB1
c8c64ef1-1e82-48c9-9d1e-43f051b6e2e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB2
454e2b18-70d1-4141-9955-226071429130 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB3
3bcde0f5-a1c0-493f-b5c1-f6f48201bc49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB4
413129ff-8e24-4dd2-9187-d9c36fa42415 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB5
8f624722-fbe7-4e0c-b081-2cb5c6f640ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2003 | Mandatory testing | CB6
8f1ebc79-0367-4286-8839-45639d632cf8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004
5284f3be-403d-4a0b-ba7d-c3b912951bcc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Leadins
2237b265-b06d-4576-9f1a-8aff2be19a10 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Roughin
6869df18-6bf6-494b-b4fd-90c08b0b21ad |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Cut out
1d9bf8f3-8d19-45ff-a2e4-c9f77ad288bc |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Fit off
f11fabc8-7cc1-40e2-a3a9-b7e58ea2ade3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Commissioning
f70a89ab-01e0-45af-8573-0466ed4f989a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing
e90039d2-da00-44f6-9e92-ed7065ceb6bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB1
6fbe1a59-e8b3-4bd8-b0ff-3cd99b2f5b95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB2
e767383b-4517-4740-b9f9-43d66566c09b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB3
fe41e3f3-7765-4882-a2a6-0bde92cb2a29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB4
33647d34-35e7-487b-8997-d48bd30d5afa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB5
c88bf383-47aa-457f-a255-840ad34a545c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2004 | Mandatory testing | CB6
f3d436a5-aec7-4cbf-85f9-65535082e2b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005
78a9d8de-10c5-4d3b-8dd8-c400f2bf8e8b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Leadins
322dc279-8032-4a1b-a1f8-b2c3ff554b54 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Roughin
de9a65a3-a2b1-42d3-b865-b967569cbe47 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Cut out
9c969183-cc55-4875-8d12-f69c99fb1e30 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Fit off
0673126e-180c-43d3-a7e7-85c60d017791 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Commissioning
79fdc628-945a-4e5f-a1d4-69afde69a45d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing
9d772105-895c-4dd3-82dc-f8e444e8b62b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB1
7ece2f63-b468-466e-b481-d0c1cc4cfe40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB2
7e58ef68-dd47-4cda-9f90-f0a074ab6269 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB3
23a19587-e589-44e6-a5bc-16b63c569599 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB4
4b9f8e10-b2ee-40ca-a27c-57a293d1cbb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB5
9d30d0df-74cc-48c3-9341-02dca7d22d9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2005 | Mandatory testing | CB6
446f621f-a852-4681-9a7c-24f1abd34ae2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006
5b870595-fd23-4971-83f5-4e1923672525 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Leadins
62e3f24e-e6dc-4f7b-b3a5-3febd36a6345 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Roughin
c5d71c5c-ad88-4479-901f-cf9a91061f57 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Cut out
48cdbbf8-327d-43f2-a68c-1e113d59a130 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Fit off
191beaf0-4bf2-41fd-9c8d-4191822b976c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Commissioning
2a98cfca-18ce-4784-aee7-02f0e0b8a5e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing
3f56018d-c455-47dd-82be-a0c4e6928f81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB1
64711cac-d7a4-44d3-9673-fd3dac5bfab3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB2
7cfd6883-d841-4309-991a-dddbdf3f8287 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB3
02117984-f566-42c0-b602-097f45d13b13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB4
cc07e869-193a-4397-924e-888f1d56dda7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB5
37efae03-4778-4e31-83a9-b37e258fc767 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2006 | Mandatory testing | CB6
20a87463-04b5-4584-8524-ec94a1949668 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007
fc4669a2-234f-4f23-9ee1-3349404b399f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Leadins
23a88d70-af7d-4aa9-8f82-6dcd033c1fa3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Roughin
4e3a3f25-0c79-4286-bed8-7d8bbec73e62 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Cut out
30be4217-38d6-4a9e-b437-437e2a363d97 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Fit off
5fbb7dc3-ac7e-45a2-b3ff-f5676988f764 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Commissioning
9af84a3d-6915-4204-a98e-44123a5da79b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing
3d314981-7def-41eb-8c6c-ad4df25f5ba8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB1
ab3dc702-3d79-4de6-b990-d0909748d912 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB2
68ba6655-201d-4bf9-a7ea-91152b4f943b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB3
ff0ea832-b404-4865-aa04-d0b14684d084 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB4
29570960-501e-4968-bc22-fa1bea732b98 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB5
def3e58a-af71-4fa9-8c72-e026d5969721 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2007 | Mandatory testing | CB6
747a6a6d-697e-489d-9e6b-ad337337287c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008
aad34cf5-7dcd-40d0-8327-850041358734 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Leadins
e626e2cf-3ac3-4e32-96d9-5bf90986d693 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Roughin
79128b39-2a10-4c73-8573-1e1b780ad4e8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Cut out
36c145b0-b4fd-407b-9212-eca3c63756ed |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Fit off
af912740-f774-4d87-a38a-d2232a961865 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Commissioning
a52c7d11-6c8a-45ab-a673-310f9ffb2a6a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing
718555c4-a66f-4b9e-91d7-7d13abce9a91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB1
aa1848a0-242f-401a-a61b-f299fff3ceef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB2
77034f6a-3daa-4512-96ec-721081aee776 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB3
cb8365dc-17bc-457f-a44e-ac381b2591aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB4
26b9b065-3df4-485f-8be9-9b9ec295e39d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB5
88586b33-e53f-4fe5-ba05-d6511ef287d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2008 | Mandatory testing | CB6
5eaae8e3-8527-48db-808a-9940a93c830a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009
02f2a792-e2d4-45cc-884a-b2ca25e4e232 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Leadins
d1abe35b-b9e7-4eab-b2a5-e5b49e57f9b7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Roughin
7defb863-23c1-4fda-b2c7-c6e5428f42fb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Cut out
7f92c21d-1359-4575-9230-dd01caff76b3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Fit off
c9613ea6-b815-48e3-a5ab-95a5ff539458 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Commissioning
1b7763a6-202a-47c6-94a9-80d87a6df856 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing
423ad1fd-6f02-43bb-a2b0-db3bcd868ea0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB1
bffa8ddf-8a8a-4ff6-bb8d-95039ab1e73e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB2
0ce25519-2a50-4c29-943c-cb3dc5f4ce9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB3
a7369598-7012-450d-8e39-47c6de3c46a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB4
b48d325f-a248-4955-8786-be09b7f73ce4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB5
3a7000ac-d6c1-4a9e-ac4b-e996953e7510 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2009 | Mandatory testing | CB6
0e1bd5e3-222a-4565-a3ba-9c08444d1aa5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010
eedccfb9-35c7-4c0a-866d-a0e42cc0956d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Leadins
56d81cdc-a781-474c-bff1-b6f42cf535cc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Roughin
41038fef-e090-4a04-bad2-2a833a0980aa |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Cut out
be6a962a-712a-4e30-a572-cf953d0c13e2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Fit off
15906dc0-ca40-4380-bdde-c0613d34c048 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Commissioning
b7ca8e54-1210-4fac-9541-9180f5d7495d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing
9a4ea76f-1a43-43e0-ad49-4ba16a2eba37 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing
4bb96c6d-5bf2-480a-92a7-ccf83495991e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB1
b4add551-ec00-4e27-8d0a-26f1362f8e1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB2
b157c2a1-913e-4d5e-947c-50713c15b3ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB3
3c4fe439-e0ff-412f-9c9e-3e54b58a8f15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB4
5445670b-6c80-4293-8bfa-68394f1d6f9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB5
f56ff9fd-7846-46d8-a4c3-ce9379478b1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2010 | Mandatory testing | CB6
566170bc-ca3d-43ed-b090-ac192486b9d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011
e2cedde9-454b-4d6b-864e-5e14a49001fa |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Leadins
129777a5-e61a-4f5b-8e12-29d9361afba9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Roughin
60c2c98a-9166-4301-b042-6e59f1a56795 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Cut out
9698eb0b-8286-4a82-8f75-cc8634fd1e40 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Fit off
25a1b48f-b21a-4c9a-84a6-595963ad7cb1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Commissioning
d4d5ef37-9bab-49ce-870f-127d76a7f82e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing
3be0d25e-794d-4038-ab53-cdb3c5c91933 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB1
930d519a-93b5-44a2-a148-f5f67c72fd52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB2
09684d76-ca60-4503-847e-dd4c632fd0b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB3
3935dc6b-9f38-4ac7-ba69-132c1e908dfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB4
e714d331-75cb-4d3e-a141-0341f3bbdd65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB5
c86f8ada-2d31-4476-860d-19f58715f3e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2011 | Mandatory testing | CB6
9a1a4efd-3bc4-46f9-a683-c6a426e662f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012
20a11ac1-0c35-4424-9536-ea1d05dddd14 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Leadins
9b85044d-efd9-4db9-ad0a-68feefcfa8d9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Roughin
5f1b027f-c333-490d-b586-0ca254901232 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Cut out
45e809e1-ac97-480b-a6ac-dad9a1f2787d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Fit off
d0cef135-1c6a-40bb-aa1b-a6979606532a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Commissioning
0d8c9efa-eda4-4aeb-93e2-093d246e2776 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing
4d1da20c-33d5-442f-9973-f0fdcc6e6f8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB1
80b2bb47-0b95-4ffd-b03f-b8e1538c06be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB2
38537cd3-d352-484d-be8e-6f63a9706562 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB3
eed7349b-fc0f-494f-b05d-b296dee7dbad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB4
503f8e04-06f9-40de-99d8-09178cf60009 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB5
d4f9327a-7546-4ce4-8da9-56ad676a81e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2012 | Mandatory testing | CB6
c1eaa84b-b222-4a86-b11b-e8e8912e2e6d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013
a6e94ce3-4d40-4cb4-b3c5-bd3049d67c27 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Leadins
a3a02395-25b2-48a4-8e2f-067ad221ee0e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Roughin
1a057abe-c3e3-4c97-a436-6ee5b2800423 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Cut out
07e564d3-c548-4ba8-b5e6-8bdb29dd0033 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Fit off
df1274b6-ec6d-4d87-b487-7ca9d002023e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Commissioning
356a8421-9dd1-44e9-9b58-9ff2ef32b5c1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing
61831daa-3230-40b4-bf94-7f2d0f1a8c3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB1
21b649e3-c6ad-4b79-aaef-59d1296ef458 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB2
c8015d6a-9ba0-4483-b31c-855831bf790a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB3
2d87a54a-b065-4758-b297-8b2ac5fc8b06 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB4
a540ba9b-eae8-4e0f-b5a8-791c3a526865 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB5
721d2f78-806a-443e-ab6c-ffba5a25dc98 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2013 | Mandatory testing | CB6
95a08524-3d1b-4ea1-80d7-9b78fc5c68aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014
36a0b74c-f8ac-4952-a87e-25f53068ef12 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Leadins
77e7ab8c-b126-4d68-9033-81a24f9b5e53 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Roughin
b82395cf-fbe5-4f70-a6fe-6cac8cd8b555 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Cut out
0c67db91-01a6-4a1a-abaa-86e1581c085b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Fit off
606d4611-88df-485f-b839-57f3c27d4034 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Commissioning
41681fdc-05f0-4b9e-a4eb-1ce6a6a5a824 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing
8ae31aef-4fed-44e5-8384-53e536488564 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB1
46f62cb5-fdd7-4c18-a291-59f75bb20168 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB2
3ca00d02-2a8a-427a-8932-fa9f9ceb6f4b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB3
a18fa1d1-8652-4f1f-84fb-2551458c62bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB4
0c29aaa6-b347-468f-844b-a2a33d60658c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB5
fa4c0bbc-2300-473b-b6f8-81a1f9e1b5a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2014 | Mandatory testing | CB6
b4aa667f-7b89-49ff-9776-3e6ac058f736 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015
9f9f0ed8-bfc4-47b6-af4f-fd7c94aeb663 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Leadins
3b70747b-2cdc-45a6-b3aa-1a05b14eec12 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Roughin
15f478e0-6fd6-44f5-afed-877e3e633586 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Cut out
bc0ce03f-7156-4e74-9897-d279520799bb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Fit off
9f7aefd7-eae7-4d76-bfff-85a9a83ff442 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Commissioning
a3c5928f-8a00-408e-965d-0b1f0ba5df01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing
fe164b05-7e5d-4005-836a-741d8f932d82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB1
c0e61a3c-db31-40b1-b4bd-5bee835b5f63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB2
d4266a97-7961-4a9d-8840-b4dd98ee5948 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB3
22cacfe7-aa02-443d-a09f-705f09db1cda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB4
b1ee2be2-5449-40d3-8653-cd5bb23e98cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB5
572c8fd1-8005-49d6-971f-cb5dbacda05a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 19 | Apartment 2015 | Mandatory testing | CB6
3e7a2902-9394-4326-a345-94fcd69811dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20
20fde8a8-d51c-4d96-951d-e3a035f22be6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101
1d69f0fd-cf85-45e0-bb2d-aed44bc9a62b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Leadins
fb1d6872-9501-4eaa-ade6-88b7a360e40d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Roughin
344c60b0-630f-4468-b15f-18b77e04538e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Cut out
c00d2097-721c-4ecc-936b-a5703649924f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Fit off
6d303757-bb6d-4dae-a91d-f8424fe2832a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Commissioning
99400c4e-26bf-47bf-b6bf-5cad91f7e1df |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing
cb22bcda-9c38-4d95-8a07-eb8bfd8da768 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB1
b83d8a53-ba46-4838-9749-b14ed423044f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB2
497cb59f-02e9-44f4-b153-d50d2d87f619 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB3
25310383-99c4-4540-a22e-928bb4485138 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB4
a4e79cd9-591c-461f-9285-0fba23d0da46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB5
b7800022-3f3d-423c-a2bd-ee925f141784 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2101 | Mandatory testing | CB6
3ada6e69-1328-412c-a2d3-c235633853ff |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102
5ccb068a-97b0-4c25-b100-6a2028caf9c5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Leadins
f8354e53-b028-4343-a8af-869927c9868f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Roughin
2d0693fc-bceb-4cce-b8bb-09f2b57a26ee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Cut out
b0498f1f-32aa-4827-aa42-46eaa9e6acd3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Fit off
91ed845b-e42f-4a49-9cd4-61f433471721 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Commissioning
9ddddd71-f2d5-4709-b497-481227285430 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing
0a7f52c0-bfdf-4915-8385-aac8624b13a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB1
13f6d612-50d4-4893-bc23-24aaa2162c0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB2
7589fa86-c990-4b93-a10b-7ba680247074 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB3
089e9792-9071-4434-b092-b765c64d600e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB4
4e892394-9791-4a9d-934f-e2158c56ac1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB5
131ecef3-1f13-4db7-b029-40bf18fe350f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2102 | Mandatory testing | CB6
8d74aa06-eef6-4b11-8392-10f240f0f3d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103
c5f42ae9-0c64-448e-a75b-a999c5474f73 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Leadins
72ba077b-0a16-4947-8715-e7f062bef43c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Roughin
07b1227c-7352-49d3-8290-3306edb9681b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Cut out
550b9d18-ed79-47a2-b964-0148fc56aa79 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Fit off
48e4055a-2c32-4af0-863c-66051aa70641 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Commissioning
aa6040c0-08f8-4f7a-9d24-793bb04416b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing
774ec0cb-6bd6-4f75-a669-d0ffacd1b4de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB1
74ad4cf9-7308-42cc-8980-06e274ecef6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB2
70529525-5a1f-4b7a-a9da-b9672d6d4b36 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB3
bc9b53c6-5a91-4cfb-8a46-db4d6dd5d8ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB4
5767e2c6-6569-4617-8173-5be901eb2af6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB5
cebaee22-df82-4933-8046-2cee245e179e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2103 | Mandatory testing | CB6
28330d22-d044-42c5-b47a-87d1219e5232 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104
99b6bde1-325d-437f-80fd-ace224031caa |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Leadins
4e2f2216-6b5c-4f47-a24e-e2becb2e72d2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Roughin
053525e9-562c-415a-bb68-cb5e2bc76106 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Cut out
bfba639a-06ac-4be7-8eaf-3ee2c2fdb7bd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Fit off
6b1c5a0d-179c-4003-a0a0-39c1f048a127 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Commissioning
110e7901-1086-417e-8824-befebaa4d826 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing
2963f668-883e-4091-b08a-ed7544d22156 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB1
9e188da6-55af-4d60-a268-38da569e8f56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB2
6f69cada-e9f3-4351-931d-475e0495ff70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB3
e7458f46-1f05-47ea-a986-c003b3f0956a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB4
1570f76b-fddd-4945-a523-f279583e5aff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB5
9380e027-a84a-4d52-8639-3a7f214d70e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2104 | Mandatory testing | CB6
0658a623-eca9-480f-a92c-71919c6d92f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105
97e57e6a-d85a-42e5-aa04-e8ac1b7738de |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Leadins
3f482543-9de8-4062-a081-67d25ab013dd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Roughin
1cae0f4a-2e1a-4104-b12e-7bd0542dd89c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Cut out
a96dbd3d-f9fb-4256-9394-1d90234cba06 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Fit off
d583bdd2-8b93-4196-be1c-ea8c26615038 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Commissioning
2573ff28-1df2-4b04-9501-c21a16295f6a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing
6f6997d2-e59d-423e-94fe-a1747b59c874 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB1
8e38d99f-e12b-4a66-a6a6-343136abcdbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB2
a23d0427-27cd-449c-8bba-962cd8b14539 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB3
eb9873c8-5388-48fb-bcc9-d81a82b10eeb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB4
33bfa25e-192a-4dee-a3e3-024f7f26a808 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB5
5cbd06b3-ea95-4189-a3aa-6cc42b443b2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2105 | Mandatory testing | CB6
1dea4133-37c8-4426-8b57-3c27858f13fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106
9f0b4dc7-c020-47b4-b79b-008f7c0e5464 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Leadins
81ddf0db-48b3-498b-97eb-c3408e0cf065 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Roughin
b86dc18e-90b7-4f44-93d9-9f559d7784ae |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Cut out
bd885e7f-f711-479a-8f3e-706b67c0926a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Fit off
45c72669-43d2-44c6-b2a5-de4acee310bc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Commissioning
c13cc693-dc94-4cb6-97c0-faf24b3bfb9d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing
b873cbd0-befc-429e-b194-bfc6a6082e80 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB1
f9cc07f6-6394-4480-b9a7-4f723a9ded46 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB2
bf9360c9-b543-4f57-879f-fb294d4066ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB3
8f632d6e-89a1-42d2-b97c-bbc12f05ad01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB4
bee6b856-62d7-41c9-9117-c6e013ebe791 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB5
5bc8854c-b465-446d-9433-dc6a36ca0ca2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2106 | Mandatory testing | CB6
348edff5-c2ac-415b-9d75-ec0456cbcd22 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107
1ba00742-6ddd-4289-b257-d8ae3be1a7b0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Leadins
eb71e0b3-9bc0-4b97-8b11-4a412f72b0d2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Roughin
c0fb0398-8dd3-4a4b-9d6e-4315e8c96eb9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Cut out
7744e5f7-4952-47d5-aa9e-c787259ce673 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Fit off
105c8058-7eb2-4c93-b865-786e8c8cc24f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Commissioning
c7f888f8-cabd-45a3-9f91-a62fc9dcc95d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing
6ef1ef58-d186-4d2a-aec1-fcc483448806 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB1
c3fef212-c155-4b69-bb5f-cd47d9cb0f0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB2
dfb08f10-64af-476d-a588-f585566a8a91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB3
391dd672-120d-4092-a02c-ac7eb5fb72b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB4
e64e0c16-4204-4d35-a716-d663f991ce2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB5
ae2afad6-9d6a-48d0-8393-872523fcd057 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2107 | Mandatory testing | CB6
0527d890-9382-4dbb-bfab-f0b975d09c02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108
bd73b5e2-2eeb-4f34-af52-c14c3ea55fa3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Leadins
edeb64bb-7bf8-4caf-a0c8-2ee8c9c1260c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Roughin
b398881e-c80e-4c63-91d9-d6d0f163b23e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Cut out
2585321f-24b9-4ff4-a9aa-bd8985ae934b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Fit off
c9d4d601-0f58-426d-b0a1-740837319257 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Commissioning
79d60b6a-fafd-4cd7-801b-e7e581510cdc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing
c443a15e-fa83-4878-9a5e-87be30f35260 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB1
85083ab7-e81a-4846-a67d-1272f4dc5a28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB2
dab6f334-678f-4bc1-a4cc-6d833ba8eae7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB3
fec607b6-4f96-4047-b62f-8628e66b95a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB4
88b44422-57cc-4c9c-b6f3-d52dcc0d66d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB5
704a53cb-c84e-4194-9fbd-a91ee2e7d3f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2108 | Mandatory testing | CB6
b9e5c237-0cb4-429d-96fa-ce1cbeb21c19 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109
01ea46ad-8b79-41e4-95e4-6f1a74ab13c0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Leadins
a3107c21-8143-4102-8102-63550e0702ea |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Roughin
85197bb1-bf52-4602-baf9-9c88801a4461 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Cut out
6756efe1-d232-4270-879d-104ad682af27 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Fit off
df8f29cd-b7f9-4e32-bedf-7ea4d5e77f78 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Commissioning
9c3695ec-d53c-4bdd-8b9e-c995cc826913 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing
d5770774-3d6b-4338-a293-1493107dc38e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB1
d9f62d1d-c2c7-4fc7-990a-488beaf3ab13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB2
1058f73f-908b-4663-9742-f5e1d75fa452 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB3
620cd449-228a-45af-a270-945607e8de60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB4
a30ff9bf-a778-44f4-9119-fb1bb43cdfeb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB5
07bd7af6-fa1d-40c7-9dc2-4fcd3d4bd3b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2109 | Mandatory testing | CB6
8a35672b-bf9c-449d-8a79-d39a5f0efea5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110
0f3b74e7-3265-4bc8-8bbe-d39324658403 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Leadins
2b7864ff-2b66-4312-a877-499d0e5b7be4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Roughin
d0d0e30d-a3e1-47bf-99af-01c93eb3fa59 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Cut out
fcf8ee00-df47-48db-99e7-c6d8c2fb05d2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Fit off
0a537a2a-5c02-4b69-8820-7651442d14a4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Commissioning
3b837a98-4e62-41b6-82c3-c31a4050fd07 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing
6543dacf-11d8-4957-8731-165712d4ae47 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing
9fee266f-a0c2-4c48-a6d3-474b2da3763c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB1
ddc99d5f-2f23-41d4-9cdd-a3b4fbd31d59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB2
02a132f5-d620-4495-a970-46ddd1e61a99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB3
48021e06-8be9-4050-a65d-54505c225bb1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB4
5e27ef48-b918-40e9-be7f-c599081cbaf4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB5
2c7ade96-178d-41cb-b223-fd0b7959b3cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2110 | Mandatory testing | CB6
cb33c444-dbc8-4a1a-9a7c-e4b06b6a7848 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111
af4d3c26-a265-4b95-aae7-132e0a6b803e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Leadins
5bcf11f2-5e8b-4274-8c15-8416f7da67b4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Roughin
3241e67c-0c75-4ea7-af0d-49a6e63a6548 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Cut out
7edffac6-88d1-4163-a0f8-de968a73d351 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Fit off
a88baf53-aad5-4eee-81b2-8905be6d41bb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Commissioning
e7f8dc5b-5f35-4e60-96e6-6cc8521ae51a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing
a5cf3965-b696-4a2b-bd61-31e6be4fbd17 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB1
c862b6aa-96f8-4db6-9984-f1ff5460f082 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB2
be15e266-c053-4fa0-b786-92c7b8670f97 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB3
5e948e1b-e069-4328-8bf8-46457579950e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB4
7e509df3-565a-4e4f-bbca-e28173585fe0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB5
81ce4c9e-1b23-482c-9ed4-24efc01f6c49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2111 | Mandatory testing | CB6
e56c32e0-bc25-4288-b886-69af5dc273e8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112
d650f12a-073c-4859-a21c-b777a8d5d1f7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Leadins
32394516-d5cb-474b-a44b-437a32b66739 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Roughin
b92b4c33-fbe1-40f4-a276-6cdc9012297f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Cut out
dbf06386-d1b1-4621-801a-c9cb39937387 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Fit off
33768d7e-e6e3-43b9-8891-cd6bad5a273a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Commissioning
655f8715-c4e3-4160-a35b-cd1505fe6e1c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing
06fe120f-11c1-487f-ac6e-68a6667d60f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB1
bbc275ad-fb36-46fd-8455-fadff84dd0f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB2
dcdc3e01-b366-4a06-b384-f49a69938f29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB3
dd56faeb-0055-4dd5-b3e2-e460936b034d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB4
3d3307be-3adb-46d6-ac79-dfde1f15c52f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB5
3e62fa17-f235-48a5-aa75-ea3f1b41551e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2112 | Mandatory testing | CB6
f3ca984d-2cb7-4be7-9716-ddf600c52d29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113
e874c526-ce9b-4692-bd39-51a8f0cbe02d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Leadins
e8719ee9-b916-4729-a807-ef6b19bc0258 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Roughin
ed35636e-fec5-4a15-8f74-e839198e4879 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Cut out
29b3fa0f-ef47-4305-8e78-9c9c79885a0e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Fit off
1bf68e1f-d399-4b7e-81ac-b9fd761a8201 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Commissioning
b49757d4-68bf-45ad-9c0f-9828b27868a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing
9e290854-4858-4a11-a8b9-9c8e470d76b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB1
1cc3862c-9db2-4f0f-a386-d1cffc61b3bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB2
d02a2e94-d2f5-40b1-a7ab-cdd8d449f8ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB3
0e29c8bf-4b2e-4380-a1dd-bda4e35b849f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB4
fa2fe0a3-26c6-4891-9b36-d42ce20c4370 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB5
e7c4c7fd-cf63-4194-9908-dda53b018bea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2113 | Mandatory testing | CB6
a1c83497-0f45-4239-95ae-ab3a8f8c901e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114
d531353e-8d74-4949-a5fb-0602e60714d8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Leadins
46c58cc9-f54a-4cfb-8516-d696c08ee2b3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Roughin
d55ef60a-63c3-4840-a326-823235bfa1d9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Cut out
61208d68-c255-4c17-853e-68bc47a3eefd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Fit off
926b9571-add6-4981-8295-5b762f6fbb57 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Commissioning
540b9fed-b945-42b9-a525-ccd5a8d0f655 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing
b112e9e9-099c-45a6-b4fd-5ce19a07bb12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB1
28ffd701-2704-426f-815d-fd10fbc50969 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB2
08bdce1f-a6d1-4eab-b7b7-4e171259d78e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB3
0a54eb14-f862-4b78-858a-0aea71f21086 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB4
d388cdfd-8dab-4455-b90b-73d22907cbda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB5
90f7f57a-1887-41cf-a4f4-c930f37374d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2114 | Mandatory testing | CB6
a8b83e6c-128f-45fb-8c6a-b83619ba951f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115
8ddc6696-cc8b-4341-9d9f-caa905acd456 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Leadins
6a63184f-8fd2-4ebe-9b00-c7d6bc95708e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Roughin
be47ebf6-543e-44de-aaca-1adb06957b89 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Cut out
f7cbc7be-f4c3-460c-892a-2c1f158ce33c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Fit off
0acb1ef5-75cf-4498-aed6-ec118bd4d5e7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Commissioning
249396bc-3e5a-4fa0-97dc-26ca743d1096 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing
6250a32b-038a-4cdb-b4ba-869a5637f590 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB1
c013a7a8-856a-47a0-80bf-448bcf569495 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB2
ba276354-1089-4e85-88a6-9adda2e448a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB3
0d49c3d2-1228-4678-a0b9-2a347e85bebd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB4
d0bab9fc-21ac-4501-a91d-815598ab4741 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB5
b0d01c59-ea36-4502-a2b7-cd52833b17dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 20 | Apartment 2115 | Mandatory testing | CB6
938697cc-48c7-43a0-95e5-f11103f2b7be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21
0a131fec-15df-4219-a571-be6dc3bbcfb8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116
8120ff8e-d42c-445f-bb19-d45ceaf65c63 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Leadins
03c4f26b-a584-49db-bf8e-cbdfb83bf7ce |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Roughin
033e30c9-096e-4713-961e-bebf68fdb07b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Cut out
40ea0666-2f16-41f1-826e-ce05f4193249 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Fit off
c1974efe-a0d7-4ce6-85c9-fa0b7d8eebcb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Commissioning
26860918-df08-4ab9-a99f-28f1163a5db8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing
bc1b77f4-ba1a-4c67-882c-559d9d9e552b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB1
9965ed9c-dc88-4de3-98be-1dbe67e0b5e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB2
222ad865-c558-4047-a8aa-e5f2ed99c3df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB3
67f01c51-38c7-42c2-9ad4-967795266b10 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB4
f8de66e8-d1d5-401c-a676-50e739f31322 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB5
a51c2e8a-6ddd-405f-a6f7-35b9f071a3a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2116 | Mandatory testing | CB6
1e25ed4e-4bdf-48e6-bda2-2d6052c806e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117
964614a2-9265-4b39-841a-e30ba1a84f91 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Leadins
dcf258cd-43cb-404f-a185-9f7c5ba5db19 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Roughin
722f3ab3-d1bb-479d-acff-854003b3a5ff |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Cut out
73d13614-cda2-40f0-93ef-07f72fd078c9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Fit off
aa0269c4-7b2c-488f-a2ca-e37d344d3267 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Commissioning
5ef99ec1-fd25-4d54-b009-bd697a5d8d45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing
bd12b52e-5842-4047-bfba-129e3484198d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB1
85900a81-eb06-4ec7-97f1-cd63db72e123 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB2
6758906a-6367-4cad-8981-e12b3ec5016e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB3
8ff47cfd-821f-4e87-834d-ea975f7fb7d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB4
0b36ad95-7171-48ac-8547-1264b8d5baef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB5
438ec66c-54b4-4fb3-9d02-71681c5f78f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2117 | Mandatory testing | CB6
a82e8ca4-90bf-4e98-86cb-ca43dd86d2e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118
7199228f-6c13-4bf4-a21b-630674f6f479 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Leadins
f67a6af4-8373-44c7-8689-f3ff6239dbac |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Roughin
498771be-cc99-414f-abf6-e0d899dd359c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Cut out
3289df8d-5449-42c0-bfdd-de7997576b52 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Fit off
7e4cb626-14ff-4d88-ba22-f7d0d9aded72 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Commissioning
44043e21-9aeb-4f29-9317-db9cf6a802da |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing
7f668e07-596f-415b-b83d-71a1a64c9845 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB1
6eb41d29-61fd-464e-b74d-3acb0672e876 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB2
0bdf805b-aa1c-4eaa-81ce-dca8763a136f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB3
05a85024-cba8-411c-b8b6-debe2d43213c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB4
e17ede01-3c34-4cac-b9d9-f5fd0eec9821 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB5
9491c0fd-2fb7-4cbc-87e3-2511a8698fc4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2118 | Mandatory testing | CB6
1fecb5e7-4ea0-43e1-b9cb-da2c13d4c84d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119
3f8db496-5aa7-4b93-a258-386275539a4a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Leadins
32917131-3b78-4418-bf29-835d1f2ab05f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Roughin
8eecbbf3-9553-4eef-aba5-9b857af0b470 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Cut out
4226eaa4-85a7-467d-abe9-6562ae76bdfb |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Fit off
6780b394-b60b-43a5-87e0-99a649f1bb24 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Commissioning
f44e62f2-1558-4c20-89b5-42280cf3b098 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing
a6b7dec2-ad35-4cd1-bcce-8cb61a7b2b68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB1
872875c8-f898-487d-a791-b2261a9b6a1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB2
bff9e760-f573-453c-9455-061bd057f975 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB3
0802a2fa-3294-48bd-8efc-067801bbd4a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB4
d5d50ba4-0500-4aa9-abc1-3ca3e40c1281 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB5
e9c42d84-16aa-4f9a-8576-6a22e495e76d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2119 | Mandatory testing | CB6
7f10fb12-0320-420b-9b48-8fe115cce3af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120
935fab53-227a-40fe-924b-ecb5955130c1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Leadins
7e6bbd27-d359-4ebb-870b-9c01246c5d5b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Roughin
dd797c08-274d-40f1-ba07-27d9ccc842e4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Cut out
8d8b7c99-d6ee-4665-b75f-b90ec7de5021 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Fit off
5201c578-d896-47c5-ab25-70553d28a8d4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Commissioning
a9285077-360a-4fcf-a77c-1c92b2422113 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing
2ba559b5-1a61-422c-9937-4ca4e4a1065f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB1
54c383b6-b76a-4afb-a8a3-a0a1ab6403ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB2
7f5b69a6-9d30-43dc-b89f-f216d9cf865c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB3
fcab8c3b-9648-4b94-b28f-8d492a12966e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB4
cdeddac9-d2ff-4aca-ba81-1b11dadda882 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB5
edb59f51-62e2-4c0b-afcf-bdf732f06e7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2120 | Mandatory testing | CB6
89c8a8c2-86ef-4f83-8cff-b60bd5339805 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121
ba09637f-3537-452d-9c71-13bc370b1cee |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Leadins
12f415ae-f07b-48c4-878b-ea4a83c903b8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Roughin
4c265f07-dc09-4060-bfea-f2cac9f699b5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Cut out
fc6ba47b-5717-486b-ac73-69687e6b5854 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Fit off
c2452dcc-3b11-4f8b-982f-bf60289e67e9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Commissioning
82dbeb20-2177-46c3-9784-6ced111bccd3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing
84e59e17-be17-48a9-83f2-f1b2f1cd9650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB1
32ceb361-d37a-470b-947d-68914511d208 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB2
9bb02028-09de-4315-b19a-fcaeafbf0cb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB3
88f3a240-a7e9-459a-9ff5-5d30a0905ccd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB4
c383a9ef-fe74-4318-9f30-686bb0d2bd43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB5
a261b08e-df33-4252-8e6c-f1c184e34456 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2121 | Mandatory testing | CB6
cc99da24-d9b4-449c-8509-a601a4671ff5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122
da4eb6ed-9a78-48a8-8c21-21dd814d569d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Leadins
f5caa245-285e-4ab2-8f84-ec5bffcfb969 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Roughin
f0efcd00-7e7f-4112-be90-8b88c161f6d3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Cut out
d339c2d4-4f44-4065-8651-b906cf4ffb87 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Fit off
652b98f4-5e53-4522-9585-f0191394691d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Commissioning
687463a0-7cd7-4e96-a10b-65dd5120cbe9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing
1d60231a-5001-4e09-902b-42d7b614860c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB1
c6a16717-44b6-40f8-b1f5-4be7f8010082 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB2
c847255e-a7b0-4332-9cea-73d976e79b64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB3
2c742f83-9835-48b9-915f-85470b76dc0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB4
7a727e37-7f3b-4a94-acb2-b5a0ac14b128 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB5
13c17db2-778a-4eb0-8167-d8114799c498 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2122 | Mandatory testing | CB6
80b8f470-fdbb-48c1-9300-e8acee8d67d8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123
cff4c6ad-8a61-42ac-8902-8589978d1abe |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Leadins
98b60e81-785c-4f61-a1fc-378e81f3729f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Roughin
2b39f668-ccde-4ba7-98a8-d63fd8b48943 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Cut out
9a77bfd7-ef33-49ec-877b-c1210ec01482 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Fit off
28b8d32b-81de-4ce4-9927-b540b4a02f78 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Commissioning
be110e94-3ada-4037-ac0d-af58f7d74ef0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing
8676ef4d-6f7f-4d53-8670-02a5e6aed868 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB1
c7dbb21a-f3f4-4043-bab3-95de73491118 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB2
286fea15-15a3-478d-9d3f-fc22d2e467b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB3
899621a7-1bc1-45ca-b196-bbbebc4e7220 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB4
d1dbb369-f6a6-4ae6-8a9d-5285ca37f578 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB5
0fa11a29-8eac-4ba3-aeb4-22537ca350eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2123 | Mandatory testing | CB6
cd152986-9086-4ac9-834f-639130d7ee2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124
eb60f726-e9a7-409b-ad98-aa08dfcd5d78 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Leadins
0ed47969-88a7-490d-be85-2ac80a163d3b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Roughin
1ee78443-9db5-4aef-848f-b15a73dea4be |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Cut out
28e118af-9dc0-4716-98c5-a203a370bea7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Fit off
b6e12c9f-5cbe-479b-9922-36be9ea83d6b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Commissioning
d641b99a-8ae2-45e7-a545-6dd68a009d0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing
dfedf224-5ea4-49f8-ad75-3e423bc42543 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB1
897ca379-77f3-4237-acc4-6506d55f1aec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB2
695edead-8bb0-4751-9760-4e2bba7bc701 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB3
4970f316-091e-4ace-9fc2-ce6ebe675136 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB4
f816f6ca-49bc-4724-8214-b11d73e59f1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB5
ad26b652-26dd-43ae-8cd2-d41c5ec0de51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2124 | Mandatory testing | CB6
92652031-9b5f-4060-8f9c-0a58fd221686 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125
1d3b1284-3877-4cb7-a4ef-5f1f85d60254 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Leadins
3cedd0cb-4b65-4a45-be1c-0eaa30c32041 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Roughin
524ea5d1-6091-42fa-8266-900958f1f1a0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Cut out
d9accec4-8bc8-47be-a51a-abe0a9915b1e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Fit off
071ff3c7-acee-4888-ac2d-cf2e35423383 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Commissioning
8865f6fe-0c10-4d6e-97ae-f41f726cbd2f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing
e2aae401-87a4-4bf4-8273-a0b188370b83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing
c9433f8d-b8f7-412a-8de2-c9f48d35c470 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB1
d35e3ed6-dbd0-4f8f-b49b-806522a33779 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB2
45aa7f28-abfc-4f05-b323-8335ca6cb33a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB3
c47495cc-b8d6-41b7-8f03-105f0a92a930 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB4
f21fc422-1588-48d2-b35f-2937dc1ed574 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB5
3a5c8d56-c1d6-4c44-a386-a57bc04c07dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2125 | Mandatory testing | CB6
61e46773-72d8-4f20-ab59-0a51c93e19f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126
f3ed9500-dab6-4415-89c3-b95a4e812392 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Leadins
1822b986-516b-40e6-baf8-4ac105197ed7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Roughin
4260180d-b407-4acd-bda0-8d5791b52bce |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Cut out
c1b412e8-0538-4cfd-90d3-4b2151a220f0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Fit off
22565b94-05a9-410a-ac1e-9c9571dcff58 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Commissioning
d4358428-bec6-4a5f-8a21-79802d15cc64 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing
8554bb41-09d5-4d8f-849f-b792ea2b6689 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB1
ca7d56a5-d0b2-445a-a1b3-b0477bc81add |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB2
37c95e46-4a26-4119-8588-a222a201965f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB3
4188edf4-0929-4b0f-95cd-1cf73fdfd4a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB4
8d7186c0-993a-4c77-a0b8-a8a63a9e6efe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB5
349cb9c6-09f4-4d93-bd4d-2d9cd4a15843 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2126 | Mandatory testing | CB6
bd4bc136-14c5-47f4-84a6-39c1ddca124d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127
c96e7afa-2c0e-4003-8052-eb10edfd95ff |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Leadins
5d0f8f24-0a1f-4edc-8caf-b3ab242ca293 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Roughin
110c7b84-23ef-4850-8bab-9b92ee7a5c81 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Cut out
78a58f6f-ac39-4afc-be14-73823e9349db |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Fit off
c29c28e3-2688-4522-9e15-5865227b49d7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Commissioning
c4e9f43f-de22-4b55-94d0-1a40e4f4ec0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing
83f7bc89-26e8-4e09-bdeb-616357e31413 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB1
a1b06ab8-4299-44f0-aa45-66efad9cb43a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB2
357ac093-02a3-4e99-9b45-f7088ac45daf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB3
e69ff09f-92e1-4b97-8ece-eb700fe3a762 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB4
fbca304f-3b09-4ce8-86e2-63a71624285e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB5
e8a323fc-c7c4-4a5b-bb82-f02427879b58 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2127 | Mandatory testing | CB6
35e3fe79-37ca-409c-90ce-9d9fcb3a4e96 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128
fa47834c-c9e8-45d3-ab6e-819bba724ba8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Leadins
22120200-f793-43e0-b723-f6437cefce9d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Roughin
238802c7-e5f8-40d9-9e63-857705e7d720 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Cut out
cead583f-9d93-42fc-a62e-3a1e337e1d8e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Fit off
b12dff7f-1841-425d-8472-685741dcd41b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Commissioning
9e55df70-6e8b-4a5d-b9f3-4b55f78bb4bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing
20c5218b-33d8-4350-864a-c2a26966eae1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB1
edfa9902-8133-4cf9-811c-ad07889e936b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB2
a6edb37c-c4d5-4a94-8e34-88256f00fe0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB3
8cfbe4be-b457-4e24-b6cf-50294133691f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB4
e6eca37b-c3dd-409b-9950-26b9a5520ee7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB5
73cb2bc0-29ab-4b77-9316-2c751ff5b9e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2128 | Mandatory testing | CB6
3ae2e4d7-1be0-4196-99d5-c94dec84c368 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129
0d681aaa-3db2-4f40-9b52-6b6ab62b0ab2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Leadins
7447b06b-94c3-4f39-8a19-75e91bcf6a4d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Roughin
86c1760d-2209-4f65-93d7-f182cf077fa9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Cut out
8fc3a1ce-276e-4bb9-b6de-9b6e50108dde |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Fit off
7b2064d5-ea9a-4206-b989-04466b989df8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Commissioning
a8ed7c7b-95a1-4e5f-acbe-e4fc2451c33f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing
cbe8fc22-ffaa-42b8-9ca3-6b0e5add6576 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB1
35e3c594-c943-44bf-a619-bf62698efb37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB2
70e43aa0-0654-44c8-9d10-bf88d39e6227 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB3
61081a8f-5e2a-4f8d-8868-a4cdc40a8b2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB4
c397e396-fcba-498d-8503-8e4458c790b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB5
f2ca3409-afc1-499a-b98e-268bc03e47c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2129 | Mandatory testing | CB6
d979b2de-64ea-4b01-a2aa-f29ecc08d774 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130
87d4365f-7b9c-4487-ab1d-84f1846bbebb |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Leadins
519d0ada-4fc0-438d-9404-1925335856e2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Roughin
990037aa-0d87-405c-8226-988780f53727 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Cut out
9053828b-90c2-4757-bba9-f99298f15872 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Fit off
97aa6743-89a3-454a-bbba-4c6c9730e867 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Commissioning
f1322db0-38c9-4b5e-ae14-817f6be97f64 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing
e7c4adef-c784-48b2-922f-c3536c8efb40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB1
618303c8-3539-4aca-897c-e6eba1f2cf3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB2
2c2fa330-d553-4b87-a0b8-313093880949 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB3
9bd1f24d-8bb5-437d-aac4-25b9fc24d83a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB4
185e8d2c-7d40-4650-959f-fcdac8045a9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB5
3d3061e3-417d-4b2e-9ea7-33b91504974f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 21 | Apartment 2130 | Mandatory testing | CB6
75e0470f-6f43-49d1-9747-9c75b72f9bda |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22
0c61f228-089c-49cc-8547-373736df82bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201
54acae24-9011-42dd-9e5d-7fa6798a961b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Leadins
00245f9d-8e40-4ef2-83b8-d5a5d4bc841a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Roughin
9d7581aa-a096-453b-ac32-bb2b9c853df0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Cut out
f27be573-afed-49c7-8a6d-be1a20a5f2d8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Fit off
e16c774f-689e-4cda-a835-21faa5823ee9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Commissioning
343fc46a-bc1a-4416-9fd4-91d17b5ee4b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing
11ebc10d-3f6e-490c-a60b-a9b9f52c9a3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB1
206e1436-0084-4ae5-9a20-81e6997ad5c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB2
c408ecf9-fc55-4806-b650-449325cd5c13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB3
a4ff6d17-7f21-47d3-b7da-59633d9c1663 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB4
2bfdd7e1-22fe-496b-bd40-5a5447fcb4a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB5
f0955b2b-87d1-4598-b203-7b8b390d1a71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2201 | Mandatory testing | CB6
bcdc1ac2-ccd7-4c52-9899-8a30d07c3100 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202
86738b2b-977e-4ca4-81f6-8c2d3692276e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Leadins
238a279d-421e-418a-b364-a6ed06333313 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Roughin
dcaeb6ef-7550-485b-bff0-0db93759d52e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Cut out
3287187b-8374-4b15-8a2a-47a80223eace |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Fit off
c0db45c2-42b2-49dd-9537-62534a21f29f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Commissioning
14aef1a6-0885-4f5f-9997-52e54c0619e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing
7f7452f3-6045-4c23-bb24-14248067fe82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB1
f654a132-35a3-42a7-8ec4-7eb0d42e4b0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB2
de4d24b1-b4da-47b6-8545-3889a7dd0d25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB3
81094093-9db3-4358-8d0e-e521131152af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB4
8be23271-5cc3-4ae8-9641-31297ad26366 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB5
5b4a9cba-9d42-4274-81c5-8f52cfad6f85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2202 | Mandatory testing | CB6
ed008b7b-c9f7-4d55-b2a7-f51f4746092c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203
8e185f23-93df-4cc8-8bad-fa52bf423bc2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Leadins
7b1fd9d3-7dac-4228-b742-13c5ce5e9be9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Roughin
b56b6802-9e51-4671-a044-0fed60c5ced2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Cut out
7fe6aa12-1d52-44a6-a133-f47e96a652ac |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Fit off
cde0a074-624a-4bc1-8241-edccaed2367e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Commissioning
d8d13720-b51b-474b-bff3-135d1ab02003 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing
b4b2101d-6105-4b54-965c-dd38ef5a18cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB1
5c3fcde5-6c78-427b-80e5-971e6768a685 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB2
132a5e4a-db39-48e7-812d-8759be278688 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB3
10e70418-6ced-4b6f-8ca2-350b343444d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB4
ecf2c4ff-1327-4cb0-8a16-219a6a6db2f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB5
77a516d1-6db8-4ae9-aa4a-dcd5c67812d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2203 | Mandatory testing | CB6
fe4f25ea-acde-4a94-82a0-b779edeb2b8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204
2031c636-6477-4800-9975-9e4fc843ef61 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Leadins
c2867a90-5f58-4968-9739-60d6c2bfe1bf |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Roughin
227ab7b0-6c0b-4759-ac36-1dbf7a631508 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Cut out
4fd07791-76e9-404d-94f2-34c5da91e7d4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Fit off
bedad3ce-1cef-46be-aadb-972998b70a30 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Commissioning
403eea45-1561-41e3-a570-3c4c537a3166 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing
4b36fe67-d49a-41cb-a6fa-226737b74c64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB1
c3361fdb-3e71-432e-a77f-4cb9c983741e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB2
8a198736-906a-456a-8df0-3b87116f8f72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB3
518fde0f-6890-428c-a6f7-c7e5a879b405 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB4
089f8908-1f7a-4b2a-8c84-da52b7e26c22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB5
9b8d5830-1c12-4394-8a51-1e933cf812aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2204 | Mandatory testing | CB6
d2cfb95e-c526-4a4a-8ca6-b75e5ac199b3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205
fdd66bc9-6304-47de-8a9d-5e4f0bf7be01 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Leadins
5f5a5a3c-f484-4d46-b08d-4ddb1d0da54c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Roughin
a4b851c8-49ce-4de9-98de-5603f0ebfc43 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Cut out
395ddc6b-b0a5-4b7a-baa6-f27b56125f77 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Fit off
aa1d9a8c-8077-4fba-9346-258d8be35f99 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Commissioning
59796ba2-252d-42de-93a1-c4333f51dc5c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing
6766ff55-1578-4b60-9470-f7ad38910dd0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB1
fbf95177-60b3-4829-a3ae-ec736f0248c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB2
820281c3-f7e4-4adb-b293-c02b03199e89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB3
6ac85023-89fe-4317-b25e-883d33879e82 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB4
38b9e94a-8fb0-4e2f-b410-83ee3a723b1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB5
4365cfdd-b618-465c-95f1-8c9cbf663e05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2205 | Mandatory testing | CB6
48ad848c-8868-41b7-acb0-67632cff636d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206
1c45ae3b-ab9e-4f68-9a60-16252e7b6de3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Leadins
d052f7f1-72cf-4440-a375-c688309e84fb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Roughin
9c3027c3-27ae-430a-8df2-b0013979b11a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Cut out
9cf964c7-f91b-4ca0-aa19-aeba11712486 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Fit off
a69e0dec-73ae-461b-829a-f647db7bd28a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Commissioning
5d866fb4-63ad-4526-bd20-5776cdab536a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing
38a65045-ad3a-493a-9f72-b30dd931a759 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB1
3b8aecf6-abc5-4288-856d-565873ca0494 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB2
95fd96fa-949e-4034-bf46-63538e010a22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB3
37474765-6f90-4b2c-a381-f499f9d239d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB4
844d1029-ba63-49ec-a27e-472968305c97 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB5
755f50ed-5e1e-418c-94b0-7cfc672c1743 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2206 | Mandatory testing | CB6
66e1bad2-139f-4201-b104-b38942fdcb3e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207
4594e4a3-4d2c-49c7-b7be-260828c75e5c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Leadins
8fda0f77-0069-4f10-9840-cadcadd13b62 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Roughin
2c2fff77-5a8a-4f9d-9ba4-e0236e0753a9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Cut out
52752810-9a79-4b1b-90eb-4bc8198c25b7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Fit off
5a94e4b0-446b-433f-a2eb-efbfbe4bee06 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Commissioning
bbf4b2fc-f33d-4741-b09d-6bb8f843762f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing
331fa8ce-60d8-44a4-a197-28956b8bb671 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB1
a305d172-ce0e-4148-b456-feac1fb3e14b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB2
670d6b26-c852-4a3b-95e7-1fa0d97d0dbd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB3
cb1faa6f-534f-4565-ade4-edeceb9591bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB4
c90d144a-10d1-4d66-96f9-28a22c1bc897 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB5
0ddcb7d1-bc21-4239-889c-1ec1bddd6e69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2207 | Mandatory testing | CB6
a4177132-d922-4af9-83c6-f79f1283f9b2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208
c89e17c3-2c0b-4b33-9820-a1a9f64e17ee |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Leadins
de23e21c-05f3-484c-9d19-4cbf4692f7df |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Roughin
dd3bed62-9359-4542-b5e2-b4d68fd11b22 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Cut out
c7cbc74d-6d91-4ba7-83b4-eb399778309a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Fit off
2f6e19cc-f286-4ac8-ac4b-772cfbbb9656 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Commissioning
ac611364-67f9-461c-862e-10b6cff87e13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing
759133f8-6a30-4fb0-a572-baae83bf6f91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB1
93be2fd7-4811-4256-8aa7-9cbc3a3c2bd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB2
3cec1c4e-ebfa-4bdb-b2fb-e760e777356b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB3
0028137c-a086-48b2-95d2-fc91964babb8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB4
a21989df-df48-4d68-bd04-031deb0cf165 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB5
82ebe9eb-ebbe-4995-8928-2d10d2bdb139 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2208 | Mandatory testing | CB6
d26f1f50-48fa-4791-b343-a0ea1dc64e2e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209
da7b1394-292b-4bf5-9018-1c12b5ee88ce |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Leadins
c3b751c8-e787-43b3-ad10-f4acbff0370e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Roughin
165a5cd0-927d-4f9f-8704-e81c646a45e2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Cut out
2de29059-4a08-401a-ac2f-ba97663dfbb3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Fit off
7705665e-8ca3-4f26-9511-5ea48d59f17f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Commissioning
bbdf0276-9568-4597-9300-781e71c1e9be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing
961f9070-ff95-444f-8164-9ee2882f06dc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB1
1c0c21e9-98b5-4862-a7ec-6ef7100cbd85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB2
1bbda03a-b1d3-459f-8d72-0126c1678238 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB3
4c902ba7-ac5c-4621-9d8a-a7edffa8f613 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB4
28d963be-e660-44d1-92cf-901268a6724a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB5
d59e2e82-df60-4b52-b74f-f1b045504efe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2209 | Mandatory testing | CB6
b3a40b22-49a2-4d39-9a87-1254e48fc50e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210
05869bde-3253-445d-a8f9-abb815487656 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Leadins
ecfac840-fd03-462b-b68c-27660fb676f3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Roughin
de939345-4507-4e59-9c31-28509e6dbfd9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Cut out
b55cd06f-b5cf-4b91-becb-2b5026ca9ce2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Fit off
3a878a56-4af7-418a-922b-9ee91dbb8413 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Commissioning
dfbf3869-c901-4c61-a5f0-a82ad062ee10 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing
2d4eafc0-11b5-4b71-91b9-314c96dff638 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing
0df1b862-e206-4bf2-90e7-69bed5ca20da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB1
2f6c0c93-049e-4f5c-a058-4d98bb90ddd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB2
e38cd836-0547-4eca-8350-7b67ea17bc63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB3
847adbb5-9d56-4b87-aee7-e50258c8a14a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB4
fa09f100-d0ba-498b-b9e4-8f1d5e0cbf71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB5
07a79c45-acaa-4810-a54b-4efe9a395714 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2210 | Mandatory testing | CB6
4c569538-cc25-4f6e-a4a4-4d73baa67245 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211
4cbbbedc-4574-435c-8fbb-66e25c173da0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Leadins
219bb88c-f43f-456c-87ed-0aaa4921c8d3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Roughin
ae924a36-be48-481a-863a-8e541b8343cd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Cut out
f23fefd9-33cd-47d2-a074-10cf6e8e010a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Fit off
5f7e2b87-67cd-45a4-9945-992456fd0cd1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Commissioning
3c60543f-4a51-4ee0-af2c-6ad11f77af39 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing
37f845b4-a822-4dab-9f0f-4e4a3e0dd4a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB1
f5577d48-64de-4073-96f0-5ced5bbb5697 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB2
bdaea46a-6916-4c8f-9680-d07c288d0b18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB3
31fc8400-d5d1-4b2d-a088-a7e1f5afe8b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB4
0dc29676-8b2e-4faa-9362-6d986d5cf2f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB5
69dd448d-c368-4596-b0f0-a1af64f96f95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2211 | Mandatory testing | CB6
134961b1-35da-495c-81f4-74a7c98fc06c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212
b4eb2ba3-26db-469c-a757-c2a7e838e577 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Leadins
414275a7-532d-4a1c-bdea-8d05dd84058c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Roughin
bc3a13e2-289b-4ce0-9c64-693a500b0daf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Cut out
d6bb56f3-a857-4caf-b570-7778ab2af82c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Fit off
e0f40549-3f11-4d2b-9bda-95c21b57c788 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Commissioning
670a7c51-d557-4497-ac71-696355952628 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing
12c8daf6-52cb-46c7-a7f3-d8cbf72ca392 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB1
718292e4-5491-48f1-bb21-68db881f8176 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB2
9f7bd32c-0714-4a95-9a27-cd010e9c41ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB3
bdfbd9e8-acdb-4e48-839b-0375f07358e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB4
4ee24f96-ab0f-47b5-97fe-a4307b7ed5d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB5
d499ed77-2dd5-4aaf-ae6e-31ba289cac0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2212 | Mandatory testing | CB6
aadf422e-cc4c-454d-9d71-72ef1ff2f744 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213
4df1e706-ba15-494e-8306-216add2c0626 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Leadins
24bc6f00-13f6-49a3-bcc1-899b9a5c70d9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Roughin
6d29020e-0eea-4003-8524-6954b1cf18c7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Cut out
6a715b71-97f1-4cf6-b5ac-bba43390b07a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Fit off
c7e99560-2bda-4b23-a93f-05e9bff12fd9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Commissioning
31cd43d8-f966-4b9b-a80b-4782a0bc125c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing
438c39dd-0553-4565-a9ef-4ad7d9ec1c56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB1
96e6e84b-12b8-4d76-9f13-49b2b2888306 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB2
90a566d9-12a3-4649-a934-f3958803d26c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB3
93b67021-23ab-42a8-884a-3f9f0a68677f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB4
27c36950-9b7c-4e17-8355-7e03f04b729e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB5
55a5c5d0-7c52-4caa-8dc7-9bbc992eaa84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2213 | Mandatory testing | CB6
8890ba62-ca48-439b-a48d-a74e1748305d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214
dd530e0c-1a44-462c-8975-39b5be79bf7f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Leadins
510cebc0-00ae-4871-a2af-886ed3d35980 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Roughin
6d38e204-69be-4c20-ab7f-b940d794cc41 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Cut out
cab09e27-008a-4ca2-ab8b-762e88ef7c78 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Fit off
d2d1101b-0b92-4f80-a2ce-8707d10a4521 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Commissioning
e53bdc2e-4dea-4c91-b0c7-7893b8021769 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing
b513008a-3674-41f5-b26b-c47010ba927c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB1
cefd2fe7-5b82-43a6-90aa-f9988cf1589b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB2
195869ac-7ad4-4206-969c-f31ceae63e00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB3
e35104ce-6fcb-463f-a5ba-08801573e71c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB4
e9bb613b-82bf-4b42-81be-37f0e4f428ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB5
ecc7eeeb-5705-4f6d-a03f-be7145355cce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2214 | Mandatory testing | CB6
e7759ac0-4e1b-4178-955b-e51b116c935f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215
2f8e5df1-661f-40c5-a068-510b468ec4a9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Leadins
005b6ec6-590b-4c1c-bf38-ea6ac04f3118 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Roughin
a4f8b0ee-4747-4b72-9142-a7b2d6ca9c34 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Cut out
ba6c2cef-f75f-4f48-8a25-6be350a652db |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Fit off
01276051-c82a-433e-9b08-f83547d55e91 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Commissioning
16ac011b-7ecb-4811-a00b-6af4572be801 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing
05bfd434-fdea-4d7a-90d8-b71eab69400f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB1
7de45925-5b14-4da6-8ef1-ed9fbf643ee7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB2
66a06cde-bceb-42c0-afe9-5a3d33c5c2bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB3
00e19cd3-0bbe-4e86-b3ec-f258ead64c59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB4
cd51ff20-1077-409f-878b-334b79061712 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB5
39382852-3573-4465-a75a-26d13773458a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 22 | Apartment 2215 | Mandatory testing | CB6
86f50c9c-8347-4683-a2bb-aa2b451e55b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23
4e2e18e7-4cb6-4d3f-ba8e-6435832d92f3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301
ab9f2f5a-b45f-44b1-a2bb-484bab9d9aef |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Leadins
cb9f0c90-de41-4376-8cc0-337c881be613 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Roughin
f844d2d8-229f-41fe-8fdb-6b71accbd39d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Cut out
bcf3aeef-558e-4e66-8f71-1ef027b0f668 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Fit off
f4ec43aa-fed4-429e-b4f2-0194da633dbf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Commissioning
722db935-29a2-429e-9d2d-32dcc99cf264 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing
e801c531-f18b-49b8-8a90-03fc0b5b0ac1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB1
f668c053-368c-4a89-9db9-e654717d1227 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB2
d94f0e96-fffc-491b-a9ea-8526fadcccb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB3
e1a45ce5-85de-4ee8-abef-61335a8bca8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB4
d50f10a9-e59d-4b68-9e8b-08f9a8324b43 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB5
8ffe7bc2-64d7-41a8-ab67-a98bb230c8a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2301 | Mandatory testing | CB6
637b02cc-0e80-4876-a7e8-b5377b896f61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302
8a08a6ab-c821-4a51-b2ac-c4b33fe5ebb9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Leadins
f8a660a5-078e-4ae6-9e88-44f7ff88a1f2 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Roughin
9eec1057-2165-4794-8585-87590d532d60 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Cut out
736bd037-9286-41a5-aa39-844218c7cba8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Fit off
37959685-71c4-47c6-8754-10f3505f5f7a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Commissioning
fd173fe9-dc54-4be8-b1e6-0a18d7628dcd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing
0a3e1a7e-be18-439e-b398-26ba9829397f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB1
72cd5932-ac73-4593-9c79-a1ba43c6e7b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB2
498cccb6-e0f5-45a5-961a-b0069121c268 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB3
2a26ceef-f1dc-498a-a308-bcbaf82591c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB4
7ca0cfff-3ea7-4f23-8a06-7a88b33b008a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB5
fdfc2393-0851-47ee-8313-e447faedd664 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2302 | Mandatory testing | CB6
e98b48a1-1aec-4d2d-898a-96b4f43b65b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303
41365c9a-b7ad-498d-8889-778426878855 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Leadins
7ce431c0-2172-4139-896f-628a325615bc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Roughin
1f385bc0-976c-469b-97e1-1f2b12219cc8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Cut out
16709174-7c93-4b36-ba4d-bfa580462eb7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Fit off
1af2aed5-b0b9-40d5-beba-cd8ddef9ec71 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Commissioning
764cb0d7-2a83-46ed-ace8-defed311bc2a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing
178c89df-a637-4620-974e-e352b89ddd30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB1
2b1d76f7-5292-4a11-b9c9-1e76dffc941a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB2
6c079de0-42dd-4964-bce6-aeb7b6d6d942 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB3
3e841d45-b54b-4f2d-ad99-a6f87fc78b4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB4
35863e9f-b08e-423e-a550-34f6bc23d5ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB5
338a9967-259a-4402-b226-f369719d39e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2303 | Mandatory testing | CB6
e85b880c-4f03-44bd-a8e1-5b4da7b24b8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304
e9e45421-e0f4-4f52-8cae-85c5b72d3dc3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Leadins
43373ed1-d8b2-4146-ada0-d898c078ed4e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Roughin
d13c82b2-9a35-4d3f-b745-7a9aa2acb80a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Cut out
5eb843dd-0c94-4901-afc2-defb023d389f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Fit off
502f0253-8c9f-4957-8fed-1b7a43e91a2d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Commissioning
dd2ed19d-caf7-4dcf-a1c7-011f4545855b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing
c334e24d-356b-433a-aa41-235c3e175aac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB1
9c5aafce-9377-4163-91df-02e1e6521117 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB2
d40c4fe5-0f6b-4f9a-8ed7-fb61f1568484 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB3
a883e84c-d382-44f0-b0ab-c4e6bbfe30e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB4
662fad55-3822-432a-a274-5adf3d262a99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB5
0fa6763e-d9c6-44a9-adb1-89f9f9934a41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2304 | Mandatory testing | CB6
3682b711-9c3e-4d05-b65b-19048a6a24c9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305
6e47a92b-34f7-40fd-aed7-096347985524 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Leadins
8a12705a-da61-4dfc-92b8-65cff4196430 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Roughin
07580cd8-c966-4986-8c63-7310afb13a12 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Cut out
920aa18d-d8aa-4d74-bd2d-a31bf051a29c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Fit off
31d95590-e520-4255-a2d0-bc0b7d3da327 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Commissioning
438d79b5-a4ed-4ecf-b2f2-2216366c32ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing
9a0b97e8-53d0-491d-85ac-3510d625bdbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB1
13fcb530-cd4c-4bd9-a620-b588b30af863 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB2
0c505238-e80a-443f-92bc-485b5f57a308 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB3
6d32169a-3700-4f76-92c5-4310ad2b8b1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB4
4f86fd99-e711-4026-bfae-75811b29d51f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB5
7fcfca48-008c-4421-b019-0e6cb2a41213 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2305 | Mandatory testing | CB6
c6285819-effa-49ec-ab06-17ddd1ccffbd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306
0bf23dcd-8145-40be-abb0-895e320b0b52 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Leadins
b0a08596-9e6b-4281-bba7-8c33e3bc9598 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Roughin
64c87119-9aba-479e-9d6f-4a03e7b766a6 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Cut out
eb81f6eb-3447-47a4-8abb-4c77d0c1bc11 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Fit off
67360dc7-3138-4e4a-a534-9cf856c84375 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Commissioning
8086f763-bade-4f2a-82d8-547b66af5460 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing
befa81f6-9b1a-47ea-af55-7ac298f624f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB1
aafe09f3-cd52-4b5c-8c31-ee9ec377a9a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB2
db6d9f42-decd-41f3-bfb4-68db820b93e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB3
be51f14a-07df-43d5-8b34-19ab808a7ff6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB4
7b5ec164-59cf-4bc4-988d-201518b2aa0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB5
8ce424bd-db91-45ed-a5fe-dbda995e4723 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2306 | Mandatory testing | CB6
d3277978-c259-46f4-84c5-77c0efe192d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307
2fa8f93b-7ad7-47ff-89cf-9fb5fd185bdc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Leadins
db613f78-f62f-4439-a6c6-001b97ab385b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Roughin
fda21b36-2530-4fa0-95f5-550806be331e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Cut out
51936bb0-d728-4051-9ac6-8354055c7620 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Fit off
33806aa0-22f2-4f23-8bed-584fa2cc18ac |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Commissioning
44191180-bc0f-475a-92a8-a8919dfbf59a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing
cc9be9b2-aa28-4233-be9f-a5c51fe933f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB1
54c985e0-e27b-4885-97fe-740a4174fb64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB2
055cccae-25a5-44b5-8802-3b447a07b30c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB3
a96f9ce4-3bc2-47a3-ba0c-318ffe943812 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB4
b9bf8026-5655-413f-b073-2279683c1196 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB5
e5a120b7-eb15-457d-82de-fc322ec61356 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2307 | Mandatory testing | CB6
45b1164d-d36d-404d-be7d-bdcb9ae6feb7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308
77dd2438-43ea-419f-a5f5-0315fb98d1a3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Leadins
7e53002d-6912-4948-becc-b15890018f4a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Roughin
ef4d45e9-5b74-4147-b0f8-248ea4f53cbb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Cut out
b3683173-9f5a-4bb4-a285-fccc9aee80d9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Fit off
9f446edb-72af-465c-ba0a-421696642ffa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Commissioning
7d4cb908-46cb-4a6f-99d9-1f625a2e897b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing
f07528f4-f150-49b2-aca7-29c50080d80b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB1
518f2b79-81e3-4ff5-9b10-24567fa7084c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB2
b8363ade-2d7e-4ef8-a688-566c854e321a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB3
803e49ab-6667-425f-9c94-ed738a96607c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB4
5d411da9-a2eb-4ba3-a396-1c1bbb6e7c3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB5
0613f2a6-02a2-45d1-abdf-6247d1f396f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2308 | Mandatory testing | CB6
adb65cd4-9b92-4fc6-a15c-76076b10bb84 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309
144b4ce8-688d-4421-8dee-d8140127ea62 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Leadins
bd8ea188-9b86-4249-869e-f90657adcae1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Roughin
2fcf44f3-d3d6-415e-a79e-d2503c8d9ef7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Cut out
9be553b9-2436-4114-99df-eed22170b513 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Fit off
d532c1a9-b3f8-43a5-aab0-294fd9ef9060 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Commissioning
fa8bd0cf-d808-44c3-8113-5541c4bc03a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing
4d587e87-f103-4975-9806-2c3ec52070e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB1
a6780a21-00c1-40cb-bd54-16c2e9de5ad0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB2
f0f5716e-0295-4738-82ca-121314a7741a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB3
5054eef6-2230-4fc3-a244-efeaf4ba218b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB4
738afd19-5e12-4781-aa41-eb5b845fe432 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB5
9552e1f5-7408-4a01-8b51-6e3829e1b49f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2309 | Mandatory testing | CB6
bd6edab8-0d3c-4fb0-86ce-32e4c4525c89 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310
31d57ec3-a81e-4193-b32f-c7dacbaaef0e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Leadins
10e67cf8-339f-4cdf-a7ce-4090970008b9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Roughin
3a95f3e9-dc16-4bb5-90c2-d721374467cb |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Cut out
8913ffcd-c6d0-48c5-a4df-afc201a3afa3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Fit off
bd378a06-1a34-4ac8-83b7-acc97b04ada0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Commissioning
c3e5e12d-a871-4c15-8126-be579f1e2d56 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing
9871f199-151b-4514-9016-1f0d8ea24ae5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing
72a1bcca-aeed-48fc-9db9-05ef5fda9a94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB1
83a33f5e-8c90-4d87-8634-14fd778f90ae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB2
7b1be0b6-b80f-44b9-8ee6-9fdb726193f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB3
b35db6c2-af18-47fa-a758-a3f307a710e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB4
99ee4333-4f01-4789-8b4c-47102cb0af28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB5
910753e2-8538-41e6-a0f0-3de49a4f48be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2310 | Mandatory testing | CB6
cb3d72ba-fa75-4956-886d-953d7d466863 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311
8633357c-6399-463b-97aa-2ad886b3aab5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Leadins
6fd91dc6-a403-4017-b6a8-c8703c01a01c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Roughin
dfc97698-2cbb-4409-a699-bcbc1bf88063 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Cut out
fcea8555-1b52-4004-9731-dc45a056dd79 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Fit off
c1c9764b-8176-465a-b839-8a1d3d63361e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Commissioning
79ba6f22-2808-4dc8-9522-b37a57d4dc04 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing
1f49a55d-44dc-42cd-92f1-b04e439caa51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB1
73381616-43d5-4916-80a7-894ee4e50819 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB2
9e17fe8e-6d7e-45d8-b43f-3f8f2f64fb37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB3
4e14d04a-34b7-4e9a-8f00-c73d200b155e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB4
649b9043-9d5f-4dff-91b4-94cf3e2abdcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB5
0cdfe332-8da3-4383-b2ee-afe753ca26f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2311 | Mandatory testing | CB6
7e2b4f1a-3238-4b86-a7e4-fb3d07259245 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312
5e455d13-0423-4fd9-819f-ce4b2794f4dd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Leadins
903dad70-e647-4395-9c1b-fbceab3c09b4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Roughin
a8454b75-9216-4ea3-889a-5e98248ad535 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Cut out
e60a2cc7-7bc9-4c02-94f5-dc853e853e63 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Fit off
a9db5c24-c5f6-4613-8611-286201d5b3bd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Commissioning
818db014-2f42-411a-b85b-6047c34c902e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing
4efb5b34-d50e-4b06-8aaf-203973a4bd4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB1
993138e2-4fc4-4360-90ba-788dd05207d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB2
01d712a4-fcc8-4ea2-8e9e-ffbc0665fecb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB3
500e2d56-7c24-4ed3-8900-81d226c85282 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB4
aae750b2-14ad-4d37-8077-fd09e89e7041 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB5
29327fd5-4bba-4aed-81bf-a0d85c2868bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2312 | Mandatory testing | CB6
86961f86-6f4a-4864-adb5-6647353788b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313
32254ae5-dbd7-4df2-bed3-0f2ba34ebc54 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Leadins
ee6f4728-bd53-4f42-b8fb-eb5e30b48241 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Roughin
db7037c8-665e-4ad4-a1d8-961edbda15d3 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Cut out
4f43fe60-38f8-4f65-b7f2-077072ecd4ad |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Fit off
96e26dbd-2392-44ec-9487-3d06951e50e1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Commissioning
36fac887-5b31-473d-a58b-68d9e40aa2c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing
4ae86778-3ddf-4dff-be90-df6644570544 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB1
62b125cd-7bb2-42a8-9776-84dc01f1716c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB2
e29c771d-afe5-419a-b3bb-b2e794232894 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB3
6c7c9d16-f132-47ee-97a7-5ae061cea7eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB4
6180046f-7433-42dd-b6a7-9395ff761d73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB5
f3f5ef14-76a9-402f-b5ea-69ef31b5346d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2313 | Mandatory testing | CB6
33987508-994f-4685-a7d0-c9dcdfc764f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314
b9a5a84e-7450-4076-8816-8d833c217134 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Leadins
2bc539a6-b68e-4252-9e65-06fe49604ecb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Roughin
c7695d03-466b-47fb-a3cd-8ec4e1d0fc91 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Cut out
414c256c-df9b-4ab6-b0b3-dd4ec7d94712 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Fit off
3efa575b-f1fa-477b-a772-45824a3532a4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Commissioning
e8975a96-3731-475e-8b30-90d9b8c4f51d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing
6b95e516-b2c9-4a99-92c4-bb6275876ccf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB1
510e16b4-4c66-4067-a16d-dd704d5882a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB2
fde16570-7dd8-44b5-9bd2-5fd8e526ce95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB3
fa6a4069-6aef-4f29-a689-ba0f1ad75497 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB4
57369580-e2cc-4b23-b049-74da46639b1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB5
f913bbd7-ddc2-4c36-9ef8-5aa7a39e9165 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2314 | Mandatory testing | CB6
1a65766c-81c9-43d1-8736-56fbffae1df1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315
76faab5a-d56f-4764-a2a8-c7d679ec0a9b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Leadins
e6e43ad1-6467-431d-8900-5a0bfc480aa4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Roughin
8c4f3b89-f03f-4f63-8ef4-8f9f16d66061 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Cut out
3b68822e-0753-4f13-9e99-4dde00c33e9f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Fit off
cc6d6596-4369-4bbe-8054-c3d160b01028 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Commissioning
897a4f66-a32b-46c6-8854-81d9a8982589 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing
b6193432-9cb9-4bd7-bd44-371826cdc096 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB1
c52b6d4b-dd39-4883-b3ad-4c3b7c30bbc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB2
478ef5a4-a93b-4647-bbef-cf5736c333b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB3
6e1e0812-790d-4ba1-8475-625d7047e62e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB4
798b6691-d254-4107-a95a-25f95db91efc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB5
4809b3d5-44d6-4d38-b2e2-de94791ca1f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 23 | Apartment 2315 | Mandatory testing | CB6
2919bc8f-7551-45ed-8c7f-c2ba3e83bf65 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24
2437c99d-eb42-43f1-84f9-a5d43a518d9b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401
3f0d27d7-6500-4af9-91b1-83af0b33377c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Leadins
48d8db22-672b-4348-8ede-d5045aeaf8a4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Roughin
cdecf032-c9ba-4af5-9bb1-87a7b7c91fcc |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Cut out
f7d5c600-a057-4b7c-bf0d-735f99e879d1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Fit off
a934a412-1687-4319-898e-81ceec17dad5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Commissioning
cb6d92d4-742d-4e80-bde6-452ac3f4efc4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing
6e23ff94-e154-486f-8084-175de6988b41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB1
ff3c08c7-49da-4913-9a3c-36f386f4c409 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB2
355f68d1-5baf-4f0f-819e-0684e2d28d7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB3
045c26d5-d94d-4384-a4b0-1b1966047bd9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB4
554f276e-1cea-4a0b-9954-144dce2a4e0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB5
e4366a1d-a9f4-4232-a224-1a2c8666d033 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2401 | Mandatory testing | CB6
86949897-9a7b-4292-9cca-0135005fee12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402
0f0d48bf-f7a8-4aa3-ae2e-27810325f560 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Leadins
cc4c8d4b-408b-45ec-9b0d-33a9940814a8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Roughin
9fc56911-3b1d-4a46-9b3a-07416583c6f1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Cut out
eb41e28e-529e-47a7-ab8e-d8840e1c785f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Fit off
fb3657f7-40e9-47bf-af37-42e8607210cf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Commissioning
7a452fab-128d-462e-bfb4-32ffe6afb12e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing
f922e42b-b940-438f-ae9f-5e2c8479ea4b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB1
8bb01e47-9611-411f-9b59-671e2fe79edf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB2
8d1370e2-616f-43d2-b125-96093fe42a11 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB3
91b483d5-a4c4-4ec1-8370-c739dee9264b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB4
0f0fccf9-f6ba-4f97-b4c3-8e1c707a61d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB5
7d94eaa9-d864-468e-91b3-e380278ec85b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2402 | Mandatory testing | CB6
0ea5aca0-2b54-4add-b55d-244fc24b3c83 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403
40659269-f135-4c76-999b-42efa256c8cc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Leadins
43d54d82-7258-4653-8379-c074eabe1647 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Roughin
76f9739f-d120-4f8d-bc06-f8406379e632 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Cut out
d9e43a10-100e-437e-bcae-a0f4d8a21aae |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Fit off
27db021a-6d0b-41d9-ba33-483affc2272c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Commissioning
3f4d49e4-76b1-4127-a35d-4145d7dd254c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing
6bf3d2b9-b75b-430d-8c89-a4f92d9f095d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB1
f39df3f1-170f-41eb-b80e-ce39d49cd806 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB2
071b808a-e8c9-4835-8609-f00d0d0f8f4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB3
bacb989e-695b-41a5-aebd-e17df47b4db9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB4
9a138993-642c-4995-b63c-037c38e15d67 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB5
ed453ee3-e326-4915-89fe-cb3178b07dc9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2403 | Mandatory testing | CB6
41a7ef56-7779-4894-a5bf-698e9366b776 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404
adb40d71-41ef-41d2-90b0-5ae12c02add2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Leadins
efb3e67a-459b-4fb8-a10c-edef4bbca3c1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Roughin
1109014b-8e0a-415e-bc35-e8e7e6af09e9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Cut out
39bc9705-22c2-409b-9980-de3a29ac8d58 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Fit off
4ff382dc-d478-463d-96b6-8d5c4db441ec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing
17497f8c-9b99-46f9-9622-6ea7f5ae7116 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB1
ee6e5a9b-b9f2-4dd4-a518-5440be7895a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB2
c47d63dd-d23d-46d2-ba8a-f4f4c0c8edcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB3
9937c84e-e3da-4e34-9027-5620bd4a1cfe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB4
427f385f-3aff-4ea4-889f-2d131a559675 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB5
440e318b-7fc3-42cf-9170-55f00cd987ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2404 | Mandatory testing | CB6
c832365e-8f91-4c02-9c83-4d5f7138bea8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405
9227a6a1-ab9a-4d26-8920-2800e6c79ece |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Leadins
b039d7bf-4948-44eb-948a-ce517a422024 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Roughin
edb61786-fa39-4b2e-8006-9c9346b57e89 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Cut out
00809f77-cc3c-4b9a-b94f-87b0ca710ab9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Fit off
344f7119-4d06-4bab-bb16-84a49f74c2b7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Commissioning
7d176a2f-8524-4200-9907-845ba0056e5d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing
222eab70-cd40-4d23-9972-86a5bc2fcaf7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB1
71395bd2-1563-4f41-a9f1-1632cbb9fbe6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB2
5567a7dc-6130-49a9-bcb1-011228661ad2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB3
9f1eb185-7d06-42c5-8f95-433e72a40c54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB4
d6313ca2-2571-49f4-b4b5-a6e8b38404bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB5
6993fbc8-257e-4b93-9686-854342229c66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2405 | Mandatory testing | CB6
54647a33-2d2f-495d-88b1-3fc073c373fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406
463615c6-6214-452d-a001-204416c555b5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Leadins
28fbdb43-4df5-4612-901a-14590b94ac6e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Roughin
b2b30db1-fa9a-45d6-becc-90f7a8283b02 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Cut out
f9414b51-9282-4ec0-b475-b7589790d6d4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Fit off
29f24c5a-cf1d-4b35-bd9a-31f7e77e0e63 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Commissioning
cc005b80-7273-42ba-b5d7-955665465065 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing
c2ecc12e-593e-4f41-a793-282828009219 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB1
a864ee7d-8e01-4b6b-8478-b392e1f6c87e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB2
4245f867-446b-4c5a-abf6-ad41f6112a50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB3
58dc2b55-5a60-45c2-8942-ba4c5c296e55 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB4
f4d49723-aefa-4278-856d-494f13fe4b05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB5
eaf21225-38bb-47e0-bb6a-e83cc399670b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2406 | Mandatory testing | CB6
849f3412-751a-4622-aa2b-548dee316888 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407
36cdcd2c-5b06-4c20-a230-99a57dfeb054 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Leadins
11796168-7fd8-4db1-aca2-0c362dd335d7 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Roughin
28b63fd8-5a3f-422c-99f8-164130f124ef |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Cut out
da64dcec-36b5-4da4-8cf1-183430ec3d93 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Fit off
c6493ec1-e769-41a1-967b-9ebed4726c3b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Commissioning
408babcf-c658-421c-ba72-373217e5031e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing
851cb0f7-db53-437e-90d8-f3293de79435 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB1
9160369d-7331-4172-9e07-371e9b143894 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB2
f866419e-be0a-421d-88d2-9f3b2fd86bab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB3
ce0ffd5d-d355-439e-b450-5473534852b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB4
c1157969-9dc2-47b7-93f8-9877fbf3e9e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB5
e8af8a86-2e3c-4e2c-9067-0dada55fea52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2407 | Mandatory testing | CB6
d5270bf9-8d49-4e53-8914-9611601e664c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408
a968eea3-60d1-4fd8-80a9-b6f1d095ffaa |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Leadins
558a7a8a-d5ca-417b-a6f2-d5adb54748b2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Roughin
8ea873fa-854f-4377-b3ce-b923daaae92e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Cut out
5ac62e67-44a4-41ab-8fd7-38825edf4c6b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Fit off
f62de778-c05e-4135-9fd9-54a86be01834 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Commissioning
d1c3f6c1-627f-4469-a2ee-0802304484f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing
70a8564a-a80c-4e3e-a0a7-b21807c01b62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB1
e23d9355-7fbf-413c-83d1-eeb56aa0a45e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB2
8cfef754-35b0-4f69-a909-b26fd42d1d74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB3
b3315f17-f51f-4750-8aff-dbe1c3af4640 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB4
c2223589-4cbd-441c-be4d-9c3565934f65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB5
fe44b345-02ab-40af-9d05-64449bed9ba2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2408 | Mandatory testing | CB6
d4e38446-9093-4f8d-bb0e-51ef05b29bac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409
6afeacf3-0d58-4652-bfcb-6f985bfd67bf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Leadins
90a59eec-720d-491b-8b10-96b7e92cf56a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Roughin
56543219-f352-45e1-b81d-baa3ae312950 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Cut out
e507d226-602a-4d24-a657-3f560fd6087a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Fit off
972bfecf-5f53-40ee-931b-68cf57c8e929 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Commissioning
00c5f99c-b26c-42e9-a8ca-8bdb39ed23ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing
15fc5d91-44cf-475c-b6f1-54eedd54abd3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB1
d5b80c5a-a75a-454c-a7d7-95a725f966f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB2
d9ac7fbe-d4f4-493c-acd7-f5766de6c017 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB3
689d8315-c316-427c-a915-79cb78c70db3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB4
d8a90ee1-be5c-4cc8-acf7-ee5b882069be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB5
1f99ef80-15c8-43da-bb2f-eff11415fcd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2409 | Mandatory testing | CB6
33809e32-25ff-4047-bb5f-bbcdd59421fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410
49863346-90e1-4e07-8cf3-baba9babfa0c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Leadins
e93f355f-bd5e-4b69-823d-ba7e8129308c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Roughin
9a0e40ba-32ca-405b-aa26-40d9db3136ca |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Cut out
57d5fe63-3ae6-405c-a620-54dafe8624ce |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Fit off
456881e1-2912-4b76-ba3c-cc6c4953ee07 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Commissioning
087bd3a4-3890-4ea0-b067-ad753baa036b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing
13393bd7-bd63-4e93-9d68-9572b7b31d4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB1
af43860d-2630-4d20-9697-e5df6892f19a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB2
33740097-1b54-4248-a679-6d68ec6e39f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB3
ce645355-6718-495d-b4c2-8e1ae0bf9d76 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB4
7932164a-682a-43cc-8164-295a9a109b0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB5
1624efc9-d6ee-4a36-9b4e-8adb2ab217fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2410 | Mandatory testing | CB6
4d7fabcb-1a83-44eb-baf7-32b002e073fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411
4d5a1414-bbba-4ef9-abef-80095727da9f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Leadins
b1691ae8-5bc6-4527-b05e-22711d438a7e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Roughin
39083fa4-d46b-472e-9f8e-4e43afe20c38 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Cut out
1f49c988-7bde-45b2-8c70-43cd2dc38291 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Fit off
4f258ecd-e9df-4664-8fee-7be78a2d1078 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Commissioning
6131c0e8-1d59-4e8f-b174-0f33b0665d29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing
51ea70d3-4f62-42e7-b00e-196e27f565c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB1
5bbbdb74-de46-4f70-a9ed-8dba4745bc33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB2
5289fa69-bde6-4a11-abcb-fc71b1562bfb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB3
311acb76-25b9-4a03-8b9b-38d5f18d8d61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB4
95b39150-376c-40f5-9ec7-2b03213315ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB5
54332c99-0d18-45bf-9202-490e5e9ecce3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2411 | Mandatory testing | CB6
7d1bb584-9597-4017-8bb6-60b077414ff7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412
fdc95b0b-0efa-4c24-af2d-fc146f186cbb |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Leadins
d3af510f-1ff4-45c9-b443-7a5d6075dac9 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Roughin
830023ea-3fdc-4929-9c5e-4758da23089f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Cut out
7996aa00-1253-47c8-ad4c-d4b25b487931 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Fit off
53e80101-000b-4afe-b884-cdcb6f4e7ac6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Commissioning
b14f5ee9-e097-4d70-9665-e31f48d9600c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing
a05a7e80-653e-4f59-b93f-593d1082fcd5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB1
67da3cf4-8aba-4040-aea6-ec9857009f0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB2
a1d3ff36-9a66-4cda-8b9a-92d01c8dbe0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB3
d6727bb5-7744-4671-9c6d-ba50a837ecc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB4
198558ab-205d-47fc-bf93-74ee74fa8f15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB5
3074430f-eaa6-48e2-8f65-c8444e238574 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2412 | Mandatory testing | CB6
767f27d6-13f3-489b-9a94-e4a542f58b91 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413
1ac7ef8b-3463-40f8-90ef-68b7da0b7ef2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Leadins
a9cce072-290f-471c-9758-6931a0ab8458 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Roughin
6f92200b-7f00-4445-b92a-907c8f5abe96 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Cut out
14a88c3c-ca8e-47f7-97f8-9404de7545a0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Fit off
9c37012a-d20d-4d62-9690-1a2fcfb6e2f8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Commissioning
81c0a702-656e-4f68-83cf-bb39426559ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing
b0e9192f-c0aa-4dac-9609-d12476d50157 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB1
cb289667-d78a-45dc-84e4-0ef85327d281 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB2
28c2d1f0-3498-4d25-8c9a-64b89e9892d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB3
fdbb5c72-2884-441c-bfc0-c8da76fb8240 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB4
99fcab1e-5425-48b8-ae6c-784196a3a1f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB5
88ede8eb-9ad6-4920-968b-58fdc75a94e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 24 | Apartment 2413 | Mandatory testing | CB6
78a4aa75-296d-42bd-b3fa-862bd7b3cb3d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25
4c2a21dc-e0d2-440d-9045-843b377ca9f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501
4be51fc8-890f-4b49-ba32-6f54aac173a1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Leadins
cbc61fa7-1c1e-4540-a560-c66aae582be0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Roughin
5fe56f02-ccfb-4ccd-932c-5a2d73959d6c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Cut out
ee534399-b20f-422f-9971-c2c1fc46fb73 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Fit off
f3a76181-01e5-4eb3-82aa-c66928579f49 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Commissioning
7c8d27d0-1190-45d7-a149-816bfeb0f338 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing
d1835a8b-be41-462a-a6f4-ada77ca17fbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB1
1ec100c1-ed1b-48f5-bdab-42bbc9291f28 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB2
a242f721-87fb-478f-8260-c8e15d6b2b30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB3
82057393-d290-46cd-a0f9-4e5cdbd87a30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB4
b6892494-116d-44be-901f-5a67c3a47bce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB5
e121d48f-1c16-4c12-a0b3-3868eaa026af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2501 | Mandatory testing | CB6
eceedfea-4661-4580-8726-1ac80e23a638 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502
61607d59-f3f6-4e4b-8450-2b30ebbf05e1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Leadins
ad54ff2f-93bb-4143-a628-2106fbd4d5f4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Roughin
71692de4-929f-44a9-8db3-63286f672b0b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Cut out
b262ed7a-22e5-443b-9488-17dffb440e42 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Fit off
c4db392f-849e-450b-b6df-883ab90970a4 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Commissioning
c11d3126-1292-4fa5-a4d8-857019399fcf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing
6ff160a1-4174-4067-9f42-cd13d5092c7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB1
9647b49d-09ba-495f-9a40-40e7e3809d65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB2
f9c6c4aa-814b-4a6d-945b-d86e3f95bc9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB3
9c822530-bb8d-4caf-92e5-e73a2c9ffb14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB4
77321df9-1def-4cde-b183-9a1b83d2431c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB5
e41ec966-67c1-4fef-b3eb-1aea863bf6f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2502 | Mandatory testing | CB6
39ebf6be-6589-47e9-bd9e-1f0dbef8337e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503
70400e82-558e-4507-96bb-47b707ef0168 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Leadins
9cce62d6-8606-46b8-946d-ebcfbca112be |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Roughin
1d642e06-5975-4577-8a08-ffe9b09572a7 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Cut out
cad58cb8-5d1f-4f16-86c7-b76c8c0bb5ba |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Fit off
ef5edb43-bd3c-430c-97e0-3b5cbab767d5 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Commissioning
85afd7e9-5ab3-4fdf-987d-86816819bfeb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing
9227cdb6-d7ce-4d93-bb45-c395e15ff0a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB1
48db7c10-78c7-46e0-8a05-c88b8ea9d68c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB2
25c273f5-cb09-4ea4-a7a4-22d74a8e0dfc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB3
abbd45e4-e439-4a0a-aba7-1e35cdb7ea37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB4
7aaa5e51-b6f0-4e0f-8745-162bac0db635 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB5
15df3d81-740e-44ec-a27c-a2102fb9ff26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2503 | Mandatory testing | CB6
fc9d8b63-fb1e-459f-966e-90222d9b7fb8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504
04ece1b6-4cb9-40e3-b18b-755ef965f404 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Leadins
515e4728-4b2d-41ae-9498-950f39833f35 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Roughin
dffcadc1-ed69-4743-afb4-14b98e079774 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Cut out
63ef45f8-6c96-4f88-a9bd-586a7450eda8 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Fit off
9c79c688-685f-4cc4-9814-ea2c9b3d553a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Commissioning
a5a74215-486e-4a20-84b9-66cbbdca9d69 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing
bcc2f516-a13e-441c-a72b-3d529e5a3ad7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB1
14a62f76-112f-459a-adb4-a12b39bd8fba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB2
d7db7f9f-4699-4673-b30e-f30116ed94e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB3
cb058ee6-8cd1-4228-ae01-57236b4f3cf1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB4
a11992d7-cf30-4cd4-9e19-932fcc229217 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB5
4e75cf94-6566-4458-a3fa-056a49d116aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2504 | Mandatory testing | CB6
eae69478-cb56-4a2e-997b-72a0d0279e4a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505
8b315fc5-c8c5-4b60-89a9-63d6ae955c0d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Leadins
8a28a825-ee4b-4ccc-81f9-fd15219fb48c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Roughin
cffbb63f-0929-420f-b9f2-2bfb72ac6bf9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Cut out
ccb99305-9d95-49bf-98db-127e4df1a120 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Fit off
ee120e3f-4861-48dd-9ac6-779935060e66 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Commissioning
90b5f23c-73b2-4a8d-a9bc-2b7c5a7837f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing
73e8fcba-2e4f-4c97-b35e-ac45df07cc2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB1
171871cb-6ea6-4bdb-9e0c-2ac1c7305eb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB2
72494ada-7f42-4d2a-93c3-ab05986696ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB3
b9107974-e457-4866-8108-1dffa353e964 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB4
1aff681e-1177-42df-99d6-0f60f613bcd4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB5
9ebadf8e-7588-48ec-82ef-5107a6d4d971 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2505 | Mandatory testing | CB6
15873582-1b59-4501-8941-8afd5f1c4d5a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506
75d17f42-e300-472e-86aa-5845a6ff35e3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Leadins
148e0383-e4bb-4931-a24b-78d65ea1656e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Roughin
4142cbeb-536b-447c-805f-6e2335b76637 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Cut out
f38b5a76-46d7-48f3-9849-b26099d0a6f4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Fit off
46dfd645-f0a7-4691-a2ad-10c376eb1b33 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Commissioning
5bfc7849-9ac9-4dbb-a497-f2fc50bb97bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing
c3a2eb17-f89c-4357-9cc8-f9a65b4fecee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB1
e1e458dc-6195-4928-aa9b-c46b7731a89d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB2
b45dfd14-5cc9-45e3-923e-f1e76addb5e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB3
9b75f48f-5dc3-45db-af55-784cd82aa6d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB4
3b1fc67b-c10c-4fcc-99c9-149159a6b203 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB5
8534f54d-a8e8-4bd2-87d4-8db8af9b0b08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2506 | Mandatory testing | CB6
026fcdf4-ef27-4e95-a872-f838ede5bcfe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507
5e6cf57b-c9cd-4e2a-9270-8165a6eb8c95 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Leadins
5e1e068f-c3f9-4f35-85ca-1277fdb05793 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Roughin
885e088b-dfb4-4b5c-9251-3d90f2a81d3f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Cut out
649d3e25-d9a1-42e7-9065-7ecc8580cbe0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Fit off
0b5df007-57dc-45a7-a467-4d518c39a45f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Commissioning
5ce0a3c0-fd26-4dc7-baea-261dfbfa8dca |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing
f30b4b17-2a42-4cf5-b7c1-0e09e1d2779c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB1
3e615d2a-d61a-4579-a76a-cd495f9f4b1f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB2
45adfbc6-b856-4c4c-b115-e8120521e21a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB3
f6c161b2-11a9-4f50-b968-d5d76ff5e209 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB4
a798270d-61ae-4168-960a-b7031f59e598 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB5
2f342a2b-c33a-49e2-a499-76e5114e84e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2507 | Mandatory testing | CB6
1566191b-ffc1-48ff-918c-1be8989ce6fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508
9840dfbc-7bc5-42f7-999d-bc461ebdcabc |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Leadins
40494eed-4f00-4830-ba0f-11fc5709fb93 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Roughin
23766c74-d2a6-4184-8915-871df940df9a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Cut out
e463b1d5-2fed-45b8-99cd-16d6d27ae499 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Fit off
679d5b59-60b3-487d-a3e8-d87be8d5abc1 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Commissioning
122d7968-04ea-41c3-9aef-73cc137d85e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing
949cff30-72a2-45dc-a065-8f9d436514a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB1
369fafb5-1a72-42de-aa26-44da79bde8c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB2
d4707f10-959c-4524-97d7-62299b6782d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB3
5bb05e0f-deb9-4ac4-a098-d521c667fcbc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB4
79df6ba7-4ebe-40f5-808b-d1f32987166f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB5
7d09cb76-19ee-41cb-a7b1-909683dbcb89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2508 | Mandatory testing | CB6
e2d333cc-9102-4a55-a873-cd0c304e4a2f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509
ea86e1e0-30f8-4c93-a021-a42dc391fac9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Leadins
8a5a1cd4-ad83-4e13-8722-48dc157e5ebd |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Roughin
86600c2d-38c3-4058-8338-113b7c62e6cc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Cut out
94274774-41ae-4713-a19e-7eb923c44a0a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Fit off
3d54e3f3-6c5e-41aa-862d-c37fbd091905 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Commissioning
f8de9fd1-67d5-404a-8eec-00b6beab152c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing
01186bb8-bc8a-4579-960d-9d2f1bc80b4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB1
cabe9841-cb52-4454-9fe2-3889d66ca9cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB2
c140be1c-7620-46dd-9cb8-accde751e69e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB3
02024f3c-d329-417b-aad2-02505a476143 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB4
0f3b68db-335d-412e-9a6c-b26ef0bd4626 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB5
a8d7af88-eadd-4b8b-8d75-336905c8ec62 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2509 | Mandatory testing | CB6
7d5a9689-af34-4f2a-9945-478e153806ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510
9759ce41-97ef-4bbd-812f-5f89007a11d4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Leadins
66fb37c5-d32e-4b4e-a531-8a1bd781a7e3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Roughin
fa31024f-c4f3-4323-b937-b270bf0943df |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Cut out
5f6f13bf-4183-4833-92cc-797181208ac0 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Fit off
69a0a302-a217-4703-8190-3a6f91c8ebd9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Commissioning
fccb8740-340b-4537-be3a-6010e5fc7adf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing
72e2bf96-638f-47cb-b1c8-b36580e22147 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB1
1eddd6a2-eb22-4bca-856f-d4c3e5519ca4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB2
f75656d7-f64f-4bb3-a308-aaabd5f3e441 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB3
9e9219f0-568d-4463-befc-b5ccfbcb011b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB4
53bc73cb-870d-4bc3-a66a-cd938a037d6c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB5
75acddf7-59c9-4232-9f9c-f999963065ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2510 | Mandatory testing | CB6
08aa258d-32db-4e80-b134-e7a37464f5fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511
6a43d1fb-5c03-4744-a462-7b4add167d0d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Leadins
38fd6c0b-9b18-496d-89a5-4b33910770b1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Roughin
73e55b2c-abfe-4545-9d15-16113f11fddd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Cut out
ca380d98-478b-40fe-a8a2-e1230802fefd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Fit off
c5c18dbb-d58c-416e-a767-364b4144fc21 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Commissioning
5c6902e6-7790-40b1-a3c7-671cf6efd82b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing
c45f6de9-72d6-476c-a03d-c2e4c76c1e01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB1
d070430b-d537-4cf1-a6b4-7fa203b587f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB2
58fa792a-80e6-4cbc-be78-67563d178f44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB3
c7318b75-1d60-4334-8e53-d26e952406b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB4
52f92871-d7dc-4830-98f5-8b608013162c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB5
0f3ce862-81d0-450d-8fb8-993ca2f4e380 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2511 | Mandatory testing | CB6
223a292b-fa54-4f8e-b6b3-6660c11b1779 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512
b5b46243-afbd-4b1f-a9f6-aa12d434fea0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Leadins
a790a9e4-425a-4524-af62-c0a048d98897 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Roughin
356b9327-1d42-4a61-bf21-acf52d663f6e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Cut out
5baeefba-7955-4282-8302-acf2a831bd77 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Fit off
d603ff86-c21a-4655-b8f0-3870c937045c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Commissioning
9a8dfe0d-40b6-48d5-8cb1-74be7c4f67db |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing
69fa586b-a80c-428c-8ffd-6a7328448aa7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB1
de5c8096-42ae-4654-9ab8-734e414fbb12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB2
b64f2e37-1c83-487a-a514-696170b209a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB3
49e35f77-6bf1-4565-b395-baf0f3a04fce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB4
012d4dde-2c92-49b2-a5ce-2a911b7df6af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB5
7d75fbd9-49a9-4a9d-a966-a79294b562bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 25 | Apartment 2512 | Mandatory testing | CB6
5a5e623d-6a7b-42e0-bd11-780cf4143b52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26
00095aa1-ad07-49fc-bf34-19a023de7a0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601
0b3d6728-bad4-4700-8305-7efa230fa0e4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Leadins
7dd34ed2-8a77-41b8-a9d1-4b95f322004a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Roughin
4a1d0209-79d6-409a-8c66-3743182458ea |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Cut out
8f8f5a85-51df-4435-8880-d31c2bbf9fef |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Fit off
9f518f82-665f-41c8-912e-f1b646ba1063 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Commissioning
ce1c6dfd-78cc-4551-8853-a4debed54db7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing
0013375c-a6d8-4458-8340-396d46e62ce1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB1
f5cb79df-5966-4863-a500-9b430481d342 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB2
6fb61d06-4f4c-4e57-a48e-423d48ada317 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB3
8a53a826-e679-4b7e-a9ae-f6a676868117 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB4
e8e99550-a3e5-4f29-ba27-e6ee4ee1ae84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB5
392cfd28-c8b0-4105-becf-c9da62d7c74e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2601 | Mandatory testing | CB6
c894c0e0-e3e6-4a24-9cd2-4b636bb7fbd7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602
c8643be2-b9f4-491c-bbba-ab0542d8b030 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Leadins
a8e6e950-78bc-4f96-b5fc-440e1743a945 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Roughin
720cb4df-4183-4d41-b8ef-cbde5da1d560 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Cut out
d84c67e0-0800-4486-a5c0-cf41e98e8aec |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Fit off
d23fdd4e-8768-460f-a108-fd773e67587d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Commissioning
ec9bd836-a743-4bb6-9f12-9af0a3aea207 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing
48bcd224-e662-4384-9784-8d26ffe74252 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB1
14345241-8435-447e-bfb2-ed6c869d9598 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB2
958894ab-32ea-4efa-8587-54f9a46e8600 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB3
72047bfc-2739-46fb-abf9-c46009060bf7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB4
83f9bb90-4b36-4225-86e1-d53ebb52493f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB5
818bc20a-d7a1-4a14-a1f6-7876057afc35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2602 | Mandatory testing | CB6
a3105e9a-c44f-4098-9280-cd00a4bbec09 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603
f4a8e35b-bf10-45f9-9c02-2d5c813689e4 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Leadins
8ddd040c-70ac-43d9-bb68-58b7300a8f4f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Roughin
130cc820-221e-441e-b6a2-fb1503bb5fbd |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Cut out
10742d33-902c-47ef-bccd-4b1a9cc18156 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Fit off
22156dab-6be0-4fd5-bb88-a196540e755d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Commissioning
7677f405-96a1-4ce1-993b-837d9a518d6f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing
1836f6c0-64c4-46b8-aa94-0914b6c37def |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB1
8c0f972a-72cf-42da-9f14-69667b7e36de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB2
4bad73ac-604e-4d7c-9f43-81fe855be342 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB3
ed14b821-3178-4c6f-af04-ea49071129d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB4
7a5db930-7033-43a7-8d45-a33e39181006 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB5
62dfe3be-9369-4230-8de0-b0437f02b38f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2603 | Mandatory testing | CB6
683871ed-ccda-4871-94e9-7bba7b89f322 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604
dd5c939d-18c7-4bd6-a905-b95f77e48076 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Leadins
c81e24fd-1b47-4ecc-b61a-b1664d134729 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Roughin
45e44bc4-fe65-43a6-be46-91cf31781751 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Cut out
45c1b237-a1f6-4fbb-811f-6004b7387974 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Fit off
7b99e5fb-ab81-4bd5-bb1b-cd74ffa99029 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Commissioning
22a66600-5f10-40e2-9112-66d7f30503da |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing
9c0d084d-349c-4c28-a750-914129190909 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB1
56bb8793-a640-4d6f-b536-9a8e7edae002 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB2
149a2173-10e3-4bb8-96dc-5b19a4937194 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB3
f80c51e0-84d7-4815-a7c7-2ce69aa56409 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB4
ae6ed151-5ce9-488f-84a5-a125dd171b26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB5
9b35725b-5800-48b1-a0dc-7258228e8d54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2604 | Mandatory testing | CB6
676eb8d2-2a32-4b41-88c0-529ff4f9d849 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605
7485c21f-8485-434f-90cd-fd9a4a2c04d7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Leadins
49795f67-992e-4868-a425-60269c3f3f90 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Roughin
4858cca0-54e1-4974-aa84-8182267ccafb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Cut out
6be59c29-8bcc-4d25-8cf3-a8b71460319e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Fit off
bd4a8f6a-47eb-4ca5-9d9b-33f157764dcd |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Commissioning
77b85846-d612-48b4-b171-f2aaed652492 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing
a1a9cad6-284a-44b2-afd7-46984abf1f69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB1
230eded3-ad3e-4fb5-b5f7-0aa4ebb29fdf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB2
8e3af1ed-0914-41cf-be9d-581cf8b40685 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB3
32825a06-5282-49b1-8136-5131cc4bd674 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB4
3702fc18-c83d-4fce-b8b5-0fca237b105f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB5
94d11b50-0bbc-458f-a91b-cc28b4ed6075 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2605 | Mandatory testing | CB6
c35d458d-0447-4ff5-b5b0-ef510d5aad78 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606
71ee5bf3-8eff-424d-b800-91c4bd5c2fd0 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Leadins
80809790-243a-49fd-81f6-6f7154b0fb21 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Roughin
4ea0b859-fb23-4116-9e09-71c6200636f4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Cut out
81c99572-48a5-416a-adce-04950d150339 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Fit off
218f29f3-13df-4618-8c5a-277366f470bf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Commissioning
46a54824-ddea-470b-8f55-047fea6d3360 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing
2a91da11-6d5f-486d-8fea-71a91e657e1d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB1
d617955f-18ab-49bd-a44b-acb200d89fcb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB2
31121fb6-bad8-47e0-89ed-4e291c747bb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB3
8284a668-94f0-402f-b1cf-133b42f19293 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB4
0e23976d-871d-4b20-bea2-c35277cb8ba8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB5
e973a54f-a812-48f9-9bbe-b4f8ae1eaa3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2606 | Mandatory testing | CB6
ce6bd3ee-a580-4e9b-a86e-194b526f4b63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607
24f01574-ef3b-42a9-b508-637f517580d9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Leadins
140d2585-9c5f-4405-bc16-f50cae28826a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Roughin
bbd702bf-c2fe-4587-a331-c313d755376d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Cut out
98507b35-3b9d-4ddf-85d6-872cc749b7d1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Fit off
65ba8581-c70e-41dc-afd9-975b5475caae |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Commissioning
386d5a74-c4ee-43c2-a6b1-9aa465c88ba2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing
8d963d48-86ac-4f4d-a93d-02d2af61e997 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB1
c7aad2ce-ec7c-4ee7-9066-3973ade26291 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB2
7fd76fc3-1c7a-4e42-bdd6-babac9040e3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB3
2da6b059-ffab-480b-bebf-0bab0752805c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB4
d4d4ce21-bb84-4768-a7ef-b7aef1f3e9f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB5
4ad8b8df-fe85-4791-970f-81301a74d7f7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2607 | Mandatory testing | CB6
d34b5c99-3c7c-4bd1-bd74-d432eb1567ab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608
a14f96e5-5c03-4840-b7d6-f26b55a36dbd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Leadins
71232164-35c9-4d98-805c-80731e1c215a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Roughin
088caea8-3a6f-4340-bb54-563c94bdab46 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Cut out
35f48421-7507-4f91-aae7-636d385fa58b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Fit off
ba5e59ac-55a6-4dc1-a7ce-0b931594302d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Commissioning
db98b0e8-4b9e-4bb7-809e-dd857cd1e5de |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing
f1777f6e-89b6-474a-81dd-996deac66f73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB1
a5dbc4cf-c90a-410b-9b0f-e1b98bd52949 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB2
d5f7eef5-de7d-4ebf-b106-33927d126285 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB3
369b9418-77ef-4d1b-9b3a-3ed2bb91ebdc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB4
7a9c3c3c-c3f4-42b1-a0d6-d5fd06852b19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB5
7614266b-1479-4875-981b-6d885c70c8b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2608 | Mandatory testing | CB6
1c274aed-04d3-4aef-bfc4-83dd633331b1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609
2755aaac-3362-4d94-82ef-cd226caf191b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Leadins
de83847d-a788-4ae1-943a-eac0ecb0bb10 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Roughin
23381e1e-6dd6-4aa1-bc19-0280d734de8f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Cut out
2e6b404a-f450-4f29-83ec-5493a8cc9291 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Fit off
b5f895c0-bf09-45b0-a799-207331eb072a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Commissioning
ea9a67d6-e95e-474a-abbe-5725248a86a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing
1b5d5e75-e16e-414b-ac75-840fe204d700 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB1
a3d445ed-f501-4310-84c1-8cde30a5feb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB2
e11d5c6b-eaec-4d81-afdf-1cc3eae0da57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB3
d2d0d8c4-1a61-40a4-aed7-da2fe970799e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB4
979df94a-5992-401a-af15-782ea5c9820b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB5
bc632dc0-ab08-48e6-a5db-c11656d4e5e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 26 | Apartment 2609 | Mandatory testing | CB6
48b552ba-ef73-41d6-941f-cb26d391ac87 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27
f6bc2aa3-d03b-46ae-b240-210c3fef3cb3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701
82425e7f-3308-4faa-8041-5ae0faae6d66 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Leadins
0d82f818-f7f6-40bb-ae1f-b5017b93c83a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Roughin
3890c5fa-c379-4c0e-bdef-798fc4bd2e0d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Cut out
f6aad791-c721-421a-b264-40dad0c45865 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Fit off
30bfe104-4b2b-410d-bbe4-2a5c4c538419 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Commissioning
17bcba75-06f3-4cfe-b8c1-0d76653b8bd6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing
8b7b98bd-f1ce-4ab7-b6e1-f73bfe126cbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB1
6b86bae6-5b2f-4d1e-86a1-e8ed97993125 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB2
f9a8f104-0d0b-4827-8332-b88bb416098b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB3
a47e03e5-3749-43fa-b47b-c4401e5768e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB4
85499167-f5f6-46e3-bc77-1485eb5dccbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB5
c5afc72b-2396-403b-9028-8823f2f32d79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2701 | Mandatory testing | CB6
039f17bc-9217-46e2-9651-f1be7c2c969d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702
582159ea-8a7d-4dda-8f28-78302e8cd293 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Leadins
a9715560-ef9a-4903-a8e4-ea55414674b6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Roughin
855a60b9-c291-4696-bbcb-9c4ee3cd5066 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Cut out
af928416-df59-43e4-b44b-1702c823c608 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Fit off
f619115d-472b-460a-97d7-abeb668d164d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Commissioning
bbb11c72-dde5-4ff8-ac4b-999144e4bb0e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing
6b5a04df-182b-46d3-8b82-abe7d52c0844 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB1
9a3a4ff5-e4c7-4a34-97b2-6aa0e8194e97 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB2
3c40c1ac-7d27-4a70-a3a9-68b17aba972b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB3
d53116d3-9a86-4f85-a584-b10f5e9ac90d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB4
30c94364-ae69-4923-a886-9b34250de3b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB5
5594b864-b8b4-4ffe-a474-fe564e66ef58 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2702 | Mandatory testing | CB6
bc8b29e4-8837-4697-be46-3d169d37d00a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703
fbf659b7-9b7a-4c57-97f8-b0798a9ce4ef |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Leadins
933ee582-4bb6-4702-ab81-808efecfc95c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Roughin
e6f9025c-33e0-4f7f-92ff-60bd9ef65305 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Cut out
1b816468-921f-41fb-9c42-56e0344b0484 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Fit off
26169fd7-d96b-4501-a4ac-b15e95c8fb8c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Commissioning
d76117e7-ea84-41a9-a5cc-78b748d786f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing
a6eb80c0-0761-4fc2-aae2-5298576e2e72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB1
f5f7a93e-4bbd-4eef-bebf-04c44ae6b6cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB2
f4d491f8-0a44-47d5-b6a5-2a66d70a3b78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB3
60afb580-ed1a-4999-be8d-df43b7835726 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB4
51196714-ec01-44c0-adf8-14d452a91597 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB5
a66f28a1-f04f-48e5-a43e-9aa5dc717c1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2703 | Mandatory testing | CB6
3da76f47-d280-4c51-9827-74323f744df1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704
3c6228b2-dfea-46dd-bd30-3a82c9249061 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Leadins
6de0abd4-b6f1-43d6-9916-00a3b2fa1cce |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Roughin
7bba4520-ef99-433f-ae84-5faa69138798 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Cut out
18bc503e-ec72-47c7-9742-0b32320ad4de |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Fit off
71cfbaea-c545-4317-ae61-589cda13f10b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Commissioning
7561ef85-e84d-44f9-ae76-f180426cffaa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing
5c70a0ce-0332-4b15-a00f-e5446ff66425 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB1
4df1f4ea-3e37-4fad-9c0b-f23570a4c0a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB2
fe06c0a2-fdc9-4d30-b154-cd135ac3cb2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB3
7d120bcd-a31f-4896-99d4-ad2f03a41f12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB4
5a6304bd-c320-4a4c-8115-bd87a232018f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB5
ecdc1178-f4c4-4524-985c-7d43f958e061 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2704 | Mandatory testing | CB6
06d2fc41-c066-44d2-8e88-aec6ee69a44f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705
e7ea365b-dbe1-4563-bddf-37746677ccaf |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Leadins
6d40c56a-6ae5-4e7e-9c07-2ef8e1a22358 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Roughin
4bd25d8e-7b23-4647-be5a-86bce61a52d3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Cut out
e5a7e51c-7f26-408b-9378-f6725f3d049b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Fit off
f972dd58-12df-4bd9-9b1b-197b3b453c64 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Commissioning
1d5f89ca-2eb3-477c-809a-f58e31b84f1e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing
8fea3651-e62a-4a7a-a567-5036fa4a74e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB1
13b9645b-f333-4d7e-a7a3-c0262ce7eec3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB2
5eb4c3d6-4d39-4a3b-ac00-eafb2f7a0a02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB3
bc5a3df3-c5cc-4572-98e4-af38620e6d3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB4
c24c986d-8938-4116-b902-8cb95d19ad90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB5
c5c5819c-41a7-49a6-8990-bbbf84b40f23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2705 | Mandatory testing | CB6
a4b1ac53-be56-48c2-97a4-b2df7ee3eab9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706
29eb6364-6cbf-4d7e-9887-362c3fd9f36c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Leadins
420f33b5-cf2a-47f2-b7e2-54da7a28c115 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Roughin
9a81d7ee-3edc-4e1b-99fc-226d0c92fbe9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Cut out
907f1af2-8e46-4e09-ba75-c4214c88d449 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Fit off
0607db2e-e06d-4218-b8ba-145e8d635ad0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Commissioning
9f291693-3aea-4359-ad5f-590bb3bf0f41 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing
8ab6a4d3-96e7-4444-8ae3-e1c13ab682d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB1
2320233f-9e28-4930-a9bb-5fd226c52f96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB2
0665956a-84ca-427a-965d-acee10086564 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB3
54a4f14c-6580-4ece-9266-d65d5a833870 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB4
e680e041-031f-4649-869f-c6be24533600 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB5
fa54d8d6-0ef6-4adc-a7bd-fa874eb6fe73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2706 | Mandatory testing | CB6
bd15b7e4-48d2-4535-8268-04948da5609b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707
68e6371b-b732-4418-9d95-7e89bdf7185d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Leadins
bf7c9e78-448e-4273-bbb2-3308760d539d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Roughin
f13c1b30-38d4-4488-be2a-2a5d7cd44719 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Cut out
8fbb1052-14ce-48b3-830d-5901484f1127 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Fit off
559deb81-f879-4f7e-9b1a-a291d65705c8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Commissioning
3eb311d9-1288-4368-a1d9-2cc893db50a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing
3bda631a-55dc-4e70-b70e-32647656358d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB1
94cdf894-dcab-4623-ab64-0c54ad62ecaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB2
ffa57b31-4c48-427e-b80e-dbbf5d1e80c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB3
5c9156f1-b7f9-40df-9e94-edcb84d1081e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB4
fd21967b-bd74-4abd-a456-baaa797286fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB5
1f04e764-67ce-4d20-b517-3e5f76bf2705 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2707 | Mandatory testing | CB6
35f16602-9d7b-4a60-87aa-cbc48d491c44 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708
ebcad7e3-0e2a-4aaf-960d-42aaa2932a41 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Leadins
ef0e0265-1c75-4ffb-a634-3b5555519753 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Roughin
65922e16-7d9e-4711-bdaf-665cc7543c5a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Cut out
a3922a93-a64c-4d11-abdb-b0d85e653da2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Fit off
1e6ff4a8-dff0-416e-b1bb-c71592a5ce27 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Commissioning
8d2dd5d5-d728-4b81-a392-62b8eaf6d3b4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing
b659895a-b91c-4ab8-9dfa-9feaf202cd29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB1
60348ce3-1ca1-4421-9fd2-4c32fe74c4e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB2
b64e0f4b-1a2c-45ef-bb60-1003a0360537 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB3
f0c7f18c-b46a-478a-9f46-667aea479636 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB4
0f912fd3-2702-4804-a63e-59abc3376b87 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB5
fe823e24-9a09-41fe-a714-4cf4120bc9b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 27 | Apartment 2708 | Mandatory testing | CB6
ada85008-897a-4b37-8e58-106c39ad7423 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28
888f0aef-550d-4736-9b65-dcbb6df22ed1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801
313c00d9-1d66-44f3-bd47-eb78c490767b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Leadins
75bb2c7d-2373-41ee-b5de-af81e6215bd6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Roughin
9e70f802-2ce2-4bb8-abba-6f431372c175 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Cut out
af1b6293-f744-401d-b429-8a9e0ff1b6e7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Fit off
ed5a7c26-5062-4af0-a504-976e24be28ce |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Commissioning
dbcca097-54b5-441f-861e-cb7a1ee55760 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing
27fd1d79-548f-4d53-9523-d816e8b5ce37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB1
1680deaf-6543-4681-be33-c83fa713cc80 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB2
e7bc677d-c18e-4955-a0ca-5e83f0b88ec7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB3
66e46eb3-0f04-4456-901e-7e2c60cf2ba4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB4
6051fe02-056f-4071-bc90-d43c434afedc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB5
bf9eedb5-42a7-4320-a963-c510b2837fca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2801 | Mandatory testing | CB6
af64913b-d80e-499b-99d9-37272914f549 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802
b426f995-8b4d-41aa-a4be-91a88f3435a9 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Leadins
197039fe-1ba8-48de-94ab-bf25483c71ea |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Roughin
295035e9-7055-4758-b44b-3f1265707e4c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Cut out
58dbc6d8-e98a-4f05-89d5-4735fe5c3d1c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Fit off
21343e61-5092-4224-809a-c99bb0e79704 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Commissioning
391097ad-a307-418a-92b7-26b6acf34047 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing
c9a1ecbb-f4b7-4654-bba5-c90f4ae70b39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB1
094945bf-ef35-4c00-b660-a260724138f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB2
24c97f86-5d3a-4946-a46a-d46bef0c2d15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB3
10e37025-fb67-4fd1-a6d9-422f3b0adee8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB4
b23c324a-f813-4541-a172-1e47b762a344 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB5
7bcd08b1-673e-467e-abb4-b56ca9730e93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2802 | Mandatory testing | CB6
197407e4-ae70-4059-9041-ddc622b15c00 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803
0eb6d92d-91a2-4a01-8bd1-07e69f30dc33 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Leadins
3f748022-4b8b-4ae7-b543-4b6b75fa3be1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Roughin
cfe33d56-f676-47d8-bbd6-23ef9ecd35e3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Cut out
71920094-542d-4884-9097-62d05bc5ec6a |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Fit off
6390fdeb-85f0-4ed3-b8cf-5d1005a576c6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Commissioning
62456ab8-06ba-4736-9234-e4c9f0604834 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing
63a31d4d-bea7-424a-898a-629eead7390b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB1
1fededc6-20b5-426b-89d8-ddebe5b6e4ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB2
b1f5bab1-f0d4-479f-8571-4284cfad7140 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB3
f48d6059-e341-49a6-ad3a-dbee5bc27a12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB4
9c5c33a6-d457-43c6-ac73-58ffb5191de1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB5
43eeccd9-6b5f-4070-b833-0f622c5b2590 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2803 | Mandatory testing | CB6
f9290a0f-7741-4686-9f19-0076980ef540 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804
469cb2a9-7a9b-4081-8519-f043db34489e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Leadins
4a9605b2-418a-48e4-91f2-cda0a0df1985 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Roughin
ce272717-2a12-4c3c-99ca-efd681ebc926 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Cut out
a17ad34e-0e80-4cdf-ba91-e7579e355da2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Fit off
152766c6-cbae-4727-b175-f47d44e2efe2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Commissioning
c56a4469-c0ff-4178-b18e-705f14462a42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing
a9725e33-d4b2-4969-9435-abe52cc24602 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB1
c53b0272-ed56-452e-bdf1-ef0d76b232ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB2
11c4d479-d697-46f9-a74b-f40db185fe41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB3
4a7c532c-9743-4c92-8284-3ceae7a3fd0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB4
c7cb5909-4686-419c-bc6f-7fd34cd6fc84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB5
ad6d92d0-df52-46e1-b6ee-d0f8c068bc30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2804 | Mandatory testing | CB6
e338c165-a8b7-470e-b8d5-130fd049bc05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805
1f4491b4-aa11-4855-894c-15e286bfa506 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Leadins
8e56b172-24f8-4b50-8237-aaa1d37cbb2c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Roughin
d4b93ba4-75b2-405b-9c0b-6f3c4195e9c3 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Cut out
8e5216ef-b477-4b3a-868f-b774a976a3fa |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Fit off
2d290d8e-c558-43ee-908c-82b65d3c27aa |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Commissioning
12c659f4-e681-4a30-beb0-826267cedd84 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing
0d3766e4-6323-4086-bb44-780508ec179b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB1
39952eb6-c988-409f-b96b-9c35d1222669 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB2
701d527d-1cfd-44e1-a0f6-c80ce5f4efb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB3
9fb2b6d8-b1b8-4b58-bc06-85e2c575484f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB4
a7d006d3-ad0d-4b3f-bc96-d85a7d4a944d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB5
c63c8e25-019c-4b65-9e02-08574807a066 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2805 | Mandatory testing | CB6
bce85813-43e1-4a10-9cfb-5abf1c6726dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806
ae75c3e1-01cb-4233-b727-bdcb4b450b85 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Leadins
5b1e0bd4-62f5-40fd-bc65-86eff80abf82 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Roughin
2fd68c05-52ad-4ec5-86dd-7c2214b21a60 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Cut out
f6579390-19fb-49a0-b429-44cbe7a2b7d1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Fit off
c701248f-e839-4a6f-8e91-0e926fa10a60 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Commissioning
dd1b233d-3073-4f33-9f2c-326326eba424 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing
a5ba1fc3-2107-4aef-af21-1b26eab9013d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB1
041ee9d7-8bee-4e5d-80a1-4c502d0ea9a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB2
05e9fa4a-b345-4a6d-b669-79037b5fba48 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB3
dc368116-b223-4041-9ba1-1a3098b7d265 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB4
cfa6a295-f2c5-465b-a758-4f7375cdd27c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB5
646eb849-c2c1-4ca6-9c36-88b257f90888 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Apartments | Tower 2 | Level 28 | Apartment 2806 | Mandatory testing | CB6
2de3e0b6-f76c-4b21-809b-adf11e041313 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas
edba8734-b711-457e-bdc7-f48ab3b4db00 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits
5349b083-537f-486b-9d12-d197a23a1025 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3
3309ba42-5175-4026-bc04-40a59683b06d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1
91b28c26-5057-41d4-96a3-8a68f1e498c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1
6a4ce0d1-54e0-4bfe-bc77-551a5c6bb693 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-029 - Rough-In
11be282f-f9a4-4c8e-9055-cab24bf1b0ab |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-030 - Cut-Out
5daa3892-eb24-43d7-a236-fbb606aa25cb |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-31 - Fit-Off
6cb7bc5f-e5e0-4437-b06c-ebf947749327 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-018 - DB Fit Off
ea1f2c32-8c14-4cfd-9348-c6ef82c1c86f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-32 - Commissioning
c4f8c18c-186b-4c9a-b05d-5ea6ab5d5271 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing
260e0f97-9f22-4f20-a4c6-c2bc818da002 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB1
db9ce934-039a-413a-86d7-15bf00cb5e1c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB2
e493e73e-4301-4d3f-8572-d168ec8af1b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB3
f2e08806-e70e-40c0-b99a-9620317692f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB4
4e0503c3-c51e-41cf-b11d-bc074cf9dfa9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB5
0a1c8dc3-f1a5-4706-b3b5-b2ff4c334177 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB6
be0a9663-042f-4f03-8760-2de38049cefd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB7
2659e7a7-8758-46a0-be85-363a4dbf2ef6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB8
a074536d-b0d1-4fd4-833c-c9106f32a9da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB9
b33c1e89-5ca6-4fb4-a738-bb84e897c46e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB10
a27cb712-2de3-4a73-a197-ad5e17b88395 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB11
89ba4fe4-2027-48a9-8441-3669b4cd3329 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB12
395a493b-f828-43e3-95f4-8116c42a3aea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB13
46451dda-b60d-4778-b8aa-2e80412316ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB14
aee7413a-184f-442a-8f95-093341745015 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB15
cbd84952-d6c9-4cb5-9724-b963491cf929 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB16
609fec01-61d1-457e-b92e-6cf18431dd69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB17
c8884914-5e33-49eb-aa16-70cdafdd5396 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB18
3d2728d8-ebee-46bf-994f-7966ff84fdcf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB19
960cf878-f296-427f-bc85-10e2a88630c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB20
6d0c8ce5-bacb-4854-989c-05e87de10ee8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB21
113bab38-0c3b-4cfe-aab9-fcc984d4d730 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB22
3d96a52c-18e0-43eb-bcab-9e8d404495d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB23
383dcadf-bccc-4037-ae2c-af160fac1d1a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB24
0b75651f-b729-444b-88a3-17d4c96456ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB25
50a1cd3c-972c-4526-aea5-49a9dbf0655a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB26
2d6af34c-965f-4bb4-9083-f1edeb3f92ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB27
6afc1428-9ccb-40d6-84e3-f41c046564f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB28
0335b4aa-eb70-46a9-9d6d-82e09db9f444 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB29
3405fcf8-13e1-47a1-b790-ae17932b469a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB30
4976b6ff-dfef-47ed-b4f4-f32d4e7f8ae7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB31
974b3fa0-ce76-45bb-b4f9-e4e444fc5d60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB32
9107437e-249b-439e-91a8-16523b76e886 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB33
cab1d3a9-a38d-4e00-8e0c-5cf260d1fc1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB34
9a535187-485d-4e56-9c13-1fc3cf5775e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB35
5d79171d-382c-405e-bde6-8f70424ed194 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB36
0e40e821-fdf4-4217-af46-2c263e0ea89b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB37
94a73de7-e01c-4340-bf89-4f4dd3629413 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB38
ca26e6ed-2e68-45e4-b148-c51a2772adfc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB39
ffe48e82-84f6-4c70-8219-3924b4a6fcc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB40
5c2526e4-54f3-4618-8830-bce723ef2cce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB41
b899f56f-fe13-4d3e-96aa-5cfafe227d01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB42
28425696-c248-40d5-bc2c-115a693cd154 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB43
6be433ec-bd9a-4387-8272-2b2cb0eea4ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB44
68cb3a74-f7e9-4b00-81b3-df7a292defbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB45
7348d0f7-ab07-458a-a4ee-d637f744b1bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB46
bb138b53-390e-4fbb-9ca4-3fae58368a21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB47
d52ef63e-44d3-47f3-bd3c-686e19b277d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB48
935a405f-d57a-40bc-8a21-c34eb170aed8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB49
1a4ca8df-5a69-4bdf-8c01-513ed5f2afbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB50
18087bd7-9f55-4e27-a8b6-7a97fee9a289 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB51
490a3c20-872e-4c93-83f0-b8c811f9eba1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB52
c04edc88-c487-4d81-9433-f61e5069234d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB53
9071ce05-5059-4bc1-a9fa-c423845d6326 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB54
0f4184b2-2ee8-417b-9319-55849c0658c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB55
17dbe4d9-8dc1-4b40-8118-13f2c1280689 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB56
398e90a4-ed1e-4ba4-b1c7-74fb15026893 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB57
b6d86c85-cc0e-49c3-afef-da8688fbe43a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB58
3016ca05-062c-4c02-9363-14917fd79da4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB59
47156b4b-9397-4f68-b49d-a8b803025c60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB60
833e2534-5e1d-40a3-9d0a-61370426a2c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB61
77046aea-90a7-40ce-9225-11c4a2720a42 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB62
20a4db4b-e4d7-4db2-a268-923a3960f436 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB63
f977d0d1-4057-4b02-afee-c7d3210a9c7b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB64
8f347c59-39f1-44a8-afd1-ad3d33a68667 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB65
d680afe7-580d-42ec-b537-ae0a35a26df4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB66
921e291b-7fb9-40be-8151-b0a1c9390de1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB67
8c104bc9-7f92-4661-a3e7-f3c47dc9a3b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB68
27e7872d-849f-4e35-8f55-7492fc472ea4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB69
72930c8f-f0e0-41e2-ba3b-1126cbd55534 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB70
3f70ca67-a8a8-4f15-8fc8-b07647cde191 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB71
c2d16186-a518-4542-9358-20deaab02341 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB72
d19f81ae-097c-42fb-b5f1-7879e8538e29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB73
769eb094-d1a7-4603-b596-012643bf379e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB74
1dbbc05c-3d05-45d1-b752-d21b904005be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB75
fa6312a7-0c56-42c4-9dbd-81fcf15655c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB76
3e36085a-282a-45e9-ac85-aa40c661e9ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB77
0cb4b0d2-35be-40ed-b42d-3c5d28caf6a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB78
957338f9-8cdf-4223-ac44-454cec123bcc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB79
a7937910-9eb9-4d7f-91d2-55dd83c8a3a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB80
870e3b51-ef2b-45b0-b37c-56d4d4f12821 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB81
b3cd6230-5eb2-49fe-bad7-b461ba756e9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB82
438b50c4-3458-4031-81a6-b5e40f15ac66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB83
b87e5825-2720-44e0-80a6-2a7948ca17d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB84
4ae85410-4576-4a2e-beca-03190c468f15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB85
e5e9939a-d7f2-4d6b-b574-c67a857c86bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB86
26326bb5-3aa3-4b9e-97bf-e149ed518b7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB87
29335541-1aaf-465d-b664-b1983673f51b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB88
2fe65825-1b19-4cc0-9ea5-c9becdde2c13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB89
317cdfd8-e515-4ef6-909c-9c881d49d139 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB90
67b88262-b17a-494a-9adc-09621995c72c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB91
03dc3229-6778-44d7-8af2-b90e8a21d13c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB92
745555e5-f3bf-4116-9c86-21aa784da8d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB93
15bba5bf-80a8-45bf-8261-18cd4c799315 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB94
0effd1e0-d8f1-4db6-ba85-33fc6a9c7201 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB95
c3ec9166-80a5-4f15-bf06-357da1bdc24e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing | CB96
e5553505-a60e-4f6b-9e79-92eff220f836 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground
3cc2dbfb-ecae-4ccc-a729-9ca72dfaa05c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01
2df829ff-4160-446c-90e7-7a14d20f1fca |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-029 - Rough-In
006d4573-dcbd-439f-b894-c874e21d591e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-030 - Cut-Out
4cd55e0c-e646-4f0d-be2a-ccc2c238038b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-31 - Fit-Off
8b0465d9-27ec-48a6-a785-3c9f1d03532d |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-018 - DB Fit Off
2530191c-dc90-4205-9efe-25d05fcfdbea |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-32 - Commissioning
701457b7-f835-41e7-8519-61a4f4d548f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing
a9348217-a555-4622-94fe-9ebd2d8b0ee9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB1
b463f894-b586-4463-b9b3-80cf138df9fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB2
b8f95023-dfc9-4e31-9e68-efdb29970d6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB3
f766c2bb-56bd-48b2-92e5-46683e2b3a29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB4
f193de9d-7be5-400c-ae12-614b86ff94da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB5
b2147f7c-143d-4e9d-88d7-7a01e7f91233 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB6
456fe27f-ca42-468a-8cfc-aec1c316f375 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB7
62089977-86aa-46df-8ea6-02466f20ab5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB8
9375d324-e627-4272-ae06-d177efdcb1e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB9
4903f893-e6a6-4c4f-9d7f-3d5804ae0f3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB10
65a8b6cb-a58b-4ad0-8144-a771f23034bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB11
2ccbedd3-7a86-4f57-bb87-ca576ab0ce13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB12
110926d5-4b40-49ac-972e-11a092b85c3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB13
cac3b7e1-c4b7-4709-af35-a322674ee9a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB14
796bec49-04ac-48a5-bad4-b050ac5d9a01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB15
7d128b48-ab35-47d7-8060-2b1a7f78cb2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB16
86e595ff-64cc-4bef-a4ba-b00e84837187 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB17
17e93eba-be93-4760-b44a-ea55bf339ba0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB18
40d76973-6198-4cb4-859e-0d942046009b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB19
c314c35e-5353-4f53-90dd-e8fba8987c02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB20
851c225f-e5ba-4961-8496-896cadc02559 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB21
ca4e906e-e299-4089-aa8e-64269e3c00a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB22
2abf3d04-c2f5-453a-98a6-231185e303b2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB23
d77b231c-b329-4191-8aa2-65d02fd62bb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing | CB24
50786135-2fa3-4ae1-a766-832bb3a63419 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G
cbcc7dc8-095e-4419-a75d-fd787ac4bb86 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-029 - Rough-In
858d0007-03c3-48ea-9016-48cd09436ec8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-030 - Cut-Out
24176775-6593-4df7-8bfe-fd40ac70dc8a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-31 - Fit-Off
ccad0480-8759-4bc3-bada-66fc64f4efbb |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-018 - DB Fit Off
6c990503-4979-4940-83c8-9d15595cf931 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-32 - Commissioning
897200d6-fe39-4691-b697-98be418b024c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing
ce652739-a098-4d08-a44c-59f14fbc44d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB1
c895046c-61cc-4ac8-9bc7-9df3c2a2576c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB2
2c993261-145c-4e4a-989e-f5212a9c44f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB3
03418d78-5be3-4d6e-a2f0-4d9981899d12 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB4
7543a15b-9237-45c2-8513-bd5cf8a094f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB5
cab87ea2-d805-4df4-b9c6-41c2f04c08a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB6
c001668f-206e-413b-a36e-e41def5d3f7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB7
7fd06620-c575-454f-9da9-038e11a221dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB8
ad3716d5-5552-4f2c-8015-dda6e6d71857 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB9
1851caaf-6803-4d9b-820f-13104c1dc3d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB10
d6d57f22-8edd-49e1-a446-51b6afc5c7ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB11
513b0036-160d-4d18-9471-552ac71c5381 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB12
41c1ca24-8167-4b89-9633-fee13eba4f8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB13
30a76dfe-8fd1-4711-ba54-0e0b65b48446 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB14
1021d2a0-922b-474c-9648-49be5ce6c901 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB15
7d138855-0951-440c-b0fc-c4735eee8c71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB16
f2f2ff1e-26c2-41a7-9fea-4100dd4f0400 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB17
e4a27ebc-6a39-4069-91d6-6b3fee74eb40 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB18
a72a636a-b7b2-42bd-a71a-13bf599949b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB19
cd84ffd8-cff6-4374-8888-bf0a1a4ba6a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB20
58f2750d-45fb-4e95-bfac-cf57d1e9ca5f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB21
58031b7a-1bec-4af6-83ad-d57cf2789e8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB22
baeff7e5-4f3d-49cb-90e1-49b048eb1c03 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB23
f6a84243-455a-4488-8efd-a0d06e7a8e04 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB24
deab3cd4-06f5-4bf5-807b-43a35a2205e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB25
ddce14d6-b200-4f18-a25e-73169cf5bf45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB26
540fe8cf-da19-493a-9eca-f7c53a068007 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB27
28e63f79-fa93-4607-8c3c-006867286e26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB28
6b95a6c4-31b5-45ba-bef4-cd86ffdb21a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB29
48827397-98a2-484a-bfa4-f90712dde29b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB30
303df184-fb45-4e6a-8160-21a910acf766 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB31
38e9f027-2e88-4b8b-aefb-767699c071db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB32
7fc482de-5f40-4d83-ace9-a43d1c8be476 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB33
f7a64be2-1894-4cf1-95db-d5b83a06edc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB34
b8c7af05-e2e0-45e1-bfb1-fc521303e08d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB35
1912edf8-7797-482f-bfaf-e53afbd4a5c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB36
56e5dae4-ba00-4a90-a7ac-8564c59f55de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB37
bd5015a1-241e-48d9-9cae-1ee4e2866454 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB38
7e825840-f31d-451c-9e6f-4598d6e70793 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB39
f5a13c1f-bed8-42b9-8010-5006da76729d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB40
df157ebd-1705-4167-b709-708df0a98804 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB41
78027ffd-2044-4284-96be-ec860f11c8bc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB42
b46c1fa2-f88e-4443-9642-47cf3fbe2ffe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB43
18f93f42-cb39-4277-bddc-1d95acea2f70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB44
86d8347a-247f-4470-a4a2-6e8667bfc6c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB45
8a98ca5b-9d65-4ff4-a081-936b42559ff4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB46
9012ff60-346d-43c2-af71-52d76cb5c1bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB47
8c6f2b54-7004-417b-9f7e-e3f2eb4adbe0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB48
ea0812c8-e3a5-4948-8192-9afdb4ffe224 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB49
8a9fdcde-f3af-4fa1-9052-f7d803849645 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB50
09204f96-1cee-450a-833a-12b1b989ebe1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB51
aa094ca8-9b4f-4c3d-b219-b5a90acca6c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB52
cfaa933c-16d3-4739-af7b-459b0dd61302 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB53
51668040-8562-4560-a230-2c75d8846ed0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB54
4b7bd59e-253b-4cd0-bae2-068f0be4bd44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB55
76cc34d4-ce88-4d27-ab06-76b81bd83d68 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB56
4c302ce2-c9df-46ad-82a5-4491f96fb3cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB57
732c7963-5c9b-44d6-a007-e3c2bf0d9627 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB58
0fb0ba29-95b1-4750-b1ce-63d4648f0cae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB59
bf9a82fe-3343-4e26-91b4-223fad23734c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB60
1ec6d5e8-0c55-47be-9a36-66ffb2a8f32c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB61
e1dfb9f6-47d5-489c-8d9c-89ada0f69fe1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB62
3738e054-cd35-402d-9fae-38fd49956095 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB63
e894ee9a-e7d5-40b4-8076-cf8e4085889f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB64
e9b8d699-eef3-4743-8976-c587d56c4e2d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB65
3278f78a-2dc4-4c9a-a5a8-4905e1c3f7aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB66
c432d1b0-322e-42c0-9ddd-646786b597e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB67
82a6d556-472a-4177-9443-5e27226333c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB68
eb3e4007-2acf-4467-a75e-fb21c219be79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB69
ea33b0f5-ee0a-4cde-b5f4-f7a3c0087973 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB70
f9c1ff74-28ec-4ec6-91ce-8b34a504c46c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB71
1924e50d-26ce-4a35-94a9-949f4c5779b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB72
7ddb2a8d-177d-4d4c-999d-36f3aa512258 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB73
abb8cd27-5470-4644-ac52-f9d51c9800e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB74
d75c8fa0-6f53-4d36-9669-f586b89a7eb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB75
77fd6b37-5158-4593-931f-fca189276284 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB76
682a3d8a-5f73-435d-b73c-9004ffa20239 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB77
38ffcd04-5bc6-4d03-89ab-fb0c224a1b60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB78
6f5a984b-dc8d-41d0-ba77-ce636cfa1071 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB79
38d240ad-8165-4f76-8559-35fe0e29e87f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB80
db4e854c-9648-4a21-bbea-6a349b080e9c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB81
e0795ae1-c800-4b5e-a1d4-d85a704b0383 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB82
b1a2de08-5916-4581-b745-837b8a9ad597 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB83
8e60ac5d-500f-4987-add1-fdab8bbff914 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB84
0d27bbb2-c01d-4d40-a9bc-fd17d1bd0557 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB85
1c233d69-3dbd-4b7b-b92c-7d7666b2a41b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB86
a8321b05-9e2c-485f-84fd-5f5915251d0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB87
18046787-0cbf-446e-ba29-c59073e9323f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB88
a628bcfb-ab0c-4f6e-9546-868ab8c7aa3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB89
846d7b6c-93c7-48bc-9055-d72e16d4e2ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB90
cde8661a-d4ca-42b3-a6f2-92d3b10a6032 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB91
98045f4c-362c-46a8-840f-390f7f770986 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB92
1f4b0d90-7f9a-415c-98e0-ee8b9708f626 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB93
854a6a3a-9e9d-4e13-a9d0-ba50f309c1f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB94
b2f26785-68f4-44c2-b949-2b1d53e7749f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB95
d3f6469a-2c96-4fff-8b46-8ac303e419cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB96
7a1fdfbd-cbeb-4995-9e8b-6cbfed824fd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB97
e59af707-e192-4c6e-b982-597c292706df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB98
fa48eda7-89b7-458d-b9e2-3a978859db0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB99
ec34fc55-f40d-49db-bc76-d7f634fe1acf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB100
061fc974-f7fa-46ba-bd0b-2f31bdc9ba56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB101
b9220a89-2cce-4df0-9c18-b1c5b46e26ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB102
ca3ccc42-2827-45f6-80ca-632955965d9e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB103
fa70de0f-0cf1-413b-a151-e36c1d8ff2a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB104
130e3958-29ce-4dc8-a62c-c5f285a9a9d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB105
08fdcb3d-495d-4320-afff-9f48f1971acb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB106
6574519e-f27e-4ef7-8c78-8f4871409433 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB107
afab83ad-3e1a-4199-a5a4-82d24c448986 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB108
f5456110-845e-407c-9f26-8fb2bc92ae59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB109
7866f357-577e-4e92-b5e4-4528829cc507 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB110
ffa11229-713a-4c85-847d-f8b5903e3805 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB111
c5850fa8-096b-4931-8b31-4ef5dcf32e8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB112
156725d1-ac9a-4f11-a868-962ff1a062f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB113
9aeac45f-df31-4617-8d5d-6bd798a093df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB114
0c6eb73c-ff4f-4603-bf68-6ade3fd3c4b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB115
8fc62201-c7f6-4a7d-bcf7-f8a584dbe561 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB116
286bfad1-e105-468a-afc9-41af94d5415c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB117
16f69ee3-c8d7-4056-bf4f-7f5b55e761b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB118
31b3cf5b-fb50-4480-b468-4028f9a39a25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB119
c9131e5d-c4fd-41cf-b1a1-bd4fd9ba0bf5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing | CB120
ac2da04e-b90b-4a78-952f-f7a3b8fb698d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1
c42413cd-37d0-4271-a23c-febcac67a653 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1
4b9c4a7f-7205-4184-8e4d-933a95c15bbc |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-029 - Rough-In
da87f70f-540b-4380-ad39-92f227eb74d1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-030 - Cut-Out
826c2911-6953-4aaf-aa1c-5737cb854791 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-31 - Fit-Off
5c64b975-a38a-4f6f-9ed0-63bb71440684 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-018 - DB Fit Off
e515d640-478e-4280-9565-75e72401b08c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-32 - Commissioning
4a6b6a22-590b-44b8-95f2-b15ac67d8edc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing
a906564f-a336-477c-a701-f66bf669d7ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB1
a2c21355-eae4-475e-81d3-8616331fb618 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB2
3e610f8f-ee3f-4ec9-ba64-cd93d1525e00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB3
6e9cdcd0-bc05-4127-b67e-05c90e7c332c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB4
209efbcf-bfd3-4d07-a038-98219556030f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB5
3bf626ae-f2ac-4c65-896e-2d3f7f3e0125 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB6
1b111d13-108a-4328-b7c7-8a8f15372ca4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB7
a8c45d41-4ba8-4bc9-9045-a3c7ad32d6d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB8
8eb0ed08-9d8c-4f48-8987-43298a6b20c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB9
b4dd2c01-df73-45f0-a1fc-540e6902a037 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB10
d0846e57-566a-48ce-9d41-453f027052ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB11
27a2ad45-d8f4-4a53-8418-0e6767655642 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB12
8ae4e17a-06e4-47a5-a916-1823dd316077 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB13
ea6531f3-4162-4c07-b330-eaf93db9312b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB14
5bc951f1-9184-4a46-b1ab-d739f513511d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB15
3287ca07-ad09-49cc-84f7-1b72523814de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB16
2b0d165c-b1c2-4fe7-ba4a-f86e1167ba1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB17
f84b81e2-5a63-46d5-aaf5-ee50b89b4414 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB18
3bd77018-faa6-4325-b6ea-27c4f2a3fa13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB19
187d8949-7ed0-47a7-b724-dd6bc57cce52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB20
e5c9ad03-ba01-4922-ab39-4e2c92a653d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB21
9f6adc40-8fce-49a3-a477-e5d6e21ea501 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB22
44e4314a-66ca-4dfb-878c-a6b2a68c5d3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB23
0d6b9e28-9b3d-4a40-bf47-cc6326d4e322 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB24
d81847f6-12a4-4cfa-b648-3477f47a8868 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB25
3e3f434e-3188-4231-963a-591eec495e51 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB26
faa5cf2e-53e7-42c1-a33c-e70358a1d592 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB27
2d1e19f3-d4be-443c-9aea-e988f9f7e37c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB28
f35a9dbe-403f-4594-92e1-f5985bf7ba2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB29
0ee962d2-0482-4df7-abc6-13b179d138ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB30
996816b5-8244-4b8d-9b1c-68730a132775 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB31
230a5096-5826-4b6d-8cf2-4d510adc0c1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB32
b20bf0a5-88b8-490f-8f3f-34177ed3deed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB33
8e63375e-5d73-4654-882e-36575f452e13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB34
aef28ca2-667e-4550-b049-4f706b105409 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB35
02979c3b-4d39-47f1-8554-2c1578ce97db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing | CB36
87e3f5e8-d1f8-41cf-a24a-837216f16b28 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS
abdc2fda-956b-4bf1-930d-9b8ccb2d6947 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-029 - Rough-In
80d6d796-5967-482c-8613-ae21594b2a77 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-030 - Cut-Out
13ec3e9b-e33a-43da-ad85-90621599e5aa |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-31 - Fit-Off
cc5c742c-a75a-496b-b7cd-26c024f50f76 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-018 - DB Fit Off
1687998c-a720-44b1-b036-f3b4395dafad |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-32 - Commissioning
975e6d7e-9c24-4671-b5b1-c9b8a6c9ce73 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing
992fa406-c67c-4b13-9dab-5fd575c23607 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB1
80e85204-8647-47fc-9c4b-fcb285be1c9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB2
10a06398-284e-4e75-a325-4f3fc6cd47e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB3
46ed3d41-b314-4295-b277-bdecdaacd8cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB4
8950c801-0b87-4aeb-b272-f10c2a4284cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB5
2d73098c-c405-4bca-b12d-5458c57b9025 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB6
9363c7cf-c571-4f85-bc69-bcaffa5b7846 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB7
49078774-affe-4624-b437-5928ca936d21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB8
4a210818-bc76-425a-86ec-596c14cb925a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB9
34875cb8-b709-46d3-b9b7-333b08146802 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB10
7f6304f2-309e-4bb8-a04a-9d72a179ced2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB11
43fd772e-ae50-4529-80b8-8a40e3a02821 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB12
400115f3-cb17-4064-8e15-53f4dc114511 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB13
7337137a-71de-4372-bf85-145f7f4b3ae6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB14
37c95cf5-1094-4991-95fd-dfd898326987 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB15
09e89058-7970-4b20-899d-4d1543a1a0c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB16
c59401f9-3fe4-4f26-9d4c-a97a71f505a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB17
53a5b63f-7eea-409e-aa45-bc0558e97037 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB18
7dd030fc-0941-4d69-a018-3a39c2b437c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB19
5144a82e-62fb-450b-892a-6b9a8c86896b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB20
93b17ded-33c4-40ab-9fee-c489eb059296 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB21
01e4e55a-b37b-40bd-9b07-3a173808bb4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB22
8f674b9c-82ef-4f6b-b189-f44dec4cdfa7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB23
76aff8df-52c9-4158-94dc-8484ea237055 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing | CB24
e0e2d629-d2c0-4fcd-8e84-ced8346406ba |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS
c1f4b0cc-029a-4c2a-b009-62cc2947374c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-029 - Rough-In
d27c2177-1563-4138-89e1-8edbad489b7e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-030 - Cut-Out
db52d864-245e-4911-99b7-40b171372c3f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-31 - Fit-Off
630147b4-3636-4571-afef-0e081d8a1732 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-018 - DB Fit Off
f88a2b93-7f70-4ad5-ac61-32cddc590363 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-32 - Commissioning
b7fd96f4-b9f6-44aa-81c2-2cfc7ab22810 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing
e4176ced-6178-48e5-bc86-bbe44d00bcfa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB1
4dd54358-ddf0-4101-883f-6c62d8bc84c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB2
8d697c08-2c1a-4e03-adbb-fd899895bcab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB3
4970baeb-629a-4a91-9aa1-3815dabef6da |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB4
b460fee7-7175-40d1-a1ea-2c701160a8e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB5
6ccb7dd3-f936-4e5a-a143-5d49ccdfeaf7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB6
d4ed8c8f-f506-4e48-83de-3055c163d4ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB7
92d98a7a-f75c-42c7-a5a5-6ef805a68274 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB8
0ec09811-7b1a-42c7-bee5-96b9aa6ae1b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB9
ae9e0c81-752a-4bce-856f-e6c7df2a6a6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB10
a839a6f2-60b3-42f6-8304-33d2ce0a7a19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB11
a4e06b82-9a34-4784-966e-6e9c0cb74a52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB12
5fbb3107-7e29-48b0-969b-11eca3b3b6b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB13
f07e46b3-b600-4d47-9d30-1f33041fccf0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB14
5389d49c-b151-42aa-a26d-ae323652a2a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB15
1a8d11a5-1626-40d9-bbaa-a0df32611990 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB16
c6ea3c26-9d70-4d0f-a4ac-d55144b02863 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB17
8fb599c8-14dc-452a-8a4d-de0c874ac296 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB18
70fefe3a-0de6-4f05-9631-d2382ecbc5c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB19
4978afa5-111a-4a99-99a9-56acdb5d2d8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB20
87382871-9350-493e-9373-a719f7a3de61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB21
173a2480-3daa-4c10-a5e5-a67c2853e03d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB22
a7d067e3-cc18-4696-b1e3-66ea65ab0617 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB23
c0aa6e8f-67ed-4f70-a69e-6bf3db1153c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing | CB24
1a1e94da-5749-4c32-8db9-05eee72a00c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction)
7c3b8af9-2130-4677-ae09-3eb2521c6794 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-029 - Rough-In
05b09be5-d4cb-4650-b7c8-dae2490a2b79 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-030 - Cut-Out
dd8fd352-3902-4123-a92e-6fdeb92f7c2a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-31 - Fit-Off
cfcbf28f-f7fa-4447-9a37-16e24ecc3780 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-018 - DB Fit Off
7197cfa1-2bb7-4fc4-a438-c78b9e9b7d84 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-32 - Commissioning
5a1dd349-403a-41ee-8097-d3781001b8be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing
c1bb400a-39c5-4b50-a838-dfb9f4ab6946 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB1
783d1ada-9a12-47bb-a92e-167698e5457f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB2
e21d6051-629e-454d-8bcb-a86b556f2d5b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB3
ec72a460-79fe-4c32-8044-949e3b688239 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB4
a7d5ee67-7daf-41e7-81b9-4bf7b24e9333 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB5
27190863-0349-416c-b8f8-191ab3b8caee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB6
642ad534-d32a-4a7e-8985-d7f49d50b786 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB7
dfde473f-a362-43e5-a993-4b11d7aa301c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB8
513ce05c-b95e-4dec-b174-7a8aae89578c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB9
78be754c-d5b9-4861-8f84-1daa22383822 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB10
6f042c4e-0374-4748-9af4-d96d428e5321 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB11
154467c2-2012-4add-85d2-dd63297fb139 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB12
ce7c9ef0-52cc-404a-970e-eb82a811f86b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB13
5bdb1b4f-1e0f-4eeb-9671-bd9ee4314a2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB14
30a5eb21-bb3f-42b2-90fd-1c39780ccdac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB15
046c9dc8-fa24-4301-9692-1a895d028f16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB16
fe9edd4b-68a4-4d5e-8b68-b5fc4f8466e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB17
6a8b4756-e933-411f-bb61-b1c1313d3b58 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB18
70963dc1-37af-4a34-8d0b-a6909b509fc8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB19
bc355701-1767-487b-aafb-379420895ff1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB20
25ba3f55-041c-415c-aa62-4b2cd4c9bff0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB21
27f3b9b3-d6b1-4792-bdb9-88822db298d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB22
f0e580bf-6696-460b-a2dc-c7030b621190 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB23
749c97bc-5d1e-4316-931c-46ba7ea2a347 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-01 (Multifunction) | AE-ITCX-015 - Mandatory Testing | CB24
35c24ddb-62f7-455c-b51f-605fe2503774 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02
e8cfbd2e-ff3b-4c4c-9c84-af11a6a683df |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-029 - Rough-In
4fa1c3f3-ee47-4272-8d5e-6f9c4f6ec8a0 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-030 - Cut-Out
da51af57-d181-41e2-a510-fba7acdeee39 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-31 - Fit-Off
219cfb75-e8ce-4a3e-8e8b-abcfcc9a5d05 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-018 - DB Fit Off
0a99ef7b-2c23-40ab-8b0f-c8174ef3c15e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-32 - Commissioning
243accd0-180c-46c8-8b48-743eb0a2d2f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing
369f9719-5d87-4a4b-9cb8-5c7b195f84fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB1
c9673147-3cb9-4fee-aef4-38bf04f5e411 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB2
9244bdc8-7f4a-403f-8522-2e473658f77a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB3
967f3344-32b5-4e97-ae4c-099ffcb85c3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB4
2cd162bb-8ecb-4f19-af5e-65c2a53bd706 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB5
14230bc6-fba7-4992-90bf-96be61e900ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB6
1691b551-0643-4b82-8edb-5d89738c5405 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB7
f47364e8-bd63-4d0c-9902-de8640bea115 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB8
87ccb1f4-4a2d-4411-b063-57b8ee1ef9aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB9
976d2d11-c72d-4c19-91eb-e5fe70d95fdb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB10
37b0c722-c7db-40eb-a3ae-80182c2ae224 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB11
434577be-c138-43d5-837c-8034ba0a12c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB12
d5e4c7d7-461f-40d5-8881-2329cb47a536 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB13
24239314-891e-4496-933e-654a031a9099 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB14
1be5839b-6981-44bc-a60f-d3e1d3a936d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB15
d5213ec8-ec05-4863-850f-5b24b927c904 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB16
f3253fe8-9c71-4da1-bc7f-1024877f167b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB17
1443fe0b-ac28-448f-8573-fcd6908ba715 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB18
81859c9c-6446-4526-8aa2-317cfbb95a21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB19
ed1b19c1-1e4d-4c25-a1f8-d6b59da61f45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB20
ac7dcfbf-137f-4e16-a6fb-e6763882904c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB21
00e35fb0-acee-4627-bb0c-9fe6c7479c6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB22
0d35c97e-2387-48db-bd54-5f47286dc347 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB23
1387c52b-2b2b-47d6-b6bc-0f1f541066fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing | CB24
7e64030a-e78a-4810-b1b0-4dc0b5c0e81b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03
1b15d578-26bf-49dc-bc49-e7c0735bbb4b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-029 - Rough-In
28eea1c2-163c-47d8-a2a4-2b9e0cc5cb02 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-030 - Cut-Out
db1c54e6-22fe-4d02-b7e8-52e40d257c9b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-31 - Fit-Off
9f2790a2-06bf-4bca-8341-3aee58377d2c |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-018 - DB Fit Off
691e0ade-1099-4d6c-b07a-7ec7188d133e |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-32 - Commissioning
6005118b-37f7-4a55-b8e2-fd8f394df2ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing
b81bee9e-aa22-4f87-a4c2-be0862b9db6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB1
65d843b8-b1a3-4eb5-9adb-2a8e932d9a8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB2
78923e60-3605-4468-9401-1746afc91443 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB3
c3753f91-98e0-43d1-b610-c9442721ba0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB4
1466dec7-8b3d-41e0-80ed-d9c3adde751a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB5
c66e99f3-fbdf-4101-ae81-42f036d070f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB6
6a2a2129-c85f-490f-82f9-d0f7e894a4ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB7
e8454f96-345b-46be-91e7-9514c1eaf5e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB8
b7990924-6b0f-4021-81ab-7f3007a31cdb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB9
bea22c2c-66fa-4884-986b-6276f5d109ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB10
8296599d-f6ae-42ef-a627-0541ed547be8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB11
c2b3de54-552c-4f3e-b9be-002f8cdc693a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB12
fbce0ddf-cf5b-41fb-adc0-e00df43c9546 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB13
5000289f-b017-4b2c-b18c-b8808f46cac1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB14
62ae16ff-a642-4ccd-a1eb-1fb6ce861fb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB15
0aa8a912-796e-4b29-86c4-24207adc540d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB16
29cdd9d6-2801-44d5-aa14-1f1c0549365a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB17
49e5aece-9a74-4342-b2f4-1730ea307939 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB18
171a3873-f62e-4f2d-92ac-6c0cb7ea305f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB19
809276c9-722a-477d-a6ef-303449fe0401 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB20
4e749cb1-b0cc-4641-9f7e-62d61fdc51eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB21
a34805cf-1f97-4b36-adb0-177517784ada |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB22
d1f178c9-88b3-4d44-98eb-5011dfbdb7d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB23
27ffc94a-b3a3-4c75-824e-9f648c668690 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing | CB24
3acecf26-0b45-46ce-909b-2ad17e687c64 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04
959d9cf3-40b0-483d-a922-e3b7c4820996 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-029 - Rough-In
396eb794-6851-4684-b38e-33f68bd2f4c8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-030 - Cut-Out
74cfaed2-ff89-4345-b658-5da6f79d245d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-31 - Fit-Off
11688c1b-dade-4700-a424-7e572d13306a |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-018 - DB Fit Off
aa99f7af-2709-4297-84f6-3c6209184425 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-32 - Commissioning
b6b42d4b-7547-4c27-a9c9-b4bae7828456 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing
6464385f-abac-4e41-a744-cefd9125f4c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB1
5bc8df17-912c-49ff-86c4-bdc7f83347dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB2
5c4b71a4-cc70-444c-8b6e-4c86d899ac7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB3
b7188346-d87e-4372-a196-e3e32090f2a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB4
0a394f88-1c1c-4359-8fb3-4941192ca4e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB5
c6d7457b-faf7-4f2a-880e-f7a9e96b1287 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB6
5ad3fdfd-3d81-45a2-bb70-06a777ac0e3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB7
68271c9a-e2c3-42a2-8134-a7b056c459d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB8
cafb4756-76b4-4af8-a06d-b8c153348c86 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB9
defbbd2b-1c4c-45ec-b60a-944022ada15c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB10
7931e329-bf79-4b9f-8bf1-71e7f2692008 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB11
fb1a638c-0606-4a52-ad7c-66d68db9925c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB12
f8dd55df-fac4-478f-9e8e-8922943b962a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB13
418a893a-70f1-4e8e-8351-14efe3ee3e0d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB14
44d11cea-d8b3-45d7-8119-68d587dcfb5b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB15
d0e327b7-b420-40de-b47f-36f256b80360 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB16
77f3ef27-ffc9-4e15-b781-634e48848827 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB17
acf6e6e3-8d60-4920-bf93-964e5242152b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB18
c52b578b-6844-48aa-a967-2b4a8d769fe7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB19
e80f2357-8583-47a6-a864-864b67a91038 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB20
0de544ef-6feb-47db-9db4-1bbaef75a6aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB21
7a8d771c-71f4-4148-8c01-c7f4d3cb3d3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB22
1e6768db-807b-482c-bf55-39f8f1b7bf8c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB23
4d2736f8-404e-43dc-abd7-003cc510f5b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing | CB24
7302e6d2-17fe-40b7-9569-75f86650ccda |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05
926b5935-a856-4c01-b3e5-0efa33570c21 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-029 - Rough-In
faf57380-c0e8-44ee-b679-624a9b881a73 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-030 - Cut-Out
2c7a44c5-ec37-41bf-8263-bfbc4dc92ee4 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-31 - Fit-Off
2cb9b3b0-5604-4cdf-83f1-4b61c35d0848 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-018 - DB Fit Off
ca150c1e-c7b6-4981-b689-b0525ccd8d96 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-32 - Commissioning
e9d8e03c-6bae-4e28-9cf0-6270a4d0c49e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing
494dc42d-42d4-4d69-96bf-6d63e13b7158 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB1
f6edbfdf-ef9e-4f36-b963-36eb3bba07e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB2
ff6f9c5a-4987-488c-bd63-87c573ad396c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB3
84aa8411-4e84-41ad-bf85-95c0930608d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB4
40da8fff-f6f6-4cbf-a612-f82db4f25725 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB5
f57b3350-b8b2-4be9-b118-427e46b5874e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB6
10477189-e766-4d73-a4fc-3efeffea6661 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB7
072138e9-f74d-4407-940b-c67955b0c591 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB8
76dcb134-d893-40b2-81f3-a7c24bf3e87b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB9
d6ce9789-79df-465f-b182-04adbef83f9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB10
39496a24-5670-4f85-b838-1796414ffa91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB11
6a478fa0-624f-4ecd-b5e4-f51c23aa29b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB12
629fa90d-4cba-4261-a24f-5f10a76899e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB13
b06d769f-9cc1-49d6-abb2-01b2eb665238 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB14
ede9eb34-ac30-449f-b5cd-237cfec8478f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB15
4e2aba36-1930-4230-97c1-92e37d254dee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB16
49329a89-2594-4a7c-938d-e9f698abc724 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB17
07282f00-3956-4d3a-8211-2301af4930c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB18
0375bfa4-e8b4-4f59-b994-d1491e97481b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB19
cbc56c63-5248-425c-ace7-eeccc2cd1696 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB20
c46f2ef9-2aa6-4273-abda-f79b7d898592 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB21
6c796c15-f7a4-4434-82ec-4be641448f4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB22
8b59177d-c76e-4f8a-b320-c2ec20d68253 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB23
930c99e4-2ff6-42bc-a0bf-f04b781a10bd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-05 | AE-ITCX-015 - Mandatory Testing | CB24
68e96154-85b7-4bca-adf2-ace3c4780a16 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06
d95272cc-b4d5-47ed-9ad4-ceae830fff7f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-029 - Rough-In
b92d21a7-fdbf-4823-b9ad-cf6fe8aa42da |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-030 - Cut-Out
59203c91-71f7-499b-9613-4ecf325ef153 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-31 - Fit-Off
2c720802-fbaa-4128-94df-40f76872f74b |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-018 - DB Fit Off
af4f248d-d88b-48e9-b05e-2044f55cf64a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-32 - Commissioning
1d3c3a96-c57e-42ed-8fd3-727e3c963765 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing
a82fd296-7daa-44d1-99c0-befb89c4a8ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB1
cc278846-ef58-43a2-8fa4-48cb0901d666 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB2
b7d2d8db-8c9f-4041-8f40-55aaa96a4975 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB3
400c5da8-112a-40e5-bc96-af6c520bc58f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB4
199ea39e-f0ab-4553-98bb-ca9fcb202402 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB5
8008e58a-297b-43ca-b843-de29cd689885 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB6
a754a827-06e6-4a1a-aa3d-d86c210358f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB7
357b3f2b-2b49-4188-8b50-a828cb1b9a95 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB8
e1be7fa1-df1e-43fe-ae2e-76c6f45cfa13 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB9
6206f69b-0ba7-4050-9cbb-bb01f7e807aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB10
d79e7c34-91d4-4434-81ee-f5bb3f236e91 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB11
91a2b57d-d650-40ce-971b-35da66ef7d16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB12
b0fce06b-e1af-43b3-9147-6a39247bec41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB13
ee0609f5-f59f-411d-ac5b-af03db10028c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB14
06b8d727-7465-47a3-962c-cc70401cae14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB15
57cc0750-e2b1-424b-bb2c-89d2de3b3239 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB16
c80c12c2-d032-4bce-8baf-c257f652b565 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB17
c4b6ecc7-a9a5-45e4-ab2d-18752237c2eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB18
88dac299-15fa-4339-8764-7f6bc5e8de5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB19
8feefcee-82f7-4e32-9acb-52ffcea10a3e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB20
e5350a8f-896d-4d83-8411-9b6de99a2844 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB21
85dcf85d-d5e4-406d-80b0-e79ed90da113 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB22
cca328fc-5325-4b16-9797-8b92a4cbfd0e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB23
79f15801-0e35-497d-b88a-d3271c1f443e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-06 | AE-ITCX-015 - Mandatory Testing | CB24
58b8b984-93cc-48ff-a221-a2c2dc0827ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07
9154ee8c-c141-41b9-ab0d-9a55c3ff68fd |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-029 - Rough-In
bb033998-6366-4ef2-94fe-014f45f5c15c |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-030 - Cut-Out
328527a2-bf94-4d7d-afa6-698a3f138c9d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-31 - Fit-Off
2fd1a2d0-d29e-4c81-b38a-137fe0da9eb0 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-018 - DB Fit Off
8bf17fdf-abb4-4764-8e51-b5f1cbcf3837 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-32 - Commissioning
b634854f-781b-4d92-bff0-ce10e7c34c6d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing
2e8d03d0-6e81-4ee8-aa04-4916425bf611 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB1
02afd6a1-0909-4f17-b663-981ff580cdcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB2
ae34f570-70fd-404a-9b75-e5820600009b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB3
68302801-b0ba-4bc6-aa05-772f54656f0a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB4
9196ef86-7582-4ac5-933d-49c6fe37cf75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB5
38935460-90cd-4d20-9b72-b5cc21104809 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB6
1682dc9b-3539-4fe4-9efe-9fa4eb9ae17f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB7
64ebd1ff-b1e5-4014-9264-ca7c4d640999 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB8
73cdf11d-1fa7-4f72-8fbd-6c38d238905a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB9
d635f55d-e59e-4294-87f1-39e5e0293be8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB10
36b39869-1197-470a-bac4-f5eebad195c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB11
5e2e9347-1d0b-4c77-935e-80677561f5f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB12
e4d039eb-1621-4745-aa8f-7fc710bd2b78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB13
ec77e8b3-242c-46b0-bcfa-7bfa29a6e210 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB14
8eeb9d44-cfc4-44d3-9c7a-8d05b1f9fb1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB15
872ef323-a8a3-4738-a749-23ba1704ee08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB16
0102a9f0-57f2-49c2-99e7-a4ddc73ab502 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB17
811bf5bb-bf4e-4fd9-9554-a9688135b514 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB18
38d3c04d-4204-4301-8845-2d94f00ada4d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB19
6bd67976-5373-41c3-bb95-d746f1f1d8ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB20
369e57eb-7eff-4a5e-8f78-0f911cdfd36f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB21
3e537ed1-4d25-4374-949a-ce90e8964b71 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB22
934bf04c-d78e-48a7-9619-0ba48dd229f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB23
bef450d3-8b19-4ed2-bd6c-5f39c55e4671 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 1 | DB-T-L1-07 | AE-ITCX-015 - Mandatory Testing | CB24
c985be53-36bf-4b21-a704-70703cbe6742 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2
ea6d9071-0899-4ee0-8954-c8b2ba60eb2e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2
6b9cda1f-0736-48e2-97ee-c5cc119f3ca5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-029 - Rough-In
8f039335-bbd8-46ee-bcbe-2f4d96d21aee |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-030 - Cut-Out
b71add51-0d9c-47ca-a884-2a7c70856ac7 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-31 - Fit-Off
99678995-7e0a-47be-9ea6-57b514ae77ac |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-018 - DB Fit Off
eafad5fe-603b-4dcb-9118-15c6001a7671 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-32 - Commissioning
8a513d00-8f3a-403d-a59d-412564fb857c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing
a4cab781-90fd-419b-a38e-d8b65e21ff09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB1
c8860ea2-3eaa-4546-afbc-062264e7fd2f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB2
8a393af2-ef65-4368-9197-417eb60de46c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB3
e18b76eb-5a8c-49df-99b5-3b508d113e4c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB4
30452fac-6c87-4ee1-b4d2-cfbec8d17b0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB5
2d88f7f1-51c3-41d8-b845-5fdba0f79bd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB6
54e589ef-e779-439e-a3fb-a0116a0e08a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB7
86dce34a-b06f-4462-ba4c-6a9c8768f46f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB8
5c9666a8-32e4-4451-8bdb-8cd765b5ac15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB9
a48de50f-832c-460d-b917-b2c5a3480b78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB10
b1f6ed14-f1e6-4bd6-afdc-7c7550a5696d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB11
581422d2-5d9d-452c-826b-e6a2393ba326 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB12
38ed6789-d4d5-45ea-9ffe-c1c7ee40a98a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB13
ba1f8af8-ac6e-4fa1-a12d-b0bb17e2b55b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB14
3b9a92b6-d120-49c0-953b-f6912eca5aab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB15
be6ef49f-c687-49ef-8fc8-b3984580d754 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB16
bb2fe3f4-a924-434b-a6ab-aceda919e14b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB17
e116361a-01d1-4af7-b890-ae4e7519482a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB18
d082b7d4-9379-4d2c-8329-6ce9c17c9b5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB19
f0fa48df-e609-4686-b978-4de5a512de72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB20
8d21ad0b-7ade-4aaa-ba25-3ca4a32b7db8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB21
f7aad21d-4b0c-4be3-bad6-5d9d882eb9ae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB22
44c0608c-4b3a-4f71-969c-911e7f794781 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB23
1d00aad7-684a-4aea-848d-a2146cf3381e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB24
1f82a8c7-abb8-4661-8e40-730b0d26bee8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB25
006c463e-7970-4a2d-b064-dd09e5964999 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB26
28056e6f-2351-4ed7-9841-d6c44a9d875c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB27
5199e76d-bffc-4b9c-a59a-5f1228135d79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB28
8698be7a-aba3-4ab4-9a6b-5998edf757e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB29
1b970694-a611-4a97-9806-728c490cbd3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB30
ab7a2ea2-27b9-4012-a742-ea0bb58d3552 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB31
b6d40f51-f046-4ad2-bf91-60bfb5653bee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB32
3889626a-487e-4c9a-bb49-ef1bf9f29826 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB33
d2aca0ac-06f4-4a48-8222-027b6bca2ce5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB34
fda1e7b1-a456-4ef8-ab45-c5b27f863b59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB35
8842eade-a3f2-4fd1-8274-2cf38e83379d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB36
d460eb91-c6c3-41a0-994f-5df0cf70d24c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB37
5c3e62e0-fe6f-4f15-8201-736975b99561 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB38
29bd3288-c32d-4698-8bfa-cff3c329ad2b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB39
3b7c03be-8ffe-4f11-83b0-6323be624e27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB40
d1aed538-3063-4862-b966-541a2e51dad9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB41
ee71e870-4f16-411d-a155-649242746fb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB42
136089f1-aaef-4977-8280-554c46200bdd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB43
f39fac38-6964-4962-ac73-5e7fe4f39eac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB44
49b93292-6f14-4e6e-b557-6f989331dcbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB45
f9967c5b-46ea-445d-8ba5-8b3db4942e90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB46
b4617b42-9d45-4336-9453-d8488ed1a011 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB47
c6875395-a99e-4295-aa4b-d0fff8d48937 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB48
f8e96765-f972-46f3-b6f6-07f775b46549 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB49
51136e7e-8302-4b7b-b17b-e536389a0806 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB50
128ac5d2-3130-47ff-81db-43b6193edde5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB51
6791a920-a471-4eb0-8f8d-4b2cb07425ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB52
f7db31df-4167-4001-a6fb-5b0603b7d277 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB53
f6f3dd64-6d57-425d-a820-2c9e8df3bfaf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB54
57b1fd64-77bd-435a-a97e-986a05789235 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB55
4f19d3cb-1b34-4155-a010-c200e6070a7f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB56
99de8efb-7194-4896-aceb-4de9b1323d19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB57
845813e4-34bd-41c1-8380-e91ea307ace5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB58
88f752f2-143a-4ac7-b5e5-5b83d0a0aa2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB59
484c26fd-00cf-45aa-bfd2-7f0db778f4a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB60
2b448e1f-2906-4a5a-bbf1-71c24b4f676a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB61
6c7edc29-1874-4eb1-b67b-c960a65db5e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB62
21611118-fbc6-4a12-9b6f-77b5d4f63891 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB63
05cf7abf-f076-4eaf-a358-3ace3e901019 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB64
d86176bf-0a49-4f01-94b6-32686658e58e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB65
5ee146a0-529d-46c6-bd1f-3dcbf7a97b32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB66
446445cc-7890-4daf-9649-c6a8c5e2c5d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB67
680c6ef7-e4b6-4929-94b1-5d6b2dfecfaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB68
51269229-06f3-481d-8fe6-38a0feeab629 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB69
ecb0bcaa-833d-495b-ab1d-970235e7d72d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB70
0b202820-51b4-47d1-a02f-576a9c0942db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB71
c417d994-f117-44de-add6-974d08f179b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB72
bf9e89ea-0aa4-4a0c-97b4-4905f610e1a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB73
b5b8783d-ddf4-4cbd-aaf7-589fabea8428 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB74
f531fb7e-b5e3-4f0d-a27c-3e1fe346592c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB75
2dac8b9e-d0cc-499e-ad7d-51b07eb96eef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB76
f83bebec-98b3-454a-9a44-132f508e303f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB77
d3d55de3-bfc5-4ce3-9bff-9a548310fe18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB78
95ba49e8-1538-4b28-ba7e-be0eafbba66d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB79
a56d227b-cd7a-4ed4-bc50-085b6755e1b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB80
4916a719-cca2-4e44-9626-dfb29c1956f6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB81
edf16d9c-8c6a-4135-8269-de35ffdf3394 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB82
9481e420-ed92-4891-b37a-1e5e76e5ddd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB83
22b1001e-d092-4e8c-8a6b-f3732963563c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 2 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing | CB84
4ea88864-4342-4543-9f55-acae8fea36aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3
c50759c8-ea5a-4876-bbf6-8fffd4f1864d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3
60bd07c3-9ca8-467d-87aa-7c4363ac4907 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-029 - Rough-In
624b06c3-850f-4748-9ed2-c86706b3ed4a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-030 - Cut-Out
7f791338-df85-4045-990a-5563f532dcab |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-31 - Fit-Off
bb63e55f-30e1-4279-9da9-c02a4c45d5ee |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-018 - DB Fit Off
98db9adb-82cd-4ccc-a132-a6100b4a0f22 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-32 - Commissioning
1add49e2-3acd-4f00-9bf2-0e54a6eec267 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing
1aa6e12d-2eae-4246-89a0-1468dcb6622d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB1
590e7c34-23df-4988-bb5a-c9d9e58c04b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB2
af02a27e-4b2b-4bcc-895d-9da835a613f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB3
9ee0eaae-ecdd-410d-83a8-81a1f9e32528 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB4
ed3e0ca4-7dfd-44ad-885b-0c5a50517118 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB5
78ea0af0-17c8-43aa-ad66-6090a1b76745 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB6
ac80da17-9348-452d-90e6-03e00921ebc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB7
65d4890f-a99b-4f82-a766-4b96ce5d4a34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB8
1c06204a-bb89-4cf2-9164-ce3783793344 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB9
e914509c-69a1-40a8-a45f-2ca7046084de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB10
074eb5ca-515c-4313-ae58-253b37d3f17f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB11
fba7f941-5a12-467f-9cf9-c2081cbfa66d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB12
f1b8e8ba-dc1a-4414-aeb3-2e948419ed6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB13
78e3ce61-4603-4d11-b87b-9271b84e10e5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB14
ec6e3042-a9cf-4e97-99c7-4c672763895b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB15
b9a896e4-fe95-45d0-a7f6-a8f2dbedb7c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB16
3e862e75-7e2b-4398-9055-0383a2019c37 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB17
1e355062-8188-41c4-979b-fcee49573b22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB18
01336c0e-ad13-4b2f-8798-aea7513f743a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB19
4f14caa3-459d-48bf-bc21-8c03298dc745 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB20
56ffbdea-1b76-45dc-a3ec-aafd4c674f93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB21
7bd69d05-3b93-4b35-b2dc-65de0ce26b66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB22
b8cd7317-0727-4bdd-8170-1a3be8773c8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB23
fbfbf15d-6e95-401a-917e-a1051e4405ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB24
8c5018c8-278b-4b8a-9e7b-e23b6468fced |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB25
8d23c6c5-3e9b-47a3-b9ed-298fde41e499 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB26
13ccfa52-2f87-4427-910c-7bb5597113a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB27
4e529656-b90c-42e5-af60-4f7e0b6ef59c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB28
c7280dbe-c47e-4e0f-aa37-0a9bf23140fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB29
06b05a93-c97d-462d-9f1e-2fd6f59a5037 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB30
c7c56ee7-3380-4326-b8a0-a0453ff35eb3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB31
fb1bcf56-709e-446b-aba8-c6bf36d20197 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB32
8cfe16c9-bd4b-4724-ab8b-ee5400b697db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB33
cf9a97c7-352c-482e-b254-bcf9acd9bfd0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB34
ed069689-9830-4356-a20d-fda68eef4bc0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB35
8092dd98-65ec-4377-a0b2-8d5469d54338 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB36
292b1a81-746c-45c3-83c5-296b88141be0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB37
26d11547-c0d1-459f-a7cb-dd9e511207df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB38
1234910f-a346-41d7-98a9-86dc9185fea9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB39
1fbe99d8-7bff-4407-a037-12dd92831d65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB40
8fc5a919-198a-49e8-840a-2125a853aa8e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB41
d1712f36-a000-41d7-bdc7-8c0ada90d65b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB42
0eddcd81-5d6c-4849-91ba-e4829925362b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB43
fe0afaf2-544f-4cbc-8783-4125d8d3baba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB44
70640f80-691c-4efe-a514-4cab6d78958b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB45
99d05a97-9901-44ec-8208-33183f1feae0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB46
af8cdcdc-435f-456d-a9e5-2bc95eabf5ab |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB47
f01ab937-53aa-47dd-b722-bb2246b3a7ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB48
cfa00fce-f2c8-48cc-8403-cd3fceaacd00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB49
70952304-ad8f-4bee-8929-4aa0b7cbe308 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB50
265cf3e9-a584-41d0-a81d-71881222c7ff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB51
df5db4fc-1a66-445e-9ffd-36ab6f140106 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB52
7e3b3c58-3621-4f5d-8eee-ff0b061ac993 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB53
0ea3f4c7-b104-4e23-bbdc-6c5c4347bd3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB54
501b8245-d198-4999-96f3-99cfbae9535d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB55
09d7edde-095f-4ced-88ec-b830362b11fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB56
b26e535f-dddc-4d81-a454-30846f7f78f5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB57
3a548b7c-0eb2-46ac-9c77-65bc0f93888e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB58
831b0303-2311-4da5-abd8-01772f3ee9ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB59
c16e78de-3616-48a7-a096-6bf06f64e998 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB60
9620c712-5869-4c39-ad04-013a84af7629 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB61
3d3b29bf-b5c6-4f58-a0f7-f382cbf1eeb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB62
c64dd1d0-ea86-4a5f-ba99-7db9369a2f59 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB63
001757cd-0fe4-45a7-b928-d03522c89f44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB64
c3868113-fb62-4a98-ab6e-2861f4eb2e9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB65
4ad54997-a823-4855-8ce3-ead577b5746c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB66
47aaa9b5-117c-4b27-aa3b-1d9ea8385bbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB67
d4e4108f-b301-4e18-8d13-45d69950c0a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB68
6ed1fe1c-b6af-45e0-a92f-b2baaf304bde |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB69
8e3c9117-ec51-4e5f-996f-92a2baad00f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB70
8a901463-8243-448c-ba34-22c7edcf1849 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB71
fca6b931-d391-4155-8510-706569d7630d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB72
232600ae-9dec-4753-8a1a-c3f7eaa74991 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB73
2f4a8159-b7fb-4722-91f4-f0dcd909bf78 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB74
e9496ded-7bee-4ca2-8c63-09a2128f5240 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB75
1ded8cf3-a031-4cdb-abeb-301a6cb1e1b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB76
305d1860-a67f-40d7-b1bb-a7da3a91d753 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB77
67d51ab4-b349-42ad-a19b-a677e8020d6e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB78
856a5afc-7819-4a7b-8028-11fc39eb4d3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB79
16cdcbea-6e3e-4f00-98fa-1bd46f214eb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB80
8d9bde30-945f-409a-8443-42b473a8c674 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB81
811d512f-ced8-413e-ab1e-727668199fda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB82
0ff4c574-fece-46c5-aefb-ba569ef6c646 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB83
af2d5612-28b8-450e-ab7e-aa9432b03fd1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB84
66906330-4dd9-4c44-a633-d40ef8ce5a08 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB85
1ef140de-46fd-40bf-b189-9d186cd6670f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB86
dd086e65-026a-4717-bb8b-adbef1288a93 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB87
5ceab72e-b405-4e1d-8f82-193584ad0b89 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB88
d73fec9f-06ac-4079-be47-5f178efa1e7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB89
34bff1d0-e9d6-4cb9-8422-91d3a7cde470 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB90
aad610fa-9617-4fdd-b7d3-ff297e177e6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB91
73943f7b-d77f-4488-9805-ea32ba5f241c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB92
fe1018ec-ecac-4999-b40b-2266501c3997 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB93
525974b6-f595-4c3c-8167-961450a6dd1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB94
5722b364-aa6b-4d62-b33c-9c68feada6fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB95
7c307d09-b7cd-4890-b0db-84ee1e6db7a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB96
4f15b52f-304e-495f-ab9f-45a06325c323 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB97
f76ececb-cc76-47a5-805a-b57c9ea5f27f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB98
41d8e620-e629-4673-8e6d-b45054b8c7ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB99
31c8f6e1-e27d-46a0-8db4-de6f2cf8d8d8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB100
82131019-b576-44c6-a690-7fc1225cb348 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB101
b5698530-b3f8-4ace-b6da-171221fcc69c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB102
8baa6256-64c6-4d1b-8561-540bd90e30ea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB103
d21ffd8f-b3b2-46d7-8932-a9d6fffc23f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB104
326b0f9d-9101-436b-9381-4259241fe8a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB105
aae4dcb2-9350-4a3f-a364-4b48a0d7fca4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB106
14f6bd8a-8a3a-43e5-8ada-72cc6e0181e3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB107
3e30f51b-f376-4210-81fd-c4935c1428a4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB108
ce5cee78-3f6a-49eb-a83d-44b0b0b208f3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB109
7b20813a-fa86-49c8-9060-1a5803be7c32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB110
6ddf145d-46a1-42a0-bc1c-af542898339d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB111
27fdbb12-dc1b-4170-b113-ec7e53244e24 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB112
9e46c547-022b-46bf-b734-fdc0779e763f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB113
8d2f5821-ff99-466c-a908-cc56de3412db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB114
3c289fd4-6c18-4e65-87a3-3659a3de4d5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB115
a7908d35-4f8c-41dd-bd69-a6416ff8d013 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB116
cf90e72d-2ec7-4cc4-a70a-adeab0c5cdea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB117
6b3a76d5-fc2c-4c74-b22d-1e4832b68818 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB118
43b19b25-3c16-4cdc-9a2e-fbc1bf57aa3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB119
7f155400-b0e8-4eb5-931e-8ad4a1be86c5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing | CB120
924ff894-e38a-4272-a301-fa1313987283 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3
b8730779-d78d-46ef-81ac-de93a10fe01b |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-029 - Rough-In
b73898e3-5fe1-4f49-be90-f3556d000abc |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-030 - Cut-Out
eb1892a1-3ddd-4b2b-8185-3d8219688057 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-31 - Fit-Off
ecaedd0e-7d2d-4fd6-a74d-9437212c6ba9 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-018 - DB Fit Off
50061879-714f-47df-af96-2c4c99dd9c23 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-32 - Commissioning
9e5aea0d-608c-4bdd-bb0d-74e05a14c94f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing
84e6e450-505d-45e3-b00e-4582cac02137 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB1
6fa62835-f8a6-4c3e-add4-406d7f2fc63d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB2
149b07b1-cb66-4781-b8a2-c7836f8d5d9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB3
882bc025-e885-4409-b761-e37480865ad5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB4
1e68f452-9614-4e12-be7a-7507f5fe6d7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB5
32750a1a-e446-4dab-9877-66b86b4c99b9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB6
902b2c9e-c6ba-42a5-860e-d65da5b573e2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB7
6a726a32-559e-4c91-8a62-723e4602b250 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB8
91203a54-68c7-40d2-b4cf-b50dc42ec4a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB9
16cb870f-234e-43ef-a2d4-d338332293a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB10
3e914107-8865-41dc-9e90-9ff8c99369ee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB11
09294a28-e4df-4182-82fa-e57dadd4c22b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB12
c2fc94d9-1c7d-4106-bbda-f8ee3e8851cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB13
e2c0ea4b-93c6-4645-ab39-b68438bf76b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB14
6881ff3c-e0c1-4a69-b01d-3a344fd956cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB15
61956848-9641-42ed-957f-fecfd4a4ecbc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB16
6b7ff57f-8940-4b09-96b9-13ed9ca923c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB17
e8f0c447-4f7e-4c63-902e-daca2e6d5a21 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB18
02f99207-9538-4397-af63-5e6f2d0d4e35 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB19
6f7748f5-f0f2-42be-9869-4670559129e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB20
fc0e1414-e50c-45bd-9fc6-acea42eeb3b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB21
44313e54-8878-456d-a649-5f3ceb6fc2ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB22
d84bc17d-6f64-4c80-821c-4638e6d92698 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB23
baae0694-0edb-4a4c-8283-67d3181949fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB24
cfd9d43a-07f1-477e-a8b0-92bd6d6deaa8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB25
204dd1b6-b925-40cf-9aba-f42735a8661a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB26
9d4f0283-d5e6-4b72-8a09-a422bbd965c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB27
8f29bb9a-9928-464f-840d-cd34d53671c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB28
d3a41115-2900-48c2-9583-faeb3ccedf56 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB29
8c3e2724-bc98-47c6-aaae-04f36190b203 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB30
3512ff6d-7cd2-480c-b1dd-f3cd78994faf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB31
5eeca586-584d-44f5-bbd2-30c9e39c7340 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB32
2c036b2e-7fc2-4120-a5b7-8c57cd0fc820 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB33
440ac394-4296-4cde-8d4c-7a57a8ef671b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB34
9e622d6b-cd7b-4888-9ed2-5fb339125b64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB35
c7c80994-0e0d-49dc-a7ec-e1be598b1985 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB36
c6b75b4b-ae09-457c-b1c5-3a1b835f8103 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB37
1f3f842a-2e29-43e1-9164-5c6f498a23bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB38
c0b4f38f-0eb8-433d-9998-9ee3a611a51e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB39
d367a390-d194-44e3-88ec-1b53d434e580 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB40
ccd8c88a-1455-4d25-a854-401265774124 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB41
0ee22688-bf80-4871-94a7-a2c159df6a9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB42
6abdb376-f400-4e90-87ff-ad0f48527af8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB43
b173feec-792d-4dd8-b93a-b0b8e17b2b5e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB44
b55bff18-14f6-4a13-9398-f66deea8ccd2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB45
a27cdd83-d2b1-4e62-9a45-da9461f53b54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB46
9f95702b-7220-4976-821d-77c7fa688126 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB47
b34a5d0b-44b4-4a10-901d-e317993c69c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB48
87c996b6-adcc-417b-b33a-37e7a27635d2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB49
2857331e-e63d-4d1b-be42-e2152268faa2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB50
03668a04-9980-480e-9bdc-360ee7a9b350 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB51
7751aeb2-9d73-49b4-b492-1ff1aba7aeb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB52
3a9cb66d-da2c-4426-b4d5-7dc61827f59c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB53
1abf423c-6704-4c81-9d52-920a8e7caa7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB54
ee4f28ca-c972-4635-a56b-aea5ebd8ab6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB55
ab2cba93-a545-409b-a96d-ee03622186b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB56
3d729510-4567-42dc-88fb-b26eb9af5a1c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB57
085b2a97-4f2a-4714-a204-f03bdac028a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB58
e9e488ff-a783-490b-8206-f685cc4196c8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB59
7a04fea0-3ce1-40ec-8b03-b372aecb09b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB60
aa7d4af5-9677-46a3-8309-76a7f614da31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB61
f7791a6f-37ec-4e34-bbc4-566684e94a1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB62
d213daa0-d9ec-492d-a2f8-fde8e0ea31f2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB63
9b674ab0-6b42-46dc-a754-32061c8f92b5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB64
e977fbdc-e5b0-4b00-9682-79617ad83487 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB65
46931bfa-7bba-4687-a59b-7e1de93b79ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB66
e8559132-b5a3-437e-8ae0-a13e8991877a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB67
9d3b9cd4-d0e4-48e7-a5af-55db51edd972 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB68
f7b253f4-7b61-4d41-8d9d-ebc95a4841eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB69
062f7ffa-410e-45ff-9970-e32711cb5c3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB70
2a26b8b9-e230-4d95-bf9d-395f69827999 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB71
93d26762-7958-4734-94ed-7533a5a97730 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB72
0e0d6a74-bedc-4bca-9662-025f5dec9e2a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB73
594aa94b-b6fc-4483-a538-3d45db54ec72 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB74
02ba5696-ca76-42fb-88e6-4aaa2835d0dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB75
2a43a94d-c3b3-4082-ae74-85392e536555 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB76
f430880f-ab29-4fa2-964a-24257aa75295 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB77
895b5810-52cd-4b7f-aa9b-45e51bfa49b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB78
c202fcb1-91de-4a3e-93b1-8d8ca89452a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB79
cfd9c6fe-b113-432b-b75c-d4c42580f2d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB80
d1cacb11-e567-4171-8dbb-d989acba757d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB81
354b830d-d35e-4501-b546-5e70a5d57885 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB82
7ed8e74a-132b-4503-84a5-5903d7b12e77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB83
144be406-19db-4ca5-8124-e708c876fac3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB84
b36c39f5-30e6-4d1e-ac5d-9bb9984473ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB85
d6a48f12-ab4d-4983-907d-982c172ba792 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB86
a83047fb-c570-42c8-9269-ea1ad87bba0f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB87
5649fcf9-17b3-46bf-8036-e72f1ed2949d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB88
3fb1a3f9-ce98-496d-82e8-36cbdc8807ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB89
9f9b0737-f0a0-420f-bb33-c88ed6f48f0b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB90
5debfbae-a5eb-480e-9be6-8dd893f18b6c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB91
3c1bcc96-82d0-4435-8530-d2f514bca3cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB92
ffdeb632-b56d-4b56-8a22-7918db45b8de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB93
dd11eec0-a334-408c-9c65-e5dfab4c4dbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB94
49431bd4-bca4-4f44-a263-b8cd4e7765ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB95
ff6a1a27-10c6-4620-b8c3-3640c6b5a340 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB96
3936a0f6-db72-4b1b-9afc-549dcfe1aaaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB97
88097d89-981a-42c5-b871-df2002c3c831 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB98
0674ceac-71d0-4e03-8aa2-5f642a3dcb52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB99
31cba869-c6f3-4bb9-9b2e-dce89aaeaba6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB100
5356764d-999f-422e-b551-ef64a353849c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB101
0169a1a9-857a-42ce-a0da-b2e5360e60c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB102
732d0d08-c3ad-4fdf-8bb4-862fe9b635fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB103
0700a929-4e5c-4b73-a0c0-52e1a382d246 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB104
ea49b5b0-f67c-40d8-88f2-49eaf566af31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB105
c6552414-557d-4978-9b74-f80ae4882c34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB106
d0860d1c-c01f-4438-b57c-333b4abc9a4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB107
4217373c-af60-484c-b647-e218b588afd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB108
cb9e1cab-fc31-42c4-af0a-aaae01762c30 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB109
12873724-c659-4784-85ce-9cd734992f5a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB110
c49a1881-b9c9-4537-bea7-4e2b4f4182cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB111
59f0e839-7185-45dc-83ee-da0ab1bae3d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB112
c7bd5518-b2e8-46d3-b72d-5664bca777c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB113
2c2d9e8c-28f8-4db0-8310-c8cb7218fcd4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB114
9dd542e7-594f-46b8-97bf-f80ff5858d44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB115
7d8fc399-6408-4f80-9156-24dbc2cda446 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB116
1d99ce8d-a8c1-4e87-bf52-f4abd9eaa1c1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB117
73f9f7be-ed5b-43fe-948c-c5d9a64098b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB118
e704310c-0333-4c71-b7b5-e6a5e70d5bb0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB119
0499e81b-1b7b-4aea-bbb7-e47a7b487b22 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | Basement - Level 3 | Level 3 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing | CB120
e61bceff-92f2-4bff-9352-6ba3e15700ae |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1
1393046a-fa26-4c18-b795-e38b9267cebb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7
5d03b30a-9613-4a5c-a894-83ae7fee5086 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7
82f80a75-c151-483c-9595-72c9c24a23a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In
bd42364f-c3b0-4dd8-bd02-aa990a23ff9b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 04
e668d1fa-1eb6-4935-bbf7-55f0dcb49e4a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 05
059db860-e241-491b-befe-eefda17008a4 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 06
ddea72b0-feef-40a8-b5a6-bd3e527901c1 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 07
5cfacb76-a34d-4871-9b34-16182d47c64f |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 08
3803c1c4-b6cd-42b4-9c19-1d976d8c0c8e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-029 - Rough-In | Level 09
a1c77e40-9184-4071-bcf6-bea291f6191e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out
b8105023-c521-499d-974c-a4031dc2569d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 04
59c41d88-6009-4560-8f39-b5076a310134 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 05
5d5ecbd3-6823-449d-89b7-c88afe956fac |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 06
e5be2b3f-feb8-40c9-af80-6f0fa89915fe |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 07
b67d0f48-6e50-4232-aa53-d715f23d70a3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 08
9d706c14-95eb-43e5-9695-74c69c42532f |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-030 - Cut-Out | Level 09
5281fcb5-4e83-4c89-b835-3b3550580e88 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off
b1445bd9-1abe-49d0-9f27-3421c953f04a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 04
e9f4b0df-ba5f-4efd-9c33-c804b1c2835f |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 05
e9dc6ab2-3b98-4cc1-9742-f28d8d18e58c |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 06
28821bf5-dca8-495e-b721-001a84ce2789 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 07
21d07d2f-4862-4cbc-a6f5-b7d345c3a2e7 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 08
139a6e37-c0ed-46dd-930c-49acef8478e0 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-31 - Fit-Off | Level 09
9434d32b-7a54-4667-af49-9e7969960ad9 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-018 - DB Fit Off
2aa481af-4aca-4b44-a1d0-170577d5b87b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-32 - Commissioning
58f30dcc-6222-42ce-b38e-7050ef99c0b3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing
1662ddd1-236c-4073-b812-4583309fc3a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB1
84c41cf5-445a-48ec-af82-6425b45ef785 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB2
8bc65f9a-a515-48fa-8bf8-2276ad2ae5ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB3
dfdd34be-c42e-4769-902e-116983228171 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB4
581a0062-24c4-41bc-9dcc-e645755cfd01 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB5
ebf03588-758e-49dc-834d-185c33e12042 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB6
c454874b-54f1-441d-b001-d87875a15a02 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB7
a2e52b62-187a-49e9-b2d6-68839c2bbe32 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB8
1c2d79ed-c9a8-41af-bd66-07520ebfd389 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB9
7ecb4572-068c-4d9c-8c11-3fb07b6cec47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB10
d25b79d4-1a2c-4371-9331-14c692b0fb74 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB11
0f66dd54-996f-4c66-87a3-3554bd76efc7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB12
b7c4b53e-294a-4804-9fe7-7fcbba0829b1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB13
a103a7b3-d32c-43aa-ad56-d75efcd7d414 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB14
e3044f61-eaf6-42c8-bacd-1ea7737c3598 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB15
a223b370-834a-48eb-8b95-40606a962112 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB16
e6b6dc33-0729-49ad-ae19-4c5d554ba726 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB17
2748c98e-47f4-4d5f-85a5-5c3100662d73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB18
91150dc4-494d-4a40-b12f-64e962143a60 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB19
0be7071a-d65c-462f-99c2-427b01cef5a0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB20
0d2dc73d-76f8-4744-922e-57911ec3c4b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB21
744136b2-0591-4047-ac43-def3a2e126a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB22
f1846cdd-5c2f-4f87-adfb-959214797018 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB23
34bc9a79-4be4-4cb2-853d-277deb99cd50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB24
3a55b6d2-dbef-44b9-ac38-753284334b84 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB25
e950a14e-836b-42d0-ac5a-5f7d01e45ce9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB26
2bb306da-3d03-4f30-a332-c13d528fa3c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB27
f0aa9f6e-3a32-46e8-b7a1-9419b366ee90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB28
20f597b0-528d-4c59-8df9-6d51ecd64dbd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB29
bbd745a7-7dfa-4bbc-ac2c-93b3d354ab99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB30
f5c2b571-89ca-4d24-8f28-4f563a755a6a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB31
f9c56011-872b-4000-9ea0-25c7e91902e1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB32
ce0cee51-4d06-42eb-a805-f107ee181ff7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB33
d3e00c43-0b49-437c-9b7b-6fe005ad9d53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB34
e8bc8404-2a57-4497-936d-ee91754cb985 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB35
8a9028dd-cfd9-4ad9-978d-3fe122b70d25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 7 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing | CB36
98566bfa-a550-4647-9376-1d8351125bb7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12
04280f49-2b68-417c-a6c3-89c7c4856959 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12
dd8f515b-b0e7-44cd-a3f4-73c07ce4b6dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In
76bd2ffa-5953-4772-8f77-85ed9bad11d5 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 10
d3b2a159-81da-4cdb-bedc-377874b9a9ae |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 11
31dcaa9f-0b7e-40d7-9110-6d7bd9dcb8f2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 12
45e387bf-000d-4ed5-a17e-0315d7df4a29 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 13
01595d32-7be1-4ee3-8b67-8c710dc2d3e9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 14
3a1e997b-82eb-4c15-b8da-a9776caf39b1 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-029 - Rough-In | Level 15
ebd51256-c00b-4159-811b-bc4e3f277f0a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out
fcde3ac4-9a8e-4194-b34d-1c1943e94795 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 10
67c607fb-5343-4648-9616-402b783ba4dd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 11
742de278-df19-46f5-96c9-9ab533068cc3 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 12
d3cf80ea-88d4-407a-ac61-12a68f5cda31 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 13
84c261a4-862c-4b9e-a62d-71c2d0895bce |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 14
02a884a3-6162-4499-bf24-6e646993cb95 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-030 - Cut-Out | Level 15
1c123184-900c-49cf-bef9-67180c3d206b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off
f5183a12-e3b4-4a4f-829e-88f48846bdab |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 10
992524a0-67b3-483a-a200-9c145221d0e8 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 11
2626f5c6-d872-46a1-aee9-613196371bfa |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 12
ba91f706-fa34-4d67-8f92-f89892e6b754 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 13
8643ffc2-fcca-4a25-9b2b-394fea66d7b2 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 14
4ab6026d-00ec-4235-9e1c-f57843e1aef5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-31 - Fit-Off | Level 15
42de8a7a-0745-4139-824b-cd0fe296dfb9 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-018 - DB Fit Off
ef3c17b1-6c9e-4236-a58f-acb8b453875f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-32 - Commissioning
563bf9c0-6f32-4b12-8153-d0d2e5282750 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing
d95248b3-7a62-44dd-b993-51a0b46423e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB1
126c6f0d-6ea0-4312-b0c5-1cd5117f0d26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB2
93382db3-3b71-455a-9aca-64a71355ca9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB3
c0f75661-33ad-4efa-b82d-ae1bf45c504c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB4
d159354b-dccb-4eea-83c2-6ee233318268 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB5
2354df74-93c2-4af4-bd09-65c6d16a5692 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB6
3ed36080-19e9-49dc-ba75-8effab975409 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB7
3330619b-251c-44f8-90ef-086f9fb7c63f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB8
d5876ef5-8e44-430d-ba40-4ff4b78f49af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB9
db56b758-cc68-4974-82b1-70e2835ec0cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB10
f10367eb-62d4-4d84-9e27-77acdf7e74bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB11
df0c659b-5c8d-4831-b338-30ed9032ad2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB12
91eaadb3-66a0-4373-948d-78b75f3945d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB13
e3ec39a7-6a1e-4e6f-9430-a77f91593521 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB14
152bce88-2bcd-4fcc-89c7-c9b5302691c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB15
d06f356c-b2e5-4011-a7fe-8cd85d8393e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB16
c82d9f34-4e3e-4aee-9454-eb2a385be102 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB17
b26fcc4b-2216-446c-9767-9e1c56a7729f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB18
762a4c43-66d6-4eb7-8db9-a90261a43c63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB19
84fc7913-1a8b-4be1-a2b9-a019aab3a971 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB20
168533a1-8234-4945-875d-13951034e891 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB21
c56f5474-dfb9-408d-8f1d-4e8cc4e4b3d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB22
81b02fc4-0584-4383-9bf0-52f0fc75a9af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB23
732e9b1f-01da-4075-bf8c-127b2ab23625 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB24
193a2563-0aab-43e1-91f6-3f82cb73b066 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB25
b7a7ae27-5411-4156-9aeb-a541f053f9f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB26
d9c13da0-076b-4919-9b8c-4fa97399bb3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB27
9e28d1f7-96fa-405a-95e3-2e9364179b83 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB28
8a49f550-ee65-4d9d-9fac-487e8e9c5dc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB29
bdd5798f-63ac-43b0-b68b-5558630926a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB30
9b5120a0-0f0d-4df0-b663-84ec506b9ae9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB31
95f9389e-5590-4783-a4c5-6075712bbfc2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB32
7cb6725c-8e3c-4d9f-9ab9-7821364bce63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB33
9eb4fd9a-f383-4d8c-ab45-673c109c8a73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB34
5afe58de-5942-403a-9323-dbe8ae5f0f94 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB35
66ad7a93-f1a9-47b3-ba7f-74a9ea58bc8d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing | CB36
f1bddd84-97f9-4b54-a686-509c168209a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18
9712d972-a2d3-4993-a40f-cc6c20c297f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18
500ccab3-dfcb-4369-8561-e8d3c30ca55c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In
e1c4ecd5-219d-4cf5-8f78-4e5b5534f79d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 16
acd24fb6-42d6-4cd9-8e73-a9c2d854e245 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 17
3f8b394e-38aa-4f05-82cd-06c469fd038a |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 18
d7c147a5-ca00-4ea5-9cdf-2556233dc1f2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 19
f55b66c1-6288-4d78-abaa-4260047df66a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 20
9a4817ba-6e44-4238-910f-ebafce3f833a |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-029 - Rough-In | Level 21
13aca88e-5be3-4df5-a58f-73cb16cff789 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out
fa10fc29-8eb3-4005-acd5-ad5dcfdd120d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 16
52225b22-5b0f-4446-b3c9-a194477ba05e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 17
20717ddd-bd05-49b7-a340-8d675bba7269 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 18
494c27bb-3cec-4168-a805-6e9f9c0cdc4c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 19
928c8b43-22c6-4c64-9f62-1c63e6487fd5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 20
bb977db4-346c-45f2-ac0c-300b47a618ad |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-030 - Cut-Out | Level 21
edcf2389-faee-4ff1-b7f5-f570fd34fcf3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off
955a4993-de45-46f2-8cbd-83bbdda402bf |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 16
fe6345e0-f546-4519-b6f1-d34a121048d1 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 17
bb07795a-9b17-4e3b-be10-e11ded5e3845 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 18
fcadd9dc-391c-47b0-98e3-12483c58692c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 19
2ff0bc9c-3803-4bd0-9fc6-b96796a612db |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 20
37c337b7-3637-4636-9000-7e4b1ec1a4d6 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-31 - Fit-Off | Level 21
f1ec09db-5615-4126-a08a-d0ab0a1d42eb |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-018 - DB Fit Off
0f20f280-d514-472d-b7a7-1b41aa7dc4b2 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-32 - Commissioning
1c633c36-6d13-4c99-8cf4-46f475ba27f1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing
b597470e-37ff-4c41-a96c-db368a39c5be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB1
36642295-fd1c-46b0-a735-5ff70f999e3d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB2
5b4d5b95-ecb3-458b-be02-9f1bdcf6a506 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB3
9674be0f-2b57-4e79-9c97-21d01958383d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB4
4dede9c1-ceb8-4e93-892d-abe43d598b9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB5
68d6323d-0f7c-488e-a4ad-fe253e747eb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB6
9c7230bd-bac9-47d2-a535-a0015f3617e8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB7
700a7cff-413f-4630-b987-33eea4820b85 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB8
bf0141d9-1e80-4c7a-8cd4-ea03ddc80ae5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB9
d76a4177-241d-468b-88da-9913dd046a26 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB10
6152be43-7d69-46dd-9b0f-f808b20a8361 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB11
91eaf567-78fb-46e8-be72-f412ef910c41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB12
0c01a119-643e-486e-a0ae-b5f59627f309 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB13
988cc200-e32e-4f65-a73b-f3487f032365 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB14
1b8d2ed1-f4f8-42d5-9825-4c508e590519 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB15
29121dfc-2b78-4fe0-8d8b-fcc19d3473c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB16
ad170880-30e5-402a-b436-e70d7b3deac0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB17
9f135df2-db7b-40d2-8465-d407cfb7c360 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB18
2647b734-f765-45d3-98ad-90bccc383227 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB19
6276ce0d-756c-40bb-b78d-10cff75d4099 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB20
aabc5430-b1e3-43a5-81e3-3d9516a3a55b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB21
5d2f25de-f131-4af4-a8c3-8daa8456d659 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB22
c8d0bb65-c0e5-46e2-97c4-c1ccfd91f710 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB23
5eda86bc-f192-4eab-8d4c-02861b0dde04 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB24
3089dac5-0598-499c-977a-04f49cb4be3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB25
f4d74ee5-2857-4f3b-ae6a-f085f246b4c6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB26
b64712ef-a0f2-486b-94b6-ffb79872031d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB27
303de113-e093-4042-a9ab-5c595aabc2fb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB28
8695d091-5b87-4229-8a8a-c2308e8b11cc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB29
57650d7a-216a-4206-9a01-8d1b5a54c0a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB30
f9e52101-baf3-4492-b240-d6edab40b016 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB31
b490ff8c-7fec-47cd-9948-f10a26aecc00 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB32
f4fab533-ab9c-4003-ae59-db97d5ce2051 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB33
8eade18c-361f-44e2-9032-c43bf051f446 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB34
4d0bf158-0a68-4f56-9344-dc07f10af4cb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB35
b2b4c7cd-f711-4e44-a008-8b22fc72c6c7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing | CB36
6b876cb5-3893-46ef-83dc-c90ad68a2e05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24
c2144bff-5a71-464a-be2a-5c1bae056862 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24
4efc53aa-fde1-4b87-9cd9-7e9b7a172f06 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In
c54fe943-3048-4161-9d16-0d0f7362b5f6 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 22
54c88af5-9cfe-439a-a7ba-eef67489741e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 23
9d532f63-b17a-49f2-b95c-97f295680133 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 24
72d8471e-0345-4dfe-badf-7d24bfe45ff3 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 25
26e7a106-e3a5-4945-a1a0-fcc3d1a42161 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 26
75dbd5ac-1cf3-4898-a76e-de32a45649e1 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 27
7e5900d0-878f-47a6-8f3b-ca6615abe50d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out
c59c3591-2491-4718-a237-aecbaba05b13 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 22
00f71bad-86de-423a-829f-7f04ccebfe76 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 23
8d89bea8-92ee-4bde-a133-9266b9d0e934 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 24
a7ca73df-9d1f-4c09-addb-374bd0377549 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 25
b741c223-3f11-4bb6-8667-354e35eeb94e |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 26
2609dd13-150b-4f6b-bb58-40c21808db67 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 27
20036a90-8327-49e5-92f5-2a116bddb536 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off
7a31454b-597f-48cb-b603-37a388e26454 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 22
3da0e8c4-0043-43d2-830d-5a72f4138a6d |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 23
b20c3a0f-9e95-408a-b5a7-cf08423e34d3 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 24
48e7089d-bdb5-4acc-af68-92e59db57a22 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 25
161697e5-5664-4628-8965-389442d0379d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 26
e6fefce9-6744-4ead-aed2-16f1e3ddb55d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 27
6600a8cf-1938-449c-8f7e-c231cd5d0e3f |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-018 - DB Fit Off
e4456644-14fe-473e-b4ad-69644cb3f701 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-32 - Commissioning
b3f36a9a-48b6-4945-9c59-6c0e2dc9fb92 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing
f565868e-e79f-4398-9545-08524c92e047 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB1
6cdc82c9-331c-45eb-ab77-4b3ae547774d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB2
d665c31f-a7f7-4d25-953f-80cc104f8442 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB3
8d6ecdc0-dd17-4e20-84a4-63e8aaf6aea5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB4
67f17398-3ba8-4fd6-8375-66874d094fee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB5
3ef54343-209b-4f87-8941-7ad66c5a1d73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB6
16176212-b90b-406e-9944-7404124cfde3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB7
14581c99-d9e0-4e14-bee1-44365c2a3388 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB8
03d8de0e-541d-4a24-962f-19972af12664 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB9
2cd17d24-ad71-4277-9751-d42465454d66 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB10
acfe7186-1dcf-405c-84a8-504276f49e09 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB11
fe041e96-7d01-487b-8f04-7f217bace64c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB12
75a4d88b-b82c-4894-82a9-5e172f2e8dbf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB13
fec9ec3e-3ebf-4091-a818-b3fda8d906a3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB14
bb84eaad-882f-4d20-a15a-a0a019e048ce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB15
291c62bc-6d39-48eb-9c38-e93e86589cf6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB16
ff822c8b-682c-4dd4-8d08-a6598798c2f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB17
e8fa6f15-db9e-47da-aabf-cf3893ade9ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB18
27dd4db8-f7ec-49ae-b6b1-074a574ed24a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB19
ab5909e7-ee0a-49d7-9576-eec1ec361858 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB20
3119b5fa-42a7-4532-a961-4cf385add614 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB21
47224d8a-972c-4c90-92ed-35b0ae665d9b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB22
639871f9-a5d5-45c1-9eee-25b3ec0a89a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB23
5750cd5f-9119-4bf6-bc78-257076d06227 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB24
aa80cb4f-c277-415d-8c5c-884412e15864 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB25
8eb179e8-a204-42f6-996c-7a588647bc9d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB26
52b21d6a-2b95-4122-846d-11e37ac1c03f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB27
d2e385c6-711b-47b8-ae82-a0f3fef50b3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB28
b79e26ec-9029-46b6-9928-c27ce1b43535 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB29
71920868-bacb-4a92-96b6-48549b44090e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB30
61d66ad1-f8b4-4f55-8766-d88b43b66d41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB31
01cfb575-34df-47ca-aacf-a82717893317 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB32
ec6f00ac-47d4-42db-81c5-d4c661683273 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB33
4bab3c38-bf13-49ba-940f-11be9d18a0be |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB34
a9aead9e-f361-42ae-8b8b-b2d417e4fa38 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB35
8592eaa0-da2e-43eb-8980-3d6947193fda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB36
14465768-9eb8-4231-a485-d45048f92821 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29
c2a98b58-d060-41f8-a2ff-509797213cb6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24
c7969c39-a095-47d4-9088-1fed09496866 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In
361d92e6-ffe2-4dc0-b202-cda745f1595c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 28
0e4a66a5-08b4-4f24-a16d-82bf20f159ee |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 29
a7b449f3-8e8c-4918-ba29-c6c3d658ac4b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-029 - Rough-In | Level 30
026f9bd7-6936-42ee-a594-9af75fbba99e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out
0d9617e4-1950-42c8-9d22-c60c2fca3213 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 28
b593bb07-8591-4260-8f61-04cd732d2a31 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 29
cd51b9ff-cfbb-4ab4-99d5-51c45eac703d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-030 - Cut-Out | Level 30
72179a2a-9300-405d-980c-0301147fa6a5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off
47c480ab-d385-4161-8bdf-891117f42b5c |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 28
28f7913b-556f-43b1-9ef6-912e5a361f08 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 29
7087a1f2-113c-4369-be12-ec474b7121a9 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-31 - Fit-Off | Level 30
32fb9b85-24b0-4d66-8aa1-37cf67ea6549 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-018 - DB Fit Off
0e617e9e-94c0-471d-b90b-802b68ec3f08 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-32 - Commissioning
6443d32d-eac7-4ff3-af77-37300d14ef7c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing
75f64fb9-575a-4ebd-be0f-c37251cb0915 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB1
e8e10639-fab6-4f37-8a08-b9d1b778b8d5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB2
e71b0572-6243-47af-87e7-646c4f5658cd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB3
725a8105-356e-4e2c-bdb5-b8bc8d058d52 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB4
e2b98548-c3be-4964-a21e-30bb211a0c57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB5
d669b38f-b621-4bee-8512-31252561f2a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB6
4c15eadc-ca23-4e40-934b-b051cc7f54cf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB7
0676e9ad-4add-49e0-9bd0-598ef8c8f683 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB8
167309a8-8828-4c92-8380-8cc67bf92b81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB9
5fe22ff1-0d39-45db-a4f2-e8edf022702c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB10
5444b512-6981-48f5-b85f-1af0451b3ce3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB11
d27484db-5b7c-439b-93fe-4ca268b70896 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB12
4207f969-c673-4ecd-bfa1-a3874ca47b0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB13
d73fe080-27c2-40e1-ade4-8f8c78c38d31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB14
5fa6212d-f2d0-4963-96af-197df676c4b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB15
f64fb608-e75a-4aae-b278-ccc7bbd47fc2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB16
97ff2724-7fa8-47e8-ab88-a31d44572c19 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB17
9ce4efab-e670-4dfd-b452-79c622103afd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB18
5f2edaf1-4d74-460d-8f49-9511f384ae16 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB19
b79128b9-8d51-4be6-881a-eb16f7916a49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB20
9ccf66c8-ff2d-427a-9732-7790da2b3fd7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB21
d4cba9f0-695e-4ac5-91a9-d38b35eb97e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB22
64ed0eca-764d-42be-b5ee-e39c802a6b96 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB23
5a4252c8-fe1b-42e9-a817-d707de330638 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB24
dda81568-5bab-4cb8-91e2-fb3c5557e9b4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB25
f425e928-e263-4016-b88b-af5a204575d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB26
d30472cc-ecaf-4686-aa82-cab8779b5749 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB27
24e7940a-29b7-44ad-a28f-ba81513aa0fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB28
6f465864-87f7-4536-943d-580655f8578c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB29
112a5c04-0780-4c3a-aed2-73325e2e5c65 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB30
2c787557-14e4-4229-a8c0-6a17dd5c60e7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB31
c627818a-6030-4384-b526-1eece5d2596d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB32
b91e5503-2931-4dec-a71f-46a34acb0bbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB33
355a3be5-dbef-4654-8bb0-e818d0b84cdf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB34
cfada6c9-cee6-4a54-aa0f-8f48e505eed1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB35
68e5debc-2a01-4f34-bc3c-a1ff0e5dbc05 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 1 | Level 29 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing | CB36
ab9c2f51-e8c0-402a-871e-d01aa139e456 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2
5bd76c32-d1c1-4690-8381-0cd073978fec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7
b5c9dc14-48fa-4ad1-b0a8-b7eacf08c590 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7
24fc0d5b-4044-4be1-b217-1685fe5c5e82 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In
28418c25-a9f7-4fed-b9ff-71a6d1d9b199 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 04
568703e8-0680-4102-8af2-abbd78b52bc2 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 05
dba6e516-2134-431b-a653-443d1d898012 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 06
41d7b3dc-1121-473a-828c-d371048db9c2 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 07
6b9c652e-db69-4641-8621-ad2fd554d567 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 08
440da5dd-7f0a-46fc-ba3e-c2e3d8450c09 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-029 - Rough-In | Level 09
58cc2c81-1de1-45ae-9b10-3bc0e9a79648 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out
11d7cdce-c7e8-4a5c-aa73-cbe3bc99151d |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 04
4e614099-50a9-4a3f-aa23-6cd986630d28 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 05
0907ea71-27a5-4f45-8275-40741e4235ef |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 06
c0558a48-8e2b-44a6-b469-64e45d4c4a2b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 07
97f3ec5f-8212-45e9-8af9-df6f13264efd |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 08
5ded2528-1047-4bd4-9bd9-6c5ccfe3252b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-030 - Cut-Out | Level 09
1b7a7acd-38c2-411f-9696-52b39de7f741 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off
390dcc4a-f798-4f82-9ce7-f70d2f686a9e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 04
fb422dcf-b09b-49b1-b9ee-1d789fbd4d13 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 05
b4f4b014-6c57-425d-9e70-217b2443e663 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 06
bbb76491-c03d-4fec-a82d-dd90e4e20235 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 07
8d3668a0-c3ea-4445-9de2-f56bf7d0baf5 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 08
cf6ef2e1-9a7d-4e4b-b973-30c5b0164602 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-31 - Fit-Off | Level 09
76ac9c73-5fd8-4197-81e7-ab983663f223 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-018 - DB Fit Off
4c7a0a4c-5b3a-4369-b3c5-d585cf7d82af |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-32 - Commissioning
ce36023d-a7ab-4dba-8c51-417e7fbc67e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing
2a18b123-04d4-45c6-a2af-bedfcaf59f1b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB1
26fd27bf-fe79-454f-bfeb-d8507c4e1380 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB2
dd137c29-19f3-48df-a9e0-49fa1525fccf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB3
ff541fd6-c57c-4452-9940-73165fb95cda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB4
39f3f78a-23bb-4a0a-9699-e59787e2e3ba |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB5
b4a0f98d-fe42-493c-808a-8af26f6d3156 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB6
13e8c7d1-5c37-4513-8e35-c53fda57c558 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB7
96530733-543a-44cf-90af-9d91b4d1e929 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB8
a1adbcef-9377-43ad-b2e0-472c72dc7520 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB9
316480f5-d0f9-448c-bd85-4cf8e399e972 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB10
e457a5e9-12c3-43ae-a925-dd6d513a2afe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB11
3d731f5d-ca62-4e28-a52d-6bb37ef292df |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB12
c68a9ff2-cbaf-459b-ad9a-e5496d277245 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB13
d78f9c47-232c-48d8-acab-6f5fa2ef5c53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB14
5244e29f-4801-4949-9853-d3c5f303e27d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB15
f2f7338b-caf0-4175-a111-b2be95c1466b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB16
5a8c579d-eb9f-482a-9b77-5c181ea65cbd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB17
e788dec9-78c1-4051-8179-b5ceb9080b1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB18
0429155c-27fe-4653-9478-0d821900da29 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB19
d4d4f6a4-2715-4456-af90-462eddb9a048 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB20
5aa79613-61a1-4131-89b2-98092f64f7d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB21
09ea651d-f2d9-4220-bfbb-b98f07c609a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB22
ef569fb0-186b-472c-9ec6-497b45566acf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB23
f8d31a40-e053-422f-80c7-634a710bdcb9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB24
bece663a-edd3-4d38-831d-5dc002c5e6ef |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB25
897aba99-51f1-4cdf-a391-584b1fd12c90 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB26
ac945408-bbe0-49f2-9c5e-edc433fb2153 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB27
c6e53c21-9a35-4f04-b5ae-ce024048a014 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB28
e6bb4bd8-0e6e-432c-a440-60bdf703eb33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB29
35dccf1e-8a29-4588-9f5d-c2427041894d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB30
2a927ef4-dc3f-460d-93ed-a7f2a3628e07 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB31
df5d6c9b-66c7-45d8-88ac-0f16df068d3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB32
129cd0bd-6663-41fa-909c-41ab4a1940c0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB33
17c0cb13-79cf-4e09-b7dc-17674396996b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB34
46c2a6be-efea-4423-8cbc-5b407eb88b5d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB35
fb7ea4c3-15d4-40f2-bae2-e0e822100c33 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB36
ad464680-a3bd-4ec0-af59-ac990d7db236 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB37
f990f2f0-3794-4984-bc3b-c41577bc4926 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB38
762193b3-dc96-45ad-a15d-e848e3a9057f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB39
79d45822-bf87-4e68-8309-6fdfaf9771c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB40
e68a2e10-db53-4b23-866b-6ec29468df81 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB41
8424e903-32a4-4d4e-8235-9a7b809332bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB42
0de380e5-6b93-43ec-a4e5-547ab4be5326 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB43
01536f72-17a2-45cd-a746-5f0c7750b130 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB44
d8217c3a-efd1-48f3-99be-d253530b9053 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB45
1ed1282f-197a-4c8a-b779-463c5d470e54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB46
40b32d87-2149-4274-a251-62722cf607bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB47
597208c9-96cd-4d7a-9899-0d4dcf538be9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 7 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing | CB48
d9304e11-ffdd-42d1-b808-86826a866c7c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13
7bec47e6-5a0d-488f-809a-bdd27cea6d70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13
a3d526be-7375-4aad-a0b4-45424ae2f76b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In
19b8271e-fa4b-4e61-b709-1558716ce34b |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 10
94080c3e-69cc-4d60-8fae-624cafc8ec12 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 11
73fe0eea-383a-4616-a37d-1027b985e2aa |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 12
6d08d333-0385-4e4e-9c90-cc6b8997b8f9 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 13
f4bef41c-4e57-4505-be9b-600d28307507 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 14
f4279216-008c-494b-8395-acda55202d93 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-029 - Rough-In | Level 15
0992257b-e7c4-4f72-b4d4-fb876a1e1b13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out
a925d60b-c6b0-44e9-9403-574706ed995c |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 10
24d94098-26ec-4c5f-b60e-f7079665ba9a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 11
b0ceb054-e052-457a-a94a-f43dc881a6b8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 12
f075016e-c297-42b1-8355-da9b62e92ddf |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 13
122fceb0-c38f-4a33-8b9b-e0367dc65ad9 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 14
a121fea1-e0cf-4f1f-8e98-4a6f7ca4b19a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-030 - Cut-Out | Level 15
d14671b6-f0ea-4ed6-8e7e-a0ce9aaf9bec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off
c0b761b8-f5e0-46db-9907-19d7e8257c8b |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 10
94c5ca33-2885-402b-9d18-bf96d2ad073b |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 11
f868c199-317a-47e2-b414-272bf719425b |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 12
f55126f2-b0e5-42d2-a921-c4e7169cb851 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 13
d5fbc4fe-3a3a-4703-a0ad-eca8a7cf6658 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 14
88b9331e-3156-4b31-8b8d-9ece249f8a98 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-31 - Fit-Off | Level 15
d54c03d3-9cb2-4ccd-b6ec-715552ec53a2 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-018 - DB Fit Off
d70957dd-baca-444c-bfbf-67f78b00fab5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-32 - Commissioning
64b54bab-784c-46df-8b97-3c854d7e002d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing
ea057faf-df61-4afd-b96b-7fda9b6c79a1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB1
44d47b65-8cf4-4838-b370-693f830699e9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB2
b74701cc-1df3-4908-b205-08c35fd23156 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB3
ac256b9c-07f0-4028-bc22-b5f2cc7b5bb5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB4
ae087f62-db9c-4ead-8a56-9d870d24bdb6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB5
f2047025-3b67-4dd6-a862-805dcd35f8c3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB6
6ac2e887-189d-4208-bad6-26ff510f21fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB7
0d731ed2-be61-441b-8eec-8a9f0f6c5369 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB8
2f044527-0ceb-4692-a970-58c3203319e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB9
738f6d32-3fa9-490c-8432-badd269baa57 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB10
5edc311d-11b0-4b4c-8411-62f9e9fcd167 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB11
438f026d-387a-4cc3-90b4-b1083a07219d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB12
0ccd99aa-8b6c-4810-8704-96bc1cb65b61 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB13
666de9a6-5138-4ec6-8fff-9d794e9a86c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB14
870a69a5-f72d-465d-8b9e-3f6c4c84aad7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB15
1c8c2f39-75aa-44f1-9afd-444cbeb9afee |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB16
acbe2f52-b6f3-4f9b-b14e-ec5b20e22212 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB17
4a8aaa8c-ebe6-4841-b3d0-67b53ebafd18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB18
a41434a9-1118-4043-9443-fab83682d131 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB19
0e8dc211-2b58-4cfb-9a40-acdf8a213696 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB20
3de6826f-24bb-44c0-8560-425394d97665 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB21
e36081ba-e110-4304-a513-5051b0f88504 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB22
c5e60fd5-1cb9-4caa-a481-13df80e4d958 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB23
c7c7f9d0-6126-4e08-9e64-47b30065451c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB24
00da282c-ba2d-495a-ab35-a3cc35bfee4f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB25
ef65902e-6193-4b49-8293-f64a82cfefc7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB26
0c3ffe08-a26d-4ce9-8f7d-c89386200805 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB27
b870e18c-3e2f-431e-8f7d-c4fa3d665a6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB28
61aaed22-021d-4fe0-8993-abac0d1978f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB29
58901b56-7900-4d86-a107-53d6ed516425 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB30
f5b1bcf3-d9b3-4d3a-8c57-c60567825659 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB31
496e0d08-a7c9-47fd-a1e0-174b6a5b1ab0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB32
f5cf6226-0a56-4a1a-bcca-ee93c41c0ed5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB33
5fec3947-1d0d-4122-9139-37e48dc235f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB34
41afde6a-2bbd-41e1-810e-56a9ef2bd0d9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB35
7204a247-a7f3-4e64-a6d6-093b194ce981 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB36
bc29acdd-1f73-4c61-a59d-4386021bb372 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB37
000952ba-2d16-4b19-93e8-31f5b85a16d0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB38
cf9096c6-0cc2-4554-bb1c-f35027554601 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB39
561f0296-fef1-407c-98a9-e973cba4c2d6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB40
2e154b4d-be89-4fea-bbf4-56f551d4051f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB41
fa892b33-1f0a-473e-8459-e9187d4d7d53 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB42
83765ba7-cdf0-499c-ab2b-bc5f6c0cabad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB43
568b33b7-da7d-4572-bb88-079998204d17 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB44
f73d6cc4-96f8-44ba-a37e-95479bba8916 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB45
297fd86e-3d61-43a6-a818-514049ca7d34 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB46
9cf16089-ddd8-4561-8953-59d0892afbc2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB47
2556c43f-00a1-434c-b866-ff32fd02bdaa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing | CB48
87457dc1-a1c2-4f86-b693-aabdec8964e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18
f11c3581-081a-477f-9019-d01b0b099dbb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18
bf50e4f9-b1fd-4555-94b2-d7f79c241037 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In
8d786f74-78f4-474e-9790-cd88a7b6c7de |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 16
b9f02c4d-808d-4e3c-859f-3d145ed9f09f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 17
f3d96eb7-0808-4fac-ac1c-8f80a05d6470 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 18
7b14aab1-5318-4e23-8022-9460292623ef |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 19
1eeed289-0b6e-44f8-ab0d-efe2b0642c54 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 20
4c462506-4782-46b5-b5b7-75d1e6a69471 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-029 - Rough-In | Level 21
941dd7fd-6069-4c13-aaed-82cad744e5fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out
061fe983-87f7-4edd-b053-d7ad9d5467ac |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 16
7f28aa15-6bf1-4ff4-9173-23c59f25662a |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 17
f559b26b-0d6f-4be5-bd6e-ec86dd946591 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 18
df333a5b-821d-4505-8110-bbadd2238d9c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 19
038dc680-a62b-4d55-9b01-84a2f53cbede |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 20
214d406f-a5c4-4268-825d-e9c85b87ad15 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-030 - Cut-Out | Level 21
3c3bd132-11f1-4498-89d3-058a7cb5ad0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off
58639be3-122f-4a42-aca6-f33695be7765 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 16
56238f04-79ab-4873-90ad-7d0d0acb5b93 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 17
29441b36-82ee-4561-8cbb-650a4519874e |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 18
88626faf-e543-48e1-a5da-2c5e7ccb84b4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 19
4b250589-4281-440e-8402-0ded520d961f |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 20
6a2294c9-91f4-43b7-a853-94b9bb0992e5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-31 - Fit-Off | Level 21
31f0819f-2e46-4b95-a2a0-21e235d5e0f5 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-018 - DB Fit Off
ff2c05a5-f143-4b87-aad5-37d874993e82 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-32 - Commissioning
eb210ae2-b113-4cf6-a339-bfa8e5f0787e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing
664b3d55-90a2-493f-9660-a90cd99be174 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB1
b3fc56f8-a5f8-4698-8ef2-4f9352660cd9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB2
85a5e992-bdfc-4bda-a53e-b8bd3835182f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB3
70ad8d56-efa2-4505-8267-baeaa1a5cfa3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB4
257fcfad-78d2-40d1-a11c-aaebbaac03a9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB5
a78a60ec-2fd6-40a4-93d3-a5caea67dc45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB6
df5c52cb-f8f3-475e-83ad-cd4b828d0942 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB7
adab079d-e93b-4ee6-90b2-08f887fdb4ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB8
9179528e-17d8-459f-a7ed-e89d712a7c8a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB9
8e0479ad-b8f3-4b19-9e28-b0c692ee389f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB10
accd629a-8657-4733-936b-c55880ca817b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB11
8e9a9f97-2dc7-4f3b-b7ac-c8197dedc9d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB12
fdf5b303-08da-4aaa-8a68-0b6504b264af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB13
1d387da7-c7fd-4ce3-a937-700f003d9650 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB14
e196cc1b-2917-4352-843a-de288ce7f7bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB15
eff63dce-1cc8-4258-acce-a254113df4af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB16
98fddba7-35a3-4a5d-905e-021a652e1141 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB17
d38ab152-1b36-4a64-a1d8-ea40074c951a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB18
7dda441d-4e9a-4e36-b060-8cc33dfebbc1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB19
ba03f452-f281-4457-b063-3ee57578de31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB20
856d0993-379f-47ad-a519-c998c05d2d39 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB21
ed06073a-b03c-42c5-b978-dbbff5c32496 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB22
fbbad629-b4e3-496f-b12c-b5416c3217c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB23
7fc43be9-18db-4585-83c6-1d9576358bca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB24
053841c4-5dd4-40dd-ba72-a2af6bca2fae |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB25
dacff33a-0950-4b9f-b3f7-179f6fb9432f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB26
6e146ca6-4f62-4e0e-aed4-5057836ba7ec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB27
60d7bdfb-3eaa-4206-91c8-45aa11ffec7e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB28
94fe4f34-0ad8-4e26-a88c-d1a3c40bb049 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB29
d11d4fdb-87ea-4853-81e6-e5a2fc31b77b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB30
5a49035d-44bf-4799-8dc7-ba07cbc3ac3c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB31
77ed85e8-752c-4965-a797-f745893f6fc6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB32
1795e58b-537f-46b1-8fb9-eae78e5cbaa5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB33
ebea48e7-9165-4816-afba-17262ec60014 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB34
d4884d52-a54f-48b4-9f7b-a80b3d86e7de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB35
4c02dc8c-d788-485c-8979-1f4d0e7be616 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB36
e40b969c-b8df-4e37-bf50-3eb53bfe6f47 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB37
754ab7ee-42af-4dc1-9571-56f89e023ccb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB38
6cdc811a-43d5-4b44-880a-7d7805ab99b3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB39
c0020e24-1369-4cda-896b-44c0d03b0a7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB40
c4429681-34c8-4a5a-928c-ff5a955b0526 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB41
fa68243a-e162-435d-9434-b64c1870ed23 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB42
b35f0587-8e9e-44a6-bfe2-84447835b384 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB43
b747e303-3f96-47e7-a56e-f3d0a82e7ad8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB44
c72bf292-197b-4757-ba51-c1deb83f70f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB45
44017ac4-9ac6-4183-8d17-e32ad2c37df8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB46
058a0e93-a998-4be1-b612-fb1f17e97d50 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB47
1e895abc-28bb-4b48-8a58-3e8235ed941d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing | CB48
cdc1c6c8-cc74-40ce-af67-63edcf0fcb4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24
0ca296e9-de6a-4e05-a325-6f9b7a081a52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24
de7a465d-a206-42ca-99f9-af83daceaa8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In
07a9fafb-25dd-4093-a868-1ef51cd1a111 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 22
77a7988a-bc78-4c02-b4b3-c536e0d42064 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 23
a456eefb-7d1d-4d07-869a-e8dfb61e611e |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 24
dd0bc4e0-40c9-4871-a55d-2258c003b22d |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 25
e5b5e6ce-dc95-461f-bb7f-712c6efd2248 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 26
e2a9cb2c-13e7-4c1c-b5d1-7c86c3c67a0c |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-029 - Rough-In | Level 27
c38924f3-0637-436d-bbea-deabaeabfd9e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out
cc14ccbf-e26e-4814-96f8-3b683d1e6b8e |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 22
b268e921-5278-49c9-9d65-c4221f1c7639 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 23
4425540f-1879-42b3-8bf0-0bc287d12d33 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 24
de50193e-c489-44cd-8bb2-10ef53a74d19 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 25
3da19764-0d33-4dd7-9dfb-9cbb6ecc8f3d |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 26
b2c67d17-7a58-4d4b-b195-50362e822101 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-030 - Cut-Out | Level 27
3d529168-3b73-4392-842e-f714a76d9c73 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off
3742a826-3078-4332-9ae6-c3a8f0ca4888 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 22
2ba17bef-e3a0-4dfa-9db4-849a350d48c8 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 23
cc276fdc-a497-4f7d-be29-ecdac50a528a |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 24
427754fe-c167-47bb-a539-282be6ecf7e8 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 25
3ebc51bd-8d85-4920-be0e-93773d69804d |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 26
6de457f8-db33-4d01-8630-2f05c58a4ca8 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-31 - Fit-Off | Level 27
f38bc182-5fc6-4176-819d-4def6291ab81 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-018 - DB Fit Off
4b1edef7-325b-4108-a6a5-16cee77e9c04 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-32 - Commissioning
3aa07619-378a-44a2-ad9f-c56c70648463 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing
49d7027d-cd38-4437-945d-b50bd18c4768 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB1
5eff1ee6-6c84-46ce-a2db-a4cd190091bf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB2
016b605f-f0b7-4de2-b34d-1fb344756ae2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB3
2e143c07-319c-4d2a-a2a0-e8641f3a3ed6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB4
d8b74f41-88a5-412f-be48-7089ed1460bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB5
e57d83d8-8fed-4a40-b339-34bf3396adf2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB6
39c51e69-f76d-45b9-847d-3871c0fb4cce |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB7
0a9cb621-84b2-4c51-b218-63b368847a75 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB8
61e5e1ad-1b0c-4d55-ad04-73d6b897e8ca |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB9
2b23600f-5e84-48a4-a629-46e727eb3953 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB10
3c3273e6-caa6-482e-bbf6-a373ecc5074f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB11
50d77502-9ed4-4136-8599-b7fca92c1e4b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB12
06109e2d-6231-4a4c-8dc2-b3642150594d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB13
a1919f0d-16e5-41f2-866a-1c8ce4897c79 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB14
f07d40d3-d916-4f40-8675-5bef3eda6d0c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB15
64d2b54f-4d97-41bb-9bd4-d6d64480d3e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB16
adfada5b-090c-48dc-982d-8a279cb58af0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB17
3c796427-08da-4aad-aacd-8b3a008139b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB18
6a0be744-25c0-44e1-ad63-e55ab8cb20fc |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB19
6abb8c66-cca2-4236-815d-40a7590548b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB20
117a058f-6f63-472c-9866-4cd91c8a9202 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB21
04245ed1-3061-4db3-a10f-c2f7efd96b9f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB22
2f1535a5-75e1-4c51-8ab4-339f98749cf5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB23
d3ae3dda-8ff5-452d-b514-d5695ce1d6b8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB24
d50f5283-e259-4e1c-be78-06ed169d9597 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB25
6689ccb0-82f2-4d01-a103-5ef628c25268 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB26
5ecb8c20-1b11-4d91-9591-11614629c063 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB27
ce8b18ba-aea1-42e9-9779-6993a3b524fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB28
4952e38c-6bf9-45ae-a497-cb28d99638a6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB29
501fbd75-706a-462b-a118-c3ffcea5a42c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB30
394b7c11-8191-46b5-bf6f-3ed8169d1a41 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB31
072783b7-f222-4423-a1f7-36740266d19c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB32
de0c5d63-6b58-43c1-8c54-529dc8b1855c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB33
83fc1833-4e8e-41ac-a70c-a41949c86202 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB34
2fec160c-6ad1-4d12-9f5a-d40150cfe349 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB35
ca45f332-e52a-4a9d-9209-20a05db05b8b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB36
6bfb923c-de90-480e-88f9-0bcae6453666 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB37
dc7c3c5f-487f-4084-be18-2873a5119e4a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB38
8dbba3c8-5b53-40b7-bfc9-90d56f988fda |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB39
0f4389ca-d61b-4b44-aa8c-56941d4bc019 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB40
1c095baa-8ea9-414a-b240-23a444ac6018 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB41
4aebb51b-6ef0-4d10-9595-fc04d2775de0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB42
dd4dc122-3980-4505-82c0-8e236657d380 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB43
b557bedb-3f8e-4081-bdb6-1b77441d1dc3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB44
28d1f92f-e7c2-49e8-b164-1cf958ba3592 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB45
92d6e25e-2620-40d4-83ec-2af3feeea004 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB46
d6e7a8a1-ec49-451d-9b89-9ca0e8169def |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB47
d113fd38-588c-4a19-aac6-774e311505f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing | CB48
792a92a8-414a-47fa-abb8-e6fa81d360aa |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29
01b29d1f-9731-4835-bbd2-a82a848fea7d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29
04c69306-7770-4900-b2ec-1f9bed583d5a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-029 - Rough-In
88be64d7-04d9-4ef4-86ec-78e83c6d9349 |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-029 - Rough-In | Level XX
f43fa3c5-71d9-422e-a596-420527f723ec |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-029 - Rough-In | Level XX
cfbfb223-2d85-406e-be0e-7d3576cd5dd4 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-029 - Rough-In | Level XX
879dc447-a5bd-41a9-95b4-53c35f9d4e6e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-030 - Cut-Out
3e174580-8aef-486e-a511-381dcd2ec346 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-030 - Cut-Out | Level XX
fa7f0eaf-2635-4657-a8cf-bfa9443ecff5 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-030 - Cut-Out | Level XX
b88f151d-b7c5-4629-90ef-0b582fde523f |  | checklist-flat | not-started | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-030 - Cut-Out | Level XX
7263a83a-ef9e-4d01-8ca3-3066fb7586af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-31 - Fit-Off
316aae47-a066-4372-ae2b-05e2b7ceb7a5 |  | checklist-flat | not-started | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-31 - Fit-Off | Level XX
509930ca-21d1-4c70-8eba-204f8c167fd7 |  | checklist-flat | not-started | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-31 - Fit-Off | Level XX
a58734ea-3040-4775-b0b8-c3afdd86ce30 |  | checklist-flat | not-started | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-31 - Fit-Off | Level XX
1708a31f-de15-4d3c-9507-0f77df077b84 |  | checklist-flat | not-started | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-018 - DB Fit Off
f6d1717c-7af6-4754-b07c-31aeebba1292 |  | checklist-flat | not-started | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-32 - Commissioning
07a18ec0-1fcf-4937-aad1-57c84e16e727 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing
efbbd30b-9b20-4a46-af69-7d78f54e1d67 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB1
147d06b5-f5c7-46a1-b737-d1b6206e7059 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB2
93815513-7e1b-4926-a96d-a2817e197b6d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB3
bd3a70b3-65b6-4bdd-964d-005f02dcc423 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB4
dc255d6a-f4c7-4c24-9989-5cca95529320 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB5
3ee5c618-e50c-430a-890a-f6cb0aa25589 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB6
a95bf041-f2ac-4b23-b554-f7e4933fb1f4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB7
562aaf9f-cf6a-4853-a848-a99e9554fc18 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB8
20a9a57a-8f15-4bcc-a649-6f7afbdf35bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB9
bdd9d3cf-a376-4c3f-b1fd-cdb4c6d4992d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB10
18e44751-30c6-402a-a80a-72a2e1e5466c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB11
fcf30de0-5c7a-40d4-9042-cfcfe18819e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB12
5fbb8fc2-33ea-4ac9-8fbe-85b4f224c664 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB13
054143e2-e733-40b7-a2d6-daa3b250b92c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB14
941fba8d-c060-4ccd-a148-51bbe33b05d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB15
6e9edd84-bfbb-463a-94fc-10875762eb7c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB16
16d493f7-d67b-4c10-88d1-5102a4643b1e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB17
70d4e2db-9f16-4510-90fb-7c9c8c04dd15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB18
91f9c4d1-6af7-4ca7-8a9f-04210f9715fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB19
dc9022b0-333f-4119-bfab-9b36321d3490 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB20
a583f925-a91a-4714-9529-0079cef1d7dd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB21
e1cb5e0c-82d1-429b-aad6-64eebf76b2c2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB22
c837ddfd-1476-4d73-a6c9-7fda29c0d255 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB23
a1abf71d-7a96-4b4b-a9c2-9545fde5feff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB24
c264beb1-5407-4d43-8039-f842405f3b3b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB25
8531d84c-f559-4baa-bfc8-3d8f608b4a63 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB26
258c8d63-ec34-452c-81ed-d5c8706c5b45 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB27
d831e18e-a003-438e-ace2-ad1150e5da49 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB28
386dfa7b-4477-48e0-a377-0cbe43fb6bbb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB29
f9d7d1b2-1198-42c4-b6a2-1fcf66b04b2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB30
4838bb7f-f78a-4d23-9bda-e992b0da5ddb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB31
b9dc0cb2-4ad6-4133-9534-8802b7170b77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB32
0c7d63f4-a904-4958-953d-241d60fd2fa5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB33
ef6a2945-e859-45ad-96d8-4bffeaaff996 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB34
175a7c04-58f7-469d-b899-5b9dd9a622f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB35
4514c73c-6e26-4409-a24f-7ab5f2fc7795 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB36
2d5bd766-b8a9-40c4-80a0-f8d0f827a3b6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB37
d3d7468f-1b98-485a-aaf8-e01a82607686 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB38
2d3f561a-517d-403d-9ab4-9cded6a99c73 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB39
81087a2d-c897-49c8-aec5-318565fc5c6f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB40
011a525a-c23d-47b6-a51d-a33ee69c057d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB41
c6ab52fd-c036-4b93-b977-c5179c012553 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB42
d395fa56-b3c0-4290-949a-be47c7ad10c9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB43
9da76b48-66ca-4aee-bebb-d5a6871d227b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB44
08a527ef-01f0-491c-aded-a932e2aff444 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB45
bd628efd-adb7-46ff-ad10-0302e599f311 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB46
f136bea1-71f4-4d54-b0f2-713d2421f773 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB47
4fdad3b5-04b5-4e8a-8f46-fffdf49ec7bb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB48
58a7e300-13bb-4b79-b779-534dcba93a27 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB49
e5911519-0d9f-4034-a2d6-9d2994df9e69 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB50
cbf835f2-b446-4d71-9637-57af40aff23e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB51
aabe2f7b-a33f-40b3-8468-9c0386882aa2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB52
9912a4f0-709e-47cd-a9b9-017b64c799a7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB53
f8f90367-adf4-48cb-98db-8824c52853c4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB54
c2fe1679-1335-4bdd-9f58-7174171f50fa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB55
dc027257-d608-4a63-b2b3-23dd0f6e809b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB56
ed1909b3-7877-4275-907f-a02da7ca1ade |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB57
ee292338-f5e7-4c93-aaf2-f61cf22e1117 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB58
d32a7467-7fb9-444c-8fdb-9a51fa657101 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB59
61f8d814-4496-4f06-9b40-d29e6e8652e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB60
3299caa2-e2c2-4e32-8c70-93a1f1d59dfb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB61
2bad2598-c9c9-4bd4-b002-46e44fa7533c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB62
834054f6-fb0f-4e13-a27f-87e0790ed9e0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB63
374fb2ee-338c-457d-8695-e81abed3a3de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB64
3434251d-6287-447a-aa63-36453b428f54 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB65
d8343a41-ea65-48cd-8d91-f0190d697ec8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB66
6b87454f-4ab2-4317-9d4f-3b0a513794b7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB67
08e392b5-0893-49d9-af9d-16642df8a170 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB68
fd41e499-087c-41aa-8049-3a685204d719 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB69
da68fb27-c2a3-4d6d-aaf6-a719f3f2b759 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB70
289314af-98ec-4550-ae2d-20bb245ef02d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB71
ef981b35-283a-4048-9905-930e4dd7d83f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB72
c8708ce9-0f0a-46c8-a9cf-738059c258db |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB73
425896fa-5fcc-4846-bdab-f3a14cf25293 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB74
120640ea-4e6b-4236-a0c9-c770e340e9de |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB75
32608f2f-d801-493f-a095-6ef7ce0a6b06 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB76
38875450-65cb-4bba-9ebd-e5e1997af973 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB77
dca02f96-2352-497d-83e8-c23c7faa1967 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB78
cf2905ab-e82d-44ca-9775-10487a78bb14 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB79
e017c890-0ab8-4994-be53-6abf1f0c3462 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB80
9ecd56c0-1439-4d44-9bd7-0ebecbdc0258 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB81
9a42affb-eaa3-454a-b1a1-af62b0e38ebf |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB82
76d3d210-61d5-4284-83cd-153a4d6993b0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB83
5a83785c-9407-4b7f-9c59-16a49674270c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB84
80e772b1-b8b5-44a1-8cfc-6b762a0b32a5 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB85
8fc1b820-1e19-44f6-a5be-eea5892ca7f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB86
7c2ece58-b563-43d5-9982-dcc9b9ba887d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB87
83fc1396-567e-4362-a081-40ad9d2d68f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB88
3b9bfb3d-e5d3-45b8-9a15-a5e96c654a99 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB89
f8515539-c4d0-4331-ae52-89c3ff33891a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB90
119c7a53-24a8-4d27-82c8-7c76af10216f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB91
66e4704a-8870-49db-946d-7bd8ed465344 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB92
00f43b04-e6b7-47ac-bc7b-03a17cf5e0f8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB93
7564a94c-0157-496c-83d9-2fd989fa0cec |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB94
68fd7fca-b379-45dd-850e-0234240c4955 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB95
6201e9b3-b944-4ef4-b77d-6c833ab72007 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Common Areas | Distribution boards and sub-circuits | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing | CB96
e43e48c8-b074-4623-9819-3bb1109bfc6f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation
83b98cce-29c9-4175-8ce7-964f05f5d371 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | MSB Installation
f2c69a7c-36c2-44c3-ad12-21e67e2138bc |  | checklist-flat | not-started | AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MSB Installation | AE-ITCX-011 - MSB1
d082da9a-5d28-4a9f-b45b-e6e316db9b4b |  | checklist-flat | not-started | AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MSB Installation | AE-ITCX-011 - MSB2
ff9c1b6b-2720-467b-9f78-cb6216882279 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation
52a2ca1d-5091-422c-a447-81cdc51fec9e |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MSB1
2f07159e-ecff-4d1b-b5e3-e9d6ee262b30 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MSB2
207f7b61-e958-4290-938e-8ef5f05bcd40 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T-L1-01
aba5a61c-995b-4559-840a-0740ca0760c1 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T-L1-02
163978b4-5e23-4868-8e36-6a7770c25e12 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T-L1-03
bbb00488-63cd-4614-a10f-3b8c73de8724 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T-L1-04
b37ff123-ff98-4c53-9ea3-a040ddbf0153 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T-L1-05
96300d4b-8ecf-42e9-91ab-87dee461d6d4 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T1-Mech Riser 1
1d5802f5-3102-48c1-a2ab-26d491009b9e |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T1-Mech Riser 2
6badedc6-c2c9-4ccf-91d9-961d180d38ee |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T2-Mech Riser 1
726d99ca-79ea-4523-827c-61bfcadef420 |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T2-Mech Riser 2
8d56ee81-aaf7-40b6-9730-7e26c69fc5ed |  | checklist-flat | not-started | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | MEN and MSB CT & Meter Panel Installation | AE-ITCX-012 - MP-T2-Mech Riser 3
0b3f4e72-53b5-4039-90d3-50e02cc88f80 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation
b087ef8b-e448-4e08-ad73-bdc264e6e958 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3
7399f9fc-fc81-4f90-a5dd-8cc61d365e73 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3 | AE-ITCX-008 - Basement (Horizontal)
c4bda172-a26e-4863-a0a5-367f9ac700ef |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3 | AE-ITCX-008 - Ground (Horizontal)
3f1382ff-5ced-4d60-a798-3e0eb164cc59 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3 | AE-ITCX-008 - Level 01 Horizontal (Substation to MSB-1 and MSB-2)
d00b96e1-650a-43fa-870a-4178a2b0ae1c |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3 | AE-ITCX-008 - Level 02 Horizontal
f1266a6f-5e85-4a2b-86c7-b0f8235d6af7 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | Basement - Level 3 | AE-ITCX-008 - Level 03 Horizontal
3239d68d-5eb2-4cd3-b2ea-58d9251a51fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1
0139a177-0cd8-4742-8da1-f2f18c784f9b |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1 | AE-ITCX-008 - Riser B1 - Level 3 (Vertical)
c200b3af-9593-474e-8b1d-232c985072d7 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1 | AE-ITCX-008 - Riser Lvl 4 - LVl 12 (Vertical)
fe79f70e-ebda-4481-a0e3-52a4c61f5c32 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1 | AE-ITCX-008 - Riser Lvl 13 - Lvl 21 (Vertical)
a0336e29-042d-4b0c-83e0-489dba7bdaf1 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1 | AE-ITCX-008 - Riser Lvl 22 - Lvl 30 (Vertical/Horizontal)
21a48c00-e4d0-4c37-8c34-c0e633ccf4ac |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 1 | AE-ITCX-008 - Roof (Vertical/Horizontal)
628dcb56-1a8a-408f-b55e-504889a51a81 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2
bb7bfcf6-a806-4079-9a58-fd06014990bf |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2 | AE-ITCX-008 - Riser B1 - Level 3 (Vertical)
703ef2a9-3a80-44db-86b8-b7097f3a0352 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2 | AE-ITCX-008 - Riser Lvl 4 - LVl 12 (Vertical)
a5e1d02f-579e-4300-8fc7-d2b8271204b9 |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2 | AE-ITCX-008 - Riser Lvl 13 - Lvl 21 (Vertical)
1cf14604-6844-4944-8e49-89f52b264ffa |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2 | AE-ITCX-008 - Riser Lvl 22 - Lvl 29 (Vertical)
5519af7b-3a39-4fd7-9dbe-fd193bd8b79c |  | checklist-flat | not-started | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Tray Installation | TOWER 2 | AE-ITCX-008 - Roof (Vertical/Horizontal)
ca7896cd-4753-4c1f-bc10-5368f283f991 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation
ff0005b6-da96-480f-8a83-023fdc8483fb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3
595f74e2-cd28-4aae-9287-3d1608d6e189 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB1
10b59d17-e4cd-42cd-b3ef-20361909170c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB1 | AE-ITCX-015 - Mandatory Testing
68d09fc8-fa44-445c-a745-7795fcd9c543 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB1 | AE-ITCX-010 - Torque Settings
9a338561-55b3-4d43-98ed-99b95182d052 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB2
87ea0221-9711-4126-94d9-4ee13b7e7ca4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB2 | AE-ITCX-015 - Mandatory Testing
a42cc506-45d9-4a7d-ac80-3c04f88a30a4 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | MSB2 | AE-ITCX-010 - Torque Settings
af95955f-7940-4cf4-ae74-31679bbf9624 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1
4d12eb76-ad8b-4823-a643-0e9436ae4d21 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1
ad6fdf21-2b82-4ad0-b965-2a41436b2d69 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1 | AE-ITCX-013 - Visual Inspection
f12725fe-4cef-42a3-8ac7-cadd6b44f4fc |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1 | AE-ITCX-010 - Torque Settings
661cc3dd-0b52-4ac9-a389-c7cf4c8d9fec |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1.1
7998119c-1d32-4eac-a9ca-c766ada9fabb |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1.1 | AE-ITCX-013 - Visual Inspection
5112b8e6-bd14-4ebf-8018-8877b9b46b41 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 1 | TOB-T1-H-L1.1 | AE-ITCX-010 - Torque Settings
03b4870b-cd6a-4f1f-b55c-65aef90b5844 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 2
ba613335-27b0-4e26-a83a-6e4b1514eeb2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 2 | TOB-T1-H-L2
f6016e5b-8b02-4fb9-91b0-59526ab25371 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 2 | TOB-T1-H-L2 | AE-ITCX-013 - Visual Inspection
bafc96ed-2f3f-4bd1-91bc-7282c3c36a5f |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | Basement - Level 3 | Level 2 | TOB-T1-H-L2 | AE-ITCX-010 - Torque Settings
d3a5004d-5683-4ab8-9c43-fa0c757ab49b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1
f52f66bc-a220-48ad-87c2-5326ceae1416 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 4
3c13487e-644e-419b-aa83-b154d44c85cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 4 | TOB-T1-M-4
37d5403a-ef71-42dd-a600-d5bb64080d27 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 4 | TOB-T1-M-4 | AE-ITCX-013 - Visual Inspection
3177d4f0-d336-4961-b06e-c83fe48639ae |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 4 | TOB-T1-M-4 | AE-ITCX-010 - Torque Settings
ee7e7d8a-1bfb-4fb6-966f-0abca9e1eddc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 5
561aad19-ec41-412c-b11a-a977b6e7b63d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 5 | TOB-T1-L5
e32a665d-7655-41f2-b857-cc37b3569b1c |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 5 | TOB-T1-L5 | AE-ITCX-013 - Visual Inspection
219e5f07-88bd-49b2-9ab7-f2b0b9825d0c |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 5 | TOB-T1-L5 | AE-ITCX-010 - Torque Settings
0abc0493-45a3-41cf-98fe-13c90ece5c96 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7
5512c122-554f-4f3c-bac8-26900f3030bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-H-L7
b81c6abd-1aaa-4b1f-84f7-253097a64baf |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-H-L7 | AE-ITCX-013 - Visual Inspection
f125f82c-1291-4362-9b43-99190e4a4403 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-H-L7 | AE-ITCX-010 - Torque Settings
61f2953b-0979-42c4-a101-dfa1a1fa7920 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-M-7
82d86b4f-36a7-4bec-b289-ebb4e48f8d43 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-M-7 | AE-ITCX-013 - Visual Inspection
533c79ea-d79c-45bd-b5e3-a2ca58d1d98d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 7 | TOB-T1-M-7 | AE-ITCX-010 - Torque Settings
d4afea61-8272-45d1-bb15-2a54060698f3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 9
84a55a94-5d66-4a79-af2a-9f46fb850617 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 9 | TOB-T1-L9
fdde1441-b704-4a46-bca5-f350d286ddc3 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 9 | TOB-T1-L9 | AE-ITCX-013 - Visual Inspection
9450d3bf-4ec5-4292-a767-4d5c559e6722 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 9 | TOB-T1-L9 | AE-ITCX-010 - Torque Settings
21f0ceb4-2aac-4ab8-915a-dcce52673af9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 10
8f2b452f-f9b8-4445-bacf-c5517def5fcd |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 10 | TOB-T1-M-10
6e02ccde-78ab-4c25-bc2a-a9b6f1927720 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 10 | TOB-T1-M-10 | AE-ITCX-013 - Visual Inspection
7759a961-9773-48ee-a4c1-120144e5cd91 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 10 | TOB-T1-M-10 | AE-ITCX-010 - Torque Settings
b5598aed-c7a2-4016-b290-9885040f9a45 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 12
d4192a09-f85d-41f4-83c7-9c97937501b3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 12 | TOB-T1-H-L12
21fa63c8-a529-4cd3-9272-55fdf4aeeb58 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 12 | TOB-T1-H-L12 | AE-ITCX-013 - Visual Inspection
13aef5fb-fa9c-4f0c-bf64-13987f7d0f5d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 12 | TOB-T1-H-L12 | AE-ITCX-010 - Torque Settings
d4377511-1829-4644-8dfa-806288336e65 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13
54fe2160-163c-4586-8f8c-c05ca0b2841c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-L13
c6f49e1d-039c-4a4b-b60a-01a07a9dd9bc |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-L13 | AE-ITCX-013 - Visual Inspection
caaa330f-66c4-42c1-aacf-ba348161c1d1 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-L13 | AE-ITCX-010 - Torque Settings
08df5d09-c598-49e7-938a-4dbad44545c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-M-13
0c3bd476-6cc7-4eb7-a3ca-9cd59a3205f9 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-M-13 | AE-ITCX-013 - Visual Inspection
7fbe9d20-7d5d-45cb-bb98-29a8dbaf95a0 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 13 | TOB-T1-M-13 | AE-ITCX-010 - Torque Settings
fa1dd1c7-0529-4e6f-8cfe-447a9c63532a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 16
646c367e-a2b5-49a9-a708-205c9a883d09 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 16 | TOB-T1-M-16
d3139cbc-a229-4008-892c-a75e86588fb8 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 16 | TOB-T1-M-16 | AE-ITCX-013 - Visual Inspection
79c757ab-6ac1-4ed4-bf46-b1512f51de6a |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 16 | TOB-T1-M-16 | AE-ITCX-010 - Torque Settings
9669f892-d8eb-45d7-8a6c-a7e678dcbd01 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 17
f5c37093-e017-4580-8394-e1dcfcc866c0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 17 | TOB-T1-L17
ddff56ef-1477-437d-afa1-7eb7d3d7f57f |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 17 | TOB-T1-L17 | AE-ITCX-013 - Visual Inspection
fe901776-067a-42b4-9f6e-19658fdf71fa |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 17 | TOB-T1-L17 | AE-ITCX-010 - Torque Settings
c2983979-0cfd-4aad-bfc2-26df0c68da9b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 18
ecdff398-9b0b-4c64-8cc8-8decd84cbc66 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 18 | TOB-T1-H-L18
5b633727-a8db-4a63-ba5b-9358d473c3fc |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 18 | TOB-T1-H-L18 | AE-ITCX-013 - Visual Inspection
f272926d-6f48-48dc-ba9a-898542b486ca |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 18 | TOB-T1-H-L18 | AE-ITCX-010 - Torque Settings
d8f7cd7b-2f74-4c03-9d32-6753e42ed7a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19
22f614e8-7e40-45d7-8842-3ad0c110e9f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-L19
2a84991a-d41e-433f-a832-85768fb46b4c |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-L19 | AE-ITCX-013 - Visual Inspection
4e456101-c19b-457b-a56f-e951c4d826dc |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-L19 | AE-ITCX-010 - Torque Settings
cfcfdcb4-a989-4e1c-b7c1-148f3b8e4066 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-M-19
0a590350-d606-4216-91cb-2905167c026b |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-M-19 | AE-ITCX-013 - Visual Inspection
75070b82-68c7-4bbe-8ad0-ee62bec5a5d3 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 19 | TOB-T1-M-19 | AE-ITCX-010 - Torque Settings
9b9c8482-3a88-4042-9b82-a174afc159a1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 22
513d3999-6cc5-41fd-b14d-a8a3b03ecfed |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 22 | TOB-T1-M-22
0f37a293-97a8-4246-b959-fac387dd4546 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 22 | TOB-T1-M-22 | AE-ITCX-013 - Visual Inspection
1a6dd204-da8b-4372-8aec-c12bb0af7aa0 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 22 | TOB-T1-M-22 | AE-ITCX-010 - Torque Settings
ab9d1f8f-f8e3-4138-8bd1-f454e4fc3c0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 23
2771dd1c-c0a3-468b-88a1-371af03f91a3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 23 | TOB-T1-L23
ac14a618-c7d2-4c4a-95ad-b0623bf84eaa |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 23 | TOB-T1-L23 | AE-ITCX-013 - Visual Inspection
9df1cc75-654b-4e0b-910c-a61c3816fa36 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 23 | TOB-T1-L23 | AE-ITCX-010 - Torque Settings
e6dffadd-9a40-4a78-b2eb-e345dbf7e443 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 24
45955637-b048-49cc-bf1f-535daff84ec0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 24 | TOB-T1-H-L24
7cdacdba-7e97-4f03-8198-bf9a74e7894f |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 24 | TOB-T1-H-L24 | AE-ITCX-013 - Visual Inspection
b5eeecf2-0d16-4cc1-9371-26f183df2b17 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 24 | TOB-T1-H-L24 | AE-ITCX-010 - Torque Settings
2c10b342-018b-4002-9d16-d6824926e77a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 25
c1a40fc9-78c0-4708-9aa7-90c91c0327f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 25 | TOB-T1-M-25
249fbf2d-c2b7-4b30-ae2e-30a025954538 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 25 | TOB-T1-M-25 | AE-ITCX-013 - Visual Inspection
ad8e053e-545b-4e09-b941-73d9a7d1e78c |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 25 | TOB-T1-M-25 | AE-ITCX-010 - Torque Settings
e46a9eb4-6efb-4c23-90ac-c0a714654199 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 27
76208aac-b962-4984-a5e6-a0e7a60c755a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 27 | TOB-T1-L27
e4751d18-9e29-4d99-b7bc-4526a2127ef8 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 27 | TOB-T1-L27 | AE-ITCX-013 - Visual Inspection
540c8107-3823-4ddd-9015-6be0e0b6cee0 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 27 | TOB-T1-L27 | AE-ITCX-010 - Torque Settings
52786bea-8539-43ed-b86b-b8f1e02ba0b3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 28
04981b4e-82bc-4738-9e19-51af6d265b15 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 28 | TOB-T1-M-28
1bf599c7-2f15-4c11-ace5-580dfcfd0b1a |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 28 | TOB-T1-M-28 | AE-ITCX-013 - Visual Inspection
de3c0638-9ba9-45da-bba0-8c7b5846882a |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 28 | TOB-T1-M-28 | AE-ITCX-010 - Torque Settings
2032eef5-0b09-46ec-add6-f48a9cee078f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 29
479fab20-662a-481d-9de7-7c5495f0e0b0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 29 | TOB-T1-H-L29
7ab100d6-584e-4ca5-a29f-2ae7253472d2 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 29 | TOB-T1-H-L29 | AE-ITCX-013 - Visual Inspection
5af03fc3-c338-4a72-bbbf-c3c052e2d94b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 1 | Level 29 | TOB-T1-H-L29 | AE-ITCX-010 - Torque Settings
3f21f100-03b8-4163-8cbd-ed06bfa3ca6a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2
d4403648-3c12-488b-8173-51f440c0daa4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 4
cc07afe0-637b-4da4-993f-41e40610dff4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 4 | TOB-T2-M-L4
c91ab971-835f-41d0-b9fa-8eeac3f84b24 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 4 | TOB-T2-M-L4 | AE-ITCX-013 - Visual Inspection
ce0a5944-faf6-4294-a60c-4793e04fd91e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 4 | TOB-T2-M-L4 | AE-ITCX-010 - Torque Settings
229f4942-a6b6-40d7-b416-de189e0eb73f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 6
5ac27542-4e31-4e63-b634-b1938b09a2e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 6 | TOB-T2-L6
a23e9226-a896-4898-a9dd-b73285c26f00 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 6 | TOB-T2-L6 | AE-ITCX-013 - Visual Inspection
3f9f05ae-ba29-405a-9f57-d10b9d261a0b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 6 | TOB-T2-L6 | AE-ITCX-010 - Torque Settings
3e5f8c8c-7257-4626-85a7-f623f1b0374b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7
d08f5902-756b-46e8-aa8c-c60af3d8b2c8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-H-L7
608d0b43-6faa-4c52-bec6-344202ef0ddc |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-H-L7 | AE-ITCX-013 - Visual Inspection
626ee2fc-61df-416f-b6ed-28c876e26355 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-H-L7 | AE-ITCX-010 - Torque Settings
23d15490-86a7-4a55-aa43-94953e6f49d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-M-L7
4401d306-d935-48dc-9c4f-f2a210836421 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-M-L7 | AE-ITCX-013 - Visual Inspection
ad02f387-bad5-4ba2-9c35-aa22396d8386 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 7 | TOB-T2-M-L7 | AE-ITCX-010 - Torque Settings
6c291ba0-d511-4c3b-aeea-ba6a07277c4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 8
1cf3e8fb-6267-46d5-9448-a8951ed26c05 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 8 | TOB-T2-L8
b528ac45-f437-461c-a2ca-61b9b46fc032 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 8 | TOB-T2-L8 | AE-ITCX-013 - Visual Inspection
83148740-159b-4436-9ce6-41086d0d62cc |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 8 | TOB-T2-L8 | AE-ITCX-010 - Torque Settings
3c5171c8-badc-4ed9-a5cd-2c2b51d4e916 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 10
4e86833f-ee50-4ebc-9a47-a5cd77ce7c93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 10 | TOB-T2-M-L10
38450c2c-3673-4233-aec5-4493bc673622 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 10 | TOB-T2-M-L10 | AE-ITCX-013 - Visual Inspection
66d30fb4-de28-447d-93f4-6a26568ecf78 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 10 | TOB-T2-M-L10 | AE-ITCX-010 - Torque Settings
443ad4d2-d554-4aa0-aaa9-e281e40849fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 12
3dca1bc1-1053-4f6a-99e3-0b62e2d8e01f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 12 | TOB-T2-L12
5a3ef3b6-ee14-49ed-97e5-01102e376cac |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 12 | TOB-T2-L12 | AE-ITCX-013 - Visual Inspection
180372ff-0b5b-42e2-8c36-c098ddfb5b15 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 12 | TOB-T2-L12 | AE-ITCX-010 - Torque Settings
269b7654-beac-4d82-bbae-5991f53ccaf4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13
993e064b-193c-416b-ba3e-a457a49f2498 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-H-L13
d41f9fe3-5009-4f9b-8647-0a666ff6075c |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-H-L13 | AE-ITCX-013 - Visual Inspection
1a3a3099-fe89-4cb4-9a3b-ab15cfe179bc |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-H-L13 | AE-ITCX-010 - Torque Settings
aa50565e-f65f-4998-859e-faaf4f25d0d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-M-L13
c72ea982-35f1-4f6b-b589-7772890f47d6 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-M-L13 | AE-ITCX-013 - Visual Inspection
d5799288-ba8e-41f2-a2af-febbb5468e54 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 13 | TOB-T2-M-L13 | AE-ITCX-010 - Torque Settings
affa8b82-8493-4bff-9bd0-8202955ab6cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 16
6da065f0-5a9d-4a24-80a8-2563b5fd950c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 16 | TOB-T2-M-L16
c7e0223c-27a4-4410-8960-e80312001931 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 16 | TOB-T2-M-L16 | AE-ITCX-013 - Visual Inspection
1f47307f-7ecb-4697-8508-b6336673aef6 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 16 | TOB-T2-M-L16 | AE-ITCX-010 - Torque Settings
2388abb1-c906-4e33-bbab-478495ccdd52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 17
1e0a66d6-9ae2-46e0-91c6-5178434a5e6a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 17 | TOB-T2-L17
628f8b4f-04a6-4a99-8be5-d2c1a7ba04e4 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 17 | TOB-T2-L17 | AE-ITCX-013 - Visual Inspection
7d2b6199-635a-4146-8b62-d8ef94b4e687 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 17 | TOB-T2-L17 | AE-ITCX-010 - Torque Settings
ed554888-b0cb-4dbd-beea-6c822add22a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 18
3f7e57d6-5014-43cc-b425-d5bbb17b7796 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 18 | TOB-T2-H-L18
7e80d837-074c-40e3-a1c9-5ad5af24d95d |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 18 | TOB-T2-H-L18 | AE-ITCX-013 - Visual Inspection
6a556921-28d4-4df0-8d87-dce46c1f697e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 18 | TOB-T2-H-L18 | AE-ITCX-010 - Torque Settings
a8d6b0e2-ba99-4ee4-bef2-7a6b2030189d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 19
8eb1af45-30fc-4d18-ac25-44665259d9f1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 19 | TOB-T2-M-L19
4d4e0336-c766-4b7a-a3a2-20f38d3b22ef |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 19 | TOB-T2-M-L19 | AE-ITCX-013 - Visual Inspection
fd8e8142-5d19-46b7-970f-2663cae03a65 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 19 | TOB-T2-M-L19 | AE-ITCX-010 - Torque Settings
c120b0c2-2a68-4784-878f-c5dcea46e6be |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 21
9fe0757a-a2be-4b2e-9eb9-1470ec1440d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 21 | TOB-T2-L21
4f61da93-4a1e-485b-84c3-5a9a9df59722 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 21 | TOB-T2-L21 | AE-ITCX-013 - Visual Inspection
2a33dae5-ae24-430c-9a40-553ccfa6dc82 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 21 | TOB-T2-L21 | AE-ITCX-010 - Torque Settings
a80d8c5b-ca06-4826-b085-4cb894ad7099 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 22
700aa80f-c682-4046-a66b-2fdac0f7103d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 22 | TOB-T2-M-L22
fc1474c8-646a-420c-98ac-7a03846411b7 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 22 | TOB-T2-M-L22 | AE-ITCX-013 - Visual Inspection
b5173975-2242-49bb-b0db-b4513cef874f |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 22 | TOB-T2-M-L22 | AE-ITCX-010 - Torque Settings
e79e79db-2c97-41dc-ad9b-d8d13b717179 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24
694180d5-ccca-4af0-a22f-a4adde69d439 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-H-L24
fe9c1471-9aa7-497a-93af-30e78a1f82e4 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-H-L24 | AE-ITCX-013 - Visual Inspection
93195be3-3ee5-42ba-ae94-670ce0de3ddb |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-H-L24 | AE-ITCX-010 - Torque Settings
b7da817c-717c-43f6-9426-ff2e36bce7f5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-M-L24
0902f970-03f3-49d0-bbad-81b6fde64358 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-M-L24 | AE-ITCX-013 - Visual Inspection
a8470fd3-6804-4083-a66b-c97dd2ce5d32 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 24 | TOB-T2-M-L24 | AE-ITCX-010 - Torque Settings
a33d9cf2-41df-410b-9d6c-76f152b481c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 25
80c78c73-f5af-4386-b1bd-e34c8185d635 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 25 | TOB-T2-L25
78936780-2a76-47a6-a1fa-f7bda849fe52 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 25 | TOB-T2-L25 | AE-ITCX-013 - Visual Inspection
946f631f-2195-47e0-9cb5-bc4ef4fbeba3 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 25 | TOB-T2-L25 | AE-ITCX-010 - Torque Settings
2e3874bb-8301-42a9-adcc-86af2903bdf9 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 25 | TOB-T2-L25 | AE-ITCX-010 - Torque Settings
b4bc42c8-ccdb-49e0-b87d-5ddd7f78e230 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 28
7404463e-d88a-44b3-bac6-e568c02b1d41 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 28 | TOB-T2-M-L28
2ee0e0de-294c-45be-bdbe-7c92145b4dfa |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 28 | TOB-T2-M-L28 | AE-ITCX-013 - Visual Inspection
5da51f6b-4a83-43ce-a2b6-d1cfabb8b3a9 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 28 | TOB-T2-M-L28 | AE-ITCX-010 - Torque Settings
ccbb0b12-78d2-4e17-b1b5-5e9317e6cc8f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 29
c0f3b40c-639f-40ea-a2ad-0ae9c92c0b7d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 29 | TOB-T2-H-L29
5e7d92b3-9b07-4e11-9d9f-ce02474dba42 |  | checklist-flat | not-started | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 29 | TOB-T2-H-L29 | AE-ITCX-013 - Visual Inspection
2e1bc6c7-9f47-4c5e-a8db-df3a2c88b016 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Consumer Mains Installation | TOWER 2 | Level 29 | TOB-T2-H-L29 | AE-ITCX-010 - Torque Settings
85f9d6ac-8e21-4d31-9b08-e97721ed3630 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation
351be018-276d-4f64-8635-3b60b23f7b95 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 1 - TRANSFORMER #2 - MSB-1 (Bus A)
9c408ce2-1c78-469a-bac4-b30c83aac1d3 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 1 - TRANSFORMER #2 - MSB-1 (Bus A) | AE-ITCX-015 - Mandatory Testing
f7e0caf6-9554-4f84-a7fc-eb2080ad2b92 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 1 - TRANSFORMER #2 - MSB-1 (Bus A) | AE-ITCX-010 - Torque Settings
8fa50c30-b6ca-4411-92f3-133707cc8a61 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 2 - TRANSFORMER #1 - MSB-2 (Bus A)
97d759f6-149c-4057-a845-fec0be2f0ec4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | RE1(e) - MSB-1 (Bus LIFE SAFETY SERVICES) - RE1
bac06df7-dbbf-43fd-9d07-b926e4331280 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | RE2(e) - MSB-2 (Bus METERED BUS)
7e9547de-7aba-4770-9043-f583fc7739d6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 3 - MSB-1 (Bus LIFE SAFTEY SERVICES) - T1-LIFT-1
a01c7e2e-28db-44fe-9c47-db249b61b1e9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 4 - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT4
aeb0e2fa-e4b6-4853-b9a4-2e0e6c3a5523 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 4(E) - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT4
e897c885-99d9-44ed-a5cf-3ba17bad55ca |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 5 - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT-5
ec8c4b14-018d-41cc-95dd-523a821d5d76 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 5(E) - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT-5
93b41c4a-6cb3-45b1-8d42-b92bb697156b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 6 - MSB-1 (Bus LIFE SAFETY SERVICES) - T1-LIFT-2
7692e024-158c-4741-937e-fba829ee941a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 7 - MSB-1 (Bus LIFE SAFTEY SERVICES) - T1-LIFT-3
da49a5c9-3068-482f-a430-4ff96d95c8f5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 8 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T2-30.02
9ccc2211-c457-40d0-aa73-060abd09d66b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 8(E) - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T2-30.02
ebbe67e7-5cbe-43cb-ad64-e603024a9e40 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 9 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T1-31.02
e2e85d03-3fda-4381-bb66-aad4d4d6f720 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 9(E) - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T1-31.02
bab73cd2-23f9-4697-8646-f4eadf85b2b4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 10 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-02.02
c435cbc4-25b0-434b-846b-6bb6b4a57831 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 11 - MSB-1 (Bus LIFE SAFTEY SERVICES) - JOCKEY PUMP
b778ed9a-2209-450b-bf46-1fcb9f9275b8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 14 - MSB-1 (Bus LIFE SAFTEY SERVICES) - TANK INDICATOR
1917202f-864e-41e5-aa55-455f875d6404 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 17 - MSB-1 (Bus LIFE SAFTEY SERVICES) - DIESEL PUMP
291fd61f-2d70-4038-a4f7-3156f5592302 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 19 - MSB-1 (Bus LIFE SAFTEY SERVICES) - ELECTRIC PUMP
0768ef49-b7b5-4c89-b44a-ab895df267ab |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 20A - MSB-1 (Bus METERED BUS) - TOB-T1-H-L1.1
f2ee6ebd-922b-4ece-9496-20f7d845cbf9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 20.1 - TOB-T1-H-L1.1 - DB-H-DAS
dc6ee053-3385-44c2-8a42-2011a02f1f34 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 20.2 - TOB-T1-H-L1.1 - DB-H-COMMS
3afcc61d-079f-4d0b-883b-ff7ec8f320eb |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 21A - MSB-1 (Bus METERED BUS) - TOB-T1-H-L2
c2a76ce1-4834-4603-a0a4-7d7cef9ca40b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 21.1 - TOB-T1-H-L2 - DB-H-T1-L2
cb0bb179-ee44-4f7d-878e-f44e065afd27 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 21.2 - TOB-T1-H-L2 - DB-H-T1-L3
36aa045a-53cb-47cd-9d0e-21a78175c01d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 22 - MSB-1 (Bus METERED BUS) - TOB-T1-H-L29
359660fe-5332-4b3c-827b-871deb5b7735 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 23 - MSB-1 (Bus METERED BUS) - MSSB-T1-31.01
de16a74f-8278-4478-8ada-35aa61200bcc |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 24 - MSB-1 (Bus METERED BUS) - MSSB-T1-03.01
42fd681c-4dd9-43d4-bd89-8b8c468264e8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 25 - MSB-2 (Bus UNMETERED BUS) - TOB-T1-L17
e461625b-23b2-4d3e-8673-34a9d0a2b7e1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 26 - MSB-2 (Bus UNMETERED BUS) - TOB-T1-L27
7fd0acbe-8b97-4ade-8f17-636289c6098f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 27 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-01
6c00b772-017a-4919-bf2b-4dbd906055a3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 27(e) - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-01
82f2a9ef-c67f-4b2e-af77-6a5689c1c13f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 28 - MSB-2 (Bus UNMETERED BUS) - DB-T-G-01
d09b9d2a-8c8f-474a-a1cd-6ad79ab63a56 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 29 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-02
dc61ff18-a777-4a21-8cf6-a7a5c843fc34 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 30 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-03
b159e4de-a04b-4f1c-a469-14a72cc2fc44 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 31 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-04
b6939915-5568-4282-a062-a5f9c16d9e8a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 32 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-05
ee7a14be-1ed5-405f-abb4-344dff5f94a4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 33 - MSB-2 (Bus UNMETERED BUS) - MP-RETAIL.01
bb88ca8a-0d33-488e-8b40-6a48b4a1e779 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 33.1 - MP-RETAIL.01 - DB-T-L1-06
314d5eb5-7778-4931-aaf7-0c6ed981cd46 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 33.2 - MP-RETAIL.01 - DB-T-L1-07
10b7f77b-fd25-4d8b-8c82-530a61c7f0db |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 34 - MSB-1 (Bus UNMETERED BUS) - TOB-T1-M-L28
ca6d13b2-7b67-4333-9a22-6de9ff9e482d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 35 - MSB-2 (Bus METERED BUS) - DB-H-T1-G
fbf0f2a4-9a20-4ff8-bc14-527c5bd1e321 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 35(e) - MSB-2 (Bus METERED BUS) - DB-H-T1-G
d859f635-8d77-4b80-a978-15b5c059b8ed |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 35.1 - DB-H-T1-G - DB-H-T1-B1
9e740ab1-9830-41ce-b611-66c705c51289 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 36 - MSB-2 (Bus METERED BUS) - MSSB-B1-01
dd63b544-5f36-4984-87dc-0740dcca9ee1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 37 - MSB-2 (Bus METERED BUS) - TOB-T2-H-L29
3fe93efb-f186-4f52-918c-a6510e1056b1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 38 - MSB-2 (Bus METERED BUS) - T2-LIFT-3
f579303b-b1e1-4a76-9e40-49d0189e9c95 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 39 - MSB-2 (Bus METERED BUS) - MSSB-T2-03.01
2e287f92-4567-4a8c-9f14-4741149dbdde |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 40 - MSB-2 (Bus METERED BUS) - MSSB-T2-30.01
6797070c-981e-4a79-8e1b-0141d250050e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 41 - MSB-2 (Bus METERED BUS) - MSSB-2.01
f1ffad63-7408-46b8-84ef-04e8725d5729 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 42 - MSB-2 (Bus UNMETERED BUS) - TOB-T2-L12
e7f4afb6-74e4-43c0-8e80-724bcd87da86 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 43 - MSB-2 (Bus UNMETERED BUS) - TOB-T2-L25
50ea8444-5e3a-40de-8c8f-9dc8c2dc868b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 44 - MSB-2 (Bus UNMETERED BUS) - MSSB-2-01-AFL
19b708e8-800f-43c7-8932-9ff0dd2fd8fe |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 45- MSB-2 (Bus UNMETERED BUS) - TOB-T2-M-L28
03eb35f6-d4c7-4201-a81e-d9541a4ec5bc |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 46 - MSB-2 (Bus UNMETERED BUS) - MP-B-01-EV
dbd19765-b8f2-4187-8519-01be1f191b0b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 46(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-01-EV
4d783e17-bfea-4ffc-9166-14e71b1bc3ff |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 47 - MSB-2 (Bus UNMETERED BUS) - MP-B-02-EV
18fba35e-6406-4fd5-9b21-e00d839cdce0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 47(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-02-EV
4f62e480-425b-4bce-b097-c22204d13ce4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 48 - MSB-2 (Bus UNMETERED BUS) - MP-B-03-EV
f1235a2b-2c33-4a0b-8cc2-dbf100699700 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 48(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-03-EV
b7892ced-b74d-4c8a-a9ac-66fcd5619eb0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Submain Installation | 49 - MSB-1 (Bus LIFE SAFETY SERVICES) - LOADING DOCK LIFT
e2d1a51e-408f-44b5-b3a3-9a53d232f33e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only)
17d7f1e4-29dc-4957-9931-c1fe56be90b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3
f272c375-40be-4770-a80b-872578c4bc73 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1
c32d1c1a-855c-4038-a0c0-7ea1198cec8a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | DB-H-T1-B1
8f0f4c7f-27c8-4d00-b1f5-1a1a692a8c09 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-010 - Torque Settings
952b4bb5-71d4-425d-80c0-4c5306e4d272 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | DB-H-T1-B1 | AE-ITCX-015 - Mandatory Testing
20677c3b-9b09-45c1-8cd8-1579bf71ae29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | MSSB-B1-01
98b7165e-3017-42d8-b9a3-0824bc88467f |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | MSSB-B1-01 | AE-ITCX-010 - Torque Settings
afd28815-8dbb-49e0-8608-8ca341793caa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Basement 1 | MSSB-B1-01 | AE-ITCX-015 - Mandatory Testing
5014d1fa-2395-4844-b924-3854f75bf5e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground
d7758d4a-5ba3-4ada-a219-740a3e2c5703 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | FIP
45bfb6e4-9126-49b8-a7ec-6eeddf450e40 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | FIP | AE-ITCX-010 - Torque Settings
8cd6c932-e0da-49b3-bb90-cd9527963e7d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | FIP | AE-ITCX-015 - Mandatory Testing
2892892e-1158-41ff-9db3-1332e92797e1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-H-T1-G
9e37c657-c6f8-48bd-ac15-1025aa37cb6e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-010 - Torque Settings
6c52576a-1e6b-4b40-a5cf-80653860d922 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-H-T1-G | AE-ITCX-015 - Mandatory Testing
5c0eb94d-3d71-4229-b93b-414963b429e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-T-G-01
54510335-475c-48dd-9528-75aa5233f8e8 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-010 - Torque Settings
f1706c55-9923-4f22-b54e-a86bb27c50ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Ground | DB-T-G-01 | AE-ITCX-015 - Mandatory Testing
bf16f5dd-92da-4d3e-8f51-1fcc45a194e4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01
5b1b9d87-8d59-4aac-87d8-210343a00b17 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | JOCKEY PUMP
57a12860-2aa2-4c23-825b-ced5dcefd2a1 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | JOCKEY PUMP | AE-ITCX-010 - Torque Settings
729e082e-a1ef-42eb-af57-3ee418bfa80e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | JOCKEY PUMP | AE-ITCX-015 - Mandatory Testing
f628dda1-526b-4bc6-82b2-e8eb6e71e3bb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | TANK INDICATOR
cb1214c7-8e7b-4da7-bb37-95fe55473358 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | TANK INDICATOR | AE-ITCX-010 - Torque Settings
889f950c-ed1f-461d-a147-fb95b739774b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | TANK INDICATOR | AE-ITCX-015 - Mandatory Testing
c1c0148c-bcb2-48ed-8b37-942c642857e9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DIESEL PUMP
f7d63e69-67cf-4834-8329-5b52cee20f09 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DIESEL PUMP | AE-ITCX-010 - Torque Settings
b7ee3e52-2164-424a-ba3d-6fab8967341f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DIESEL PUMP | AE-ITCX-015 - Mandatory Testing
c142c609-0229-4fde-a2cc-cadab44ee6cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | ELECTRIC PUMP
ecb626f8-7c1f-4d11-8f49-2b72eb9f9d24 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | ELECTRIC PUMP | AE-ITCX-010 - Torque Settings
e873a946-ef36-4528-b1ac-2d2cadb4c46b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | ELECTRIC PUMP | AE-ITCX-015 - Mandatory Testing
09f56d2b-fd01-46cf-a14b-10cc541ad8e0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-COMMS
50a815dd-fe40-499d-8d8e-452e965c8fea |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-COMMS | AE-ITCX-010 - Torque Settings
1232e3ff-39b1-4926-9d0e-b18cdcf3a6a2 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-COMMS | AE-ITCX-015 - Mandatory Testing
e07ff569-f5ea-4184-9fb5-0725fa3a925b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-DAS
bebe9ecb-bb22-4743-a14a-65641ad78937 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-DAS | AE-ITCX-010 - Torque Settings
5c88e2ee-2df1-483d-b934-2c544ef33480 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-DAS | AE-ITCX-015 - Mandatory Testing
689cc583-d101-4ba3-935a-44add2bf197d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-T1-L1
42d26ddb-fbbe-4f20-9709-970775fa40a5 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-T1-L1 | AE-ITCX-010 - Torque Settings
57324e7d-a3e0-4c36-90c2-6d9d2dd4e398 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-H-T1-L1 | AE-ITCX-015 - Mandatory Testing
7e9e00c9-21f2-43f7-a2c3-8d0e25ae9da3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-01
c0fafd86-3ab4-43f9-a2e5-b057613ba1c8 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-01 | AE-ITCX-010 - Torque Settings
17d4bad5-1784-47b7-828a-ca25b40b3647 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-01 | AE-ITCX-015 - Mandatory Testing
8222e172-0641-453f-a726-2e431e9416e6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-02
8e6e65bc-74cf-4e90-85fc-076d62dba53d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-02 | AE-ITCX-010 - Torque Settings
b32956ab-19d1-4b98-b468-6eda2e0049e4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-02 | AE-ITCX-015 - Mandatory Testing
d35d1888-5926-4255-988d-227e5d0b2ef9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-03
8d0c95a0-0824-40b8-9ddd-9cbda579331d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-03 | AE-ITCX-010 - Torque Settings
db2cf3df-389a-4031-8512-15f5bdf166eb |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-03 | AE-ITCX-015 - Mandatory Testing
59b9de12-c5e3-405b-8fab-ef5540e372bb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-04
be336235-1e90-4f9f-9dea-ff12563c5877 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-04 | AE-ITCX-010 - Torque Settings
242b2e43-215e-4fe3-a664-0a9ede3b4dcd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 01 | DB-T-L1-04 | AE-ITCX-015 - Mandatory Testing
68b885c4-e525-4252-8d13-5d7321044d67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02
e5e98c53-dcb4-45e0-8f96-7eebd5fd3c3b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | LOADING DOCK LIFT
1cb5941f-c285-4910-b09c-520d642ec68b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | LOADING DOCK LIFT | AE-ITCX-010 - Torque Settings
e8316ae3-2965-4e3a-850d-a5b9a78845d7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | LOADING DOCK LIFT | AE-ITCX-015 - Mandatory Testing
642b27a5-592a-454a-91a7-e7a1455e1f32 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-02.02
7cf06414-c6d6-47af-89f1-97ab9ddd9b78 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-02.02 | AE-ITCX-010 - Torque Settings
31945c37-15a2-4e02-909a-d793ee3cb81f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-02.02 | AE-ITCX-015 - Mandatory Testing
c4c2b286-7cca-4cbf-8838-8d5ad08213cc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | DB-H-T1-L2
a25ad558-b0be-4bc5-a014-c227b1161b02 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | DB-H-T1-L2 | AE-ITCX-010 - Torque Settings
29a43a94-d7b9-4d3d-9f32-22e2b915b65a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | DB-H-T1-L2 | AE-ITCX-015 - Mandatory Testing
7a3d7b02-51e2-44dd-9927-d3a973084ed3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01
93e283f2-d742-4ad6-bd3d-5c9f87fedffb |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01 | AE-ITCX-010 - Torque Settings
71f6b8d4-742a-4f3c-8dc5-b7772befd898 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01 | AE-ITCX-015 - Mandatory Testing
45daa46f-7745-4983-bf81-3e8ca0ddd99e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01-AFL
9aa4c9ad-f7ca-418a-8ef1-5644728f78df |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01-AFL | AE-ITCX-010 - Torque Settings
c10b6f90-0185-4316-ad5f-a8d19a23f16f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 02 | MSSB-2-01-AFL | AE-ITCX-015 - Mandatory Testing
66c3155b-5607-4561-9966-246b8e7bcb54 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03
6f1d0808-c11a-427a-ba9c-edad92fc3fbb |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T2-03-01
e2ef958a-32b2-455a-8435-c012b90617aa |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T2-03-01 | AE-ITCX-010 - Torque Settings
c76062cb-a5ee-4042-bdef-5260578a9702 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T2-03-01 | AE-ITCX-015 - Mandatory Testing
2cb8576f-c876-4689-8d7a-7c0b4134d7e5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T2-L3
5eec0239-dd6b-4950-9c00-51c7e50fbf8a |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T2-L3 | AE-ITCX-010 - Torque Settings
43ac803e-49af-4973-afb7-9f112e224081 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T2-L3 | AE-ITCX-015 - Mandatory Testing
572976e1-6304-4daa-bc64-193da7e70618 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T1-03.01
bba5953d-5c57-4ddb-ac9d-2f4732a23964 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T1-03.01 | AE-ITCX-010 - Torque Settings
ce18cf4e-c5ab-4c55-bb7d-d4d916bb1627 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | MSSB-T1-03.01 | AE-ITCX-015 - Mandatory Testing
ca00bd20-28d9-4469-ac4b-33aa8802c64d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T1-L3
ac1a842f-4e1d-403a-9c32-c7d82e7a51aa |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T1-L3 | AE-ITCX-010 - Torque Settings
810a2598-1c4d-4792-9cda-71409e0a686e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | Basement - Level 3 | Level 03 | DB-H-T1-L3 | AE-ITCX-015 - Mandatory Testing
e7ab8588-ba53-4651-85a9-af53338996a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1
bc5abb37-8c44-47be-93f9-4005a278ff13 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 04
64cdf537-ff4b-4ebc-8e00-d3dd01f0b20e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 04 | MSSB-T1-L4.01
e6821736-9201-4819-8f89-d4af218cc424 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 04 | MSSB-T1-L4.01 | AE-ITCX-010 - Torque Settings
6276ef71-64aa-4ebe-b7fd-7a67b0fc6335 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 04 | MSSB-T1-L4.01 | AE-ITCX-015 - Mandatory Testing
dbd6404c-721e-4728-884b-bc6f8ec34267 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07
b94be2b7-f149-4cb8-a077-e87482837967 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | DB-H-T1-L7
d3e482f1-1b62-4874-b95b-8485d8f92a45 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | DB-H-T1-L7 | AE-ITCX-010 - Torque Settings
9a986b55-1928-468b-9de4-3313cbfe500a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | DB-H-T1-L7 | AE-ITCX-015 - Mandatory Testing
32fac2ef-5683-40f8-a17b-da8c9dddfef0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | MSSB-T1-L7.01
3cc9ffd9-30b5-4722-84d4-835c880f163e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | MSSB-T1-L7.01 | AE-ITCX-010 - Torque Settings
a59c9334-50a5-4dfd-aa27-108cfaa7ab15 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 07 | MSSB-T1-L7.01 | AE-ITCX-015 - Mandatory Testing
950c6801-e60a-433b-b7e1-c129015622ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 10
cd51e44a-a820-498a-a1d3-a3dfc0b34b50 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 10 | MSSB-T1-L10.01
b3511f14-0b23-4394-b06c-0b083d0be357 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 10 | MSSB-T1-L10.01 | AE-ITCX-010 - Torque Settings
5609d8c4-bd54-4493-814f-867c5114f5f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 10 | MSSB-T1-L10.01 | AE-ITCX-015 - Mandatory Testing
db84cd36-16fd-4d46-a42c-38cd5b846f4c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 12
fe3a9169-6b9a-4a1d-87a5-d781a89eaf29 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 12 | DB-H-T1-L12
fdf4ac85-27b6-4333-af0d-ac17b74ddb1b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-010 - Torque Settings
fc3b3b8f-dad3-4f37-b448-027a9bd2b0e6 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 12 | DB-H-T1-L12 | AE-ITCX-015 - Mandatory Testing
15b8dc4b-2e59-47d9-872c-4a4d59b8e9e2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 13
7f60c61e-7a37-4a8e-9b64-3b9a78ef8815 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 13 | MSSB-T1-L13.01
99dfc4e4-ce66-4f6d-a2fe-2d76213465c1 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 13 | MSSB-T1-L13.01 | AE-ITCX-010 - Torque Settings
4b52974a-17e9-4ff1-af58-3bbaf0c0954a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 13 | MSSB-T1-L13.01 | AE-ITCX-015 - Mandatory Testing
aed77cb8-2922-4f80-85a9-1f0c7bf3ac0b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 16
43550836-1511-422c-b805-4301551c99f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 16 | MSSB-T1-L16.01
4a9cd85d-83b0-46ee-9d57-ecd364fae830 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 16 | MSSB-T1-L16.01 | AE-ITCX-010 - Torque Settings
e6807a9e-13c2-4a31-9cd7-a08d3571d6ac |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 16 | MSSB-T1-L16.01 | AE-ITCX-015 - Mandatory Testing
40817823-45c6-4398-9736-c1edcaed970b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 18
5b09cf7a-b279-409d-ad45-bc63103c785a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 18 | DB-H-T1-L18
c07f9622-b10b-42a5-8fc8-a8caf76bd122 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-010 - Torque Settings
00cdf535-df35-40bc-a099-d3c34456e0ad |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 18 | DB-H-T1-L18 | AE-ITCX-015 - Mandatory Testing
3b7b62ee-613a-4d59-a7ed-3fccbfacbd52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 19
81989d0d-1e6b-4aba-bf82-5fe3f68cf04c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 19 | MSSB-T1-L19.01
043a08e3-d543-4314-afb8-7babe52a2307 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 19 | MSSB-T1-L19.01 | AE-ITCX-010 - Torque Settings
b6f09ff4-71c7-48b7-8e28-45f4f9bef84c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 19 | MSSB-T1-L19.01 | AE-ITCX-015 - Mandatory Testing
27b94615-73a0-4b3e-9587-e69a721a2fb6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 22
d59f31b6-fecc-496f-9a62-0e5816a41224 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 22 | MSSB-T1-L22.01
1fd208d8-f094-4dcc-873f-2782fba2bcf3 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 22 | MSSB-T1-L22.01 | AE-ITCX-010 - Torque Settings
9e98dabb-d4b3-4c7a-af11-8548dfe64b70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 22 | MSSB-T1-L22.01 | AE-ITCX-015 - Mandatory Testing
19506b4c-27ac-42a4-ac3a-ff8bcd160b88 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 24
2eeffda8-f7b1-4052-a546-c483b259d5d4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 24 | DB-H-T1-L24
a15d3c02-d232-4eb9-870c-18d947d4a358 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-010 - Torque Settings
14f12b9d-bd1f-4ae1-8a9c-2ba2f006b789 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 24 | DB-H-T1-L24 | AE-ITCX-015 - Mandatory Testing
b4e071b4-3c31-4ec7-80df-322fdf672265 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 25
4ad61a3d-dc78-4306-91dc-1da383d6a3af |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 25 | MSSB-T1-L25.01
002dff8b-a992-4332-90f4-ea37832d8da0 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 25 | MSSB-T1-L25.01 | AE-ITCX-010 - Torque Settings
898e3a6d-07a9-4bc6-950d-b35e92df16f1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 25 | MSSB-T1-L25.01 | AE-ITCX-015 - Mandatory Testing
3e0cfc09-3376-43a7-8c2c-fb4cb9ad512d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 28
e5234c03-2929-4255-ba14-ace829ffb99b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 28 | MSSB-T1-L28.01
87f29f63-b2da-48e2-8449-970328ff1114 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 28 | MSSB-T1-L28.01 | AE-ITCX-010 - Torque Settings
87e147c6-91cd-4033-8676-fa1547e06fc8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 28 | MSSB-T1-L28.01 | AE-ITCX-015 - Mandatory Testing
738edcce-6244-476f-b1ed-7dd2df366877 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 29
4850e387-b240-47ec-ac1b-388ef1e94f35 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 29 | DB-H-T1-L29
464ced83-b9f2-4248-a6be-ee33d2416a6b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 29 | DB-H-T1-L29 | AE-ITCX-010 - Torque Settings
db28e25b-b07a-44be-873e-28ad21c4a9d1 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 29 | DB-H-T1-L29 | AE-ITCX-015 - Mandatory Testing
d0591c18-561f-4f25-8e7a-fde4ec624a0c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31
4bc175db-5d32-4145-a09d-66843795d09d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.01
7c468e23-8133-4efc-a2e5-82c245085f7b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.01 | AE-ITCX-010 - Torque Settings
c943fb9e-9a09-4a7f-acbe-054d7cc687a8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.01 | AE-ITCX-015 - Mandatory Testing
41f683fe-fb01-4a71-93d4-97ec17098ada |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.02
800c0702-05e7-403e-ad53-4e851a82a62f |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.02 | AE-ITCX-010 - Torque Settings
a5c1d326-b3ef-40fa-86d3-67bb22caca25 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | MSSB-T1-31.02 | AE-ITCX-015 - Mandatory Testing
d5f4fc3a-d77d-4eec-a28c-33d5bf00e653 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-1
03da38cd-fe7c-4a45-80dc-b2c940a50bbe |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-1 | AE-ITCX-010 - Torque Settings
e74f31dd-1781-4c60-bc54-92f024d38dff |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-1 | AE-ITCX-015 - Mandatory Testing
f5264a58-5ad0-4597-8447-794e6e0bb997 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-2
9a12eb92-9fcc-4280-986e-ad8707462fc3 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-2 | AE-ITCX-010 - Torque Settings
fee9d65a-1554-4e11-98a5-db3dab62eb2e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-2 | AE-ITCX-015 - Mandatory Testing
3f4f1bc9-a687-4ddc-b95b-257531bad557 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-3
c3aa5e39-c764-4b20-a9f3-b2dcdd33afde |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-3 | AE-ITCX-010 - Torque Settings
a429b909-7b11-4aeb-a1db-4b89c96d4320 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 1 | Level 31 | T1-LIFT-3 | AE-ITCX-015 - Mandatory Testing
942736eb-84d4-4c56-a634-5bc5e4921126 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2
1c596619-63b0-4402-abb3-9aa0e1517755 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 04
0f4f9ece-715c-47d9-a537-e53005a71c4c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 04 | MSSB-T2-L4.05
0dfd8695-2941-4b9d-8e48-cd3947e584c8 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 04 | MSSB-T2-L4.05 | AE-ITCX-010 - Torque Settings
59d07ec8-5beb-43e7-bf7f-c322b57a217b |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 04 | MSSB-T2-L4.05 | AE-ITCX-015 - Mandatory Testing
a2a7e51f-938c-465f-9b56-e0baf21a1b10 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07
cdab35df-2d27-47b7-bd2d-4aace5023367 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | DB-H-T2-L7
ac0e48a5-d30f-452b-bd11-a78becae5d59 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | DB-H-T2-L7 | AE-ITCX-010 - Torque Settings
1a2c9920-a719-4fef-a717-574a7923f603 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | DB-H-T2-L7 | AE-ITCX-015 - Mandatory Testing
cda44b2d-fea6-44cc-803c-f65844de3430 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | MSSB-T2-L7.01
9afaf167-2c09-4b14-9264-0e54aa8317b8 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | MSSB-T2-L7.01 | AE-ITCX-010 - Torque Settings
5d7512f3-5b31-4510-adef-8f0b81e64798 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 07 | MSSB-T2-L7.01 | AE-ITCX-015 - Mandatory Testing
7221e305-02bf-473a-9078-57a2d6adc6a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 10
05872bd5-571e-4a54-ae35-acfaf909a4cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 10 | MSSB-T2-L10.01
40acf55d-ad83-47b3-bdef-cda41b8f8b08 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 10 | MSSB-T2-L10.01 | AE-ITCX-010 - Torque Settings
7a762545-85f4-4c18-b40b-ac24d6d2c123 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 10 | MSSB-T2-L10.01 | AE-ITCX-015 - Mandatory Testing
3fa38108-a004-4ad8-b213-cfd143fc720b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13
b05f2bdc-c3a8-4a82-b668-9eca8f057a67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | DB-H-T2-L13
00e5119a-8fbf-4b0c-8848-ddbcb22884dd |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-010 - Torque Settings
b8042c20-8ff1-4eb0-be5b-798d910b91af |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | DB-H-T2-L13 | AE-ITCX-015 - Mandatory Testing
5be569be-fc93-47d2-804f-5825a6016c4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | MSSB-T2-L13.01
fa1b175d-96aa-4dd7-99aa-772a944c8197 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | MSSB-T2-L13.01 | AE-ITCX-010 - Torque Settings
f3473ae0-2ed4-4597-bffd-35e4c67a07fd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 13 | MSSB-T2-L13.01 | AE-ITCX-015 - Mandatory Testing
43c66b0a-c646-4081-99e9-e79dd8233aaf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 16
286151b6-fa33-4bdc-b7c0-a35fd996ce67 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 16 | MSSB-T2-L16.01
6e3048ad-ff3a-4b8e-a35b-9dd5f8a92c50 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 16 | MSSB-T2-L16.01 | AE-ITCX-010 - Torque Settings
b6c16824-b7a7-43f7-a108-3f997681dd44 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 16 | MSSB-T2-L16.01 | AE-ITCX-015 - Mandatory Testing
faab72be-17a4-4b44-8630-dd3ebbfd83a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 18
4883cf17-6016-4d7c-a2fc-f4cee512ab0c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 18 | DB-H-T2-L18
19765780-b40f-4826-b551-da66d207bd91 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-010 - Torque Settings
d847abf4-2a8f-4a3b-be98-e7592bd42085 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 18 | DB-H-T2-L18 | AE-ITCX-015 - Mandatory Testing
52e42698-116b-4a99-b1d3-21691c8871ad |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 19
ab2b979f-57f4-4091-9372-3c606caa77a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 19 | MSSB-T2-L19.01
e267d668-a130-4e32-b75b-8fba419b5696 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 19 | MSSB-T2-L19.01 | AE-ITCX-010 - Torque Settings
572495d9-6d70-4545-ba05-1e5dbaf3bbd8 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 19 | MSSB-T2-L19.01 | AE-ITCX-015 - Mandatory Testing
01070334-736c-4acb-aaf3-2872e34cf207 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 22
46fc6d8a-5aa6-41d5-80f8-4e1652d69ab3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 22 | MSSB-T2-L22.01
932dd309-c54f-4fc7-9bcb-748b075e82d1 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 22 | MSSB-T2-L22.01 | AE-ITCX-010 - Torque Settings
e2189d7e-c7bc-4b90-9701-2264e4e53944 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 22 | MSSB-T2-L22.01 | AE-ITCX-015 - Mandatory Testing
460ad9ee-8bf7-428b-9018-9d4c41d23f4a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24
ef2231df-2af3-4650-8b1f-fa732568899d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | DB-H-T2-L24
71876879-a6fa-438e-b24a-ab0677389764 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-010 - Torque Settings
c19c77a5-6ddc-457c-bdf4-d8857adc2261 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | DB-H-T2-L24 | AE-ITCX-015 - Mandatory Testing
b6efdeb5-7377-4e4f-9221-89b1a5bd3bd1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | MSSB-T2-L24.01
5b19d68e-47ea-47de-aeb4-2d97064c8521 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | MSSB-T2-L24.01 | AE-ITCX-010 - Torque Settings
546c48c9-1223-4ea8-8a48-dde033ea627f |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 24 | MSSB-T2-L24.01 | AE-ITCX-015 - Mandatory Testing
9f49b014-ac83-45b1-ba07-e32714cf42f3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 28
1f55124d-048a-4f16-9db5-5791bd14a249 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 28 | MSSB-T2-L28.01
cd9e6d80-1ee1-47f5-ad91-e298b9a338e4 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 28 | MSSB-T2-L28.01 | AE-ITCX-010 - Torque Settings
3bec03f8-0f49-449e-9700-23965f818983 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 28 | MSSB-T2-L28.01 | AE-ITCX-015 - Mandatory Testing
dfa2c37f-93e4-4b20-b5af-62929e1cf3d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 29
9cdfec13-fa8f-4b4e-9834-7874e42a1e70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 29 | DB-H-T2-L29
6669b766-b7c2-48cf-8b93-ab372b7f68ee |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-010 - Torque Settings
2e2709d5-2185-465d-8979-dabdbabd2bdd |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 29 | DB-H-T2-L29 | AE-ITCX-015 - Mandatory Testing
21ceceb2-5e76-4a4a-a8f3-d45de03327cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30
b9c908ff-22cf-4579-aa99-ce587c6663a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.01
269ba52e-577a-4278-a38b-5c053ed42e81 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.01 | AE-ITCX-010 - Torque Settings
6441a7d8-ef4f-45fd-9ddd-064c87cdffea |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.01 | AE-ITCX-015 - Mandatory Testing
f065474b-8ee4-4a70-af14-0e1b4bbeff68 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.02
d2d9c9c7-9c37-4d5c-a08f-64445cdd5895 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.02 | AE-ITCX-010 - Torque Settings
ad7dc2e8-997a-4ae9-8bba-0cd9876fbed7 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | MSSB-T2-30.02 | AE-ITCX-015 - Mandatory Testing
c9f8673a-5513-43a7-ab47-e7902490354a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-1
791ab63f-43f4-4167-adbd-2900d8f31fbe |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-1 | AE-ITCX-010 - Torque Settings
1885b754-8eb7-48cc-871e-75f6b9919190 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-1 | AE-ITCX-015 - Mandatory Testing
213e977e-623e-4a11-9dfd-46ae7cbb9bb7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-2
91c095c3-f395-4cd4-8997-d145642e1241 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-2 | AE-ITCX-010 - Torque Settings
6f23e67a-b9a1-445f-8ccc-fe06ac756a4e |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-2 | AE-ITCX-015 - Mandatory Testing
c3bce981-c608-4797-b7ef-b3efe750f619 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-3
aed2fd11-4e79-4220-82d0-fda6ae742ff1 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-3 | AE-ITCX-010 - Torque Settings
7e24bc2c-5867-4028-9bf0-1f784f58cafa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | DB Installation - (Top of Main Switch Only) | TOWER 2 | Level 30 | T2-LIFT-3 | AE-ITCX-015 - Mandatory Testing
22cb18f4-9e6f-4927-ba18-1260cfd5a8a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only)
956a0b1d-39f0-4f60-a547-90504c18c71b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3
b06c3f3f-ee1c-4b2d-b839-6cd29db37cba |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01
5605692c-da44-432f-9a5b-db359f83d493 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-01-EV
78869f64-e962-4c67-ae60-76f015680156 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-01-EV | AE-ITCX-014 - Visual Inspection
efca1a9c-ef82-43b8-83c3-f91bcbb45500 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-01-EV | AE-ITCX-015 - Mandatory Testing
5e78a1fd-8a85-492f-9b1e-14e1ce438316 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-01-EV | AE-ITCX-010 - Torque Settings
47d5b4e0-f6c4-47cc-a3d0-ab9d35497509 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-02-EV
00d35caa-a49f-4976-8db5-49c2c136ee59 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-02-EV | AE-ITCX-014 - Visual Inspection
2b820f4f-6e22-4692-84e2-3fe001bd8772 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-02-EV | AE-ITCX-015 - Mandatory Testing
fcbb5cc4-2ad6-4af3-829b-2487bb3f53e5 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Basement 01 | MP-B-02-EV | AE-ITCX-010 - Torque Settings
4528486f-13e1-42fb-9199-f719fe7cee89 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Level 01
a23d9af6-a933-4bda-a56f-870f61d1f218 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Level 01 | MP-RETAIL.01
f2e532ed-2ff9-4244-a395-a6d16b84aacb |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Level 01 | MP-RETAIL.01 | AE-ITCX-014 - Visual Inspection
6e109141-9767-45f1-8c8b-c01c6426dc64 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Level 01 | MP-RETAIL.01 | AE-ITCX-015 - Mandatory Test Result Sheet
8839728b-06b7-41db-b671-fa5469ffdae9 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | Basement - Level 3 | Level 01 | MP-RETAIL.01 | AE-ITCX-010 - Torque Settings
0e3ad843-9379-43e0-beab-28503008341b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1
b3b069b4-7fa7-47a2-9cd4-65c3a0ff7111 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 05
6988e916-f60d-47ac-bc83-ec647de80a42 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 05 | MP-T1-L5
0b40fb4f-a327-454b-8f4f-19a96310790e |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 05 | MP-T1-L5 | AE-ITCX-014 - Visual Inspection
3cc1a72b-4479-47cb-8fe3-bd4e8cf8520c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 05 | MP-T1-L5 | AE-ITCX-015 - Mandatory Test Result Sheet
71f2dbcb-27b5-4f3c-88a4-069e35205d0f |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 05 | MP-T1-L5 | AE-ITCX-010 - Torque Settings
6caa2202-70cf-4e59-a004-c22f97daa33c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 06
8f6b8d02-32fa-4e97-99a1-88d4868042a5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 06 | MP-T1-L6
d35bb2b3-e6e6-44e0-8987-7097e937d320 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 06 | MP-T1-L6 | AE-ITCX-014 - Visual Inspection
cd22ac1b-d632-450d-9b6b-e202afe7fda9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 06 | MP-T1-L6 | AE-ITCX-015 - Mandatory Test Result Sheet
76707afe-5fe8-4333-a6e4-495cd333fd0a |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 06 | MP-T1-L6 | AE-ITCX-010 - Torque Settings
8439633b-81ca-4a49-b9b0-78f1b527bf92 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 09
8f6107a7-c0fa-45cd-87d0-150ea058975c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 09 | MP-T1-L9
6e4d65da-b1cf-4804-b4e4-f0360f6f466c |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 09 | MP-T1-L9 | AE-ITCX-014 - Visual Inspection
fccc68b0-b8fe-4f46-a184-d57e7cf7f3f9 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 09 | MP-T1-L9 | AE-ITCX-015 - Mandatory Test Result Sheet
4761d12c-11bc-4cad-b2f9-684a6e3ba528 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 09 | MP-T1-L9 | AE-ITCX-010 - Torque Settings
0acf60cc-4fd5-4468-8950-4bdadd67a7f6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 10
8bc8b15d-0377-465e-b6ac-c66689f3ef54 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 10 | MP-T1-L10
9719d6fd-747b-4adb-aec3-5c8c5efded0b |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 10 | MP-T1-L10 | AE-ITCX-014 - Visual Inspection
f011e692-3b42-4b31-9c82-c7d0ae5c3644 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 10 | MP-T1-L10 | AE-ITCX-015 - Mandatory Test Result Sheet
6675acfc-265d-4c46-ac52-368d9a6e3281 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 10 | MP-T1-L10 | AE-ITCX-010 - Torque Settings
d7021e52-67f8-4336-9c68-72eccd210dcf |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 13
b4229dac-c923-4378-9a44-1df1d5c65751 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 13 | MP-T1-L13
ac088b80-3c39-450b-a41f-e202fae0356a |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 13 | MP-T1-L13 | AE-ITCX-014 - Visual Inspection
da99e2a1-3dc8-4448-80c0-33155ab1ff31 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 13 | MP-T1-L13 | AE-ITCX-015 - Mandatory Test Result Sheet
ba821fec-5b19-413d-8720-29fc01cabd1e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 13 | MP-T1-L13 | AE-ITCX-010 - Torque Settings
092b3021-079a-4166-9fa2-ff5909783b91 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 14
767c9340-a9be-4ac2-8668-c39d2434f839 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 14 | MP-T1-L14
293f769b-e9bc-4d1c-b3cb-9fa259c4afbe |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 14 | MP-T1-L14 | AE-ITCX-014 - Visual Inspection
bcaf5261-d75d-4bc0-a630-8750ac59da55 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 14 | MP-T1-L14 | AE-ITCX-015 - Mandatory Test Result Sheet
fa79743c-bbcf-43b1-9a3e-1c91030c503d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 14 | MP-T1-L14 | AE-ITCX-010 - Torque Settings
bfd22787-3086-47d4-a8b1-0462710e6d74 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 17
d6f32542-eb5e-4b52-a393-9871d904075e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 17 | MP-T1-L17
d6c6a338-c6fe-449c-9ad1-761973ebd0fd |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 17 | MP-T1-L17 | AE-ITCX-014 - Visual Inspection
2aaf3ba0-db88-4883-982b-39a526d50b98 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 17 | MP-T1-L17 | AE-ITCX-015 - Mandatory Test Result Sheet
317f2ba8-cf9b-4b7d-aaa3-9ad34332a1de |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 17 | MP-T1-L17 | AE-ITCX-010 - Torque Settings
10b6cab0-e5ce-4e31-8595-163b0cea72d9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 19
9f7b5221-3648-4667-859c-1baba88e4849 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 19 | MP-T1-L19
401749cc-2a82-41b5-b03e-6b2275e6588c |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 19 | MP-T1-L19 | AE-ITCX-014 - Visual Inspection
1f2fba6b-d6f0-4a87-8617-8d81dc072075 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 19 | MP-T1-L19 | AE-ITCX-015 - Mandatory Test Result Sheet
c4cc47d2-3c34-4d44-a17b-c0e5972cf264 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 19 | MP-T1-L19 | AE-ITCX-010 - Torque Settings
14afc04c-0001-4b79-8508-eaaa3f20595c |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 20
78e207ad-3580-447f-a81d-1bbc1e540b77 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 20 | MP-T1-L20
762ed30e-ef77-47bc-9bed-009416d11d9e |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 20 | MP-T1-L20 | AE-ITCX-014 - Visual Inspection
f8d7208c-ca78-4afe-b4cf-d6db91c6853c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 20 | MP-T1-L20 | AE-ITCX-015 - Mandatory Test Result Sheet
a699f149-9df7-4c89-946d-74b2bbc5372c |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 20 | MP-T1-L20 | AE-ITCX-010 - Torque Settings
521787ca-5bf9-45c9-b239-1f10692569fc |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 23
7380e333-1d97-4f73-9a85-5e3bf959ccc4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 23 | MP-T1-L23
cf1dc3d7-bbcc-45d7-a956-bb32cc1b23fd |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 23 | MP-T1-L23 | AE-ITCX-014 - Visual Inspection
1df51e86-7693-40b7-8acd-ccdbf81715ed |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 23 | MP-T1-L23 | AE-ITCX-015 - Mandatory Test Result Sheet
0c9604cd-ad17-419d-8ceb-ec2d9a18c212 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 23 | MP-T1-L23 | AE-ITCX-010 - Torque Settings
89cd5d83-ad82-45a0-a108-ea8f7b737e4a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 24
4dd1a758-76c7-4386-a1af-f1aa318276b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 24 | MP-T1-L24
da97b167-49f2-4e61-8832-99666b5e1cab |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 24 | MP-T1-L24 | AE-ITCX-014 - Visual Inspection
152019d7-70be-4d0d-a210-ba75541421f0 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 24 | MP-T1-L24 | AE-ITCX-015 - Mandatory Test Result Sheet
9d3861f1-493c-404f-9347-7bf47129fea8 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 24 | MP-T1-L24 | AE-ITCX-010 - Torque Settings
12d07cd8-11e7-44a6-a2e5-3174a2316e12 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 27
6c5b7a50-875d-46dc-bdf4-bf38559aeda3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 27 | MP-T1-L27
f97f4f16-7980-4a60-9266-029dc9de21cb |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 27 | MP-T1-L27 | AE-ITCX-014 - Visual Inspection
4f632be0-3504-4584-ad5c-6fd668b4c9fe |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 27 | MP-T1-L27 | AE-ITCX-015 - Mandatory Test Result Sheet
cd4d6258-818e-4ab8-9f0f-928d5c9a7d9e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 27 | MP-T1-L27 | AE-ITCX-010 - Torque Settings
c7c56c09-2008-4cf3-94bc-f3c2576a338e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 28
5517d563-d128-46ed-a956-1e13ec5a7615 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 28 | MP-T1-L28
424f74ee-2288-416f-a3b5-a594215d3e6e |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 28 | MP-T1-L28 | AE-ITCX-014 - Visual Inspection
60482761-545c-4c19-8ffb-3b85e1571b9a |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 28 | MP-T1-L28 | AE-ITCX-015 - Mandatory Test Result Sheet
bd1513d5-db48-4509-a8ef-b3fb8b353b5b |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 1 | Level 28 | MP-T1-L28 | AE-ITCX-010 - Torque Settings
0e5c3b45-a4db-4d81-86b3-77dd41eed3ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2
2c8cb25a-2dcd-4c16-8dbf-ede9d2018753 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 04
43326993-3d6f-4f7e-9f15-55fe1c4d968d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 04 | MP-T2-L4
b5090a10-c9cf-4e8c-b116-f721804e711b |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 04 | MP-T2-L4 | AE-ITCX-014 - Visual Inspection
881a5617-7f14-47b0-a1f5-f89e1054142c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 04 | MP-T2-L4 | AE-ITCX-015 - Mandatory Test Result Sheet
9f0fe692-e00c-42c8-9eac-6224e3f002bf |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 04 | MP-T2-L4 | AE-ITCX-010 - Torque Settings
b409f782-e177-4972-888d-35a2c1cb9b16 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 06
19d96ac6-e3e6-4694-844c-8d4a9f6fca36 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 06 | MP-T2-L6
acc6bdee-aa14-40d0-9a55-4e0d0ccd98d8 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 06 | MP-T2-L6 | AE-ITCX-014 - Visual Inspection
129016ea-515a-4d11-9987-f66dfbf91208 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 06 | MP-T2-L6 | AE-ITCX-015 - Mandatory Test Result Sheet
c4587ed8-55d3-4fb0-952e-906c14953fa0 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 06 | MP-T2-L6 | AE-ITCX-010 - Torque Settings
6fd4ac83-62c9-4121-806e-19031a55f51a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 08
713419c5-b55c-4580-89c1-353c40498288 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 08 | MP-T2-L8
f7686503-f3e3-4206-a09f-de75849daf98 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 08 | MP-T2-L8 | AE-ITCX-014 - Visual Inspection
1f4f8b4e-e432-4ab4-9d4a-5f05101d1bb4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 08 | MP-T2-L8 | AE-ITCX-015 - Mandatory Test Result Sheet
f26428f9-a0be-4efa-9c5d-7d8204889046 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 08 | MP-T2-L8 | AE-ITCX-010 - Torque Settings
dd2e020f-cf7a-45ff-84aa-a6948be83858 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 10
365ada91-24e5-4436-8093-a096852898a2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 10 | MP-T2-L10
c49a3504-67dc-4c24-95d9-6866f78875c4 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 10 | MP-T2-L10 | AE-ITCX-014 - Visual Inspection
da5f5ddd-ac34-459d-ab0a-4bed3676ead4 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 10 | MP-T2-L10 | AE-ITCX-015 - Mandatory Test Result Sheet
8de75271-8b58-4811-9c7d-70d7810e6730 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 10 | MP-T2-L10 | AE-ITCX-010 - Torque Settings
3df8681d-5207-4808-8604-7add8540919e |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 12
63521ad8-0c28-4dd6-8f58-407117c1e63f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 12 | MP-T2-L12
ddc2332b-bde0-4641-97ae-a85527e68106 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 12 | MP-T2-L12 | AE-ITCX-014 - Visual Inspection
1361fafb-960e-43ca-9d6b-d7522bee2647 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 12 | MP-T2-L12 | AE-ITCX-015 - Mandatory Test Result Sheet
fb61c777-35a3-4209-a7ea-91ed7bd012df |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 12 | MP-T2-L12 | AE-ITCX-010 - Torque Settings
9742a9da-2bff-4924-a022-b99f1fbc6b8f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 14
34a37e57-3e14-4422-98bf-02ee859f7f9f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 14 | MP-T2-L14
6196f436-5ee7-4173-b171-4644b790fbdb |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 14 | MP-T2-L14 | AE-ITCX-014 - Visual Inspection
9b423205-b472-476d-9505-416e6c3f330d |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 14 | MP-T2-L14 | AE-ITCX-015 - Mandatory Test Result Sheet
3d2ba7b2-e690-49d3-918f-5d2925032813 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 14 | MP-T2-L14 | AE-ITCX-010 - Torque Settings
39056159-3b53-4a08-82f9-5eca366135ba |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 17
eaddfaa7-0f7e-413a-ab43-991484ef4cd0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 17 | MP-T2-L17
8dd95f58-f898-4d38-af73-d04304fdab96 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 17 | MP-T2-L17 | AE-ITCX-014 - Visual Inspection
d011b69e-7ba9-4bd4-98cc-47c8daedd7aa |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 17 | MP-T2-L17 | AE-ITCX-015 - Mandatory Test Result Sheet
5f660b78-b9d3-4c38-b817-2fe74b00838e |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 17 | MP-T2-L17 | AE-ITCX-010 - Torque Settings
1ade6bd6-e203-4305-9858-1a3e1b31a63b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 19
916de4d8-10a9-4491-8675-bedd9601bc03 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 19 | MP-T2-L19
91656e7c-fec1-4032-b92c-68a6500ba6bc |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 19 | MP-T2-L19 | AE-ITCX-014 - Visual Inspection
1ed51925-6d77-4787-b0fa-2efa7de00b70 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 19 | MP-T2-L19 | AE-ITCX-015 - Mandatory Test Result Sheet
6b8b7657-014a-4d47-9c30-b29a26ae86ac |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 19 | MP-T2-L19 | AE-ITCX-010 - Torque Settings
48ddbbcb-ba03-441e-af31-90bc19bf40c7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 21
5050684c-6f85-4ace-9e9a-ba6e69555c73 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 21 | MP-T2-L21
7fbd8385-69fd-4857-a948-9a6efcf2b1ad |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 21 | MP-T2-L21 | AE-ITCX-014 - Visual Inspection
c416674f-fcf6-41de-a5d7-ac4d13b6c42c |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 21 | MP-T2-L21 | AE-ITCX-015 - Mandatory Test Result Sheet
c8661bdd-bc95-4b8d-80cf-d9ed9d57a473 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 21 | MP-T2-L21 | AE-ITCX-010 - Torque Settings
d2739481-7d7e-4aa0-bab0-98f3cc4b2605 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 23
fbdcba22-fac0-451a-8b9a-a61092c30b32 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 23 | MP-T2-L23
de796304-7a33-455e-a02a-d488a529cb49 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 23 | MP-T2-L23 | AE-ITCX-014 - Visual Inspection
2e38a6ba-7414-43f3-af3f-793afd035369 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 23 | MP-T2-L23 | AE-ITCX-015 - Mandatory Test Result Sheet
fc60afaf-fe79-4160-8e2e-5630788d78a2 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 23 | MP-T2-L23 | AE-ITCX-010 - Torque Settings
9facea1e-6754-4a92-9345-665550cb0ea7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 25
99bb6151-3f02-4c39-9227-d315df6bd2ab |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 25 | MP-T2-L25
5b24fc3e-2cd3-4698-be7a-089879032b91 |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 25 | MP-T2-L25 | AE-ITCX-014 - Visual Inspection
c093bbca-955e-4bb6-9703-d10435252c77 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 25 | MP-T2-L25 | AE-ITCX-015 - Mandatory Test Result Sheet
2f0c60fb-2ec0-4ff2-a08e-5f4583c0afc7 |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 25 | MP-T2-L25 | AE-ITCX-010 - Torque Settings
28a66364-1a17-4a9f-bee0-573d5d70e2f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 27
fb44abca-ab3e-4f1e-be1e-c3fab20de36f |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 27 | MP-T2-L27
fe9e47c4-2b44-4ccb-abf6-61a98a15f9aa |  | checklist-flat | not-started | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 27 | MP-T2-L27 | AE-ITCX-014 - Visual Inspection
b469a9f5-8e21-4961-905d-c55be51fc006 |  | checklist-flat | not-started | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist-flat | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 27 | MP-T2-L27 | AE-ITCX-015 - Mandatory Test Result Sheet
4ffa1646-0420-43d9-8a91-e4d65ef4401d |  | checklist-sectioned | not-started | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | Mains Reticulation | Meter Panel Installation - (Mount and connection to panel Isolator only) | TOWER 2 | Level 27 | MP-T2-L27 | AE-ITCX-010 - Torque Settings
bdccda65-91fc-4ca3-9b54-5a50e40d98b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | MATV panels and backbone
588a2275-88c2-4f90-9568-a5a8940b9225 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | MATV panels and backbone | Basement to Level 3
0c3afc33-5799-4175-a3fd-3c020cf517f0 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | Basement to Level 3 | TVP - Retail Tenancies/Level 1/ Ground
e8e0e334-0058-4b2a-85ab-dfd19232814f |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | Basement to Level 3 | TVP - L2
39dc2927-aae7-4caf-a2f8-33d8011d9bad |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | Basement to Level 3 | TVP-L3 East
4617bd0e-a1eb-4854-9570-e1431d0caaf4 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | Basement to Level 3 | TVP-L3 West
ceba0d48-b026-4998-b5cf-f10988962b95 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1
6b268be5-9e95-4706-97a0-328a551a923d |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 4
08714324-84ca-4c80-a76a-2f81d09a9505 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 5
14324871-3649-4e33-a718-0cee806df85b |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 6
70e0360d-f016-4c73-8697-4c26fb6bfc65 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 7
e0af3c5f-4513-4daa-bd43-d133e7d227db |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 8
150d702d-b7dc-4470-a3f2-91b0362daf20 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 9
501ea29a-9dd9-421c-ae01-3bb849ff1c08 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 10
0b534193-ad49-4df9-9159-3f4071e2b9ae |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 11
04be47b0-cba5-472b-b8c9-665e0dcaccd0 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 12
7c23b5ae-2205-4f72-9822-6b24d241d4bd |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 13
885e9845-25ad-46bc-b402-7aed8970c252 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 14
df3f9be6-fd7d-46bb-85c1-58736dc33e6f |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 15
19674f25-8146-4607-85f0-899ace774df3 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 16
ca5cf25a-be69-4bea-8e9a-82a066ad56de |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 17
c10e0fbd-3fd8-4e2d-8751-20827066841a |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 18
c2562c0c-86b5-4f2d-b830-eeef7e99f135 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 19
0aaa8793-8e4b-4b8a-bc14-db81c94ca062 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 20
ef8dc1b3-7d57-419b-bc9c-ca5b8ffed4e7 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 21
34777289-6c71-44e0-af54-e6b90d1c071a |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 22
9da70e44-cbd0-4241-8d2c-22605b3bf00a |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 23
46c893da-2189-46f8-a48f-bacf313b692c |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 24
2d0616ed-8046-4ce9-84bb-1360fbcfc0e7 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 25
da1a422e-44ca-478f-b3e0-7c3242e01bd1 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 26
2abc4a39-a20b-4d1f-a877-00c9a8f224d8 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 27
2784594e-360e-4e3c-9dbe-b0c6fe95846b |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 28
53ca05e7-0189-4c53-8dbc-b5189450b81a |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 29
916f5bd5-30f3-4814-a5e8-e8673600e050 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 1 | TVP - 30
8653356f-575e-4aa1-8528-84cbaed55e98 |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2
b209e248-4c17-4474-97e0-dfe3950a7309 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 4
89ca6564-abdf-4727-b668-1aabde9d9715 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 5
790dc258-b8a9-4df4-89c7-fd76620a6d0d |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 6
3d962d7b-8e1b-485e-a30c-9c64949994f0 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 7
181d23a9-0a66-4d3d-876a-173f4e2cfedd |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 8
81786b52-039e-418a-b9d5-8ce159602fc5 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 9
e1508df5-4070-4f18-8791-1936cbeed41b |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 10
9c552afb-fa6c-4e8a-880e-4f5d52158763 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 11
3e9dd251-273f-4f4d-bca6-979402206ae6 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 12
5a61881f-827f-4fa8-a6a5-9b78166e19bc |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 13
cb15e6a6-0ee9-40f6-b860-906810db43ab |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 14
7984f9dd-2080-4968-ac67-6e88c46ca8b8 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 15
4f9f5515-b886-422d-9a9a-08280a54a3e1 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 16
fdc92b87-b9cc-41ea-89cf-bccf29419bc7 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 17
bdd779cc-d637-4381-9462-636bfde20b3e |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 18
c96b83e1-8d1f-46e3-9538-954ed00e5920 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 19
8bc17433-ee18-441f-972f-8f408820ec70 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 20
973ee337-7f3c-4e2f-91a5-5b349c20a794 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 21
e91948ff-bc21-4b31-af80-5c013175dae6 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 22
846c7566-b4c6-4f22-b820-e2a4f690bf2c |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 23
05fd25af-3d0c-49ae-9844-55a7afc9f07a |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 24
407fc158-327f-419d-a957-f773167a9a63 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 25
2fb840ad-1f10-4468-b5e9-71759a4d4915 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 26
21d986f3-214f-49eb-a3ef-3d6503ddf3a7 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 27
78c45bfc-c7b0-45e4-8f85-4d32ae55c832 |  | checklist-sectioned | not-started | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | checklist | FALSE | FALSE | Appselec - Site QA | MATV panels and backbone | TOWER 2 | TVP - 28
b519c315-5978-4e05-839b-580513255d3a |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Comms/Security
2c67fbe8-beda-438c-a2e0-f73fbd098722 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | Basement 1
063b0258-95ee-4e9f-9952-04f7e96bea78 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | Ground
4f3e9386-47b8-4d51-b79b-050eb6da93ce |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | Level 1
e33f05ca-c8da-4145-90fe-2ba5a83798b2 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | Level 2
3136ba82-538e-4303-9313-92a24b13748e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | Level 3
f0d488b7-671b-4717-8fdc-1b851f249c4b |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1
d3f12cff-d91a-46cb-90c0-0f3e49dd19f9 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 4
3fad5d18-4603-4503-9317-2a3a6f19807a |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 5
9cc8b2ea-96d7-4eb6-a41b-f16d7db9202e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 6
b1fe34e6-7c2c-43d4-be97-255ac93e57ed |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 7
355bd4b3-0417-4b2c-a832-107f7f9cb02e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 8
dbcd2dac-910d-4ee1-9704-1a357a5315fc |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 9
aa019c16-e944-4c81-8f6b-48faea285347 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 10
b81fe912-a355-47ae-9d3c-9ae45b1bbee8 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 11
29fefe64-4ef1-4171-9aef-b887c64fff56 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 12
0b5275e9-b830-49bb-8a56-243e97c3fce6 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 13
45ad5280-98f3-4877-8a76-f18f725fc4af |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 14
e4d95f5f-72e8-4a22-8991-5c84002f10d0 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 15
bdcbb5ef-b4e8-496d-bd04-a453c79cedba |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 16
d0b9f882-9f10-4253-ae8a-0089a0ba2cd7 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 17
e28f07b5-eb22-4deb-945f-82b0669298de |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 18
aa0b3bd1-6d8c-44a1-a942-c83b72cea4e7 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 19
ef76fe21-a207-4839-957a-a4b6e2263591 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 20
b6db4ff9-4b66-498b-adda-b0967741f102 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 21
fdd8c526-c97a-4aab-8370-2bbd219d292c |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 22
d8b58bf5-e0c6-4a18-ae83-43d574684cdb |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 23
6ceac5fa-5ed3-4396-9ead-769eda5eaf8b |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 24
36ae8b01-05fe-4ea7-bed2-f36015a22a93 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 25
e030fe1d-544b-4fea-807b-8c37a40ad83e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 26
9fdc329c-087e-4055-9f2d-11a8f88dfb44 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 27
fbddd802-8003-411d-8a10-b7d735b1da28 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 28
b261edc2-9649-4e05-8b08-3697fc0c896f |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 29
ab8dbe14-410c-4296-904e-ec9eebf9a5b3 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 30
09505a27-902e-4234-bd23-0db60a9a016f |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 1 | Level 31
ebb2c773-cc49-4e33-91a6-5a0b1a53ff2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2
ee4c63d6-f073-4f7e-a9ce-9ddf302d0eb9 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 4
9b0257a6-761a-4060-8eb1-e495dc913103 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 5
e9f23827-cc0b-4cfc-b0d0-2bf22bced595 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 6
0618993d-8ebf-47c9-b9f4-6949a4400f9c |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 7
0f936cb1-3077-4197-9e32-7f4bfd1a2607 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 8
e781abf5-b4d9-42a6-9218-53ea68485371 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 9
c12bc3c2-0d6a-4e79-a5b1-e99be1c96444 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 10
96f4c1f6-5f6b-4386-bcd6-9fbfe58fca44 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 11
b16f4e6d-359b-43d1-aebd-5f40a985bada |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 12
9ef1df93-cb3a-40cd-8dec-6f6ac194c96c |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 13
9dad1af5-0ea2-487e-b7be-d4baaad63cee |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 14
0fdab071-af9d-4715-a149-cd778dd94baa |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 15
78d5bc5f-0a25-49d8-83e6-0c7d17163fcb |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 16
56faedb6-f459-4b5f-9291-72c7d5d9e69a |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 17
ee31dc7d-e707-4d06-92d9-effaea8f4ee8 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 18
46ca2ea8-f2c2-4a6f-8b23-ef47be43c073 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 19
76483c4f-cd86-47a7-8404-6fe6423306ce |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 20
ce86e759-87a2-4e43-b505-b9dd69bde21d |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 21
31b91012-d1ce-4972-a5c1-d60ef80e447e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 22
3b58dbb6-5b87-4076-a590-1c0bbc0d4ab8 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 23
4aca4045-3a89-4001-9b0c-78e7c4f0d858 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 24
51b18254-f90c-4359-a83e-b68fafa298ec |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 25
b591248d-7a06-4fe9-a4e7-529ebafacd6e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 26
c825adff-1da9-4744-97e4-07d9ac05234e |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 27
85d053bb-dd43-43bb-b661-88539894fb11 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 28
b94cd78d-0b93-4108-a912-ae0b54dde7a1 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 29
13b6eeab-b38c-4af5-bf60-a611a69c95b9 |  | checklist-sectioned | not-started | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | checklist | FALSE | FALSE | Appselec - Site QA | Comms/Security | TOWER 2 | Level 30

## resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | AE-ITCX-025 AS:3003 - Appendix E Body Protected CL (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-025 AS:3003 - Appendix E Body Protected CL (Rev 0 +Names) | 0d7a95a3-065d-44ae-a9a3-8d40ca79e1bd
checkpoint-group |  |  | section | Preface
checkpoint-status |  |  | checkpoint | Appendix E: Summary of Information - Pass once confirmed
label | 38fcaff2-7ea9-5d71-9d84-de8aaa6f2e1d |  | note | Routine inspection checklist for Body-Protected electrical areas
label | dd6fe60c-c8e3-5834-ac82-2a08930f349a |  | note | .. ..
label | be936f88-6e6c-5819-a681-46fcc3c9e384 |  | note | This checklist shall be used in accordance with Clause 8.2.7
label | b190d5c8-ea53-5b58-9f2a-55068c0646c0 |  | note | Note: The checklist may be in a different format and may be recorded electronically
checkpoint-group |  |  | section | Inspection & labelling
checkpoint-status |  |  | checkpoint | 8.2.1.1: Inspection - All electrical equipment and fittings in good condition
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Circuit identification visible and intact on each
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Protected points labelled as to which RCD protects them
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Circuit identification visible and intact on each LIM
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Overload monitors labelled with alarm setting
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Socket-outlets protected by RCD labelled 'RCD PROTECTED'
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Socket-outlets protected by isolating transformers labelled 'ISOLATING TRANSFORMER PROTECTED'
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Socket-outlets intended for cleaning purposes labelled 'CLEANING PURPOSES ONLY'
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Body-protected electrical area sign - Still Visible
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Body-protected electrical area sign - Labelled with current inspection date
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Body-protected electrical area sign - Labelled with identity of authorised person
checkpoint-status |  |  | checkpoint | 8.2.1.2: Labelling - Body-protected electrical area sign - Labelled with next test date
checkpoint-group |  |  | section | Socket-Outlets
checkpoint-status |  |  | checkpoint | 8.2.1.3.1: Socket-outlets coloured according to type of supply
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: If RCD protected, power-available indicator operational
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: Number of socket-outlets and permanently wired electrical equipment protected by RCD does not exceed 12
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: On/Off luminous indicators operational, if applicable
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: Socket-outlets double-poled if protected by a transformer-isolated supply
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: All socket-outlets below 2.3m protected by LPD
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: Confirm that when a fault is applied to each socket-outlet within patient area or within 2.0m of entrance of the patient area, the RCD trips
checkpoint-status |  |  | checkpoint | 8.2.1.3.2: Confirm that when a fault is applied to each socket-outlet within patient area or within 2.0m of entrance of the patient area causes a response on LIM
checkpoint-group |  |  | section | 8.2.2: Earthing
checkpoint-status |  |  | checkpoint | Confirm that the earth pins of all socket-outlets below 2.3m are earthed to less than 1.0-Ohm
checkpoint-status |  |  | checkpoint | Confirm that the earth pins of all socket-outlets within 2.0m of entrance to patient area are earthed to less than 1.0-Ohm
checkpoint-status |  |  | checkpoint | Confirm that all socket-outlets used by medical electrical equipment accessible above 2.3m are earthed to less than 1.0-Ohm
checkpoint-status |  |  | checkpoint | Confirm that all permanently wired electrical equipment with conductive parts below 2.3m are earthed to less than 1.0-Ohm
checkpoint-group |  |  | section | RCD
checkpoint-status |  |  | checkpoint | 8.2.3.2: RCD Sensitivity for Australia - Confirm that the RCD trips between 4.5-10.5 mA
text | 90cb8e66-f076-58bd-9374-1e7d6a9b81c5 |  | textbox | Record the RCD sensitivity (may)
checkpoint-status |  |  | checkpoint | 8.2.3.3: RCD Tripping times for Australia - Confirm this by carrying out at least two such tests
text | ca291a86-7bd7-5b32-97a7-ec129ae36cdd |  | textbox | Record the worst case (ms)
checkpoint-status |  |  | checkpoint | 8.2.3.5: RCD Supply available indicator lights - If applicable, confirm that they are operational
checkpoint-status |  |  | checkpoint | 8.2.3.6: Audiovisual RCD Trip Indicators - If applicable, confirm that they are operational
checkpoint-group |  |  | section | 8.2.4.1: Prospective Hazard current
checkpoint-status |  |  | checkpoint | Confirm that the hazard current is below 2.00mA
text | 0064cd30-9a69-5f48-8a3f-aa0f542a811b |  | textbox | Record hazard current (may)
label | 6452184c-9dc7-575e-9836-3f96844ff543 |  | note | For routine testing, the PHC under normal conditions of operation shall be verified by applying the following process to each transformer Line Isolation Overload Monitor (LIOM)
checkpoint-status |  |  | checkpoint | All electrical equipment are disconnected from the supply
checkpoint-status |  |  | checkpoint | The current flowing through a low impedance ammeter connected between one isolated supply conductor and earth is noted
label | 8871c008-fc67-52c7-85d6-b102c7cde2c6 |  | note | The test is repeated for the other isolated supply conductor. The larger of the noted values is the prospective hazard current. It shall be less than 2mA
checkpoint-status |  |  | checkpoint | The prospective hazard current of the supply is recorded in the commissioning checklist
checkpoint-group |  |  | section | 8.2.5: Overload Monitors
checkpoint-status |  |  | checkpoint | Confirm that a load of 110-120% of transformer rated current causes the alarm to activate in 3-5 Seconds
checkpoint-group |  |  | section | 8.2.6: Uninterruptible Power Supplies (UPS)
checkpoint-status |  |  | checkpoint | Confirm that UPS status indicator performance is routinely verified
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Checks completed to specification/drawings - Area left clean & tidy
label | e990acc9-b480-5714-adf5-f6574d4c015b |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | d6ecf87e-301a-5010-ab8e-1ea7bc75356a |  | note | Any Corrective Actions to be Photographed & Commented below
select | dadaa7bf-82e6-5ee5-9bcb-5877507aab9d |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 54d5e05b-a537-5b40-9fa1-a255f0d2bfef |  | textbox | Other (Specify here)
label | 7ceea444-3405-509d-ae63-bf3232395160 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-005 - Construction Wiring 6-Monthly Re-Test Results (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-005 - Construction Wiring 6-Monthly Re-Test Results (Rev 0 +Names) | 1817d858-c1a9-4fb3-b2ac-f95517ede3da
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 0f2f3916-3a7f-59be-987f-2aba5a845d55 |  | textbox | Level
text | 10e90a8f-f5e6-5522-9cf0-09c3f4f6097c |  | textbox | DB No.
text | 841ea121-f62e-52bb-aa5f-8fa366a51a07 |  | textbox | Drawing # & Revision (Or photograph below)
select | d903ccd4-7bf9-561d-93d0-8903390ccbec |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c90cf289-aff5-5537-8a7d-18fa1c3509e6 |  | textbox | Other (Specify here)
boolean | 5b95f9c9-d3bb-5465-8775-6726a8daaa5a |  | tickbox | Signature added below
label | 3765d9ae-bcb2-5f0f-9c45-ceafc6383e5c |  | note | .. ..
label | 16b0306a-cc86-58d8-97d2-b57033ddb8e9 |  | note | Test Equipment
text | d5a53244-e79f-51eb-b1cb-8fb943200adc |  | textbox | Tester Type
text | da53fccf-9289-52dd-bc1d-079901b73826 |  | textbox | Serial No.
text | 0e4e3330-e0aa-5d20-b83f-a4e648cb5161 |  | textbox | Calibration Certification Date
checkpoint-group |  |  | section | Test No.1
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | 41dee3f8-f0ca-5795-bfd5-8fe7535bcc32 |  | textbox | Sub Main cable No.
text | d729f8a9-5613-5c17-90e3-7cdd72b851a7 |  | textbox | Cable Size
text | eaf94b47-b334-53ee-a53e-35c749ac39c1 |  | textbox | Phase Qty
text | e17fc4dc-85fc-52e6-ae18-e41464981ee5 |  | textbox | Insulation Resistance - A+N/E
button | 1ba4677c-f4e0-5367-a079-c73dead0ad1c |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | 0f3f5b2a-f462-520c-9500-5c4dd62db176 |  | note | .. ..
text | 2f94caef-6028-5ef9-aab0-ddbd3d72b99d |  | textbox | Earth Continuity
button | f905ad8d-60dc-52bc-b77d-bb84b938554e |  | button | Result | Pass, Fail
label | d6393f0e-6751-57d9-a11a-02ffd47db5a4 |  | note | .. ..
text | 02cf5979-e84e-5eaf-8c2b-7dc8ffbac126 |  | textbox | Earth Loop Impedance (to furthest point) Result
button | c3ee6081-a346-5d73-9eca-516b4df0b9ce |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.2
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | 84c9459f-988e-5548-adb7-458d472e4c59 |  | textbox | Sub Main cable No.
text | 4a9d7fcf-84a2-5efc-9fb5-5a526f550678 |  | textbox | Cable Size
text | 5042e502-3517-52f1-b750-70f0903d7c66 |  | textbox | Phase Qty
text | c0eee362-b6cc-58ad-a74b-4c847c5b1a26 |  | textbox | Insulation Resistance - A+N/E
button | cc3c6451-5be9-58a6-ab08-058aa22c1c7e |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | e69ec222-75ed-5f9f-be9e-ae8041cd1870 |  | note | .. ..
text | a97b0beb-ce0a-5923-8889-84d21c0ae01c |  | textbox | Earth Continuity
button | a1238a40-65a5-5b8e-bd87-9253fa8ea017 |  | button | Result | Pass, Fail
label | 3c52c833-03cb-5cfa-a02c-14563bc57837 |  | note | .. ..
text | c1fe7f1b-9a7b-5338-92fc-9fc634fc586f |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 3f68566f-7a43-5d43-a365-91bbc711d40c |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.3
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | 0186cb43-b7cc-5697-9557-269506cdc0f9 |  | textbox | Sub Main cable No.
text | b73aba62-e43c-5f38-86a3-c94a9367690e |  | textbox | Cable Size
text | 09af6282-c178-5e6a-8850-754543a4f5f3 |  | textbox | Phase Qty
text | 5c748e55-d48e-52fb-961e-0c00598ef9f2 |  | textbox | Insulation Resistance - A+N/E
button | 35d18033-5c39-5938-a690-f2e1cbb04205 |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | b1ee6f20-0b1a-5d4a-bebc-f9d8d63d0383 |  | note | .. ..
text | 1af13cee-4f12-5634-bd01-98e3e1bd47ee |  | textbox | Earth Continuity
button | dafef8d0-0573-5228-96fd-588817f63552 |  | button | Result | Pass, Fail
label | f4c397fb-eded-5f3c-966e-720dee555bb0 |  | note | .. ..
text | 679d55c2-ba23-51eb-aa22-b1e341a26d13 |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 33de2d35-06b6-55ac-a8fb-f3f86ca6d9ca |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.4
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | d22e746a-6a1a-56e1-8254-02d5f172f3a3 |  | textbox | Sub Main cable No.
text | ee70b2be-dfff-54a6-9842-fec9c5ff6e80 |  | textbox | Cable Size
text | 0e0c5dc0-cb7f-53b1-bc71-59120093373d |  | textbox | Phase Qty
text | 00d77938-81dd-561b-95f7-8dffc4c19903 |  | textbox | Insulation Resistance - A+N/E
button | da36ec74-cb87-51fd-98f1-25286cb060ec |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | f14e7ef3-88b0-5fd9-83d3-109640598939 |  | note | .. ..
text | 49a19be8-73a0-530f-93f1-d63d42a53a40 |  | textbox | Earth Continuity
button | 7b735cfa-c757-5a85-8116-884ab833806f |  | button | Result | Pass, Fail
label | 202d1233-c780-58f5-9163-32eb3d516a74 |  | note | .. ..
text | b4ecf8d7-df3e-583a-b726-21aca032b078 |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 807aff14-00d5-5201-9d47-f30f4981be43 |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.5
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | e39cdab6-4e50-5e5e-8fbb-9a2b8e6d4491 |  | textbox | Sub Main cable No.
text | c5af398a-2b12-5391-9065-a3c6e31fe30b |  | textbox | Cable Size
text | 2e6edfe3-2965-5848-a925-55fa36065077 |  | textbox | Phase Qty
text | 9b3f679b-72fe-5900-ba34-e4a25af26d0e |  | textbox | Insulation Resistance - A+N/E
button | 6aa96cb6-3380-5a91-9fd8-c82443e324c6 |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | 848cd6d3-5006-5611-bf13-3c9dc1ce2414 |  | note | .. ..
text | 294b27e9-6942-52b0-85a9-adad9de1af01 |  | textbox | Earth Continuity
button | da05cb30-ff36-53fb-9aeb-e0411b755ac2 |  | button | Result | Pass, Fail
label | 09d4ef82-419a-5958-af29-161a1f33ea88 |  | note | .. ..
text | aa057062-dc6d-5748-b345-75f8b52d5ec6 |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 063905fe-8803-5da9-8126-85721fafb6eb |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.6
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | c88e1360-d327-5f62-81d0-e1182114eb0b |  | textbox | Sub Main cable No.
text | ea0e842b-9f69-534d-a7c4-e12cea3a1b1e |  | textbox | Cable Size
text | 70d0423c-dddc-52c6-9a35-391afa4821bc |  | textbox | Phase Qty
text | 5c1286b6-b4ea-5ea3-b3e0-ea36b613194f |  | textbox | Insulation Resistance - A+N/E
button | afce8197-db28-5b6e-b03e-c353712ac55c |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | 80a00373-add8-5397-8c42-e03c56b6e4b9 |  | note | .. ..
text | a630a775-b61c-5ba3-9632-b7a1b89ccf09 |  | textbox | Earth Continuity
button | a95b374c-7399-53c5-935f-4b907f554272 |  | button | Result | Pass, Fail
label | eab35b8c-7c23-55a4-bdca-89eaa1b821fa |  | note | .. ..
text | c6aaa820-500a-5a6f-aa08-feeae952cde0 |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 44bbb946-4fc6-5402-8d65-e0dc9321be88 |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.7
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | 5839cce3-b497-5c48-baca-0f63c5ca83f6 |  | textbox | Sub Main cable No.
text | 2fd99212-7cd6-5cb5-89ba-55465c197682 |  | textbox | Cable Size
text | d4675019-330c-50e7-b5b1-ec7bebe1a821 |  | textbox | Phase Qty
text | e3beb3a3-0737-5d34-8b1c-7974dac73382 |  | textbox | Insulation Resistance - A+N/E
button | 5bffb0f6-0708-52f8-9e6d-5a1453de7c5e |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | e73c2a7a-c55b-5e9d-b0b8-8a4bc29b2a20 |  | note | .. ..
text | 0c8962e3-0c8a-5c78-b3a4-c21b5c900790 |  | textbox | Earth Continuity
button | b255b99b-32cb-553d-8504-0a2639ca440a |  | button | Result | Pass, Fail
label | c52b9fca-f7df-5556-ade4-63852b89d459 |  | note | .. ..
text | 8879e71c-ddc0-59b9-aa9a-e3fa645e114f |  | textbox | Earth Loop Impedance (to furthest point) Result
button | ccb79dba-42ad-585a-be23-8fdac68c0a11 |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.8
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | 458f3c9b-3cc9-5156-b7b2-d6399bb4419b |  | textbox | Sub Main cable No.
text | cb9fb7d8-be23-59f0-b103-209721d67018 |  | textbox | Cable Size
text | 2eab06ed-f8bf-5f17-92c3-ca3f1945cbde |  | textbox | Phase Qty
text | b7de978a-a4de-540c-873c-3186b4d80582 |  | textbox | Insulation Resistance - A+N/E
button | d3710b95-b4c1-5adb-a423-7bfe37e61a05 |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | dbefb1d0-61fd-5345-82b5-8f75e06dbb6c |  | note | .. ..
text | 7deb53ac-efaa-5f6b-8d4d-1ba2ce464a8f |  | textbox | Earth Continuity
button | 52d2331f-11ea-5405-9c08-abc778594fd9 |  | button | Result | Pass, Fail
label | 73746f5a-1574-52e9-b7b6-8a95e733aeec |  | note | .. ..
text | 4e23c1d5-af59-5a35-974b-51237840a6be |  | textbox | Earth Loop Impedance (to furthest point) Result
button | e77fa924-812f-5837-864a-f410584b288d |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.9
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | f0afc80f-7462-55e6-8b5c-7ed1613ece37 |  | textbox | Sub Main cable No.
text | dbd1d3ce-7988-51e4-b51d-776da5d6ec0c |  | textbox | Cable Size
text | 17b98d55-7609-5d9b-bc84-391aa1331ac0 |  | textbox | Phase Qty
text | 43bc72d9-f5f3-5c48-af19-28e6508c9e2d |  | textbox | Insulation Resistance - A+N/E
button | c0850298-cb76-51a7-a623-2d7c58e994f7 |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | 92aae526-5dbc-549b-b6f4-ebaebe8d5eee |  | note | .. ..
text | dab87d5b-6895-5cdc-b91b-914ff475ca9f |  | textbox | Earth Continuity
button | 09c85c6d-0267-5405-a259-21dc125b57e3 |  | button | Result | Pass, Fail
label | 0983db09-0c04-5857-9950-a9a2c6305804 |  | note | .. ..
text | 65b7a265-e41a-5661-99d0-5bf81dd1475f |  | textbox | Earth Loop Impedance (to furthest point) Result
button | 2e670b5d-b41b-50f6-8786-6a7ed8ff03d1 |  | button | Result | Pass, Fail
checkpoint-group |  |  | section | Test No.10
checkpoint-status |  |  | checkpoint | Test Details - Pass once entered
text | ef567f91-fad4-5adf-ab3e-06702dc4718e |  | textbox | Sub Main cable No.
text | a42e6628-875a-5b6d-adee-04d24a2fed5e |  | textbox | Cable Size
text | ed7eab5d-008e-5deb-870c-1be4c0cd1108 |  | textbox | Phase Qty
text | 76971444-0540-5399-9795-c093414b17d0 |  | textbox | Insulation Resistance - A+N/E
button | 90ac1fbd-4a5e-51c9-a594-cb0fb0baa454 |  | button | Pass/Fail (>1MOhm) | Pass, Fail
label | 5271a559-ec59-5c9b-9ace-e5e6fc7e02af |  | note | .. ..
text | 7ac9c941-c947-5da2-9d6d-7bcf62fad8bd |  | textbox | Earth Continuity
button | 27410ce4-31d6-5fee-a7fe-b64c38e0103e |  | button | Result | Pass, Fail
label | f15a4d45-68f3-5e5f-b2f0-f8951baaf80d |  | note | .. ..
text | 8e9de8bf-7c18-5deb-a71c-03204fef037e |  | textbox | Earth Loop Impedance (to furthest point) Result
button | e1fb1f12-069e-5498-ae4e-242ff59d9c85 |  | button | Result | Pass, Fail
checklist-flat |  |  | checklist | AE-ITCX-035 - Lead In Fit Off |  |  |  | 0 | Yes | AE-ITCX-035 - Lead In Fit Off | 1b8130ab-b7fa-4638-8fa6-74d3d3d24dc1
checkpoint-status |  |  | checkpoint | Fit off Leadin cables
button | b36bf914-d3af-5d62-9d00-e7bc35043263 |  | button | Submain cables is terminated at field/Distribution Board End? | Yes,No
button | 41983556-6d99-5f85-97f2-4d35c756494d |  | button | Apartment Db is fit off, backing plate installed (where applicable) and fire sealed? | Yes,No
label | 43a99265-6d97-586d-aa91-aea0d6e50b0f |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
button | 4daefafa-106e-51e7-b9b0-88d8419c2178 |  | button | CAt6/Cat6A Outlets are all fit off (this may include House CCTV/WAP or Intercom!) | Yes,No
label | b4f74336-e71b-52ef-844c-f3b50f0adb78 |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
button | b0c2f5b3-798e-574b-b5ea-02225d5fdbe9 |  | button | NBN conduit and string labelled and accessible at correct location within enclosure or cupboard? | Yes,No
label | f62c469a-f319-557c-9460-32a5059a070d |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
checkpoint-status |  |  | checkpoint | Lead In Fit Off completed to specification/drawings - Area left clean & tidy
label | 557324d8-4bea-5fe8-a667-0f5a3c52464e |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 57b29611-7c63-5e6c-9715-b56fa979f375 |  | note | Any Corrective Actions to be Photographed & Commented below
select | bec9acdb-0b84-5ee3-a91c-6cfe7cbc6d59 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | b3f01ae2-f5ce-5284-9bec-75a81cf4a98d |  | textbox | Other (Specify here)
label | 97576f19-962c-5070-b8c7-74f5a6d37e77 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) |  |  |  | 28 | Yes | AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | 22c679fc-3b1f-4e16-a9bb-e51d45f013eb
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 592324b0-3a5c-5ba2-99d2-bf8139ce4421 |  | textbox | Meter Panel Info
text | e577b9cd-d448-5586-908d-b8c31db179da |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Wiring Neatly Loomed
checkpoint-status |  |  | checkpoint | All connection points tight Inc. fuses and panel isolators
checkpoint-status |  |  | checkpoint | All factory fitted connections tight
checkpoint-status |  |  | checkpoint | Panel, cover plate, door, lock and pole filters
checkpoint-status |  |  | checkpoint | Supplier Check List (e.g. Aline) Completed and Attached
checkpoint-status |  |  | checkpoint | Meter panel installed as per Appselec shop drawing
checkpoint-status |  |  | checkpoint | Meter panel and cupboard cleaned
checkpoint-status |  |  | checkpoint | Apartment sub-main relabelled at entry point.
checkpoint-status |  |  | checkpoint | Meter panel face wiped and cleaned
checkpoint-status |  |  | checkpoint | Glands tight
checkpoint-status |  |  | checkpoint | Cables fire sealed where required
checkpoint-status |  |  | checkpoint | Wago Plugs installed, labelling is correct & polarity is correct
checkpoint-status |  |  | checkpoint | Meter Panel Visual inspection completed to specification/drawings - Area left clean & tidy
label | 206faa30-1439-5f6e-b1b0-9d6fb40baa52 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 703f98df-4bfa-5ad6-aedd-25bbd2e81b1f |  | note | Any Corrective Actions to be Photographed & Commented below
select | 7427522d-251c-5d4e-899c-15fa83a445c2 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c2904fb7-85da-54b8-8235-51e05f9356d3 |  | textbox | Other (Specify here)
select | ddcb1f53-430e-54fa-b601-a4fc7e34cd8d |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 92049511-1fed-5d48-b421-8226ef6fc6d6 |  | textbox | Other (Specify here)
label | 7d34dcec-c0d5-5f37-9f87-f9b1134cf17d |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-017 - RCD Test Sheet (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-017 - RCD Test Sheet (Rev 0 +Names) | 268ceb72-0a93-4c2f-a000-49a9f43dac4b
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | fc227e33-7cf8-5709-8fab-fb13b31d0fdf |  | textbox | Test Date
text | 6ea8892c-efc1-5ef0-ae4d-aaf967bf79b2 |  | textbox | Switchboard No.
select | 98826e45-fb4a-5bd9-921c-4c4757297688 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 78b34d34-033b-5fe1-80d3-26b25bb62b7f |  | textbox | Other (Specify here)
boolean | 8f324eb8-1d45-52f1-8aa9-0eaa3e1c9fbe |  | tickbox | Signature added below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed3743bc-8f36-5dbc-a507-05ebd3ecef35 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | cfe8fa4c-eec2-5c3e-babd-5a16406f8381 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | c9fdd562-4a8b-5930-ab5b-093c4eb10c76 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | 36f483cf-8b57-5cff-b24c-a7f13003bd29 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | a5719bd9-d6e1-5e84-b122-281c0d13c831 |  | textbox | 0.Deg
text | f11a0fea-7e33-57d0-b28d-bf8dd0c181cf |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | bfca89b7-0b2f-53e4-816b-76a5c12fb4a5 |  | textbox | 0.Deg
text | e20883f2-8061-5cc1-bad6-709235b35d9a |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | e6daf82f-9254-5531-aeeb-039378e6d977 |  | textbox | 0.Deg
text | 680d44c5-ab49-5e65-99f5-7e8e9dcba5d4 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b9b0478b-81c4-56ab-b4b3-58d36d9337c6 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 388e19fd-72e0-5205-a78b-ebffa27c65f7 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | a4751b74-5736-5d09-82c3-4d7dc3f97d17 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 096bc401-87b9-5175-ad9c-5dc397212ecf |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | 898a73da-0de5-5871-82ee-da933f7c1e3f |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 1b3c761f-73e7-50ad-829d-6c14fdb8ef81 |  | textbox | 0.Deg
text | a4a6d20b-bbee-5ff4-9bdc-603f424aeed3 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | cf137e9a-6f77-53af-a047-9b36d8436ef0 |  | textbox | 0.Deg
text | 463a9c3c-36f2-53a9-bed6-e4e637cd47e4 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 1a07a8ff-4ac7-5882-9ca9-97390f70518b |  | textbox | 0.Deg
text | b53458dc-7379-5287-a227-6cee3f0d226c |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 9f749d6b-c446-5b16-ae83-fe715d467832 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | d57b9920-c1c3-5d27-8c31-f54bc3629659 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c44ce5d2-8dc9-5f31-b9f3-6dd4b4fb2bae |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 7fae7777-007e-50f6-82db-cb809a1fcf19 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | e716d3b9-403a-5ae1-9311-c6dc7c40456e |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 83128dc2-fff1-53ca-9f15-f827e27cd85d |  | textbox | 0.Deg
text | 47dda1ca-33ec-5758-80ca-5fbf50655b0e |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 6361b79b-40ff-539a-b551-3ef811c4241e |  | textbox | 0.Deg
text | eee965cc-f444-57d9-9401-6d8e063691e9 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 74aff6b9-0308-5823-a436-9a66ad85fa10 |  | textbox | 0.Deg
text | 85c7b690-40dc-592a-9f98-ff92e1b25d19 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 4a96f2e0-e2c1-5bb4-bb77-6252d4f598bb |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0b33df76-9630-5d86-852d-91a0ac3929fb |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | cbcbc4d5-b874-5a5e-a3a3-1705a0712476 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 2b372804-0d2b-5120-9251-783b165f2b8e |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | ea8dc9d8-ebd0-52ae-b98a-319c540b15e6 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 9ab99233-127d-5441-a48d-5412e76a473b |  | textbox | 0.Deg
text | 236e1b2b-b25d-5f97-8217-0c853ada0926 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 73bb2b49-087f-58c3-84fb-d0e419d77853 |  | textbox | 0.Deg
text | 0036794e-13af-5886-be7e-f4ec083682e9 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f29ea53f-3a56-51ba-9f0e-a369508ae449 |  | textbox | 0.Deg
text | 3e283d3a-a74c-5d7b-924d-032923bee767 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | ebb02e54-8b6e-51b1-8d31-d1630e2a9329 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 9cd0a48c-43b7-5b41-b248-c8ab356c1838 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 42c3a57a-d95a-5e24-ae06-4221330294e1 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 1f55a53e-ade8-553d-8a61-42269af98476 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | 9baf630f-e8ba-5e6e-af4a-4c3937b9b35b |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 7fe1f4aa-6d89-5556-9695-d4e9122164fb |  | textbox | 0.Deg
text | 6f34bd91-1840-5639-981f-66d0212cd8fc |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | f6917455-e96f-50e8-8437-dbc0e533775e |  | textbox | 0.Deg
text | 5df7f2d6-ce81-5abf-b498-e1049574a6f8 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 02409086-f4ad-5f33-8f15-755308a9e649 |  | textbox | 0.Deg
text | 0943b95a-6ef5-5987-9775-873513a1e883 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 9dd4130f-bb02-5381-9eab-79c911f137b7 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | f4688ea6-e4f4-5044-a327-7dd660181dda |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 055c4933-76e9-5b6f-a135-f0449ec5ae5d |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 8a3f8c0b-efaa-5183-8b6e-09ae6e9d0af1 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | 5fa94e35-da1a-52f5-badb-5d0699d0dca1 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 39f57ba9-3fee-5751-975d-e7f8ebcc0a38 |  | textbox | 0.Deg
text | d4c80de4-5d4d-5b92-8c4c-bf597ab826fa |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | abb55ce5-b7fc-5fab-b60a-7aef28f36337 |  | textbox | 0.Deg
text | c531ca3f-a3aa-5418-8bc4-4634bf031563 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 0ea10e2b-0f13-5f9d-9ed9-9b3e5c6578ef |  | textbox | 0.Deg
text | 04a490d2-ef33-5875-83f1-4002854c48c3 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 53bce831-d56f-50c6-9a70-a54e1327a8f3 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 3cb9e8e8-62b7-5bf7-a9ce-87c4d8b9ed21 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 0a5077b5-f4f2-583e-a379-a476d3beb091 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 8e9f67cb-8b49-5b5b-b650-6a2be7869e7d |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | ee8c24dc-e063-5036-9034-8cbd4325d25f |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 812f445e-a0c0-55e1-8095-a1b3be824638 |  | textbox | 0.Deg
text | 14337029-5e7a-5dff-a3c3-845cae8b1c88 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | bf8b0aa0-50d8-5344-9a9d-d450bbb8a06c |  | textbox | 0.Deg
text | e997dc04-915c-599c-8168-3dce65ffb93e |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 4e9db3b4-028f-53ef-8e12-f92c92688304 |  | textbox | 0.Deg
text | 9bebbfcc-0106-519f-b9e9-3dd179bacf4e |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b760a4e9-c9ff-5a48-92f9-c0df1f281e6d |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 670b5a12-a249-5fbc-85cd-95c1ce245e5f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 865e4361-17a2-56c4-ac39-2d2794276729 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | eaef3688-227a-5ed8-baeb-5ae7925ebe58 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | f743d5c9-be55-5210-bd09-df43a9939dcb |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 8c539d0b-bdb2-5bfa-be78-91eb22460ed2 |  | textbox | 0.Deg
text | 7b17fb3a-181d-561c-a0b0-419e23113c9c |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | ab88764f-354c-5c1f-8981-9c14086a55c1 |  | textbox | 0.Deg
text | 9de9402a-872b-5373-ae5b-d83161686db7 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 9794aa87-a3e2-56d5-8e83-9cf4ad06332b |  | textbox | 0.Deg
text | 749c3ccb-5247-54e7-b753-0b26b84df2f4 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f7276447-0a68-5356-9bca-f6f58d2f8935 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 9
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 2ee21601-7f35-5645-9b82-103744fd01aa |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 09873548-ba39-5c66-87ed-fc863f1d514b |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 44ef1a2a-0d2b-5ced-b5f5-bc90fc187fb0 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | c9cd6d58-7761-5175-b8e3-7145584880a3 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 50b9ef45-a578-5681-b20c-5edce9632426 |  | textbox | 0.Deg
text | c8db7b63-6e51-5bfe-8be2-25b03f4108fb |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | e01f5001-f58d-5e71-a743-c21572fc1751 |  | textbox | 0.Deg
text | 961bae5f-73cf-570f-93a6-ba613397ea5d |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | c7ed54b1-a9dd-51e8-96a9-67f232f6b586 |  | textbox | 0.Deg
text | 6266c114-ca3e-55a3-be95-45c23aaabb48 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 166fb961-01d9-5925-bff0-097bf70d4e65 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 10
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 12fa21fc-e6f5-5bf3-bf9c-5e655426e5fa |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | eee7ede4-3076-5a04-bb99-670f35e1325a |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 5d7d963d-1865-5a09-ab51-e43940347946 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
text | 27cdd486-d6e5-5bc4-84be-c9ab7bd2afe4 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 4a60201d-c1ba-515b-b119-f82de0c50251 |  | textbox | 0.Deg
text | 497bbd16-a7ab-56d1-b39f-f5f11f55adcc |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 58f86e64-bfc2-5c34-85e5-6d3a7794b990 |  | textbox | 0.Deg
text | 407b7147-86d4-5cde-8a4f-175042acb6e0 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | eed19252-7aa1-5e9b-b878-1d01e5f8b5f5 |  | textbox | 0.Deg
text | 493ce70f-aad1-5607-bd36-e97e643aecbd |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f6da65c4-cf81-5001-a893-fce1fc551b80 |  | textbox | Action taken
checklist-sectioned |  |  | checklist | AE-ITCX-022 - Emergency & Exit Lighting to AS 2293 Logbook (Rev 0) - TBC W/CONQA |  |  |  | 0 | Yes | AE-ITCX-022 - Emergency & Exit Lighting to AS 2293 Logbook (Rev 0) - TBC W/CONQA | 2aed7b97-8771-4b40-8a3a-d14c381b20da
checkpoint-group |  |  | section | Preface
checkpoint-status |  |  | checkpoint | Summary of Information - Pass once confirmed
label | 058d9dc7-0944-5ecf-b229-ae390e76bd73 |  | note | This logbook has been compiled in accordance with the requirements of Australian Standard AS 2293. Persons using/completing this logbook should be familiar with all parts of AS 2293
label | 2ccd5866-5592-5e86-b021-9d0ac212d970 |  | note | .. ..
label | d4395522-88b6-558b-949e-0ba94d3bc38e |  | note | Summary of Test Procedures as required under AS 2293 Part 2 Section 3. Six (6) monthly inspection and test procedures for Single Point Systems
label | 8a407992-b78f-5377-ab63-ed8de693e2f1 |  | note | 1. Test procedures should be carried out at intervals not less than 6 months
label | a307afda-212b-5b46-9b55-811e9d875d9a |  | note | 2. Check to ensure that no interruption has taken place to the power supply of fittings to be tested for at least 16 hours prior to carrying out testing
label | 45465c5c-a4fe-5fbc-9d62-7cfe1e9d477f |  | note | 3. Carry out visual inspection of all fittings prior to conducting testing to ensure that power is connected, tubes are functioning correctly and fittings are free of damage that may otherwise affect the test results
label | 455472b5-733c-5682-9a7d-c78ecd6e03ca |  | note | 4. Operate the emergency and exit luminaires from their battery supply by simulating failure of the monitored supply. All emergency and exit luminaires shall remain illuminated for a period of not less than 90 minutes or 2 hours for initial test of new fittings
label | 2cec0c77-995d-5954-ab2c-49a21903164a |  | note | 5. Restore all emergency and exit luminaires to normal monitored supply and check battery charge operation is functioning
label | 087cee3a-24c3-5fe0-9eb2-d727f9d2aec8 |  | note | 6. Enter test results into logbook
label | b011223e-53f3-513b-a280-4c001c5b4a09 |  | note | .. ..
label | d4b76d54-d5c5-5cd0-9f0b-cb8679ec1eb4 |  | note | Summary of Test Procedures as required under AS 2293 Part 2 Section 3. Annual inspection and maintenance procedures for Single Point Systems
label | 21f986fc-8414-5397-9e33-93fedad0325e |  | note | 1. Carry out all functions listed above as per six (6) monthly
label | 73960e77-6cfc-59b0-ae1b-6fd5079ba63a |  | note | 2. Clean all light emitting and reflective surfaces of emergency and exit luminaires as required
label | 98501bcd-7201-5e27-a043-815e2a3fe17a |  | note | For further information regarding the testing of emergency and exit lighting, please refer to AS 2293-2
checkpoint-group |  |  | section | Emergency Light Fitting Legend
checkpoint-status |  |  | checkpoint | No.1 - Details Completed and Entered below
text | bbd31e44-4206-55a2-bc71-9c2d94a5c3d0 |  | textbox | Legend
text | 0a026475-4554-5906-a874-ab87e6c1b00c |  | textbox | Manufacturer
text | b21f4898-d90e-5033-902e-fe91f6216187 |  | textbox | Cat Number
text | f1727df2-fe8a-5a4a-8b0e-2416ed662692 |  | textbox | Description
text | ab93a5e5-7170-51c6-993d-2a36bfd7785a |  | textbox | Lamp
text | 63a2a7b8-d456-5621-8b43-1e3e19abe22e |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.2 - Details Completed and Entered below
text | 56bde358-15a5-5619-bc72-091dc63cb51a |  | textbox | Legend
text | 13ff404c-f359-5a89-bcdc-6e8a81fd70b6 |  | textbox | Manufacturer
text | 2f78be48-ac97-5de7-b415-e876023f4e5e |  | textbox | Cat Number
text | 79ba05cf-fbe6-5cb0-ba1f-81b6aa5d431b |  | textbox | Description
text | 3aae093e-a9cc-5dc2-9d4b-4a20267836d4 |  | textbox | Lamp
text | 3c798731-c1fa-5de8-8fc4-11704b24393e |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.3 - Details Completed and Entered below
text | 46ccc75b-f268-547d-b209-41270d218e02 |  | textbox | Legend
text | 0254d4d4-6647-5b06-a70b-99578480e59d |  | textbox | Manufacturer
text | b8fd5967-24c3-5ae8-bc32-33e74ae8370e |  | textbox | Cat Number
text | 01fa8e17-04dc-5044-9ad6-6423fa43c824 |  | textbox | Description
text | fb9d3055-13f1-582c-8550-efb3a00848d4 |  | textbox | Lamp
text | 7067eca3-1bb5-5096-ad5a-25c972f8c81a |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.4 - Details Completed and Entered below
text | 14b9d3f8-012b-5336-8d1c-bf0a453e55d7 |  | textbox | Legend
text | 2590731d-99bb-5a86-a2d1-bd686017536a |  | textbox | Manufacturer
text | 6b474fa4-d87b-5ace-8d52-a9999020bff7 |  | textbox | Cat Number
text | 42eb9878-0af3-5648-abd4-55e3e18bcd83 |  | textbox | Description
text | 274584ba-4589-56a3-a1b0-0c7da09b6b73 |  | textbox | Lamp
text | 4ca62fce-95c6-5dfa-ab40-7bd07c9fef76 |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.5 - Details Completed and Entered below
text | 953baa5d-e2ad-5817-8587-4e7c67d6c2bd |  | textbox | Legend
text | 50729618-7a1c-51cb-978d-9f02279e7420 |  | textbox | Manufacturer
text | 4179c0fb-ab2c-57fc-9aa9-af4710de7c6a |  | textbox | Cat Number
text | 13457744-8874-5fe5-b3d5-7f31bef4d05a |  | textbox | Description
text | 836388d7-3e5d-598b-8bb0-498effd7a2b7 |  | textbox | Lamp
text | f8dfc09b-832a-5dac-bb01-263e83fe9085 |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.6 - Details Completed and Entered below
text | 06dd06c9-66e1-574d-8779-3da9e9c44690 |  | textbox | Legend
text | 7b4ca45d-37c2-528c-8d5e-fa90d11a296d |  | textbox | Manufacturer
text | 24bfa1c0-98ce-51c5-99e8-61b3661665f4 |  | textbox | Cat Number
text | 9d6470b0-dd85-5c60-b6f8-cdfc9ffcdcba |  | textbox | Description
text | 442c2247-b825-5155-b491-73c15043b068 |  | textbox | Lamp
text | 3cc60cb5-c158-5861-bd5b-0ec99320da8b |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.7 - Details Completed and Entered below
text | ad621550-bd19-5091-a2aa-e0bc51b44380 |  | textbox | Legend
text | 3317808f-f4ba-5df3-be1a-ade0c8a2f847 |  | textbox | Manufacturer
text | 7f029c48-59ff-59ab-9552-1d0ad64b3a3d |  | textbox | Cat Number
text | 5dfdc557-ec5d-5c92-a4f9-b92d20c8f4ad |  | textbox | Description
text | 940cbceb-539c-525f-a059-b81b6af743ff |  | textbox | Lamp
text | e7f2fb9c-ff61-5deb-a5c7-3a19dfc7666b |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.8 - Details Completed and Entered below
text | b9b59cca-0a49-5af3-8989-11fbf86aacad |  | textbox | Legend
text | 1db8248d-de05-5c06-8bee-fa84570bddb8 |  | textbox | Manufacturer
text | 488b79b7-d73c-51be-b1f4-25a99773a08f |  | textbox | Cat Number
text | 20984b74-e492-597c-91c0-a86ab416d33a |  | textbox | Description
text | 9868e56e-50aa-5277-b3f5-a0ad26f3e145 |  | textbox | Lamp
text | 2f854ce2-0a6c-55a0-a88c-bd0bd03b7d37 |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.9 - Details Completed and Entered below
text | 0ac1f597-8d25-5205-88d6-110695493748 |  | textbox | Legend
text | 7d376454-50d1-5d00-9f7c-dc66e2f69b25 |  | textbox | Manufacturer
text | 7495c4ac-9131-5025-a4a9-010e7fe326b5 |  | textbox | Cat Number
text | c4c172f3-101b-56e4-9e5c-b85d981c371d |  | textbox | Description
text | 60c16962-6b10-58ce-b262-ce83d3d561bf |  | textbox | Lamp
text | 59610376-f21d-5be3-ac07-7363d64749db |  | textbox | Battery
checkpoint-status |  |  | checkpoint | No.10 - Details Completed and Entered below
text | 3eaf999d-0f30-546f-8911-4a31560aaf00 |  | textbox | Legend
text | 79a77798-65ec-560f-bff3-8a7e55b60f7c |  | textbox | Manufacturer
text | 8966676f-b37e-5848-b7c8-a021e6e9162d |  | textbox | Cat Number
text | b65c0b48-afa6-5e4c-8fa9-06fe42874609 |  | textbox | Description
text | 69cdedc4-f297-5860-ba55-8c9a8bd36ffb |  | textbox | Lamp
text | 14cc4c5b-f5fd-5af5-a83f-2c0ef6acee8f |  | textbox | Battery
checkpoint-group |  |  | section | Fittings
checkpoint-status |  |  | checkpoint | Fittings Details - Pass once entered
text | 4dc1a616-f312-54e7-ba74-50f760b44e31 |  | textbox | Fitting Number
text | 49beb1a8-3594-5b6c-b9e3-3244798a2d94 |  | textbox | Fitting Type
text | ba4a6e2c-bfc2-5123-824f-d624a39254da |  | textbox | Controlled from Switchboard
text | e9410a09-5ee0-5331-9195-a049d36bed75 |  | textbox | C/B Number
checkpoint-status |  |  | checkpoint | Fitting No.1 - Pass once completed
button | 00976536-02a7-57fc-aa0d-964cf5914564 |  | button | Fitting Condition | Pass, Fail
button | 8ca6fbd5-cc50-50ae-b876-f92bf9908004 |  | button | Lamp Operation | Pass, Fail
boolean | 65de7bdc-6be8-52a5-9eb5-06663770e509 |  | tickbox | Clean Fitting
label | a8a33c39-3072-5227-8fd0-eb0841c06991 |  | note | .. ..
label | 25883687-858b-57fe-9587-626bf2104c91 |  | note | Operating Time
text | 38b7010a-7a79-5a15-a7fc-e51331b69a31 |  | textbox | Time
text | 5112df6f-3e98-50de-9a3d-dcc3b73b873b |  | textbox | P/F
label | 747632a2-0f43-51a3-94d9-b4d2e457c209 |  | note | Any repairs photographed/commented on below
label | 8143fdc7-2535-50dc-8ef7-b6b2630cc138 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.2 - Pass once completed
button | 2644d296-14d5-56f1-9786-76c908ed80e9 |  | button | Fitting Condition | Pass, Fail
button | a8074948-3c63-5089-9238-eb6a76555101 |  | button | Lamp Operation | Pass, Fail
boolean | 2cb58f32-1108-5026-a402-2b7781e28647 |  | tickbox | Clean Fitting
label | 09d46492-16e7-538a-b860-e2037e0c87f5 |  | note | .. ..
label | 2d180a41-59d8-5a6b-aa7b-c857fc261e1f |  | note | Operating Time
text | 4c457b2d-143e-555a-870a-b02d65897c4e |  | textbox | Time
text | 40576dc4-9619-5608-8a80-f58103ff6406 |  | textbox | P/F
label | a5b84cb5-eb99-5fb3-a7dd-eb744c1b6225 |  | note | Any repairs photographed/commented on below
label | 4289941c-9faa-5591-94c6-a33552d858da |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.3 - Pass once completed
button | 18cde5c4-29c5-5803-a3eb-1e61e7f9b776 |  | button | Fitting Condition | Pass, Fail
button | 40295e97-3184-5fec-acd5-a543ff1bf65b |  | button | Lamp Operation | Pass, Fail
boolean | ed592cd3-d2e8-5b70-9cbf-a97611bd6f2f |  | tickbox | Clean Fitting
label | d4d255c4-5101-541a-b760-74199d7adcf8 |  | note | .. ..
label | d821639b-cf28-5ccc-af97-a1ae0ec65f3e |  | note | Operating Time
text | 506a9e80-117b-53a4-a8eb-5c600d907c5d |  | textbox | Time
text | 781aed7a-f56e-5e75-8c66-5933afdaf2c3 |  | textbox | P/F
label | eb882e79-8beb-5775-b2b8-fde90c74dd48 |  | note | Any repairs photographed/commented on below
label | f61f72af-670c-528e-ad19-1f7bdcd920d8 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.4 - Pass once completed
button | db12928c-bf53-5560-8e53-8d7ac636ad47 |  | button | Fitting Condition | Pass, Fail
button | 77983226-937b-58b9-9df7-a1c1534329a8 |  | button | Lamp Operation | Pass, Fail
boolean | 21a63088-8d94-58c9-a227-4e068f868ff8 |  | tickbox | Clean Fitting
label | c5359d62-4fb1-5b50-8182-51cc6c1676d0 |  | note | .. ..
label | 1b522c85-16e1-5594-910a-1f843f74150a |  | note | Operating Time
text | f499b9bc-eeb6-5c25-9ccc-b05217949902 |  | textbox | Time
text | 6d0eaed1-fc4d-535e-b5c6-75fa1e87e618 |  | textbox | P/F
label | 448aa677-3abc-5e40-8b06-87b03a612de1 |  | note | Any repairs photographed/commented on below
label | 03cd34df-de2e-5b02-aa40-ede275c20524 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.5 - Pass once completed
button | 1f36e506-3e3b-58c9-a539-30aca51aae95 |  | button | Fitting Condition | Pass, Fail
button | 0266139d-f41f-5247-ae82-4e6695beb378 |  | button | Lamp Operation | Pass, Fail
boolean | b3fba14d-5928-5196-84df-24956677932c |  | tickbox | Clean Fitting
label | 606d7f7f-5a0c-57fd-b269-82df83c77a64 |  | note | .. ..
label | 6a47a1e1-286e-52be-abc7-b47f32074b4b |  | note | Operating Time
text | d4f71fd0-a836-5296-a8be-9b7433b10772 |  | textbox | Time
text | aac2cad7-bdaf-5af0-a69d-5f40ec2a27d1 |  | textbox | P/F
label | c52e7ee1-16dd-559f-842c-491938712e24 |  | note | Any repairs photographed/commented on below
label | c7a2f7e7-3dab-5966-a34c-f262e6965116 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.6 - Pass once completed
button | f9d7c429-9f69-536a-9518-e72954e0407b |  | button | Fitting Condition | Pass, Fail
button | 2497103e-ec15-5fab-9695-f5bbbc8966cf |  | button | Lamp Operation | Pass, Fail
boolean | e02c6cc2-29e3-5d7d-8c8b-d71539d1830c |  | tickbox | Clean Fitting
label | bd938903-b329-585c-b8fe-d7af4e30bd9f |  | note | .. ..
label | 0ecee6bd-dbfd-5644-b578-f92d815fde51 |  | note | Operating Time
text | 82147e9e-7c66-5075-85ab-566ce13832ff |  | textbox | Time
text | cc3c8e6b-fc19-5006-a896-87888b59be6f |  | textbox | P/F
label | 135f3649-bcf5-5e70-8c18-81388e5920e2 |  | note | Any repairs photographed/commented on below
label | 996adbae-8555-539c-a6e6-61f3abf2abca |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.7 - Pass once completed
button | b96edfc5-422d-532e-ad80-afcdeecc42e1 |  | button | Fitting Condition | Pass, Fail
button | 085ba965-bc80-51c7-99a4-de1cfb3ace43 |  | button | Lamp Operation | Pass, Fail
boolean | 97233cf3-e23a-5d49-9bce-71ea78fff48f |  | tickbox | Clean Fitting
label | 6dbaf62e-0bb8-5d79-aff9-2acdf9463225 |  | note | .. ..
label | 052bc439-657b-510f-9362-d1a441cf5b2a |  | note | Operating Time
text | d55fb2e7-11f2-5091-943e-2eaf9569b9c6 |  | textbox | Time
text | a43c6098-2942-554a-b326-bb88855c97c6 |  | textbox | P/F
label | b8773872-6e6e-5b73-b6e4-2fdf17898f19 |  | note | Any repairs photographed/commented on below
label | f9b6244d-ad99-5293-82a4-719f240c1b87 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.8 - Pass once completed
button | a2e6d8aa-0c9f-588d-ba7b-1803a780b5d0 |  | button | Fitting Condition | Pass, Fail
button | e89fb252-e838-5760-badf-448418929231 |  | button | Lamp Operation | Pass, Fail
boolean | 9eea1c31-14d1-5947-b8b3-c931f2068a6f |  | tickbox | Clean Fitting
label | 748fdc62-3740-5b95-a506-e995db8e4645 |  | note | .. ..
label | c417208e-6dc1-55d1-8ddb-903e0cccd084 |  | note | Operating Time
text | cf5616ce-2636-5617-8088-0f585b7b914e |  | textbox | Time
text | d9572482-ef4e-5295-9aa7-1b07b637a219 |  | textbox | P/F
label | 2daec218-baf1-53ac-bb4f-e32d7367d2e8 |  | note | Any repairs photographed/commented on below
label | d0ab488a-1297-5f99-9f99-ff3af40e5359 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.9 - Pass once completed
button | 6bcb5337-8168-532c-a076-1eec7f59fba5 |  | button | Fitting Condition | Pass, Fail
button | 9c3dca93-9117-5190-94f5-a38e6eec8312 |  | button | Lamp Operation | Pass, Fail
boolean | 3c363464-292a-5330-a790-dd25e251c61c |  | tickbox | Clean Fitting
label | 6c7600a9-9253-5f97-9a07-e982ad1a346b |  | note | .. ..
label | 69a78763-0fb7-536b-8640-be245484758d |  | note | Operating Time
text | efc9af95-421e-59a6-b9db-8b3017cad2d5 |  | textbox | Time
text | 78ff5875-db9b-5cfc-8162-c44d1c310b86 |  | textbox | P/F
label | bdbe3bfa-e4a4-55e3-a9fa-f8fa42d2d90a |  | note | Any repairs photographed/commented on below
label | c521d76d-56ce-52b2-a162-08f319c35eb6 |  | note | Attach Signature Sign-off below once completed
checkpoint-status |  |  | checkpoint | Fitting No.10 - Pass once completed
button | b6d7d7c3-2783-52eb-adbb-d032f929bc4a |  | button | Fitting Condition | Pass, Fail
button | 8f1dd6db-ce0f-5847-9477-aa84226e74fa |  | button | Lamp Operation | Pass, Fail
boolean | 19919fb8-b65b-5618-a03d-cc6999f085d7 |  | tickbox | Clean Fitting
label | f6a7e7db-a56c-523f-8eaf-59119590e080 |  | note | .. ..
label | f36db8d8-d470-5208-a0aa-db35788f4fc2 |  | note | Operating Time
text | 90395278-e1ed-5853-b27c-2faa73fc0486 |  | textbox | Time
text | 1bfe8d5e-ac83-571d-9ec1-c2cc1284a22b |  | textbox | P/F
label | a6f8fb8b-83f4-5b7a-8ce4-24d62af325a1 |  | note | Any repairs photographed/commented on below
label | dc775120-3d22-5266-a828-95eb21c8154e |  | note | Attach Signature Sign-off below once completed
checklist-sectioned |  |  | checklist | AE-ITCX-009 - Mains Cabling Reticulation Test Sheet (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-009 - Mains Cabling Reticulation Test Sheet (Rev 0 +Names) | 2d982289-3d21-4e05-979a-22b7a50db148
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | ea24f633-e1ed-533a-ac31-70af5d45bd58 |  | textbox | Drawing & Revision #
checkpoint-group |  |  | section | Test No.1
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | e14ea52a-5641-56b4-bddd-58c61629a30d |  | textbox | Cable No
text | 0954a00e-d3be-5578-a91c-1bd8f9ded416 |  | textbox | Cable Origin
text | b1269fb4-b663-5c77-ba4b-a052ca2081a5 |  | textbox | Cable Destination
text | 2db93642-189e-51be-a250-877c85e107a2 |  | textbox | Upstream Circuit Breaker Size
select | 4fbc1f43-789d-5b6b-af60-400491aca507 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 72922ee5-8803-55aa-8b3c-b1ea6698acb9 |  | button | Fire Rated | Yes, No
text | 48af6235-8b77-57da-a751-2358ad8a8cb2 |  | textbox | Cable Size (mm²)
text | 777a4369-8f5c-5d92-af14-0af1586eb9b1 |  | textbox | Earth Conduit Size (mm²)
text | bac2b394-b230-5196-8c63-008da5dac267 |  | textbox | Earth Conduit Size (mm²)
select | 260d0dc1-cc76-5677-b544-be16c3ca3937 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | c203852b-db6a-5794-b767-3b505d82931c |  | textbox | Other (Specify here)
button | c5eead5c-319a-5820-8c82-90055196e83a |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 6405a80a-4462-54be-9bff-1c7f698c10ea |  | dropdown | Cable Spacing | Trefoil, Flat
text | ee814108-987a-5dcc-bfc0-305515936b42 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 39eeca96-5272-5b06-88c9-f3282689c424 |  | textbox | Red / White
text | efc77ad7-e073-54f0-8926-3fffcaeb05e9 |  | textbox | Red / Blue
text | 06ae0aa5-b52a-5350-b96b-97499948103e |  | textbox | Red / Earth
text | 4e23e2ab-645b-5953-8012-f0ce947f9d38 |  | textbox | Blue / White
text | 007c09f4-dc6b-52a2-a8c3-c410aa72a25a |  | textbox | Blue / Earth
text | e0825c48-661c-52ad-bf96-05a74772a92d |  | textbox | White / Earth
text | 4a22339d-70db-503e-917c-4401d7418444 |  | textbox | White / Neutral
text | 0ef6fefe-3aba-597b-bb23-5c1dcbb7bfef |  | textbox | Red / Neutral
text | 9fa784b8-22c8-55c7-99da-c067dbdb2ebc |  | textbox | Blue / Neutral
text | 50b3f600-add8-51c9-be23-1a2de1f70475 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 8979cdc8-a0d3-5538-945a-08810b165045 |  | textbox | Earth Loop Impedance
text | 75c1ffe6-9765-54c3-859b-c4ed16b891a2 |  | textbox | Name
label | c3dc679b-945f-5df8-881d-adb919c7430f |  | note | Signature added below
checkpoint-group |  |  | section | Test No.2
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 74a45714-e9c6-5841-b7b8-c4bea0546d2b |  | textbox | Cable No
text | 5e9a2c04-d502-5aaf-b0e5-9d61158c872f |  | textbox | Cable Origin
text | 923fdc65-de66-5771-af70-8a40b42b5320 |  | textbox | Cable Destination
text | 0ad9c5c2-9cb1-5d55-8a3d-cdf71d5d39ea |  | textbox | Upstream Circuit Breaker Size
select | 42853cfb-8b53-5508-873c-5f2ddd8f660e |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 0a28ee48-5d58-56fd-8e86-8f14ddabea3a |  | button | Fire Rated | Yes, No
text | 6931d7d3-f0ea-5d65-be75-150547165294 |  | textbox | Cable Size (mm²)
text | 93741741-6b5e-5419-996e-ac65d818b714 |  | textbox | Earth Conduit Size (mm²)
text | 7d55853a-9eee-599f-82e3-f4bb91a7454f |  | textbox | Earth Conduit Size (mm²)
select | 2223e37c-984e-551f-93aa-6f41e56581fc |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 14043d9d-9c87-57c0-8b24-56a69577ea4c |  | textbox | Other (Specify here)
button | 0a73ccde-cd77-5126-afa0-dfe0c09e633b |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 8aca8fb2-2d10-5f28-a137-03655776d1ef |  | dropdown | Cable Spacing | Trefoil, Flat
text | faddae2a-d1f0-5501-8c7b-b6731ab41f10 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 0ba5217b-1f78-51d0-b16b-0deeef8f2d09 |  | textbox | Red / White
text | 0ce9a123-0576-5105-9b64-55652432ef02 |  | textbox | Red / Blue
text | 6ee8d90c-eda2-50ce-a3a4-70ec4459a29c |  | textbox | Red / Earth
text | ab935f23-27b3-5b11-849f-09332d5c148f |  | textbox | Blue / White
text | 392fc177-cd23-5786-b2bd-307fef24670d |  | textbox | Blue / Earth
text | 7d250542-1261-51ff-97f7-cd329645842f |  | textbox | White / Earth
text | e1db496a-3f01-5088-8354-504a46b3f015 |  | textbox | White / Neutral
text | 35b38a91-7a5f-5d0a-afe1-696e986dd78f |  | textbox | Red / Neutral
text | 2e023313-b7e6-5383-9daf-da6aaf360bde |  | textbox | Blue / Neutral
text | e6dd5707-7c77-5fa4-98fb-efce57b0a4fc |  | textbox | Neutral / Earth (MEN Disconnected)
text | 143f12ed-93a2-5b8e-adf8-176aebb7e502 |  | textbox | Earth Loop Impedance
text | c8007d02-f80e-5210-a206-4587d6d57734 |  | textbox | Name
label | 57252fb7-2000-5326-b054-e4bf6613aaa8 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.3
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 77f06984-3446-5955-94b6-8c055d84419a |  | textbox | Cable No
text | 9db4ea2b-bf63-54ef-a282-53cb1ef86933 |  | textbox | Cable Origin
text | 93906d82-97df-5c17-92b0-ca0c3321c037 |  | textbox | Cable Destination
text | b87e37bf-21bf-56e1-a34f-625f2ab7e513 |  | textbox | Upstream Circuit Breaker Size
select | 31476f76-d659-5cd1-be42-d2a3fd6aa5d9 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 568d8996-4c26-5bd9-ba82-2d96ef2e5d3b |  | button | Fire Rated | Yes, No
text | 43fae144-bf3d-5a3f-b2bc-17a835361e2f |  | textbox | Cable Size (mm²)
text | f7a58331-61bd-5d14-b5d5-aea252f05151 |  | textbox | Earth Conduit Size (mm²)
text | 42d32df0-71a8-5580-a710-5c6f2366a2ca |  | textbox | Earth Conduit Size (mm²)
select | 15a183c2-d3ac-50d4-a05c-1d4e5da26f99 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 0b8a8090-3bfa-57a1-b007-6c377a45964e |  | textbox | Other (Specify here)
button | 28b95b3e-513e-5dc0-a328-7ca7d94d18e3 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 28207215-a6a4-5585-8382-1a64759506d6 |  | dropdown | Cable Spacing | Trefoil, Flat
text | afb626cc-183d-5a1a-87c8-3beec059f5d5 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 41a44d42-499d-56f3-9e0f-9f752cbcd719 |  | textbox | Red / White
text | 31c958f9-533a-5ab3-a12b-d15c1a8b7a8f |  | textbox | Red / Blue
text | a6d7fcd8-b0ac-5cb6-a21a-8c3270d23c78 |  | textbox | Red / Earth
text | eb92b04f-6ac6-532f-9c6c-37950361bddb |  | textbox | Blue / White
text | e3866e0e-41c2-5e79-9d16-5c607b4a7032 |  | textbox | Blue / Earth
text | 7aaae40b-e79a-53de-b041-0cc1f6f1d456 |  | textbox | White / Earth
text | 2b09bf63-80a3-5bbd-b9e7-dd6b40b8c922 |  | textbox | White / Neutral
text | 9cfc66e8-b306-5a58-bd8d-4c338a33ef08 |  | textbox | Red / Neutral
text | d9908cb2-a906-516f-a117-2c29064f43b3 |  | textbox | Blue / Neutral
text | a2c1e334-4bda-5857-8cf1-6be6345c7f24 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 95645609-e7c8-5fcb-b133-74072434bf72 |  | textbox | Earth Loop Impedance
text | 0f950d12-798e-5b69-8b68-43922f0c520b |  | textbox | Name
label | e17992c2-3976-5ed2-b9ee-dba72ed18fb3 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.4
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 626dde58-b6d9-51d0-8261-056ffb9c8a13 |  | textbox | Cable No
text | 552551ab-c857-5a89-8180-5526ef2b8a05 |  | textbox | Cable Origin
text | ef2ba396-f32b-5e15-b16a-5f5342444faa |  | textbox | Cable Destination
text | 08aa3f6f-4b01-5e9e-a0c9-bc2e9524e4af |  | textbox | Upstream Circuit Breaker Size
select | 6db8c499-6e23-518b-9b52-7918b62fc595 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | a11cce1d-3b18-56fa-baee-f58bd49eb60a |  | button | Fire Rated | Yes, No
text | 2cf9a1df-fc90-54c0-8797-ceba40211d51 |  | textbox | Cable Size (mm²)
text | c475f27b-23a3-5a3d-9d88-0817ff9b46ee |  | textbox | Earth Conduit Size (mm²)
text | bc3afd33-a6bc-51fd-bcf9-e2928c0b800a |  | textbox | Earth Conduit Size (mm²)
select | 3014235e-3934-576b-8b63-f005a14019aa |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | a189687d-c6cb-5cd1-9e1e-993de66ca5de |  | textbox | Other (Specify here)
button | 2fd001d5-7673-5a06-9522-10e8bc0a6e6b |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | e875754d-d1e0-564c-8c85-b291e256fb6e |  | dropdown | Cable Spacing | Trefoil, Flat
text | 21cab9b5-e22a-53b0-ae06-27797fb37cde |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 33f103cf-d89c-52cf-bd58-089bbbceba1d |  | textbox | Red / White
text | bbee22b0-a380-5d85-a93a-68982ddab76a |  | textbox | Red / Blue
text | 24b4ca24-a628-51fb-925b-14b6c2f4c605 |  | textbox | Red / Earth
text | 37725fe5-fff9-5fcc-aef9-0ae64c9c22b9 |  | textbox | Blue / White
text | 6d4a4226-c9e2-546d-ad4f-4ab65ac5f434 |  | textbox | Blue / Earth
text | b6c6fadb-5df2-5b83-b733-a0e7133161ee |  | textbox | White / Earth
text | e1f4d436-d764-54a8-9e7e-cad5eb5f9ec3 |  | textbox | White / Neutral
text | 3d7d6b42-2be6-50f5-901f-6121b5d47fc1 |  | textbox | Red / Neutral
text | b6d05b9b-b2e6-5c66-aa93-7eb04a282cd0 |  | textbox | Blue / Neutral
text | 45663465-92bb-5f0f-bfc4-f742f9254e22 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 607229e6-1c84-5360-9302-a9edd611944d |  | textbox | Earth Loop Impedance
text | 8b9c8eff-3248-5010-8476-9c64f0d927b1 |  | textbox | Name
label | c18601ff-aa79-50b6-bb15-262e88aaf75d |  | note | Signature added below
checkpoint-group |  |  | section | Test No.5
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | fd5642a1-d622-55a0-8ae8-e596382ad1db |  | textbox | Cable No
text | 66bd0d64-ee40-5f5a-bdfa-2c3d7a17e32b |  | textbox | Cable Origin
text | bba126d8-ddf5-5569-8c7a-733effc144e6 |  | textbox | Cable Destination
text | 29aafba5-90a2-5f91-b3f9-f37d446c8e7b |  | textbox | Upstream Circuit Breaker Size
select | 6c26b6c9-0a41-5e0a-a80b-258662dc3773 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 8d2f450b-27a3-5be5-9614-0ccb8e029fe7 |  | button | Fire Rated | Yes, No
text | a4ca4c97-d7ad-5416-9670-805b4013a012 |  | textbox | Cable Size (mm²)
text | b0c4370d-519c-5188-99ef-b410397c0121 |  | textbox | Earth Conduit Size (mm²)
text | 347bb805-24a6-575a-bb50-341bb1f9f42b |  | textbox | Earth Conduit Size (mm²)
select | 41facd65-3242-5248-be56-30a441bc4d58 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | ab5e5b40-8c9c-5512-bfbb-0079159e2f96 |  | textbox | Other (Specify here)
button | 67d21d6c-8842-5920-8115-4a3aaac900a6 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 029ccc16-bb35-5893-9b16-7b9562c20ff9 |  | dropdown | Cable Spacing | Trefoil, Flat
text | 4e710b19-62ca-5642-a801-4ccf17b1f0cf |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 4b0c55b9-3812-53f4-b076-8cd5489e5dbd |  | textbox | Red / White
text | 9e1cefdb-6c79-594b-bb57-b57134feb08f |  | textbox | Red / Blue
text | acbe18b6-bd21-518b-be8b-ccd207143486 |  | textbox | Red / Earth
text | 07a97173-26b0-5d4e-b55c-df9c442225dc |  | textbox | Blue / White
text | 0cfb1953-6e4c-5939-a0c4-ed4b22d0b064 |  | textbox | Blue / Earth
text | 6fbb0baa-bf11-57f7-89d7-9c0b3fd32002 |  | textbox | White / Earth
text | f63119fb-595c-51b0-a7ba-d964f62067dd |  | textbox | White / Neutral
text | d3a3f9ed-7783-5f92-81d1-70293e0418a2 |  | textbox | Red / Neutral
text | ded62efa-4543-569d-a09e-256954c7c7e5 |  | textbox | Blue / Neutral
text | 9b47c055-e23a-55a4-96f0-51e40a2282df |  | textbox | Neutral / Earth (MEN Disconnected)
text | 84c597ae-346e-5dae-bd9d-d762b9da59ec |  | textbox | Earth Loop Impedance
text | 33d8a829-c325-5637-8f67-65bd9238cacc |  | textbox | Name
label | 8c351e8f-3cc4-560f-832f-3a19734dd56b |  | note | Signature added below
checkpoint-group |  |  | section | Test No.6
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | e4538067-fa64-504a-9025-5dfbf128e36b |  | textbox | Cable No
text | 7ca48b44-8fae-55f4-b2e6-3d679e5b7f12 |  | textbox | Cable Origin
text | 2cfb5d82-eb02-5b15-b2c2-738e0f4377e0 |  | textbox | Cable Destination
text | 83ceec54-7df9-55a4-bb5c-ce972e7149aa |  | textbox | Upstream Circuit Breaker Size
select | 7627456a-7168-5af6-9eaa-2ce9ac5ac075 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 8554d840-8aa5-51ec-bb8a-6ef245a9a952 |  | button | Fire Rated | Yes, No
text | 7dfb0623-f58e-5b62-810f-c3f9921de694 |  | textbox | Cable Size (mm²)
text | fb3b868b-edcc-5424-a7bd-f5dc7571bedd |  | textbox | Earth Conduit Size (mm²)
text | 294683d3-26d4-5ff6-9a47-52617f6c51a4 |  | textbox | Earth Conduit Size (mm²)
select | 6341bd8f-e1ec-51d5-bc5f-e2f46ff38e45 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 3a3244cc-5b9d-55dd-9687-9aacb8873609 |  | textbox | Other (Specify here)
button | 70a2c486-e9ea-5018-a452-1553152a1889 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | ceafec0f-6066-5d4a-b7b4-020800ac2803 |  | dropdown | Cable Spacing | Trefoil, Flat
text | da3e4a54-3b1b-571d-a081-b0731a232615 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 35104af4-6b4c-56d4-bdb7-781ee02f5388 |  | textbox | Red / White
text | 32cd63d2-d6c6-53c2-92b4-323808bc9205 |  | textbox | Red / Blue
text | 98799cc6-b3cf-5d59-9583-68f4b5a0280b |  | textbox | Red / Earth
text | 5a98c75e-316d-59f9-96d4-594a12f90361 |  | textbox | Blue / White
text | 03f215ca-58fd-55b5-bf23-a0a1e0f946f4 |  | textbox | Blue / Earth
text | d22f0861-baa5-5c39-9860-8eec00209d20 |  | textbox | White / Earth
text | adc71021-f9b6-5a23-a736-e7156dbce0e9 |  | textbox | White / Neutral
text | e2c21f68-c85b-5418-9843-2351b3ef8456 |  | textbox | Red / Neutral
text | 435b32e1-6c5e-5e9a-b87c-40d27b6b06d3 |  | textbox | Blue / Neutral
text | 05945070-ff5a-5d59-a41f-f44e21ada2c8 |  | textbox | Neutral / Earth (MEN Disconnected)
text | 1b6c6cce-507f-518f-91d7-2bfff9e0bddc |  | textbox | Earth Loop Impedance
text | 921eafcf-fcac-5922-bf82-5f102ac893d8 |  | textbox | Name
label | b06fd5c1-67a1-57e0-9549-c35d976136c7 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.7
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | c022d3d7-2f3e-5184-ab5d-9174227c8d7c |  | textbox | Cable No
text | 9ff54443-2d92-5257-b6ca-ed6e3c8c12ba |  | textbox | Cable Origin
text | 5fa73251-6e4b-5463-b7dc-b166d30bbc33 |  | textbox | Cable Destination
text | b0c2f159-7714-52f6-9f10-f3f202beab6f |  | textbox | Upstream Circuit Breaker Size
select | a1903ece-247a-5cde-be4e-aad1012d91d7 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 6a7ed18a-0c89-5690-bcf9-43e3646e501e |  | button | Fire Rated | Yes, No
text | 25c31c50-1390-5005-b2f6-6d3da0fa5a9f |  | textbox | Cable Size (mm²)
text | 12c2cac8-afcb-548d-a255-29b849603763 |  | textbox | Earth Conduit Size (mm²)
text | 020f41d8-abfd-5f55-859e-e6b1a7294e96 |  | textbox | Earth Conduit Size (mm²)
select | c32b5df7-3c11-53f1-b77d-034e454e825a |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | b6e91705-2d29-5e48-b04d-fe6015f69a0d |  | textbox | Other (Specify here)
button | 967aa242-96e4-523a-ba00-cd90174c45e4 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | b6366808-0dfb-5305-bdf8-2a334248a2cb |  | dropdown | Cable Spacing | Trefoil, Flat
text | 585e2b54-c8f0-502e-8c55-1ec368d0f4b5 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | ac31bc97-b65e-598e-b707-8e93abdfc123 |  | textbox | Red / White
text | 93b45b36-d3f2-5485-9562-7a32bde230d2 |  | textbox | Red / Blue
text | e343cb09-f279-5ca1-952b-8a583b104226 |  | textbox | Red / Earth
text | dd303f06-e080-5889-ac04-b825c2e2fa7d |  | textbox | Blue / White
text | 540dbdd1-c62a-5f3d-85af-59635f644136 |  | textbox | Blue / Earth
text | 82a3c8bf-4c82-5ff3-a6d3-e5b9689d423d |  | textbox | White / Earth
text | 6da1b6a2-b62e-57b5-b8d9-fccbedee0f18 |  | textbox | White / Neutral
text | 94039aac-b5f0-5721-be88-b96c18d8ffde |  | textbox | Red / Neutral
text | e264b6bd-70ee-5f2a-ac6f-1112bb3d141e |  | textbox | Blue / Neutral
text | c9783a79-fd77-59b5-8d6a-c6068b0ff6de |  | textbox | Neutral / Earth (MEN Disconnected)
text | 0233065b-d5d1-5659-9a11-7ce02dee5a90 |  | textbox | Earth Loop Impedance
text | b99c4bc4-7a35-5db9-a093-141a3c89374c |  | textbox | Name
label | 8184de9e-dd79-5f4c-9271-305b1ae13104 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.8
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 4801cefa-538c-5b62-a41f-24d074f8b884 |  | textbox | Cable No
text | 8750b016-15cb-50ab-9980-70c250030d88 |  | textbox | Cable Origin
text | f1fc5614-7ddc-53a7-848f-88e16eefcb32 |  | textbox | Cable Destination
text | 96354e80-ccd0-56de-95c7-71b03310abea |  | textbox | Upstream Circuit Breaker Size
select | 3fd21ba0-527b-5a6c-a638-e53a14286c5c |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 0eb72bd0-7619-5181-adfc-070ed8c12f4a |  | button | Fire Rated | Yes, No
text | dc8e7e65-4ffd-5a88-9cca-b3581eeb134c |  | textbox | Cable Size (mm²)
text | a8e3c297-95a5-519b-a18e-66bee57533a9 |  | textbox | Earth Conduit Size (mm²)
text | 0f08d123-7827-5622-b3b2-bcf9fe92ffa7 |  | textbox | Earth Conduit Size (mm²)
select | 244d09c6-b6d1-5ee5-a40c-95d13eac37fa |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | 40a487f6-131b-5c01-942d-5c9a80bcbbfb |  | textbox | Other (Specify here)
button | 88963221-0e2d-5807-809a-02921e2841f3 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 27126c94-c883-5ad0-85e5-b92796dbeeb0 |  | dropdown | Cable Spacing | Trefoil, Flat
text | cdd94e60-71ce-5b94-aca7-02634fd5a475 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 616ee3eb-c22b-56a6-a337-d3eabc6d0fb2 |  | textbox | Red / White
text | aebeb70c-4b4e-511a-9ed4-00557a521b04 |  | textbox | Red / Blue
text | 5c71f5cd-b9a3-58e6-92c9-5250a6b0f166 |  | textbox | Red / Earth
text | fddb1e37-0f05-57a4-81f2-9a9bbb4a92e2 |  | textbox | Blue / White
text | 8e238177-675b-525e-a0df-596d85fd41c6 |  | textbox | Blue / Earth
text | a6236975-3104-5f4b-bab3-9fea1fba5b97 |  | textbox | White / Earth
text | 110ea03e-682e-5162-848b-51fbb5f136b1 |  | textbox | White / Neutral
text | 1757fef2-7626-5c02-825b-6df03045c3f1 |  | textbox | Red / Neutral
text | ef6213da-67df-553d-819b-b7b1977de9bd |  | textbox | Blue / Neutral
text | db44d4bd-7023-5547-83ab-f15ee429aabd |  | textbox | Neutral / Earth (MEN Disconnected)
text | e241432d-1531-5abe-b71d-da165b1c5860 |  | textbox | Earth Loop Impedance
text | e17e5250-569c-5fb5-a5fd-091baa142e00 |  | textbox | Name
label | 67dd9597-6f27-5aba-8c3a-3c755dbec575 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.9
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 5bb6809b-dc64-5981-9f84-a378a45fef7e |  | textbox | Cable No
text | 1d0da867-729c-5186-919d-e486a5c4453a |  | textbox | Cable Origin
text | c5e63594-4da4-5f2b-97c8-4ce872959a2a |  | textbox | Cable Destination
text | 3e1f9ffd-c1cb-5e02-8499-dad3de317587 |  | textbox | Upstream Circuit Breaker Size
select | 1e096560-5c37-50a8-b989-ff9e2827d453 |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | b7b8ef9f-3cdf-5977-ba5f-d1f8504df2fb |  | button | Fire Rated | Yes, No
text | 90620f91-5e7b-5582-83e9-839b3b2eb185 |  | textbox | Cable Size (mm²)
text | 6807c4af-6082-55d9-b005-783ff6fddf07 |  | textbox | Earth Conduit Size (mm²)
text | aa0aa46a-0a48-52e0-a230-29f664b9fd16 |  | textbox | Earth Conduit Size (mm²)
select | e43c759e-4e59-5a16-a3c7-69728c35e4c1 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | eafd764d-e99d-5225-af9e-45c46f261f84 |  | textbox | Other (Specify here)
button | 8902d41c-7d69-5ad7-af6f-b97409121df3 |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 11e51ba8-be8e-5a67-b181-441540a98cc7 |  | dropdown | Cable Spacing | Trefoil, Flat
text | 79a0dbed-80fb-59e2-8dc6-0e9d4942aa09 |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 4ec035b9-4718-5831-921d-deeac78ee5b1 |  | textbox | Red / White
text | 7af586bd-8efe-5d5c-9ddd-76c85166cae1 |  | textbox | Red / Blue
text | 24f55189-1352-5000-8b0e-0b20aaf8714d |  | textbox | Red / Earth
text | dac585ba-7cab-5572-b180-29f258f907dd |  | textbox | Blue / White
text | 8dd78104-34ec-5f04-a9b5-830dde937276 |  | textbox | Blue / Earth
text | aa99f0df-9d32-5c71-8a7f-56fae5bea052 |  | textbox | White / Earth
text | 7c0f8e57-96c7-5da6-8cca-208ddc9b44cc |  | textbox | White / Neutral
text | 710d428a-5158-5f12-89ec-96b8b686a7b1 |  | textbox | Red / Neutral
text | 77c3534b-e1ff-56af-b37f-1dc372c476e7 |  | textbox | Blue / Neutral
text | c37a849c-e2b3-5e85-a0fe-e9bbd94f10da |  | textbox | Neutral / Earth (MEN Disconnected)
text | fda2b2f9-9cb2-5c19-8110-0a6957af7437 |  | textbox | Earth Loop Impedance
text | 10c0d3c5-23b2-53c0-8de4-cd01e56dc712 |  | textbox | Name
label | 651b4ef0-2b05-5f3b-a717-9333966b6e32 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.10
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 330c2890-6dab-54a7-85cb-93f0d6e3b6b8 |  | textbox | Cable No
text | 6b40f00a-893c-5dae-a30e-acf998f6bd58 |  | textbox | Cable Origin
text | e266f226-4ccf-55dd-a9d1-a064cbc2ee88 |  | textbox | Cable Destination
text | 2c9efee8-1540-5e22-b863-f2bf3858420e |  | textbox | Upstream Circuit Breaker Size
select | 9f42acd6-12ba-5a06-8e87-f4e69b1e0cdf |  | dropdown | Type of Cable | X = XLPE, O = Orange Circ, M = MIMS
button | 09e8e354-51d6-5f48-acd4-9c6f39ae6d13 |  | button | Fire Rated | Yes, No
text | 585e0614-0ff7-55db-91b7-bca733ce9e86 |  | textbox | Cable Size (mm²)
text | 9aa44f65-77ec-52f4-bf38-8da4ee83d0f4 |  | textbox | Earth Conduit Size (mm²)
text | 6577a801-a4b7-5d7f-bf63-1321f3e59487 |  | textbox | Earth Conduit Size (mm²)
select | da1a062e-26e2-56f6-80e0-271c62c846d8 |  | dropdown | Support Method | Tray, Catenary, Duct, Other (Specify Below)
text | afba5ef9-ca0b-5308-8216-d9bf579643ce |  | textbox | Other (Specify here)
button | b0609aa8-d894-5924-b198-481bebf8893b |  | button | Line & Load Side Termination Checked & torque (AF128-2) | Yes, No
select | 7c05434f-b13e-5063-b0bd-48404e40c62f |  | dropdown | Cable Spacing | Trefoil, Flat
text | f5a4b514-8d1f-5ac0-ad4e-c2df4daa348c |  | textbox | Cable Earth Resistance
checkpoint-status |  |  | checkpoint | Insulation Resistance - Pass Once below details are completed
text | 6a18a394-dcba-571d-a24f-bf609decd28e |  | textbox | Red / White
text | 9e80a33b-4e80-511d-8512-d6028363351d |  | textbox | Red / Blue
text | 72fd340f-adc2-5492-8df6-c33b11e9ff1e |  | textbox | Red / Earth
text | 619b66f0-1b4e-534b-8e14-060b3c14e179 |  | textbox | Blue / White
text | 2ae809c0-8303-5dc6-90fb-d4fc55b0331c |  | textbox | Blue / Earth
text | f9612990-d104-5424-a2b7-481c96f531ab |  | textbox | White / Earth
text | d78e2856-c0f5-5378-a419-8e3cfaf25e4a |  | textbox | White / Neutral
text | 2fab6dc6-5dd1-5489-99a5-18b72ef69e65 |  | textbox | Red / Neutral
text | 936c3da6-2e99-562e-a4aa-92a71f2922cc |  | textbox | Blue / Neutral
text | d5fd79bf-4f86-585f-8fee-d43e150afa19 |  | textbox | Neutral / Earth (MEN Disconnected)
text | dd4c5b55-7ec2-5b1f-b6c9-8d94cff16cce |  | textbox | Earth Loop Impedance
text | 47bcd869-09f5-50c6-bce3-105ef46957e7 |  | textbox | Name
label | 599abeaf-4cd6-5f1d-83fe-13cf75d353f4 |  | note | Signature added below
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Testing completed to specification/drawings - Area left clean & tidy
label | 8d762302-78be-5601-81b9-b9a948519097 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 46678a51-d9d7-5d75-b6cc-9f3df1708227 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 016dee99-978e-5ec9-88a9-41bd8eea7baa |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | ee081c0b-1d28-5c00-bef6-c7734406fe67 |  | textbox | Other (Specify here)
select | c754920a-2ea5-5e89-8af7-d8d9e4b1d126 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | aa0b5b4c-0e35-5413-b637-1d90c472876a |  | textbox | Other (Specify here)
text | 6ecffec9-98d4-5236-b20a-823bcff2441f |  | textbox | Witnessed by (Builder/QAM)
label | f59cff8e-a15d-5613-a08c-09449859b2e6 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) |  |  |  | 722 | Yes | AE-ITCX-028 - Lead-Ins Checklist (Rev 1 +Names) | 35147533-6e93-4417-94cd-76d15168e50e
checkpoint-status |  |  | checkpoint | Lead In Cables been roughed in to final locations as listed below completed?
button | 392b0acd-62de-535b-8e02-b6d4d85e74be |  | button | Submains installed to the documented location in the field/riser, grouped together 3 or less and labelled correctly? | Yes,N/A
label | 17b309f1-b7de-5f3e-9f9c-d97e9820c019 |  | note | *Mandatory Image - Marked Drawing Including Title Block Revision
button | 7da55d58-fd1d-597b-affd-7be41c8e01d6 |  | button | MATV cables installed to the documented location in the field/riser and labelled as per shop drawings? | Yes,N/A
label | 9c43ee7f-103d-5303-a570-82cc01c33c2b |  | note | Is Cat6/6A Intercom Cabling Appselec scope and installed to correct location? - (If sub contract N/A)
button | 4572323e-352f-56ce-893d-569a3b1f61a7 |  | button | Confirm Cat6/Cat6A leadins installed as documented. (This may include House Area CCTV/WAP outlets on drawings also) | Yes,N/A
label | c4467e91-f1e3-521d-b6c3-9e20ea89f736 |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
checkpoint-status |  |  | checkpoint | NBN and Private Network conduits been completed?
button | 4d49114c-6c2e-5adf-8154-968a138699a5 |  | button | P23 White Comms Conduit installed to the documented location as per Appselec Shop Drawing | Yes,N/A
button | d8c38d4a-8359-5ca6-baf9-2056df4c91a1 |  | button | Draw string installed with the correct “stopper” tied off and labelled correctly? | Yes,N/A
label | 5ced8a7d-ad2e-5383-8ae5-79097e371462 |  | note | *Mandatory Image - Pathway Drawings Drawing Including Title Block Revision
checkpoint-status |  |  | checkpoint | General Checks
button | b3c36c70-ae11-5a3b-9cda-231d4f27e80c |  | button | Apartment Recessed DB installed prior to plaster, in the correct location and height? | Yes,N/A
button | ede520d4-8478-5300-8420-a60a0f299a72 |  | button | Leadin cables & conduits have been installed ready for fire rating systems and are in correct locations. | Yes,N/A
checkpoint-status |  |  | checkpoint | Lead-Ins completed to specification/drawings - Area left clean & tidy
label | cc9b2ac9-7862-5acd-aca0-a3254c7d60af |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | c7b14809-2bb8-5507-91eb-7d2ef3f0470b |  | note | Any Corrective Actions to be Photographed & Commented below
select | 8e144034-53df-5859-8ef3-c68b6ecc28c2 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | a36a19e3-e454-5020-a331-b0067a66160a |  | textbox | Other (Specify here)
label | 3772831f-d7c4-5605-91ef-d6a67cff2b0a |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) |  |  |  | 44 | Yes | AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | 41b34b28-bc8f-4876-8927-184850a1a9d1
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 8b5acfe0-449c-57fb-9773-aefd8fd2f1f0 |  | textbox | Switchboard No.
text | 906ab643-cbb6-59b5-a11d-f30afd1c0716 |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Earthing check
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | All terminations points tight
checkpoint-status |  |  | checkpoint | Labels
checkpoint-status |  |  | checkpoint | Insulation Test
checkpoint-status |  |  | checkpoint | Wiring neatly loomed
checkpoint-status |  |  | checkpoint | Check takeoff box fuse/breaker rating
checkpoint-status |  |  | checkpoint | Energisation procedure
checkpoint-status |  |  | checkpoint | Fire rating of penetrations
checkpoint-status |  |  | checkpoint | Cover plate secure
checkpoint-status |  |  | checkpoint | Switchboard and cupboard cleaned
checkpoint-status |  |  | checkpoint | T-Off Box Visual inspection completed to specification/drawings - Area left clean & tidy
label | 80c10064-2aca-5fc7-8220-cde5c4caa563 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 7398278c-0de1-5a19-805a-d42a3d860b4b |  | note | Any Corrective Actions to be Photographed & Commented below
select | ffe0711a-be39-543c-8ca3-a86608089c92 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c3b11943-1378-5832-90d9-baef4d2a5b48 |  | textbox | Other (Specify here)
select | a97043fd-9bf1-5eac-91bb-8600b52ed4a8 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | bfcb63fc-91f5-5477-9d14-8a6a7e765ba5 |  | textbox | Other (Specify here)
label | 072d3e95-55c2-5aac-8139-76568756d5a7 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) |  |  |  | 722 | Yes | AE-ITCX-031 - Fit-Off General Checklist (Rev 1 +Names) | 4873c25b-3808-415e-b4e4-e3b9ea1fcf00
checkpoint-status |  |  | checkpoint | Wall Fit Off - Light and Power
button | 72979303-3de1-5843-8761-119115b6d2b3 |  | button | Power outlets fit off including GPOs, isolators & hard wired equipment are all fit off, straight and installed by installer with black texta | Yes,No
button | 9f5d5cda-2a6a-5700-b4b5-7e381c9f0b5c |  | button | All Light Switches and LCP's are fiit off and switch plates initialled by installer with black texta. | Yes,No
label | 810068f8-405a-5d85-a556-7047f15b68af |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
label | d6dc30e3-dfe8-5486-b74b-c439625f9dc1 |  | note | Additional Photos as required.
checkpoint-status |  |  | checkpoint | Ceiling Fit Off - Light and Power
button | 48b76957-dc56-5dcc-9e46-88c892c9b36b |  | button | All Light Fittings, drivers, PUKS etc are fit off as per shop drawings | Yes,No
button | 07ae688c-adb2-5fbd-b3c1-4ad4b7e0a902 |  | button | All LED, joinery and feature lighting is completed as per shop drawings | Yes,No
button | 1154462f-6ed6-5601-9991-cc7594b0dfb8 |  | button | All external Lighting, 240V Motion Detectors and Smoke Detectors are completed as per shop drawings | Yes,No
button | 38f596e4-f1f8-5aad-82e2-a7c3410d7106 |  | button | All required EMG and Exits are installed labelled and unobstructed from required view as per shop drawings | Yes,No
button | e094d665-6a61-5f1c-9240-0bc1875e0837 |  | button | This installation is considered ready to hand over to Commissioning crew. | Yes,No
label | 30464c72-59f5-5f3a-834c-94c350b7cd6d |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
label | ca07ca20-65d1-5d70-9c52-1c4790f642ff |  | note | Additional Photos as required.
checkpoint-status |  |  | checkpoint | MATV and Cat6/6A
button | 4b2e3975-fb9c-5bd8-954d-8948672bd3be |  | button | MATV outlets and splitters are fit off and splitters are fit off with correct F-Connect Tools (no frayed copper strands!) | Yes,No
button | fae13c3f-4df4-5448-b120-12877ec85447 |  | button | All Cat6/6A outlets are fit off with outlet label on switch plate (behind cover) along with the initials of the installer. (check CCTV and Intercom when applicable) | Yes,No
label | 674097c8-dad1-5b4c-ba6b-23dcfb2ccd61 |  | note | *Mandatory Image -Marked Up Drawing Including Title Block Revision
label | c7bbbd78-d79e-5e0f-b8a9-395d40e36cb9 |  | note | Additional Photos as required.
checkpoint-status |  |  | checkpoint | Fit-Off completed to specification/drawings - Area left clean & tidy
label | 2214f8d8-bf65-513a-9db8-030de13a70f2 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | b4b80cf1-5843-5b81-a4c0-d93e53582ae3 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 1b1dcf95-2f6f-59ec-ab8d-8d8562545a30 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | 585c6f87-cb02-5277-9372-6db73e2ad131 |  | textbox | Other (Specify here)
label | 8f24f945-778d-5c85-9257-49dd16cbba74 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) |  |  |  | 144 | Yes | AE-ITCX-003 - Mandatory Test Results For Construction Wiring (Rev 0 +Names) | 55b36e94-7ae6-4a0b-bba2-cf1ec8d7a74a
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 9404b53b-77e6-5348-ad5f-30c615614e3b |  | textbox | Equipment being Energised
select | 12524ee2-a9bc-5508-bb9f-f17a09cd8ded |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 6c98874e-588d-5715-a54b-8d4ad89309ad |  | textbox | Other (Specify here)
boolean | 51da268d-7f6d-5367-b321-3cdbaec956e5 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Temporary Board Visual Inspection
checkpoint-status |  |  | checkpoint | All cables secured and protected appropriately
checkpoint-status |  |  | checkpoint | All cables identified with Construction Wiring tape
checkpoint-status |  |  | checkpoint | Switchboard is structurally sound
checkpoint-status |  |  | checkpoint | Appropriate signage in place
checkpoint-status |  |  | checkpoint | All holes filled with stops
checkpoint-group |  |  | section | Temporary lighting visual inspection
checkpoint-status |  |  | checkpoint | All cables secured and protected appropriately
checkpoint-status |  |  | checkpoint | All cables identified with Construction Wiring tape
checkpoint-status |  |  | checkpoint | Appropriate number of emergency lights installed
checkpoint-status |  |  | checkpoint | All lighting plug bases terminated
checkpoint-status |  |  | checkpoint | Light fittings in serviceable condition with wire-guards or plastic diffusers
checkpoint-group |  |  | section | Test Results
checkpoint-status |  |  | checkpoint | Test Results - Pass once complete
text | 6a62bcdc-7672-58fd-8540-460928b932c8 |  | textbox | Insulation Resistance (Mega Ohms)
button | 8074ffdf-00e5-576d-a897-4d35fa578e99 |  | button | Result | Pass, Fail
label | 62de714a-b683-5f1f-a443-e743dc117813 |  | note | .. ..
text | 34c22603-70b5-517f-8604-cda9197ce5bc |  | textbox | Earth Resistance & Continuity (Ohms)
button | 18d37146-3588-5420-a9cc-fa0efa81d221 |  | button | Result | Pass, Fail
label | 74fa3882-1c4c-5e9b-99c8-ae33990a8c28 |  | note | .. ..
text | c1478da9-6adc-5d0c-b62d-c235793e73cd |  | textbox | Polarity
text | 48927e79-7eea-5d1c-afc9-978cf8941682 |  | textbox | Earth loop impedance
button | fedaed71-9248-509c-b0fe-7e4cbcb81ef0 |  | button | Result | Pass, Fail
checkpoint-status |  |  | checkpoint | RCD Time trip test completed
checkpoint-status |  |  | checkpoint | Correct circuit connection
checklist-sectioned |  |  | checklist | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) |  |  |  | 60 | Yes | AE-ITCX-024 - Communications/Security Rack Installation QA (Rev 0) | 5d58f2e8-4e3d-4977-9d33-9b4f27a28ec1
checkpoint-group |  |  | section | QA ITEM 1 - Communications Rack
checkpoint-status |  |  | checkpoint | Is the communications riser ready for communications rack installation
label | 316a9c3a-dedb-546f-9154-920afb462ada |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
checkpoint-status |  |  | checkpoint | Does the communications rack match the approved technical data
checkpoint-status |  |  | checkpoint | Has the communications rack been installed in position as per the Appselec communications riser elevation shop drawings and floor plan layout
text | 98b9e046-21d3-567b-8513-0d9502f6af72 |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Has the communications rack been fixed to the floor using appropriate fixings
checkpoint-status |  |  | checkpoint | Are the doors and side panels installed and free from damage
checkpoint-status |  |  | checkpoint | Does the communications rack comply with all the relevant clearances
label | c718d4cf-260f-5c3a-9624-c186672bd898 |  | note | Are door swings and access to the communications rack unobstructed
checkpoint-status |  |  | checkpoint | Has the communications rack been permanently labelled with a traffolyte label or similar on the door
label | 95d61b8c-7581-5435-8efd-244ca051a78c |  | note | Check that the label matches the communications rack layouts
checkpoint-status |  |  | checkpoint | Has the Appselec label/logo been fixed to the front of the communications rack
checkpoint-group |  |  | section | QA ITEM 2 - Communications Earthing Terminal (CET)
checkpoint-status |  |  | checkpoint | Has a CET been installed adjacent to/or within the communications rack and has a 6 mm2 green/yellow earth cable been terminated to the CET
label | 8c8c9c05-3efb-57c6-81e3-35c4b49a3e2e |  | note | Refer to Communications SLD for earth cabling schematic
checkpoint-status |  |  | checkpoint | Has an earth bar been installed adjacent to/or within the communications rack and has a 6 mm2 green/yellow earth been terminated to the earth bar from the CET
checkpoint-status |  |  | checkpoint | Has the 6 mm2 green/yellow earth been identified and labelled with “Communications Earth” at the originating electrical distribution board
checkpoint-group |  |  | section | QA ITEM 3 - FOBOTS (Fibre Optical Breakout Trays)
checkpoint-status |  |  | checkpoint | Does the FOBOT match the approved technical data
checkpoint-status |  |  | checkpoint | Has the FOBOT been installed in the correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Has the FOBOT been labelled permanently with traffolyte label or similar
checkpoint-status |  |  | checkpoint | Has a service loop been provided in the optical fibre cable
checkpoint-status |  |  | checkpoint | Has the fibre port arrangement on the FOBOT been detailed and labelled
checkpoint-status |  |  | checkpoint | Do the fibre adapters on the FOBOT match the type of fibre being used
label | 93f88055-29d5-5116-b4e9-9ba789b2fbcd |  | note | For example: aqua = multimode, green = singlemode. Adapters, pigtail connector colours must match, fibre cable type must match
checkpoint-status |  |  | checkpoint | Have fibre protective caps been installed on all fibre adapter ports
checkpoint-group |  |  | section | QA ITEM 4 - Cat 6/6A Patch Panels
checkpoint-status |  |  | checkpoint | Does the Cat 6/6A patch panels match the approved technical data
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panels been installed in correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panel ports been labelled permanently with traffolyte label or similar
checkpoint-status |  |  | checkpoint | Have cable wrap-around labels been attached to each individual Cat 6/6A cable behind the patch panels
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panels been earthed with 2.5 mm2 green/yellow earth cable from the earth bar within the communications rack
label | 4357a377-4fab-53f1-a8a2-291222cf8618 |  | note | Shielded patch panels only
checkpoint-group |  |  | section | QA ITEM 5 - Cable Management
checkpoint-status |  |  | checkpoint | Have horizontal cable managers been installed in the correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have vertical cable managers been installed in the correct rack RU position as per the communications rack layout
checkpoint-group |  |  | section | QA ITEM 6 - Power
checkpoint-status |  |  | checkpoint | Has the correct power been provided for the communications racks
label | 72b6876d-c8cf-5dad-9d1a-361813065364 |  | note | Check for captive outlets? Are there 2x or 1x? Are they 10A, 15A or 20A? Check the Appselec power floor layouts against the communications specification
checkpoint-status |  |  | checkpoint | Do the PDU’s match the approved technical data
checkpoint-status |  |  | checkpoint | Have the PDU’s been installed in position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have the PDU’s been plugged into the captive outlets/rack mounted UPS as detailed on the communications rack layouts
checkpoint-status |  |  | checkpoint | Have the PDU’s been labelled appropriately detailing the power source
label | 30228316-f1d3-5f2c-8a82-53a92b94abbe |  | note | For example UPS supply (Generator backed) DB-XX
checkpoint-group |  |  | section | QA ITEM 7 - Rackmount UPS
checkpoint-status |  |  | checkpoint | Is the communications rack/riser ready for UPS installation
label | 26a2460c-f25e-5ef5-bdd2-af98bbb6cd3e |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
checkpoint-status |  |  | checkpoint | Does the UPS match the approved technical data
checkpoint-status |  |  | checkpoint | Has the UPS been installed in position as per the communications rack layouts
checkpoint-status |  |  | checkpoint | Has the UPS been labelled appropriately detailing the power source
label | 014d2887-da97-51a6-8a97-f4af9d5aef69 |  | note | For example UPS supply (Generator backed) DB-XX
checkpoint-status |  |  | checkpoint | Has any associated Battery Backup for the UPS been installed as per the communications rack layouts and is it connected
checkpoint-status |  |  | checkpoint | Has the UPS been commissioned? Refer to UPS ITP for commissioning details
checkpoint-group |  |  | section | QA ITEM 8 - Active Equipment
checkpoint-status |  |  | checkpoint | Is the communications rack/riser ready for Active Equipment installation
label | 07a25eaf-962e-5bb8-93f2-9aee3ee7c6d2 |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
checkpoint-status |  |  | checkpoint | Does the Active Equipment need to be configured prior to installation within the communications rack
checkpoint-status |  |  | checkpoint | Does the Active Equipment match the approved technical data
checkpoint-status |  |  | checkpoint | Has the Active Equipment been installed in the correct rack RU position as per the communications rack layouts
checkpoint-status |  |  | checkpoint | Do you have a network diagram detailing the connection and labelling of all Active Equipment
checkpoint-status |  |  | checkpoint | Has the Active Equipment been labelled appropriately as per the vendor requirements
label | 9a5876c8-22d0-591b-bd99-6c5b94229fa4 |  | note | All switches are to be labelled with the correct vendor labelling convention
checkpoint-status |  |  | checkpoint | Have SFPs been provided and installed
label | 42fa398e-dd40-5a29-bfea-28cb696c71a8 |  | note | Check that they are the correct SFP for the optical fibre cable installed. Check they are installed into the correct port. (SFP is a small form-factor pluggable transceiver)
checkpoint-status |  |  | checkpoint | Have stacker cables been provided to stack switches together Are they connected as per the integrator/vendor requirements
label | c09e545b-2c8b-5536-9650-1b12f05cc96f |  | note | Are they connected as per the integrator/vendor requirements
checkpoint-status |  |  | checkpoint | Have the switches been connected to the PDUs
label | ede763d4-4bad-51d7-ac0a-f5d1b8e1e1d7 |  | note | Check if switches require one supply or two supplies (dual power redundancy). Check if switches require UPS supply/UPS + generator supply
checkpoint-group |  |  | section | QA ITEM 9 - Patching
checkpoint-status |  |  | checkpoint | Do you have the correct length, colour, type (Cat6/6A) and quantity of patch leads
checkpoint-status |  |  | checkpoint | Do you have a patching schedule detailing which switch port patches to which patch panel port
checkpoint-status |  |  | checkpoint | Do you have the appropriate cable management capacity installed to patch cables as per the patching schedule
checkpoint-group |  |  | section | QA ITEM 10 - Photos
checkpoint-status |  |  | checkpoint | Photos must be taken of each communications rack when completed
label | 44e7fa88-ca6d-50f8-8070-8d38c6510827 |  | note | Attach photos below as applicable
boolean | 315c79aa-123b-52a1-bba4-ed8528457bb0 |  | tickbox | Photo 1: Front of rack, door closed
boolean | f23c7c29-42c0-580b-be78-f2c003cd7535 |  | tickbox | Photo 2: Front of rack, door open
boolean | ac2f44b6-5013-5182-a714-ea25c833931e |  | tickbox | Photo 3: Front of rack, door closed
boolean | 8cc2292c-9612-59b6-b0c9-d4ae1fe32b10 |  | tickbox | Photo 4: Rear of rack, doors open
boolean | 5f18076c-f3e7-59df-80d0-f46435232162 |  | tickbox | Photo 5: Any other relevant photos
checklist-sectioned |  |  | checklist | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) |  |  |  | 143 | Yes | AE-ITCX-001 - Temp Board Checklist (Rev 0 +Names) | 6071d65c-7e39-49d8-81c3-b9fb8b86c54b
checkpoint-group |  |  | section | Defects
checkpoint-status |  |  | checkpoint | Major Defects (Send back to Aline)
label | a94ef80e-5085-56dd-b609-ff58f46b486d |  | note | Add photos/comments & Send back to Aline
button | 28515f6a-71f7-59fa-a659-03f302df7837 |  | button | Is the switchboard structurally sound | Yes, No
button | af3cdfb0-b283-5155-bc20-57362e656e78 |  | button | Does the main door close | Yes, No
checkpoint-status |  |  | checkpoint | Minor defects (Fix Onsite)
button | cf9a7d3a-60f3-5e32-b899-e90e211caf73 |  | button | Is the main isolating switch identified | Yes, No
button | ee84c0d4-e8f7-5bdd-973f-c9ad685175fe |  | button | Are all C.B’s and R.C.D’s identified | Yes, No
button | 99ec5ddc-4492-5ccf-8e20-bb26eb358205 |  | button | Is 1.2m clearance signage in place | Yes, No
label | 49709b53-9fdb-50bf-85ed-6d8b09a087d1 |  | note | Add Photo below
button | 77b516e4-12c7-5368-acb2-a4beb1cbaac7 |  | button | Is ‘Live Parts’ signage in place | Yes, No
label | 96c45bd3-eb24-5091-9514-bda0d19a6e5d |  | note | Add Photo below
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Do pole fillers cover all gaps
checkpoint-status |  |  | checkpoint | Are test points installed in the board
checkpoint-status |  |  | checkpoint | Are all holes in connection (J.Box) filled with screwed stops
checkpoint-status |  |  | checkpoint | Are Perspex covers in place
checkpoint-status |  |  | checkpoint | Do escutcheon plates have all screws fitted
checkpoint-status |  |  | checkpoint | Is insulated lead stand attached and insulation intact
checkpoint-status |  |  | checkpoint | Do the flap-lock and door-lock work
checkpoint-group |  |  | section | Replacement Parts
checkpoint-status |  |  | checkpoint | Replacement parts list - Pass=Required, N/A if not Required
label | 5226e385-b775-5dc1-a2c5-2b9f293b6c27 |  | note | Complete this section and order from the office as required. Send report to office Top Right
label | 59b27105-3702-59d0-908e-b52dbbfe4428 |  | note | ----Please do not strip other boards for parts.----
checkpoint-status |  |  | checkpoint | Galvanised Style - Pass=Required, N/A if not Required
label | 2ce85e76-4c2f-574b-b90e-c9f2940d0cda |  | note | Input quantities required below
text | 57c659f2-49b3-567b-bcdd-10e627db8bcc |  | textbox | 10 A DIN mounted GPO
text | 6f735f76-3166-5e54-90cb-edaee3c44d5b |  | textbox | 15 A DIN mounted GPO
text | 71ecd207-a2d3-52b4-8907-de8779430d4c |  | textbox | Line taps
text | afc017fd-5d80-5cbd-99a1-1886354a4559 |  | textbox | Hinges
text | b8866938-ed55-5f31-95ea-6ead47ef1f1b |  | textbox | Door
text | 93c95e03-a1d6-5dfd-b7e0-2893e903d176 |  | textbox | Door handle and tongue
text | ebcb2a0f-747a-5126-942e-0640b3dae059 |  | textbox | Bottom connection box
text | e09dc031-9962-57e0-a021-d66d133e31be |  | textbox | Bottom connection box cover
text | f6da2e42-7054-5864-afb0-481274705f17 |  | textbox | RCD cover lock 001
text | 5420da5b-fdf6-5472-87d9-9cd31945c448 |  | textbox | RCD cover
text | ef8218fe-bf7f-5f78-a1de-ef7369bfce90 |  | textbox | Pole fillers
text | 91c4e277-8299-5b5b-b45e-158246d0dd8f |  | textbox | 63 A main switch
text | 2d42415a-d6a6-56ec-8011-d2f290b4722e |  | textbox | 100 A main switch
text | dcae526c-415a-5e12-9a88-0dbd63f6f634 |  | textbox | 16 A RCBO 2 pole
text | eb74cce0-0827-598b-8ff9-cb84b4842a19 |  | textbox | 20 A RCBO 2 pole
text | 57a6c9a9-aa6f-52e5-ada8-658d4b0e29b6 |  | textbox | 32 A 4 pole CB
text | e3208510-a654-5c17-80dd-9da6785ca127 |  | textbox | 40 A 4 pole CB
text | 584c7967-1515-5817-a65f-1b625102a8c9 |  | textbox | Set of legs
text | f5ff17e7-95f8-5bf1-a2cb-7dc09fb9dae7 |  | textbox | Set of feet
text | 17c9788e-7d88-5feb-8525-17db908bc76e |  | textbox | Perspex cover for line tap
text | 8ce568a9-a845-5fb6-a394-54bf6bf09a80 |  | textbox | Lead stand
text | dc59d639-f01e-587a-83eb-7ce292291830 |  | textbox | Escutcheon
text | 777f70a9-ed14-579b-9094-c71e3da59021 |  | textbox | Connectors
text | 7743e459-7de2-5653-ae15-96064ab10229 |  | textbox | RCD cover lock 001
checkpoint-status |  |  | checkpoint | New Green Style
label | afdac5f6-b009-50b3-9ebc-5729fbd20082 |  | note | Input quantities required below
text | 4b62d1d3-e0cf-5b66-86c9-eed00aa9a0a6 |  | textbox | Door
text | 7de30eab-725b-5dc3-91d4-b091f5034007 |  | textbox | Hinges
text | f7533c79-8188-5b92-9f62-59568f0dd38d |  | textbox | Legs
text | b7d2f545-e251-56b1-ad6a-c967e0d447c7 |  | textbox | Lead stand
text | e5213592-0fc9-5cd3-ada6-200c9112f85f |  | textbox | Escutcheon
text | b73f9b1e-f9f5-5a8d-bde4-c7b723881b29 |  | textbox | Rcd cover
text | 0c9a4cec-f71a-5ea6-9395-1abbce010ede |  | textbox | Rcd cover lock 001
text | b68a23d7-7c87-586b-ae3b-48645b31758f |  | textbox | Door handle and tongue
text | 8786f4da-4a83-56ee-9312-c66bda04ba6b |  | textbox | 32 A 3 phase outlet
text | cc536e3f-a962-544a-af4b-e21137b0eaa1 |  | textbox | Connectors
text | 7336d684-a3cd-5759-8d0d-656c07065b09 |  | textbox | 15 A GPO
text | c318363c-6a5a-57e1-817a-bcac935d6cb0 |  | textbox | 10 A DGPO
text | 3302fa32-813d-59ac-b702-eb029d87b3ed |  | textbox | 63 A main switch
text | db4ae15c-4892-52bf-9092-e11ac7f4acda |  | textbox | 100 A main switch
text | 9e15a3d7-3ddd-536a-80aa-62b3201ea260 |  | textbox | 40 A 4 pole CB
text | 7b784095-58ab-5114-813c-3e30dab6a9aa |  | textbox | 32 A 4 pole CB
text | cb0c66ae-ab31-54f1-a070-7a6dcd126e1d |  | textbox | 16 A RCBO 1 pole
text | 972c274c-192c-548b-a231-1a2c55d99ae6 |  | textbox | 20 A RCBO 1 pole
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Temp Board completed to specification/drawings
label | 73ea5f87-0010-52ba-8a68-1e1fb5fc4d94 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 95ce9462-18b2-59ed-a25b-72f30c3519a2 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 1a2326f4-658b-5cdf-88c9-dfb9aaedccf3 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 9c1ac2ba-2261-519d-b88b-cbffa66e6a01 |  | textbox | Other (Specify here)
select | 746f6baf-dfcb-5da5-98ba-aedacfef4e85 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 2911a4c9-dab9-57b6-ae7b-969f49f93295 |  | textbox | Other (Specify here)
label | 9bce34b6-1c36-5332-ad11-5d7991f8a30c |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) |  |  |  | 722 | Yes | AE-ITCX-029 - Rough-In Checklist (Rev 1 +Names) | 62ffb1f9-c829-4f11-b00a-9973a8cd0c2b
checkpoint-status |  |  | checkpoint | Power
button | 684cb044-157f-534f-b6ba-17678375b2bf |  | button | Power circuits roughed in to the documented location and cable sizes in the field/riser/DB and labelled correctly? | Yes,No
button | c32e38ae-ae43-5042-a69c-ac64c8f29213 |  | button | Outlets within joinery/feature ceilings and walls have been coordinated so cables can be found later. | Yes,No
button | e97123a9-12df-5439-bbb7-8db4d6ef4f89 |  | button | Has steel framework been earthed appropriately? | Yes,No
label | 1163b769-2377-5311-bc86-19134ada4c84 |  | note | *Mandatory Image -Marked Drawing Including Title Block Revision
checkpoint-status |  |  | checkpoint | Lighting
button | 68aed9a2-6dc7-5a5d-aadf-bdef2b4ece64 |  | button | All cabling installed to the documented location in the field/riser/DB location and labelled correctly, including 2 way/int switching, smoke detector interlink & LED ELV cabling? Cables sizes have been checked, External Lighting and PE Cells | Yes,No
button | c19802b1-b870-5a2e-b634-acd785b4d365 |  | button | Plugbases/Quick connects fit off at rough in stage? | Yes,No
label | 6168d94e-1fa4-596d-a7ce-8ff7f8509567 |  | note | *Mandatory Image -Marked Drawing Including Title Block Revision
button | ea2bead5-eab1-57c4-98cd-0bc8905ff56e |  | button | Lighting control cabling installed to the documented location and zones and correct cable type used? Check cable is 240v rated or segregate? | Yes,No
button | 066b07a6-1273-5e9e-b040-7d95ac04bf49 |  | button | Confirm the maximum allowable of 55 dali addresses has not been exceeded? | Yes,No
label | 5ef07e0b-6df2-54b7-b88c-62a3343befbf |  | note | *Mandatory Image -Marked Drawing Including Title Block Revision add driver and puk locations is changed.
button | c2531f00-80f0-5e97-82a8-7b289436d052 |  | button | Timber noggins installed for large pendant lights? | Yes,No
label | b2bfb565-0c07-52ec-a585-f41175825123 |  | note | Optional - Additional Photos
checkpoint-status |  |  | checkpoint | MATV and Cat6/6A
button | e17f8417-c12f-5f28-9b14-ae82cbca5b95 |  | button | MATV cabling been installed to the documented location and labels reference shop drawing? | Yes,No
button | 92b8192c-9a62-5690-8c1c-f9ea534d95cb |  | button | MATV Splitter is fit off in ceiling inlcuding 2.5mm earth roughed and labelled to Distribution Board | Yes,No
button | df0aba1b-68d5-51ac-b12f-7b71af33f91a |  | button | Cat6/6A cabling installed to the documented location, including correct cable type and labeled as per shop drawing? Cables are spaced 50mm or segregated from 240V rough in. (In some cases this may include Intercom and CCTV Cat6/6A cables also) | Yes,No
label | af6a7116-5caf-5751-b513-de46c1db0a7f |  | note | Mandatory Photo - Accurate as wired drawings upon completion of fit off including variations, site changes?
label | 923ccf89-b800-547c-a382-8546afb3ad62 |  | note | Optional - Additional Photos
checkpoint-status |  |  | checkpoint | UPS
button | ddaba609-6210-5f86-bbea-86bf71c05273 |  | button | UPS circuits installed to the correct locations, and labelled correctly at the DB? | Yes,No
button | 441dbf00-f5a0-50c6-80dc-99a85f8c1085 |  | button | Mandatory Photo - Accurate as wired drawings upon completion of fit off? | Yes,No
label | a743d279-5045-520c-8fea-7ebeae39a371 |  | note | Optional - Additional Photos
checkpoint-status |  |  | checkpoint | Rough In completed to specification/drawings - Area left clean & tidy
label | 141b0106-89f1-5e8e-b0ac-ff5877979cf9 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | ded9385f-841b-5eb4-aff7-7fafa01659f3 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 1c2bf8e8-c3f2-5c0a-b74f-714786e9dad5 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | b8b07811-4c19-5915-9431-dbd7200acc3b |  | textbox | Other (Specify here)
label | 8697a7eb-76fb-59d3-b6b3-83d0e7804246 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-026 AS:3003- Appendix F Cardiac Protected CL (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-026 AS:3003- Appendix F Cardiac Protected CL (Rev 0 +Names) | 68979566-816a-4fd9-892c-4723f8e81736
checkpoint-group |  |  | section | Preface
checkpoint-status |  |  | checkpoint | Appendix F: Summary of Information - Pass once confirmed
label | fd329ea2-5097-53fb-8782-2f458493f832 |  | note | Routine inspection checklist for Cardiac-Protected electrical areas
label | db4bd06e-ecb0-59e5-ac17-3f926313cfd0 |  | note | .. ..
label | f44668af-a773-5349-8ee9-5a6040bd69fd |  | note | This checklist shall be used in accordance with Clause 8.3.7
label | 1b5d80bc-dc3c-51ca-bd92-9d7b20cc9428 |  | note | Note: The checklist may be in a different format and may be recorded electronically
checkpoint-group |  |  | section | Inspection & labelling
checkpoint-status |  |  | checkpoint | 8.3.1.1: Inspection - All electrical equipment and fittings in good condition
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Circuit identification visible and intact on each
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Relevant electrical points labelled to identify associated RCDs
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Circuit identification visible and intact on each LIM
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Relevant electrical points labelled to identify associated LIMs
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Overload monitors labelled with alarm setting
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Socket-outlets protected by RCD labelled 'RCD PROTECTED'
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Socket-outlets protected by isolating transformers labelled 'ISOLATING TRANSFORMER PROTECTED'
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Socket-outlets intended for cleaning purposes labelled 'CLEANING PURPOSES ONLY'
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Body-protected electrical area sign - Visible
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Body-protected electrical area sign - Labelled with current inspection date
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Body-protected electrical area sign - Labelled with identity of authorised person
checkpoint-status |  |  | checkpoint | 8.3.1.2: Labelling - Body-protected electrical area sign - Labelled with next test date
checkpoint-group |  |  | section | 8.3.1.3: Socket-Outlets
checkpoint-status |  |  | checkpoint | Socket-outlets coloured according to type of supply
checkpoint-status |  |  | checkpoint | If RCD protected, power-available indicator operational
checkpoint-status |  |  | checkpoint | Number of socket-outlets and permanently wired electrical equipment protected by RCD does not exceed 12
checkpoint-status |  |  | checkpoint | On indicator light operational, if present
checkpoint-status |  |  | checkpoint | Socket-outlets double-poled if protected by a transformer-isolated supply
checkpoint-status |  |  | checkpoint | All socket-outlets used for medical electrical equipment or installed below 2.3m protected by LPD
checkpoint-status |  |  | checkpoint | Confirm that when a fault is applied to each socket-outlet within patient area or within 5.0m of entrance of the patient area, the RCD trips
checkpoint-status |  |  | checkpoint | Confirm that when a fault is applied to each socket-outlet within patient area or within 5.0m of entrance of the patient area causes a response on LIM
checkpoint-status |  |  | checkpoint | Confirm that RCDs do not protect socket-outlets in another patient location
checkpoint-group |  |  | section | 8.3.2: Earthing
checkpoint-status |  |  | checkpoint | Confirm that the earth pins of all socket-outlets below 2.3m are earthed to less than 1.0-Ohm with respect to EP junction or node or other electrical equipment
checkpoint-status |  |  | checkpoint | Confirm that the earth pins of all socket-outlets within 5.0m of entrance to patient area are earthed to less than 1.0-Ohm with respect to EP junction or node or other electrical equipment
checkpoint-status |  |  | checkpoint | Confirm that all permanently wired electrical equipment with conductive parts below 2.3m are earthed to less than 1.0-Ohm with respect to EP junction or node or other electrical equipment
checkpoint-group |  |  | section | RCD
checkpoint-status |  |  | checkpoint | 8.3.3.2: RCD Sensitivity for Australia - Confirm that the RCD trips between 4.5-10.5 mA
checkpoint-status |  |  | checkpoint | 8.3.3.3: RCD Tripping times for Australia - Confirm this by carrying out at least two such tests
text | c9b3298d-ee1b-5439-8a79-01c99ad45dcf |  | textbox | Record the longest tripping time (ms)
checkpoint-status |  |  | checkpoint | 8.3.3.5: RCD Supply available indicators - Confirm that they are operational
checkpoint-status |  |  | checkpoint | 8.3.3.6: Audiovisual RCD Trip Indicators - If applicable, confirm that they are operational
checkpoint-group |  |  | section | 8.3.4.1: Prospective Hazard current
checkpoint-status |  |  | checkpoint | Ensure PHC is less than 2.00mA when no electrical equipment is plugged in
label | 88ec6f7d-1ad5-5fde-90b6-4ef7d33f9c27 |  | note | For routine testing, the PHC under normal conditions of operation shall be verified by applying the following process to each transformer Line Isolation Overload Monitor (LIOM)
checkpoint-status |  |  | checkpoint | All electrical equipment are disconnected from the supply
checkpoint-status |  |  | checkpoint | The current flowing through a low impedance ammeter connected between one isolated supply conductor and earth is noted
label | 060367f3-41a7-557a-8b06-35c8e2405fe7 |  | note | The test is repeated for the other isolated supply conductor. The larger of the noted values is the prospective hazard current. It shall be less than 2mA
checkpoint-status |  |  | checkpoint | The prospective hazard current of the supply is recorded in the commissioning checklist
checkpoint-group |  |  | section | 8.3.4.2: LIM Prospective Hazard Current Alarm
checkpoint-status |  |  | checkpoint | Confirm that the LIM alarms between 4.5-10.5mA
text | 42576272-c827-5440-86d5-7320981a432d |  | textbox | Record alarm current (mA)
checkpoint-group |  |  | section | 8.3.5: Overload Monitors
checkpoint-status |  |  | checkpoint | Confirm that a load of 110-120% of transformer rated current causes the alarm to activate in 3-5 Seconds
checkpoint-group |  |  | section | 8.3.6: Uninterruptible Power Supplies (UPS)
checkpoint-status |  |  | checkpoint | Confirm that UPS status indicator performance is routinely verified
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Checks completed to specification/drawings - Area left clean & tidy
label | cb0d0faa-ba64-5442-b680-f072b5560718 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | ade1ca0c-b278-5161-8580-b0b863ef4435 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 0821aedf-d997-515f-bc2e-03f632ba7909 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | ef3c2300-1925-5d9c-9bf1-c97078a17106 |  | textbox | Other (Specify here)
label | 2287b45f-1591-53a5-953f-24ed54dcc98a |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) |  |  |  | 26 | Yes | AE-ITCX-018 - DB Fit Off Sheet (Rev 0 +Names) | 6feb226f-3c32-4043-8d70-8ab261c6feba
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | aa4013cb-e62e-5044-adba-23574bd4e122 |  | textbox | Distribution Board No.
text | fc4a8519-01c2-5af0-9df9-5589289a356c |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | All screw terminations tight
label | a25d6b00-ab29-5a2d-982e-1023b4fcaa31 |  | note | With copper not visibly out of terminal
checkpoint-status |  |  | checkpoint | Neutrals correspond with actives
checkpoint-status |  |  | checkpoint | Pole fillers installed
checkpoint-status |  |  | checkpoint | DB door and escutcheon scratch and defect free
checkpoint-status |  |  | checkpoint | Switchboard labelled and cleaned
checkpoint-status |  |  | checkpoint | Cable entry points fire sealed
checkpoint-status |  |  | checkpoint | BMU circuits protected by a 100mA RCD
checkpoint-status |  |  | checkpoint | Correct lighting control equipment installed
checkpoint-status |  |  | checkpoint | Appselec 'installed by' sticker installed
checkpoint-status |  |  | checkpoint | Warning: Interrupting power supply will discharge emergency lighting batteries' installed next to RCBO feeding emergency lighting
checkpoint-status |  |  | checkpoint | Energy Meter been installed with CT metering
checkpoint-status |  |  | checkpoint | Wiring goes through the correct CT,
label | 1f89ef15-47e2-5ada-9ebf-b0fb60192237 |  | note | Installed in the correct direction and terminated to the correct phase
checkpoint-status |  |  | checkpoint | Wiring neatly loomed internally and externally of the DB
checkpoint-status |  |  | checkpoint | MANDATORY PHOTO 1 - Accurate DB schedule (Taken and Attached below)
label | 0e0f91d5-4429-58f8-b488-979678bf95b6 |  | note | Additional photos where required (Example - Lighting control schedule)
checkpoint-status |  |  | checkpoint | DB Fit-Off completed to specification/drawings - Area left clean & tidy
label | 387fd3a4-2514-5533-b00e-4f4977c85682 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | f41513f5-acf0-5d6d-8d5c-d063b8a40823 |  | note | Any Corrective Actions to be Photographed & Commented below
select | a5a5cc38-00ac-526c-8b68-6f43baf95032 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c2c4345a-0064-562c-858e-ea46fa7e5f37 |  | textbox | Other (Specify here)
label | 6d5f2e98-5c45-5253-b4d4-14cf43da8bd3 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) |  |  |  | 56 | Yes | AE-ITCX-020 - MATV Backbone Rough in, Testing & Panel Fit Off (Rev 0 +Names) | 70b7e7c0-3e5c-4bd9-bd5d-60858e0c71fb
checkpoint-group |  |  | section | No.1
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 1a1ccb45-e095-5f04-aac9-8bb89b07bffc |  | textbox | MATV Backbone Cable Type
text | d79e5f8d-d836-5648-be58-857a348ffe1a |  | textbox | From MATV Panel
text | 4afe61a2-bb45-5f74-a7e2-bbd847d6ad14 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.2
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 6df44e5e-ed2c-5164-9624-d7ae4ca2124b |  | textbox | MATV Backbone Cable Type
text | ec7565ed-254b-5d6e-86bc-df611eca5ba8 |  | textbox | From MATV Panel
text | 97a32cbc-7792-5049-a88e-0db6add1b964 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.3
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 09ed19af-260a-55d2-89eb-a13dc09dd5a3 |  | textbox | MATV Backbone Cable Type
text | 140df01d-ad89-52dd-934c-4f97fc335990 |  | textbox | From MATV Panel
text | ffe63677-0fcb-524b-b506-8a026bea337c |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.4
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 0dce6ef9-5736-51a6-93a8-934e6fd2c323 |  | textbox | MATV Backbone Cable Type
text | 6edd7426-c4ba-5bbd-96c8-51d4eb9bb6cf |  | textbox | From MATV Panel
text | 99788ad2-4391-554a-8dae-89dbe8cd4ce0 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.5
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 80a6b9a8-bff3-55f8-bfeb-174a33afcbdc |  | textbox | MATV Backbone Cable Type
text | cdffc667-64a4-5520-9c6a-76915220aa28 |  | textbox | From MATV Panel
text | 996f8216-8291-5e7f-a690-9a298a7a2f06 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.6
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 351c37e9-acac-5261-80e9-3ecaf7fc0a79 |  | textbox | MATV Backbone Cable Type
text | 15b23aab-c0c4-5465-b45a-8cf6d238eeee |  | textbox | From MATV Panel
text | 442523c3-5570-5c94-8106-7268be7ff5bf |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.7
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 5bd57b8c-44df-50ff-a2fc-d5a2bb46af1f |  | textbox | MATV Backbone Cable Type
text | 23a67f93-74b7-5f78-b127-72837e1add7e |  | textbox | From MATV Panel
text | a618f5c5-4279-5184-a55e-c9704eb22f17 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.8
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 2f01963c-4fa1-5c96-a1c0-23066bb6731c |  | textbox | MATV Backbone Cable Type
text | f1b06675-77e6-56e2-9b04-fc75feee91cf |  | textbox | From MATV Panel
text | e6c6f858-540e-5e63-954d-420ecee0e59e |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.9
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | c2b6d770-cd6c-5170-b699-fd8a18e5d6a6 |  | textbox | MATV Backbone Cable Type
text | 421eb7f0-4c4a-5133-96c4-5640d0f37d05 |  | textbox | From MATV Panel
text | 70664369-1ba3-5e37-9242-c5d781a5fefe |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | No.10
checkpoint-status |  |  | checkpoint | MATV Backbone Instalaltion completed
text | 43d0b0e8-eb82-59b8-8de3-956fdf72a343 |  | textbox | MATV Backbone Cable Type
text | d840929a-092f-54f7-b2d2-ddb1d0f9f5c0 |  | textbox | From MATV Panel
text | 68a8e31e-8e4e-5fd4-bd15-b88a080fd176 |  | textbox | To MATV Panel
checkpoint-status |  |  | checkpoint | Tested and Labelled
checkpoint-status |  |  | checkpoint | MATV Panel Installed (Level)
checkpoint-status |  |  | checkpoint | MATV Panel Fit-Off Completed
checkpoint-status |  |  | checkpoint | MATV Panel Labelled
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Backbone Works completed to specification/drawings - Area left clean & tidy
label | cc4a7c66-3d95-5d9f-80ca-8c040ab24f1a |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
select | c5ca68fe-fda5-58a4-ac1f-829fca074041 |  | dropdown | Backbone by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 66c1e1ed-abf1-5faa-ac0f-d98accfd1fa2 |  | textbox | Other (Specify here)
text | 11d6e36c-62cc-550b-817f-ff6502a023ad |  | textbox | Witnessed by
label | 0b439af2-c2d9-57eb-9e43-839bf6d788b5 |  | note | Signature Sign-Offs - Attach signature(s) below
label | e7813e87-356e-5619-ac1c-996592a47732 |  | note | .. ..
select | 38118056-0e4a-534b-ab6d-ff1098ddbca1 |  | dropdown | Panel Fit-Off by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 606877f8-24e4-5f64-aa5e-8f2ab2fa9e4c |  | textbox | Other (Specify here)
text | bcb563a9-f8a8-5355-a838-dbd3ca6bb115 |  | textbox | Witnessed by
label | dddab27b-acb6-50e4-be15-b118cc46c0fb |  | note | Signature Sign-Offs - Attach signature(s) below
label | 5a44202f-eb04-54e1-b4ec-8112af48db9b |  | note | .. ..
select | 4baa6e26-d6be-577d-8dc4-b4f5c3d06a38 |  | dropdown | Testing by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | a7696a87-6274-562f-8119-f199124bc91b |  | textbox | Other (Specify here)
text | 5f3f8e12-da36-524c-b8af-4b699af92bb5 |  | textbox | Witnessed by
label | 50cbcba5-363f-588e-832e-ce1cf10ded2d |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-027 AS:3003-Table B1 Patient Area CL (Rev 0) |  |  |  | 0 | Yes | AE-ITCX-027 AS:3003-Table B1 Patient Area CL (Rev 0) | 72e152c3-c2bf-458a-af16-305041b022fc
checkpoint-group |  |  | section | Preface
checkpoint-status |  |  | checkpoint | Appendix B: Summary of Information - Pass once confirmed
label | 0d432b3b-e9a2-553c-8889-31f78f583913 |  | note | Commissioning Inspection Checklist
label | 8097111e-af92-5fb5-a159-3abb2670d77d |  | note | .. ..
label | 1d25f73e-3ce0-508a-a87d-b549ec712409 |  | note | B1: General
label | 44db9954-f18b-5618-b7f4-9909ea21574f |  | note | This Appendix sets out a checklist for electrical area installations in accordance with this standard
label | 57a79a0a-cfd9-56e5-b933-143a2b12a6fb |  | note | All body-protected and cardiac-protected electrical areas shall be in accordance with this Standard by the use of a commissioning checklist
label | f06b8e2c-1ced-5e51-beb3-970581c621ec |  | note | The commissioning results may be recorded electronically, on paper, or other similar medium. The commissioning checklist shall be retained by the person conducting the tests and a copy provided to the responsible organisation/entity. NOTE:This checklist can also be used for special patient areas as specified in Section 5
label | f8ab7cf2-2f9f-5341-9bca-0e6d8f33efa1 |  | note
label | 1d0cd41b-6950-5664-9ff1-724cd400b82f |  | note | .. ..
label | 16e0d43e-a9a4-51c6-8d4a-2acaea354d9e |  | note | B2: Commissioning Inspection Checklist for Patient Areas
label | 59d781b4-3978-54ed-a319-534e892c205d |  | note | A checklist shall be developed to record the results for each patient area commissioned, in accordance with each of the required clauses of this Standard
label | 4837485b-08a3-593b-a62e-cbcb2f9fcc00 |  | note | The checklist shall be in English, and shall clearly record the result for each item. NOTE: Checked boxes with a 'Pass' or 'Fail' or 'N/A' would satisfy this requirement
label | 4642e8fc-8b5c-5a52-b445-7a5219282de0 |  | note | .. ..
label | db719867-ef3e-53da-b8b2-77c4a5f1d086 |  | note | B3: Commissioning Checklist
label | d8dfde2d-49b2-5a87-b555-b68bfbbfafaa |  | note | The information in Table B1 shall be included in the commissioning checklist and have a result recorded against each item
checkpoint-group |  |  | section | 2.1: General Requirements for Body-Protected and Cardiac-Protected Electrical Areas
checkpoint-status |  |  | checkpoint | 2.1 - All locations that form part of the current works and which it is intended that low-voltage medical electrical equipment will be used in contact with patients and can be operated while connected to the electrical supply mains (except in emergencies) are checked to confirm that they are signposted as body-protected or cardiac-protected electrical areas
label | eb9e2211-0156-5268-9987-f115b03674ec |  | note | Where there is doubt about the intended use of a particular location, formal clarification should be sought from the responsible organisation
label | d1e91ea0-3b45-52fc-8cb5-a925839cde85 |  | note | If an area is not required to be wired as a patient area a letter stating that mains operated medical electrical equipment will not be used within that area should be provided by the responsible organisation
checkpoint-status |  |  | checkpoint | 2.1 - Cardiac-protected and body-protected electrical areas not in the same room
checkpoint-group |  |  | section | Classification of Patient Areas
checkpoint-status |  |  | checkpoint | 2.2.3 - Only those specified areas are wired as cardiac-protected
checkpoint-status |  |  | checkpoint | If others nominated, then confirm documentation outlining specific requirements is provided by responsible organisation
checkpoint-status |  |  | checkpoint | 2.2.4 - Patient areas not wired as cardiac-protected electrical areas are wires as body-protected electrical areas
checkpoint-status |  |  | checkpoint | All patient ensuites, bathrooms, shower rooms and toilets wired a body-protected electrical areas
checkpoint-group |  |  | section | Low-Voltage A.C. Supplies
checkpoint-status |  |  | checkpoint | 2.4.1.1 - Confirm that electrical final sub-circuits are unique to respective rooms in body-protected electrical areas
checkpoint-status |  |  | checkpoint | Ensuite in adjoining room may share final sub-circuit
checkpoint-status |  |  | checkpoint | Confirm that cleaning outlets are on a separate electrical sub-circuit to other socket-outlets in the room
checkpoint-status |  |  | checkpoint | 2.4.1.2 - Confirm that electrical final sub-circuits are unique to respective rooms in cardiac-protected electrical areas
checkpoint-status |  |  | checkpoint | 2.4.1.3 - Final sub-circuit for socket-outlets identified 'CLEANING PURPOSES ONLY' supplies no other socket-outlets
checkpoint-status |  |  | checkpoint | 2.4.2 - Confirm conformance with AS/NZS:3000 for protection against mechanical damage
checkpoint-status |  |  | checkpoint | 2.4.3.2.1 - Confirm by inspection and testing that al socket-outlets specified are protected by LPD (except those exempted)
checkpoint-status |  |  | checkpoint | 2.4.3.2.2(a) - Socket-outlets that are accessible in patient areas without using a key or tool
checkpoint-status |  |  | checkpoint | 2.4.3.2.2(b) - Excludes multi-phase outlets conforming with AS/NZS:3123
label | 53a08f34-f7fb-598e-b0ef-e60fad51a683 |  | note | Socket-outlets conforming with AS/NZS:3112 that are located within 2.0m of the entrance to a body-protected electrical area and are accessible without the use of a key or tool in any room, corridor, etc., opening directly off a patient area
checkpoint-status |  |  | checkpoint | Socket-outlets conforming with AS/NZS:3112 that are located within 5.0m of the entrance to a cardiac-protected patient area and are accessible without the use of a kay or tool in any room, corridor, etc., opening directly off a patient area
checkpoint-status |  |  | checkpoint | 2.4.3.2.2(c) - Socket-outlet(s) installed outside the patient area but used to supply medical electrical equipment used within the patient area
checkpoint-status |  |  | checkpoint | 2.4.3.2.3 - LPD protection not required for permanently installed pendant-type sockets that will not accept common 10 or 15A plugs conforming to AS/NZS:3112
checkpoint-status |  |  | checkpoint | LPD protection required for socket-outlets that are mounted on, and form part of, a permanently installed medical system provided that such socket-outlets are clearly intended to power specified component parts of the medical electrical system
checkpoint-status |  |  | checkpoint | LPD protection not required for socket-outlets specifically intended for clocks
checkpoint-status |  |  | checkpoint | 2.4.3.2.2(a) - LPD protection not required for socket-outlets that are mounted on the ceiling or above 2.3m on the wall, and are clearly intended for permanently mounted plug-in equipment other than medical electrical equipment
checkpoint-status |  |  | checkpoint | 2.4.3.3 - LPD protection provided for permanently wired medical electrical equipment with Type B applied parts, consisting
boolean | 9bb1c2fb-c090-5846-abed-7f1008f24e47 |  | tickbox | Electrodes or transducers that contact patients
boolean | 2c48c4fc-df2f-5f56-b9ce-23b0cdb36100 |  | tickbox | Parts that enter patients
boolean | 61bf0418-f239-5871-a139-5ffcdddb9513 |  | tickbox | Parts that contact liquid in patients
button | 7c8c6de6-806f-52d2-9de5-5a8389b1c260 |  | button | Other permanently wired electrical equipment is protected as required by AS/NZS:3000 | Pass, Fail, N/A
checkpoint-status |  |  | checkpoint | 2.4.4.1 - Where the switchboard from which the UPS is to be supplied contains an essential supply of sufficient capacity the UPS is connected to that essential supply
checkpoint-status |  |  | checkpoint | 2.4.4.2 - Where the output circuit of the UPS is earth-free in every mode of operation, the UPS is treated as an isolation transformer and provided with a LIM
checkpoint-status |  |  | checkpoint | Where one output terminal of the UPS is connected to the neutral input terminal earthed within the UPS, the output is protected by RCD or isolated supply
checkpoint-status |  |  | checkpoint | 2.4.4.3 - A suitably located UPS status indicator is provided where socket-outlets or permanently wired equipment are connected to a UPS and there is continuous patient observation
checkpoint-status |  |  | checkpoint | Confirm that the alarm/indicator operates as intended
checkpoint-group |  |  | section | Low-voltage D.C. Supplies
checkpoint-status |  |  | checkpoint | 2.5 - Reticulated low-voltage D.C. - Confirm that they are earth-free and measure current
text | de7805f7-3194-5bba-a2a6-7787d8da8708 |  | textbox | Current
checkpoint-group |  |  | section | Access to Controls & Indicators
checkpoint-status |  |  | checkpoint | 2.6 - Confirm that Controls & Indicators are readily accessible
checkpoint-status |  |  | checkpoint | Confirm that Controls & Indicators, depending on the location of socket-outlets or permanently connected equipment requiring LPD protection, located in accordance with Table 2.1
checkpoint-status |  |  | checkpoint | Confirm that Controls & Indicators, Not mounted under benches, within cupboards or cabinets, or behind bulky equipment in such manner as to inhibit easy access to the controls and indicators
checkpoint-status |  |  | checkpoint | Confirm that Controls & Indicators, if mounted ne the entrance of a room, separated by at least 500mm from any wall-mounted light switch
checkpoint-status |  |  | checkpoint | The above checked requirements do not apply to RCDs protecting socket-outlets that are identified 'CLEANING PURPOSES ONLY' in accordance with Clause 2.7.3 or RCDs mounted in ensuite vanities
checkpoint-group |  |  | section | Socket-Outlets
checkpoint-status |  |  | checkpoint | 2.7.2 - Socket-outlets that are not readily accessible and are not protected by a dedicated LPD are provided with a separate readily accessible isolating double-pole switch
checkpoint-status |  |  | checkpoint | 2.7.3.1 - In body-protected electrical areas, confirm socket-outlet identified 'CLEANING PURPOSES ONLY' within 15.0m of any point in the patient area
checkpoint-status |  |  | checkpoint | In cardiac-protected electrical areas, confirm socket-outlet identified 'CLEANING PURPOSES ONLY' within the patient area
checkpoint-status |  |  | checkpoint | 2.7.3.2 - Socket-outlets that are identified 'CLEANING PURPOSES ONLY' are protected by LPDs that do not protect any other type of socket-outlet
checkpoint-status |  |  | checkpoint | 2.7.4 - Correct labelling is used
checkpoint-status |  |  | checkpoint | 2.7.4.1 - Socket-outlets protected by LPD are labelled 'From RCDX' or 'From LIMX', depending on whether the LPD is an RCD or isolated supply
checkpoint-status |  |  | checkpoint | 2.7.4.2 - Confirm 'ON' indication of socket-outlet switch
checkpoint-status |  |  | checkpoint | 2.7.4.3 - Confirm socket-outlets connected to a normal (mains) supply are colour-coded white
checkpoint-status |  |  | checkpoint | Confirm socket-outlets connected to an essential supply are colour-coded red
checkpoint-status |  |  | checkpoint | Confirm socket-outlets connected to an uninterruptible supply are colour-coded dark blue
checkpoint-status |  |  | checkpoint | Confirm socket-outlets identified 'CLEANING PURPOSES ONLY' are colour-coded beige
checkpoint-status |  |  | checkpoint | 2.7.4.4 - Confirm indicator colour and operation
checkpoint-status |  |  | checkpoint | 2.7.5 - Confirm each socket-outlet is individually switched
checkpoint-status |  |  | checkpoint | Confirm if socket-outlet supplied from isolated supply then it is double poled
checkpoint-group |  |  | section | Residual Current Devices (RCDs)
checkpoint-status |  |  | checkpoint | 2.8.1 - Confirm Type1 RCDs in use
checkpoint-status |  |  | checkpoint | Confirm RCD sensitivity using tests in this Standard (and record results)
text | 6bd02669-e559-5992-b92f-85301eb9d8dd |  | textbox | RCD result
checkpoint-status |  |  | checkpoint | Confirm RCD maximum tripping time using tests in this Standard (and record results)
text | f686f1a8-0db2-57ea-a08c-85a999ada16b |  | textbox | RCD result
checkpoint-status |  |  | checkpoint | Check cClauses 8.2.3.2 and 8.2.3.3 for body-protected areas or Clauses 8.3.4.2 and 8.3.4.3 for cardiac-protected areas
checkpoint-status |  |  | checkpoint | 2.8.2 - Confirm by inspection and testing that there are no RCDs protecting other RCDs
checkpoint-status |  |  | checkpoint | 2.8.1 - Confirm by testing that all RCDs are double poled
checkpoint-status |  |  | checkpoint | 2.8.3 - Confirm that RCDs that are used as LPDs do not protect the supply to the below
boolean | a3f69cf8-7441-5edf-80b1-75f205efdf1c |  | tickbox | More than 12 electrical points, i.e. socket-outlets, items of permanently-wired equipment or combinations thereof
boolean | 436925d1-8ac0-516d-8372-d577e7a0f683 |  | tickbox | Socket-outlets in different rooms
boolean | 4accb6a5-3485-5cc7-a630-4705e9d14f02 |  | tickbox | Socket-outlets in a a patient area and socket-outlets in an area that is not a patient area except, if applicable, for socket-outlets mounted in the ceiling space of a patient area in accordance with Clause 2.4.3.2(iii)
checkpoint-status |  |  | checkpoint | 2.8.4 - Confirm indicator colour and operation of power available indicator of RCDs used as LPDs
checkpoint-status |  |  | checkpoint | 2.8.5 - Confirm by inspection that each RCD is labelled to identify distribution board and circuit breaker, and with unique identifier, e.g. RCD X
checkpoint-status |  |  | checkpoint | 2.8.7 - Confirm that separate test facility is provided for RCD used as LPD when connected to permanently wired equipment
checkpoint-group |  |  | section | Low Voltage Isolated Supplies
checkpoint-status |  |  | checkpoint | 2.9.1 - Confirm isolation transformer LIM and overload monitor are correctly labelled that they conform with AS/NZS:4510
label | 7a2e7ee0-f955-5fd1-b9c4-d10445b3410f |  | note | 2.9.2 - Confirm by examining the location, housing and ventilation of the isolation transformer
checkpoint-status |  |  | checkpoint | In cardiac-protected electrical areas, confirm that isolation transformer only supplies one patient location
label | 42ab3156-94a4-596d-99a6-38a968a3bb45 |  | note | 2.9.3 - See to Clause 2.9.3
checkpoint-status |  |  | checkpoint | 2.9.4 - Confirm overload monitor by inspection and testing using tests in this Standard (and record results)
text | dc9e4211-ec89-557b-8917-c9de738574f6 |  | textbox | RCD result
checkpoint-status |  |  | checkpoint | 2.9.5 - Confirm LIM prospective hazard current display and current alarm using tests in this Standard (and record results)
text | 12d9c96f-328d-55b8-a828-6727f6d1bf41 |  | textbox | RCD result
checkpoint-status |  |  | checkpoint | Confirm by inspection that labelling is consistent and identifies circuit and LIM
label | a238345a-f8ee-5c2f-9cda-33bdb599aa77 |  | note | See to Clause 2.9.3
checkpoint-status |  |  | checkpoint | 2.9.6 - Confirm prospective hazard current of each transformer-isolated supply does not exceed 2mA
checkpoint-status |  |  | checkpoint | For commissioning, the PHC under normal conditions of operation shall be confirmed by applying the following process to each transformer Line Isolation Overload Monitor (LIOM)
boolean | b6ac45fc-4824-5a1a-8f2c-fa28071285f0 |  | tickbox | All electrical equipment are disconnected from the supply
boolean | a9de1f70-0f78-5405-96a2-86f823809da6 |  | tickbox | The current flowing through a low impedance ammeter connected between one isolated supply conductor and earth is noted. The test is repeated for the other isolated supply conductor. The larger of the noted values is the prospective hazard current. It shall be less than 2mA
boolean | 89a5e62e-139a-5c5e-9645-57b3fca08976 |  | tickbox | The prospective hazard current of the supply is recorded in the commissioning checklist
checkpoint-status |  |  | checkpoint | 2.9.7 - In body-protected electrical areas, confirm that the number of socket-outlets protected by isolated supply does not exceed 12
checkpoint-status |  |  | checkpoint | In cardiac-protected electrical areas, confirm that the number of socket-outlets protected by isolated supply does not exceed 12
checkpoint-status |  |  | checkpoint | 2.9.8 - Confirm that a test facility is provided if permanently wired equipment is protected by an individual isolated supply
checkpoint-group |  |  | section | Isolation Switches
checkpoint-status |  |  | checkpoint | 2.10 - Confirm that a separate individual readily accessible switch(s) has been provided for the below
boolean | 05cc23a8-19b7-5fe6-afed-39332bc96d82 |  | tickbox | For conductors that supply an inaccessible socket-outlet that is protected by an LPD
boolean | 55e69100-a16b-5229-8dec-42bb1b87da44 |  | tickbox | To permanently wired electronical equipment that is connected to an LPD that also protects socket-outlets
checkpoint-status |  |  | checkpoint | Confirm correct labelling of the switch
checkpoint-group |  |  | section | Identification
checkpoint-status |  |  | checkpoint | 2.12.1 - Confirm labelling is of the correct format and size and placed in correct location
checkpoint-status |  |  | checkpoint | 2.12.2 - Confirm patient area signage installed in correct location and appropriate labels attached and signed
checkpoint-group |  |  | section | Testing & Verification of Electrical Work
checkpoint-status |  |  | checkpoint | 2.13 - To confirm that requirements of this Standard have been met, after completion, but before being placed in service, the installation shall be as per below
boolean | 133846f0-365f-5178-9bcd-711269868116 |  | tickbox | Inspected as far as is practicable
boolean | cad6d881-3996-5a4f-95e3-58347cf75f93 |  | tickbox | Tested and confirmed in accordance with Appendix B of this Standard and AS/NZS:3000
checkpoint-group |  |  | section | Additional Documentation
checkpoint-status |  |  | checkpoint | 2.14 - Confirm commissioning checklist in accordance with Appendix B
checkpoint-status |  |  | checkpoint | 3.2 - Additional requirements for body-protected electrical areas - Earthing
label | cff11fd7-6a3d-5c89-801e-02631a20cb9a |  | note | Confirm conformance with AS/NZS:3000
checkpoint-status |  |  | checkpoint | 4.2 - Additional requirements for cardiac-protected electrical areas - Earth-Free ELV
label | 978e87af-fe99-5c41-a1c5-ccf0b8e6b872 |  | note | Confirm that no more than 10mA can flow to earth
checkpoint-status |  |  | checkpoint | 4.3 - Disposition of electrical points controlled by LPDs
label | ee3de247-24c7-5db8-aaa6-6465bebda825 |  | note | Confirm by tripping all RCDs in a particular patient location, to confirm that socket-outlets in any other patient location(s) are not protected
checkpoint-group |  |  | section | Earthing & Equipotential Bonding
checkpoint-status |  |  | checkpoint | 4.4.1 - Confirm earthing has been carried out in accordance with the requirements of this Clause and the requirements of AS/NZS:3000
checkpoint-status |  |  | checkpoint | The minimum size of any protective earthing system conductor shall be not less than that required by AS?NZS:3000
checkpoint-status |  |  | checkpoint | The minimum size of any EP bonding system conductor associated with the fixed wiring installed on site shall be 4mm2
checkpoint-status |  |  | checkpoint | 4.4.2.3 - Confirm by inspection that only one EP junction is in use
checkpoint-status |  |  | checkpoint | 4.4.2.4.1 - Confirm by inspection and testing that the resistance of the earthing conductor between each socket-outlet and EP junction or node is <=0.1 Ohm For the below
boolean | 8c215a3c-0164-5bb2-81d4-08493498faaf |  | tickbox | Socket-outlets within cardiac-protected electrical area
boolean | c968cf68-26d1-5d6a-a595-7117e360468e |  | tickbox | Socket-outlets within specified distance of entrance to cardiac-protected electrical area
boolean | fc688285-dbd9-549e-a439-51842a767219 |  | tickbox | Socket-outlets in another room/ceilings for medical electrical equipment with conductive parts accessible within cardiac-protected electrical area
checkpoint-status |  |  | checkpoint | Confirm protective earthing conductors are insulated and segregated from other conductive items
checkpoint-status |  |  | checkpoint | Confirm the below by inspecting and testing
boolean | 0417ed49-780c-5fc4-971e-921f4c8f6d31 |  | tickbox | Each node is individually connected to the EP junction by insulated conductors with a maximum resistance of 0.01 Ohms
boolean | 268473ba-69ce-50d2-af3f-f8a1d16bc04a |  | tickbox | Each node is accessible and its location identified by labelling
boolean | 9801f3fb-321f-5b31-86c7-2f6a2de5b03b |  | tickbox | Each node is fully insulated or isolated from contact with structural metal
boolean | a04b1b22-4b3d-574f-ae17-ece52b9006ec |  | tickbox | Each node is numbered and identified to identify the location of the EP junction
boolean | a797c100-049f-5f6e-a969-520c15a57d64 |  | tickbox | 4.4.1 - Confirm earthing has been carried out in accordance with the requirements of this Clause and the requirements of AS/NZS:3000
boolean | 85a5f91d-3f29-51d6-908b-6f7ca6b09b48 |  | tickbox | The EP junction is identified to identify the number of nodes connected
checkpoint-status |  |  | checkpoint | 4.4.2.4.1 - Confirm inspection and testing that the following socket-outlets conforming to Clause4.4.2.4.1 are connected to an EP junction or node
checkpoint-status |  |  | checkpoint | All socket-outlets that are accessible anywhere in the cardiac-protected electrical area without using a key or a tool, including those that are mounted on permanently installed electrical equipment and are available for general use
checkpoint-status |  |  | checkpoint | All socket-outlets that conform with AS/NZS:3112 or AS/NZS:60884.1, or both, and are located within 5.0m of the entrance to the cardiac-protected electrical area and accessible without the use of a key or tool in any room, corridor, etc,., opening directly off the cardiac-protected electrical area
checkpoint-status |  |  | checkpoint | Confirm that these outlets are only connected by one EP earthing system
checkpoint-status |  |  | checkpoint | Socket-outlets that are installed outside cardiac-protected electrical area but are used to supply medical electrical equipment
checkpoint-status |  |  | checkpoint | 4.4.2.4.1 - Confirm earthing in accordance with AS/NZS:3000
boolean | 0d80e72f-caba-5dec-8605-766e2745648a |  | tickbox | Permanently installed cord extension sockets that are part of a medical electrical equipment system and will not accept common 10A plugs
boolean | 2140342e-7e02-56e5-98ee-9763810b1252 |  | tickbox | Earth pin of socket-outlets for clocks
checkpoint-status |  |  | checkpoint | 4.4.2.4.2 - Confirm that the protective earthing conductors used to connect socket-outlets to the EP junction or node is insulated and segregated from contacting other conductive items except at the EP junction
checkpoint-status |  |  | checkpoint | Check the resistance between the earth pin of the socket-outlet and the EP junction or node is <+0.1 Ohms using a four-wire milliohm measuring device
checkpoint-status |  |  | checkpoint | 4.4.2.5 - Confirm by inspection and measurement that the following (if within patient environment) are directly earthed to the EP junction or node with a resistance of <+0.1 Ohms:
boolean | 409e81fa-32e5-53e6-ade3-291e6dabdee6 |  | tickbox | The protective earthing terminal of permanently installed Class1 electrical equipment that is accessible within patient environment
boolean | c359f6ac-ab2f-56a5-a99d-a8c7e986b4d1 |  | tickbox | Metal enclosure containing socket-outlets
checkpoint-status |  |  | checkpoint | 4.4.2.6 - Confirm by inspection and measurement that the following (if within patient environment) and measure <1 Mega Ohm with respect to the EP junction or node are directly earthed to the EP junction or node with a resistance of <=0.1 Ohms
checkpoint-status |  |  | checkpoint | Medical gas outlets and water taps contact reticulated metal services such as medical gas, water or drainpipes, the reticulated metal services etc
checkpoint-status |  |  | checkpoint | Accessible fittings such as hinged window frames or lift-out air-conditioning registers, etc
checkpoint-status |  |  | checkpoint | 4.4.2.7 - Confirm inspection (except for EP junctions) that all joints are as per below
boolean | e7722c8d-9af8-50d8-87a5-44d1c3c54b71 |  | tickbox | Fully insulated or isolated from contact with structural metal
boolean | 9ced8520-e25e-524a-80cc-520594bfcc5c |  | tickbox | Effected so that conductors forming part of the equipotential earthing systems are not joined in tunnel connectors in which a single screw bears directly on the conductors
checkpoint-status |  |  | checkpoint | 4.4.2.8 - Confirm where EP junction is readily accessible within the cardiac area it is identified
boolean | 774872f9-cd08-5320-9d5b-58553058b5c8 |  | tickbox | EP Test Point
boolean | 0bd35715-9306-5280-953d-6133beffbd30 |  | tickbox | 0.1 Ohm Ep Earthing System
boolean | e55e1554-3eae-5c56-861c-08c5eb7d1baf |  | tickbox | EP Junction
checkpoint-status |  |  | checkpoint | 4.4.2.9 - Confirm where the EP junction is not readily accessible in the cardiac-protected electrical area, a test facility is provided as per below
boolean | 32a48f9c-4e76-5c86-8885-9564b6de1972 |  | tickbox | Isolated from structural steel
boolean | c8aa960c-6969-5d6c-af80-04ba446861fd |  | tickbox | Identified 'EP Test Point'
boolean | eb8bc35f-8c5e-561e-b168-6e20488d4e94 |  | tickbox | Identified '0.1 Ohms EP Earthing System'
boolean | 8cd00b94-ed66-5339-ad9f-1da9c491b4b2 |  | tickbox | Indicates the location of the EP junction
checkpoint-status |  |  | checkpoint | 4.4.2.10 - Confirm that the EP test terminal between EP junction or node has resistance of <+0.01 Ohms
checkpoint-status |  |  | checkpoint | Confirm that the EP test terminal is not used for any other purpose
checkpoint-status |  |  | checkpoint | Confirm that the EP test terminal has separate individual return earths
checkpoint-status |  |  | checkpoint | 4.4.3 - Confirm return to earth distribution board supplying the cardiac-protected electrical area
checkpoint-status |  |  | checkpoint | Confirm each return earth is labelled correctly at the EP junction and the distribution board
checkpoint-status |  |  | checkpoint | Confirm each EP junction has separate individual return earths
checkpoint-group |  |  | section | Alterations & Repairs to Electrical Installations in Patient Areas
checkpoint-status |  |  | checkpoint | 6.2.1 - Confirm that every alteration of the electrical installation in an existing patient area conforms with all relevant provisions of the Standard
checkpoint-status |  |  | checkpoint | 6.2.3 - Confirm inspection within the last 12 months before carrying out any alterations
checkpoint-status |  |  | checkpoint | Confirm in-service sticker is current
checkpoint-status |  |  | checkpoint | 6.2.4 - Check % increase in socket-outlets. If 10% or more increase, then verify all socket-outlets in patient area conform with colour requirements
checkpoint-status |  |  | checkpoint | 6.2.5.1 - Confirm EP wiring system as per below
boolean | 75f53766-fc2c-58fa-9748-90a9c92ab1e8 |  | tickbox | EP junction accessible
boolean | b72a9d30-47d1-58d5-bbf9-c114b1765ea8 |  | tickbox | EP test point labelled
checkpoint-status |  |  | checkpoint | Confirm the rating of the new fixed electrical equipment
checkpoint-status |  |  | checkpoint | 6.2.5.2 - Conformance is checked by confirming or actioning Items (a) to (c) of Clause 6.2.5.1
checkpoint-status |  |  | checkpoint | 6.2.5.3 - For the reclassification of a cardiac-protected electrical area to a body-protected electrical area, verify the below
boolean | c0f5f04c-6494-555e-ac86-3494d12f1923 |  | tickbox | Conformance with Sections 2 & 3, except that, the requirement of Clause 2.4.1.3 for a claner's outlet to have a dedicated circuit need not apply
boolean | 5a84023b-cc24-52bc-bdeb-83a4228002f2 |  | tickbox | All EP studs or EP receptacles removed
boolean | b6c38da5-8236-56f6-a5d6-d449b4bc7923 |  | tickbox | Re-certification as a body-protected electrical area in accordance with Clause 2.13
boolean | 948b20c4-2969-5bb2-a1eb-a088984c8c1b |  | tickbox | Identification in accordance with Clause 2.12
checkpoint-group |  |  | section | Repairs
checkpoint-status |  |  | checkpoint | 6.3.1 - If the patient ares is not sign posted as a cardiac-protected electrical area or a body-protected electrical area, the repairs may only be completed when the patient area meets the requirements of this Standard
checkpoint-status |  |  | checkpoint | 6.3.2 - Confirm that the repair is only an equivalent fitting replacement and not the replacement for the fixed electrical equipment
checkpoint-group |  |  | section | 7.1, 7.2. 7.3 - Identification of Patient Areas
checkpoint-status |  |  | checkpoint | Confirm that sign is correct size, affixed in correct location, correctly completed, dated and sighted and the tester clearly identified
checkpoint-status |  |  | checkpoint | Where alterations have occurred, confirm addition of label stating this and indicating the date, name and organisation responsible
checklist-sectioned |  |  | checklist | AE-ITCX-34 - Communications/Security Rack Installation QA (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-34 - Communications/Security Rack Installation QA (Rev 0 +Names) | 763bdf75-35c4-4e73-8be4-ba3ea54c8731
checkpoint-group |  |  | section | Communications Rack
checkpoint-status |  |  | checkpoint | Is the communications riser ready for communications rack installation
label | 4dfc664d-c0a8-559f-9202-2419a7a4cc8d |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
label | 0c03dd16-e798-578a-97fa-ff984fdb8243 |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Does the communications rack match the approved technical data
checkpoint-status |  |  | checkpoint | Has the communications rack been installed in position as per the Appselec communications riser elevation shop drawings and floor plan layout
text | c96311d8-ec8d-5bb3-8dc6-ba991ed050b7 |  | textbox | Drawing & Revision # (or Attach photo below)
checkpoint-status |  |  | checkpoint | Has the communications rack been fixed to the floor using appropriate fixings
checkpoint-status |  |  | checkpoint | Are the doors and side panels installed and free from damage
checkpoint-status |  |  | checkpoint | Does the communications rack comply with all the relevant clearances
label | bfc847ac-97b2-5410-8b40-85a2308d1ac2 |  | note | Are door swings and access to the communications rack unobstructed
checkpoint-status |  |  | checkpoint | Has the communications rack been permanently labelled with a traffolyte label or similar on the door
label | 0aedff3b-23b4-5369-b693-273576dca182 |  | note | Check that the label matches the communications rack layouts
checkpoint-status |  |  | checkpoint | Has the Appselec label/logo been fixed to the front of the communications rack
label | da305366-e946-58fd-ae89-269304c4d731 |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-group |  |  | section | Communications Earthing Terminal (CET)
checkpoint-status |  |  | checkpoint | Has a CET been installed adjacent to/or within the communications rack and has a 6 mm2 green/yellow earth cable been terminated to the CET
label | 26acad4e-a619-55a2-9632-e6438f3834db |  | note | Refer to Communications SLD for earth cabling schematic
label | b974b2a4-1153-5aef-808f-dde90761c3a4 |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Has an earth bar been installed adjacent to/or within the communications rack and has a 6 mm2 green/yellow earth been terminated to the earth bar from the CET
checkpoint-status |  |  | checkpoint | Has the 6 mm2 green/yellow earth been identified and labelled with “Communications Earth” at the originating electrical distribution board
checkpoint-group |  |  | section | FOBOTS (Fibre Optical Breakout Trays)
checkpoint-status |  |  | checkpoint | Does the FOBOT match the approved technical data
checkpoint-status |  |  | checkpoint | Has the FOBOT been installed in the correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Has the FOBOT been labelled permanently with traffolyte label or similar
checkpoint-status |  |  | checkpoint | Has a service loop been provided in the optical fibre cable
checkpoint-status |  |  | checkpoint | Has the fibre port arrangement on the FOBOT been detailed and labelled
label | f25bd8dc-5b4d-5a5a-ab39-908d3c76af80 |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Do the fibre adapters on the FOBOT match the type of fibre being used
label | 4f9347b5-642e-5edf-bec3-e774586eb455 |  | note | e.g. aqua = multimode, green = singlemode
label | 1adc78ad-e6e8-5ad7-86d7-972cd1d9e51e |  | note | Adapters, pigtail connector colours must match, fibre cable type must match
checkpoint-status |  |  | checkpoint | Have fibre protective caps been installed on all fibre adapter ports
checkpoint-group |  |  | section | Cat 6/6A Patch Panels
checkpoint-status |  |  | checkpoint | Does the Cat 6/6A patch panels match the approved technical data
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panels been installed in correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panel ports been labelled permanently with traffolyte label or similar
label | d8aba68a-6919-5022-841c-91fb0df31e1d |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Have cable wrap-around labels been attached to each individual Cat 6/6A cable behind the patch panels
label | 13da515b-d0d1-5385-b52d-344b7dfb6315 |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Have the Cat 6/6A patch panels been earthed with 2.5 mm2 green/yellow earth cable from the earth bar within the communications rack? (Shielded patch panels only)
checkpoint-group |  |  | section | Cable Management
checkpoint-status |  |  | checkpoint | Have horizontal cable managers been installed in the correct rack RU position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have vertical cable managers been installed in the correct rack RU position as per the communications rack layout
checkpoint-group |  |  | section | Power
checkpoint-status |  |  | checkpoint | Has the correct power been provided for the communications racks
label | d8fead46-6d8c-5390-ba43-76f0307b48fa |  | note | Check for captive outlets? Are there 2x or 1x? Are they 10A, 15A or 20A? Check the Appselec power floor layouts against the communications specification
checkpoint-status |  |  | checkpoint | Do the PDU’s match the approved technical data
checkpoint-status |  |  | checkpoint | Have the PDU’s been installed in position as per the communications rack layout
checkpoint-status |  |  | checkpoint | Have the PDU’s been plugged into the captive outlets/rack mounted UPS as detailed on the communications rack layouts
checkpoint-status |  |  | checkpoint | Have the PDU’s been labelled appropriately detailing the power source
label | 04f6f1bf-bdb4-5a8f-a0e5-ebf9a6663bcb |  | note | For example UPS supply (Generator backed) DB-XX
checkpoint-group |  |  | section | Rackmount UPS
checkpoint-status |  |  | checkpoint | Is the communications rack/riser ready for UPS installation
label | a481f08b-9997-581d-87d9-57399f81865d |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
checkpoint-status |  |  | checkpoint | Does the UPS match the approved technical data
checkpoint-status |  |  | checkpoint | Has the UPS been installed in position as per the communications rack layouts
checkpoint-status |  |  | checkpoint | Has the UPS been labelled appropriately detailing the power source
label | 4ed2339e-3c62-5ee3-80a0-773c52385063 |  | note | For example UPS supply (Generator backed) DB-XX
label | f1159abd-8484-57d1-a971-291cce43e75c |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Has any associated Battery Backup for the UPS been installed as per the communications rack layouts and is it connected
checkpoint-status |  |  | checkpoint | Has the UPS been commissioned? Refer to UPS ITP for commissioning details
checkpoint-group |  |  | section | Active Equipment
checkpoint-status |  |  | checkpoint | Is the communications rack/riser ready for Active Equipment installation
label | 65f4ae05-a991-5bf9-817e-23f102dd704a |  | note | Riser must be in a finished dust-free state, finished floors, cable tray installed, clean and permanent doors installed
checkpoint-status |  |  | checkpoint | Does the Active Equipment need to be configured prior to installation within the communications rack
checkpoint-status |  |  | checkpoint | Does the Active Equipment match the approved technical data
checkpoint-status |  |  | checkpoint | Has the Active Equipment been installed in the correct rack RU position as per the communications rack layouts
label | b77e86b7-3284-55a9-84f7-6ac4172c5fcc |  | note | MANDATORY PHOTO - Photo attached below
checkpoint-status |  |  | checkpoint | Do you have a network diagram detailing the connection and labelling of all Active Equipment
checkpoint-status |  |  | checkpoint | Has the Active Equipment been labelled appropriately as per the vendor requirements
label | 252b01be-77fd-5b86-bb34-36d168202127 |  | note | All switches are to be labelled with the correct vendor labelling convention
checkpoint-status |  |  | checkpoint | Have SFPs been provided and installed
label | fefa77f6-dd69-5641-b9ca-ab42eb7b1e39 |  | note | Check that they are the correct SFP for the optical fibre cable installed
label | d5d7cfa2-0e35-5bff-a87e-24b4b14c157c |  | note | Check they are installed into the correct port
label | 493a20a9-26c8-5305-8da2-063359cc9ecf |  | note | (SFP is a small form-factor pluggable transceiver)
checkpoint-status |  |  | checkpoint | Have stacker cables been provided to stack switches together
label | ed631453-bce1-5258-8c7e-335d5c9ba9d5 |  | note | Are they connected as per the integrator/vendor requirements
checkpoint-status |  |  | checkpoint | Have the switches been connected to the PDUs
label | 643770fb-a285-54d5-bb84-3f46e159431d |  | note | Check if switches require one supply or two supplies (dual power redundancy)
label | 3a7b0f91-9e27-5295-87d8-2ce3be2163ae |  | note | Check if switches require UPS supply/UPS + generator supply
checkpoint-group |  |  | section | Patching
checkpoint-status |  |  | checkpoint | Do you have the correct length, colour, type (Cat6/6A) and quantity of patch leads
checkpoint-status |  |  | checkpoint | Do you have a patching schedule detailing which switch port patches to which patch panel port
checkpoint-status |  |  | checkpoint | Do you have the appropriate cable management capacity installed to patch cables as per the patching schedule
checkpoint-group |  |  | section | Mandatory Photos
checkpoint-status |  |  | checkpoint | MANDATORY Photo 1: Front of rack, door closed - Photo attached below
checkpoint-status |  |  | checkpoint | MANDATORY Photo 2: Front of rack, door open - Photo attached below
checkpoint-status |  |  | checkpoint | MANDATORY Photo 3: Front of rack, door closed - Photo attached below
checkpoint-status |  |  | checkpoint | MANDATORY Photo 4: Rear of rack, doors open - Photo attached below
label | 4fcc7f81-838b-5f4b-8ad2-8d92f35015ca |  | note | Additional Photos attached below as applicable
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Communications/Security Rack Installation completed to specification/drawings - Area left clean & tidy
label | 5dba73c8-5282-53af-bb34-ff1c8c6fe280 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 22893bbd-0c66-5114-bc8f-13038d5551fe |  | note | Any Corrective Actions to be Photographed & Commented below
select | 54facadf-c292-51fd-82c4-65819fcdb2c7 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 6f3c7532-c97d-57ce-985f-a8dc10c81a00 |  | textbox | Other (Specify here)
label | a514b3d2-387f-533b-8f55-32f0750e8a40 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) |  |  |  | 12 | Yes | AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | 77a19ae8-578a-4c30-b5ca-6ae17816856b
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 38dbb7a9-063f-5126-b578-e17d16e2fcab |  | textbox | Drawing & Revision #
text | c5213a53-6057-582e-93a7-7ca1024a9112 |  | textbox | Switchboard No.
checkpoint-status |  |  | checkpoint | Incoming Service Protection Device
text | d527e297-6b5a-5fa9-bcfa-5b183b985efe |  | textbox | A
text | ee93cfec-7e5e-512b-9200-ec4df49f5c4b |  | textbox | kA
checkpoint-status |  |  | checkpoint | CTs Installed
text | e39cbbf4-0aa1-55ec-9313-cb4c5bf106dc |  | textbox | CT Ratio
checkpoint-status |  |  | checkpoint | CT Rated to Suit Supply
checkpoint-status |  |  | checkpoint | CT - Meter Mounted
checkpoint-status |  |  | checkpoint | CT - Metering Loom Installed
checkpoint-status |  |  | checkpoint | Voltage Fuses checked
text | 737267be-4678-5121-82b2-e1e6c1bc14e4 |  | textbox | Amps
checkpoint-status |  |  | checkpoint | Isolation Circuit Breaker checked
text | 9319a89a-6ee5-5022-9fa2-da9fcdf6b0f9 |  | textbox | kA
select | f1aafc4f-3139-59bf-b316-7a1363147947 |  | dropdown | Isolation Method | Circuit Breaker, Isolator
checkpoint-status |  |  | checkpoint | Earthing Testing Completed - As per below
text | f3b86ae0-6c42-5922-b8be-5f144c469c78 |  | textbox | Main Earth Resistance Test (Substation) - Ohms
text | 7594079c-3dc5-56d0-b9ee-63abd29a2b99 |  | textbox | Earth Resistance
text | 2fcd1f62-4450-534d-ab61-78175c0339d8 |  | textbox | Earth Stake
select | 383a7cf9-ae1f-5a40-9415-ec952acc8d48 |  | dropdown | MEN Position | Wall Switchboard, Main
button | e5a49888-6d97-58db-afae-8ee89659f0b2 |  | button | MEN Size Equal to Neutral | Yes, No
button | 20385865-6a67-5f3c-8e29-3f89f49bab54 |  | button | MEN Bonded to Switchboard Chassis | Yes, No
checkpoint-status |  |  | checkpoint | Bonding Testing Completed - As per below
text | 6eb91fe0-5049-57f5-9a1d-82f7777ed28a |  | textbox | Cold Water
text | 8e7700a7-3a3c-5e6c-8b92-27795f3ded5b |  | textbox | Cable Support Systems
text | 8f7295b8-73b1-5201-b95d-bc03e49312c5 |  | textbox | Fire Hydrant
text | f7554770-f5c4-579e-a822-d9e2e1e9773f |  | textbox | Gas Services
checkpoint-status |  |  | checkpoint | Labelling Inspection - DB Labels installed
checkpoint-status |  |  | checkpoint | Labelling Inspection - Cable Labels installed
checkpoint-status |  |  | checkpoint | MEN & MSB works completed to specification/drawings - Area left clean & tidy
label | 3137960b-a1c6-53ed-baa6-44b070f525d0 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 490a1d83-ff22-5b86-b935-91432f6ec423 |  | note | Any Corrective Actions to be Photographed & Commented below
label | 827934f7-4d55-5dee-8ff6-ebca6eccabcc |  | note | .. ..
text | c537496a-dcdc-57a8-8388-545eb3d83833 |  | textbox | Test Equipment Tester Type
text | c9ebd84f-596d-5172-a714-a46f9b4a98ee |  | textbox | Serial No.
text | c5b305c0-bdc2-5cac-a871-e8b9a76615d3 |  | textbox | Calibration Certification Date
select | 1657e6ad-7017-590d-a5a8-ffa81862b9b4 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 0b94b595-c8de-51f2-a71b-6bd947bc30c3 |  | textbox | Other (Specify here)
select | 69ee20b0-29a6-51d4-89b2-e08691d41e6d |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | f432bf92-c57f-5016-9ee7-2ea7d829f856 |  | textbox | Other (Specify here)
label | 167d8226-d71d-50fd-bd18-ea77a34ad004 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-006 - Distribution Board Visual Inspection (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-006 - Distribution Board Visual Inspection (Rev 0 +Names) | 7b96b1dd-612e-4aa1-b21d-fd81b4f441cc
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | d2686dcc-2fff-5ac3-a75b-463307695cbf |  | textbox | Switchboard No.
text | acc9b028-0b44-5275-905f-1c7bc6455773 |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Appselec typed legend, schematic and labels all in place
checkpoint-status |  |  | checkpoint | Manufacturer's QA check list provided - Attached as applicable
checkpoint-status |  |  | checkpoint | All connections tight with no copper visible out of terminals
checkpoint-status |  |  | checkpoint | Contactors labelled
checkpoint-status |  |  | checkpoint | Wiring neatly loomed (Internally and Externally)
checkpoint-status |  |  | checkpoint | Surge arrestors installed
checkpoint-status |  |  | checkpoint | Cable entries appropriately insulated and fire rated
checkpoint-status |  |  | checkpoint | Bottom entry cables have mechanical protection (if applicable)
checkpoint-status |  |  | checkpoint | Panel, escutcheon, cover plate, door, operable lock and pole fillers in place
checkpoint-status |  |  | checkpoint | Lighting control cabling and emergency cabling labelled
checkpoint-status |  |  | checkpoint | Emergency power sensing installed (if applicable)
checkpoint-status |  |  | checkpoint | Switchboard cupboard cleaned
checkpoint-status |  |  | checkpoint | Distribution Board Visual inspection completed to specification/drawings - Area left clean & tidy
label | 8dc97c8f-6960-5bcb-97e1-46fdf4a41e6e |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | f5aebd21-809d-5b61-b38c-e21ffcab3cba |  | note | Any Corrective Actions to be Photographed & Commented below
select | 8c629664-8aca-5cf3-9ed3-e34ef0c4aaeb |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | df2c3979-2734-5c8a-9192-bdfb61bea7af |  | textbox | Other (Specify here)
select | a68a694b-6ab8-55e2-aee3-e213882fa4d1 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | e833b4b5-34fa-5b31-9ecb-31b0570b52f3 |  | textbox | Other (Specify here)
label | fadacc35-4c30-58f3-8e9c-a696bcdde082 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | Mandatory testing |  |  |  | 5428 | Yes | AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | 7db29913-3544-41d6-97e5-80675f28ac3f
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | dc356e57-4f7e-5aee-b929-b4728efa9c00 |  | textbox | Meter Panel Info
text | 7c9ff004-df02-5b92-a83a-1022757b7658 |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | Details - Pass once entered
select | 8b88c91c-c6f8-56cc-8b80-d3d3d7d96a0b |  | dropdown | Type | RCD, RCBO, MCB, MCCB, Fuse, Other (Specify below)
text | 8504ce19-635f-56b1-80a4-dd651f636507 |  | textbox | Other (Specify here)
select | 2728bdba-1b8b-50ac-af2e-6b8905d7f2a7 |  | dropdown | Type | A, B, C, D, Other (Specify below)
text | 2412b6c5-f500-50e4-9c0c-e6b6f2d73e56 |  | textbox | Other (Specify here)
select | 6f311ada-f3f4-5e5d-a1a2-8403a3cfcc3c |  | dropdown | RCD/RCBO mA | 10mA, 20mA, 100mA, Other (Specify below)
text | 5eade737-429d-55bf-a224-493a1dc05ddd |  | textbox | Other (Specify here)
select | fdb180cd-4707-5e36-a398-aed33ca5e7bf |  | dropdown | Rating in (A) | 6A, 10A, 16A, 20A, 25A, 32A, 40A, 50A, 63A, 80A, 100A, 125A, 160A, 200A, 250A, 320A, 400A, 630A, Other (Specify below)
text | 25c3c38a-1896-57c6-aa0a-e4b36212eab8 |  | textbox | Other (Specify here)
select | 8c35d587-cfd7-5618-a9c3-f1fe102b266c |  | dropdown | Cable size (mm2) | 1.5mm, 2.5mm, 4mm, 6mm, 10mm, 16mm, 25mm, 35mm, 50mm, 70mm, 95mm, 120mm, 150mm, 185mm, 240mm, 300mm, 400mm, 630mm
select | 2b41c599-9366-5c72-8125-25bb2a3c850b |  | dropdown | Phase Qty | 1 Phase, 3 Phase
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity
label | fd04f475-e2b7-5aec-9fdb-a4bf9d744118 |  | note | Pass/Fail Measurement in OHMS, <0.5 for main earthing conductor, refer to Table 8.2 for final sub circuits
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Earth loop impedance
label | e896a0f6-7ecc-56da-ae56-1c0e919afbc9 |  | note | Pass/ Fail Measured in OHMS to the furthest point Refer to AS3000 table 8.1. N/A for an RCD protected circuit
checkpoint-status |  |  | checkpoint | Correct circuit connections
checkpoint-status |  |  | checkpoint | L1 - N (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L2 - N (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L3 - N (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L1 - E (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L2 - E (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L3 - E (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | N - E (Measurement MEN disconnected) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L1 - L2 (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L2 - L3 (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | L1 - L3 (Measurement) >1MΩ is a Pass
checkpoint-status |  |  | checkpoint | RCD Testing
label | ab264c21-ee7a-5c97-a31a-e87a43dd3dcf |  | note | Correct function of RCD has been verified by the operation of the integral test device or by the use of special test equipment
checkpoint-status |  |  | checkpoint | Commissioning Completed to specification/drawings - Area left clean & tidy
label | 5ea4b925-b631-5b66-a902-50b38201fa71 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 891ca979-13e5-5f5f-9a3f-491e7dea71f8 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 40613022-c48a-53da-a2a2-f8c4ec104171 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 968c9014-4a8f-531b-a3f4-0c0e410b2ccd |  | textbox | Other (Specify here)
label | ab2915ff-fec2-5606-8c94-e337c42e8ac2 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) |  |  |  | 722 | Yes | AE-ITCX-032 - Electrical Commissioning Checklist (Rev 0 +Names) | 82314656-49ba-4bae-818a-42ce42105e98
checkpoint-status |  |  | checkpoint | Documentation to proceed with commissioning
button | 4ca36688-ea96-557c-9817-a2f618ca6f3e |  | button | AE-FORM-006 - Builders Works Completion Notice, AE-FORM-011 - Notice of Intent to Energise Electrical Installation, AE-FORM-009 - Start card been filled out by all workers within the commissioning crew? | Yes,No
button | 0fd460f9-a879-5cf8-aee5-cba295c87af2 |  | button | All Rough In and Fit Off and DB Fit Off QA has been closed out and As-Installed drawings are available to commissioning team confirming area is ready for commissioning to begin. | Yes,No
button | 44cb6c05-4500-586e-98d9-6efc31c3b906 |  | button | Have you checked if are there variations within zone/ area that may not be on shop drawings? (Check with Site Manager before continuing). Commissioning team to add to asbuilt immediately! | Yes,No
label | 7ce4229b-942c-5893-983e-705998c0da3e |  | note | Commissioning Team have been provided copies of As-Builts, DB Schedules and AE-Form-038 to begin commissioning process.
checkpoint-status |  |  | checkpoint | General - Final Visual Checks in addition to AE-FORM-038
button | 9338087a-5070-5536-b9ed-07de4b870181 |  | button | Outlets, switches and other equipment installed straight, level, in the correct location and mounting height? | Yes,No
button | 1b06af09-589e-53b6-a22c-e88b47e6cfd8 |  | button | Are any items left incomplete and made safe for energising (e.g missing splashback) If so please photo document here. | Yes,No
button | 2e5f911d-b08f-5a83-960e-97d45462b15c |  | button | If Yes add image of item made safe. | Yes,No
button | 414a4480-f134-5e45-a150-dd040be9d2b6 |  | button | All switching devices are operating documented items? As per drawings documents. | Yes,No
button | 07937d11-a9c5-593c-b729-24f3a61cabf7 |  | button | Smoke Detector is tested, has back up power supply activated and is in permanent operation. | Yes,No
button | 08449d83-9b29-5b8f-8344-c1913d729e04 |  | button | Electric cooktop has a visible isolation switch in accordance with AS3000? | Yes,No
button | 81355884-3735-5bf6-85f4-9b3820c2fc2d |  | button | Exhaust fans function correctly? Where a fan is switched from multiple locations, double pole mechs are installed to prevent the “back feeding” of lights in the other spaces? | Yes,No
button | db9bfe2e-7d85-5ec0-ab78-a727b4e0fd38 |  | button | All outlets labelled correctly and all cover plates are installed. | Yes,No
button | ec6492d7-bb6e-5736-8323-c093f73985a1 |  | button | All power is now available and Lighting Control System (if any) is ready for intergrator/specialist commissioning | Yes,No
button | dc3836fe-7d2e-5df6-ad68-a433dd7c9287 |  | button | Is the Exit and Emergency /circuits now powered and ready for Emergency discharge test and Commissioning to be performed. | Yes,No
button | 0d98223c-923b-55b2-ab58-00e20cacd5c4 |  | button | All circuits locked/tagged out been entered into the AE-FORM-010 - Isolation Tag Register? | Yes,No
button | 5dbc6c59-21c0-51f8-bf04-5f4156421133 |  | button | Distribution Board is now energised and officially put into service. | Yes,No
label | 6391b17d-1f36-5a2c-a175-7d7b8123b433 |  | note | Mandatory photo - Accurate as built drawings upon completion of commissioning including variations, site changes, driver and puk locations?
label | 3a447284-fe95-5566-a1b0-2d48eb7cf3a0 |  | note | Mandatory photo - Internal DB escutcheon off image documenting condition left at energisation.
label | 28b3cf52-cbbf-5f1d-99a5-bbd5abd865fe |  | note | Mandatory photo - Isolation tag register?
label | 3dcd0240-e2f4-5b72-8270-7834bf91737d |  | note | Mandatory photo - Commissioning Test Sheet FORM- 038 (obtained from Appselec way) including all test results.
label | ef29d193-ebd9-5226-a5e7-c596cdec8b4c |  | note | Mandatory photo - Certificate of Electrical Safety (screenshot for electronic forms)
checkpoint-status |  |  | checkpoint | Electrical Commissioning completed to specification/drawings - Area left clean & tidy
label | b35dcfa0-a221-5b5a-b49c-ecf3a860a69c |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 16217422-a0d2-569e-89e3-94502d4ebb81 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 67c14ef8-a2cc-594d-884e-cc82b2002431 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | c5a7f3f3-201a-55a8-a8f4-65258a4ab8f2 |  | textbox | Other (Specify here)
label | 82f1d76c-9558-5477-963c-34f81e97db4a |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AF-502 - Electrical Services commissioning Sheet - DETAILS & 10x Circuits- Insulation Resistance (Rev 0 +Names) |  |  |  | 0 | Yes | AF-502 - Electrical Services commissioning Sheet - DETAILS & 10x Circuits- Insulation Resistance (Rev 0 +Names) | 865a970e-5463-4b8c-8c7c-b9990e43be8c
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 70d2bb7e-9147-5ea2-9918-6abc27290d86 |  | textbox | Test Date
select | 2fba96f2-ad74-5e7f-98c8-a477f047aa91 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c3897c2e-3ded-5c64-bfc3-145ccdc6a09c |  | textbox | Other (Specify here)
boolean | d7ff72ea-013f-59c9-a66f-5c011c8571f3 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Circuit Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 5e24bc8f-b52f-5561-b5e6-d989d40e87d0 |  | textbox | Designation of service
text | 77284689-0871-585f-a449-af0b62d95390 |  | textbox | Location of Service
label | 5cb47cef-21e4-5a80-8017-6b6626525a77 |  | note | L1= Red Phase, L2= White Phase, L3= Blue Phase
label | 03e0428e-7796-586f-8689-7c727632d77b |  | note | Where a single phase circuit is being tested, enter the result in the column that corresponds to the supplying phase, enter N?A for the other phases
checkpoint-group |  |  | section | No. 1
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | bf308022-0b3d-524a-82e0-55fa8786859a |  | textbox | L1 - N
text | 229efe0a-0b90-5031-ac0c-6634db2e91c8 |  | textbox | L2 - N
text | df2f4997-c2bc-53c2-8b8c-5067fad2eda6 |  | textbox | L3 - N
text | e298d8ba-8fd6-534b-af47-7bd73ebfa366 |  | textbox | L1 - E
text | 5485b7fa-6cac-5e72-a275-a51123c9b645 |  | textbox | L2 - E
text | e9d803b9-ecfe-54c1-b258-335963fd57d0 |  | textbox | L3 - E
text | 0ccdb916-c2be-555e-91d2-d5e006878f9f |  | textbox | N - E (MEN Disconnected)
checkpoint-status |  |  | checkpoint | L1-L2 (N/A if 1 Ph)
text | 0db4f89d-993c-5cb7-b73e-93a417c57770 |  | textbox | Calculation
checkpoint-status |  |  | checkpoint | L2-L3 (N/A if 1 Ph)
text | 19cb2f0c-e8c1-5a3e-8f35-97e5613a7cc1 |  | textbox | Calculation
checkpoint-status |  |  | checkpoint | L1-L3 (N/A if 1 Ph)
text | 9937cc0e-81dd-5a47-8b23-a5db78ee00b4 |  | textbox | Calculation
checkpoint-group |  |  | section | No. 2
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | ed6f66b1-561a-5da7-a0df-51e0d95f355b |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | c240f09f-cbbe-5d23-9877-de442379805f |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | 03fda6b6-b6ba-5c42-96f6-9d27be6786c2 |  | textbox | Rating in (A)
text | da6109fc-9581-5f64-9a1f-f834d238e2c5 |  | textbox | (A) Active CSA mm2
text | 6e1db47c-9bef-5e1a-86bc-213dcf43c85f |  | textbox | (B) Earth CSA mm2
text | 8a7fbb2a-7bff-5fb6-9046-502eaa22fbd7 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 02540ac2-2628-56d1-acca-54cc442b644a |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 9347f14b-8695-55b5-a990-6f712bdf8da2 |  | textbox | RE = (D/C) * A
text | 8e8a018e-3ea4-55aa-ab48-957eac5d348b |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 085a0197-9d01-59fc-b352-fdbe13d5c0c8 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 2f5b582b-d66f-50ed-8a41-82373a842bf3 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 3
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 456f1e08-0620-5d50-b64d-7a1388b58514 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 4a8e49ed-de8a-5c25-9645-ed3cb9b0cb22 |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | 0519c74e-9626-5059-be40-c7f7687c5406 |  | textbox | Rating in (A)
text | b684ca2f-193a-5db5-be79-1141d7b65913 |  | textbox | (A) Active CSA mm2
text | ea367746-0728-5543-99bb-4e5c8a4683d2 |  | textbox | (B) Earth CSA mm2
text | 96107ac2-0378-5820-9589-83ec432ae3e4 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 53039a13-2a34-59e1-8b01-77fa17d4b8e6 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | bce74c24-d296-508d-bb14-5f97abdfbc8c |  | textbox | RE = (D/C) * A
text | 3fa31a6c-6cf5-563c-a72f-6c48a4fcff60 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 05653e71-66f5-57a7-a877-76ef97c4c8bc |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 882b0663-53b7-55f3-b555-a39a03a49e64 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 4
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 8e59553b-c2bf-5f2f-ac13-a4a92010fad5 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | a1df3882-c68d-5fbb-b917-cdbd66690e32 |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | 4c2fd695-ad0c-51f3-98ff-092b41f5f8e2 |  | textbox | Rating in (A)
text | 1c1b0bd1-f69c-500d-b19f-a1ff5c528789 |  | textbox | (A) Active CSA mm2
text | ff965f1d-d4e9-5e4b-818b-b356bd65d1e4 |  | textbox | (B) Earth CSA mm2
text | b7118871-ee93-51e3-a0ec-a8dcd23b0bd5 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | aaa2994f-878c-5238-9f19-6af2ce9e6148 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 961c0f87-a8a0-5ce3-819e-2e9656ce8508 |  | textbox | RE = (D/C) * A
text | ab91f8df-7cf7-5be8-974c-485424f00156 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 3edd0f98-81f1-5424-9a6b-def0e68940a3 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 1a5aee63-d185-50a8-ac55-6e39aeaad8b5 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 5
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 00b8018e-ee3f-5928-a9b1-d7a0a9cdb58c |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | d7dd703f-723d-575c-b65e-b483dde2753d |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | ee32df2e-c8cb-5b32-a65f-e26ae1272c08 |  | textbox | Rating in (A)
text | 2c494b74-e567-506e-a622-3b4efe184bb5 |  | textbox | (A) Active CSA mm2
text | 1183226f-0f1e-5e53-a28d-fccb2f91df63 |  | textbox | (B) Earth CSA mm2
text | d0be9015-855e-5f84-a035-f1e60a986be3 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 3f80a875-bd40-5215-a516-a0b388ec30de |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | b44eb293-63ba-5d20-87de-96c9d68f9037 |  | textbox | RE = (D/C) * A
text | 052dc738-6fc4-5c5e-8b92-63c745b72ddd |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 01f67b28-b844-507c-bc03-90203b06ec9e |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | cd2f77d0-7c95-529a-9309-e11b776d484b |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 6
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | f5529b72-4858-54e4-b72c-0a7c7407d60b |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 5264a59c-f21e-58c6-9cdb-8be3cd11c74f |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | cee79698-141d-586d-a82d-94600c53fe4d |  | textbox | Rating in (A)
text | c7b3be24-5525-5852-bf33-56865c502421 |  | textbox | (A) Active CSA mm2
text | 0afb3761-9378-577a-be21-5d7d97502e67 |  | textbox | (B) Earth CSA mm2
text | 797325b3-04fa-5d9d-be2c-14bd173ddbd4 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 4acdc220-26a3-5aec-957b-ea6cfc33ba3f |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 3cb76d8b-00ea-5151-9dc4-2f5a08c107d9 |  | textbox | RE = (D/C) * A
text | 99e469d9-8bc3-5071-9c76-949cd33233c4 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | d142744e-b5ea-5140-95ab-cc358e3144d5 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 6fa3eea6-5e27-5394-879f-df9e418e813b |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 7
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 63da258a-9b5f-5b88-8e31-2d9c114f090d |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | d7783041-9975-5659-9719-e3f248972cba |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | 7957f1ba-0041-5b95-b4d8-2f494a6f54ba |  | textbox | Rating in (A)
text | ddb85559-2790-5d59-b841-edae1002dd80 |  | textbox | (A) Active CSA mm2
text | 42280605-b677-594e-b4af-b72438dcc906 |  | textbox | (B) Earth CSA mm2
text | 1eecd63e-59aa-52a9-98cc-239dd7f5bf4e |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 77ade9fb-b860-575c-94d7-ab1bc9d5dd55 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | c761d387-9177-508d-961b-0ad2e0efa3a0 |  | textbox | RE = (D/C) * A
text | a5baf36a-e08a-507f-a915-e8aad226e533 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | d46db13b-5e7d-5848-9d6c-2f2f8cdebc8d |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | ca689d8d-bf3c-5ab2-aba4-e1045ebaa748 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 8
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 23458d48-5d60-5319-8c59-82f38decb3a9 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 6e3af69a-d751-5431-940b-de14165acd2f |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | a3770997-66d5-574d-9f5f-19ce9f950216 |  | textbox | Rating in (A)
text | 304c222f-802d-5326-8531-24cfc63903da |  | textbox | (A) Active CSA mm2
text | 28f0c04f-f355-55e3-a1a5-762be501732e |  | textbox | (B) Earth CSA mm2
text | db707525-b798-5a34-bec7-79db772d8a40 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 9b54723e-4cb6-5091-b083-4f9c3ea2528c |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 391d6b2f-6ec1-52c6-8a7c-778ede86e730 |  | textbox | RE = (D/C) * A
text | eefc5d88-30f3-53e9-9f7f-4b2e5c0db63e |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 606a320d-02d6-5b4e-b12b-3b607ae41c6b |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 1c34b64b-e98f-5ab0-aa74-030a8d7500ed |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 9
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 063636fd-3a5c-5bb7-97e4-d2e9e320f0b4 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | a4fbef3a-8b67-5741-a4fc-003db359ce36 |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | ea4732b8-e900-5a25-8f92-940e10a6973d |  | textbox | Rating in (A)
text | f3b0e818-d28c-56ee-9f47-44a8bb8a1716 |  | textbox | (A) Active CSA mm2
text | 0dff9098-d83e-5490-b920-f697e960036a |  | textbox | (B) Earth CSA mm2
text | f2fbd9e4-2222-5fd3-a5c6-ba054d368b30 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 6caf8c76-a329-5d0f-b0b0-72d55beb27e0 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | c715dc4b-5256-593c-8d4a-1c06debe3a69 |  | textbox | RE = (D/C) * A
text | d197dfeb-d2b4-54e3-b56d-b251ee1277ac |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 8ce4b2c0-0dfa-5f21-8436-e317d23e8471 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 15b3b7e9-884f-57ca-b8a5-5141f8a89fc8 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 10
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 9c22ad36-231e-5222-ac73-4ce16cf1357a |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | ca6a78db-42f4-56c6-a69a-d6d498f3c3e7 |  | textbox | Type B, C, D, TM Electronic
checkpoint-status |  |  | checkpoint | Data Capture
text | dc576dca-6f0f-5128-bd90-ce640174ec75 |  | textbox | Rating in (A)
text | 65b7715b-f965-5c97-ac1e-85a60a1a90c3 |  | textbox | (A) Active CSA mm2
text | 21ee220d-02be-5fbb-8a43-a647ad54356c |  | textbox | (B) Earth CSA mm2
text | 92c2d8c9-e020-5d44-8b0f-bce58e03e498 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 4c4ae2a1-22bb-54b2-ad57-eeed9b66435e |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 9195cfbe-855f-5ffc-8477-5f3f51d352f9 |  | textbox | RE = (D/C) * A
text | 96caca84-7cea-5145-b6ff-e40af2838ae1 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 58fe2e2d-401b-5f6b-bdcf-368c66ee391d |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | fdfa7416-3e84-5b34-8edf-d25a5b00fbab |  | textbox | Difference (F) - Calc'd ZS
checklist-flat |  |  | checklist | AE-ITCX-033 - Busduct Installation (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-033 - Busduct Installation (Rev 0 +Names) | 8ec0dd08-2ab7-4258-a72a-20c81443baf1
checkpoint-status |  |  | checkpoint | Busduct Details - Pass once entered/confirmed
text | 94920f7c-048f-5eff-acd3-74665e556a06 |  | textbox | Drawing & Revision # (or Attach photo below)
text | 3a6f3170-dcd3-52b2-ab72-efc4cb0b59e4 |  | textbox | Run details
text | a0a7075f-013f-54ba-8b03-b2b5e8731ea1 |  | textbox | Package #
text | bcae3136-6006-5909-86ec-6524fb4bb264 |  | textbox | Approx weight (kg) - Excluding Packaging
checkpoint-status |  |  | checkpoint | Piece 1 - Item onsite - Pass=Yes / Fail=No
text | d02d7a44-baa2-505e-8d0c-0067e5ace8bc |  | textbox | Vass Shop Drawing Piece #
text | 2baa39d1-23c6-5b47-a9db-d443933a9d81 |  | textbox | Piece weight
select | 8942edba-0e82-5204-95c1-7dc79dec4611 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 71d2daff-3da5-5a4a-8001-8cf6c2882ae3 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 2 - Item onsite - Pass=Yes / Fail=No
text | 281efd4a-f687-5c49-a202-38a5b245289c |  | textbox | Vass Shop Drawing Piece #
text | c2dd4289-e838-53d1-90a6-a2095f75ec9e |  | textbox | Piece weight
select | 5c8cb690-4813-5ddc-a762-b92f74b5360a |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 785141a3-b248-5e4b-aa57-e046ed0e18cf |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 3 - Item onsite - Pass=Yes / Fail=No
text | aefc595b-8019-56f5-94e2-e2b1632d1961 |  | textbox | Vass Shop Drawing Piece #
text | 960b1c12-7a95-5340-96c8-fc1c5f3a9fd3 |  | textbox | Piece weight
select | 1deb8564-a0bc-536e-b4da-642b26ce7d89 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 47040040-67ec-571f-9ec3-493633aa4d60 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 4 - Item onsite - Pass=Yes / Fail=No
text | 666c2b6f-ee4b-5367-a8c7-15eff2e6b276 |  | textbox | Vass Shop Drawing Piece #
text | f6eb77c0-22c7-585b-997d-02ca7dd39219 |  | textbox | Piece weight
select | 2f275d5d-ff5e-5b86-b7cb-e975ff343453 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 84086b42-e13d-51c0-91d3-5c9f0f9a72cf |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 5 - Item onsite - Pass=Yes / Fail=No
text | fad48937-5a72-5584-8630-e0b46dae9a18 |  | textbox | Vass Shop Drawing Piece #
text | 77e97773-ea24-580b-8ad4-59c9ba7061cb |  | textbox | Piece weight
select | 63a4e82c-5dc9-53ff-8b94-b241413f8df1 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 85ce5915-5bfa-5666-a3d9-5fe09d7301ec |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 6 - Item onsite - Pass=Yes / Fail=No
text | f6730dc9-3156-5e2a-a415-e4c8569f3bbd |  | textbox | Vass Shop Drawing Piece #
text | 31ad19d2-1126-56d3-b428-a7f787f9a78c |  | textbox | Piece weight
select | 70300b72-c774-5ab2-89ca-7126eabcaa7b |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 5e598dee-951a-5ea6-b88d-91793f8d1353 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 7 - Item onsite - Pass=Yes / Fail=No
text | 380c283f-0759-58f5-99b4-fafe9b9c4819 |  | textbox | Vass Shop Drawing Piece #
text | f44ca10b-8d8e-5f7c-b334-00c040112952 |  | textbox | Piece weight
select | 6f72bd1d-0cb7-53a7-98e7-4a821dfb2f38 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | aa03b5ef-0175-5076-860f-2bbfd188d5ae |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 8 - Item onsite - Pass=Yes / Fail=No
text | 55331efa-74dc-5e83-9043-0854cdf7775c |  | textbox | Vass Shop Drawing Piece #
text | 68c6b057-1a8d-59ab-a8a1-93469b0e3d20 |  | textbox | Piece weight
select | 7e0f8403-a187-50e5-8759-9f3d35711c97 |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | a26001e8-8cd4-5db0-b5ab-d08762747563 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 9 - Item onsite - Pass=Yes / Fail=No
text | ee8778c0-e014-5d80-9588-3c9909679309 |  | textbox | Vass Shop Drawing Piece #
text | 90bed723-da45-5e89-8f09-1a245ba7435e |  | textbox | Piece weight
select | 19a1e853-411b-5782-961f-f09f1bf0c8fd |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | 0b36ea01-e359-504a-bda7-0e8163987eb9 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Piece 10 - Item onsite - Pass=Yes / Fail=No
text | 2739c712-e24b-5227-b990-30a45b1f5475 |  | textbox | Vass Shop Drawing Piece #
text | e6719a8f-885a-5fae-8a81-c25a6affdee0 |  | textbox | Piece weight
select | 17c187cd-8cc6-5891-a7a5-a5e5a7ad8aed |  | dropdown | Any Damage - If Yes, attach photographs/comments below | Yes, No
text | a0d55cdc-0a4b-5d0e-8610-b4f0626e7541 |  | textbox | Final location
checkpoint-status |  |  | checkpoint | Sign-Off - Busduct Installation completed to specification/drawings - Area left clean & tidy
label | 54f66c4b-b231-5282-9eba-7429b644da4d |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | ff36801a-9478-5c06-a1f6-501e07c0b830 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 4c3fa3e2-97fb-5df7-9b90-ff0387945e98 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 6ecbee60-dfb5-526b-aef8-f3b6c48c5295 |  | textbox | Other (Specify here) |  | To be updated with employee list
label | 7d4fb492-409d-5acc-84d1-5d40375ff1fb |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) |  |  |  | 44 | Yes | AE-ITCX-007 - Conduit Checklist (Rev 0 +Names) | a21be19e-49c8-4006-a8cb-e5ab0133687b
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 2661a420-a7d3-5fd9-92ea-96764f80fc0d |  | textbox | Drawing & Revision #
text | 5d195503-ec5d-5c7a-bde3-5e3d1e5acfe1 |  | textbox | Location
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | 76f7b40f-ad57-50a7-aa66-1b0262bcca1f |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Conduit layout plan prepared
label | 9aa2f255-fda3-5950-8c75-61552c3555eb |  | note | Plan addresses minimum distance from other services, as per AS/NZS 3000 Table 3.7 (Minimum Separation of Underground Services
checkpoint-status |  |  | checkpoint | Required cover identified as per AS/NZS 3000 – Table 3.6 (Underground Wiring Systems – Minimum Depth of Cover)
checkpoint-status |  |  | checkpoint | Conduit installation. Check all joints
checkpoint-status |  |  | checkpoint | Accessories installation. Check all joints
checkpoint-status |  |  | checkpoint | Check conduits are securely anchored
checkpoint-status |  |  | checkpoint | Check accessories are securely anchored
checkpoint-status |  |  | checkpoint | Warning tape installed (not required for cast-in concrete conduits) as per AS/NZS 3000 – 3.11.4.5.
checkpoint-status |  |  | checkpoint | Conduits installed as per plan (inspect prior to pour)
label | f609a268-68ac-5af5-bf8b-9230269e76c2 |  | note | Photos taken showing all conduits - Attach below
checkpoint-status |  |  | checkpoint | Required cover in place
checkpoint-status |  |  | checkpoint | Conduit locations marked on As built drawing - Attached below as applicable
checkpoint-status |  |  | checkpoint | Conduit works completed to specification/drawings - Area left clean & tidy
label | 607df82c-b890-5805-91e2-1d1084815b2a |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
select | 4d90d466-9b51-501b-8990-9df7632a3758 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | dad3e9f3-ae9a-5137-a603-0241197564f3 |  | textbox | Other (Specify here)
select | 4b3a7622-b629-5059-bce8-a5d87811cdbe |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | ed11f906-4337-5efd-b445-69c3572b23c9 |  | textbox | Other (Specify here)
text | 496a5097-f2f3-5d00-9297-c6b40e733d9f |  | textbox | Witnessed by (Builder/QAM)
label | 9bb4545a-2a9b-5cb7-9261-c1e70b1a64de |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-flat |  |  | checklist | AE-ITCX-036 - Cable pit installation |  |  |  | 0 | Yes | AE-ITCX-036 - Cable pit installation | a2ee73c3-b645-44d0-8c64-ebe7e26ef960
checkpoint-status |  |  | checkpoint | Pit installed in correct documented location
label | f80a186b-bae2-527c-a096-261652eb6c7c |  | note | * Mandatory Image - (Drawing Title Block)
checkpoint-status |  |  | checkpoint | Pit installed to the correct RL (Reference Level)
label | 0aa62992-f123-57ad-8111-5781b5e5c9fa |  | note | * Mandatory Image - (Drawing Title Block or Surveyor Details)
checkpoint-status |  |  | checkpoint | General Checks
button | 566665ed-de90-59ec-97de-3fae3c25d745 |  | button | Bellmouth conduit sealant is installed where conduits enter pit. | Yes,N/A
button | 56ce5edf-dab6-558a-8b81-054084816831 |  | button | Is drainage connected to pit | Yes,N/A
button | dba8b02d-8c5e-5de1-9c39-5dac12c5f33b |  | button | Pit lid is squared and leveled | Yes,N/A
button | b0da5fc5-5412-5480-873a-ec26b8a7c004 |  | button | Pit has been caulked between lid and riser. | Yes,N/A
button | 7f803f75-bc7f-576f-8e3c-a03dc2d58fc5 |  | button | Pit is cleaned and clear of debris. | Yes,N/A
label | 4f244f2e-af37-5c09-adea-b4f4a655e767 |  | note | *Mandatory Images Pit Installed (lid on finsished)
label | 446042c5-d753-5076-a822-960cead5cad7 |  | note | *Mandatory Image Pit Open visual of conduit entrys (Multiple images if required).
checklist-sectioned |  |  | checklist | AF-502 - Electrical Services commissioning Sheet - Details & 10x Circuit Checklist (Rev 0 +Names) |  |  |  | 0 | Yes | AF-502 - Electrical Services commissioning Sheet - Details & 10x Circuit Checklist (Rev 0 +Names) | a44fba08-d0f5-47b3-a725-a2d31ab6b3f0
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e512e842-bfe8-5fe1-af23-adf32518171e |  | textbox | Test Date
select | e10adc9f-fb6d-5e7a-9163-f0d32aa23470 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 9399f240-2560-5deb-8252-0363b8ba3ed5 |  | textbox | Other (Specify here)
boolean | 4e4acbb0-de0e-5e5a-8d81-bf69ae9e8556 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Circuit Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | a61a9043-d289-5c3a-bd7a-c1c7fe871408 |  | textbox | Designation of service
text | b98ede8c-4675-571d-954a-4689f660f2b7 |  | textbox | Location of Service
text | de4be1ac-ddcf-55a3-a0ae-449d81acf47d |  | textbox | Test Equipment Model
text | d5f4dc04-3014-5305-912e-8ede78e3c0ac |  | textbox | Test Equipment Serial No.
text | 51b382ee-edf7-5093-9dee-9fc51bb2b7f7 |  | textbox | Method of Fault Protection
text | 04cfc482-6ed4-565d-ab94-057bc91592d4 |  | textbox | Prospective Fault Current
text | 629c3d0d-9435-508b-9773-a888bf1c8f8f |  | textbox | ZE
label | 52b1952f-c3ac-5a33-add7-9a7fe92934ee |  | note | .. ..
label | 4c712e24-41f7-5da6-b6db-dd52bdf1b57f |  | note | Specify Board Type below,Pass to applicable, N/A to irrelevant ones
checkpoint-status |  |  | checkpoint | Main Switchboard
label | 45a6075e-fe4a-546e-8fd4-cd50b128cc4c |  | note | Visual inspection, Earth continuity, Insulation resistance, Polarity, Correct circuit connection, Fault loop impedance
checkpoint-status |  |  | checkpoint | House Dist. Board
label | 269d7f18-fb37-57ae-b46a-25488ffb8abd |  | note | Visual inspection, Earth continuity, Insulation resistance, Polarity, Correct circuit connection, Fault loop impedance, RCD Test (Where installed)
checkpoint-status |  |  | checkpoint | Apartment Dist. Board
label | e9969445-0f5c-51a8-9613-aa546cf7e263 |  | note | Visual inspection, Earth continuity, Insulation resistance, Polarity, Correct circuit connection, Fault loop impedance RCD test
checkpoint-status |  |  | checkpoint | Mains Reticulation
label | 0d10dc67-6830-5a43-860d-0e47eacc4e6d |  | note | Visual inspection, Earth continuity, Insulation resistance, Polarity, Correct circuit connection, Fault loop impedance
checkpoint-status |  |  | checkpoint | Other (Specify below)
text | 99630a76-956c-57e6-add1-a117a3ceabaa |  | textbox | Other (Specify here)
label | 676e2d96-9459-593c-9a5c-889efdbeb8cd |  | note | To be determined by competent/qualified technician
checkpoint-group |  |  | section | CB 1
checkpoint-status |  |  | checkpoint | CB Details
text | 16f69049-c5f8-54bf-b26d-8e1233f6854f |  | textbox | CB #
text | 6b1cd0c3-e2a5-51db-a31b-778f9589077e |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 2
checkpoint-status |  |  | checkpoint | CB Details
text | 50888580-0099-527a-a12e-a892e861bebb |  | textbox | CB #
text | 653d19f9-3df1-5c79-afa1-70558b915a7c |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 3
checkpoint-status |  |  | checkpoint | CB Details
text | 394720b2-039d-5816-9752-a1dd55aada1d |  | textbox | CB #
text | e3be4677-a2e0-5a41-be4f-c5ffa696e427 |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 4
checkpoint-status |  |  | checkpoint | CB Details
text | 3aa411f4-cd21-545d-bac5-2612f0a67a4c |  | textbox | CB #
text | a23624f1-cd0a-5f3c-8706-3b541d8e74f9 |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 5
checkpoint-status |  |  | checkpoint | CB Details
text | eb616c57-2a6d-5f1d-8607-1d780b41428c |  | textbox | CB #
text | e7ca84eb-72e4-5aae-a7e5-6fce6d8a15f3 |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 6
checkpoint-status |  |  | checkpoint | CB Details
text | 1242a75e-6319-5d92-b3fa-767b3bef0647 |  | textbox | CB #
text | c6a68e1a-2fb4-599a-899e-8b9ec96b2f4a |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 7
checkpoint-status |  |  | checkpoint | CB Details
text | b2a49737-c6f4-5c63-af6e-63bd2c50b2f1 |  | textbox | CB #
text | b0e034e0-6258-524b-a042-96aa93d7c100 |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 8
checkpoint-status |  |  | checkpoint | CB Details
text | e24e3d3e-0c8e-5162-91ab-4ae454b8d47d |  | textbox | CB #
text | 3d05dbb9-739e-5c11-8a62-c52f5acda44c |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 9
checkpoint-status |  |  | checkpoint | CB Details
text | 4187a68c-629c-5608-8469-dea23d2b6263 |  | textbox | CB #
text | 7687a115-976b-53d6-920f-75d4d1638dab |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checkpoint-group |  |  | section | CB 10
checkpoint-status |  |  | checkpoint | CB Details
text | ac0e0236-f71d-5515-9085-5ff398a4c5aa |  | textbox | CB #
text | dcbaea37-11d4-5dec-ae70-1ed8cb7378d1 |  | textbox | Circuit description
checkpoint-status |  |  | checkpoint | Visual Inspection
checkpoint-status |  |  | checkpoint | Earth Continuity (Pg. Resistance)
checkpoint-status |  |  | checkpoint | Insulation Resistance (Pg. Insulation)
checkpoint-status |  |  | checkpoint | Polarity
checkpoint-status |  |  | checkpoint | Correct Circuit Connection
checkpoint-status |  |  | checkpoint | Fault Loop impedance (Pg. Resistance)
checkpoint-status |  |  | checkpoint | RCD Test (Pg. Proactive)
checklist-sectioned |  |  | checklist | DETAILS & 10x - AF-502 - Electrical Services commissioning Sheet - Protective Device Details and RCD Results (Rev 0 +Names) |  |  |  | 0 | Yes | DETAILS & 10x - AF-502 - Electrical Services commissioning Sheet - Protective Device Details and RCD Results (Rev 0 +Names) | bab0ae72-9477-460b-b6e5-7a7440e7517b
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | c998f075-c7a3-59ee-bcf9-a99b61af2cfa |  | textbox | Test Date
select | 67b81411-886a-5865-ace3-3d40f4eb2e01 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 4fac9ab7-0599-51d4-b89c-b1c48f197ff0 |  | textbox | Other (Specify here)
boolean | 857add40-2f9e-5e4d-ab76-ffebc3e0ed6c |  | tickbox | Signature added below
checkpoint-group |  |  | section | Circuit Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 0e1575c4-8e7f-5b7d-9f24-652e88e4ab50 |  | textbox | Designation of service
text | 0d60bf4e-5b1d-5231-a25f-a4c340693666 |  | textbox | Location of Service
checkpoint-group |  |  | section | No. 1
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 47e9fd45-c09e-5287-987a-928ff1dedf4e |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | e070ca8a-8777-5143-be4f-e7e9bca0ea4a |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 1b53e290-2d59-5629-a00b-825ea3d807d2 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 05890e11-69f4-519e-8c80-4b59f1a3bdd1 |  | textbox | 0.Deg (P/F)
text | 7586b8a8-3186-587b-bdc5-8fb652f64776 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 0a51bf93-f5d2-5339-bad6-6578466a37af |  | textbox | 0.Deg
text | 18b2f850-1c81-5443-9730-675f61b74758 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 3e854118-df53-50a2-b81e-b292b79bef66 |  | textbox | 0.Deg
text | 80d196b7-5025-51dc-a89d-f756aede4fb6 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 60c7264f-e8a4-541d-8d17-35f6ba0d3fa0 |  | textbox | 0.Deg
text | 1eddbb82-095e-57b3-b69c-87fda4d52f5a |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 71265b4a-9b46-56a4-9e37-97126bd7b72f |  | textbox | Action taken
checkpoint-group |  |  | section | No. 2
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | f5982834-099b-5f15-9074-7a081ffd1c5b |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 94a74283-c3ac-52b3-af26-52cc18b5f554 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | d20a2685-34a4-5819-8e0b-412ae3251f9b |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 92b73982-6912-5e93-8149-dd2d035fbbd3 |  | textbox | 0.Deg (P/F)
text | 70b4430a-8a96-541f-8d49-8636d25f8318 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 919f7ed8-c02e-5179-9b90-8ab86687e00f |  | textbox | 0.Deg
text | 9fa2c18c-4ae9-5ca1-a871-4dc74f1864a1 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 7594fa53-65fe-58d5-9d34-d214bb8c61d2 |  | textbox | 0.Deg
text | fae514d5-3eaf-5655-918b-de7e3efaa8f5 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 54ea5129-4a73-5f79-9a8b-fbf7a3fc3a0a |  | textbox | 0.Deg
text | b43806c0-bb85-5bc6-9b95-8f250e15607c |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 84735f99-a7ca-51fc-bdbc-4fb0aa64f1a7 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 3
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | e719e413-3c92-52bc-90c7-94dca09383dd |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | bfcb115f-967a-55a8-bdc3-00362c088e12 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 705b59a6-a519-5fcf-8a36-8ce83882dece |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | dbc0125e-a09f-52aa-a375-0535a1ba02a3 |  | textbox | 0.Deg (P/F)
text | c2bda63b-6d19-5c3c-9d7a-749874cfe8c7 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 8ba9f847-e84f-5c8d-93b9-7b19055d8ecc |  | textbox | 0.Deg
text | e226582e-b63c-5fb4-b712-709555665478 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 2314dc68-d05f-5137-91d1-3e8d0136971f |  | textbox | 0.Deg
text | a4fa858e-0854-5e17-86c2-b32de6e20f8a |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | d19cf2b0-ac7a-5f3d-a40b-c45a49d5a496 |  | textbox | 0.Deg
text | b265990b-faf7-522a-848a-1f42bccf8000 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 798dac15-b1c3-57b8-8384-f3d90abefe49 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 4
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 40d56713-9828-56f7-a222-5b96987bf0b9 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 9408852f-795a-5fb8-ad6b-8e01546f18a9 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 227688f9-0e6e-54df-b4c9-97710adf2b13 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | f226abf9-bd73-5a98-8c94-f8c76a999372 |  | textbox | 0.Deg (P/F)
text | e1ac26b4-23b3-5eec-81c3-bb2cb4ad6d45 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 50db21dc-7e6f-582e-8ab3-a1a5f169afba |  | textbox | 0.Deg
text | d928ce75-42b1-5174-bdec-329dfb17328b |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 644b1155-62c7-535b-90a4-0a95b2f58307 |  | textbox | 0.Deg
text | e6210688-973a-5ee2-971e-a29d46f25d41 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 45bba4c9-20e0-5bd5-bebc-e8b7e3e2ac8a |  | textbox | 0.Deg
text | 5494758d-6d17-5bb0-84bf-4271f91c59d7 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 081c5e2d-f331-533f-8d35-8a8c90579568 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 5
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | b323e35b-6adb-5ae1-92d4-7ede21ea51b1 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 29801cff-6042-52a2-ae67-79e0c8240ce3 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 1db212a4-de40-538a-91f1-4ccba216dfc9 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | bd246490-f495-51ac-97dd-71976ad8376f |  | textbox | 0.Deg (P/F)
text | 937c3c01-ddbb-5ab8-8967-bd2b9bc7c25d |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | f410806c-6288-5b58-9515-517c1ec45f3e |  | textbox | 0.Deg
text | eee07daf-5321-52df-8159-b446556c7073 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 0b67347d-e33f-5a29-a510-5e83179e3336 |  | textbox | 0.Deg
text | 5b192f31-a3a3-5f15-855a-1d3c4538a763 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | ae7a4a44-16a1-50a8-856e-e9af915eb53a |  | textbox | 0.Deg
text | 5f6a8a1d-a738-5f4c-9581-b4dd428a3a35 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 52e16530-2a7d-55fe-9c7c-774cc0bfb658 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 6
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | dfff2c96-3513-5968-ad4d-b675141e18ac |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 9b572051-1067-5ad5-9438-04c37680b246 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 2a7dfa70-77e4-5de9-aa5d-dd81fd44ddbf |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c0f88372-1943-5bd8-bc75-6fd4f6511019 |  | textbox | 0.Deg (P/F)
text | 79440df2-81c7-5284-9ae8-d32ae72989d6 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 6447cd75-b248-55c8-a2fd-4e624e8b3cc7 |  | textbox | 0.Deg
text | c1bbaf99-3255-557e-95b4-f584a2a0267e |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | ee850734-ab00-59dc-bd08-009bc59f16db |  | textbox | 0.Deg
text | f5a6522f-c2b8-5f05-9001-d3fbb08b2cd8 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 20f72f33-d17e-51d3-8e8b-0643edf6f200 |  | textbox | 0.Deg
text | cf9e6b03-58fc-5944-b503-c338b323df92 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 76e54694-4e09-5211-ab86-cd228f3ba75b |  | textbox | Action taken
checkpoint-group |  |  | section | No. 7
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | a46ee438-cbba-56f3-9339-571a26f0b90b |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | dea5288f-f59f-5085-b32c-429ef0f41854 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 58a6ef33-053f-541a-ae5d-73b54f3d22bd |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | a1077eca-a3a2-5398-9aad-d957a9d160d8 |  | textbox | 0.Deg (P/F)
text | 8eeceb61-812a-50b2-9146-efafa8649819 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 66185b9b-cd40-5521-9b96-e7d09d467551 |  | textbox | 0.Deg
text | 54b15066-3d20-5939-8e99-f4e22df18043 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | e74418b7-aa5c-52bc-a959-d0536a5420e8 |  | textbox | 0.Deg
text | 7a55d727-4f75-538b-aaf9-47f07963f790 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 20a1ba50-a7e7-5aaa-9867-7e3ec539621d |  | textbox | 0.Deg
text | 05ad1d05-e00b-5af2-96d8-1158805f78be |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | ea4768cc-8764-5cd1-a6e6-82570dd6f2b7 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 8
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | edf8f01e-994c-5cdb-bfc8-8dca5825a7ce |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 589e9d8a-6c5e-5040-9f0f-553747d1a403 |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 842f3488-8a41-5d25-9942-1e04afeb76a9 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | a7547356-d973-5e64-b858-a093e41900f3 |  | textbox | 0.Deg (P/F)
text | ebd5a726-6bb0-569e-8b44-3d4953244c16 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | d5630552-4637-522c-99bd-f64ab1deece8 |  | textbox | 0.Deg
text | 04b78f9e-d000-56f4-9146-5342bb214c6c |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 7f3abe8a-75a7-5f17-a415-f9bd7cac84bb |  | textbox | 0.Deg
text | 35273982-3412-5aa8-a5d0-3b85eccce0d2 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | ad973681-e94f-50f7-b6ff-7365a83eb568 |  | textbox | 0.Deg
text | 4a67b8c2-7106-5d9c-b7fa-b9b6c136aee7 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 921b293b-108c-5f21-9dc0-63e47db545a3 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 9
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | 4dd03e28-9350-5972-8112-33e2aa4c5b7d |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 6a9a7081-1406-518f-87bb-74eb83b309ff |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | 220ab311-e9e4-54b5-a4ad-7ca78788f7f1 |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | ae07dfc1-2cae-5b92-b91e-1c0cc0954fa6 |  | textbox | 0.Deg (P/F)
text | 52fe8ff7-9534-5cd3-a83c-5989ea9772e2 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 9098f71a-781d-5315-bf9c-e569c1cd4615 |  | textbox | 0.Deg
text | d21990e1-6915-55b5-b08a-72391229cf68 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | b0ca8f0d-cf22-5dfc-9a3f-71f4877b0087 |  | textbox | 0.Deg
text | dc7b12f6-673b-5b76-85f4-ea1fc8bd79fe |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 083890b3-3336-5d5b-89c1-7a88d752353b |  | textbox | 0.Deg
text | 182c2866-18a6-5cb9-8480-bb864fbe5401 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 028396b4-2444-56b5-9f59-7694dbefe540 |  | textbox | Action taken
checkpoint-group |  |  | section | No. 10
checkpoint-status |  |  | checkpoint | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
select | a97a7ce3-eb78-5f1d-ae19-58f9d91153d6 |  | dropdown | Device type | RCD, RCBO, CB, FUSE
select | 36f7bb51-d499-5b87-b02b-21ca943cc5ee |  | dropdown | RCD Type - Where applicable | A, AC, B, F
text | c3cb2139-8d32-5cd9-9e1d-a9a716d56e8b |  | textbox | Nominal Trip Current (may)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d7e70706-f6dd-55d1-941a-58927dcac089 |  | textbox | 0.Deg (P/F)
text | 9f9cce1d-d11b-5b11-b426-845aa0534be3 |  | textbox | 180.Deg (P/F)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 2721512c-f2e8-5780-8d5e-1a76dc586430 |  | textbox | 0.Deg
text | 7e786154-8a89-5969-a53e-78f83c35ad1b |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <150ms - x2 Trip Time (ms)
text | 89e357fe-917c-518c-93c4-5e2f0b9a3a00 |  | textbox | 0.Deg
text | 5bd6e0db-42bd-590a-ab53-150538fa0137 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 2c22bd0e-6c77-5d69-a568-c90ea0ebb3b4 |  | textbox | 0.Deg
text | cc21834f-517c-52c3-8b1e-bf913448d9d5 |  | textbox | 180.Deg
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 1cf98f82-c58d-5de7-95b5-92f3fc8336b5 |  | textbox | Action taken
checklist-flat |  |  | checklist | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) |  |  |  | 722 | Yes | AE-ITCX-030 - Cut-Out Sheet (Rev 1 +Names) | c31e9bf7-cce6-46eb-b446-834b4d4d5ee4
checkpoint-status |  |  | checkpoint | Walls cutout
button | e6676fd6-b45c-5ad3-9a3d-a10bb364ee4b |  | button | Wall Cut Out is complete and cables have been located and withdraw from wall cavity. | Yes,No
button | 6e89adf4-098c-56a9-b634-8f68d1b3bb3b |  | button | Cut outs with obstructions have been resolved? (for example furring channel, main bar) | Yes,No
label | 6d12ca34-b831-5b39-9358-5f2b603c814e |  | note | Additional photos of Obstructions
checkpoint-status |  |  | checkpoint | Ceilings cutout
button | 719b0bf4-50ea-5b92-be66-1c38e8f2d379 |  | button | Ceiling Cut Out is complete and cables have been located and withdraw from holes. | Yes,No
button | ce354e55-e501-5db1-b375-d44a750542ea |  | button | Cut outs with obstructions have been resolved? (for example furring channel, main bar) | Yes,No
label | c63ffdaf-c1d8-5c09-8b70-02c2afbc05aa |  | note | Additional photos of Obstructions
checkpoint-status |  |  | checkpoint | Fire Rating - (Note this is note the Fire Register!)
button | b9f1ba7b-fd18-5de9-8880-15652b1a2a73 |  | button | Fire boxes installed correctly on all fire rated walls with cables withdrawn from wall cavity. | Yes,No
button | c810522a-9ea2-5da2-999e-979f3548af96 |  | button | All wall penetrations, distribution boards and cables drops from top plates are appropriately sealed and labelled. | Yes,No
label | 49d1812e-bf1e-5982-8619-23b30e29ca05 |  | note | Mandatory photo of completed fire rated locations (Fire Register is recorded separately)
checkpoint-status |  |  | checkpoint | Cut-Out completed to specification/drawings - Area left clean & tidy
label | f6fb6151-89f5-53a2-b44d-775501513785 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 5c33d0c2-a99b-5976-a920-25fe8e51a444 |  | note | Any Corrective Actions to be Photographed & Commented below
select | 9f760ae8-ff6a-5890-86f6-18f3f2e1fc02 |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622, ADAM STRONG - AGrade: A38815 - Employee#: 2002, ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794, ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684, ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863, ALAN BIRCHALL - Agrade: A18981 - Employee#: 379, ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111, ALI HASAN - Agrade: A48087 - Employee#: 1654, ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015, ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957, ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972, ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309, BEN DARBY - Agrade: A53332 - Employee#: 1702, BEN FINDLAY - Agrade: A41429 - Employee#: 2006, BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933, BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733, BENJAMIN STEWART - Agrade: A50504 - Employee#: 1865, BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801, BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850, BRENTON HILL - Agrade: A47213 - Employee#: 1729, BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887, BROCK DOWNIE - Agrade: A53290 - Employee#: 1849, BROCK LLOYD - Agrade: A44808 - Employee#: 1680, CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644, DAMIEN CASEY - Agrade: A39744 - Employee#: 1193, DANIEL BENDINELLI - Agrade: A67728 - Employee# 2097, DANIEL MILLER - Agrade: A42685 - Employee#: 1909 , DANIEL SETTE - Agrade: A50502 - Employee#: 1812 , DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194 , DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937, DAVID OLSEN - Agrade: A42915 - Employee#: 1685, DEAN NGUYEN - Agrade: A48514 - Employee#: 1515, DEREK JACOBS - Agrade: A67318 - Employee#: 2078, DWAYNE KLOET - Agrade: A48278 - Employee#: 1239, ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782, EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895, FERGUS COATES - Agrade: A59054 - Employee#: 1774, FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679, HUY DO - Agrade: A40954 - Employee#: 873, IMMANUEL KAWITI - Agrade: - Employee#: 2023, JACKSON SHARPE - Agrade: A53801 - Employee#: 1540, JAMES MARASCO - Agrade: A55184 - Employee#: 1758, JAMES PLEASANT - Agrade: A62956 - Employee#: 1976, JAMES SPOKES - Agrade: A48756 - Employee#: 1770, JASON CRAMER - Agrade: A57832 - Employee#: 1673, JASON GARETTO - Agrade: A46469 - Employee#: 1896, JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756, JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719, JASON PERL - Agrade: A36692 - Employee#: 1868, JASON SALE - Agrade: A28662 - Employee#: 1615, JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029, JESS ZAHRA - Agrade: A52969 - Employee#: 1403, JOEL BASSETT - Agrade: A39498 - Employee#: 1958, JOEL COGHLAN - Agrade: A43339 - Employee#: 1220, JOHN BATTISTA - Agrade: A41810 - Employee#: 1908, JOHN GREEN - Agrade: A55589 - Employee#: 1734, JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682, JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720, KALE BLACKLER - Agrade: A39293 - Employee#: 1751, KAYNE WALKER - Agrade: A38805 - Employee#: 1718, KEVIN MURPHY - Agrade: A63544 - Employee#: 2022, KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698, LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834, MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308, MARK D_ANGELO - Agrade: A40610 - Employee#: 1832, MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352, MATTHEW COX - Agrade: A42092 - Employee#: 1704, MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894, MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915, MICHAEL BRASHER - Agrade: A29237 - Employee#: 954, NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748, PAT DOUBLE - Agrade: A46604 - Employee#: 1118, PAUL HARMAN - Agrade: A26306 - Employee#: 1728, PAUL RABAHI - Agrade: A52747 - Employee#: 1939, PAUL WAISTELL - Agrade: A41819 - Employee#: 1190, PETER LEWIS - Agrade: A53556 - Employee#: 1749, PHILIP BROWN - Agrade: A55466 - Employee#: 1940, PHILLIP CHOW - Agrade: A55466 - Employee#: 1612, ROB POLLARD - Agrade: A56906 - Employee#: 1754, ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132, RYAN DEPRADA - Agrade: A41361 - Employee#: 1848, SCOTT RYAN - Agrade: A59062 - Employee#: 2017, SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034, SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771, SIMON COLLARD - Agrade: A32749 - Employee#: 883, STEVEN THOM - Agrade: A48941 - Employee#: 1199, STUART MALVENAN - Agrade: A61071 - Employee#: 1829, TOM HAMILTON - Agrade: A48254 - Employee#: 1434, VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218, WILLIAM FISHER - Agrade: A20679 - Employee#: 859, Other (Specify below)
text | 91d22d34-6a59-5bf2-9b86-9cdd771cb7c9 |  | textbox | Other (Specify here)
label | bff23e7a-2029-587f-9898-635f3657e625 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-004 - Construction Emergency and Exit Lighting to AS 2293 Logbook (Rev 0 +Names) |  |  |  | 0 | Yes | AE-ITCX-004 - Construction Emergency and Exit Lighting to AS 2293 Logbook (Rev 0 +Names) | c4aac035-3974-476f-87df-0cdc3d0e79d1
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | f6af00fb-83b4-5992-86c9-bcdfb9b5dff2 |  | textbox | Building/Level
text | ec6bf84a-d912-51ca-a0f0-6ab8107cbe68 |  | textbox | Switchboard No.
text | 64c13d38-dd1a-5c0e-8675-53b0c669f11d |  | textbox | Circuit No
text | 7e87cdce-8e7b-51e2-a35b-d75fd6045e32 |  | textbox | Test Date
text | 1697067c-a0e9-5661-ba92-a2f3d6a23184 |  | textbox | Start Time
text | f53f70f8-ab9a-5ee5-a40f-234fadb51d72 |  | textbox | Finish Time
select | 18a996e2-d987-5eae-af33-8e54015deba6 |  | dropdown | Tested By | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | bd72395e-d7d0-5467-a2af-537b12e54dcd |  | textbox | Other (Specify here)
boolean | 1a798649-4849-57b4-8d30-d7c69bb49439 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Fitting No.1
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | 84d268ff-fda5-5593-8dea-01ffb12b0eff |  | textbox | Fitting No.
text | 3fe86d63-e584-5463-a14e-5b25bbbded32 |  | textbox | Fitting Type
label | 971bf772-0125-551e-8429-05996f618aa1 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.2
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | 32c439ad-7211-5205-a8d0-40e7710d0114 |  | textbox | Fitting No.
text | 106e307f-5385-50c7-9c5b-23f20df35a1f |  | textbox | Fitting Type
label | 2fb02810-93d0-53be-b69c-80e5419c6058 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.3
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | 4ab0fa8a-826c-5e84-985b-da7e51baa5b8 |  | textbox | Fitting No.
text | 0352abeb-b3c5-5b23-be5b-12666572928e |  | textbox | Fitting Type
label | c3da7935-eca8-5a34-b27f-371b89af6bd8 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.4
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | f2421739-65f5-58f0-ad88-89716a87107d |  | textbox | Fitting No.
text | 8eb1d672-eb83-5af4-b7f0-56d440a5151f |  | textbox | Fitting Type
label | fe48ff31-568f-5320-a04e-5692ed8126ec |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.5
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | a52fa7f0-70e9-59e5-8201-5c633487627e |  | textbox | Fitting No.
text | 48ed1568-6676-5bc2-8ce2-f2178f865259 |  | textbox | Fitting Type
label | 5516c7c6-7609-5357-96d0-361ae516cdf4 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.6
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | d31041fc-e1a6-5e7e-aeee-c7c875fe2a7c |  | textbox | Fitting No.
text | bd21dccc-4bb9-5768-b166-b0dd96e768be |  | textbox | Fitting Type
label | 13b21b85-606e-57ce-8265-d20d7b6e7de4 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.7
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | a6f60c04-90fc-5a8a-bd6b-653a92c468d3 |  | textbox | Fitting No.
text | 41c954fb-d753-56f8-9e17-860ced32c70a |  | textbox | Fitting Type
label | 9ba75e08-ec84-582c-b2a4-6b1aad00a652 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.8
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | d9e81053-108f-5bd0-8c30-05fbebc88dfb |  | textbox | Fitting No.
text | b39ebd49-1fa5-5b76-88de-fb3fb3de4490 |  | textbox | Fitting Type
label | d8ed8bd5-4e78-586f-8023-d0535185790b |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.9
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | 9ce729bd-2da5-5e6c-a16f-471444aadfb1 |  | textbox | Fitting No.
text | 0a1b451f-bf31-5f34-a901-0241b8ce3c90 |  | textbox | Fitting Type
label | 18d55558-5d6f-5c57-a4d2-be67ad021de5 |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checkpoint-group |  |  | section | Fitting No.10
checkpoint-status |  |  | checkpoint | Fitting Details - Pass once entered
text | 379c6162-0b9d-5245-9326-b84c451734d4 |  | textbox | Fitting No.
text | 5496f3f4-eb43-5466-9550-f6015e6efb21 |  | textbox | Fitting Type
label | 97bbb494-5815-5b8d-b409-78f494a85bfc |  | note | Report/Repairs undertaken photograph/comment below
checkpoint-status |  |  | checkpoint | Fitting Condition
checkpoint-status |  |  | checkpoint | Lamp Operation
checkpoint-status |  |  | checkpoint | Operating Time
checklist-flat |  |  | checklist | AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) |  |  |  | 2 | Yes | AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) | c8569b35-88d6-4296-b26d-22fe54e4606b
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 3e9620a5-d43d-57e8-a087-623de9642fac |  | textbox | Switchboard No.
text | 0d0771a5-5673-5344-b5f4-3fbcb10e585e |  | textbox | Drawing & Revision #
checkpoint-status |  |  | checkpoint | MEN and MSB Meter Panel Checklist (AF019) complete
checkpoint-status |  |  | checkpoint | Main switchboard location and clearances as per AS/NZS 3000
checkpoint-status |  |  | checkpoint | Perform insulation resistance test on main switchboard
checkpoint-status |  |  | checkpoint | Service protection device set and labelled
checkpoint-status |  |  | checkpoint | Consumer mains entry point fire rated
checkpoint-status |  |  | checkpoint | Emergency and exit lighting complete
checkpoint-status |  |  | checkpoint | Access/egress doors installed and labelled
checkpoint-status |  |  | checkpoint | Switchboard room fire rating confirmed
checkpoint-status |  |  | checkpoint | Verification of Switchboard Integrity by Supplier (e.g. Aline Final Inspection & Testing Checklist)
checkpoint-status |  |  | checkpoint | Electrical inspection – Prescribed Works Certificate signed
checkpoint-status |  |  | checkpoint | Power Supply Authority energisation sign off
checkpoint-status |  |  | checkpoint | Main Switchboard works completed to specification/drawings - Area left clean & tidy
label | f8e387c5-59f3-5416-9da8-ea1b73a28a74 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 254c4d00-2935-5b47-bbb4-e11d3606d6de |  | note | Any Corrective Actions to be Photographed & Commented below
select | 2b3650c9-ce5e-5c60-9248-adcaf118b812 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | ea4954ca-9706-529d-a08a-9ab75fb1fd32 |  | textbox | Other (Specify here)
select | 7cef845d-6c9b-5e27-91f7-c5618952ae23 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 7c154d78-d6a0-5392-99e7-717611c50c90 |  | textbox | Other (Specify here)
label | bc054a9d-5668-539c-b236-19c3b315880f |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AF-502 - Electrical Services commissioning Sheet - Details & 10x Circuit Resistance & Fault-Loop Impedance (Rev 0 +Names) |  |  |  | 0 | Yes | AF-502 - Electrical Services commissioning Sheet - Details & 10x Circuit Resistance & Fault-Loop Impedance (Rev 0 +Names) | cc5554dd-71a1-4cb9-98b1-830dc8063d91
checkpoint-group |  |  | section | Electrician Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | 006ffb26-a9c1-52b2-8e40-d78a21e137d8 |  | textbox | Test Date
select | ac3241c6-311c-5be7-9a04-50b68aec8dcb |  | dropdown | Name of A-Grade Electrician | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 340396cf-5437-5938-a6bd-0331a543cf38 |  | textbox | Other (Specify here)
boolean | d3dd1209-cf20-5836-a8c8-e5d8965905e6 |  | tickbox | Signature added below
checkpoint-group |  |  | section | Circuit Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | d794ea60-2f83-5f36-b12f-8398333b43ba |  | textbox | Designation of service
text | 8d5688e8-4405-5879-a7c0-e39b720065cd |  | textbox | Location of Service
text | 459a4b4c-447d-58fb-9657-f15c0b3add9f |  | textbox | ZE
checkpoint-group |  |  | section | No. 1
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | dc96969a-593f-5ca4-9dc3-47da58937d17 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | b3620806-244e-5b2e-a8b9-01a83ebb8281 |  | textbox | Type B, C, D, TM Electronic
text | e904e9b9-4841-5dd6-b42e-d04cf9b03356 |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | fe7b8915-821b-5b3c-b542-48de85dcd30d |  | textbox | (A) Active CSA mm2
text | aac8b594-df05-5a34-b675-2b1250fb53fa |  | textbox | (B) Earth CSA mm2
text | d2b5ce69-a701-5806-88f4-3e45d7efcead |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 54b0775d-ecb5-566f-ac34-32a02843608a |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 77a92029-0d60-5c61-87a7-9d84eeabb03e |  | textbox | RE = (D/C) * A
text | 02fbfee8-327a-5fb3-bbaf-f1ccc16f336b |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | b4305d22-dade-5724-b4c3-09931ee24030 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 95a56d97-831a-5bf8-99d3-d1c558adc82b |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 2
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 6db18607-dcc1-59d8-b3ce-64ba7f67fe9d |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | f854ded9-e78f-535d-8c8b-8cff24b47661 |  | textbox | Type B, C, D, TM Electronic
text | 51a54950-ae4c-539a-ae5f-eed438b6fabf |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | bb195a18-6a8f-51d5-8de2-226a57fb28f7 |  | textbox | (A) Active CSA mm2
text | fbe809e7-abee-5f7a-851a-6bb842ea1527 |  | textbox | (B) Earth CSA mm2
text | 25ab9952-4d8a-57d9-b6d4-0e8f30d25ef4 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | cd0e7162-ddc3-5e06-9dbd-ebb4d7ab7e36 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | e235a3a5-54ee-5267-b5d5-9535f6779f31 |  | textbox | RE = (D/C) * A
text | d5c38683-7346-5e4f-878e-7abc4062b70c |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 254b32d0-48d7-5ece-b78b-bbef9cba7f36 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 18b5cf42-c639-5680-9077-4f3f193e6f2c |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 3
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | e6ad1ff1-a220-56a0-9ac7-abb799980746 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 304aef7f-5ad3-531f-b4a1-057f316c371f |  | textbox | Type B, C, D, TM Electronic
text | ec740c74-4206-504f-be0c-e47184b2152f |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | f3c4cec3-4aa5-540d-9349-85aa83f9fdfd |  | textbox | (A) Active CSA mm2
text | c673ae7d-6fde-5120-953f-84dab010b963 |  | textbox | (B) Earth CSA mm2
text | d6e59680-58ce-5f6c-ae61-e21c6671d24a |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 19bdf3ef-fbf4-512f-b579-a710585865dd |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | efa7a694-22ec-5c68-80a1-c71c5cc4ee36 |  | textbox | RE = (D/C) * A
text | c2144bae-f199-5545-b9fd-a401aedd093b |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 4e168ad8-14a7-5b10-88cf-6d51fa79a774 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | b2540b37-61a7-5965-b9d2-04e587a25c48 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 4
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | fe4233b8-e639-5c05-8d02-7a00ed186e0d |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 45b1db85-b384-5be5-97e0-ab9a7d602e98 |  | textbox | Type B, C, D, TM Electronic
text | 592b3233-6448-5b4b-9a90-a4e1d991a053 |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | 2eeee5ad-ea81-5562-91e2-3de0293cb8c4 |  | textbox | (A) Active CSA mm2
text | 062861b2-3e24-5f5a-ab2c-66ed31477393 |  | textbox | (B) Earth CSA mm2
text | 2c913251-919a-5975-a3d2-48c782ed9942 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 29080db7-3a45-5db7-add8-9fd60f4ae565 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 97759b75-8e3c-58fe-b9e9-6166abd39dc0 |  | textbox | RE = (D/C) * A
text | 5cd7ae10-2889-58f8-ac60-43e6b0a5ef7e |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | bd9e7ab4-c1d4-5900-95fb-279d955722cc |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 741e8548-0923-5e7f-b375-97a8972b608a |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 5
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 9e3e0234-e6aa-5c13-a3b2-f27fe8a8ee4b |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | ea8d29d8-931b-5498-80a4-cc667f9c2bfa |  | textbox | Type B, C, D, TM Electronic
text | d4e85c9b-b93e-5f98-88b0-912280ea383e |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | f34e0e58-33d8-5bbd-97a9-9394b7ee9bea |  | textbox | (A) Active CSA mm2
text | 3599f6ae-140a-50fa-90b6-3ff2496845f1 |  | textbox | (B) Earth CSA mm2
text | 51b0918e-1bdc-5bfd-a2a7-54d6f8841e59 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 4437c644-f476-5821-9043-0de7fb6d382d |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | fbbeb9ca-b553-51f9-939e-38b7335fa830 |  | textbox | RE = (D/C) * A
text | 8207e2f6-f6d7-5f1c-ba0a-732ed56c3fa4 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | c08cfcc9-4f42-585a-a319-eaebfd68eecc |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 52939ff7-5fe5-5783-bcce-3b5c73cdfadd |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 6
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | eb9bdc07-8aa6-5c23-9615-e5a1672cf9cc |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 754221d6-cc23-53d6-a07b-fc0a2c40d937 |  | textbox | Type B, C, D, TM Electronic
text | 8a2890ee-ceb2-5a6a-a73f-22b957fc905a |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | b376d4e5-7f4c-5e7a-bed4-c9fe44bbd3e0 |  | textbox | (A) Active CSA mm2
text | bbb27ac0-b73e-5f26-8d61-aadf8ed46328 |  | textbox | (B) Earth CSA mm2
text | 5158112b-dfd2-5f61-9006-38496c5f5ef6 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | f29af7b2-bdd9-59bb-b700-f11b8ab99763 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 3d1653e4-b177-5fde-abf4-48bf82b41114 |  | textbox | RE = (D/C) * A
text | 84922ae3-64b4-540e-99b6-6bc6c48f22ad |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | 53af2383-d063-5630-bb2d-3217119b181e |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 8f528ed8-90da-54eb-8848-228b8f040a01 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 7
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 3259f405-5761-5b22-8f97-c1b00dff231e |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | df897743-1a11-586d-bbda-453ed75f1e22 |  | textbox | Type B, C, D, TM Electronic
text | 6373fd82-ebe5-5fd0-8a7c-8e00f1804bfa |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | fc90f08a-8a35-5f40-b943-31255013b24c |  | textbox | (A) Active CSA mm2
text | a2628f16-c140-561e-8418-ae736698a8f5 |  | textbox | (B) Earth CSA mm2
text | 5bca017c-955b-5f44-b75b-3793859900cf |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | f0908f57-8ce8-5b06-8a4a-e4cc23f7116f |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | e344a137-db29-55a0-a110-cabbcfabf4e5 |  | textbox | RE = (D/C) * A
text | 249d76de-8cc5-5141-8585-7456c4e0167f |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | d7d3bb5d-d2e9-53c7-9449-ab95c89dc617 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 0a2c0a34-f984-5417-9050-c365640fc978 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 8
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 3da054f8-d132-5faa-ade2-ed2d56f67361 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 178b4b19-0a35-545e-a581-4a5323b5bd58 |  | textbox | Type B, C, D, TM Electronic
text | 6993d499-e5bf-585e-a2aa-4050c905dc2f |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | ab2635fc-ff85-55be-9de0-98f5294f4410 |  | textbox | (A) Active CSA mm2
text | d02957c2-d0d2-5c66-81c7-8f21ed0dfa07 |  | textbox | (B) Earth CSA mm2
text | 6f2ad26e-dd87-593b-8311-39877d1da7e3 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | bb6b8666-bad2-5b4f-84bd-720eec10e909 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 0d3a1700-67a6-5e09-9728-99d455a36a92 |  | textbox | RE = (D/C) * A
text | 53ba8bf8-8d4e-51c4-8907-d78148516a20 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | f4a70b34-b9ef-51f3-b801-7778f13e9259 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 6b31c7bc-cc09-5eba-8e2e-504f84ce78a0 |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 9
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | f19a7273-19ca-5157-a6c8-d0d4ae6c09be |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | 9e1ddcb4-6b1c-5b04-a06a-72117984c42b |  | textbox | Type B, C, D, TM Electronic
text | c4217a41-ea66-594c-9ed5-df4e14c03ec4 |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | f26ece9b-0141-5d12-9fe9-f0bfef79c061 |  | textbox | (A) Active CSA mm2
text | 472ba63f-8ded-526c-89f5-690db0af11fb |  | textbox | (B) Earth CSA mm2
text | 5e197462-da72-5da8-8069-8fd93039815b |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | fe99d5cb-5563-5060-9fcb-d743d0bd7808 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | 1b40b1ce-cdfe-5955-abe1-fcce1f418c7d |  | textbox | RE = (D/C) * A
text | 894d2858-63fe-5819-828c-7b2f4f08f873 |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | f98b7730-eed8-5cfa-8cc5-92f9b6facafe |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 71798988-04b7-5526-bc08-9049ed9ef64d |  | textbox | Difference (F) - Calc'd ZS
checkpoint-group |  |  | section | No. 10
checkpoint-status |  |  | checkpoint | Overcurrent Device - Pass once entered
text | 6484a308-0cb5-583c-9383-309dc4881a23 |  | textbox | Short Circuit Capacity (i.e. 6kA, 10kA)
text | d57e7c05-2dcb-5339-a60d-469501decf02 |  | textbox | Type B, C, D, TM Electronic
text | ac1a7307-43a8-5a81-9785-7f313393cacf |  | textbox | Rating in (A)
checkpoint-status |  |  | checkpoint | Data Capture
text | 2cfb45ae-576b-562f-86e4-e1074f7d34db |  | textbox | (A) Active CSA mm2
text | 2de81698-c479-5b9b-95e3-20f9886fbf27 |  | textbox | (B) Earth CSA mm2
text | e1678631-8c23-54bf-abed-bdb6370b0048 |  | textbox | (C) = A+B
checkpoint-status |  |  | checkpoint | Measure
text | 91601649-6e31-59aa-a564-cbd6188fc639 |  | textbox | (D) Rphe (Ohms)
checkpoint-status |  |  | checkpoint | Data Capture
text | badf8170-6229-5685-8f90-bab8cda79fe3 |  | textbox | RE = (D/C) * A
text | 0a34ca59-d8cb-5785-abb4-68908c08a24d |  | textbox | Calculated Loop impedance = D + ZE
checkpoint-status |  |  | checkpoint | Measure
text | e5f29157-fc9e-5bc4-b3d8-a5a0c16d1d58 |  | textbox | (F) Tested ZS
checkpoint-status |  |  | checkpoint | Data Capture
text | 9c319d4f-e024-5dfa-97da-04ff99bc55e2 |  | textbox | Difference (F) - Calc'd ZS
checklist-sectioned |  |  | checklist | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) |  |  |  | 121 | Yes | AE-ITCX-002 - Monthly RCD Test Sheet (Rev 0 +Names) | d4a27ad5-9a97-4207-9c53-c0d2db62bb76
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7febf8ac-fbe2-504d-b45b-b17d05c1011c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 6f32795f-6f87-5a51-9daf-f8201cccbf23 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | c951c877-143e-5d13-b187-7dd9c04d9561 |  | textbox | RCD No
text | 3a1e5afa-e6c9-5116-ac04-636520b7c68f |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 127b9588-d5d3-501f-9de1-1bcaa2594213 |  | textbox | 0.Deg (ms)
text | f8fb5274-6dba-5fe3-9004-8f423498504a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 78122b77-9238-583e-bf5f-9d93fb360823 |  | textbox | 0.Deg (ms)
text | 550d811e-d87e-5113-a385-9ca5d865e869 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | b948baf9-543b-56ea-a7c8-f14f00fb5f42 |  | textbox | 0.Deg (ms)
text | 238daa5e-a234-55de-bca0-4498b7e1d939 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fb7a4dd5-8e60-556d-a7aa-81d8eb501530 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 95466412-27c0-5ce2-8c90-06dda9d4fd27 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 0398e3b3-f228-5563-a062-274c87ce6156 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 902cfe70-a186-55a2-bd85-ba8f0a8e2043 |  | textbox | RCD No
text | 240c2984-1a84-5bce-b4ae-a07f60ae3633 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 0b3d0642-a635-550b-9cac-93445f40d7cf |  | textbox | 0.Deg (ms)
text | 601a751c-2565-54be-9c49-eaaa28950134 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | d959b407-69f5-5aac-b064-730a749e6aa4 |  | textbox | 0.Deg (ms)
text | 7ae02c0e-950f-578b-bf84-5720599e4ee7 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | fe0111fb-375b-5120-a66a-9655215a3bad |  | textbox | 0.Deg (ms)
text | 888d7ad0-2ad9-51b5-9a3b-735f1ef6d7b2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 8b8265ae-3bbc-587b-bef2-ac7ffb14327d |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 9
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 2d313044-58bf-561f-af75-d45ea5c9829d |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 36adf6c2-0c7a-5d54-baaa-35b43a2f679e |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 8bef231b-1a76-542c-8db2-cee5f88a2248 |  | textbox | RCD No
text | ff437b9b-cb6b-59f4-8700-922c9cea1047 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 12d9e349-7fcd-576b-9f50-96067e293d0c |  | textbox | 0.Deg (ms)
text | 4ae61f83-4e31-55e3-9cf0-41f1b08cc59e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | ecc92d59-0eb0-56b9-8397-bf2dfe47a6da |  | textbox | 0.Deg (ms)
text | 903f6838-edb3-5174-b6ea-8129e41b1399 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 1246ac31-c8d9-5b61-973f-e72351f7e276 |  | textbox | 0.Deg (ms)
text | 4462a795-fd5a-53e0-a902-41456dc60394 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 349b0d2f-ebba-5f2f-9b45-a9fbe4e7f093 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 10
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | e0d2ed6c-1ede-5ded-a0eb-4f95f05e8ac3 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | dbce0000-d09a-5b46-ab1f-586fc551f637 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | fc8b3b3a-7da9-5dc8-b872-e5a6c8455af7 |  | textbox | RCD No
text | ba104c95-3670-526c-a891-d3ef15a9201e |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 5d1344d4-9d22-54c9-821d-3820e227e980 |  | textbox | 0.Deg (ms)
text | 966f4eb1-2cda-51e5-8817-09ba941eb9ef |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | cf6a6600-9391-5118-bccb-1f040987f9f0 |  | textbox | 0.Deg (ms)
text | 3163e0fa-e0f5-5d87-b982-e5da1f30f7dc |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 5b3b920a-ce6f-56c1-9e13-634d11a2e0aa |  | textbox | 0.Deg (ms)
text | da4d99ba-7a9e-5fb8-93a3-036a91e9fb8f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | c6ebc6b7-1662-5002-a1f8-f78af1dd71d5 |  | textbox | Action taken
checklist-flat |  |  | checklist | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) |  |  |  | 15 | Yes | AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | d865494f-b0b1-46a8-9d87-d2dec056df04
checkpoint-status |  |  | checkpoint | Latest consented drawings checked & referenced
text | 531b51ca-310a-5cfb-9cea-1e4cb02e4694 |  | textbox | Drawing & Revision #
text | f76188eb-8f41-5204-9694-e81e84b7ce02 |  | textbox | Position & Purpose of Cable Tray
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | 00a5d164-9429-5b02-bc81-897ee5be3aa2 |  | note | Attach Photos/Comments below if any issues & Send report to Builder
checkpoint-status |  |  | checkpoint | Plan & confirm cable tray route
checkpoint-status |  |  | checkpoint | Coordination of other services (Mechanical, Hydraulics Fire)
checkpoint-status |  |  | checkpoint | Correct spacing of brackets
checkpoint-status |  |  | checkpoint | Correct & suitable fixings for brackets
checkpoint-status |  |  | checkpoint | Joins of tray are secure
checkpoint-status |  |  | checkpoint | Tray is securely fixed to brackets
checkpoint-status |  |  | checkpoint | Check all hangers secure?
checkpoint-status |  |  | checkpoint | Check all lock nuts are tight?
checkpoint-status |  |  | checkpoint | Check the tray is level & straight?
checkpoint-status |  |  | checkpoint | Check no sharp edges or protrusions?
checkpoint-status |  |  | checkpoint | Update drawing for as built
checkpoint-status |  |  | checkpoint | Cable Tray works completed to specification/drawings - Area left clean & tidy
label | df1a5305-c689-5828-bd1d-38c52012cd9a |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
select | 4d9bfedd-851e-5aa9-95c8-9607f02d1a15 |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 5998fd83-3be0-5618-afd9-df463fc335bb |  | textbox | Other (Specify here)
select | b2c67cce-3381-5432-906c-4e4099978a7a |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 2232cc5b-62c0-507a-b527-07aa9925278c |  | textbox | Other (Specify here)
text | 650075a6-c798-5fb5-b536-d560e6070c13 |  | textbox | Witnessed by (Builder/QAM)
label | 2b2510d6-c346-5394-b8b7-ca48e840e561 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | Torque settings |  |  |  | 139 | Yes | AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | e62e9bff-d189-4327-976a-d62ab4420001
checkpoint-group |  |  | section | Reference Tables
checkpoint-status |  |  | checkpoint | Torque Setting Tables - Pass once tables are confirmed/read
label | 9d4de5ad-704d-5564-8baf-5e26bf010c91 |  | note | .. ..
label | 1cf30b0f-ee39-5e2a-8fb0-e6b6323acada |  | note | Lugged Cables
label | 8f5f1ab8-9f03-5b0f-9e5c-4645c20557b2 |  | note | M6 - Class 8.8 Zinc plated - 9 Newton Meters
label | 29a1074a-66b3-5365-b283-fe43c19a3347 |  | note | M8 - Class 8.8 Zinc plated - 22 Newton Meters
label | 1124947f-0aa0-555a-8a16-8e177a3ca33c |  | note | M10 - Class 8.8 Zinc plated - 44 Newton Meters
label | 19416309-70f8-51ea-b055-9a61fc8d7337 |  | note | M12 - Class 8.8 Zinc plated - 77 Newton Meters
label | e92ed372-74bd-546d-b97d-b29c65494234 |  | note | M16 - Class 8.8 Zinc plated - 190 Newton Meters
label | 1eefd331-cbba-51a0-9c94-1deae8d8574b |  | note | .. ..
label | 248b4d15-5f0b-5c2c-8001-e4f36b0ee834 |  | note | Bus Bars
label | a8ec7616-8ce8-5489-aa24-8b1e79851ab4 |  | note | M8 - Class 8.8 Zinc plated - 35 Newton Meters
label | 3d290ccc-af43-50ce-a652-d1b6922bde5d |  | note | M10 - Class 8.8 Zinc plated - 50 Newton Meters
label | 18acb1d3-a3cd-5830-aefb-f01971194d8d |  | note | M12 - Class 8.8 Zinc plated - 75 Newton Meters
label | 8124e62f-65c0-58ca-9268-1b5b4abc2c93 |  | note | M16 - Class 8.8 Zinc plated - 190 Newton Meters
label | d3c26282-bff5-535f-a27c-849c9599a2d6 |  | note | .. ..
label | b5293d94-1cfe-5428-a7d0-f13d9e860d99 |  | note | ALL BOLTS SUPPLIED BY SWITCH BOARD MANUFACTURERS, INCLUDING ALINE, ARE GRADE 8.8 BOLTS AND SHOULD NOT BE SUBSTITUTED
label | 4e2e8171-9ee1-5983-b38f-4477af8e72a4 |  | note | .. ..
label | 7e8264c8-9be8-5aeb-bc83-4f06499dad00 |  | note | Torque Settings for SAGAME IPCs
label | 634c0d5f-c2f8-5329-a10f-c4e152f84dfe |  | note | TTD051XFA - 16 to 95 (Conductor Size MM2) - 1.5-10 (Branch Cable MM2) - 9 Newton Meters
label | bd644fdc-7031-5289-b47f-d15c22a51424 |  | note | TTD101XFA - 6 to 54 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 9 Newton Meters
label | 96394299-76a7-571e-a01c-bf814e39c6bc |  | note | TTD151XFA - 25 to 95 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | 680a6d86-979e-50d2-84f4-88a26a4f2341 |  | note | TTD201XFA - 35 to 95 (Conductor Size MM2) - 25 to 95 (Branch Cable MM2) - 18 Newton Meters
label | 1ea26cd3-6dd2-5529-846f-04b948e267f5 |  | note | TTD241XFA - 50 to 150 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | b5c1c053-d63a-5d59-8a46-702a3e6e4a83 |  | note | TTD251XFA - 50 to 150 (Conductor Size MM2) - 35 to 95 (Branch Cable MM2) - 18 Newton Meters
label | 3be4c114-eee7-5d84-bc87-a5a830a3e64b |  | note | TTD301XFA - 25 to 95 (Conductor Size MM2) - 25 to 95 (Branch Cable MM2) - 14 Newton Meters
label | a90d5e27-a87b-5ed0-bcaa-e3a3d863cf0c |  | note | TTD341F - 50 to 150 (Conductor Size MM2) - 6 to 35 (Branch Cable MM2) - 14 Newton Meters
label | 0ba4fa89-39eb-5e03-8871-83fd8be1d6de |  | note | TTD351XFA - 50 to 150 (Conductor Size MM2) - 35 to 95 (Branch Cable MM2) - 18 Newton Meters
label | 8d32215a-264f-550e-a6fb-7f186c37597c |  | note | TTD401XFA - 50 to 185 (Conductor Size MM2) - 50 to 150 (Branch Cable MM2) - 18 Newton Meters
label | 90426824-e846-5904-8cfe-934886a98b15 |  | note | TTD431XFA - 70 to 240 (Conductor Size MM2) - 16 to 95 (Branch Cable MM2) - 20 Newton Meters
label | 0b52e411-4af1-53d2-8d3d-ce252f227b2e |  | note | TTD451XFA - 95 to 240 (Conductor Size MM2) - 95 to 240 (Branch Cable MM2) - 25 Newton Meters
label | b4d54949-ce60-5b1b-81e4-95001bbfd2b4 |  | note | TTD551FJA - 120 to 380 (Conductor Size MM2) - 95 to 240 (Branch Cable MM2) - 37 Newton Meters
label | a8d58759-5303-5fda-b6ab-080dc3b76ad5 |  | note | INSTALLATION NOTES FOR IPC’S: WHEN USING TWO BOLT CONNECTORS EACH BOLT MUST BE TIGHTENED A1/4 T0 1/2 TURN ALTERNATIVELY UNTIL THE SHEAR HEAD OPERATES
checkpoint-group |  |  | section | Test No.1
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 05ec8fe7-e6df-5ae6-8058-6879f05da02b |  | textbox | Bolt Size
text | a73f24d1-1f7e-52cf-9a51-5314be8feebb |  | textbox | Switch/cable Identification
text | 3bdf9e86-ef2c-538f-8fa2-822c52edb26f |  | textbox | Line/Load
text | 24a55adb-4b11-590c-9a99-85bdb98ca524 |  | textbox | Red Phase Torqued
text | 1cc239d4-9108-5bba-b0af-3113e36ce946 |  | textbox | White Phase Torqued
text | 3d0df69a-8cf8-59de-8bcf-a19052f49304 |  | textbox | Blue Phase Torqued
text | b65d6dfb-3c0c-5d29-8f0c-8f78c3c6c85f |  | textbox | Neutral Torqued
text | 0e153177-bb36-5546-aa0e-90e22e76bf80 |  | textbox | Earth Torqued
text | f3c79dfa-a35d-5866-ab84-f6eb84d6721c |  | textbox | Bolts Crossed With Black Texta
text | 50615d8e-7673-5608-b4c7-a1eaad536a38 |  | textbox | Name
label | 9fad7321-f137-5f76-a269-8b48a86e6601 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.2
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | d84f4993-861a-5a7e-a2fe-47263bd32d1a |  | textbox | Bolt Size
text | 7a95157e-9ad7-55a4-9c30-c28f5be83106 |  | textbox | Switch/cable Identification
text | 9f24fd36-aec9-5237-90f3-bccad964aec4 |  | textbox | Line/Load
text | d919445a-5859-5612-b5ac-235ba7870434 |  | textbox | Red Phase Torqued
text | 9f7397c8-c9a8-57e5-b6aa-f6c8dd3f9560 |  | textbox | White Phase Torqued
text | 098cc9e8-92fc-5b35-ac36-93cc740b400e |  | textbox | Blue Phase Torqued
text | c58ea653-ee7e-55e5-95af-4518f03c1990 |  | textbox | Neutral Torqued
text | 1c7e9c55-07fd-5853-b46d-01d013f07387 |  | textbox | Earth Torqued
text | 7b9a7772-3695-5208-8fdd-b38882d34fc0 |  | textbox | Bolts Crossed With Black Texta
text | 56e3ce40-022a-51c0-abd6-708f4bff193e |  | textbox | Name
label | 9b038270-dcc3-57fb-bf48-70d17b1b07ab |  | note | Signature added below
checkpoint-group |  |  | section | Test No.3
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 71b3a215-80c1-5574-a833-a04fbcd40980 |  | textbox | Bolt Size
text | 08246929-d2f6-5676-84fe-76784521cb7d |  | textbox | Switch/cable Identification
text | a2bc3436-f171-55cc-b112-973576b7467a |  | textbox | Line/Load
text | 764de244-c8fb-5abd-b033-2b8cd530d20a |  | textbox | Red Phase Torqued
text | e8e65d61-7e16-5d64-bdb2-ac5fd7fd9481 |  | textbox | White Phase Torqued
text | 8e8bd568-4a9d-5db2-95d8-f110c6d47697 |  | textbox | Blue Phase Torqued
text | 3a1a61f2-2e79-5a0d-b21e-316a56ce3c52 |  | textbox | Neutral Torqued
text | 3692964d-051f-5f19-bc81-14c4af5e58af |  | textbox | Earth Torqued
text | 53bf56d9-eb2f-5006-b157-7e45d73eaa1b |  | textbox | Bolts Crossed With Black Texta
text | bcff73e8-de5b-5eb3-95cb-9f631718bbd6 |  | textbox | Name
label | dfc58ef0-8238-5298-9252-51f48bb577f1 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.4
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | e629d02b-495a-5d66-abe2-f8c8f7ba2fd7 |  | textbox | Bolt Size
text | 4461c3fd-3780-5f7f-ba68-1f1f9fa709fb |  | textbox | Switch/cable Identification
text | 45424b32-c002-531e-ad0a-b4fda084eb0d |  | textbox | Line/Load
text | 7d0602c3-99ac-5be2-8923-344b987aab21 |  | textbox | Red Phase Torqued
text | 1c9a3e50-82bd-5770-8fed-ba58f6af6962 |  | textbox | White Phase Torqued
text | 464261f4-9568-5a7a-b82b-51a39b692f4e |  | textbox | Blue Phase Torqued
text | 996b5de2-b27e-5846-a21a-de64b4dd4179 |  | textbox | Neutral Torqued
text | 714b4e01-4f27-54ce-ac69-b362241f396a |  | textbox | Earth Torqued
text | d62c695f-56b5-5139-9ecf-d328c05f6ec4 |  | textbox | Bolts Crossed With Black Texta
text | b02b45f6-d0e3-5267-a169-b1f63bfcd644 |  | textbox | Name
label | 3b5afb9e-9e31-5a1b-9810-f18f6310aa4f |  | note | Signature added below
checkpoint-group |  |  | section | Test No.5
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | bc1c4b42-fe27-54c1-a46c-ac3c47b139c8 |  | textbox | Bolt Size
text | e73ed5ed-dc1a-5930-acb9-34e890b9679c |  | textbox | Switch/cable Identification
text | ac8491e2-e6f0-5f04-b482-ac3debd273fa |  | textbox | Line/Load
text | 95043dd6-2c3e-5fe0-82de-6da7baffaf0a |  | textbox | Red Phase Torqued
text | 4ceb9c38-1820-5c2f-b750-a9b257c34dcf |  | textbox | White Phase Torqued
text | 9c6657b3-cc0e-5006-bbbe-ad12b78bfa19 |  | textbox | Blue Phase Torqued
text | 5d7b441c-4437-59f2-82b9-22a397453252 |  | textbox | Neutral Torqued
text | 6a229c9c-99e3-5f5d-8b6b-0ee4a3348f70 |  | textbox | Earth Torqued
text | 38b2ab55-3b42-5ed4-8d63-9c8b9df55015 |  | textbox | Bolts Crossed With Black Texta
text | 4fc72c91-59a8-5e5a-bc9c-b23fcf259181 |  | textbox | Name
label | 8dcfd47a-95dc-525a-b482-1e07af111f99 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.6
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 1850647f-83da-56f4-884b-5e714a67a8a0 |  | textbox | Bolt Size
text | e543ce76-4ce0-5be9-9be9-f756433bb59b |  | textbox | Switch/cable Identification
text | 4d0d7ab1-2e58-5240-a0f8-c8056b20366a |  | textbox | Line/Load
text | f533324e-4008-5da3-a4af-5d761563c938 |  | textbox | Red Phase Torqued
text | 33e44823-f43e-5444-81f5-343792904658 |  | textbox | White Phase Torqued
text | 4ff35e13-2a2f-57c6-8cec-546eb2501736 |  | textbox | Blue Phase Torqued
text | 88d4f320-1caa-5330-a7ca-83ab3c241b45 |  | textbox | Neutral Torqued
text | e7251184-0bbb-530f-afed-4216c25f2fe3 |  | textbox | Earth Torqued
text | 28de3a22-0d40-5be2-9b0e-947fb48b00c7 |  | textbox | Bolts Crossed With Black Texta
text | c6d6a992-8ab8-544b-ae38-75f2dfc4d34f |  | textbox | Name
label | df2b19be-faa9-59f1-9ffc-4c6e64ba5bea |  | note | Signature added below
checkpoint-group |  |  | section | Test No.7
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 63679eeb-115c-5dc6-b166-8ca303581edf |  | textbox | Bolt Size
text | e7ede900-8cf8-5cc9-8bb4-fe3b2f0c4267 |  | textbox | Switch/cable Identification
text | 02d1bfc3-b96a-5fbb-9971-63fb3bac7361 |  | textbox | Line/Load
text | ddb3a5ce-c323-5cac-a771-90e3a3010cf5 |  | textbox | Red Phase Torqued
text | d8d8f04b-ba3b-5490-af0d-0fb00b14e351 |  | textbox | White Phase Torqued
text | 9edbb134-6edc-5056-a2a0-b595629a2fe5 |  | textbox | Blue Phase Torqued
text | 2e56e013-5c5f-534e-a677-576043352cb0 |  | textbox | Neutral Torqued
text | 4218ee57-8792-5b51-ab78-c7446a3a6979 |  | textbox | Earth Torqued
text | dd0039c0-1e93-53b8-b742-9c1537488a74 |  | textbox | Bolts Crossed With Black Texta
text | 6c71c71d-7038-5f01-a51c-c375726f7175 |  | textbox | Name
label | 26b8c0d6-5499-528f-9de6-aca6737011e1 |  | note | Signature added below
checkpoint-group |  |  | section | Test No.8
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | d4dbacb0-ed89-50e7-a451-3da209eefd42 |  | textbox | Bolt Size
text | a3715998-ee2a-5612-9d5c-09839d33ff5b |  | textbox | Switch/cable Identification
text | 48389e9f-5186-572b-9c02-938147c974e7 |  | textbox | Line/Load
text | 4d981b4f-0b4c-5e3b-a642-fe6770fe9a7d |  | textbox | Red Phase Torqued
text | 3b804ee6-a401-56f4-8e3b-3b41ec18b198 |  | textbox | White Phase Torqued
text | d3758516-7e2a-54a3-b472-75ae0de67fbd |  | textbox | Blue Phase Torqued
text | 856156dd-f4bc-5a38-8fd8-077cb134c3b7 |  | textbox | Neutral Torqued
text | 9feaf6d7-f8a1-57d7-99b6-6ebc74d61f92 |  | textbox | Earth Torqued
text | 94047105-8608-53e0-8473-5f2553248bde |  | textbox | Bolts Crossed With Black Texta
text | d3a3b2b3-3f94-5083-b7e7-84a711e1651c |  | textbox | Name
label | b61ae03a-53d0-50f1-bd5c-fe9268d957ba |  | note | Signature added below
checkpoint-group |  |  | section | Test No.9
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | f922ad0a-1b24-5e17-9728-ef07ebd2aad2 |  | textbox | Bolt Size
text | 1cf02795-bc2e-5bb2-a3f0-ed7b9ac9a3c0 |  | textbox | Switch/cable Identification
text | cfe2e65d-88c8-58db-a139-cfb446b1c7b8 |  | textbox | Line/Load
text | f0928b29-b382-58d6-8de7-eb2cbde02226 |  | textbox | Red Phase Torqued
text | 17968919-e5f4-5e15-91c9-a5dc0c98e250 |  | textbox | White Phase Torqued
text | 6de261ca-8eb7-537a-b802-f51d0699049c |  | textbox | Blue Phase Torqued
text | 779e18bb-7041-57f8-9463-1094ffc4c6d4 |  | textbox | Neutral Torqued
text | 2f6e3840-e9fe-5b1d-92e9-df55fed94696 |  | textbox | Earth Torqued
text | e8f15fef-e1ba-5981-8fe7-51aafd3fd1db |  | textbox | Bolts Crossed With Black Texta
text | a61dbc76-c7c4-57ee-84f4-6f0ebb69167f |  | textbox | Name
label | bbb5e70f-f321-59fe-ac84-7e70c02a240e |  | note | Signature added below
checkpoint-group |  |  | section | Test No.10
checkpoint-status |  |  | checkpoint | Pass Once below details are completed
text | 313ccd89-80d3-5ef5-a85c-affb0e0c649d |  | textbox | Bolt Size
text | d9d80f75-b07e-5aad-948a-9cc54f436fd9 |  | textbox | Switch/cable Identification
text | 19144458-e79c-5ff4-9a2c-7aecd1b20506 |  | textbox | Line/Load
text | 717ac6c6-52c7-566c-96fd-55ae39af229c |  | textbox | Red Phase Torqued
text | 2be03f2c-9828-57b8-ac76-7ab78e717f14 |  | textbox | White Phase Torqued
text | 12066bf8-b761-5c78-91f9-ffb85fe485ce |  | textbox | Blue Phase Torqued
text | 88073007-437f-55fb-a3b3-c70a716bd856 |  | textbox | Neutral Torqued
text | 44098a32-1524-542e-a29b-55133e7341f2 |  | textbox | Earth Torqued
text | ee9293c4-ccd3-5479-8eea-e2d1a567a6b6 |  | textbox | Bolts Crossed With Black Texta
text | 30a41d76-5bff-50cb-84dd-a129fe8a21eb |  | textbox | Name
label | 7bd67664-2ecc-51f3-ace4-0831c54be1b3 |  | note | Signature added below
checkpoint-group |  |  | section | Sign-Off
checkpoint-status |  |  | checkpoint | Cable Tray works completed to specification/drawings - Area left clean & tidy
label | fb63c6e7-2928-5620-acc6-3c83015da643 |  | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
label | 18a75b06-97f3-5ec3-9b17-8fcd71b836b8 |  | note | Any Corrective Actions to be Photographed & Commented below
select | df0b5e69-8395-56cf-90bd-e212e8762cbc |  | dropdown | Installed by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | b74fa197-1c8c-59dc-8bc6-a625f5dde144 |  | textbox | Other (Specify here)
select | 72731e29-58dd-5266-ad9c-2dd31d9463d6 |  | dropdown | Checked by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | c3ab5391-2c6b-5fbd-a416-8ed40983b140 |  | textbox | Other (Specify here)
text | 4a8af145-695b-5ec8-94a5-96ab8695b6ff |  | textbox | Witnessed by (Builder/QAM)
label | 2e9fc6fa-b83b-5e40-b999-82888c797078 |  | note | Signature Sign-Offs - Attach signature(s) below
checklist-sectioned |  |  | checklist | AE-ITCX-021 - Temp Board Audit Form (Rev 0) |  |  |  | 0 | Yes | AE-ITCX-021 - Temp Board Audit Form (Rev 0) | fff27093-e126-442d-b32c-63925b2fab39
checkpoint-group |  |  | section | Structural
checkpoint-status |  |  | checkpoint | Is insulated lead stand with board and in good condition
checkpoint-status |  |  | checkpoint | Is the insulation on the lead hook in good condition
checkpoint-status |  |  | checkpoint | Is the switchboard structurally sound
checkpoint-status |  |  | checkpoint | Does the main door close properly
checkpoint-status |  |  | checkpoint | Does the main door have the facility to be propped open
checkpoint-status |  |  | checkpoint | Is the chain to prevent the wind catching the door
checkpoint-status |  |  | checkpoint | Is the insulated bar in place
checkpoint-status |  |  | checkpoint | Do the flap-lock and door-lock work
checkpoint-status |  |  | checkpoint | Are all screws holding escutcheon covers in place
checkpoint-group |  |  | section | Signage
checkpoint-status |  |  | checkpoint | Is the main isolating switch identified
checkpoint-status |  |  | checkpoint | Are all C.B’s and R.C.D’s identified
checkpoint-status |  |  | checkpoint | Is 1.2m clearance signage in place
checkpoint-status |  |  | checkpoint | Is ‘Live Parts’ signage in place
checkpoint-status |  |  | checkpoint | Is KEEP CLOSED-RUN LEADS THROUGH BOTTOM sign on the door
checkpoint-status |  |  | checkpoint | Is the ID number of the board clearly visible
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Has all external wiring been removed?(not just cut off)
checkpoint-status |  |  | checkpoint | Do pole fillers cover all gaps
checkpoint-status |  |  | checkpoint | Are test points installed in the board
checkpoint-status |  |  | checkpoint | Is the 15amp GPO’s protected by a 25amp C/B
checkpoint-status |  |  | checkpoint | Are all holes in connection (J.Box) filled in/covered
checklist-sectioned |  |  | checklist |  |  |  |  | 2 | No |  | 43cbec7221431bc53e63051a4660e949334e1f5cd955ebc450ae122009ae65de
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 95466412-27c0-5ce2-8c90-06dda9d4fd27 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 0398e3b3-f228-5563-a062-274c87ce6156 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 902cfe70-a186-55a2-bd85-ba8f0a8e2043 |  | textbox | RCD No
text | 240c2984-1a84-5bce-b4ae-a07f60ae3633 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 0b3d0642-a635-550b-9cac-93445f40d7cf |  | textbox | 0.Deg (ms)
text | 601a751c-2565-54be-9c49-eaaa28950134 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | d959b407-69f5-5aac-b064-730a749e6aa4 |  | textbox | 0.Deg (ms)
text | 7ae02c0e-950f-578b-bf84-5720599e4ee7 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | fe0111fb-375b-5120-a66a-9655215a3bad |  | textbox | 0.Deg (ms)
text | 888d7ad0-2ad9-51b5-9a3b-735f1ef6d7b2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 8b8265ae-3bbc-587b-bef2-ac7ffb14327d |  | textbox | Action taken
checklist-sectioned |  |  | checklist |  |  |  |  | 2 | No |  | b247bedfb082f77200c004e2fcdc7a486b7b361b878a4ba9dedf8ec9d5326372
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7febf8ac-fbe2-504d-b45b-b17d05c1011c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 6f32795f-6f87-5a51-9daf-f8201cccbf23 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | c951c877-143e-5d13-b187-7dd9c04d9561 |  | textbox | RCD No
text | 3a1e5afa-e6c9-5116-ac04-636520b7c68f |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 127b9588-d5d3-501f-9de1-1bcaa2594213 |  | textbox | 0.Deg (ms)
text | f8fb5274-6dba-5fe3-9004-8f423498504a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 78122b77-9238-583e-bf5f-9d93fb360823 |  | textbox | 0.Deg (ms)
text | 550d811e-d87e-5113-a385-9ca5d865e869 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | b948baf9-543b-56ea-a7c8-f14f00fb5f42 |  | textbox | 0.Deg (ms)
text | 238daa5e-a234-55de-bca0-4498b7e1d939 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fb7a4dd5-8e60-556d-a7aa-81d8eb501530 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken
checklist-sectioned |  |  | checklist |  |  |  |  | 15 | No |  | 5818319960efe30259e7047a1d40e9412c17414d6b8fabc79a4a8a2f9961807f
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken
checklist-sectioned |  |  | checklist |  |  |  |  | 1 | No |  | 87f90e51ae340061e20e95dbe0d6ec1a14d4d5e6089d2c90d3329e2535fd4045
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7febf8ac-fbe2-504d-b45b-b17d05c1011c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 6f32795f-6f87-5a51-9daf-f8201cccbf23 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | c951c877-143e-5d13-b187-7dd9c04d9561 |  | textbox | RCD No
text | 3a1e5afa-e6c9-5116-ac04-636520b7c68f |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 127b9588-d5d3-501f-9de1-1bcaa2594213 |  | textbox | 0.Deg (ms)
text | f8fb5274-6dba-5fe3-9004-8f423498504a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 78122b77-9238-583e-bf5f-9d93fb360823 |  | textbox | 0.Deg (ms)
text | 550d811e-d87e-5113-a385-9ca5d865e869 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | b948baf9-543b-56ea-a7c8-f14f00fb5f42 |  | textbox | 0.Deg (ms)
text | 238daa5e-a234-55de-bca0-4498b7e1d939 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fb7a4dd5-8e60-556d-a7aa-81d8eb501530 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 95466412-27c0-5ce2-8c90-06dda9d4fd27 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 0398e3b3-f228-5563-a062-274c87ce6156 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 902cfe70-a186-55a2-bd85-ba8f0a8e2043 |  | textbox | RCD No
text | 240c2984-1a84-5bce-b4ae-a07f60ae3633 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 0b3d0642-a635-550b-9cac-93445f40d7cf |  | textbox | 0.Deg (ms)
text | 601a751c-2565-54be-9c49-eaaa28950134 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | d959b407-69f5-5aac-b064-730a749e6aa4 |  | textbox | 0.Deg (ms)
text | 7ae02c0e-950f-578b-bf84-5720599e4ee7 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | fe0111fb-375b-5120-a66a-9655215a3bad |  | textbox | 0.Deg (ms)
text | 888d7ad0-2ad9-51b5-9a3b-735f1ef6d7b2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 8b8265ae-3bbc-587b-bef2-ac7ffb14327d |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 9
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 2d313044-58bf-561f-af75-d45ea5c9829d |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 36adf6c2-0c7a-5d54-baaa-35b43a2f679e |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 8bef231b-1a76-542c-8db2-cee5f88a2248 |  | textbox | RCD No
text | ff437b9b-cb6b-59f4-8700-922c9cea1047 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 12d9e349-7fcd-576b-9f50-96067e293d0c |  | textbox | 0.Deg (ms)
text | 4ae61f83-4e31-55e3-9cf0-41f1b08cc59e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | ecc92d59-0eb0-56b9-8397-bf2dfe47a6da |  | textbox | 0.Deg (ms)
text | 903f6838-edb3-5174-b6ea-8129e41b1399 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 1246ac31-c8d9-5b61-973f-e72351f7e276 |  | textbox | 0.Deg (ms)
text | 4462a795-fd5a-53e0-a902-41456dc60394 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 349b0d2f-ebba-5f2f-9b45-a9fbe4e7f093 |  | textbox | Action taken
checklist-sectioned |  |  | checklist |  |  |  |  | 1 | No |  | 50a87c21342129868180db8841c411de2d4e2eddb09972777818c6a90cdb1907
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 6
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7febf8ac-fbe2-504d-b45b-b17d05c1011c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 6f32795f-6f87-5a51-9daf-f8201cccbf23 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | c951c877-143e-5d13-b187-7dd9c04d9561 |  | textbox | RCD No
text | 3a1e5afa-e6c9-5116-ac04-636520b7c68f |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 127b9588-d5d3-501f-9de1-1bcaa2594213 |  | textbox | 0.Deg (ms)
text | f8fb5274-6dba-5fe3-9004-8f423498504a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 78122b77-9238-583e-bf5f-9d93fb360823 |  | textbox | 0.Deg (ms)
text | 550d811e-d87e-5113-a385-9ca5d865e869 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | b948baf9-543b-56ea-a7c8-f14f00fb5f42 |  | textbox | 0.Deg (ms)
text | 238daa5e-a234-55de-bca0-4498b7e1d939 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fb7a4dd5-8e60-556d-a7aa-81d8eb501530 |  | textbox | Action taken
checklist-sectioned |  |  | checklist |  |  |  |  | 1 | No |  | 5cd22d810171ce23a2c0a5b6de70759ed1e6ab5997204a0fbe2c67bd9a99f390
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details - Pass once entered
text | e19f2f9a-543e-57e6-b329-b0eb70d09fe4 |  | textbox | Test Date
text | 0ab160f5-fb42-5ad9-812e-2c4609af0534 |  | textbox | Switchboard No.
text | fe28ad86-6e6e-517c-bce3-ef38d53ac0d0 |  | textbox | Tag No.
select | 49969680-14a9-5b82-aff8-e29dc7dbb34f |  | dropdown | Tested by (Appselec) | ADAM KENT - AGrade: A56009 - Employee#: 1622,ADAM STRONG - AGrade: A38815 - Employee#: 2002,ADRIAN BROWNE - AGrade: A37356 - Employee#: 1794,ADRIAN FANCELLU - AGrade: A58098 - Employee#: 1684,ADRIAN IVANCIC- Agrade: A62060 - Employee#: 1863,ALAN BIRCHALL - Agrade: A18981 - Employee#: 379,ALBERT ISMAIL - Agrade: A42436 - Employee#: 1111,ALI HASAN - Agrade: A48087 - Employee#: 1654,ALLISTER DAVEY - Agrade: A43940 - Employee#: 1015,ANDREW NANCARROW - Agrade: A36974 - Employee#: 1957,ANGELO MIHELAKOS - Agrade: A28568 - Employee#: 1972,ARTHUR KAPLON - Agrade: A29972 - Employee#: 1309,BEN DARBY - Agrade: A53332 - Employee#: 1702,BEN FINDLAY - Agrade: A41429 - Employee#: 2006,BENJAMIN ICELY - Agrade: A59057 - Employee#: 1933,BENJAMIN OSMOND - Agrade: A59204 - Employee#: 1733,BENJAMIN STEWART - Agrade: A50504 - Employee#: 186,BRADLEY TRUSCOTT - Agrade: A35473 - Employee#: 1801,BRANDON DUDLEY - Agrade: A45361 - Employee#: 1850,BRENTON HILL - Agrade: A47213 - Employee#: 1729,BRINSLEY TELLER - Agrade: A59986 - Employee#: 1887,BROCK DOWNIE - Agrade: A53290 - Employee#: 1849,BROCK LLOYD - Agrade: A44808 - Employee#: 1680,CHRISTOPHER HUTCHESON - Agrade: A55937 - Employee#: 1644,DAMIEN CASEY - Agrade: A39744 - Employee#: 1193,DANIEL MILLER - Agrade: A42685 - Employee#: 1909,DANIEL SETTE - Agrade: A50502 - Employee#: 1812,DARREN STACE-SMITH - Agrade: A48737 - Employee#: 1194,DARRYL ROWLEY - Agrade: A35492 - Employee#: 1937,DAVID OLSEN - Agrade: A42915 - Employee#: 1685,DEAN NGUYEN - Agrade: A48514 - Employee#: 1515,DWAYNE KLOET - Agrade: A48278 - Employee#: 1239,ESMIR GOLETIC - Agrade: A60319 - Employee#: 1782,EVAN CAMPBELL - Agrade: A35710 - Employee#: 1895,FERGUS COATES - Agrade: A59054 - Employee#: 1774,FRANC AUFFRAY - Agrade: A58054 - Employee#: 1679,HUY DO - Agrade: A40954 - Employee#: 873,IMMANUEL KAWITI - Agrade: - Employee#: 2023,JACKSON SHARPE - Agrade: A53801 - Employee#: 1540,JAMES MARASCO - Agrade: A55184 - Employee#: 1758,JAMES PLEASANT - Agrade: A62956 - Employee#: 1976,JAMES SPOKES - Agrade: A48756 - Employee#: 1770,JASON CRAMER - Agrade: A57832 - Employee#: 1673,JASON GARETTO - Agrade: A46469 - Employee#: 1896,JASON MASTROPASQUA - Agrade: A52370 - Employee#: 1756,JASON MURAWEZUK - Agrade: A58791 - Employee#: 1719,JASON PERL - Agrade: A36692 - Employee#: 1868,JASON SALE - Agrade: A28662 - Employee#: 1615,JAYDEN ZAHRA - Agrade: A64270 - Employee#: 2029,JESS ZAHRA - Agrade: A52969 - Employee#: 1403,JOEL BASSETT - Agrade: A39498 - Employee#: 1958,JOEL COGHLAN - Agrade: A43339 - Employee#: 1220,JOHN BATTISTA - Agrade: A41810 - Employee#: 1908,JOHN GREEN - Agrade: A55589 - Employee#: 1734,JOSEPH PETROVIC - Agrade: A55175 - Employee#: 1682,JUSTIN CROCKER - Agrade: A43258 - Employee#: 1720,KALE BLACKLER - Agrade: A39293 - Employee#: 1751,KAYNE WALKER - Agrade: A38805 - Employee#: 1718,KEVIN MURPHY - Agrade: A63544 - Employee#: 2022,KEVIN SOUTAR - Agrade: A32524 - Employee#: 1698,LUKE O_KEEFE - Agrade: A43627 - Employee#: 1834,MARC MCLAUGHLAN - Agrade: A45201 - Employee#: 1308,MARK D_ANGELO - Agrade: A40610 - Employee#: 1832,MARK GASCOIGNE - Agrade: A48674 - Employee#: 1352,MATTHEW COX - Agrade: A42092 - Employee#: 1704,MATTHEW JOYNSON - Agrade: A35535 - Employee#: 1894,MATTHEW KNIGHT - Agrade: A43800 - Employee#: 915 MICHAEL BRASHER - Agrade: A29237 - Employee#: 954,NICHOLAS EVANS - Agrade: A56890 - Employee#: 1748,PAT DOUBLE - Agrade: A46604 - Employee#: 1118,PAUL HARMAN - Agrade: A26306 - Employee#: 1728,PAUL RABAHI - Agrade: A52747 - Employee#: 193,PAUL WAISTELL - Agrade: A41819 - Employee#: 1190,PETER LEWIS - Agrade: A53556 - Employee#: 1749,PHILIP BROWN - Agrade: A55466 - Employee#: 1940,PHILLIP CHOW - Agrade: A55466 - Employee#: 1612,ROB POLLARD - Agrade: A56906 - Employee#: 1754,ROSS KOSTOGIANNIS - Agrade: A46721 - Employee#: 1132,RYAN DEPRADA - Agrade: A41361 - Employee#: 1848,SCOTT RYAN - Agrade: A59062 - Employee#: 2017,SEAN SMALLACOMBE - Agrade: A64078 - Employee#: 2034,SHANE SINCLAIR - Agrade: A55009 - Employee#: 1771,SIMON COLLARD - Agrade: A32749 - Employee#: 883,STEVEN THOM - Agrade: A48941 - Employee#: 119,STUART MALVENAN - Agrade: A61071 - Employee#: 1829,TOM HAMILTON - Agrade: A48254 - Employee#: 1434,VAUGHAN ROBINSON - Agrade: A45819 - Employee#: 1218,WILLIAM FISHER - Agrade: A20679 - Employee#: 859,Other (Specify below)
text | 49daf72c-9f10-5dcb-b3dd-ecd4266f9c24 |  | textbox | Other (Specify here)
boolean | 0ed324e9-72ce-5eda-bc34-2eb4d8f744aa |  | tickbox | Signature attached below
checkpoint-group |  |  | section | RCD Test 1
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 62a86e66-3f36-528e-b087-ea7df870a935 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 7e183f81-e8ad-59cf-8d41-82fc45e48c67 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 3da22ff8-59d8-584c-b8bd-75a00f402d71 |  | textbox | RCD No
text | b93166be-264d-5ed0-ba20-d1cecccc1d24 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 347fe8b9-07c8-5026-94b6-85bf7ae765a2 |  | textbox | 0.Deg (ms)
text | a2a749e3-d0a2-52f8-958e-e450ff5c179c |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | b0e54694-83f8-54f1-b92b-cf8c713b255a |  | textbox | 0.Deg (ms)
text | c88e0136-8052-51a0-8a1f-c529df25c6b5 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | be191f77-ac91-5a6e-8434-e04343f9fc77 |  | textbox | 0.Deg (ms)
text | b02fdf83-51a7-5246-bbf6-eb2727ac414f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | f68ee410-a265-5234-923e-2f4c412ffbd0 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 2
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 6609a039-82fb-59e2-b005-394ff29c181a |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c7ab65d9-cba8-598f-b4b0-25a6c3a5f350 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | d11ef2b9-5d6b-58de-b09b-613798d9eef8 |  | textbox | RCD No
text | c07f7619-be00-596b-84d3-1ecb5fe8d826 |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 2bc26e85-b569-59ab-a4f0-14d6e061fa3b |  | textbox | 0.Deg (ms)
text | 4b5e7039-46fc-538c-9af8-0bb110822860 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 54e31f21-b5d4-55e6-88a8-7b22ee4d6d84 |  | textbox | 0.Deg (ms)
text | ffb99f46-50ef-5dd1-9ebb-bc794e6ee63b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 43db8990-d6c7-5d3f-b75c-3d40b49cfdb7 |  | textbox | 0.Deg (ms)
text | a1c49d47-eb70-5571-be46-873c78b7ab90 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 400d946e-b207-5fcd-9da3-47d54f9ddcad |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 3
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | da88adaa-b7e5-5056-a0a3-ffa75b58135c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | ff788054-fd65-5ebc-a788-f9f41c4df090 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 7a1bc7c4-0b2c-5ab7-969e-4ec2c8e7ad60 |  | textbox | RCD No
text | 0045e67c-2db0-58eb-9122-0ceca2cca9ee |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 25771015-4d31-53fc-81b2-3dfd31590c06 |  | textbox | 0.Deg (ms)
text | 31d6b48b-b791-5d68-a6e1-bc3b523addf4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 52136244-b82a-56c5-9c64-f795990b4e09 |  | textbox | 0.Deg (ms)
text | 434436df-ca13-5159-99c5-ed425ab0d0a2 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 96ce3a6e-d717-5302-8be3-1f75ab40583c |  | textbox | 0.Deg (ms)
text | 13776282-6451-5cdb-b3f5-78a3a488646f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 3cf77a7f-9f3d-5dcc-9090-d2f5fadf483e |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 4
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | ed9868ae-dcf6-531a-ad09-56759efea218 |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 74a3dc34-cd8f-5290-89a8-edc52395fc7f |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 6cd9738b-079f-588a-9c6d-11e5160d7c6f |  | textbox | RCD No
text | 84eda14a-cbf3-5527-8fb5-473314e61fcb |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | d89c758f-54ce-5b9b-a737-a44f3ac573dd |  | textbox | 0.Deg (ms)
text | 1e2331e8-1e85-58df-9d96-17b49aa054e4 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 1539e408-7c9b-5fda-a6c8-79e779c779f6 |  | textbox | 0.Deg (ms)
text | 7d697446-2695-5c54-ab7f-87f5bb29f04a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | f8ba811d-adba-593b-8489-eca7ada4762f |  | textbox | 0.Deg (ms)
text | 3bb818bb-baaa-5c76-8976-accea0a25146 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | b1c8a79f-0b62-5e5a-9f41-bb19bdac9f8a |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 5
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 91349220-b2b4-5f92-8431-490f33ba76ae |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 37504205-2b67-5fa2-999d-0dace6616c69 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 05e91cd7-7d30-5e88-a687-e19a5250576d |  | textbox | RCD No
text | 48f31e97-a3fb-58f6-80df-71e68c0f6a2b |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | c8d03669-91de-53da-a170-4fd3641581a8 |  | textbox | 0.Deg (ms)
text | 41a0c292-88f7-5f8c-9dfa-8f04a8262f6f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 5f4452e5-0da3-5964-b5fe-d00fce289d90 |  | textbox | 0.Deg (ms)
text | 3330fcdd-e7ae-5dca-ac49-e9d9c9e8c89a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 8b6a4018-efb4-5ec5-8ef4-8ab6acd755a3 |  | textbox | 0.Deg (ms)
text | 2dbf4c8d-b9d8-5549-82f3-2439c995be35 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 5e5362dc-14a0-5584-b510-717b5bbbbb54 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 8
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 7febf8ac-fbe2-504d-b45b-b17d05c1011c |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | 6f32795f-6f87-5a51-9daf-f8201cccbf23 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | c951c877-143e-5d13-b187-7dd9c04d9561 |  | textbox | RCD No
text | 3a1e5afa-e6c9-5116-ac04-636520b7c68f |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | 127b9588-d5d3-501f-9de1-1bcaa2594213 |  | textbox | 0.Deg (ms)
text | f8fb5274-6dba-5fe3-9004-8f423498504a |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 78122b77-9238-583e-bf5f-9d93fb360823 |  | textbox | 0.Deg (ms)
text | 550d811e-d87e-5113-a385-9ca5d865e869 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | b948baf9-543b-56ea-a7c8-f14f00fb5f42 |  | textbox | 0.Deg (ms)
text | 238daa5e-a234-55de-bca0-4498b7e1d939 |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | fb7a4dd5-8e60-556d-a7aa-81d8eb501530 |  | textbox | Action taken
checkpoint-group |  |  | section | RCD Test 7
checkpoint-status |  |  | checkpoint | Tested tripping time of RCD’s (using RCD Tester)
label | 0cbd7177-f5dd-5594-b0ff-2732c4e4b82f |  | note | FAST TRIP FOR TYPE 1,2 OR 3 MUST BE LESS THAN 40 MS
label | c4a3407e-be17-505f-8925-842612732905 |  | note | Test results to include both phase relationships readings in milliseconds (ms)
checkpoint-status |  |  | checkpoint | Protective Device type selected and details entered
text | 9025e907-3794-5198-8925-ddf0fa23a196 |  | textbox | RCD No
text | 5b6829ed-e501-5f7b-a4e2-82d5e32543df |  | textbox | Nominal Trip Current (mA)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= No Trip - x1/2 No Trip Time
text | feb1a901-0f00-50bc-bec7-714a3263883b |  | textbox | 0.Deg (ms)
text | 6d737ff0-8ceb-5e96-a559-c3858001152f |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <300ms - x1 Trip Time (ms)
text | 63c0f725-54ac-551e-8c71-7a4260642eae |  | textbox | 0.Deg (ms)
text | 58ce8947-c683-5225-9b26-c4dc42ce104e |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Acceptance Criteria= <40ms - x5 Trip Time (ms)
text | 005233f5-7f8e-567a-b1c7-1a918edec297 |  | textbox | 0.Deg (ms)
text | a52b3be4-961b-5b77-875e-116660e9420b |  | textbox | 180.Deg (ms)
checkpoint-status |  |  | checkpoint | Any action taken for unsatisfactory results - PASS=No / FAIL=Yes (noted below)
text | 54b18f2a-58dd-5338-9393-23ef6d67e020 |  | textbox | Action taken