## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-007 - Hot Mix Asphalt | itp |  |  |  |  | ITP-01-007 - Hot Mix Asphalt
section | 1 - Construction Works
checkpoint | 1.1 Submission of Mix Design
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
note | – – – – – – – – –
note | RECORD OF CONFORMITY: VR approval, Completed ITP
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Site Inspection and Base Condition
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS:
note | • 407.14
note | • AS2150 10.1
note | • AS2150 10.3
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Ambient Conditions for Placing
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
note | • Base & Intermediate Courses: 5°C for conventional binders or
note | • 10°C for PMBs & Class 600
note | • Wearing Courses: 10°C for conventional binders or 15°C for PMBs
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.13
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Thermometer
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.5 Planning of Joints
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
note | • Transverse Joints Offset from layer to layer by at least 2m
note | • Longitudinal Joints Offset from layer to layer by at least
note | • 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Paving Plan
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.6 Longitudinal Joints with existing Pavement
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
note | • Depth of step to be cut to the full depth of each indiviual layer.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
section | 2 - Asphalt Placement works
checkpoint | 2.1 Tack Coat
note | FREQUENCY: Prior to commencing paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content).
note | • This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving.
note | NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.15 AS2150 11
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Spray area
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Commencement of Placing
note | FREQUENCY: Prior to commencing Paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.18
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.3 Mix Design Confirmation
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Delivery of Mix
note | FREQUENCY: Each load
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.16 Table 407.081
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Delivery Docket
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Traceability
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Daily Lot Record
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Layer Thickness and Level Control
note | FREQUENCY: Regularly during paving
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Dips using ruler or dip stick
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Paver Stoppages
note | FREQUENCY: If paver stops
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.20 (c)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Thermometer
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Surface Finish of Wearing Course
note | FREQUENCY: During paving and after final roll
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.23 (a)(i)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.9 Kerb and Channel
note | FREQUENCY: During paving and after final roll
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.10 Alignment of layers not placed against concrete edge
note | FREQUENCY: During paving and at completion of work
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.11 Width of layers not placed against concrete edge
note | FREQUENCY: During paving and at completion of work
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
note | • The average width over any 300m shall not be less than the design or specified width
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 407.23 (a)(v)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
note | – – – – – – – – –
textbox | DATE:
section | 3 - Testing
checkpoint | 3.1 Compaction
note | FREQUENCY: Per Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | ○ For layers <50mm, if characteristic density ratio is:
note | • 94.0% or greater Accept lot
note | • 91.0% to 93.9% Lot may be accepted at reduced rate
note | ○ For layers ≥50mm, if characteristic thickness is:
note | • 96.0% or greater Accept lot
note | • 91.0% to 95.9% Lot may be accepted at reduced rate
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Table 407.221
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Test Report
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
note | – – – – – – – – –
textbox | DATE:
checkpoint | 3.2 Level Conformance
note | FREQUENCY: Per 4,000m2 at completion of work
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Table 407.232
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey Conformance
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: