## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-011
[11 empty] | Revision : | Date :
Client: |  | VicRoads |  | Construction Process: | Profiling | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | West Gate Distributor - Stage 1 |  |  |  | Name: | Mustafa Kamel | Name: |  | Matt Coe | Name: | Ajith Kulappurath
Contract No: |  | 9087 |  | Specifications: VicRoads Standard Specification - Sections 402 Removal of Pavemnt by cold planning
|  |  |  | Structure / Component: Asphalt Pavement |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Profiling Works |  | Each lot | Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement | 402.02 | Visual Inspection | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A
3.2 | Depth check |  | Each lot | Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction. | 402.02 | Visual Inspection | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A
3.3 | Temporary ramping (longitudinal) |  | Longitudinal edges | Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical. | 402.05 | Verify | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A
3.4 | Temporary ramping (transverse) |  | Transverse Edges | Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less | 402.05 | Verify | This ITP signed | WP | Fulton Hogan Engineer / Foreman/ subcontractor | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on E20: Kamel, Mustafa: check average depth and pavement type of existing