## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | fbadf54e-f527-4c2c-a505-d4cb2799f486 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | 24784239-33e2-4512-9e03-8a34a901f7f1
checkpoint-status | 7158a30e-3b72-4475-b96d-8f05a06a16e8 |  | checkpoint | Variation completed with photos of work
text | 50824351-b5d5-5a3b-99f2-64c71f58ac29 |  | textbox | Details (Level/Unit/Area)
text | 6628b37d-ba2b-53f3-9720-e829ecb6a4f3 |  | textbox | Hours/Minutes
checklist-flat | 3841f0f3-a28d-48b0-8051-3ede0c32508c |  | checklist | Preprufe 300R walls |  |  |  |  | Yes | Preprufe 300R walls | 3cf9f869-464d-4970-98c8-95e900e25288
checkpoint-status | 45d5a593-b183-408a-9a9b-314d2f20ffd6 |  | checkpoint | Area Specified Below
checkpoint-status | 213aec4a-f503-4103-adda-60f0581bdd6b |  | checkpoint | Geotextile to walls
checkpoint-status | b9ec62fb-29d4-46c1-8de8-682149d4cb85 |  | checkpoint | Preprufe to walls
checkpoint-status | a97ffcfb-e611-4d05-ae05-afef81265bb8 |  | checkpoint | All laps taped
checklist-flat | 62112f97-d528-42bc-a517-b45c97fa3347 |  | checklist | Preprufe 300R beams and underfloor |  |  |  |  | Yes | Preprufe 300R beams and underfloor | 7c19f4cb-1e09-4681-9582-9c8df7aad94b
checkpoint-status | 478c9482-7bc7-4714-b3e6-907c66404ece |  | checkpoint | Area Specified Below
checkpoint-status | 11f4d7bb-d14b-4abc-8d67-d50309c1e2f3 |  | checkpoint | Geotextile to substrate
checkpoint-status | 292a7680-3cb7-4950-8dac-b79ddbf9aa3c |  | checkpoint | Preprufe placed all laps taped Preprufe bedded into LM 300 on top of piles
checkpoint-status | 934a91fd-4778-4b9a-a5cf-a083c3d57571 |  | checkpoint | Adcor 500 T placed around top of pile
checkpoint-status | 7ee79742-9fed-4dd1-a1cd-b0b5ff2fd6e7 |  | checkpoint | Swell seal WA placed around all pile bars
checklist-flat | 73e32d56-72e6-44ab-82d3-f20a819b0e06 |  | checklist | Head Wall Bituthene 3000 |  |  |  |  | Yes | Head Wall Bituthene 3000 | 98a84e5d-5b4b-4c3e-a1af-27eb24558a41
checkpoint-status | 6486c8ba-0239-4517-8b4c-fe44ab804403 |  | checkpoint | Substrate and all voids filled
checkpoint-status | 450972a9-9903-4a56-92f7-ebd2fa7d49bc |  | checkpoint | Substrate primed ready to receive the Bituthene 3000
checkpoint-status | fc31ccb4-1d5a-4b30-bcbf-3861745d751a |  | checkpoint | Bituthene 3000 placed on the prepped area
checkpoint-status | 0de0f9af-7a38-40ee-8cbe-d822c1b1498a |  | checkpoint | Laps sealed with Liquid Membrane
checkpoint-status | 953d9318-e459-4696-994d-bd5d1f4f29aa |  | checkpoint | Coreflute protection placed
checklist-sectioned | cd8d961e-5337-4cdf-9f7e-f5b0125cc971 |  | checklist | Warm Roof Checklist |  |  |  |  | Yes | Warm Roof Checklist | e6ef95c3-8586-44f1-94eb-0d73bca15c9a
checkpoint-group | 94dcabd6-fc13-4f19-8953-17319e25c94a |  | section | Substrate
checkpoint-status | 9c192e24-3c37-4734-accd-70acfec2995c |  | checkpoint | Area accessible
checkpoint-status | 754cbc2d-8986-4854-bb83-975be0d6cdc9 |  | checkpoint | Edge protection and safety installed
checkpoint-status | d0092630-1093-4a32-8d07-d31655239823 |  | checkpoint | Perimeter support installed if metal deck substrate
checkpoint-status | 4b40c35f-ed10-4dd3-8843-66bd5c08fe77 |  | checkpoint | Substrate acceptable (clean, dry and stable)
checkpoint-group | f0740daf-17c6-4002-99c0-6c96843f30ac |  | section | ST400
checkpoint-status | e18c72c4-17c2-49bb-9231-3a37a253b0dd |  | checkpoint | Falls checked and correct
checkpoint-status | cc057763-ecc1-427b-84fb-63d34b9e6710 |  | checkpoint | Purlins and roof structure ready for ST400 and approval given to lay
checkpoint-status | 2b1cec6a-a11a-4a18-b618-de8550079cd1 |  | checkpoint | Fix steel to manufacturers specifications in compliance with NZBC
checkpoint-status | d4a15fd5-2803-4bed-9298-8825a013cb50 |  | checkpoint | The metal profile installed upside down and the specified fastenings installed in the trough
checkpoint-status | 9d8dea8f-5fed-4d48-bf16-e805096d920f |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status | 6ea258c9-c41f-4b43-a3ab-ae2a670ee1e5 |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status | ee4417fa-ae58-40eb-8d1d-af2acae332e5 |  | checkpoint | The timber height is exact height of the insulation and the outside edge of the timber has a generous radius to ensure maximum bond of the membrane when dressed over it
checkpoint-status | 38b8d1a0-f488-44e3-9b3d-2cd1448ac51e |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status | 182c5042-6b70-463c-96a9-492523b4a95a |  | checkpoint | ST400 installed as per spec and complete. Any general observations made
checkpoint-group | 48c9c988-940c-4ad1-b551-b67deeac24fd |  | section | Polyiso
checkpoint-status | 7186aac7-fa4c-42cd-ae09-adfe52d97712 |  | checkpoint | All Polyiso sheets butt jointed - np gaps created
checkpoint-status | 7cc37ed5-9054-48df-a25d-e3acc9c57821 |  | checkpoint | Polyiso Sheets glued down with Viking FAST Adhesive (STP900B) using a proprietary dual cartridge caulking gun
checkpoint-status | 2c467872-78dd-44f3-9e54-02280e9d7af6 |  | checkpoint | STP900B adhesive applied in sweeping ribbons on every steel rib and then left to ‘foam-up’ over the next few minutes
checkpoint-status | 7a4772b3-88fa-40cd-b967-c2f1d2cc6d0e |  | checkpoint | Polyiso boards laid in a brick-bond pattern.
checkpoint-status | abf23cd6-1124-4ae8-934c-a56e3724fce9 |  | checkpoint | Butt the polyiso sheets up to the pre-formed timber edging where applicable
checkpoint-status | 27bb8a3b-3b8c-4509-8d40-0fafc5562c86 |  | checkpoint | Entire roof inspected upon completion to ensure a uniform flat surface
checkpoint-status | 9d37b9bb-3ace-4bc4-a532-edddc7cf7385 |  | checkpoint | Polyiso installed as per spec and complete. Any general observations made
checkpoint-group | fe5c323b-f74f-488c-8250-afb50d6f2aca |  | section | Membrane
checkpoint-status | a7ce03fc-3888-4cb2-95db-e3c178f94f38 |  | checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint-status | f815bc34-9c34-4f3a-88a0-760b32d8a0ec |  | checkpoint | Checked to ensure no dye-batch colour variation
checkpoint-status | 385f7333-5173-407f-a2ec-b3ea485ba241 |  | checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint-status | cd419f8d-1f94-4790-9426-dec6fe234c4d |  | checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested ‘system’ - Drains and accessories supplied by Viking Roofspec
checkpoint-status | d8da6939-72ed-4de1-a015-d42d0369468a |  | checkpoint | All welded seams and proprietary items to to be seam probed.
checkpoint-status | b07e2566-8f31-4bb0-a4f4-e7e8c07cb45d |  | checkpoint | Membrane installed as per spec and complete. Any general observations made
checkpoint-group | 753dc549-fd1a-4bc6-8007-7688e517614f |  | section | Handover
checkpoint-status | 62e4b78a-c580-4575-8596-e960c7649cd5 |  | checkpoint | Area 100% completed and waterproof as per specification
holdpoint | 247f79b3-7114-460e-97e9-4acae39e9710 |  | signoff | Request Review / Sign Off
checkpoint-status | 7bff4a8e-17da-4376-91fc-2b6903c74414 |  | checkpoint | Area left clean and tidy
checkpoint-status | 78ffa1d0-7266-412d-89c8-71dfe172aab8 |  | checkpoint | Area complete and ready for FSW inspection
checkpoint-status | 34924539-4be5-44c7-842d-0c14ea00399e |  | checkpoint | Report sent through to client
checklist-sectioned | d4c5c3a0-01b9-4a94-8767-a2e492313a16 |  | checklist | Nuraply 3PT and 3PTM Installation Checklist |  |  |  |  | Yes | Nuraply 3PT and 3PTM Installation Checklist | f7d0a35a-a17e-4537-928b-6321f9a9dea2
checkpoint-group | 3efc7610-53ce-4445-a01a-1f44e0aff426 |  | section | Location of Work
checkpoint-status | 26c46abb-5f27-42fc-9317-192ab6d2a48a |  | checkpoint | Area where product is being installed
text | 256a12df-13d3-5ed7-8fdd-0b6e34410639 |  | textbox | Area
text | ffe4e8a8-fd62-5b2f-b622-9f70522a7f5d |  | textbox | Grids
text | 3f5fa993-2ac7-5a5f-a895-02c650e12b96 |  | textbox | Other
checkpoint-group | 5a114f0b-065f-4259-9c02-0cb4e94a5414 |  | section | Nuraply 3PT and 3PTM Concrete Substrate Readiness Checklist
checkpoint-status | 02f7a8b4-8d89-42c7-8f8c-492e848d58c7 |  | checkpoint | Nuraply 3PT and 3PTM Concrete Substrate Readiness Checklist received from Main Contractor
checkpoint-status | bb86b88d-6ae4-415f-b690-b4600d4f9e98 |  | checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content
checkpoint-status | 2193d400-c727-4d56-b881-1aca8241430e |  | checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured.
checkpoint-status | e258af99-f686-44bc-9a30-81aa4e9b5965 |  | checkpoint | Nuraswell installed to construction joints as per specification - located 50mm from rebar.
checkpoint-status | 2421e6bf-98e8-40e5-9e15-e963cbb110a4 |  | checkpoint | Concrete surface firm with any soft concrete or laitance removed.
checkpoint-status | 7b1146a9-a9b6-4854-9628-fcb96f3dd93f |  | checkpoint | All protrusions removed. Surface free from foreign matter
checkpoint-status | 3a00e38a-84af-43c2-89e8-3c6c3a3cc35a |  | checkpoint | Mortar or bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint-status | a9abf83c-e5fd-4609-b7ef-2c8cb0673d74 |  | checkpoint | If terminating into a chase, pre-form the chase and ensure it’s straight and 20mm deep.
checkpoint-status | e9e7553a-6ddb-43d3-a91f-cd688d0ac5bd |  | checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite system.
checkpoint-group | bdb2f2e9-f7b6-4022-bad5-379c8ac775eb |  | section | 3PT and 3PTM Installed Product Checklist on Concrete Substrate
checkpoint-status | c0cef751-90e4-43bc-83b3-27ceecf3ab69 |  | checkpoint | Concrete Substrate checklist completed before work commenced.
checkpoint-status | 1c4bacb0-c455-40e3-87d6-c592b6a6fafe |  | checkpoint | Any movement joints installed to approved specification/detail.
checkpoint-status | 5b7458fe-b833-4735-ad56-2e00f8f1914a |  | checkpoint | Mortar/concrete fillets fitted to all internal junctions and corners chamfered at a 45°.
checkpoint-status | e804c179-cd09-4202-a641-6828af76c50a |  | checkpoint | All corners and upstands incorporate reinforcing or under flashing
checkpoint-status | 37c7124f-01fa-479b-bc14-4bd66b6354eb |  | checkpoint | Under-slab membrane extends beyond footing and protected until vertical membrane installed.
checkpoint-status | c58055f3-5cee-4464-a45b-336f58545e2e |  | checkpoint | Side laps 100mm and end laps 150mm fully torched and seamed. Bleed visible on all joints.
checkpoint-status | 65ba4e35-70f9-4a8a-8c24-bb9f0e991e41 |  | checkpoint | All penetrations installed to specification including under/over flashings.
checkpoint-status | 824cca3c-0160-4c1b-9bcb-e646783cde01 |  | checkpoint | Junction of the floor and wall membranes installed to specification fully bonded and watertight.
checkpoint-status | a1a92323-bd42-407a-ad4e-282096cbcd9c |  | checkpoint | All non-standard details installed as per pre-approved specification (attach approved drawings).
checkpoint-status | 5935f8e1-25ac-4eb4-b561-6bb48866ed5d |  | checkpoint | Any mechanical damage to membrane repaired to specification.
checkpoint-status | b990d2ea-82ef-4a47-a2fb-35799a36a14c |  | checkpoint | Membrane termination completed to approved detail.
checkpoint-status | 4f77ff8f-6205-4ead-bd2d-4c54daddb2fd |  | checkpoint | Suitable drainage system installed below footing as per specification.
checkpoint-status | f9ea09f8-c1a7-47e9-9493-f94c57cf3a39 |  | checkpoint | Membrane protection boards installed correctly.
checkpoint-status | 7d56fc3d-b5e7-4da4-b947-88dcbe7fc864 |  | checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
checkpoint-status | 696f8d80-0297-48f8-8672-950d48805421 |  | checkpoint | Overall installation free of wrinkles, bubbles, creases and splits.
checklist-sectioned | 345971a6-e457-4f75-b911-69b604a133cb |  | checklist | Nuraply 3PM Installation Checklist |  |  |  |  | Yes | Nuraply 3PM Installation Checklist | fc1f9cc4-adb1-4eea-bf44-a725d50dd913
checkpoint-group | aa3dc222-6eb0-4d53-a429-10acf60b34ec |  | section | Location of Work
checkpoint-status | 101158c3-00a6-424d-a8c7-0e1d15884770 |  | checkpoint | Area where product is being installed
text | 0127bc4f-5997-557d-adea-a248eab0045d |  | textbox | Area
text | 341bd57b-e4ec-5d62-9562-fd9c89857f53 |  | textbox | Grids
text | 9d916d24-6931-530c-8402-68cad71b2b26 |  | textbox | Other
checkpoint-group | 52edb057-aef6-4e3b-9235-af4e80fd6d01 |  | section | New Concrete Substrate Readiness Checksheet received from Main Contractor and Accepted
checkpoint-status | 92fd1f68-a05b-48dd-a601-01af887a65fd |  | checkpoint | Underflashings installed to all corners and upstands (pay attention to parapets,gutters, junctions)
checkpoint-status | e42afde6-e39f-45ea-92fb-13331023a335 |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint-status | de8fce83-cd6a-4775-8b95-f6407ce5f19f |  | checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-status | 0d319f70-bbd9-41fb-a003-e5c25c54770c |  | checkpoint | Membrane adequately adhered to substrate with no evidence of bubbles or lifting. Correct quantities of primer or adhesive used as per specification.
checkpoint-status | b6135a2f-5d30-49bb-9148-97de85bdb94b |  | checkpoint | Cap sheet and basesheet fully bonded together, no areas of delamination.
checkpoint-status | e9c4c2ff-c24c-44d0-9cb7-2078d51e2473 |  | checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off
checkpoint-status | 7bb19015-3ea2-4192-98a2-89301ba39225 |  | checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm).
checkpoint-status | 9e55abcf-ae54-432f-b173-0d3ee03431b9 |  | checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three layer lap build-ups
checkpoint-status | b51ba29d-2ca3-446b-83ed-57cd74b5e23b |  | checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint-status | 64fad49f-afde-4807-b47c-f26bce941d5f |  | checkpoint | Nuravents installed to specification.
checkpoint-status | 34326db7-5532-4dba-98a7-7744785ebde9 |  | checkpoint | All penetration details completed to specification including under/overflashing
checkpoint-status | e1046eb6-1fba-481c-818e-4da5604a25c8 |  | checkpoint | Standard details used throughout including at upstands, parapets, construction joints
checkpoint-status | fbf6318f-df17-4619-b372-12a3cd1c2b97 |  | checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint-status | e0b984ea-d6db-4cb4-b705-e69500a06045 |  | checkpoint | Gutters and outlets have been floodtested
text | 8d1643be-d80c-59a5-87bb-2211f6f59764 |  | textbox | Initial height check made
boolean | ab8041eb-bdd1-549b-b2a6-50e9269ab4ef |  | tickbox | Flooded for 24 hours
text | 0cf3de74-f028-523e-8257-dfb735d556fd |  | textbox | Height check assessed
boolean | d55e7d37-2d24-506a-81f6-50d0451cb3cb |  | tickbox | Remedials closed out
checkpoint-status | 8f93c7f3-2d41-4184-bde1-3d81b5430ee2 |  | checkpoint | Any damage to cap sheet repaired to specification.