## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | FADX-ITP-009 (FTC-05) FACTORY FABRICATION | itp |  |  |  |  | Factory ITP
checkpoint | Check the delivery docket and compliance certificate is available upon receiving raw material
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Production manager to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Shop Drawings/Engineering and Samples approved for fabrication
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Production manager to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Connections as per approved shop drawings
bool | (1) Welded (need to provide welding documents
bool | (2) Bolted, classify the bolt type (nug, TF or TB)
bool | (3) Other
textbox | Other - Please specify:
note | – – – – – – – – –
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Production manager to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Confirm & check finish as per approved Shop Drawings
bool | (1) Paint (check TDS)
bool | (2) Powder coat (check warranty certificate)
bool | (3) Other
textbox | Other - Please specify:
note | – – – – – – – – –
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Production manager to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Check Panel size and dimensions against drawing
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Check Diagonal dimension to ensure odd shape panel are done correctly
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | QA check delivery docket and receipt from the painter
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Check Frame dimension against Shop Drawings check Factory QA to sign off
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Check the finished frame is Square and plumb with bracket attached (if applicable)
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Check if the Crash rail has been fabricated to drawing and attached to the frame of the module
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Check if external grow cable has been installed into the correct location (if applicable)
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Installed finished panels to the frame, and spilt batten been locked with silicone
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Horizontal cladding shall have a minimum slope of 1:15 and shall be sloped away from visible vertical façade areas to prevent staining
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | No defects/scratch/dents/distortion/crack (visual) on the finish
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Is Fabricated item labelled as per drawing
dropdown |  | YES - Label ID, NO
note | – – – – – – – – –
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
label | Shop Drawing number: N/A
textbox | Date:
checkpoint | Fabrication complete
dropdown |  | Yes,No
note | – – – – – – – – –
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Lifting Lugs holes has been drilled on the frames
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Prevent direct contact between incompatible metals, and between green hardwood or chemically treated timber and aluminium or coated steel
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | Pack onto the stillage for delivery after completion of all above
note | Responsibility: FACADEX
note | – – – – – – – – –
note | Acceptance Criteria: Factory QA to sign off
note | – – – – – – – – –
textbox | Shop Drawing number:
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
label | Ensure the product was done base on the design complying AS standards including the following where applicable
label | • AS1562.1 Clause 5.5 (Resistance to wind pressures)
label | • AS1530.1 (Combus􀆟bility)
label | • AS5637.1 (Fire Hazard Proper􀆟es)
label | • A S1530.4 (Fire resistance level)
label | • A S2904 (Flashings)
textbox | Lead Fabricator – Checklist Completed:
textbox | Date / Time:
textbox | Factory Manager – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed
checklist-flat | FADX-ITP-008-2 (FTC-05) SITE INSTALLTION - CLADDING | itp |  |  |  |  | Site ITP
checkpoint | Multiplex - IFC Drawings Shop Drawings Approval
note | Responsibility: Multiplex
note | – – – – – – – – –
note | Acceptance Criteria: Multiplex Sign Off
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Multiplex - Material Approval
note | Responsibility: Multiplex
note | – – – – – – – – –
note | Acceptance Criteria: Multiplex Sign Off
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Materials - check materials meet Aust Stand AS1562.1-1992 and are supplied as ordered and specified for the project
note | Responsibility: Facadex
note | – – – – – – – – –
note | Acceptance Criteria: Facadex sign off - Site Supervisior
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Multiplex - Materials inspection upon delivery and prior to installation
note | Responsibility: Multiplex
note | – – – – – – – – –
note | Acceptance Criteria: Multiplex Sign off AS1562.1-1992
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Check Structure is level and plumb prior to commencing subframing for wall cladding
note | Responsibility: Facadex/MPX
note | – – – – – – – – –
note | Acceptance Criteria: Standard Cladding Tolerance:
note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
note | Expansion & Contraction:
note | +/- 3mm @ every 1000mm in length & height
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Site Installation – Grid lines established and RL by MPX
note | Responsibility: Facadex
note | – – – – – – – – –
note | Acceptance Criteria: Standard Cladding Tolerance:
note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
note | Expansion & Contraction:
note | +/- 3mm @ every 1000mm in length & height
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Site Installation – Installation: SHS framing and Cladding including all capping and flashings Sealing and Cauking
note | Responsibility: Facadex/MPX
note | – – – – – – – – –
note | Acceptance Criteria: Standard Cladding Tolerance:
note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
note | Expansion & Contraction:
note | +/- 3mm @ every 1000mm in length & height
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | Site Installation – Ensure the internal crash rail and external Grow cable are installed correctly
note | Responsibility: Facadex/MPX
note | – – – – – – – – –
note | Acceptance Criteria: Standard Cladding Tolerance:
note | +/- 3mm for all elements panel to panel, horizontal and vertical up to 2400mm
note | +/- 4mm for all elements panel to panel, horizontal and vertical up to 3000mm
note | +/- 6mm for all elements panel to panel, horizontal and vertical up to 13000mm
note | Expansion & Contraction:
note | +/- 3mm @ every 1000mm in length & height
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
holdpoint | HOLD POINT - All Criteria above must be signed off before proceeding
checkpoint | Client inspection of installed wall with Facadex representative. Any sighted defects (incurred during installation) to be recorded and subcontractor to be notified within 24 hours of installation.
note | Responsibility: Facadex /MPX
note | – – – – – – – – –
note | Acceptance Criteria: Defect notification via Teambnder or Builder email
note | Evidence of close out / rectification.
note | (SI / Photographic record & evidence of close out to be attached to this ITP for each wall type).
note | – – – – – – – – –
textbox | Reference Document AS1562.1-1992
textbox | Date:
checkpoint | AUTHORITY TO PROCEED
label | In signing the above the Facadex Construction and Named parties are confirming that all works have been completed in accordance with all the relevant Design Documentation & Specifications.
textbox | Foreman – Checklist Completed:
textbox | Date / Time:
textbox | Coordinator – Checklist Completed:
textbox | Date / Time:
holdpoint | Checklist Completed