## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CTN-ITP - Spray Sealing Operation | itp |  |  |  |  | CTN-ITP - Spray Sealing Operation
checkpoint | 1.1 - Binder
note | Frequency - Delivery Docket upon request
note | Acceptance Criteria - Verify binder being used matches that specified on the job pack
note | Reference Documents/Clause - 408.08
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Delivery Docket
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | ITP Opened:
textbox | Date Completed:
checkpoint | 2.1 - Aggregate Specification
note | Frequency - Delivery Docket & Maximum lot size 350t of same class and size
note | Acceptance Criteria - VicRoads Standard Specification Sections:
note | • 801 - Source Rock;
note | • 831 – Aggregate; and
note | • 832 - Sands
note | Reference Documents/Clause - 408.11 (a)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Delivery Docket
note | HP/C
note | Responsibility - Spray Seal Engineer
textbox | Date Completed:
checkpoint | 2.2 - Aggregate Precoating Materials
note | Frequency - All works carried out & Delivery Docket upon request
note | Acceptance Criteria - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
note | • Supply plant pre-coated aggregate from supplier or field pre-coated aggregate from stack site
note | Reference Documents/Clause - 408.09 (b) 408.11 (b)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Delivery Docket
note | IP
note | Responsibility - Spray Seal Engineer/Supervisor
textbox | Date Completed:
checkpoint | 3.1 - Rates of Application
note | Frequency - All works carried out
note | Acceptance Criteria - The Contractor shall determine the rates of application in accordance with the procedures set out in the Guide to Pavement Technology: Part 4K.
note | • Rates shall be expressed in L/m2 and residual binder at 15°C.
note | • At least 1 week prior, rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
note | Reference Documents/Clause - 408.13 (a)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Rate of Application for Residual Binder at 15°C
note | HP/S
note | Responsibility - Spray Seal Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Calibration of Bitumen Sprayer
note | Frequency - Prior to commencing works
note | Acceptance Criteria - Calibration Certificate to be provided
note | Reference Documents/Clause - 408.07
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Compliance Certificate
note | WP
note | Responsibility - Spray Seal Engineer/Supervisor
textbox | Date Completed:
checkpoint | 3.3 - Commencement of works
note | Frequency - Prior to commencing works
note | Acceptance Criteria - Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from the Superintendent to any variation in the rates of application to those provided under Cl. 408.13(a)
note | • Works shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit & ready for surfacing no more than 24 hours prior to the works occurring
note | • DSG Specification Section 310 – Preparation of Granular Pavement for Bituminous Surfacing shall be satisfied for initial seals
note | Reference Documents/Clause - 408.04 (b)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off
note | HP/S
note | Responsibility - Spray Seal Engineer/Supervisor
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Minimum Temperature
note | Frequency - Prior to commencing works
note | Acceptance Criteria - Minimum Temperature to meet criteria as set out in Table 408.131
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Treatment Type ¦¦ Min. air & pavement Temp. (°C)
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Primes ¦¦ 10
note | Initial seals (single/single) ¦¦ 15
note | Initial seals (double/double) ¦¦ 10
note | C170 and crumb rubber modified PMBs ¦¦ 15
note | Other PMBs ¦¦ 20
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Reference Documents/Clause - 408.13 (d)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off & Temperature Check
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | Date Completed:
checkpoint | 3.5 - Spraying Binder
note | Frequency - Each Run
note | Acceptance Criteria - Complete spray sheet
note | Inspection / Test Method - Dip sprayer after each run
note | IP
note | Responsibility - Sprayer Operator
textbox | Date Completed:
checkpoint | 3.6 - Spreading aggregate
note | Frequency - Each load
note | Acceptance Criteria - Complete spray sheet
note | Inspection / Test Method - Measure spread of aggregate
note | IP
note | Responsibility - Supervisor
textbox | Date Completed:
checkpoint | 3.7 - Removal of loose aggregate
note | Frequency - All works carried out
note | Acceptance Criteria -
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | (AADT) ¦¦ Max. Time Limit
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | >5000 and all Freeways ¦¦ Within 8 hours of sealing
note | >2000 to 5000 ¦¦ Within 24 hours of sealing
note | >500 to 2000 ¦¦ Within 48 hours of sealing
note | <500 ¦¦ Within 5 days of sealing
note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
note | Reference Documents/Clause - 408.14
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | Date Completed:
checkpoint | 4.1 - Records
note | Frequency - Each Lot
note | Acceptance Criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
note | Reference Documents/Clause - 408.17
note | Inspection / Test Method - Verify
note | Conformance Record - Spray Sheet Record
note | WP
note | Responsibility - Spray Seal Engineer
textbox | Date Completed:
checkpoint | 4.2 - Acceptance of work- Binder rates
note | Frequency - Each Lot
note | Acceptance Criteria - Actual vs design rates. Variation between actual & design assessed by Table 408.131
note | Reference Documents/Clause - 408.15 (a)
note | Inspection / Test Method - Verify
note | Conformance Record - Spray Sheet Record
note | IP
note | Responsibility - Spray Seal Engineer
textbox | Date Completed:
checkpoint | 4.3 - Acceptance of work - Surface Texture
note | Frequency - Each Lot
note | Acceptance Criteria - Acceptance - visual assessment or (where required) as per Table 408.152
note | Reference Documents/Clause - 408.15 (b)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | Date Completed:
checkpoint | 4.4 - Acceptance of work - Aggregate retention
note | Frequency - Each Lot
note | Acceptance Criteria - Acceptance - visual assessment or (where required) as per Table 408.153
note | Reference Documents/Clause - 408.15 (c)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | Date Completed:
checkpoint | 4.5 - Acceptance of work - Visual Uniformity
note | Frequency - Each Lot
note | Acceptance Criteria - Provide a surface with uniform colour, texture and consistent appearance
note | Reference Documents/Clause - 408.15 (d)
note | Inspection / Test Method - Verify
note | Conformance Record - This ITP signed off
note | IP
note | Responsibility - Spray Seal Supervisor
textbox | Date Completed:
checkpoint | Final Inspection - Fulton Hogan
note | This is to verify that the final inspection has been carried out in accordance with the FH’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
textbox | Work Completed On:
textbox | Date: