## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-STR-Precast Basin Retaining Wall (Supply & Install)
ITP Description: |  | Precast Basin Retaining Wall (Supply & Install)
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-03-01
ITP created by: |  | Michelle Lim
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Camms Road Project
Inspection & Test Plan - Precast Retaining Wall &/or Architectural Panels (Supply & Installation)
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-03-01
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 610 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 620 May 2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VicRoads Section 630 October 2013 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Joint Sealant | MRPA Quality Management Plan | Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP* | Nominated Authority | This ITP
2.2 | Subsurface Drainage | IFC Drawings 702.03 702.06 702.07 702.09 (f) | Details of subsurface drainage as per IFC drawings 100 dia slotted subsoil drain Category 1 (Class 1000) perforated plastic pipe. Perforations max width of 1.5mm and min length of 150mm per m2 Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP* | Nominated Authority | This ITP
2.3 | No Fines Concrete | 702.05 | No Fines Concrete to be used as backfill in geotextile A64 around subsurface drainage. No Fines to comply with 702.05(e) Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product | HP* | Nominated Authority | This ITP
3 | Preliminaries - Procedures and Documentation
3.1 | Precast Elements | IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (March/June 2019) | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019). Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each element | HP* | PE/SE | This ITP
3.2 | Precast Base Slab Founding | IFC Drawings Temporary Works Design | Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters: - Minimum undrained shear strength 80kPa Attach: Test report or Geotechnical report | Document Review | Each installation location | HP | Geotechnical Engineer | Attached Report
4 | Pre-installation Activities
4.1 | Materials Inspection Checklist | 620.06 620.07 MRPA Quality Management Plan | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each element | HP* | SE/PE | This ITP
4.2 | Survey Set-out of Precast Elements | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element. Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance. If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast. Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius. | Measure Visual | Each element | HP* | Surveyor SE/PE | This ITP
4.3 | Shims Placement | IFC Drawings | Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances. Packers to allow for 50mm grout under the precast elements | Measure Visual | Each element | HP* | Surveyor SE/PE | This ITP
5 | Installation Activities
5.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | SP | SE/PE | This ITP
5.2 | Precast Placement | IFC Drawings Temporary Works Design 610.27 | Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance. The nominal gap between elements is 20mm as per the IFC Drawings. | Measure Visual | Each element | SP | Surveyor SE/PE | This ITP
5.3 | Waterstop Seals, Compressible Seals & Isolation Joints Application | IFC Drawings Product TDS | Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists. 300mm wide Bituthene placed centrally over joint. Bituthene to cover retained height of upstand and extend 100mm along top of base slab. Compressible filler with backing rod to be installed on both faces Fabric Geosheet CS15F or equivalent to be installed over retained area of upstand, and over the 300 wide granular backfill for subsurface drainage, as per IFC drawings. Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings. | Measure Visual | Where applicable, each installation location | IP | Surveyor SE/PE | This ITP
5.4 | Joint Sealant Application | IFC Drawings | Compressible filler with backing rod to be installed on both faces. The gap between each precast element on the retained side to have 300mm wide bituthene placed centrally over the joint. Bituthene to extend the retained height of the upstand and extend 100 along the top of the base slab | Visual | Where applicable, each element | IP | SE/PE | This ITP
5.5 | Subsurface Drainage | IFC Drawings 702.03 702.06 702.07 702.09 (g) | Subsurface drains shall be the type nominated on the IFC drawings - 100 dia slotted subsoil drain. The drainage shall be backfilled with 300mm wide No Fines Concrete in Geotextile A64 as shown on the IFC drawings. No Fines Concrete to be compacted within 1 hour of mixing Joints in the drainage shall be over-lapped 450mm min. by the geotextile. Weep holes shall be checked for obstructions. | Measure Visual | Where applicable, each installation location | IP | SE/PE | This ITP
5.6 | Flowable Grout Pour | IFC Drawings | Grout shall be poured in the gap between the bottom of the precast element and blinding layer below. Utilisiing shims to ensure 50mm thick of grout. | Visual | Where applicable, each element | IP | SE/PE | This ITP
6 | Post-installation Activities
6.1 | As-built Survey | IFC Drawings 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report Attach: Survey As-builts / Survey Report | Measure Visual | Each element | HP* | Surveyor SE/PE/SPE | This ITP
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /