## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-032-STR-Precast Basin Retaining Wall Installation | itp |  |  |  |  | ITP-032-STR-Precast Basin Retaining Wall Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-STR-Precast Basin Retaining Wall (Supply & Install)
note | ITP Description: Precast Basin Retaining Wall (Supply & Install)
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): STR
note | Revision Number: 0
note | Revision Date: 01/03/22
note | ITP created by: Michelle Lim
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 610 November 2018
note | 1.2 Non Dependent
note | Reference: VicRoads Section 610 June 2019
note | 1.3 Non Dependent
note | Reference: VicRoads Section 620 May 2009
note | 1.4 Non Dependent
note | Reference: VicRoads Section 630 October 2013
section | Preliminaries - Materials
checkpoint | 2.1 Joint Sealant
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.2 Subsurface Drainage
note | REFERENCE: IFC Drawings
note | 702.03
note | 702.06
note | 702.07
note | 702.09 (f)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Details of subsurface drainage as per IFC drawings
note | 100 dia slotted subsoil drain
note | Category 1 (Class 1000) perforated plastic pipe. Perforations max width of 1.5mm and min length of 150mm per m2
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.3 No Fines Concrete
note | REFERENCE: 702.05
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: No Fines Concrete to be used as backfill in geotextile A64 around subsurface drainage.
note | No Fines to comply with 702.05(e)
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Preliminaries - Procedures and Documentation
checkpoint | 3.1 Precast Elements
note | REFERENCE: IFC Drawings
note | 610.46 (a), Table 610.463 (November 2018)
note | 610.47 (a) Table 610.473 (March/June 2019)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
note | i. Certificate of Compliance / Birth Certificate
note | ii. Compressive strength test results
note | iii. Precast Lifting Design
note | iv. Pre-pour check sheet / ITP
note | v. Post-pour check sheet / ITP
note | vi. Covermeter check record
note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
note | Note: Different revisions of 610 have different clause numbers
note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.2 Precast Base Slab Founding
note | REFERENCE: IFC Drawings
note | Temporary Works Design
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters:
note | – Minimum undrained shear strength 80kPa
note | Attach: Test report or Geotechnical report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each installation location
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Geotechnical Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Attached Report
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-installation Activities
checkpoint | 4.1 Materials Inspection Checklist
note | REFERENCE: 620.06
note | 620.07
note | MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
note | Elements shall have unique identification and orientation marked (if applicable).
note | Complete: Materials Inspection Checklist in ConQA
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 Survey Set-out of Precast Elements
note | REFERENCE: IFC Drawings
note | 610.46 (a), Table 610.462 (November 2018)
note | 610.47 (a) Table 610.472 (March/June 2019)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
note | Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Shims Placement
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
note | Packers to allow for 50mm grout under the precast elements
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Installation Activities
checkpoint | 5.1 Precast Handling
note | REFERENCE: 620.07
note | Crane Lift Study
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Precast Placement
note | REFERENCE: IFC Drawings
note | Temporary Works Design
note | 610.27
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
note | The nominal gap between elements is 20mm as per the IFC Drawings.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: SP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Waterstop Seals, Compressible Seals & Isolation Joints Application
note | REFERENCE: IFC Drawings, Product TDS
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
note | 300mm wide Bituthene placed centrally over joint. Bituthene to cover retained height of upstand and extend 100mm along top of base slab.
note | Compressible filler with backing rod to be installed on both faces
note | Fabric Geosheet CS15F or equivalent to be installed over retained area of upstand, and over the 300 wide granular backfill for subsurface drainage, as per IFC drawings.
note | Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each installation location
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.4 Joint Sealant Application
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Compressible filler with backing rod to be installed on both faces.
note | The gap between each precast element on the retained side to have 300mm wide bituthene placed centrally over the joint. Bituthene to extend the retained height of the upstand and extend 100 along the top of the base slab
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.5 Subsurface Drainage
note | REFERENCE: IFC Drawings
note | 702.03
note | 702.06
note | 702.07
note | 702.09 (g)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - 100 dia slotted subsoil drain.
note | The drainage shall be backfilled with 300mm wide No Fines Concrete in Geotextile A64 as shown on the IFC drawings. No Fines Concrete to be compacted within 1 hour of mixing
note | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
note | Weep holes shall be checked for obstructions.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each installation location
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.6 Flowable Grout Pour
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Grout shall be poured in the gap between the bottom of the precast element and blinding layer below. Utilisiing shims to ensure 50mm thick of grout.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Where applicable, each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-installation Activities
checkpoint | 6.1 As-built Survey
note | REFERENCE: IFC Drawings
note | 620.09
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
note | Attach: Survey As-builts / Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP