## QA Folder Structure
QA Folder Structure | Line item | Line item 2 | Line item 3 | Checklists
Building B |  |  |  |  | Enviro 700X - Balconies
| Balconies and couryards | level 1 |  | Enviro 700X - Balconies | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balconies | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 700X - Balconies | Enviro 700X + 250NS
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Bathroom | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room
|  |  | level 6 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 5 | Enviro 700X + 250NS
|  |  | level 6 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
| Landscape | Membrane to landscape planters | Level 05 | Enviro 700X + 250NS
|  |  | Level 06 | Enviro 700X + 250NS
|  |  | Level 07 | Enviro 700X + 250NS
|  | Membrane to slab below GRC planters | level 04 | Enviro 700X + 250NS
|  |  | level 05 | Enviro 700X + 250NS
|  |  | level 06 | Enviro 700X + 250NS
| Slab Edges | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 7 |  | Enviro 700X + 250NS
| Hebel | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building G
| Balconies and couryards | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
|  | level 7 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Bathroom | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 8 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 4 | Enviro 700X + 250NS
|  |  | level 5 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
|  |  | level 8 | Enviro 700X + 250NS
| Landscape | Membrane to landscape planters | Level 05 | Enviro 700X + 250NS
|  |  | Level 07 | Enviro 700X + 250NS
|  | Membrane to slab below GRC planters | level 04 | Enviro 700X + 250NS
|  |  | level 05 | Enviro 700X + 250NS
| Slab Edges | Window Set downs |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 2 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 3 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 4 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 5 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 6 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 7 | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Slabe edge brickwork | level 2 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 3 | Enviro 700X - Balcony Set Downs & Window Reveals
|  |  | level 4 | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 8 |  | Enviro 700X + 250NS
| Hebel | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building E
| Balconies and Courtyards | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
|  | level 7 |  | Enviro 700X - Balconies
|  | level 8 |  | Enviro 700X - Balconies
|  | level 9 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 9 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 9 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Bathroom | level 9 |  | Enviro 200P Ultra - Internal Wet Areas
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 10 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 10 | Enviro 700X + 250NS
| Landscape | Slab Below GRC planter | level 05 | Enviro 700X + 250NS
|  |  | level 06 | Enviro 700X + 250NS
| Slab Edges | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 9 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 10 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 10 |  | Enviro 700X + 250NS
Building F
| Balconies and Courtyards | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
|  | level 7 |  | Enviro 700X - Balconies
|  | level 8 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 9 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 9 | Enviro 700X + 250NS
| Landscape | Planter Boxes | level 09 | Enviro 700X + 250NS
|  | Slab below GRC Planter | level 05 | Enviro 700X + 250NS
| Slab Edges | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 9 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 10 |  | Enviro 700X + 250NS
| Precast Joints | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building J
| Balconies and Courtyards | Basement 1 |  | Enviro 700X - Balconies
|  | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
| Laundry | Basement 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | Basement 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| POD Puddle Flanges | Basement 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 5 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 5 | Enviro 700X + 250NS
|  | Non-trafficable slab under structural slab | level 3 | Enviro 700X + 250NS
| Landscape | Planter Boxes | level 3 | Enviro 700X + 250NS
|  |  | level 5 | Enviro 700X + 250NS
| Slab Edges | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 5 |  | Enviro 700X + 250NS
| Precast Joints | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Hebel | Basement 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building A
| Balconies and Courtyards | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
| Laundry | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Bathroom | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| POD Puddle Flanges | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 9 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 3 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
| Landscape | Planter Boxes | level 7 | Enviro 700X + 250NS
|  | Slab below GRC planter | level 6 | Enviro 700X + 250NS
| Slab Edges | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 9 |  | Enviro 700X + 250NS
| Hebel | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building C
| Balconies and Courtyards | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
| Laundry | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| POD Puddle Flanges | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | Level 6 | Enviro 700X + 250NS
|  |  | Level 7 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 6 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
| Landscape | Planter Boxes | level 6 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
|  | Slab below GRC planter | level 5 | Enviro 700X + 250NS
|  |  | level 6 | Enviro 700X + 250NS
| Slab Edges | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 9 |  | Enviro 700X + 250NS
| Hebel | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building D
| Balconies and Courtyards | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
|  | level 7 |  | Enviro 700X - Balconies
|  | level 8 |  | Enviro 700X - Balconies
|  | level 9 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 9 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | Level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 9 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Bathroom | level 9 |  | Enviro 200P Ultra - Internal Wet Areas
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 7 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 8 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | Level 9 | Enviro 700X + 250NS
|  |  | level 10 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 9 | Enviro 700X + 250NS
|  |  | level 10 | Enviro 700X + 250NS
Landscape
Slab below GRC planter
|  |  | level 6 | Enviro 700X + 250NS
| Slab Edges | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 8 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 9 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 10 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 9 |  | Enviro 700X + 250NS
Building H
| Balconies and Courtyards | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
|  | level 5 |  | Enviro 700X - Balconies
|  | level 6 |  | Enviro 700X - Balconies
| Laundry | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | Level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| POD Puddle Flanges | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 5 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 6 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | Level 5 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 3 | Enviro 700X + 250NS
|  |  | level 4 | Enviro 700X + 250NS
|  |  | level 5 | Enviro 700X + 250NS
|  |  | level 6 | Enviro 700X + 250NS
|  |  | level 7 | Enviro 700X + 250NS
Landscape
Planterboxes
|  |  | level 1 | Enviro 700X + 250NS
|  |  | level 2 | Enviro 700X + 250NS
|  |  | level 5 | Enviro 700X + 250NS
| Slab Edges | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 7 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 7 |  | Enviro 700X + 250NS
| Precast Joints | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
level 6
| Hebel | Level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 5 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 6 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Building K
| Balconies and Courtyards | Basement 1 |  | Enviro 700X - Balconies
|  | level 1 |  | Enviro 700X - Balconies
|  | level 2 |  | Enviro 700X - Balconies
|  | level 3 |  | Enviro 700X - Balconies
|  | level 4 |  | Enviro 700X - Balconies
| Laundry | Basement 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | Level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | Level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | Level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | Level 4 |  | Enviro 200P Ultra - Internal Wet Areas
| Water meter cupboards | Basement 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| POD Puddle Flanges | Basement 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 1 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 2 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 3 |  | Enviro 200P Ultra - Internal Wet Areas
|  | level 4 |  | Enviro 200P Ultra - Internal Wet Areas
| Roof | External Plant room | level 5 | Enviro 700X + 250NS
|  | Exposed area covered with pebbles | level 4 | Enviro 700X + 250NS
|  |  | level 5 | Enviro 700X + 250NS
Landscape
Planterboxes
|  |  | level 4 | Enviro 700X + 250NS
| Slab Edges | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Lift lids | level 9 |  | Enviro 700X + 250NS
| Precast Joints | level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
| Hebel | Basement 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 1 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 2 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 3 |  | Enviro 700X - Balcony Set Downs & Window Reveals
|  | Level 4 |  | Enviro 700X - Balcony Set Downs & Window Reveals
Common Areas
Podium Slab
|  | Basement 1 |  | Enviro 700X + 250NS
|  | Level 1 |  | Enviro 700X + 250NS
|  | Level 2 |  | Enviro 700X + 250NS
|  | Level 3 |  | Enviro 700X + 250NS
| Planter Boxes | Basement 1 |  | Enviro 700X + 250NS
|  | Level 1 |  | Enviro 700X + 250NS
|  | Level 2 |  | Enviro 700X + 250NS
|  | Level 3 |  | Enviro 700X + 250NS
| Retaining Wall | Level 1 |  | Enviro 700X + 250NS
| Basement Plant room | B2 Hydrant Sprinker Pump Room |  | Enviro 700X + 250NS
|  | B1 Booster |  | Enviro 700X + 250NS
| Basement Garbage Rooms | B1 Garbage Rooms |  | Enviro Epoxy RC
|  | B2 Recycle |  | Enviro Epoxy RC
|  | L1 Bin Room |  | Enviro Epoxy RC
|  | B2 Retail waste |  | Enviro Epoxy RC
| Retail Area Amenities | B1 Male Toilet |  | Enviro 200P Ultra - Internal Wet Areas
|  | Female Toilet |  | Enviro 200P Ultra - Internal Wet Areas
|  | AWC |  | Enviro 200P Ultra - Internal Wet Areas
| Gateway Building Amenities |  |  | Enviro 200P Ultra - Internal Wet Areas
| Cold Store | Level 1 |  | Enviro 200P Ultra - Internal Wet Areas
| Cleaners Room | Basement 2 |  | Enviro 200P Ultra - Internal Wet Areas
| Membrane to Entry Mats | Building A |  | Enviro 700X + 250NS
|  | Building B |  | Enviro 700X + 250NS
|  | Building C |  | Enviro 700X + 250NS
|  | Building D |  | Enviro 700X + 250NS
|  | Building E |  | Enviro 700X + 250NS
|  | Building F |  | Enviro 700X + 250NS
|  | Building G |  | Enviro 700X + 250NS
|  | Building H |  | Enviro 700X + 250NS
|  | Building J |  | Enviro 700X + 250NS
|  | Building K |  | Enviro 700X + 250NS
| Scott Street Bridge |  |  | HP1200+800TC
| Building E Columns | Level 1 |  | Enviro 700X + 250NS
|  | Level 2 |  | Enviro 700X + 250NS
|  | Level 3 |  | Enviro 700X + 250NS
|  | Level 4 |  | Enviro 700X + 250NS
|  | Level 5 |  | Enviro 700X + 250NS
|  | Level 6 |  | Enviro 700X + 250NS
|  | Level 7 |  | Enviro 700X + 250NS
|  | Level 8 |  | Enviro 700X + 250NS
|  | Level 9 |  | Enviro 700X + 250NS
| Building F Columns | Level 1 |  | Enviro 700X + 250NS
|  | Level 2 |  | Enviro 700X + 250NS
|  | Level 3 |  | Enviro 700X + 250NS
|  | Level 4 |  | Enviro 700X + 250NS
|  | Level 5 |  | Enviro 700X + 250NS
|  | Level 6 |  | Enviro 700X + 250NS
|  | Level 7 |  | Enviro 700X + 250NS
|  | Level 8 |  | Enviro 700X + 250NS

## ITPs Checklists
type | name | values
checklist-flat | Enviro 700X - Balconies
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Substrate crack and falls inspection
Label | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be reffered to engineers for treatment methodolgy. Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Moisture Content
Label | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
Label | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane. RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
Label | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
Label | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Seal/apply bondbreaker at junctions hob/floor
Label | Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint | Application of Enviro-700X
Label | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | QA Testing
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Protection of membrane edge
Label | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint | Builder Sign Off
checklist-flat | Enviro 700X - Balcony Set Downs & Window Reveals
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Substrate crack and falls inspection
Label | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint | Moisture Content
Label | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5% Enviro Prime 789 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
Label | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane. RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
Label | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
Label | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Application of Enviro-700X
Label | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | Protection of membrane edge
Label | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
checkpoint | QA Testing
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint | Completion of Work Element
checklist-flat | Enviro 200P Ultra - Internal Wet Areas
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Substrate crack and falls inspection
Label | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2. Ensure all fixings and joints have been set and junction between wall and floor does not exceed more than 10mm. Ensure Puddle flanges reccessed in concrete.
checkpoint | Substrate crack and falls inspection
Label | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be reffered to engineers for treatment methodolgy. Builder to approve falls on substrate(Min 1:100 outside shower and 1:80 in showers ) prior to application of membrane.
checkpoint | Moisture Content
Label | Note. min. 3 tests per bathroom Enviro Epoxy B-LV up to 6.9% Enviro Prime WB up to 6.9%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
Label | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane. RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
Label | If applying Enviro Epoxy B-LV, thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform. If applying Enviro Prime WB, mix at low speed (400RPM) until thouroghly mixed.
checkpoint | Applying primer
Label | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Application range: 5-40 degrees celcius.
Seal/apply bondbreaker at junctions hob/floor | Apply Enviro Flex Pro to form smooth 12mm flexible cove to all internal corners, penetrations and joints.
Application of 200P ultra | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply two coats of 200p Ultra to wet area in accordance with Australian Standards Application range 5-40*C
QA Testing | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT to manufacturers instructions. 0.6mm walls 1.0mm floors 3 tests on floor/ 3 tests on walls. 24 hour Flood testing.
holdpoint | Completion of Work Element
checklist-flat | Enviro 700X + 250NS
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Substrate crack and falls inspection
Label | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint | Substrate crack and falls inspection
Label | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be reffered to engineers for treatment methodolgy. Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
checkpoint | Moisture Content
Label | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
Label | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane. RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
Label | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
Label | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Seal/apply bondbreaker at junctions hob/floor
Label | Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint | Application of Enviro-700X
Label | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | QA Testing
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Application of 250N-S Top Coat
Label | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply 1 coats of 250N-S Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | Protection of membrane edge
Label | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint | Completion of Work Element
checklist-flat | Enviro Clad |  | `
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Primer Application - Pending Substrate Condition, Apply Enviro Prime WB using a brush or roller
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Membrane Application (1st coat) - Mix and Apply Enviro Clad as a first coat to the thicknesses prescribed by the specifications
checkpoint | Membrane Application (2nd coat) - Mix and Apply Enviro Clad as a second coat to the thicknesses prescribed by the specifications
checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro Hydrostatic 1
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Primer application - Lightly Spray areas with water to receive Hydrostatic 1
label | Attach Photo
checkpoint | Membrane Application (1st coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply first coat of Enviro Hydrostatic 1 by brush or roller Use Enviro Joint Band in floor-wall junctions and general movement joints
checkpoint | Membrane Application (2nd coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply second coat of Enviro Hydrostatic 1 by brush or roller
checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF

## Sheet1 (hidden)
Enviro 700X application
Batch Number
Record batch number of product(s)
Yes | No | N/A
attach photo
Substrate Preparation
Obtain clearance for work to commence.
Yes | No | N/A
Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. Must achieve CSP-1 to CSP-2
Yes | No | N/A
Attach Photos reference of swatch next to substrate
Cracks in substrate
Fill all cracks in substrates wider than 1.0 mm (but not more than 1.6mm) with filler compatible (Enviro-Flex Pro) with the membrane system.
Live cracks or greater than 1.6mm to be referred to engineers for treatment methodology
Yes | No | N/A
Attach photos
Moisture content of susbtrate
3 tests per 15m2 Must be less than 4% and AS4654 (1 and 2). If greater refer to Mirvac for special instruction for change of primer to Hydro-epoxy
Yes | No | N/A
Attach photos of moisture readings( mark area and full shot of area
HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
Ambient temperature and RH (Reading twice a day - every 4 hours)
Mirvac to record temperature and provide reading. Temp must be applicable to membrane application
Yes | No | N/A
Notes of temperature day and time
Mirvac to confirm temperature suitable for application. Sign off
Application of Primer
If using epoxy, Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
yes | No | N/A
If using Enviro 789- Mix at low speed (400RPM) until thouroghly mixed
Yes | No | N/A
Using a brush and roller, apply primer.Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Prime 789 will take around 1-5 hrs @ 20 degrees C (but could be longer depending on ambient temp and RH). Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C (but could be longer depending on ambient temp and RH)
Yes | No | N/A
Attach Photos
Application of sealant to Australian Standard
Apply Enviro Flex Pro to form smooth 12mm flexible cove to all internal corners, penetrations and joints.
Yes | No | N/A
Attach Photos
first coat Application of Enviro-700X
Mix bucket at low speed ( 400RPM) until thouroghly mixed. Record ambient temperature, day and time using a brush for cutting and roller for surface, apply the first coat of 700x. Where membrane is terminated on a building element: Ensure that the termination height is 150mm of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Yes | No | NA
attach photos
second coat application of Enviro- 700X
Allow first coat to fully cured prior to application. Mix bucket at low speed ( 400RPM) until thouroghly mixed. Record ambient temperature, day and time using a brush for cutting and roller for surface, apply the first coat of 700x. Where membrane is terminated on a building element: Ensure that the termination height is 150mm of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Application of 250 N-S Top coat
Allow membrane to fully cured prior to application.Mix bucket at low speed ( 400RPM) until thouroghly mixed.If final coat has been exposed greater than 48 hours, refer to Mirvac for special instructions.Using a brush and roller apply 250 NS as final U.V protection coat. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Yes | No | N/A
attach photos
Protection of Membrane edge
Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Esnure vertical membrane termination junctions are caulked with Enviro FC pro.
Yes | No | N/A
attach photos
QA Testing
Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required
Yes | No | N/A
attach photos
Thickness testing of application to the recommended dft of 1.5mm to manufacturers instructions. 5 tests per 15m2
Yes | No | N/A
Attach photos
24hours flood testing to mark out if applicable
Yes | No | N/A
Attach photos
Holiday/ spark testing of area if flood testing is not applicable
Yes | No | N/A
Attach photos
CLICK HERE TO REQUEST BUILDER SIGN OFF