## Project breakdown
Site QA
| Building A |  | Apartment numbers to be confirmed by Joe
|  | Ground Floor | G.08 | Bathroom Waterproofing & Tiling ITP |  | Ensuite G.06,07.02, | per level add a folder with a check for correct drawing and tile spec
|  | Level 1 | G.23 | Balcony ITP |  | 5,6,11,12,13,14,15,16,21,
|  | Level 2 | G.23 | Benchtop & Vanity ITP |  | 5,6,11,12,13,14,15,16,21,
|  | Level 3 | G.18 |  |  | 4,5,9,10,111,12,13,14,15,16,17
|  | Level 4 | G.18 |  |  | 9,10,111,12,13,14,15,16,17
|  | Level 5 | G.14 |  |  | 11,12,13
Building B
|  | Ground Floor | G.10 |  |  | 5,
|  | Level 1 | G.16 |  |  | 2,3,4,11
|  | Level 2 | G1:G.16
|  |  |  | Bathroom | Bathroom ITP
|  |  |  | Ensuite (G.02, G.03,G.04,G11) only | Ensuite | 2,3,4,11
|  |  |  | Laundry | Laundry
|  |  |  | Stone | Stone Installation
|  |  |  | Balcony ITP | Balcony ITP
|  | Level 3 | G1:G13G.13
|  |  |  | Bathroom | Bathroom ITP
|  |  |  | Ensuite (G.02, G.03,G.04,G10) only | Ensuite | 2,3,4,10
|  |  |  | Laundry | Laundry
|  |  |  | Stone | Stone Installation
|  |  |  | Balcony ITP | Balcony ITP
|  | Level 4 | G.10 |  |  | 2,3,8
Variations |  | Level 5 | G.08 |  |  | 6,
Building C
|  | Ground Floor | G.09 |  |  | 2,3,4,7,9
|  | Level 1 | G.10 |  |  | 2,3,4,7,9
|  | Level 2 | G.14 |  |  | 11,12,13
|  | Level 3 | G.12 |  |  | 4,9,10,11
|  | Level 4 | G.09 |  |  | 2,3,6,7,8,
|  | Level 5 | G.08 |  |  | 4,

## ITP's
Bathroom ITP
Substrate prepared and Tremco primer installed (photo required) | Pass/Fail
Fillet, bandage, angle & 2 coats coat of Tremco membrane installed (photo required) | Pass/Fail
Install angel & screed to falls completed (photo required) | Pass/Fail
Screed / Water test | Pass/Fail
Finish coats of Tremco membrane installed (photo required) | Pass/Fail
Tiling, Caulking & Grouting complete, installer signed off. (photo required) | Pass/Fail
Balcony ITP
Substrate, including Hobbs prepared and primer installed (photo required) | Pass/Fail
2 coats of Tremco membrane installed (photo required) | Pass/Fail
Install pods & pavers.
Stone Installation
Splashbacks, benchtops, Island & Vanity
Protection installed, installer sign off (photo required) | Pass/Fail
Laundry
Angle, acoustic matt & Tremco mebrane (2 coats)
Tiling & Grouting complete. (photo required)
Ensuite
Substrate prepared and Tremco primer installed (photo required)
Fillet, bandage & 2 coats coat of Tremco membrane installed (photo required)
Install angel & screed to falls completed (photo required)
Finish coats of Tremco membrane installed (photo required)
Tiling, Caulking & Grouting complete, installer signed off. (photo required)
manufacturer's Inspection