## Dig-out in Tie In
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA B/2 Activity: Dig-out in Tie In Locations |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Sire Engineer | Eng. Rep / NZTA | Contractor | Date
1.0 Dig-out in Tie In Locations
1.01 | Excavation | Excavate from finish road level (FRL)/existing road level at a depth specified in the design drawing | M | In pavement tie In locations | Measure / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.02 | Geogrid | Install geogrid (prosolve 30x30mm or similar approved) | M | For each pavement tie In locations | Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.03 | Sub-base Backfilling Compaction | 1st layer backfill at a depth specified in the design drawing, use AP65/Stockedpiled material approved by the Engineer | M |  | Measure / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.04 | Sub-base Backfilling Compaction | AP65/AP40 2nd layer backfill at a depth specified in the design drawing | M | 5 per 1,000m2 | NZS 4407.4.2.1/Clegg | Average DoC ≥ 95% Minimum DoC ≥ 92% or CIV 30 | IANZ Report | Contractor |  | A | I | R | dd/mm/yy
1.05 | Sub-base Backfilling Compaction | AP40 3rd layer backfill at a depth specified in the design drawing | M | 5 per 1,000m2 | NZS 4407.4.2.1 | Average DoC ≥ 95% Minimum DoC ≥ 92% | IANZ Report | Contractor | Final backfill layer and testing will be done in FBS ITP | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.