## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Dig-out in Tie-in | itp |  |  |  |  | ITP - Dig-out in Tie-in Rev 0
section | 1.0 Dig-out in Tie In Locations
checkpoint | 1.01 - Excavation
label | Detail of Activity / Test - Excavate from finish road level (FRL)/existing road level at a depth specified in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - In pavement tie In locations
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.02 - Geogrid
label | Detail of Activity / Test - Install geogrid (prosolve 30x30mm or similar approved)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each pavement tie In locations
label | Inspection / Test method - Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.03 - Sub-base Backfilling Compaction
label | Detail of Activity / Test - 1st layer backfill at a depth specified in the design drawing, use AP65/Stockedpiled material approved by the Engineer
label | Action (Hold, Monitor, Witness) - M
label | Inspection / Test method - Measure / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.04 - Sub-base Backfilling Compaction
label | Detail of Activity / Test - AP65/AP40 2nd layer backfill at a depth specified in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1/Clegg
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92% or CIV 30
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.05 - Sub-base Backfilling Compaction
label | Detail of Activity / Test - AP40 3rd layer backfill at a depth specified in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Final backfill layer and testing will be done in FBS ITP
label | Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature