## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e9f70f0a-79b9-46aa-8aeb-935861834072 | checklist | DOT36563 ITP - Safety Barrier Installation, NDD and Service Location Rev1 | itp | DOT36563 ITP - Safety Barrier Installation, NDD and Service Location
ffb556b8-bfba-49f8-b8c5-a15778c2c1cd | section | 1 - Preliminary Works
508ca174-def9-4a93-adb2-c81e3f93379d | checkpoint | 1.1 - Obtain up to date Dial Before You Dig (DBYD) Information
113b7bc3-0ec9-5cc4-860a-9a6e8694b754 | note | FREQUENCY: Prior to commencement
85351801-542a-510c-90c1-6e97a1b80776 | note | ACCEPTANCE CRITERIA: All current DBYD information received prior to commencement of works
f6da0a7c-83c4-5a31-b897-b58557a4e534 | note | REFERENCE DOCUMENTS: 100.5(1)
9db94b47-476a-5df2-9a9f-3bf1e8179556 | note | RECORD OF CONFORMITY: This ITP signed + documentation received
18daacc6-e892-5409-8aa5-e4e2b2128caf | note | HP*
74b23b2a-2273-5982-bd46-9a0f6a287486 | note | RESPONSIBILITY: Site Engineer
b17f1341-27c4-59e2-87c9-720e7cceec95 | date | Date Completed:
d10da089-e845-463a-a704-3924905065c9 | checkpoint | 1.2 - Obtain necessary approvals and permits from the relevant service authorities
0dd38ce7-5ec2-5246-adcc-3af00028e6d0 | note | FREQUENCY: Prior to commencement
9d8a023d-f9c0-5a26-ae82-3e5c2d12b0a1 | note | ACCEPTANCE CRITERIA: All current permits approved and issued prior to commencement of works
00563430-8b4c-5181-afe2-ecb96773a217 | note | REFERENCE DOCUMENTS: 100.5(1)
c4340ca3-5f05-5431-80ee-25437d7ab3c9 | note | RECORD OF CONFORMITY: This ITP signed + Permits issued
8aeaa04b-2ed4-594b-8bef-7ef7f3528a05 | note | HP*
17f288ac-2d9d-5da0-afba-94f3b052cec8 | note | RESPONSIBILITY: Site Engineer
1b31ecdf-13ec-5789-9b3d-8bcf96398597 | date | Date Completed:
249c68f8-d275-4a78-80f8-c3932e336707 | checkpoint | 1.3 - Receival and activation of authorised Memorandum of Authorisation (MOA)
b9e8d72b-a895-564b-8772-70cc72363765 | note | FREQUENCY: Prior to commencement
d51c1822-9bd9-537d-91c5-86e4184023e5 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence work until the relevant authorised MOA has been received and activated
f8fffcc2-30e6-52c5-a8b3-060a7e58f6ab | note | REFERENCE DOCUMENTS: 100.6
c166d4c5-a8f9-54ac-9524-060db25e5ae2 | note | RECORD OF CONFORMITY: This ITP signed + Authorised MOA's received
4962e829-5664-5661-b8fc-b1323e6c9401 | note | HP*
2cf43a69-eb98-5c8b-bdc6-1c5bda45ea28 | note | RESPONSIBILITY: Site Engineer
1cff43d3-ebcc-5866-bb47-cf8e6f8ba3aa | date | Date Completed:
7c04d50a-3243-4ddf-abe4-ee8119e7bd75 | checkpoint | 1.4 - Submission of relevant PMP Documentation, insurances etc.
34f38cea-3c5a-52a6-88b3-9cc96381a2a3 | note | FREQUENCY: Prior to commencement
f75efa15-f20a-5209-890a-bee900f0834b | note | ACCEPTANCE CRITERIA: All PMP documentation submitted to DTP 14 days prior to commencement of works. This includes QMP, EMP, IERP, TMP, HSMP, SWMS
d0ba5da1-f267-549e-a26f-48c05c13eb41 | note | REFERENCE DOCUMENTS: 160.C1
4a90026a-d31d-573c-ba4c-b30c8ec13fc4 | note | RECORD OF CONFORMITY: This ITP signed
0cf16a5d-d07f-5f4f-87a1-24c1af049d3d | note | HP*
c09ca22f-42c5-5c49-9906-d682d06cb9a8 | note | RESPONSIBILITY: Site Engineer
f7aabf7e-4e41-57de-97ec-3be56eeba251 | date | Date Completed:
c713ec6d-0d66-41f9-ae05-91d94a928ed2 | checkpoint | 1.5 - Submission of overall works procedure
94899cdb-b74b-5912-94b0-56b2b357b1a0 | note | FREQUENCY: Prior to commencement
eac2d4e4-79a2-5c46-95f9-36f880f76e4c | note | ACCEPTANCE CRITERIA: Works procedures for GPP process, NDD, Service Location and TreeTrimming/Removal to be submitted to DTP 14 days prior to commencement of works
9613e2cd-8c41-5601-90e9-8fe3997a0df2 | note | REFERENCE DOCUMENTS: Fulton Hogan works procedures
0e214aab-88a5-591f-839c-1da343696d66 | note | RECORD OF CONFORMITY: This ITP signed
92716379-9647-5ca6-a8e0-048c0c121e62 | note | HP
a6c7c19b-d584-5137-886e-e1fba66e8a06 | note | RESPONSIBILITY: Site Engineer, Project Manager
7368feb5-4fbb-5b66-82f6-e76032657465 | date | Date Completed:
f5d98250-eb0c-468c-88a8-3861b8d1a956 | signoff | AUTHORITY HOLDPOINT
b5fd8c4e-c99d-4723-a237-c7901a4dc127 | checkpoint | 1.6 - Submission of Contractors representatives
7d62fbb7-1146-59bd-86ea-0bad09b3b8a1 | note | FREQUENCY: Prior to commencement
158e9999-c9c9-5e75-9cdf-177b15d2ea8a | note | ACCEPTANCE CRITERIA: List of contractor representatives submitted to DTP
b4e99b39-b6da-5101-92f1-40d258f9028e | note | REFERENCE DOCUMENTS: 160.C6
d1f887db-ef7c-502e-bfa8-4fb7eb31c863 | note | RECORD OF CONFORMITY: This ITP signed
2c2dbed9-0120-5c47-a9aa-273e8a64e493 | note | HP
0177907f-4fe9-5998-9012-0c24bc3498f6 | note | RESPONSIBILITY: Project Manager, Superintendent
f592d928-0c5f-5a86-aa6b-6688207d3245 | date | Date Completed:
fab0257a-9c05-4ca3-905a-d9da7348b227 | signoff | AUTHORITY HOLDPOINT
54b387a7-764b-4a1f-9a2e-99bfbd6cf9b3 | checkpoint | 1.7 - Review of Traffic Management Plan
3c620b50-d8f7-5b55-968c-8d2b01caefe9 | note | FREQUENCY: Prior to commencement
7ad40b50-72e5-5ec9-bf13-9aeaeb0b4fc1 | note | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point
113cdff3-1a59-5a98-9425-a3184223dfb2 | note | REFERENCE DOCUMENTS: 166.08
d6fc0623-a785-5b95-9ebd-f4326fd5b4a2 | note | RECORD OF CONFORMITY: This ITP signed
66e3602a-d7b5-50df-9378-b2e68c3d83d5 | note | HP
f832cbf9-e9da-5fa7-aede-cb09575fef6a | note | RESPONSIBILITY: Superintendent
b70030f5-a008-5ad4-b2ad-ed6035a4712a | date | Date Completed:
66d4a450-6a43-49f2-8c6c-e314dfb0ab45 | signoff | AUTHORITY HOLDPOINT
ea8dcda3-9fef-414c-adf9-eda2f369c7af | checkpoint | 1.8 - Road Safety Audit
659c5454-4288-5c4e-a79f-d5cf0a854c32 | note | FREQUENCY: Prior to commencement
b67fd4e4-1134-5130-aa83-698948b345b8 | note | ACCEPTANCE CRITERIA: First batch of MOA's and TGS's submitted for approval to be audited by an external auditor.
379752c2-18f1-5e09-b720-cd19ebaf5cac | note | REFERENCE DOCUMENTS: 100.1, 100.6, 100.7
47abcf78-4fb7-568d-acfc-40d9901a078c | note | RECORD OF CONFORMITY: This ITP signed + RSA report received
25a08210-e18e-5721-9617-d76ffda4f950 | note | HP
3adb0526-e45f-5f87-b1ad-1e88b24ee42c | note | RESPONSIBILITY: Project Manager, Site Engineer, Superintendent
6cb0fe17-13a3-562b-8581-a339842573f9 | date | Date Completed:
14a955e2-2a17-4d84-9255-36f32b80a2fb | signoff | AUTHORITY HOLDPOINT
26f8533a-7983-491a-9667-12c879d9eff7 | checkpoint | 1.9 - Condition of Site
869fed31-399b-5b66-9ec1-2409d67c2c36 | note | FREQUENCY: Prior to commencement
f721ebc4-3a7a-56b2-8b4d-0f627ba4f7ba | note | ACCEPTANCE CRITERIA: Undertake precondition inspection of site prior to works commencing
b3548a73-0a79-5c40-912f-93fac929d519 | note | REFERENCE DOCUMENTS: MP4 / video file for records
b23949f8-6687-587b-8933-14c62a0931c0 | note | RECORD OF CONFORMITY: This ITP signed
38fd6dcc-1b8b-5f87-aae3-b5438e691f16 | note | HP*
f0bd8884-0d05-517a-b714-b69873e63ee8 | note | RESPONSIBILITY: Site Engineer, Project Manager, Foreman
575b8d31-d4f5-5d83-bf09-12bd96cfa96b | date | Date Completed:
260dff7d-8b61-4f9e-a01e-33287e58ad2f | checkpoint | 1.10 - Sign removal and installation
25ec96a5-bb49-5e80-8841-98b3f815a4b6 | note | FREQUENCY: Prior to removal of signs
1cdf51ed-44c4-5df2-9892-3efce1bdcb26 | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
ab470b58-5591-5a33-8619-a2b87afbef38 | note | REFERENCE DOCUMENTS: 714.06
048640b2-0854-5b89-9743-85d73e30d8f0 | note | RECORD OF CONFORMITY: This ITP signed
8aa14450-cf3f-5d37-a22c-78ac785c2910 | note | HP
6b8bc645-f104-5d55-bad4-99c46e45f81c | note | RESPONSIBILITY: Site Engineer, Foreman, Superintendent
841406f5-ce4b-5ffb-a1ff-5fcea49e3ab9 | date | Date Completed:
dd89f10a-37bb-450d-bb1f-ba168218dfcf | signoff | AUTHORITY HOLDPOINT
6805dffe-d50a-4e84-8170-a3d435544b72 | section | 2 - NDD and Service Location
5feeea08-4d3b-4bb9-bb89-cc18ac86baa9 | checkpoint | 2.1 - Service Location and marking
99e8fc17-0899-5e27-9947-84529ea0c440 | note | FREQUENCY: Prior to excavation, stripping, clearing/grubbing, ground penetration
b94a794a-782f-5e0e-a588-d8f60a47e54d | note | ACCEPTANCE CRITERIA: All underground services must be located by a suitably qualified service locator. Where denoted NDD in the drawings, services must be visually inspected
b984c928-3f5f-5c84-94ef-4113b2a89ca1 | note | REFERENCE DOCUMENTS: 100.12, 100.5(2) Drawings
901893d5-4afe-5e14-a248-30c29586f0c8 | note | RECORD OF CONFORMITY: This ITP signed
10b1e4b1-0185-54ca-a5cd-da27fb900814 | note | HP*
6b795bab-2bbe-594e-8d2d-d869183075b6 | note | RESPONSIBILITY: Site Engineer, Foreman, GPP, Subcontractor
f9024260-09d0-55e4-b614-866774493cae | date | Date Completed:
0b4fdbc5-026d-47e4-8c29-6348227acc1a | checkpoint | 2.2 - NDD Works / service locating
fb01393b-c302-527e-8e5e-9b9d5307ceb7 | note | FREQUENCY: Prior to barrier installation
564c4675-1096-5430-826e-89e79794f655 | note | ACCEPTANCE CRITERIA: NDD locations confirmed within 10 working days from submission of prior to completion of Non Destructive Digging (NDD) works
8bd26e05-a5a9-54ae-9217-78d58b0df916 | note | REFERENCE DOCUMENTS: 100.5(3)
0550666d-b6a4-5d33-b91b-ab184c86ee1a | note | RECORD OF CONFORMITY: This ITP signed
667ba96d-d2fa-5400-a825-77bb491bfc08 | note | HP*
984f892b-7507-59df-9415-b0c97e8923a7 | note | RESPONSIBILITY: Site Engineer, Foreman, GPP
047e6ba5-a93a-53d5-8658-1b6c79163ce5 | date | Date Completed:
c02e522a-fc54-4a24-ae92-66f195a7ff4e | checkpoint | 2.3 - Approval of NDD information
ffb00300-b209-50f1-85da-b8cb5a1c5bbc | note | FREQUENCY: Prior to barrier installation
31949731-b705-58a0-a368-36d0f0ea6d40 | note | ACCEPTANCE CRITERIA: NDD information supplied to DTP a minimum of 14 days prior to any works commencing on any safety barrier run.
cbd90c62-ad77-5f53-ae31-bfa7e1ee5d1e | note | REFERENCE DOCUMENTS: 100.5
4bf447dc-6cef-5758-a5c0-05ffff651a59 | note | RECORD OF CONFORMITY: This ITP signed
5ae4594c-cd5d-505f-9754-aff7c1f6647d | note | HP
25e5e2aa-9fb0-5c0a-9d9c-d12c28d9d7ca | note | RESPONSIBILITY: GPP, Foreman, Superintendent
f229e499-d917-5a8b-afd9-e10d88c359ae | date | Date Completed:
d4484548-c118-44a9-9d4f-fa2b40eac0eb | signoff | AUTHORITY HOLDPOINT
eeec250a-bb6d-48b1-a8a7-cc00feed9614 | checkpoint | 2.4 - Refilling of NDD potholing
4b5ede6a-bd30-5a3d-8334-17557895e04c | note | FREQUENCY: Prior to leaving site for the day
da934903-a1a2-56ed-8c27-c75f653c7633 | note | ACCEPTANCE CRITERIA: Potholes refilled with compacted sand the same day
2926fce0-a650-5f3f-a495-6feeb7025e0c | note | REFERENCE DOCUMENTS: 100.5
c8e5ff5b-f825-529f-8b06-326ba97a558c | note | RECORD OF CONFORMITY: This ITP signed
602b6906-a0aa-5982-b944-33d7d0989f39 | note | WP
9cd013cc-ab2a-5237-8be3-577e43ee52e7 | note | RESPONSIBILITY: Foreman, GPP, Subcontractor
c8dd58de-c2eb-5005-bed1-2aa775f3769e | date | Date Completed:
4a63c924-f96d-4a00-a452-18a52915ddba | section | 3 - Vegetation Works
15f33071-1719-4872-b503-637ff19309ca | checkpoint | 3.1 - Approval for vegetation removal
0ff695a4-4642-55df-a632-0d5daba5567f | note | FREQUENCY: Prior to commencement
e42ff66c-771d-5f57-aadb-56ebd46cdb67 | note | ACCEPTANCE CRITERIA: Meeting held with DTP and Council to identify and mark trees / vegetation for removal and approval permits issued
b0552fdb-67f9-54e4-b8e6-37828eee6f0e | note | REFERENCE DOCUMENTS: 176.I1
456fbf1e-b1c5-5eaa-9818-4ae0395ddacd | note | RECORD OF CONFORMITY: This ITP signed
82c690e1-29e9-519c-b90a-cfd0b87aa0ab | note | HP
fb26598b-cda5-5522-80bc-f8c30914da84 | note | RESPONSIBILITY: Site Engineer, Project Manager, Superintendent, Council Representative
9a8f0776-099f-5965-a835-a4024307d0c9 | date | Date Completed:
92c70808-d65f-4dc6-bf56-e5742947bb7c | signoff | AUTHORITY HOLDPOINT
417b8e75-18e5-47de-9149-a0d75c177d09 | checkpoint | 3.2 - Tree trimming
c164acd6-9a1a-59ed-964d-5ca0384dd3bf | note | FREQUENCY: During NDD/Service locating works
e8a0faa3-7601-5e95-9c41-4b58143accc4 | note | ACCEPTANCE CRITERIA: Trees to be trimmed in accordance with specification and in designated locations as per drawings and Superintendent's advice
9e9e0096-465f-5680-8dea-1265c3962d4d | note | REFERENCE DOCUMENTS: 201 Drawings
aa340404-0b50-5ab3-be91-9b05dc8149d6 | note | RECORD OF CONFORMITY: This ITP signed
1ce9db9b-07db-5aa3-b47f-feb6b0bf7064 | note | WP
8e5d95ad-c641-5301-8eaf-83fbaac96429 | note | RESPONSIBILITY: Foreman, Superintendent, Council representative, Subcontractor
db77ede9-9aa1-52c8-b9ce-65214670b469 | date | Date Completed:
4729806a-507a-4bbb-bec8-8987690d857c | checkpoint | 3.3 - Tree removal
9437a3af-7e66-546f-acc9-a2ba7ab07a6d | note | FREQUENCY: During NDD/Service locating works
edcb562d-284f-5dc1-90a2-cb177e7b2e49 | note | ACCEPTANCE CRITERIA: Trees can only be removed with the approval of Council Representative and Superintendent. All tree matter removed from site and holes left from tree stumps filled accordingly.
c4fca37b-c812-5fa9-b606-04346a6c82ae | note | REFERENCE DOCUMENTS: 201 Drawings
2c7bcf2a-da86-5cca-a2a4-2f4af2224d46 | note | RECORD OF CONFORMITY: This ITP signed
3d775427-6b6c-5996-9418-0f2a10572338 | note | WP
45a0870e-c544-59f9-8da2-b03e8c865802 | note | RESPONSIBILITY: Foreman, Superintendent, Council representative, Subcontractor
665aa7f1-610d-57da-980c-1a4ac65f2c4e | date | Date Completed:
c7247791-eee2-4910-a335-50c3f9670ea4 | section | 4 - Safety Barrier Installation
90aeb023-d207-46d4-bffe-cfb8489d20c0 | checkpoint | 4.1 - Setout of barriers
ef680ec7-3afc-5138-b956-b867cec2bdcf | note | FREQUENCY: Prior to barrier installation
b0c45acb-c31b-5979-aeb4-2334951dd27a | note | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence. Barriers to be set out in accordance with contract documentation and VR specification
b5061b24-5b82-568b-b9dc-0a5462d1a4c5 | note | REFERENCE DOCUMENTS: 708.08
a47b06a3-61e5-553e-9e95-c4b02dd591bb | note | RECORD OF CONFORMITY: This ITP signed
9eef980e-8093-51d7-ace7-4c4307ab921d | note | HP
ad5c8b35-f0b2-506f-96ad-54c1647729fe | note | RESPONSIBILITY: Site Engineer, Foreman, Superintendent, Subcontractor
c0f84c4f-8d7d-5588-b5b1-61dde6937c6e | date | Date Completed:
0f014b69-9d52-4241-9d0b-535011b1f3b9 | signoff | AUTHORITY HOLDPOINT
59418da5-8736-47a7-a4ad-c563e527741b | checkpoint | 4.2 - Approval of ground beam locations
80a40caa-bc03-5e75-a47d-5fa3e3a5891e | note | FREQUENCY: Prior to barrier installation
2476b89e-54f0-53f5-87e9-b754371e8426 | note | ACCEPTANCE CRITERIA: Details provided to DTP and proposed location for ground beam approved prior to installation
c13eb226-c442-5c87-9bfe-639215226abd | note | REFERENCE DOCUMENTS: 708.08 (a)
964b19e7-5d4e-5760-b769-91f58ebf0982 | note | RECORD OF CONFORMITY: This ITP signed
272292fd-8370-500c-ba6c-4ddc4a72fa5c | note | HP
115e28c6-b121-58ad-90de-18b5731da66d | note | RESPONSIBILITY: Site Engineer, Project Manager, Superintendent, Subcontractor
b73db744-c020-5969-a6b9-fe58e20a5144 | date | Date Completed:
8eea3419-d6ba-4b18-9a5d-bb005318cc7e | signoff | AUTHORITY HOLDPOINT
14e37c9a-e1cf-4d89-814d-68fa9baf9ca3 | checkpoint | 4.3 - Compliant safety barrier installation
024e7cb4-1fd3-5547-b672-4d5acf88f9b7 | note | FREQUENCY: All barriers
3e3d1d03-4e55-5adc-bdf6-b3210ee369fe | note | ACCEPTANCE CRITERIA: All safety barriers installed within VR and Manufacturers Speficiation
5b19c08a-e0a1-5e93-9816-ef4e6f04045c | note | REFERENCE DOCUMENTS: Manufacturers specification
139a3728-f233-5c93-8a8a-8346525ba627 | note | RECORD OF CONFORMITY: This ITP signed
584b5e11-807b-599a-8729-bcf26e773fcb | note | AP
778a0e73-ad8f-57f4-a034-d7abffcafef6 | note | RESPONSIBILITY: Site Engineer, Superintendent, Subcontractor
5fc8a924-f8d8-5316-adec-3529f3cf9e37 | date | Date Completed:
c711ef8c-859f-426d-a27f-5069e71447da | checkpoint | 4.4 - Certification of steel for guardrail
3fa8f392-9481-5f93-bca1-9fd95aee4ccc | note | FREQUENCY: All barriers
3d7afd1c-f2a1-5ef6-b942-49677a30c63d | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
5c5bd234-74cb-5cfc-ae86-d857ee1de1b8 | note | REFERENCE DOCUMENTS: 708.05
cef274fb-afd5-51a6-aeb9-343f50e8f6cb | note | RECORD OF CONFORMITY: Certificate received
45f5c03f-a173-54a7-a321-9955d2d64a57 | note | AP
4a36ec52-7ed9-513d-ba19-a2b7b80903f9 | note | RESPONSIBILITY: Site Engineer, Superintendent, Subcontractor
915847c4-9c5d-5782-baae-9139630f648c | date | Date Completed:
8515d018-a494-409a-bd1e-96a8cdd56e51 | checkpoint | 4.5 - Safety Barrier CoC documentation
58bbf633-0c82-5b2b-a92c-0575373bf497 | note | FREQUENCY: All barriers
1718ccd9-96c9-5990-89dc-b18a101ed4f4 | note | ACCEPTANCE CRITERIA: Certificates of Compliance issues for all barriers installed
72fef2c1-0e53-53d4-a038-3f8409d4a197 | note | REFERENCE DOCUMENTS: 708.1
1350a48d-7ad6-5df9-9e77-52a2a23b8937 | note | RECORD OF CONFORMITY: CoC received
7f26f6fa-2f4e-5490-9e33-235f0828b153 | note | AP
94a4beff-7f66-5687-98c8-8939b2e62d3c | note | RESPONSIBILITY: Site Engineer, Subcontractor
7f91d610-7470-5a77-8c3b-d57ca9f46f36 | date | Date Completed:
93845326-7ac2-4295-9daa-230d2f98a26d | checkpoint | 4.6 - As-constructed drawings
ffdf4069-f6e8-5f0e-85b1-66d84734d568 | note | FREQUENCY: Completion of project
7ffcf109-38f5-5c80-86e2-7806297a7fda | note | ACCEPTANCE CRITERIA: Submission of As-Constructed drawings to DTP within 20 days of practical completion
c836c2c6-ee00-5d10-88f2-da8b60ccb960 | note | REFERENCE DOCUMENTS: 160.A9
ce67112e-9d54-5022-9996-236cf62997c7 | note | RECORD OF CONFORMITY: As-constructed drawings
266864c4-c400-5267-b02c-368c13b058d0 | note | AP
7cf775bc-80fe-5192-bf87-0a61da58ed4c | note | RESPONSIBILITY: Site Engineer, Superintendent
352f183c-0927-5e0a-8cdf-a72cd3d5f40d | date | Date Completed:
31804b59-2731-470c-b520-f2348a52ae53 | checkpoint | Final Inspection
14e56508-e7bc-5e01-9925-4bc7b889b270 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8f5e1469-db32-5016-a473-ca3c39959e24 | textbox | Print Name:
78eb1ee7-5016-59b9-8d3a-1101366c3188 | textbox | Position:
11377853-aff4-5713-a119-95c5b31774eb | date | Date: