## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Project Startup Hold Point |  |  |  |  | Yes | Project Startup Hold Point | 1bbb3619-f0db-4d7b-8af8-9fa989fc7f02
checkpoint-status |  |  | checkpoint | Project Startup Hold Point
label | 13a2ceed-9142-5446-a1f0-eaa6b3e83750 |  | note | Attach Hold Point details and any relevant documents, photos, etc.
label | e7395725-5637-57e6-a068-6f2f726c5ca6 |  | note | Issue to Client for their approval and sign off.
text | 671c7abf-93c4-5abf-b1d8-67759621f3e5 |  | textbox | Hold Point number:
text | 32969f13-66ad-59da-9555-5643e62e231b |  | textbox | Title:
text | 1cd104df-af16-524d-b306-6bf36352ee1d |  | textbox | Specification / Clause Reference (if applicable):
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | ITC 02 - R11 Stormwater and Drain Installation (R11) Rev 1 |  |  |  |  | Yes | ITC 02 - R11 Stormwater and Drain Installation (R11) Rev 1 | 2d5f3e77-db12-49cb-a756-1934ff7e3934
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 07481814-ac3b-5ce3-a6b6-12e022f069e7 |  | textbox | Lot Opened On
text | 07f30bbc-f730-57a2-b8c9-8bcbaa47cf22 |  | textbox | Date of Works
text | 85aed185-e62d-5714-bde5-9e2b158cfc94 |  | textbox | Lot Type
text | e999e85a-d980-514b-86c1-d1029ce97ec0 |  | textbox | Start Chainage
text | 50576da8-a3d3-5bf5-b104-a475683f8cd7 |  | textbox | End Chainage
text | 3790d4e6-8e1a-598f-a1d3-dfcb0f577c99 |  | textbox | Offset
text | d5f87945-431e-5e4b-a0b4-1d342b15514c |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Safety Review
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 3c46ee8a-152f-5372-9699-2cca6165e7bb |  | note | REQUIREMENTS / REFERENCE - Project Safety Plan
label | c3e85edc-d0e6-591b-80fd-8dcc96335519 |  | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural)
label | 63002b4f-1563-513c-834b-e5fd458cb028 |  | note | Required Safe Work Method Statements completed and signed
label | a245ef69-9ee5-5185-9b27-bdddbe4d6a3e |  | note | Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 00a06390-845f-5f3d-b7cb-ce52b981f017 |  | note | REQUIREMENTS / REFERENCE - Project Environment Plan
label | 5153b7a9-99c8-5298-a306-19c59257fc2e |  | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs / G38.
label | d9044f11-ab8f-56cd-b75b-718385192344 |  | note | Air quality to be visually monitored for dust etc. as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Supply of Precast Concrete Members subject to traffic and/or Earth Pressure
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 14be60d2-065c-592c-9316-726ebf874aba |  | note | REQUIREMENTS / REFERENCE - R11 Cl 2.4.1
label | c65b0dff-423b-5a06-b05f-822c61e610c7 |  | note | ACCEPTANCE CRITERIA - Submit to the Principal:
label | 05200fbf-2095-5ced-bacd-b62d1efbbda8 |  | note | Product Drawings Including
label | 3c80120a-0ca7-5618-8fd1-c91ddc7cb3ea |  | note | Full product dimensions
label | c480b776-a5c0-56d9-b786-4bc6d680b8ad |  | note | Reinforcement details
label | 5d7cab95-f5e4-5ced-9827-52cf7782d28a |  | note | Cover (if reinforced concrete)
label | 48d96a7b-8852-566d-85dc-d8d5cd730338 |  | note | Design lifting points
label | eadeb0e3-6c76-51f4-91a6-ee426bda0d52 |  | note | Recommendations for attachment to adjoining structure(s) (if applicable)
label | 76b78957-672c-5f64-b7fb-6f3e30ad211b |  | note | Certification by Structural Engineer.
label | 90318c7a-0d30-5669-9fea-935b9a0aa0c9 |  | note | Details of methods of manufacture, testing & installation etc.
label | e2520ef7-853a-595c-9ada-ec8dcbcc6916 |  | note | HOLD POINT: Submission of all quality documents specified in clause R11 2.4.1 at least 7 days prior to date of delivery, for precast concrete members subject to traffic and / or earth pressure loading, and water retaining structures with capacity greater than 25 000 litres
text | 76ec9cf2-fe35-54e4-a16d-bd89b9b74c2c |  | textbox | HOLD POINT NUMBER:
text | ece81e14-0fc3-5cc0-afb1-4d411fe59b1a |  | textbox | DATE SUBMITTED:
text | 28018c20-ee72-5b75-b3db-127a65f0850c |  | textbox | SUBMITTED BY:
text | 9900201e-5331-5c73-a311-1aef19775300 |  | textbox | SPECIFICATION AND CLAUSE:
text | 0a2f11ab-4f32-5678-9954-0837b9784108 |  | textbox | HOLD POINT DESCRIPTION:
text | 4139a7ee-7cf3-52fa-b697-5c7e98b31a82 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Certificate of Conformity
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 41ae64db-5350-5125-a67f-51e3043ffec4 |  | note | REQUIREMENTS / REFERENCE - AS 4058 R11 cl 2.6
label | af5b05f8-59ba-56ed-b2f4-f7236b67de54 |  | note | ACCEPTANCE CRITERIA - Signed certificate stating that the materials used in the finished product conform to the requirements of AS 4058, and must describe the item and identify the inspection and test records that verify conformity
label | 612c30cb-a4d9-5892-bf9b-1b0d9e87dad4 |  | note | As per Clause 2.7, where shown on the drawings, supply CMP Manufacturing half round corrugated steel pipe (or Principal approved equivalent) for batter drains. CoC is required for this product
label | dbe9c600-240a-5c1c-90c4-af52e0768b89 |  | note | HOLD POINT: Certificate of conformity
text | 1844e413-c05c-5fee-885e-6bfb0ef1b404 |  | textbox | HOLD POINT NUMBER:
text | 68b2b86b-adc9-58ce-8bbf-c07585da9c17 |  | textbox | DATE SUBMITTED:
text | fa9c2145-c704-5534-bfb2-8daff39fc923 |  | textbox | SUBMITTED BY:
text | 6a5b2925-50dd-50b5-a21d-1c7371fe061d |  | textbox | SPECIFICATION AND CLAUSE:
text | 93a74234-9a0b-508d-9cd6-7ba361f6fc32 |  | textbox | HOLD POINT DESCRIPTION:
text | 22d9259c-c043-5001-b3cf-742a59ff2f57 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Supply of bedding and support fill material
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 48860caf-eea2-5af2-8501-e6cbff5b0176 |  | note | REQUIREMENTS / REFERENCE - R11 cl 3.1 AS 3725 - Table 6 AS 1597.2 – Table 5.1
label | 475da5c2-90c9-5e2c-be22-d5975835e500 |  | note | ACCEPTANCE CRITERIA - Bed, support and backfill all pipes with non-aggressive material (pH > 5.5, SO4 < 1000 mg/Kg (ppm) and chloride < 1000 mg/Kg (ppm))
label | 4982be74-b5b5-53b3-8b95-6df154fec8c4 |  | note | Bedding and Haunch Zones must have particle size distribution within the limits set out in Table 6 in AS 3725 or table 5.1 in AS1597.2, and a PI not more than 6
label | e1538199-710b-52a1-af50-6859c6f9c2e4 |  | note | Side and overlay zones must have a maximum particle size of 53mm and a PI between 2 & 12
label | 993b0d50-57ab-511b-93d0-62ef0c4a8fcb |  | note | Fill Material for Embankment in Open Drain must be graded and compacted as required
text | 9cc9a221-36be-56bb-bda6-352d091d9fac |  | textbox | HOLD POINT NUMBER:
text | deee5530-2030-57cc-b7a7-e203c6296da5 |  | textbox | DATE SUBMITTED:
text | 66db27f3-90f4-5ce0-95ea-69baa52d1dac |  | textbox | SUBMITTED BY:
text | 57c4525b-91e8-50c6-a3ea-bba790d94636 |  | textbox | SPECIFICATION AND CLAUSE:
text | 57f1030f-6a09-5393-8158-d5d950b46603 |  | textbox | HOLD POINT DESCRIPTION:
text | 8a4219f4-597a-54e3-acb3-27741f143a7c |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Rock Rip Rap
checkpoint-status |  |  | checkpoint | HOLD POINT
label | a458ae1e-8c4b-5116-b4ad-c343a14f0c93 |  | note | REQUIREMENTS / REFERENCE - R11 Cl 3.4
label | 916f73ad-ddea-5bb0-9d1a-5be58e799cc9 |  | note | ACCEPTANCE CRITERIA - Rock for rip rap scour protection must be dense, hard, durable, resistance to weathering, angular in shape and free from defects and degradation and chemical alteration.
label | 1ed9ab1c-ba7a-5c6e-9351-18aff8bc27e0 |  | note | Rock that is laminated, fractured, porous or physically weak must not be used.
label | 26660ca7-441b-5173-bf03-fa5ce19b3793 |  | note | Rock must be free from overburden, spoil, shale and organic matter.
label | c455aef3-a645-551a-910f-1d45f22481c7 |  | note | The rock must be certified by the Geotechnical Engineer to confirm that it is suitable for use in the works
label | 22aa25f0-2bd4-5e3f-b5cc-eeba5660d2bf |  | note | The rock must also comply with the property requirements of R11 Cl 3.4.2, and the sizing and grading requirements of Cl 3.4.3
label | 8ab07806-df4a-5c8f-b32d-1969fca03517 |  | note | Provide test results for rip rap rock once for each source of rock material, prior to placement
label | 7b61253d-af67-5945-b01e-8f9065b062c8 |  | note | HOLD POINT: Provide test results and certification documentation regarding the properties and source of the rock rip rap
text | 25815364-bbd0-5658-9344-ba9222c778ef |  | textbox | HOLD POINT NUMBER:
text | 727c10ab-2cb4-567e-9485-11dc27b41558 |  | textbox | DATE SUBMITTED:
text | 7a8b1cf1-dd4c-59b2-8457-27d034e2cb55 |  | textbox | SUBMITTED BY:
text | 32c6ebc9-8945-553c-a5ff-a5ae12884876 |  | textbox | SPECIFICATION AND CLAUSE:
text | 5bfb2814-1b6a-5c5e-a889-8dd3c84ab364 |  | textbox | HOLD POINT DESCRIPTION:
text | c70ecc82-aa93-510e-be0b-8359e3449e0a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Setting out
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 90c085c0-4b8f-5015-9f34-ae28378b02e9 |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.1.1 R11 Annexure C
label | 8efd8b02-ea4c-568c-a961-b40e6c7d67de |  | note | ACCEPTANCE CRITERIA - HOLD POINT: At least 10 working days prior to the date of commencement of the work, provide notification to the Principal that set out of drainage system has been completed and details of any design changes in locations and levels proposed by Abergeldie
text | 4b57178c-b0ec-5b0e-8e07-6c9ba4f56891 |  | textbox | HOLD POINT NUMBER:
text | 001d305e-9fc5-5dde-8308-125eb960e250 |  | textbox | DATE SUBMITTED:
text | 0de23369-ce0a-5ac4-be5e-8b2abc5fece5 |  | textbox | SUBMITTED BY:
text | 1be5c596-2f0c-52b6-83f1-50b67b16e6b3 |  | textbox | SPECIFICATION AND CLAUSE:
text | a5b6651a-bf8b-53fc-a875-ba954e4fa4bc |  | textbox | HOLD POINT DESCRIPTION:
text | c45336c8-f1f5-590e-9cc4-65050f2b0919 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Open Drains
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 0f7988b6-0f7b-5f31-aece-763328a84106 |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.2.1
label | 36066ac7-8996-5b90-8208-3df17cc21add |  | note | ACCEPTANCE CRITERIA - Excavate open drains (including topsoil) as per Drawings or to a minimum depth of 300 mm, minimum base width of 500mm and a minimum waterway area of 0.2 m2, with side batter slopes not steeper than 2H:1V.
label | 710a56fe-0649-5f58-8909-3d172231da97 |  | note | Grade to a slope of not less than 0.5% to ensure a free flow of water.
label | aaf27656-5fbb-5c9c-a63a-a4a2428f47de |  | note | All linings must be placed to prevent water ponding
label | b24104bb-2607-5a3d-aefe-1cf8b0e9351e |  | note | HOLD POINT: Notify the Principal if 0.5% minimum grade cannot be achieved
text | 45a7efef-3ff1-513a-8e84-4576fadf89b6 |  | textbox | HOLD POINT NUMBER:
text | e3f6a2f1-b127-51f1-b2a5-bb590f09d393 |  | textbox | DATE SUBMITTED:
text | 37591d9a-d313-59c0-8d39-5acd34b34838 |  | textbox | SUBMITTED BY:
text | dfaa8044-b13f-50d5-bfcd-953b480225ac |  | textbox | SPECIFICATION AND CLAUSE:
text | 86c29a41-4a1e-5f00-bff4-7513e0444ecb |  | textbox | HOLD POINT DESCRIPTION:
text | 857cf449-dee1-56c9-b1d7-939a403887f2 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Excavation for drainage structures
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 89386a1d-db47-5591-b5ac-600632302adf |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.3.2 Table R11.2
label | d6d7b89d-8a02-51f8-a497-288bcb064635 |  | note | ACCEPTANCE CRITERIA - WITNESS POINT: Submit notification to the Principal, not later than 24 hours but not earlier than 5 working days prior to the anticipate date of completion of excavation and preparation of foundations for pipe installation and other drainage structures.
text | 04537a94-1be8-5427-be79-f90d4904f166 |  | textbox | WITNESS POINT NUMBER:
text | 67cd60b0-a20d-5f16-94f3-25d6a0e167eb |  | textbox | DATE SUBMITTED:
text | 21755e54-6016-5990-a65c-6c3dea6ef6b0 |  | textbox | SUBMITTED BY:
text | ccff1f5a-0f13-5e3a-9e25-ab015bb9e72c |  | textbox | SPECIFICATION AND CLAUSE:
text | 70c625b1-fd28-5f5d-8cc8-c8809e4109b3 |  | textbox | WITNESS POINT DESCRIPTION:
text | 6e6676ef-5003-5afa-951d-b4eabc83d434 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Inadequate Foundation Material
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 31e3ccb9-a301-5106-962d-bf688cd7ad5f |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.3.3 Table R11.2
label | 195aface-877e-590c-8335-eecbf825108d |  | note | ACCEPTANCE CRITERIA - Notify the Principal of any area of the foundation which may contain material that is inadequate to support the drainage structure. Principal may direct method of rectification if they are in agreeance.
label | d52cb443-be94-5aab-ad63-042196bccab5 |  | note | Where sides of trenches for drainage structures are composed of material which may require removal and replacement, notify the Principal of the presence of such material
label | ebf8819e-a3f4-5da1-af94-11b33199a378 |  | note | Replace inadequate foundation material with materials from cuttings or with other material acceptable to Principal and compact to (requirement of Table R11.2) 95% compaction
label | 70691957-7226-5cf4-85a9-3d783c2e39f1 |  | note | Geotechnical engineer to arrange tests and inspect all foundations of all proposed drainage structures following replacement or foundation treatments and provide certification that foundations are acceptable
label | 7436b700-5ac3-548b-ab30-0569f2795bb6 |  | note | HOLD POINT: Details of tests, inspections, assessment and any proposed foundation replacement or treatment by the geotechnical engineer
text | 7b5bf6d2-7f1c-510c-8902-4742e35baea9 |  | textbox | HOLD POINT NUMBER:
text | f39dae23-0cdf-5347-909b-4686c6d5c5fd |  | textbox | DATE SUBMITTED:
text | c237e27b-3c03-5069-8d9a-ec9526a84f2c |  | textbox | SUBMITTED BY:
text | 010aaef0-11a6-5b50-a78c-46489c226e0a |  | textbox | SPECIFICATION AND CLAUSE:
text | d3f13a77-980b-5a81-8cdd-4b1e4fc3313f |  | textbox | HOLD POINT DESCRIPTION:
text | 0dcc263e-d7e5-5b7f-9ff1-8150d9a6b640 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 11 - Construction of Other Drainage Structures
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 2e4cb7a3-0b74-55f4-9ca8-485ab70c74b4 |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.7
label | 5d1460fb-c22b-5f32-b979-6be33b0b9b0a |  | note | ACCEPTANCE CRITERIA - References to “other drainage structures” means “drainage structures other than pipes and box culverts” and includes pits, associated ladders / step irons, pit covers, lintels and grates, junction boxes, drop structures, inlet and outlet structures, headwalls, wingwalls, batter chutes and energy dissipators, and modifications to existing drainage structures
label | cc8ac97f-d46c-57fd-933b-ea70a8ffe296 |  | note | WITNESS POINT: Submit notification to the Principal at least 7 days prior to construction of drainage structures other than pipes and box culverts
text | 97025f74-0f03-5e82-9c03-fb7f588e9274 |  | textbox | WITNESS POINT NUMBER:
text | 8f02576b-c35d-5bb8-9d63-842fd3dbb585 |  | textbox | DATE SUBMITTED:
text | d87e5afe-0db2-565c-86c7-ecd3b6fc1691 |  | textbox | SUBMITTED BY:
text | 3b4a67a8-faa5-5397-99e8-e064f7c01885 |  | textbox | SPECIFICATION AND CLAUSE:
text | 86cc4e86-fae6-5530-849e-9796e1a3a50a |  | textbox | WITNESS POINT DESCRIPTION:
text | d05a2d14-7da7-5cf7-a096-8f24ac5f794a |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 12 - Compaction
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8e444f64-d294-52d7-85b4-0d76455f2749 |  | note | REQUIREMENTS / REFERENCE - R11 cl 4.9.2 Table R11.2
label | f0399b9a-70fa-5f7e-8936-61c55a750707 |  | note | ACCEPTANCE CRITERIA - Place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150mm compacted thickness and compact to 95%. For backfill of Select Fill in Side and Overlay zones of box culverts, and for existing twin 1800mm diameter culvers as shown on the Drawings, the minimum relative compaction is 98%
label | 22d393b4-bc94-55ec-a7a1-f0204a3395d8 |  | note | For backfill material within the Selected Material Zone of the adjoining earthworks (Refer R44 Spec) the minimum relative compaction is 102%
label | 99fdcfbd-e10d-5383-9244-5bed0e9b7b3e |  | note | Refer to Table R11.2 for compaction requirements
label | 96cb7f7c-e245-5f14-86ed-0c33a8362fc4 |  | note | Follow procedures for achieving adequate compaction of fill outlined in Abergeldie’s Project Quality Plan
label | f127d336-ed51-5457-a0bf-02f762535710 |  | note | Comments / Attachments / Records - Compaction test results
checkpoint-group |  |  | section | 13 - Construction Traffic
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 7d1940e6-7dcf-55d0-8912-3033a9065d70 |  | note | REQUIREMENTS / REFERENCE - R11 Cl 4.10 TfNSW G2 – C2
label | 9d68efc8-f6bf-5b71-83c2-065b6838f422 |  | note | ACCEPTANCE CRITERIA - Prior to moving heavy construction plant or vehicles over box culvert structure, submit the Principal with a certificate and verification of protective measures in accordance with TfNSW G2-C2 if required.
label | 45229acc-79b4-5147-aa68-d7da37bad0a4 |  | note | HOLD POINT: Submit certificate of verification of protection measures prior to heavy construction loading
text | 713628dd-b982-5a27-aa60-dcb980b49dd5 |  | textbox | HOLD POINT NUMBER:
text | 027c0eb9-022f-5208-9d62-65ab1245680a |  | textbox | DATE SUBMITTED:
text | 2ffe0d26-37fb-54e4-a4c0-88cae40514f6 |  | textbox | SUBMITTED BY:
text | eb0ab50c-6697-50ec-be2c-7ae02d82b76a |  | textbox | SPECIFICATION AND CLAUSE:
text | 16053338-d5c8-506b-9f17-8ad9fbdf8e0e |  | textbox | HOLD POINT DESCRIPTION:
text | 542d20ad-de3c-5d28-922e-034c26ec4606 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 14 - Construction Tolerances
checkpoint-status |  |  | checkpoint | VERIFICATION
label | aa3b4fb6-a33b-543e-8497-b6fe3ef87a9d |  | note | REQUIREMENTS / REFERENCE - R11 Cl 5.1 Table 11.4 TfNSW R116 TfNSW R119 TfNSW R83
label | 7030ad1f-984d-5a78-940b-7b64f0cbdf9e |  | note | ACCEPTANCE CRITERIA - Assets installed as per required construction tolerances
label | f40241f8-0aeb-599c-8f3f-4b140e112d1a |  | note | Comments / Attachments / Records - Survey report
checkpoint-group |  |  | section | 15 - Inspection of Stormwater Box Culverts
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 2991a518-22fb-57ab-813b-8a85d7380fc8 |  | note | REQUIREMENTS / REFERENCE - R11 cl 5.2
label | 95032ac9-186b-5caa-8790-3963f0c618a3 |  | note | ACCEPTANCE CRITERIA - Prior to commencing construction work undertake a CCTV inspection of any existing stormwater drainage pipes and box culverts that are to remain and provide a condition report to the Principal. Report any non-conformities including cracks greater than 0.15mm. Nominate a repair method in line with Concrete Pipe Association of Australasia’s publications listed in R11 Cl 5.2. Do not commence repair works until the Principal authorises the repair method(s)
label | fc8530e4-ac27-5225-8f6f-53bcbb27e27d |  | note | Carry out CCTV inspections of box culverts to verify that the works have been constructed within the specified tolerances, the flow of water is not obstructed by waste construction material left inside, and to check for visible signs of defects, at the following times:
label | 1755b627-3ed7-525d-b9f0-a053bf342046 |  | note | On completion of the subject drainage structure and prior to commencement of the overlaying pavement,
label | e7d8ee2e-35e3-54d5-bf5f-b64929f92e47 |  | note | On completion of overlying pavement but prior to opening to traffic, and
label | f0704cec-bd94-5415-8ba4-c1e8efa1a7d0 |  | note | No more than 14 days prior to completion
label | f90742af-3577-51f1-aec3-ce8e083919b1 |  | note | On completion of the inspections, submit to the Principal a report of these inspections and any nonconformity detected. The inspection and reporting must be in accordance with WSA05-2008
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | NCR
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | 5d7a643f-0fe7-577b-ac1e-73fb5beba4b9 |  | textbox | Lot Verified By:
text | 993eb967-1e39-5e6c-9baf-fa4faae1bd6f |  | textbox | Lot Closed Date:
button | 26f077df-075d-56bb-bdfc-20a24d310d52 |  | button | Submitted to Client | Yes, No, N/A
button | 9f667acf-330b-56a1-be68-bc589889226d |  | button | Reviewed by Client | Yes, No, N/A
text | 13491500-b7b2-5809-8dfc-219876f03934 |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | Submission of Management Plan |  |  |  |  | Yes | Submission of Management Plan | 44e131df-390b-4073-a81a-44530ab29b0f
checkpoint-status |  |  | checkpoint | Submission of Management Plan
label | 9151bae5-daf0-5402-9bef-8c4bf483e28c |  | note | Attach Management Plan and any relevant documents, photos, etc.
label | db71e6bb-fdef-5704-bf48-b41a6e458bf0 |  | note | Issue to Client for their approval and sign off
text | be47e92d-1578-5c55-aed5-e275bb529905 |  | textbox | Management Plan:
text | c20c62b5-b2f2-5b31-a1e5-412bab6f85d8 |  | textbox | Specification / Clause Reference (if applicable)
holdpoint |  |  | signoff | Management Plan
checklist-sectioned |  |  | checklist | ITC 03 - B80 Concrete Structures (B80) Rev 1 |  |  |  |  | Yes | ITC 03 - B80 Concrete Structures (B80) Rev 1 | 47c5ebdb-09bb-49d4-86b6-d20f4a576a74
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | e7d66b59-69bd-5fc9-a5fe-b133085aaf1c |  | textbox | Lot Opened On
text | ff2e23b0-1741-52e4-aee6-455d66c6610b |  | textbox | Date of Works
text | 43c5c9f5-2c22-5e07-8763-e3478ab0a3c1 |  | textbox | Lot Type
text | f2028499-00e6-5f45-92d5-f14d961b1199 |  | textbox | Start Chainage
text | 371ca9c2-8bde-5a54-b29d-cba95247f0ce |  | textbox | End Chainage
text | e25563a5-6dd8-4b41-843d-b8bd8e8a04e8 |  | textbox | Offset
text | c1d19be5-5864-5b6f-8159-eded07136416 |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Safety Review
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 673c6cf8-8834-5af3-8315-10bb4ceb8840 |  | note | REQUIREMENTS / REFERENCE - Project Safety Plan
label | b03963fa-c406-5053-80e2-16de3476609c |  | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural).
label | 89117d20-a4ac-516a-8f2b-697bde15ef0a |  | note | Required Safe Work Method Statements completed and signed.
label | c00bbcbd-aee0-5a64-8c35-21fe7326964c |  | note | Comments / Attachments / Records - Subcontractor’s safety plan/procedure approved.
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | d4f31725-c468-5938-bc95-86a1f268c859 |  | note | REQUIREMENTS / REFERENCE - Project Environment Plan
label | ccaa00c9-beeb-5966-8f08-3f3606102103 |  | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | ffb3faa2-babf-53d6-bbad-d1e67619741d |  | note | Air quality to be visually monitored for dust etc as a direct result of construction activities.
checkpoint-group |  |  | section | 3 - Concreting Personnel
checkpoint-status |  |  | checkpoint | HOLD POINT
label | f4e0f334-ed06-52d9-891e-3df388126ceb |  | note | REQUIREMENTS / REFERENCE - B80 Cl 7.2.3
label | fad431ee-56f7-5940-9e78-2eb564fab36d |  | note | ACCEPTANCE CRITERIA - Two weeks prior to first concrete pour, submit names and evidence of personnel holding TfNSW Bridgeworks concreting grey card
text | 4b28d30c-ef4e-5ea4-a901-dccb1f587d6c |  | textbox | HOLD POINT NUMBER:
text | 0fe8940b-042f-5142-b283-e948cb88c90b |  | textbox | DATE SUBMITTED:
text | 067103b0-bee3-5ca7-8a58-c45714dae975 |  | textbox | SUBMITTED BY:
text | 9546e3f6-22f5-5a58-b0e0-998ed835d145 |  | textbox | SPECIFICATION AND CLAUSE:
text | 14b1b9ff-ec76-5f08-a410-fef89d991fd8 |  | textbox | HOLD POINT DESCRIPTION:
text | 4aa455ee-5296-5f7e-afe0-66982228b87f |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 4 - Submission of Mix Design
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 82dce949-cb66-5c38-b290-b8b08a27f5a7 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 3.9
label | 745dfacc-7e2f-584b-abaa-b40b7a5c51d8 |  | note | ACCEPTANCE CRITERIA - Submit to the principal 4 weeks prior to use of any concrete mix all details under Cl 3.9 and the mix ID, if applicable
text | f6110ff1-cbe8-5282-9b21-ae6e20c71464 |  | textbox | HOLD POINT NUMBER:
text | 61e818f9-0c15-5afa-8e88-3abd3dc62139 |  | textbox | DATE SUBMITTED:
text | 31aef8ea-b415-5036-b591-bf6f70fea1dc |  | textbox | SUBMITTED BY:
text | 303533ba-0dd3-5200-a17a-1102128a2b3e |  | textbox | SPECIFICATION AND CLAUSE:
text | fd038f86-cb97-5ca8-9e38-f9bab4973b7d |  | textbox | HOLD POINT DESCRIPTION:
text | ee617af1-f7e5-54a8-9f5b-569c6c4121b6 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Test Members
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 5228ecc8-8a5d-5d5e-b47c-00d4685f726a |  | note | REQUIREMENTS / REFERENCE - B80 Cl 5.3
label | 788b5a76-8a6b-5f9f-9f0d-a49ebdc71d50 |  | note | ACCEPTANCE CRITERIA - Provide notice in writing to the Principal, at least 2 working days, of the upcoming placement of concrete for the test member(s)
text | c02e6251-d574-5670-91ec-ef7ad2103020 |  | textbox | WITNESS POINT NUMBER:
text | 11cbcfcf-fb6c-5d86-a258-a197e702c072 |  | textbox | DATE SUBMITTED:
text | bffd22de-167d-5e0f-8ac2-ca6df149c168 |  | textbox | SUBMITTED BY:
text | 439dd451-8a89-5f21-809e-24d1c0e14478 |  | textbox | SPECIFICATION AND CLAUSE:
text | 27ef1a03-7282-58e4-a248-de8f7be0bfe3 |  | textbox | WITNESS POINT DESCRIPTION:
text | 080a2dd4-71a2-5aaa-96ee-8c681ff12785 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 6 - Formwork Certification
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 4a569ffc-f9a8-57f9-912e-799593259ebb |  | note | REQUIREMENTS / REFERENCE - B80 Cl 5.2.3
label | 11173b65-a800-5580-9ebf-d08164bf2087 |  | note | ACCEPTANCE CRITERIA - Formwork and all temporary supports to be designed and conform to AS 3610.1
label | 303f5297-3baa-52a5-8e2f-54e782f360b9 |  | note | Submit to the principal either 5 or 10 days prior (as per category B and C) formwork documentation and design certification before erection
label | 4eaf1f25-132f-5a0e-bb6d-5edaa762ea32 |  | note | Comments / Attachments / Records - Refer Table B80.11- Submission and Certification requirements for formwork HP at Risk Category B and C.
text | 96cf4908-f927-5dc8-813e-f3ef6e30171e |  | textbox | HOLD POINT NUMBER:
text | dc4867d2-3a8c-52c1-bb8c-f80f7df4701d |  | textbox | DATE SUBMITTED:
text | 94ac1c7d-b709-5758-83fa-0f1edc5673fb |  | textbox | SUBMITTED BY:
text | 401016ad-1ac2-53b2-8ed9-518acc917023 |  | textbox | SPECIFICATION AND CLAUSE:
text | ae5c55bb-ea9f-5dd7-8c0f-d428151c3353 |  | textbox | HOLD POINT DESCRIPTION:
text | 63252f81-cdd3-50cd-9a91-371832019e67 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Prefabricated Cages
checkpoint-status |  |  | checkpoint | WITNESS POINT
label | 3fd9e637-da36-5d70-8525-d239162d6647 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 6.6.2
label | 2c715b47-a1b5-51d7-a15d-c9979b6e9d8b |  | note | ACCEPTANCE CRITERIA - Detail design location of lifting and transport support pins for prefabricated cages
label | 40b80bec-8f1b-5232-9cc6-70568528792e |  | note | Submit to the principal shop drawings of the prefabricated design with certification, at least 2 working days notice of intention to transport
text | 77049eb5-e986-5999-8895-4ae1ab48114e |  | textbox | WITNESS POINT NUMBER:
text | fdf34a70-5997-503c-9456-f3c0f480bb77 |  | textbox | DATE SUBMITTED:
text | 8771da34-41b5-5ce6-a354-dc042a86b320 |  | textbox | SUBMITTED BY:
text | 0d6fdd1e-9ed4-52da-b0fb-933437d9e1ae |  | textbox | SPECIFICATION AND CLAUSE:
text | 8af49849-3515-5226-8b3b-6094f961ab6c |  | textbox | WITNESS POINT DESCRIPTION:
text | 5de22bb7-c43f-5ed6-8bb8-8d525b9623e2 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | WITNESS POINT SIGN OFF
checkpoint-group |  |  | section | 8 - Checklists for Conformity
checkpoint-status |  |  | checkpoint | HOLD POINT
label | dd4b66db-2322-5e2c-ae63-e9747744543d |  | note | REQUIREMENTS / REFERENCE - B80 Cl 7.5.1
label | 3d4bac9f-2eaa-5b09-8c2c-4869e879327e |  | note | ACCEPTANCE CRITERIA - Submit to the Principal the checklists used for verifying conformity of the nominated concrete mix, formwork, reinforcement and embedments for precast concrete members cast off site at least 2 working days prior to commencement.
text | a6fbd43e-f016-51c8-90ae-32319e197e21 |  | textbox | HOLD POINT NUMBER:
text | efa73acd-1c81-56e8-833b-3aa56702146c |  | textbox | DATE SUBMITTED:
text | 70f0a10b-a09e-5ce3-ad5a-a475660f090b |  | textbox | SUBMITTED BY:
text | ae85a546-ee17-512c-a009-297d25a255df |  | textbox | SPECIFICATION AND CLAUSE:
text | fb799235-01c2-5bdb-9d17-a84df65480a2 |  | textbox | HOLD POINT DESCRIPTION:
text | 8c5f37d2-9571-598f-8335-f3ab0531a438 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 9 - Certificate of Conformity
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 96000298-60fe-5b4b-bb44-e4e242f99862 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 7.5.2
label | 63a288a8-69df-5a3f-b0dc-09b977e2d4ea |  | note | ACCEPTANCE CRITERIA - Where concrete is not a precast member cast at an off-site location, submit to the principal, at least 2 working days prior to each concrete placement, Specific Method Statement. And at least 4 working days prior to commencement a Certificate of Conformity of formwork, reinforcement and embedments for the member(s)
text | 11d1676b-b5f6-5254-b3cd-7c688c409c90 |  | textbox | HOLD POINT NUMBER:
text | 444d1256-d246-5292-8a51-cace821697ad |  | textbox | DATE SUBMITTED:
text | bb846d0f-46c6-5f2e-b0f1-c288106bd857 |  | textbox | SUBMITTED BY:
text | 89691d97-05b5-5969-9b9a-83e898ee6a32 |  | textbox | SPECIFICATION AND CLAUSE:
text | 50045255-0773-5eed-8a3d-9e4990564dac |  | textbox | HOLD POINT DESCRIPTION:
text | 46f4a44f-0fc1-57bc-9a19-47da44f99496 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 10 - Supply and Delivery of Concrete
checkpoint-status |  |  | checkpoint | VERIFICATION
label | b417b114-654e-507f-8f8c-94411648b1e4 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 4.1
label | 6fb0ccc9-f2cb-5c4c-9577-ca17a0f40ab9 |  | note | ACCEPTANCE CRITERIA - All concrete to conform to the nominated mixes. All batched to be delivered with details outlines in Cl 4.4.2 Clause 4.4.3 Place and compact all concrete within 1.5 hours of batching Check slump in accordance with AS 1379 Check and record slump when water is added Do not use concrete if less than 10 or more than 32 degrees. Only add water less than 45 minutes since batching Mix water for 3 minutes once added
label | 58726abd-4fa0-5347-80f8-a7385d658866 |  | note | Comments / Attachments / Records - Concrete delivery dockets
checkpoint-group |  |  | section | 11 - Sampling & Testing
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8832669d-d9d0-5cc9-ab01-2c37b1a22542 |  | note | REQUIREMENTS / REFERENCE - B80 L1
label | a5ce14c2-577c-5cb7-9ee7-a02735d7c3ee |  | note | ACCEPTANCE CRITERIA - Slump test to be taken each load
label | e12ce030-2949-50ac-8674-8cad66bebc71 |  | note | Compressive strength cylinders to be taken once every 25m3
label | ef100eb9-13a5-534a-9005-9a51d322f3d3 |  | note | Comments / Attachments / Records - Concrete test results
checkpoint-group |  |  | section | 12 - Formwork Removal
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 7b7dd752-346a-5a9d-a2b7-01d909afc6c3 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 5.9
label | dfea85fa-fe73-5950-b7a2-9cdfb81314d7 |  | note | ACCEPTANCE CRITERIA - Remove formwork in a way and time that achieves specified characteristics and prevents damage
label | b3882cc3-a815-5db7-9fa5-3b5f2ac7e9fa |  | note | Adhere to the minimum stripping times as detailed in CL 5.9.2 and table B80.12
label | 2f00c0ee-406a-52c3-b2a9-11ce298abcc2 |  | note | Comments / Attachments / Records - Survey report for completed works
checkpoint-group |  |  | section | 13 - Concrete Cracking
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 66d3dcc3-b2e8-5198-9e4a-e8c5c922a920 |  | note | REQUIREMENTS / REFERENCE - B80 Cl 9.3
label | 04392d83-010b-551f-b281-7dc24aec2a5a |  | note | ACCEPTANCE CRITERIA - Concrete must have cracks no greater than 0.05mm wide after curing period and 0.1mm after 28 days
label | 90af7ca1-3d1b-574a-9f12-83754ac50020 |  | note | Submit crack map to the principal with proposed remedial actions
checkpoint-group |  |  | section | 14 - Early Trafficking
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 6ae6e8e4-35ab-5470-9627-75e713324fca |  | note | REQUIREMENTS / REFERENCE - B80 Cl 9.9
label | a85533e0-d464-5bda-b0d6-da9b9582127e |  | note | ACCEPTANCE CRITERIA - In the event early trafficking of the bridge deck is requested, at least 2 working days prior to commencement of early trafficking, submit the “strength versus age” relationship of concrete, with supporting test results, and evidence of completion of curing.
label | dd3b4102-2416-5ba3-ae3d-bcf5c3967a01 |  | note | Make good any damage arising from early trafficking of the bridge deck
text | 4676bd85-68f9-59c4-9116-ab7e76edd8f1 |  | textbox | HOLD POINT NUMBER:
text | c44ad129-d27c-57ea-9362-33b6d2a59c32 |  | textbox | DATE SUBMITTED:
text | 038ed12a-ffb7-5b47-8eaf-b864e8a08547 |  | textbox | SUBMITTED BY:
text | cc7b73da-4e53-5e8c-8a3f-c8f23e0e5a13 |  | textbox | SPECIFICATION AND CLAUSE:
text | 21d907af-7473-5e28-b353-9f96762ae98d |  | textbox | HOLD POINT DESCRIPTION:
text | b5180de7-aba8-58dd-9b30-44a66263baf9 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | NCR
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | f8010050-5501-5739-b6bd-7bd6873a9cc8 |  | textbox | Lot Verified By:
text | 912ec9ca-3cec-5fcd-893f-8564616d5701 |  | textbox | Lot Closed Date:
button | 60e2b0c3-3118-59f6-b5da-f334f3758513 |  | button | Submitted to Client | Yes, No, N/A
button | a040dc4d-a575-57d8-8075-a1a5bc2b1d9d |  | button | Reviewed by Client | Yes, No, N/A
text | 12eba556-3b84-55ad-a135-31ed9fc16142 |  | textbox | Submission Comments:
checklist-flat |  |  | checklist | NCR |  |  |  |  | Yes | Add NCR | c8b0fc28-da86-4a8f-978d-255243762067
checkpoint-status |  |  | checkpoint | Non-Conformance Report
label | 576af39a-9a77-5595-91d6-357624bf52fa |  | note | Attach NCR form and any relevant documents, photos, etc.
label | 6d9a7d57-118c-5fa8-9cbd-baf9d0c49a68 |  | note | Issue to Client for their approval and sign off.
text | 9af7224a-640a-5212-8ae6-c64f3f158603 |  | textbox | NCR Number:
text | 214c8fa8-67d6-5607-9421-dee99c156fb1 |  | textbox | Lot Number:
text | 8f7b07b5-a395-5a19-8b75-cd6006bac9b4 |  | textbox | NCR Description:
text | 30278478-8d46-5a4d-be3e-6ec3207e0015 |  | textbox | NCR Resolution:
holdpoint |  |  | signoff | NCR SIGN OFF
checklist-sectioned |  |  | checklist | ITC 01 - G40 Clearing and Grubbing (G40) Rev 1 |  |  |  |  | Yes | ITC 01 - G40 Clearing and Grubbing (G40) Rev 1 | f8c306a6-38cf-4bc3-99d9-5cdcc84b00ce
checkpoint-group |  |  | section | Lot Information
checkpoint-status |  |  | checkpoint | Lot Information complete
text | 6c21dd55-630f-5ce3-a7e8-025bb5b18bd3 |  | textbox | Lot Opened On
text | 635804b9-bf94-527b-93a9-5e640feb02f7 |  | textbox | Date of Works
text | 6b44ae30-2ce8-5c03-9ae6-b5adfb6bbc31 |  | textbox | Lot Type
text | 0fdb06f3-8faf-544c-b3aa-f606cafd813b |  | textbox | Start Chainage
text | 16df3670-7975-55d4-aa55-2f39749a7d90 |  | textbox | End Chainage
text | e7ae9b51-e9e4-4fdb-9091-f5bcd552d388 |  | textbox | Offset
text | de87ad75-b3ce-5e35-82c2-8a4e9e3f672e |  | textbox | Control Line
checkpoint-group |  |  | section | 1 - Safety Review
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 845e01d6-d582-50a8-b13b-fba68bb28c8c |  | note | REQUIREMENTS / REFERENCE - Project Safety Plan
label | fad15500-f847-5fde-9de4-9727e235b3d5 |  | note | ACCEPTANCE CRITERIA - All site personnel inducted (includes environment and cultural)
label | bcfa5377-3066-5bba-92be-b6d6ee03f749 |  | note | Required Safe Work Method Statements completed and signed
label | f2b202cc-d2fb-5524-a26b-4e2db5f050c5 |  | note | Subcontractor’s safety plan/procedure approved
checkpoint-group |  |  | section | 2 - Environment
checkpoint-status |  |  | checkpoint | VERIFICATION
label | c97daabf-4ba3-5b28-bd78-4cedf8846438 |  | note | REQUIREMENTS / REFERENCE - Project Environment Plan G36 CL 3.1 G38, G40
label | 7c987c84-fc1a-560f-be0d-0233cafb8ef2 |  | note | ACCEPTANCE CRITERIA - Installation of soil erosion and sedimentation controls completed in accordance with ESC Plan and EMP, as well as Specification TfNSW G38
label | a7484d08-b912-5ddb-b10a-bed4467d9a83 |  | note | All work undertaken under this Specification must be approved by the Environmental Site Representative (refer TfNSW G36) and comply with Abergeldie’s CEMS and CEMP
checkpoint-group |  |  | section | 3 - Services
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 8faaec68-9a98-5736-9c4d-38ef4945f2a1 |  | note | REQUIREMENTS / REFERENCE - DBYD drawings
label | 3cb9beb3-e470-5080-9465-c4d6bfcc4051 |  | note | ACCEPTANCE CRITERIA - Existing services to be located and relocated or protected prior to Clearing and Grubbing works commencing, where practical to do so
checkpoint-group |  |  | section | 4 - Clearing Approval
checkpoint-status |  |  | checkpoint | HOLD POINT
label | 9e028853-9808-5c1b-b9ab-1f09029b1bed |  | note | REQUIREMENTS / REFERENCE - G40 CL2.4.1
label | 3a9689be-2d21-53ee-95e4-3a15847b0bc6 |  | note | ACCEPTANCE CRITERIA - Prior to undertaking any clearing, prepare a site-specific Clearing and Grubbing Environmental Work Statement to cover the environmental management of works under this Specification (see Annexure G40/D and TfNSW G36 Clause 3.2.4). Include in the Clearing and Grubbing EWMS all the controls required by the Flora and Fauna Management Sub-Plan, Heritage Management Sub-Plans, Noise and Vibration Management Sub-Plans and the Soil and Water Management Plan for the Works. Outline in the EWMS how clearing limits will be progressively maintained and how to ensure that no person, plant, equipment or material goes beyond these limits.
label | 5709fa21-ce53-5157-8cbf-389e23f7e7b8 |  | note | Also provide a report, prepared in consultation with the Ecologist, and to be incorporated into the CEMP, which covers the requirements of Clauses 2.4.1 (a) to (c).
label | 0c591c55-2dea-5709-9345-b3ba1e2bca25 |  | note | Prepare a pre-clearing survey procedure and have the Ecologist undertake a pre-clearing survey to identify and mark any habitat trees within the clearing footprint and advise on the presence of any fauna
label | 93d3b5c5-4013-5c11-a559-f12c6d7a98db |  | note | HOLD POINT – At least seven days prior to starting any clearing, submit Clearing and Grubbing Plan, Environmental Work Method Statement (Annexure G40/D) and report on all locations of environmentally sensitive areas, measures to reduce clearing in environmentally sensitive areas, the presence of weeds and unsound trees, together with written notice that limits of clearing and areas of weed infestation identified in the ecologist report (Clause 2.4(a)) are marked. The Principal will consider the documents and will inspect trees or built structures marked for preservation, including the set out clearing limits, prior to releasing the Hold Point.
text | 3bc5a163-ccd0-5bce-b9e6-3f9e454f3a57 |  | textbox | HOLD POINT NUMBER:
text | 03de8eb8-beed-5b60-9f60-4184185acb54 |  | textbox | DATE SUBMITTED:
text | 39f584d1-7d88-5952-91b6-563a8bfec0a3 |  | textbox | SUBMITTED BY:
text | a699d4a3-bf4f-5666-94f3-a76902be345c |  | textbox | SPECIFICATION AND CLAUSE:
text | 99f2205a-0e26-529f-af04-84bfa76464e2 |  | textbox | HOLD POINT DESCRIPTION:
text | a343289e-f07e-5fcc-bf4d-546abbc4eb36 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 5 - Progress Reports
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 25808153-5470-5516-b6a4-7aab857cd15c |  | note | REQUIREMENTS / REFERENCE - G40 CL 2.6
label | 70e2f30b-1b93-554f-b103-572ee13c5731 |  | note | ACCEPTANCE CRITERIA - Provide to the Principal progressive Clearing Reports providing a summary of the results of surveys, fauna rescues, fauna injury and mortality, at weekly intervals during clearing activities. Include details as per G40 Cl 2.6
label | 4b1afb14-911a-53c8-9e42-d4e598242bd4 |  | note | Provide the Principal with a Post-Completion Clearing Report within 21 days from the completion of substantial clearing (as determined by the Principal) providing a final summary of the progressive Clearing Reports
label | 76d89319-7168-5091-a9a3-70ba49d4b453 |  | note | Progressive Clearing Reports
label | 9ba937e1-bd0a-5848-b475-e2b8d0405517 |  | note | Post-Completion Clearing Report
label | cd2b7b9b-7f5e-5b6f-a299-839de7617f3d |  | note | Comments / Attachments / Records - Progressive Clearing Reports
label | b94d28a3-1d57-5da5-b3eb-204265446664 |  | note | Post-Completion Clearing Report
checkpoint-group |  |  | section | 6 - Weed Management and Implementation
checkpoint-status |  |  | checkpoint | HOLD POINT
label | c6266ca3-605c-51f2-b80b-a3ec21a4f18d |  | note | REQUIREMENTS / REFERENCE - G40 CL 6
label | 392dd1c2-3397-5346-ad5b-699614f9f909 |  | note | ACCEPTANCE CRITERIA - HOLD POINT – At least seven days before starting any clearing, submit to the Principal the Weed and Pathogen Management Sub-Plan together with written notice that areas of weed infestation identified in the Ecologist / Dubbo Regional Council Weeds Inspector’s report (Clause 2.4.1) are marked. The Principal will review the documents and inspect marked weed infestation areas prior to releasing the Hold Point
text | ba06d4a5-a2df-59ae-b480-e67ef4515ce4 |  | textbox | HOLD POINT NUMBER:
text | 4d826675-aef5-5420-bec9-641e86aaf6f4 |  | textbox | DATE SUBMITTED:
text | 9d989655-def6-5dd4-81c0-c5fc34c90695 |  | textbox | SUBMITTED BY:
text | d0254e31-4d23-5887-b3da-71b0900f233b |  | textbox | SPECIFICATION AND CLAUSE:
text | 56007a72-6fb8-5c51-acc9-7e4bf8b78b06 |  | textbox | HOLD POINT DESCRIPTION:
text | 4c308c32-5329-5a55-ac1c-a31bd5627301 |  | textbox | BRIEF NOTES:
holdpoint |  |  | signoff | HOLD POINT SIGN OFF
checkpoint-group |  |  | section | 7 - Post clearing Inspection and Rehabilitation
checkpoint-status |  |  | checkpoint | VERIFICATION
label | 3c594593-ff14-54f3-ad56-dc3df1579b8c |  | note | REQUIREMENTS / REFERENCE - G40 Cl 7
label | 95b93e36-19e8-56f7-bf2e-53a28cd40469 |  | note | ACCEPTANCE CRITERIA - ACPL to walk site after clearing has been completed to identify any further trees / stumps that require removal
label | d3807673-9383-5be0-8a9a-7d6424acf503 |  | note | After the completion of any clearing and/or grubbing ensure that any native vegetation required to be re-established is done in accordance with the TfNSW Biodiversity Guidelines, Guide 3: Re-establishment of native vegetation. Also refer TfNSW R178
checkpoint-group |  |  | section | Identified Records
checkpoint-status |  |  | checkpoint | Please upload any Identified Records here
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | NCR
checkpoint-group |  |  | section | Lot Verification
checkpoint-status |  |  | checkpoint | Lot Verification complete
text | b6fee0a0-0029-5818-9e02-9cb9426f2aee |  | textbox | Lot Verified By:
text | eb28f022-1e7d-5091-a4d1-ed3f36c6f5b8 |  | textbox | Lot Closed Date:
button | 80309eb1-d6fe-5e70-8b8f-ea5f1dbfa4dc |  | button | Submitted to Client | Yes, No, N/A
button | 2f686dab-04a6-548f-81f5-df79c32cea65 |  | button | Reviewed by Client | Yes, No, N/A
text | 3c2d56ec-8c3d-53dc-abb6-0b5e872a0048 |  | textbox | Submission Comments: