## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-164-CIV-PSDS-Embankment Fill | itp |  |  |  |  | ITP-164-CIV-PSDS-Embankment Fill Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-164-CIV-PSDS-Embankment Back Fill
label | ITP Description: Embankment Fill
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 13/05/2024
label | ITP created by: Anthony Pearson
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: IFC Drawings
label | 1.2 Non Dependent
label | Reference: VicRoads Section 173 (Oct 2008)
label | 1.3 Non Dependent
label | Reference: VicRoads Section 204 (Dec 2015)
label | 1.4 Non Dependent
label | Reference: Code of Practice RC500.20, RC500.5
section | Preliminaries-Materials
checkpoint | 2.1 Material Conformance
label | REFERENCE: IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848) Section 204.04 b) Table 204.041
label | ACCEPTANCE CRITERIA: CBR ≥ 8% and Swell ≤ 1.5%
label | ○ Max Permeability = 5E-9 m/s
label | ○ Grading:
label | 75.0mm 100%
label | 4.75mm 40-80%
label | 0.075mm 10-40%
label | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | Reference: TeamBinder Material Approval Ref No.
label | METHOD: Document Review
label | FREQUENCY: Once, for each material type
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries-Documentations
checkpoint | 3.1 Pre-Commencement of Fill Works
label | REFERENCE: Section 204.10 (b)
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | ○ Reference: Subgrade Preparation / Previous Layer Lot Number
label | ○ Attach: Lot Maps
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set Out
label | REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
label | ○ Attach: Lot Maps
label | METHOD: Visual Inspection
label | FREQUENCY: Prior to commencement of fill works
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
section | Type A Fill Activities
checkpoint | 5.1 Placing of Fill
label | REFERENCE: Section 204.10 (d)
label | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | METHOD: Visual Inspection
label | FREQUENCY: Each Lot
label | CATEGORY: WP
label | RESPONSIBILITY: PE/SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
checkpoint | 5.2 Fill at Structures (where applicable)
label | REFERENCE: Section 204.11 (b)
label | ACCEPTANCE CRITERIA: No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
label | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
label | METHOD: Site Inspection
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE/SE/Site Supervisor
label | VERIFYING DOCUMENTS: This ITP Signed Off
checkpoint | 5.3 Test Roll / Proof Roll
label | REFERENCE: Section 173.03, Section 204.12
label | ACCEPTANCE CRITERIA: Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
label | The plant for use in proof roll to comply with the following requirements:
label | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
label | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
label | METHOD: Visual Inspection, Test Roll as per 173.03
label | FREQUENCY: Each Lot/Layer
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: Conqa HP Release
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.4 Compaction and Moisture Content Testing
label | REFERENCE: Table 204.131, Table 204.142 Section 173.04 (d)
label | ACCEPTANCE CRITERIA: Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
label | ○ Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
label | ○ Minimum Testing Frequency: Every second lot
label | Lot size
label | Type A Material - the lesser of one day's production or 5000sqm
label | Or
label | – Testing Small Areas
label | ○ For earthworks and pavement construction any lot which has a surface area less than 500 m2 may be treated as a small area. When testing a small area as a lot and where test requirements are based on characteristic values of density ratio and/or moisture ratio, acceptance of the lot shall be based on the mean values of 3 individual tests. In this case the lot will be accepted as far as compaction is concerned if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
label | ○ Attach: Compaction & Moisture Content Test Results
label | METHOD: Review Document
label | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
checkpoint | 5.5 Post Compaction Material Property Testing
label | REFERENCE: Table 204,041, Table 204.141 Section 204.14 (a)
label | ACCEPTANCE CRITERIA: Material Properties:
label | ○ CBR ≥ 8% and Swell ≤ 1.5%
label | ○ Max Permeability = 5E-9 m/s
label | ○ Grading:
label | 75.0mm 100%
label | 4.75mm 40-80%
label | 0.075mm 10-40%
label | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | ○ Scale B:
label | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | Attach: Post Compaction Material Property Test Results
label | METHOD: Review Document
label | FREQUENCY: Each Lot/Reduced Testing Frequency, Refer to Section 204
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
section | Post-construction Activities
checkpoint | 6.1 Survey Conformance
label | REFERENCE: Table 204.031
label | ACCEPTANCE CRITERIA: Level tolerances (Scale B):
label | ○ Range Mean = +5, -25mm
label | ○ Max Standard Deviation = 15 mm
label | ○ 40 measurements per lot
label | ○ Attach: Survey Conformance Report
label | METHOD: Review Document
label | FREQUENCY: Top of Type A
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE/ Surveyor
label | VERIFYING DOCUMENTS: This ITP Signed Off
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP Signed Off
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP