## Sheet6
type | name | values
checklist | FiberTite warm roof to CLT mechanically fixed and adhered checklist
section | Pre start
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Visual inspection of substrate ready for SWP
checkpoint | QA document received from previous trade from main contractor
section | CLT Substrate
checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
checkpoint | Installation of SA primer
section | Vapor control layer
checkpoint | Substrate clean, dry, free of debris
checkpoint | Z flashing installed
checkpoint | Install VCL over primer
checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint | Installation of SA primer
section | Insulation
checkpoint | VCL clean, dry, free of debris prior to install
checkpoint | VCL has been checked for damages and repaired
checkpoint | Closure flashings installed correctly
checkpoint | Install board adhesive in specified pattern
checkpoint | Specified insulation board installed
checkpoint | Insulation board mechanically fixed with specified fixing pattern
checkpoint | Boards tightly butted
section | Tapered EPS
checkpoint | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
checkpoint | Install board adhesive in specified pattern
checkpoint | EPS board installed into adhesive
section | ILD system installed
checkpoint | ILD System installed as per specs
checkpoint | ILD test plate installed
section | HDP board
checkpoint | PIR clean, dry, free of debris prior to install
checkpoint | Install board adhesive in specified pattern
checkpoint | HDP board installed in brick pattern where possible
section | FiberTite
checkpoint | Prime substrate where required
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean laps prior to welding
checkpoint | Test weld with welding machine
checkpoint | Probe of seam with QA hook
section | Sumps
checkpoint | Sealant installed to dropper flange under membrane
checkpoint | Membrane dressed in to outlets
checkpoint | Clamp/rings/basket installed
checkpoint | Flood test
section | ILD report
checkpoint | ILD report
section | Fiberclad flashing
checkpoint | Installed correctly according to specifications ( right way around )
checkpoint | Fixing and welding done according to specifications and details
checkpoint | Probe of seam with QA hook
section | Pressure bar installed
checkpoint | Installed correctly according to specifications ( right way around )
checkpoint | Fixings done according to specifications and details
checkpoint | Prime of Substrate where required
checkpoint | Sealant installed
section | Over flashings
checkpoint | Over flashings has a separation barrier
checkpoint | Fixings done according to specifications and details
checkpoint | Primer of Substrate
checkpoint | Sealant installed
section | Review and sign off
checkpoint | Area left clean and tidy
checkpoint | All installation work completed, checked and reviewed as per specifications
checkpoint | Client/main contractor sign off
checklist | FiberTite Checklist - Area:
section | Pre Start
checkpoint | Area Accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
checkpoint | Perimeter support installed installed if metal deck substrate
section | Metal Deck
checkpoint | Timber to have separation barrier
checkpoint | Base deck screwed down in every pan
checkpoint | Sheet edges stitched together at 300mm centres
section | Vapour Control Layer
checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint | All areas covered and sheets lapped 50mm
checkpoint | All holes/penetrations patched and water tight
section | Acoustic Board
checkpoint | Is the surface dry
checkpoint | Installed in brick pattern
checkpoint | correct length screw with recessed flat plates
checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
section | Insulation
checkpoint | Surface is dry prior to install
checkpoint | Vapour control layer has been checked for no damage
checkpoint | Insulation board installed in a brick pattern
checkpoint | Joints flush (no gaps between boards on ends)
checkpoint | Fixings at correct spacing according to spec if no Securock in system.
section | HDP Roofboard
checkpoint | Is the surface dry
checkpoint | Installed in brick pattern
checkpoint | correct length screw with recessed flat plates
checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
section | FiberTite
checkpoint | Test weld with welding machine
checkpoint | Adhesive installed to substrate
checkpoint | Laying of membrane into the adhesive
checkpoint | Broom/rolling of membrane
checkpoint | Wipe and clean of laps prior to welding
checkpoint | Probe of seams with QA hook
checkpoint | Clamp and weld of outlets and overflows
checkpoint | Flood test of outlets
section | Fiberclad flashings
checkpoint | Installed correctly according to specifications (Right way around)
checkpoint | Fixings and welding done according to specifications and details
checkpoint | Probe of weld with QA hook
section | Sign Offs
checkpoint | Area Complete (Request MC Signoff)
signoff | Request Sign Off
checklist | Carpark MMA Checklist
section | Pre Start
checkpoint | SSSP onsite
checkpoint | Photos of any existing line markings installed
checkpoint | Fencing demarcation installed
checkpoint | Site signage installed
checkpoint | Area Accessible
checkpoint | Substrate complete and ready for SWP
section | Surface Prep
checkpoint | Removal of coatings
checkpoint | Grind of substrate
checkpoint | Shotblast of substrate to achieve suitable profile
section | Pre-start of membrane install
checkpoint | Substrate dry
section | Membrane install
checkpoint | Prime of substrate
checkpoint | Stripe out cracks
checkpoint | Map out areas based on coverage rates for install
checkpoint | Membrane layer installed
checkpoint | Wear layer installed and broadcast
checkpoint | Excess broadcast swept and removed
checkpoint | 1st Top coat
checkpoint | 2nd top coat
checkpoint | Line Marking installed
checkpoint | Site cleared and broken down
checkpoint | Site cleared and broken down
checklist | Fiberglass System Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready for SWP
section | Surface Prep
checkpoint | Concrete free of contaminants
checkpoint | Concrete flat and smooth
checkpoint | Bug holes in plinths filled and smooth
checkpoint | All 90 deg corners chamfered
section | Membrane install
checkpoint | Install sealant angle fillets to all wall floor junctions
checkpoint | Prime surfaces with Epistixx
checkpoint | 1st body coat with 300 gram fiberglass installed
checkpoint | 2nd body coat
checkpoint | 3rd body coat
checkpoint | Traxx 2000 wear coat.
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | Weather Monitoring
section | Current Weather
checkpoint | Today's date & Time
checkpoint | Wind / weather conditions
checkpoint | Record any delays
checkpoint | area / gridlines
checkpoint | Comments / issues / observations
section | Weather Forecast
checkpoint | What is the weather forecast this week
checkpoint | Record any delays
checkpoint | area / gridlines
checkpoint | Comments / issues / observations
checklist | Fibertherm Checklist
section | Prestart
checkpoint | Area accessible
checkpoint | Edge protection and safety installed
checkpoint | Substrate complete and ready for SWP
section | Metal Deck
checkpoint | Timber to have separation
checkpoint | End openings to have closure foam installed
checkpoint | Base deck screwed down in every pan
checkpoint | VCL tape to be installed to all sheet laps
checkpoint | VCL tape to all upstands
section | Post and Rail install
checkpoint | Post installed at correct fixing centers
checkpoint | Thermal break pad under post foot
checkpoint | Rail installed to posts
checkpoint | Gutter line closure/drip edge flashing installed
section | Insulation install
checkpoint | Specified Insulation installed
checkpoint | No Gaps
section | Top Deck install
checkpoint | Lay sheets straight
checkpoint | Hang over into gutter min 75mm
checkpoint | Top end of sheets turned up
checkpoint | Bottom end of sheets turned down
checkpoint | Fixing back to rail
checkpoint | Profile washers
checkpoint | Screwed off as per fixing plan
section | Flashing install
checkpoint | Installed correctly, according to specs & drawings
checkpoint | Fixings according to specs & details
section | Review and Sign Off
checkpoint | Area left clean and tidy
checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint | Client / Main Contractor sign off
checklist | Variation Details -
checkpoint | Variation Details Approved
textbox | Reference/Drawing/Instruction Number
textbox | Variation Area
textbox | Materials & labour breakdown
signoff | Request Variation Acknowledgement
checkpoint | Variation Completed
signoff | Request Variation Signoff
checklist | Flood Test Area:
checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint | Flood test details
textbox | Date:
textbox | Area tested:
textbox | Duration:
button | Have you checked regularly for leaks | Yes, No, N/A
button | Is there rain in the forecast | Yes, No, N/A
button | Have you left some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | Have all leaks been repaired | Yes, No, N/A
checkpoint | Flood test complete
button | Have the plugs been removed from the drains | Yes, No, N/A
button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
signoff | Sign Off