## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP L8P2 | itp |  |  |  |  | ITP L8P2
section | Details
checkpoint-no-status | Details
label | BUILDER: LendLease
label | PROJECT NO: J0805
label | DOC NO: QA Rev 2
label | PROJECT: One Circular Quay
label | DESCRIPTION: Concrete Supply and Place
label | AUSTRALIAN STANDARDS: AS3600 / AS1379 / AS1012
label | SITE STRUC. SPECS: 18295-RBG-ZZ-XX-SP-ST-00001[01]
label | LOCATION: As per attached markup drawings
date | DATE CONCRETED:
label | SPECIFIED MIX (MPa):
textbox | SLAB:
textbox | WALLS:
textbox | COLUMNS:
dropdown | PLACEMENT METHOD: | PUMP,TRUCK,KIBBLE,OTHER
textbox | OTHER:
label | DMG SUPERVISOR:
label | CONCRETE POURED (Element / Volume / MPa):
label | (TA) 80MPa - 3m3- Level 8 Pour 2 L7-L8 Columns
label | (TA) 65MPa - 7m3- Level 8 Pour 2 L7-L8 Wall & slab puddling
label | (TA) 50MPa - 15m3- Level 8 Pour 2 L7-L8 Wall
label | (TA) 40MPa - 57m3- Level 8 Pour 2 slab
textbox | WEATHER:
number | TOTAL m3: |  |  | m3
textbox | TIME START:
textbox | TIME FINISH:
section | PRE-POUR ITP INSPECTION
checkpoint | 1 - Determine equipment requirements: Pumps & Delivery lines, Placing tools, Finishing Machines
label | Acceptance Criteria:
textbox | INITIALS:
date | DATE:
label | REVIEW: W = Witness
checkpoint | 2 - Main Slab RL
textbox | Acceptance Criteria: Drawing No.
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 3 - Ensure Pre-pour inspection complete and signed
button | Acceptance Criteria: | Yes,No
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 4 - Check cleanliness of slab /formed walls & columns - clear of debris
label | Acceptance Criteria: Visual
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 5 - Received formwork Certificate
button | Acceptance Criteria: | Yes,No
textbox | INITIALS:
date | DATE:
label | REVIEW: H = Hold
holdpoint | HOLD POINT
checkpoint | 6 - Specific slab finish requirement steel trowel
textbox | Acceptance Criteria: Drawing No.
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 7 - Check concrete mix Required? Y/N
label | Acceptance Criteria: Use approved mix design.
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 8 - Check concrete mix design and strengths
label | Acceptance Criteria: Mix designs to meet the requirements of AS 1379 as specified in the approved Boral Mix Design Submission. In accordance with RBG concrete supply specification.
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 9 - Concrete adequately vibrated
label | Acceptance Criteria: Visual
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 10 - Concrete tester in place (Testing as per Engineer Specification)
label | Acceptance Criteria: Compressive strength testing as per AS1012. In accordance with RBG concrete testing specification.
textbox | INITIALS:
date | DATE:
label | REVIEW: W
section | POST-POUR ITP INSPECTION
checkpoint | 1 - Application of curing agents
label | Acceptance Criteria: Masterkure250 – conforms to AS 3799 & in accordance with RBG Concrete Place & Finishing Specification
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 2 - Post pour inspection – check slab finish/quality – clean up
label | Acceptance Criteria: Visual
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | 3 - Pre-Stress As Built Survey – complete and submit to Lendlease at earliest opportunity
label | Acceptance Criteria: Visual
textbox | INITIALS:
date | DATE:
label | REVIEW: W
checkpoint | Final Acceptance
textbox | Organisation:
textbox | Name:
date | Date:
holdpoint | Signature