## ITP Cover Page
Northern Access Road & Carpark - Waste water Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210-SP2 - 030-002-001 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 030-002-001
Project Number: |  |  | DN1210-SP2 |  |  |  |  | ITP Status: |  |  | Draft
ITP Description: |  |  | Wastewater Pressure testing |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-WST(01/03/010/112/203/209/320/321/322/324/324/328)
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Section 22.1 to Section 22.13
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
[10 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) (Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point) |  | PE/SE | QA Manager / Rep
[10 empty] | I | Inspection (Formal inspection activity to be undertaken and recorded) |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point (Review of text reports/records or other evidence of compliance) |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS | [5 empty] | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN | [5 empty] | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)
Note on P8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Your CWP document number and the ITP number doesn't match. Please correct this. Reply: I changed both to 021-003-001 good spotting

## ITP Master Body
Northern Access Road & Carpark Wastewater
Tauriko Enabling Works
DN1210 - SP2- ITP011-002 - REV 0
Item No. | Inspection and Test Point | Detail / Activity | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | ConQA Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION - MATERIAL , PERSONNEL & THIRD PARTY APPROVALS (P&G / ESTABLISHMENT)
3.1 | Work method statement | Provide the Engineer with a detailed work method statement (WMS) with details of how the pressure testing will be carried out at least 10 Working Days prior to the test | WSP sign off | PS: 22.7.12 d) | Ineight approval | Pre aproval | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.2 | Witnessing of Pressure Testing | Pressure testing will be carried out at least 10 Working Days prior to the test | On site | PS: 22.7.12 b) | Email | All Testing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 4 – CONSTRUCTION ACTIVITY - WASTEWATER PIPELINE TESTING
4.1 | Pressure Acceptance Testing | Backfill/cover with embedment before testing. Complete pressure acceptance template. End caps in place, provision for filling the pipeline and bleeding air. | Wastewater Rising Main Pipelines – 800kPa Ensure the STP is not more than 25% above the rated pressure of any pipeline component. Complete pressure acceptance template. | PS 22.7.12 d) PS 22.7.13 b) Appendix XXI | Test Report Pressure Log in.csv or .xlsx format | All Pipeline All valves | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG