## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
Project Name: | SH58 Safety Improvements, Stage 2B | [5 empty] | Inspection Key |  | Responsibilities
Project Number: | TBC | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi (NZTA) | [5 empty] | B | Report by Breach | CM | Construction Manager | Jamie Nisbet. | JN
Contract Number: | TBC | [5 empty] | C | Check | ER | Engineers Representative (Assisstant)
Area/ Sub-System: | Reinforced Concrete - In-Situ |  |  | Lot ID Number: | TBC |  | D | Dimension Inspection | IP | Inspection Personnel | N/A | N/A
[7 empty] | E | Examine | MC | Material Controller | N/A | N/A
ITP Number: | DS2681-SH58-ITP-001 |  |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager | N/A | N/A
ITP Description: | Pautahunui Bridge 7 - Substructure works. | [5 empty] | I | Inspection | PM | Project Manager | Gordon Lemon | GL
Discipline: | Infrastructure (Substructures) | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | SH58 Safety Improvements, Stage 2B – Harris Road to East of Moonshine Road including additions for Flighys Road to Transmission Gully Contract No. 7269 | [5 empty] | O | Operation | QA | Quality Advisor | Lissa Gatehouse | LG
[7 empty] | R | Review | QM | QA Manager
Drawings: | 80510096-02B-330 Series. | [5 empty] | S | Subcontractor | SP | Supervisor
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Falakiko Veatupu |  |  | Date: | 2023-04-29 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [6 empty] | T | Field Testing | WS | Welding Supervisor | tbc | tbc
SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2024-08-01
Downer Approval |  | Name: | Diliban Sengottian |  |  | Signature: |  |  |  |  | Date: | 2024-08-01
Customer Approval |  | Name: | Purvik Patel |  |  | Signature: |  |  |  |  | Date:

## In Process Inspections
SECTION 2 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
2.01 | Reinforcing & Formwork - Cover | Reinforcing cover to formwork | PS Cl. 24.1.13 Table 20.2.2 |  | Pre-Pour Inspection | Per Pour | Documentation | H | ER
2.02 | Reinforcing & Formwork - Reo placement and bar bending | Reo placement and bar bending | Ensure reinforcing bends comform to NZ standards and project specifications | Bars shall be cut and bent in accordance with NZS 3109 to the shapes indictated in the drawings and placed correctly in the arrangement shown; Unless noted on drawings reinforcing bars to be bent to min bend diameters outlined in NZS3101; Heat bending of bars is prohibited | Pre-Pour Inspection Bar bending schedule | Per Pour | Documentation | H | ER
2.03 | Reinforcing & Formwork - Formwork | Formwork | AS/NZS 4671: 2001, 'NZS 3109 PS Cl. 24.1.16 | Formwork to be constructed so that finished concrete will be to the shape, lines and levels shown on the drawings; All forms shall be designed such that exposed concrete edges have a min 20mm chamfer unless otherwise indicated on the drawing; Interior surfaces of the forms shall be treated with a release agent. Any reinforcement in contact with the release agent shall be cleaned thoroughly; Forms to be sufficiently watertight to prevent grout loss | Pre-Pour Inspection | Per Pour | Documentation | H | ER
2.04 | Formwork and Pour - Finishes | Formwork and Pour | PS Cl. 24.1.16 |  | Photo & Pre-pour Inspection | Per Visible Surface | Documentation | W | SE
2.05 | Concrete Pour | Concrete Placement | AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing | Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer. Concreting to be a continous operation between ends of members and/or properly formed construction joints. Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m. | Pre-Pour Inspection | Per Pour | Documentation | W | SE
2.06 | Concrete Pour | Concrete Test Cylinders | PS Cl.24.1.14 | A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days. Strength of concrete = Dependent on Mix Design. | Lab Report | Per batch | Report | W | SE
2.07 | Concrete Pour | Approved Concrete Mix Design | PS Cl 24.1.3 | Confirm correct mix design brought to site Concrete Docket Showing: • Mix Design Item Code • 28 day specified strength = 45MPa • concrete placement method that the mix was designed for - Pump Mix • type of supplementary cementitious materials (if used); • slump (target and actual slump when measured); • Order and Delivery Quantity • Load Time out of plant • To site time • Unload Time • Associated Products e.g. cement and additives | Concrete Docket | Each truckload | Documentation | W | SE
2.08 | Concrete Pour | Slump Test | PS Table 9.1 | Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm. Slump test tolerances: | Visual/Photos | Each truckload | Test | W | SE
2.08 | Concrete Pour | Time Limits | PS Cl 24.1.17 | Incorporated in the works within 90minutes of batching. Incorporated in the works within 30minutes of discharge from concrete truck/agitator | Dockets & pour sheet | Each truckload | Dockets | W | SE
2.09 | Concrete Pour | Concrete Vibration | Clause 7.6 of NZS 3109 | All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: - All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured. | Visual/Photos | Per Pour | Visual | W | SE
2.1 | Post Concrete Works | Curing | AS/NZS 4671: 2001, 'NZS 3109 | Concrete to be cured for min 3 days; | Pre-Pour Inspection | Per Pour | Documentation | W | SE

## Final Inspection and Handover
SECTION 3 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
3.1 | Survey As-built | Survey as-built | Specification Cl 26.4 & AS2159 (Page 167) | As-built survey CAD File | As-built survey CAD File |  | Documentation | C | SE/ER/SV
SECTION 6 – COMMENTS
Customer Release Granted: ☐ Yes ☐ No |  |  |  | Comments
Certificate Number: |  |  | Date: