## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | MRAB and FRAB |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-002 Earthworks Cut |  |  | Version: | A |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Bulk Earthworks | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Nick Talbot | NT
[7 empty] | R | Review | SPE | Senior Project Engineer | Henry Cheung | HC
Drawings: | 80510096-02B-100-C102 Rev1, 80510096-02B-100-C106 Rev1, 80510096-02B-100-C132 Rev1 and 80510096-02B-100-C331 Rev1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyler Collinson | TC
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) |  |  |  | Date: | 2025-07-09 |  | W | Witness Point
Quality Specified: | Section 15 of Project Specification and TNZ F/1
SECTION 2 – SIGNATURES – APPROVALS
Construction Manager Approval |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-07-10
Project Manager Approval |  | Name: | Gordon Lemon |  |  | Signature: |  |  |  |  | Date:
QA Doc Controller Approval |  | Name: | Lissa Gatehouse |  |  | Signature: |  |  |  |  | Date:
Customer Approval (if required) |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add full doc number DS2681-SH58-ITP-002

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification Clause | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[8 empty] | Key | By (Role Key)
3.1 | Pre-Construction Survey | Specification Cl.2.11.2, Cl.15.6.6 | Drone/GPS | Receipt of survey by engineer | Topo Survey | Prior to works - each lot | Witness | W | SPE & SV

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to Project Spec.
Item No. | Activity/ Task Description | Specification Clause | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[8 empty] | Key | By (Role Key)
4.1 | Topsoil Depth Checks | Project Spec Cl.15.3.4 | Nominal depth checks at 100m intervals longitudinally and 50m interval transverse | Photos with tape measure to show depth of topsoil layer. Date and location to be recorded | Site Photos, Record Sheet | 100m intervals longitudinally and 50m intervals transverse to earthworks | Witness | W | SE
4.2 | Hazardous & Classified Soils | Project Spec Cl.15.3.3 & 15.3.5 | Hazardous waste and contamined soils encountered during the excavation process | Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered | Visual, Site Photos | Continuous | Witness | W | SE
Cut
4.3 | Final Cut Observation Monitoring | Project Spec Cl.15.6.6 | Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed | Agreement with Engineer's Rep | As Required by Stantec Representative QC-01 Earthworks Checksheet | As requested by engineer | Hold | H | ER
4.4 | Cut Batter Tolerances | Project Spec Cl.15.6.7 | Post-construction - Excavation of batters complying with design issued and within tolerance | Slope Tolerance 1H:1V or Flatter: +300 / -300 mm Steeper than 1H:1V: +300 / -600mm | As-Built and DN-QUA-QC-01 Earthworks Checksheet | Continuous | Witness | W | SE/SV
4.5 | Site Fill Material - Segregation of Material Type | Project Spec Cl.15.6.8 | Moisture sensitive material stockpiled | Drainage blanket (polythene cover) if any material is stored on site to avoid saturation | Visual, Site Photos | Continuous | Witness | W | SE
Cut-face tolrence
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added inspection sign/date etc
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Geotech engineer not listed in role key Reply: Geotech note removed. Stantec Rep is ok as it id for them to decide who does it.

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification Clause | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[8 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location/ Hold Points
SECTION 6 – COMMENTS
|  |  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number:
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added inspection sign/date etc