## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 RC In-Situ | itp |  |  |  |  | ITP-001 RC In-Situ
section | SECTION 2 – IN-PROCESS INSPECTIONS
checkpoint | 2.01 - Reinforcing & Formwork - Cover
label | Inspection Point: Quality Control Activity - Reinforcing cover to formwork
label | Specification Reference - PS Cl. 24.1.13 Table 20.2.2
label | Acceptance Criteria - TABLE 20.2.2: CONCRETE EXPOSURE CLASSIFICATION — MINIMUM COVER FOR 100 YEAR DESIGN LIFE
label | — — — — — — — — — — —
label | Exposure Classification ¦¦ Specified Compressive Strength (f'c) — 30 MPa, 40 MPa, 50 MPa
label | — — — — — — — — — — —
label | A2 ¦¦ 40mm, 35mm, 35mm
label | B1 ¦¦ 50mm, 40mm, 35mm
label | B2 ¦¦ 65mm, 50mm, 40mm
label | — — — — — — — — — — —
label | Verifying Document - Pre-Pour Inspection
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Reinforcing & Formwork - Reo placement and bar bending
label | Inspection Point: Quality Control Activity - Reo placement and bar bending
label | Specification Reference - Ensure reinforcing bends comform to NZ standards and project specifications
label | Acceptance Criteria - Bars shall be cut and bent in accordance with NZS 3109 to the shapes indictated in the drawings and placed correctly in the arrangement shown;
label | ○ Unless noted on drawings reinforcing bars to be bent to min bend diameters outlined in NZS3101;
label | ○ Heat bending of bars is prohibited
label | Verifying Document - Pre-Pour Inspection, Bar bending schedule
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Reinforcing & Formwork - Formwork
label | Inspection Point: Quality Control Activity - Formwork
label | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, PS Cl. 24.1.16
label | Acceptance Criteria - Formwork to be constructed so that finished concrete will be to the shape, lines and levels shown on the drawings;
label | ○ All forms shall be designed such that exposed concrete edges have a min 20mm chamfer unless otherwise indicated on the drawing;
label | ○ Interior surfaces of the forms shall be treated with a release agent. Any reinforcement in contact with the release agent shall be cleaned thoroughly;
label | ○ Forms to be sufficiently watertight to prevent grout loss
label | Verifying Document - Pre-Pour Inspection
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Formwork and Pour - Finishes
label | Inspection Point: Quality Control Activity - Formwork and Pour
label | Specification Reference - PS Cl. 24.1.16
label | Acceptance Criteria -
label | Verifying Document - Photo & Pre-pour Inspection
label | Frequency - Per Visible Surface
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.05 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete Placement
label | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing
label | Acceptance Criteria - Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer.
label | ○ Concreting to be a continous operation between ends of members and/or properly formed construction joints.
label | ○ Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m.
label | Verifying Document - Pre-Pour Inspection
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.06 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete Test Cylinders
label | Specification Reference - PS Cl.24.1.14
label | Acceptance Criteria - A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days.
label | ○ Strength of concrete = Dependent on Mix Design.
label | Verifying Document - Lab Report
label | Frequency - Per batch
label | Inspection Type (Visual, other) - Report
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.07 - Concrete Pour
label | Inspection Point: Quality Control Activity - Approved Concrete Mix Design
label | Specification Reference - PS Cl 24.1.3
label | Acceptance Criteria - Confirm correct mix design brought to site
label | Concrete Docket Showing:
label | ○ Mix Design Item Code
label | ○ 28 day specified strength = 45MPa
label | ○ Concrete placement method that the mix was designed for - Pump Mix
label | ○ Type of supplementary cementitious materials (if used);
label | ○ Slump (target and actual slump when measured);
label | ○ Order and Delivery Quantity
label | ○ Load Time out of plant
label | ○ To site time
label | ○ Unload Time
label | ○ Associated Products e.g. cement and additives
label | Verifying Document - Concrete Docket
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.08 - Concrete Pour (1)
label | Inspection Point: Quality Control Activity - Slump Test
label | Specification Reference - PS Table 9.1
label | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm.
label | Slump test tolerances:
label | — — — — — — — — — — —
label | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
label | — — — — — — — — — — —
label | 60 or less ¦¦ ±20
label | 70 - 110 ¦¦ ±30
label | Greater than 110 ¦¦ ±40
label | — — — — — — — — — — —
label | Verifying Document - Visual/Photos
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Test
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.08 - Concrete Pour (2)
label | Inspection Point: Quality Control Activity - Time Limits
label | Specification Reference - PS Cl 24.1.17
label | Acceptance Criteria - Incorporated in the works within 90minutes of batching.
label | ○ Incorporated in the works within 30minutes of discharge from concrete truck/agitator
label | Verifying Document - Dockets & pour sheet
label | Frequency - Each truckload
label | Inspection Type (Visual, other) - Dockets
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.09 - Concrete Pour
label | Inspection Point: Quality Control Activity - Concrete Vibration
label | Specification Reference - Clause 7.6 of NZS 3109
label | Acceptance Criteria - All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: -
label | ○ All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured.
label | Verifying Document - Visual/Photos
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 2.10 - Post Concrete Works
label | Inspection Point: Quality Control Activity - Curing
label | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109
label | Acceptance Criteria - Concrete to be cured for min 3 days;
label | Verifying Document - Pre-Pour Inspection
label | Frequency - Per Pour
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
section | SECTION 3 – FINAL INSPECTION AND HANDOVER
checkpoint | 3.1 - Survey As-built
label | Inspection Point: Quality Control Activity - Survey as-built
label | Specification Reference - Specification Cl 26.4 & AS2159 (Page 167)
label | Acceptance Criteria - As-built survey CAD File
label | Verifying Document - As-built survey CAD File
label | Inspection Type (Visual, other) - Documentation
label | Inspection: Key - C
label | Inspection: By (Role Key) - SE/ER/SV
checkpoint | Inspection Point/ Signature & Date
date | Date:
textbox | Customer Requirements Verification Record / Location/ Hold Points
signoff | Downer Signature
checklist | ITP-002 Earthworks Cut | itp |  |  |  |  | ITP-002 Earthworks Cut
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Pre-Construction Survey
label | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
label | Specification Reference - Drone/GPS
label | Acceptance Criteria - Receipt of survey by engineer
label | Verifying Document - Topo Survey
label | Frequency - Prior to works - each lot
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SPE & SV
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Topsoil Depth Checks
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
label | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
label | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
label | Verifying Document - Site Photos, Record Sheet
label | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Hazardous & Classified Soils
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
label | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
label | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
label | Verifying Document - Visual, Site Photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.3 - Final Cut Observation Monitoring
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.6
label | Specification Reference - Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed
label | Acceptance Criteria - Agreement with Engineer's Rep
label | Verifying Document - As Required by Stantec Representative, QC-01 Earthworks Checksheet
label | Frequency - As requested by engineer
label | Inspection Type (Visual, other) - Hold
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Cut Batter Tolerances
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.7
label | Specification Reference - Post-construction - Excavation of batters complying with design issued and within tolerance
label | Acceptance Criteria - Slope Tolerance 1H:1V or Flatter: +300 / -300 mm
label | ○ Steeper than 1H:1V: +300 / -600mm
label | Verifying Document - As-Built and DN-QUA-QC-01 Earthworks Checksheet
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE/SV
checkpoint | 4.5 - Site Fill Material - Segregation of Material Type
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.8
label | Specification Reference - Moisture sensitive material stockpiled
label | Acceptance Criteria - Drainage blanket (polythene cover) if any material is stored on site to avoid saturation
label | Verifying Document - Visual, Site Photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | Inspection Point/ Signature & Date
date | Date:
textbox | Customer Requirements Verification Record / Location/ Hold Points
signoff | Downer Signature
checklist | ITP-003 Earthworks Fill | itp |  |  |  |  | ITP-003 Earthworks Fill
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Pre-Construction Survey
label | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
label | Specification Reference - Drone/GPS
label | Acceptance Criteria - Receipt of survey by engineer
label | Verifying Document - Topo Survey
label | Frequency - Prior to works - each lot
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SPE & SV
checkpoint | 3.2 - Use of Flighty's Mound material for fill
label | Inspection Point: Quality Control Activity - N/A
label | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
label | Acceptance Criteria - Confirmation of use
label | Verifying Document - Mail Confirmation from Stantec Representative
label | Frequency - Start of Earthowrks
label | Inspection Type (Visual, other) - Hold Point (where required)
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
label | Inspection Point: Quality Control Activity - N/A
label | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
label | Acceptance Criteria - Confirmation of use
label | Verifying Document - Mail Confirmation from Stantec Representative
label | Frequency - Start of Earthowrks
label | Inspection Type (Visual, other) - Hold Point (where required)
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - AP65 Material acceptance
label | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
label | Specification Reference - Material Testing and Compliance
label | Acceptance Criteria - IANZ Testing
label | Verifying Document - Testing report
label | Frequency - Every 1000m3 or change in material source
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Topsoil Depth Checks
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
label | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
label | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
label | Verifying Document - Site Photos, Record Sheet
label | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Hazardous & Classified Soils
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
label | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
label | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
label | Verifying Document - Visual, Site Photos
label | Frequency - Continuous
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.3 - Subgrade testing - Trim and Compact
label | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.10
label | Specification Reference - Trimming & Compaction of in-situ subgrade. Conduct plateau test.
label | Acceptance Criteria - N/A
label | Verifying Document - Plateau worksheet
label | Frequency - Full surface
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.4 - Subgrade testing - Scala
label | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.11
label | Specification Reference - Scala Testing
label | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
label | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
label | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.5 - Subgrade testing - Benkelman Beam
label | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.12
label | Specification Reference - Benkelman Beam Testing
label | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
label | Verifying Document - Lab report
label | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.6 - Subgrade testing - Proof Roll
label | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.13
label | Specification Reference - Proof Roll
label | Acceptance Criteria - As instructed by the Engineer
label | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
label | Frequency - Proof Roll: Full surface using suitable plant
label | Inspection Type (Visual, other) - Hold
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Fill Compaction Trial
label | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
label | Specification Reference - On-site Testing - NDM, Visual, Shear Vane
label | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
label | Verifying Document - NDM Worksheet, Shear Vane Worksheet, Plateau Density Sheet
label | Frequency - When a new type of fill material is used
label | Inspection Type (Visual, other) - Hold
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.8 - Fill Backfill layer thickness
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
label | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
label | Acceptance Criteria - Fill placement not exceeding 230mm
label | Verifying Document - Visual, Site Photos and NDM check sheets, DN-QUA-QC-09 NDM Worksheet
label | Frequency - Every layer
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.9 - Fill Compaction Testing Laboratory
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
label | Specification Reference - Water Content, Standard Proctor and Wet Sieve.
label | Acceptance Criteria - N/A
label | Verifying Document - IANZ report
label | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day, MDD & WS - 1 test per 2000m3
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.10 - Fill Compaction Testing Site
label | Specification Reference - Compaction test by plateau
label | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
label | Verifying Document - DNZ Plateau Test work sheet
label | Frequency - Daily
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.11 - Fill Compaction Testing Site
label | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
label | Specification Reference - NDM and OMC testing of fill material, Shear Vane
label | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC
label | ○ Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95%
label | ○ Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
label | Verifying Document - NDM Record Sheet, DN-QUA-QC-09 NDM Worksheet, Shear Vane Sheet (Cohesive soil only)
label | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day
label | ○ Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.12 - Fill Tolerances
label | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
label | Specification Reference - Survey of finished surface
label | Acceptance Criteria - Tolerance of +-50mm
label | Verifying Document - As-built
label | Frequency - At Completion
label | Inspection Type (Visual, other) - Witness
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE/SV
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | Inspection Point/ Signature & Date
date | Date:
textbox | Customer Requirements Verification Record / Location/ Hold Points
signoff | Downer Signature