## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6a6772fe-ffae-453c-b16c-96fe7304e834 | checklist | Precast Beams |  | Precast Beams
ef9b77a6-f820-4e6f-9467-afb75a0d4ea3 | section | Pre-Pour Checklist
67684c49-8848-4439-8307-cfffe9ca306c | checkpoint | Pre-Pour Checklist completed
f16313bc-a09d-5fe9-89d2-5d1b19fdf29e | textbox | Cast Number
94ca6869-886b-515d-a6e5-deae740d1f92 | textbox | Precast Beam 1
08827d85-409c-51ea-894f-b515f6bc19ef | textbox | Precast Beam 2
e18810b6-4250-44fc-86ce-6ec7825cadef | checkpoint | Shop Drawings approved for Works
a07d80dc-ef0b-4c3f-9880-6dacde69e76f | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
6e4072f2-843a-52eb-bfcc-849acb3c3399 | note | Length
083fbea6-5b6d-581b-9cde-219c1656e9c1 | note | Width
802edc77-2aa8-5d3c-8bab-214e11452598 | note | Height
dc8665ee-02d0-5673-8b77-9836715a2c69 | note | Straightness
0e0e536a-2bad-505f-97ce-583074b7dfae | note | Cross-section
617db944-2845-4865-9d8a-651a165741bf | checkpoint | Mould Surface Checked
9badfcd3-47b4-5f1f-a29a-4f94c741333f | note | Cleaned
a93da351-87ea-575f-8f2d-d3ffe23df0ed | note | Sealed
06652008-1fbf-5c00-b922-821d93b23c35 | note | Rubbers in Place
8772ddb9-2ba6-5d4f-9aaa-c50fec895c1e | note | Oiled
9a018964-fa6c-5eca-b3c6-562663468392 | note | Chamfers in Place
d45e026f-e109-48ec-9912-89d1c423e729 | checkpoint | Duct tub installation
f7d7119f-fb5a-53fc-b1f9-b70da0829e3d | note | Duct positions verified against drawings
ed578430-2702-5b86-b479-936e69501ff1 | note | Stiffener pipes greased, installed and positions verified
1e85232b-c07f-5ef5-93f8-70390e182fc1 | note | Allowable tolerance +/- 3mm individual ducts, +/- 6mm as a group
097e2447-e90b-4985-a9b6-b0a3f8c27244 | checkpoint | VSL Cast-in anchors
fa5b8f76-2913-5e90-ad55-6ac2374dc775 | note | VSL bar positions verified against drawings
428cf8ea-6409-5717-ba1c-ad60eabff7e9 | note | VSL bar no tilting observed
f3e823b7-cd8f-55f7-8475-bdb306141aba | note | Recess for VSL sleeve created
a3da7b4d-670f-5a57-b5c3-97907a9baea4 | note | Allowabe tolerance +/- 3mm
0fe15766-4938-41da-80e8-1bc8103c360c | checkpoint | Reinforcement in Accordance with Drawings
f7b5a390-f920-5cda-8b07-61dd76033864 | note | Reinforcement size
21f66887-ad1f-5b8a-b0e1-f77564530a9f | note | Lap Length
cb26c8c3-cedb-5c44-a37e-5386a67d7139 | note | Splicing
d74536e7-2468-5132-ac9a-0d64e48aa4d1 | note | Bar Chairs
9a083739-04cc-4eaa-8267-0db7e3a3b376 | checkpoint | Cover maintained and within tolerance
1b489e73-fbe3-486b-8974-91ebf5b9593f | checkpoint | Formwork Ferrules Installed
c308b2e7-0a86-5c30-b011-5b97f6360208 | note | Stainless Steel Ferrules used
aab89d1a-2063-5a1d-bedd-aee10fe70640 | note | Positioning and tolerance is verified against Shop Draings
c86bd0bc-aada-43aa-95a7-b0174eaefa7e | checkpoint | Internal Diaphragm Ferrules Installed
4dadc833-9eaa-5857-b658-6abcf9090811 | note | M20x96 ferrules installed
ec624196-93d8-594f-a847-18f9622fc361 | note | Positioning and tolerance is verified against Shop Draings
862f20bf-a085-492d-aa6d-f5ddc81a7417 | checkpoint | Non-drill cone lifters installed (Type A)
88fd6094-6dcb-52c4-a77c-fb9fdddae50f | note | Quantity and spacings is verified against Shop Draings
6de53da8-678c-4374-b3c9-fd17adfac433 | checkpoint | Prestressing Strands
a4ec72f5-491b-5561-8d4d-100008251645 | textbox | Enter Coil Number Used for this Cast
520f4406-96ce-5aa8-a0c6-1f512da847d2 | note | Sag Load all Strand
632e64e4-1474-573a-9374-fd498c4e5302 | note | Mutli-Stress as per Pre-stressing Procedures
e8a39376-6f25-4732-a66f-f2ff97dbeb27 | checkpoint | All Temperature Loggers are installed as per Approved WMS
e7927840-e410-5f4a-8825-102ddb27db5f | note | Every 25m
b7cf34cc-adc2-5b58-937b-27e2ec6e47d5 | note | 1 x End Block Mid-Diaphragm
a502b68c-11cf-5546-b5f9-b92252cb8e09 | note | 1 x Within Cover Zone
14a7a992-333a-50dd-bf9d-5438a54fa7c3 | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
1c6c2ac4-97e1-5ef7-a164-e9940ce6d6b6 | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
3a0609ad-5750-4160-9eef-6ed1ee38ae6e | checkpoint | Ensure All temperature Loggers are Working (Check App)
19f3372e-89f2-47c0-be73-b2233d712648 | checkpoint | Prepare Stressing Records and Submit to Client for Review (Hold Point)
ca6021a6-0bae-4267-b03f-a5804c430326 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
10b17b19-487c-4966-b77b-fd4900a599a9 | checkpoint | QA Engineer Check Completed by
3271c69b-50c9-4cfb-a305-3c6a628c289d | checkpoint | Client Inspector (if present)
bb2458ff-3c7d-46be-b051-b6a5a01100c1 | section | Supervisor Release
4883d63b-91a0-4f46-a434-4827e1d954e7 | checkpoint | Supervisor Release to Engineering Team
12ea324e-ea59-4a0b-bf08-4ceaf038a39b | section | Casting Checklist
7fb381ab-046b-4158-8d20-8a9c82091eae | checkpoint | Casting Information
4e953bd0-7228-5c30-a76a-96dde9e8c635 | textbox | Cast Date
3e761740-99ba-4acd-8d28-bdebf5e82309 | checkpoint | Concrete Delivery Dockets
7e2aabec-da93-5e7b-8c7a-c19defb6519c | textbox | Concrete Delivery Dockets
432c686a-5938-4f7d-a2b1-b92e28c0fafa | checkpoint | Total Concrete Volume
654bd367-c698-5ac4-995e-b6c270a46e7e | textbox | Volume (m3)
06f6fb56-d439-4458-937f-93a3b82141f9 | checkpoint | Mix Design Verified WS654TD04 (S65/14/200)
85f669e2-c692-4453-b0f7-7f92513f32db | checkpoint | Ambient Temperature within Limits
cbd512ca-f574-5258-9930-d87617bf141f | note | 5 - 38°C
ae400924-6fc2-452e-adab-2e72d80dd3f4 | checkpoint | Concrete Temperature
746495be-a2aa-5599-aed2-73b4f902d66e | note | max 32°C
80e6d484-e0ad-4f98-8c22-bc3a30c6da5a | checkpoint | Slump within Allowable Tolerance
fb5491b2-cb35-5ea5-ab4a-138c3a276ccb | textbox | Slump 1
f3c145d7-6183-5bd9-b9ee-c88fa09c8bab | textbox | Slump 2
7804657c-eead-5bca-86be-f0ebbc0b7894 | note | Holcim 200 ± 40mm
f7343183-c0f6-4cbd-bce2-ed41d065f074 | checkpoint | Truck Tested for strength
f04ffc31-18a9-5583-8ce8-2cb30b14a034 | textbox | Test Report Reference Number 1
a40126e2-97f7-5a3a-b198-724ff93590ba | textbox | Test Report Reference Number 2
2329e21a-d70b-4026-9470-ffe749665d6f | checkpoint | Time Lag Between Concrete Layers (< 20min)
f29d24bf-e1f2-4c9c-8940-7cb34e5b6fb2 | checkpoint | Concrete Placed within 90min from Batching Plant
86d91639-8318-41f2-882e-181e949ba529 | checkpoint | Required Finish Applied as per Drawings
107421d1-755b-4d9b-b12d-7bff2d6de145 | checkpoint | Concrete Covered Overnight
090dc192-ac15-40b9-9d3f-f07424933933 | checkpoint | Cylinders Stored next to Bed
2f15587a-a662-47b2-8d31-d9a38324bd32 | section | Stripping Checklist
45e7296f-f594-46ca-912f-b81ab82bf65e | checkpoint | Date Stripped
e11eeff5-3fe7-51a3-8fbe-c59a32be4396 | textbox | Enter Date
44b16c9e-133b-4e59-925e-15cfd67f96b8 | checkpoint | Concrete Cylinders Crushed and Submitted to Client (Hold Point)
4d28f7e6-ddd4-5c01-8dc6-6bef904bdbf3 | textbox | Stripping Strength
12514243-81c0-500c-9c05-9462ce1c6816 | note | Strength = Reading / 7.851
f3862656-1425-464f-92a3-3c2d42305038 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
7519404a-e1f7-4d9e-adbf-a9f4493673ae | checkpoint | Lifting Strength Achieved
af9e2513-1789-49ef-b0eb-35042cef7a79 | checkpoint | Product Clearly Labelled
f2f8b0f8-f075-4ac1-98a9-0c914a8a5d3b | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
dd15db2d-fb67-533f-8fd2-f35eaedfce59 | note | Length
93a2dbdf-92a1-5004-b75c-0b9724c11cc8 | note | Width
70c7d9ec-3447-56c0-b618-5168109adbe5 | note | Height
bfb207f7-80a3-57c4-a3b5-58060c84d3a3 | note | Straightness
2640f4ff-3c1b-583a-8c9b-0cce29d68e85 | note | Cross-section
7f340593-595d-45df-b653-2a93a2f0a8d9 | checkpoint | Specified Finish Achieved
36e4850e-df1c-433d-a526-171bb01e2858 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
08698667-ffe4-57f3-8eb4-9a389d500b24 | note | Duct Sleeves
323aaf9f-006a-5b51-8d3d-da04d86dd81a | note | VSL Cast-in anchors
18e61c23-9937-545e-8626-3e550554a1de | note | Lifters
b61a1bfc-bcc9-5639-9897-1a4d72dc9296 | note | Temporary works Ferrules
6305290c-37fb-5d26-81a8-092d2ac96a2b | note | Internal Diaphragm Ferrules
623bc548-9f18-5ebe-9275-989fbae80396 | note | Non-drill cone lifters (Type A)
479e91a2-cbac-4b7e-bbcd-a66055c5f573 | checkpoint | Lifted and Handled as per Drawings
a55d7cb6-3f48-4967-b2a3-e1298ae15385 | checkpoint | Storage/Stacking as per Approved Plan
bcbd3ec6-07a5-4a41-a03a-95d2ff7e5d45 | checkpoint | Curing as per Approved Methodology
3661e941-4b37-4541-9da9-e493145c4163 | checkpoint | Post-Pour Works Completed (As Required)
65852d17-60ef-5d16-8707-4064ecf16112 | textbox | Strands are Cut Flush
f2df6546-38f7-53b7-9237-3ca499e3d96b | textbox | Areas requiring greencut are completed
ee4bb2cb-37fd-5320-afae-a425799f936c | textbox | Condeck Installed where required
a40782de-05ed-57a0-80e4-8d5a37f0cd7a | textbox | Cooling pipes are cut and sealed
2c9a9302-b0c4-5414-993b-40b001c0fe56 | textbox | Tub Void formers are filled with grout
b1d8f9a5-eec7-5124-92fa-93c89137d73e | textbox | Threaded Bars are cleaned and checked for coupler installation (Type A Beams only)
5746a038-8bfc-5b52-968f-cdd1def58802 | textbox | All Drain Holes are Clean
67d416b1-bb80-5181-b013-bc07533800c3 | textbox | Dekguard applied on where required
2c1d934f-df10-555b-8270-8a46045c78d6 | textbox | Duct and VSL sleeves are cleaned inside
e5df0b15-4efb-546e-b9ac-20d3b9c612e5 | textbox | All Miscellaneous Items are Completed
e576377a-2406-4377-8678-fb3f24766624 | checkpoint | Survey of Beams
b35dcfc0-38bb-57ed-a973-3b8ea9f3f115 | textbox | Survey Report Completed as per WMS
aa12c33a-e67e-450c-85c8-1afe933343a5 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
d069710a-4012-4243-904c-23d0b17a8d13 | section | Any Defect Identified
be03632f-f3a6-4d5c-a2b4-3eebfbbc43b0 | checkpoint | Punchlisting Completed
26dc963b-6b71-4a8c-9215-fd573d48bfbd | checkpoint | Repairs Required (if applicable)
61039f53-dc11-423c-8cd7-ffeb3db0beb7 | checkpoint | Repairs Completed as per approved WMS (if applicable)
9d1bb568-3350-4a4d-8d91-493fc8e9fe5b | checkpoint | Any NCR Required (if applicable)
32835d9d-be4b-4547-937c-f5c59b8c21c4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
491a884b-fffd-401f-b388-16eb80394e88 | section | As-Built Drawings
fc636a43-e364-40f3-bee0-cd6f2ee7f48e | checkpoint | As-Built Drawings Completed, Stamped and Attached
cbf91459-7718-42d1-bcf3-7e13c18e5223 | section | Concrete Strength Test Report
d0b7bbb2-0d54-45d9-a284-52df235b0c59 | checkpoint | Concrete Strength Test Report Received
2f2365a2-2c2b-59b2-a2a6-60590471aea4 | textbox | Concrete Test Report Number 1
09a7f27a-6173-561a-ac6a-9b93c6962323 | textbox | 7 Day Strength (1)
03dd0ded-ac42-5916-8085-d52fec4644f0 | textbox | 7 Day Strength (2)
83f87dd1-0250-57b4-8a05-c450e8f50097 | textbox | 28 Day Strength (3)
a4a0fc97-01ec-5607-9e8b-795748939246 | textbox | 28 Day Strength (4)
bb6a7a3d-cb8c-5251-9fc0-1c3360c4e208 | textbox | 28 Day Strength (5)
e3495446-d416-50e1-875e-13e738ef36a5 | textbox | 28 Day Strength (6)
a1362f8e-5a1d-5c77-a194-e77ad58d49c4 | textbox | 29 Day Strength (7)
b3970d03-148a-5908-a547-e407e02554fe | textbox | 29 Day Strength (8)
8f4bc4b8-0a4a-48cf-a1f7-355688b27539 | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
0473fecf-1dad-4026-983b-f33ee52e79e7 | checkpoint | Certificate of Conformance
12fe40ec-7523-4453-87b8-1b05cdc44fa4 | checkpoint | Inspection Release Certificate
b9d2e5ae-537e-466c-8d19-1803bc1229d9 | checkpoint | Completed by
cb2b3bf5-4bcb-4d34-9396-aaded50e44c8 | checkpoint | Reviewed by
8c6de217-8667-431f-976b-8c50fc9dfdb6 | signoff | (INTERNAL HOLD POINT)
28447eeb-c298-43d7-9db3-4c360c7e274c | checkpoint | Client Representative (if applicable)