## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
6a6772fe-ffae-453c-b16c-96fe7304e834 | checklist | Precast Beams |  | Precast Beams
| section | Pre-Pour Checklist
| checkpoint | Pre-Pour Checklist completed
| text | Cast Number
| text | Precast Beam 1
| text | Precast Beam 2
| checkpoint | Shop Drawings approved for Works
| checkpoint | Mould Dimensions are within Shop Drawings Tolerance
| label | Length
| label | Width
| label | Height
| label | Straightness
| label | Cross-section
| checkpoint | Mould Surface Checked
| label | Cleaned
| label | Sealed
| label | Rubbers in Place
| label | Oiled
| label | Chamfers in Place
| checkpoint | Duct tub installation
| label | Duct positions verified against drawings
| label | Stiffener pipes greased, installed and positions verified
| label | Allowabe tolerance +/- 3mm individual ducts, +/- 6mm as a group
| checkpoint | VSL Cast-in anchors
| label | VSL bar positions verified against drawings
| label | VSL bar no tilting observed
| label | Recess for VSL sleeve created
| label | Allowabe tolerance +/- 3mm
| checkpoint | Reinforcement in Accordance with Drawings
| label | Reinforcement size
| label | Lap Length
| label | Splicing
| label | Bar Chairs
| checkpoint | Cover maintained and within tolerance
| checkpoint | Formwork Ferrules Installed
| label | Stainless Steel Ferrules used
| label | Positioning and tolerance is verified against Shop Draings
| checkpoint | Internal Diaphragm Ferrules Installed
| label | M20x96 ferrules installed
| label | Positioning and tolerance is verified against Shop Draings
| checkpoint | Non-drill cone lifters installed (Type A)
| label | Quantity and spacings is verified against Shop Draings
| checkpoint | Prestressing Strands
| text | Enter Coil Number Used for this Cast
| label | Sag Load all Strand
| label | Mutli-Stress as per Pre-stressing Procedures
| checkpoint | All Temperature Loggers are installed as per Approved WMS
| label | Every 25m
| label | 1 x End Block Mid-Diaphragm
| label | 1 x Within Cover Zone
| label | 1 x Within Tent/Tarp Enclosure (Outside concrete)
| label | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
| checkpoint | Ensure All temperature Loggers are Working (Check App)
| checkpoint | Prepare Stressing Records and Submit to Client for Review (Hold Point)
| signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
| checkpoint | QA Engineer Check Completed by
| checkpoint | Client Inspector (if present)
| section | Supervisor Release
| checkpoint | Supervisor Release to Engineering Team
| section | Casting Checklist
| checkpoint | Casting Information
| text | Cast Date
| checkpoint | Concrete Delivery Dockets
| text | Concrete Delivery Dockets
| checkpoint | Total Concrete Volume
| text | Volume (m3)
| checkpoint | Mix Design Verified WS654TD04 (S65/14/200)
| checkpoint | Ambient Temperature within Limits
| label | 5 - 38°C
| checkpoint | Concrete Temperature
| label | max 32°C
| checkpoint | Slump within Allowable Tolerance
| text | Slump 1
| text | Slump 2
| label | Holcim 200 ± 40mm
| checkpoint | Truck Tested for strength
| text | Test Report Reference Number 1
| text | Test Report Reference Number 2
| checkpoint | Time Lag Between Concrete Layers (< 20min)
| checkpoint | Concrete Placed within 90min from Batching Plant
| checkpoint | Required Finish Applied as per Drawings
| checkpoint | Concrete Covered Overnight
| checkpoint | Cylinders Stored next to Bed
| section | Stripping Checklist
| checkpoint | Date Stripped
| text | Enter Date
| checkpoint | Concrete Cylinders Crushed and Submitted to Client (Hold Point)
| text | Stripping Strength
| label | Strength = Reading / 7.851
| signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
| checkpoint | Lifting Strength Achieved
| checkpoint | Product Clearly Labelled
| checkpoint | Product Dimensions Achieved and are within Specified Tolerance
| label | Length
| label | Width
| label | Height
| label | Straightness
| label | Cross-section
| checkpoint | Specified Finish Achieved
| checkpoint | Cast-in Items are all in Place and within Specified Tolerance
| label | Duct Sleeves
| label | VSL Cast-in anchors
| label | Lifters
| label | Temporary works Ferrules
| label | Internal Diaphragm Ferrules
| label | Non-drill cone lifters (Type A)
| checkpoint | Lifted and Handled as per Drawings
| checkpoint | Storage/Stacking as per Approved Plan
| checkpoint | Curing as per Approved Methodology
| checkpoint | Post-Pour Works Completed (As Required)
| text | Strands are Cut Flush
| text | Areas requiring greencut are completed
| text | Condeck Installed where required
| text | Cooling pipes are cut and sealed
| text | Tub Void formers are filled with grout
| text | Threaded Bars are cleaned and checked for coupler installation (Type A Beams only)
| text | All Drain Holes are Clean
| text | Dekguard applied on where required
| text | Duct and VSL sleeves are cleaned inside
| text | All Miscellaneous Items are Completed
| checkpoint | Survey of Beams
| text | Survey Report Completed as per WMS
| checkpoint | Temperature Logging Completed and Conforming. Attach Results
| section | Any Defect Identified
| checkpoint | Punchlisting Completed
| checkpoint | Repairs Required (if applicable)
| checkpoint | Repairs Completed as per approved WMS (if applicable)
| checkpoint | Any NCR Required (if applicable)
| checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
| section | As-Built Drawings
| checkpoint | As-Built Drawings Completed, Stamped and Attached
| section | Concrete Strength Test Report
| checkpoint | Concrete Strength Test Report Received
| text | Concrete Test Report Number 1
| text | 7 Day Strength (1)
| text | 7 Day Strength (2)
| text | 28 Day Strength (3)
| text | 28 Day Strength (4)
| text | 28 Day Strength (5)
| text | 28 Day Strength (6)
| text | 29 Day Strength (7)
| text | 29 Day Strength (8)
| section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
| checkpoint | Certificate of Conformance
| checkpoint | Inspection Release Certificate
| checkpoint | Completed by
| checkpoint | Reviewed by
| signoff | (INTERNAL HOLD POINT)
| checkpoint | Client Representative (if applicable)
de14216b-1004-4810-ae59-80235ce003a7 | checklist | Preliminary Activities and Materials Approval |  | Preliminary Activities and Materials Approval
| section | Preliminary Activities (Approved by Client)
| checkpoint | Compliance to AS/NZ ISO 9001:2015
| checkpoint | HSE Management Plan
| checkpoint | Project Quality Management Plan & Work Method Statement
| checkpoint | MDR Index and ITP (Inspection & Test Plan)
| checkpoint | Shop Drawings
| checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
| section | Concrete
| checkpoint | S65 Concrete Mix Design Approved by Client
| label | Supplier : Holcim
| label | Mix Code: WS654TD04 (S65/14/200)
| label | Slump : 200 ± 40
| section | Steel Reinforcement
| checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
| checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
| section | Prestressing Tendons
| checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
| checkpoint | Ensure that all Coil Numbers are recorded
| checkpoint | Stressing Calculations Submitted and Approved by Client for Works
| checkpoint | Stressing Jack Calibration Certificates
| section | Lifting Anchors
| checkpoint | Lifting Design Approved by Client
| checkpoint | Lifting Devices Approved by Client
| checkpoint | Inspection of Delivery for Completeness and Quality
| section | Cast-in Items and Ferrules
| checkpoint | All Cast in Materials Approved
| checkpoint | Inspection of Delivery for Completeness and Quality