## Project Breakdown
343 Parkville |  |  | Checklists
QA / ITP's
Level 4 Platform Roof
|  | Insulation | Insulation checklist - Level 4 Platform
|  | Roof | Roof Installation checklist - Level 4 Platform
|  | Flashing | Flashing/Capping Installation Checklist - Level 4 Platform
|  | Roof Penetration | Roof Penetrations checklist - Level 4 Platform
|  | Box Gutter | Box Gutter Installation checklist - Level 4 Platform
Level 5 POP UP Askin Roof
|  | Roof | Askin Roof PANEL INSTALLATION
|  | Flashing | Flashing/Capping Installation Checklist - Askin Roof
Level 5 POP IP Askin Wall
|  | Askin Wall Cladding | Askin Performance Panel Wall Cladding checklist
Lift Overrun Roof
|  | Askin Roof | Askin Roof PANEL INSTALLATION
|  | Flashings | Flashing/Capping Installation Checklist - Askin Roof
|  | Eaves Gutter | Eaves Gutter Installation Checklist
Board Room Roof
|  | Insulation | Insulation checklist - Boardroom
|  | Roof | Roof Installation checklist - Level 4 Platform
|  | Box Gutter | Box Gutter Installation checklist - Level 4 Platform
Plant Room 1
|  | Insulation | Insulation checklist - Boardroom
|  | Roof | Roof Installation checklist - Level 4 Platform
|  | Box Gutter | Box Gutter Installation checklist - Level 4 Platform
Lift Motor Room
|  | Askin Roof | Askin Roof PANEL INSTALLATION
|  | Flashings | Flashing/Capping Installation Checklist - Askin Roof
|  | Eaves Gutter | Eaves Gutter Installation Checklist
Level 5 Raked Roof
|  | Insulation | Insulation checklist - Raked Roof
|  | Roof | Roof Installation checklist - level 5 raked roof
|  | Flashing | Flashing/Capping Installation Checklist - Level 4 Platform
|  | Eaves Gutter | Eaves Gutter Installation Checklist
Level 5 Curved Roof
|  | Insulation | Insulation checklist - Level 4 Platform
|  | Roof | Roof Installation checklist - Level 4 Platform
|  | Flashing | Flashing/Capping Installation Checklist - Level 4 Platform
|  | Box Gutter | Box Gutter Installation checklist - Level 4 Platform
Bike Shelter Roof
|  | Roof | Roof Installation checklist - Bike Shelter Roof
|  | Flashing | Flashing/Capping Installation Checklist - Level 4 Platform
|  | Eaves Gutter | Eaves Gutter Installation Checklist
Bin Closure Roof
|  | Roof | Roof Installation checklist - Bike Shelter Roof
|  | Flashing | Flashing/Capping Installation Checklist - Level 4 Platform
|  | Eaves Gutter | Eaves Gutter Installation Checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
COVID Tracking Reports
Delivery Dockets | Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Checklist Library | Add Delivery Docket
Add Non Conformance Corrective Action Report
Add Offhire Information
Add Onsite Material Install Form
Add Pre-Start Tool Box
Add Tool Box Training
Add Variation
Inspection Reports | Wire Mesh Install
Handrail Install

## Sheet1
343 Parkville
type | name | values
checklist | Insulation checklist - Level 4 Platform
section | Material Inspection
checkpoint | Insulation: 80mm Glasswool on Medium Sarking
checkpoint | Thermal spacer: 60mm thermal spacer
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist - Level 4 Platform
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 25mm - 35mm 12G without NEO Seal
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist - Level 4 Platform
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Plyboard under Capping
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist - Level 4 Platform
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation checklist - Level 4 Platform
section | Material Inspection
checkpoint | Box Gutter Brackets: #2
checkpoint | Insulation under gutter: 60mm Glasswool
checkpoint | Insulation under gutter: Aircell
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Colorbond to match
checkpoint | Sumps: 1.2mm 316 Stainless Steel
checkpoint | High Capacity Overflow: 0.55mm 304 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Roof PANEL INSTALLATION
section | Material Inspection
checkpoint | Panel: Askin 100mm roof panel
checkpoint | Ridge Foam Filler
checkpoint | Internal liner colour: Surf Mist
checkpoint | External liner colour : Surf Mist
checkpoint | Buildex fixings 14 x 135mm - bonded washer
checkpoint | Stitching Screw: 25mm 12 G
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Metecno Spec to SHS steel member
checkpoint | Panels located correctly
checkpoint | Fixings as per Metecno Spec
checkpoint | Gun grade Butyl sealant to underside lap of panel 6mm
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist - Askin Roof
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Plyboard under Capping
checkpoint | 6mm Butyl Tape
checkpoint | Infill insulation for Soffit
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | 6mm Butyl Tape for Soffit Flashigns
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Askin Performance Panel Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding type: 100mm Askin with Standard Liner
checkpoint | Curved Wall Cladding type: 100mm / 120mm Mineral Wool Panel
checkpoint | Type of Fixings: Stainless Screws
checkpoint | Butyl Tape
section | Installation
checkpoint | Butyl Tap to Soffit Flashing
checkpoint | Infill Insulation to Soffit Flashings
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Eaves Gutter Installation Checklist
section | Material Inspection
checkpoint | Eaves Gutter: Trimline Eaves Gutter
checkpoint | Eaves Gutter Brackets: To suit Trimline eaves gutter - Zincalume Internal
checkpoint | Stop ends: Trimline
checkpoint | Downpipes: YES - Colorbond or PVC
checkpoint | Pops: 100mm Dia
section | Installation
checkpoint | Spout Brackets installed with fall as per Specification
checkpoint | Spouting installed to sizes shown in spec & drawings.
checkpoint | Outlets installed to correct sizes.
checkpoint | Downpipe installed as shown on drawings and correct
checkpoint | size and connected to stormwater
checkpoint | Downpipe installed straight and bolted to downpipe clip
checkpoint | Downpipe spreader installed as shown on drawing
checkpoint | Overflow outlets installed at each downpipe location
checkpoint | Outlets installed to correct sizes.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation checklist - Boardroom
section | Material Inspection
checkpoint | Insulation: 60mm Glasswool on Medium Sarking
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation checklist - Raked Roof
section | Material Inspection
checkpoint | Insulation: 60mm Glasswool on Medium Sarking
checkpoint | Insulation: 145mm Glasswool on Medium Sarking
checkpoint | Thermal Spacer: 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist - level 5 raked roof
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Kliplok
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 25mm - 35mm 12G without NEO Seal
checkpoint | 15mm Marine Plywood
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist - Bike Shelter Roof
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Kliplok
checkpoint | Insulation: Roof Sarking Medium weight paper
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: 25mm - 35mm 12G without NEO Seal
checkpoint | 15mm Marine Plywood
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: