## Sheet1
3.1 | Pre-Construction Survey | Specification Cl.2.11.2, Cl.15.6.6 | Drone/GPS | Receipt of survey by engineer | Topo Survey | Prior to works - each lot | Witness | W | SPE CHAR(AMP) SV | 3.1 - Pre-Construction Survey | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6 | Specification Reference - Drone/GPS | Acceptance Criteria - Receipt of survey by engineer | Verifying Document - Topo Survey | Frequency - Prior to works - each lot | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SPE CHAR(AMP) SV | 3.1 - Pre-Construction Survey
3.2 | Use of Flighty's Mound material for fill | N/A | On site material visual confirmation and IANZ testing requested by the Stantec Representative | Confirmation of use | Mail Confirmation from Stantec Representative | Start of Earthowrks | Hold Point (where required) | H | ER | 3.2 - Use of Flighty's Mound material for fill | Inspection Point: Quality Control Activity - N/A | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative | Acceptance Criteria - Confirmation of use | Verifying Document - Mail Confirmation from Stantec Representative | Frequency - Start of Earthowrks | Inspection Type (Visual, other) - Hold Point (where required) | Inspection: Key - H | Inspection: By (Role Key) - ER | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
3.3 | Use of Moonshine Rd Cut material to be used for fill | N/A | On site material visual confirmation and IANZ testing requested by the Stantec Representative | Confirmation of use | Mail Confirmation from Stantec Representative | Start of Earthowrks | Hold Point (where required) | H | ER | 3.3 - Use of Moonshine Rd Cut material to be used for fill | Inspection Point: Quality Control Activity - N/A | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative | Acceptance Criteria - Confirmation of use | Verifying Document - Mail Confirmation from Stantec Representative | Frequency - Start of Earthowrks | Inspection Type (Visual, other) - Hold Point (where required) | Inspection: Key - H | Inspection: By (Role Key) - ER | Specification Reference - Drone/GPS
3.4 | AP65 Material acceptance | Specification Cl 17.1.11 | Material Testing and Compliance | IANZ Testing | Testing report | Every 1000m3 or change in material source | Hold Point | H | ER | 3.4 - AP65 Material acceptance | Inspection Point: Quality Control Activity - Specification Cl 17.1.11 | Specification Reference - Material Testing and Compliance | Acceptance Criteria - IANZ Testing | Verifying Document - Testing report | Frequency - Every 1000m3 or change in material source | Inspection Type (Visual, other) - Hold Point | Inspection: Key - H | Inspection: By (Role Key) - ER | Acceptance Criteria - Receipt of survey by engineer
4.1 | Topsoil Depth Checks | Project Spec Cl.15.3.4 | Nominal depth checks at 100m intervals longitudinally and 50m interval transverse | Photos with tape measure to show depth of topsoil layer. Date and location to be recorded | Site Photos, Record Sheet | 100m intervals longitudinally and 50m intervals transverse to earthworks | Witness | W | SE | 4.1 - Topsoil Depth Checks | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4 | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded | Verifying Document - Site Photos, Record Sheet | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Verifying Document - Topo Survey
4.2 | Hazardous CHAR(AMP) Classified Soils | Project Spec Cl.15.3.3 CHAR(AMP) 15.3.5 | Hazardous waste and contamined soils encountered during the excavation process | Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered | Visual, Site Photos | Continuous | Witness | W | SE | 4.2 - Hazardous CHAR(AMP) Classified Soils | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 CHAR(AMP) 15.3.5 | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered | Verifying Document - Visual, Site Photos | Frequency - Continuous | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Frequency - Prior to works - each lot
4.3 | Subgrade testing - Trim and Compact | TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.10 | Trimming CHAR(AMP) Compaction of in-situ subgrade. Conduct plateau test. | N/A | Plateau worksheet | Full surface | Witness | W | SE | 4.3 - Subgrade testing - Trim and Compact | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.10 | Specification Reference - Trimming CHAR(AMP) Compaction of in-situ subgrade. Conduct plateau test. | Acceptance Criteria - N/A | Verifying Document - Plateau worksheet | Frequency - Full surface | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Inspection Type (Visual, other) - Witness
4.4 | Subgrade testing - Scala | TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.11 | Scala Testing | 1 blow per 100mm is the minimum requirement for general fill placement | DN-QUA-QC-04 1m Scala Worksheet | Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m. | Witness | W | SE | 4.4 - Subgrade testing - Scala | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.11 | Specification Reference - Scala Testing | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m. | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Inspection: Key - W
4.5 | Subgrade testing - Benkelman Beam | TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.12 | Benkelman Beam Testing | Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm | Lab report | Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m. | Witness | W | SE | 4.5 - Subgrade testing - Benkelman Beam | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.12 | Specification Reference - Benkelman Beam Testing | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm | Verifying Document - Lab report | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m. | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Inspection: By (Role Key) - SPE CHAR(AMP) SV
4.6 | Subgrade testing - Proof Roll | TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.13 | Proof Roll | As instructed by the Engineer | Visual Assessment - Sign off on ConQA by Engineer | Proof Roll: Full surface using suitable plant | Hold | H | ER | 4.6 - Subgrade testing - Proof Roll | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.13 | Specification Reference - Proof Roll | Acceptance Criteria - As instructed by the Engineer | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer | Frequency - Proof Roll: Full surface using suitable plant | Inspection Type (Visual, other) - Hold | Inspection: Key - H | Inspection: By (Role Key) - ER | 3.2 - Use of Flighty's Mound material for fill
4.7 | Fill Compaction Trial | Project Spec Cl 15.6.11 | On-site Testing - NDM, Visual, Shear Vane | Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P | NDM Worksheet Shear Vane Worksheet Plateau Density Sheet | When a new type of fill material is used | Hold | H | ER | 4.7 - Fill Compaction Trial | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11 | Specification Reference - On-site Testing - NDM, Visual, Shear Vane | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P | Verifying Document - NDM Worksheet Shear Vane Worksheet Plateau Density Sheet | Frequency - When a new type of fill material is used | Inspection Type (Visual, other) - Hold | Inspection: Key - H | Inspection: By (Role Key) - ER | Inspection Point: Quality Control Activity - N/A
4.8 | Fill Backfill layer thickness | Project Spec Cl.15.3.8 | Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction | Fill placement not exceeding 230mm | Visual, Site Photos and NDM check sheets DN-QUA-QC-09 NDM Worksheet | Every layer | Witness | W | SE | 4.8 - Fill Backfill layer thickness | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8 | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction | Acceptance Criteria - Fill placement not exceeding 230mm | Verifying Document - Visual, Site Photos and NDM check sheets DN-QUA-QC-09 NDM Worksheet | Frequency - Every layer | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
4.9 | Fill Compaction Testing Laboratory | Project Spec Cl.15.6.12 | Water Content Standard Proctor and Wet Sieve. | N/A | IANZ report | WC - 1 test per 400m3 with 2 tests minimum per day MDD CHAR(AMP) WS - 1 test per 2000m3 | Witness | W | SE | 4.9 - Fill Compaction Testing Laboratory | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12 | Specification Reference - Water Content Standard Proctor and Wet Sieve. | Acceptance Criteria - N/A | Verifying Document - IANZ report | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day MDD CHAR(AMP) WS - 1 test per 2000m3 | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Acceptance Criteria - Confirmation of use
4.1 | Fill Compaction Testing Site |  | Compaction test by plateau | Plateau Testing to determine true MDD value based on site conditions | DNZ Plateau Test work sheet | Daily | Witness | W | SE | 4.1 - Fill Compaction Testing Site | Inspection Point: Quality Control Activity - | Specification Reference - Compaction test by plateau | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions | Verifying Document - DNZ Plateau Test work sheet | Frequency - Daily | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Verifying Document - Mail Confirmation from Stantec Representative
4.11 | Fill Compaction Testing Site | Project Spec Cl.15.6.10, Project Spec Cl.15.6.12 | NDM and OMC testing of fill material, Shear Vane | Moisture Content: between-2% and +4% of OMC Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95% Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only) | NDM Record Sheet DN-QUA-QC-09 NDM Worksheet Shear Vane Sheet (Cohesive soil only) | NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only) | Witness | W | SE | 4.11 - Fill Compaction Testing Site | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12 | Specification Reference - NDM and OMC testing of fill material, Shear Vane | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95% Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only) | Verifying Document - NDM Record Sheet DN-QUA-QC-09 NDM Worksheet Shear Vane Sheet (Cohesive soil only) | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only) | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE | Frequency - Start of Earthowrks
4.12 | Fill Tolerances | Project Spec Cl. 15.3.11 | Survey of finished surface | Tolerance of +-50mm | As-built | At Completion | Witness | W | SE/SV | 4.12 - Fill Tolerances | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11 | Specification Reference - Survey of finished surface | Acceptance Criteria - Tolerance of +-50mm | Verifying Document - As-built | Frequency - At Completion | Inspection Type (Visual, other) - Witness | Inspection: Key - W | Inspection: By (Role Key) - SE/SV | Inspection Type (Visual, other) - Hold Point (where required)
Inspection: Key - H
Inspection: By (Role Key) - ER
3.3 - Use of Moonshine Rd Cut material to be used for fill
Inspection Point: Quality Control Activity - N/A
Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
Acceptance Criteria - Confirmation of use
Verifying Document - Mail Confirmation from Stantec Representative
Frequency - Start of Earthowrks
Inspection Type (Visual, other) - Hold Point (where required)
Inspection: Key - H
Inspection: By (Role Key) - ER
3.4 - AP65 Material acceptance
Inspection Point: Quality Control Activity - Specification Cl 17.1.11
Specification Reference - Material Testing and Compliance
Acceptance Criteria - IANZ Testing
Verifying Document - Testing report
Frequency - Every 1000m3 or change in material source
Inspection Type (Visual, other) - Hold Point
Inspection: Key - H
Inspection: By (Role Key) - ER
4.1 - Topsoil Depth Checks
Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
Verifying Document - Site Photos, Record Sheet
Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.2 - Hazardous CHAR(AMP) Classified Soils
Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 CHAR(AMP) 15.3.5
Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
Verifying Document - Visual, Site Photos
Frequency - Continuous
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.3 - Subgrade testing - Trim and Compact
Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.10
Specification Reference - Trimming CHAR(AMP) Compaction of in-situ subgrade. Conduct plateau test.
Acceptance Criteria - N/A
Verifying Document - Plateau worksheet
Frequency - Full surface
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.4 - Subgrade testing - Scala
Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.11
Specification Reference - Scala Testing
Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.5 - Subgrade testing - Benkelman Beam
Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.12
Specification Reference - Benkelman Beam Testing
Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
Verifying Document - Lab report
Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.6 - Subgrade testing - Proof Roll
Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2 Project Spec Cl 17.1.5 - 17.1.13
Specification Reference - Proof Roll
Acceptance Criteria - As instructed by the Engineer
Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
Frequency - Proof Roll: Full surface using suitable plant
Inspection Type (Visual, other) - Hold
Inspection: Key - H
Inspection: By (Role Key) - ER
4.7 - Fill Compaction Trial
Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
Specification Reference - On-site Testing - NDM, Visual, Shear Vane
Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
Verifying Document - NDM Worksheet Shear Vane Worksheet Plateau Density Sheet
Frequency - When a new type of fill material is used
Inspection Type (Visual, other) - Hold
Inspection: Key - H
Inspection: By (Role Key) - ER
4.8 - Fill Backfill layer thickness
Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
Acceptance Criteria - Fill placement not exceeding 230mm
Verifying Document - Visual, Site Photos and NDM check sheets DN-QUA-QC-09 NDM Worksheet
Frequency - Every layer
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.9 - Fill Compaction Testing Laboratory
Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
Specification Reference - Water Content Standard Proctor and Wet Sieve.
Acceptance Criteria - N/A
Verifying Document - IANZ report
Frequency - WC - 1 test per 400m3 with 2 tests minimum per day MDD CHAR(AMP) WS - 1 test per 2000m3
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.1 - Fill Compaction Testing Site
Inspection Point: Quality Control Activity -
Specification Reference - Compaction test by plateau
Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
Verifying Document - DNZ Plateau Test work sheet
Frequency - Daily
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.11 - Fill Compaction Testing Site
Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
Specification Reference - NDM and OMC testing of fill material, Shear Vane
Acceptance Criteria - Moisture Content: between-2% and +4% of OMC Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95% Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
Verifying Document - NDM Record Sheet DN-QUA-QC-09 NDM Worksheet Shear Vane Sheet (Cohesive soil only)
Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE
4.12 - Fill Tolerances
Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
Specification Reference - Survey of finished surface
Acceptance Criteria - Tolerance of +-50mm
Verifying Document - As-built
Frequency - At Completion
Inspection Type (Visual, other) - Witness
Inspection: Key - W
Inspection: By (Role Key) - SE/SV