## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | SQE-020-F-068 - 3M Mould
section | Details
checkpoint-no-status | Details
textbox | Pour Item:
textbox | Product ID:
textbox | Drawing References:
date | Date:
textbox | Cast No:
textbox | Foreman:
section | Mould Setout
checkpoint | Forms: Length
checkpoint | Sides and ends secured
checkpoint | Orientation of Unit
checkpoint | Rake/Skew
checkpoint | Width
holdpoint | Signed:
section | Cage inspection
checkpoint | Steel cage matches latest drawing revision
checkpoint | Bar size and spacing match specification
checkpoint | Bends, ties, and overlaps comply with standard
checkpoint | Correct bar cover distance to mould
checkpoint | Rebar labels or cage tags match ID
checkpoint | General cleanliness of cage
holdpoint | Signed:
section | Cast in items Setout
checkpoint | Tims
checkpoint | PVC pipes
checkpoint | Plates
holdpoint | Signed:
section | Reo added after cage QA
checkpoint | Reinforcing around openings
checkpoint | HR12 Stirrups @ 150/300mm
checkpoint | PFC125
checkpoint | HR8 Stirrups @ 90/300mm
checkpoint | HD16 Hairpins @ 300mm
checkpoint | HD20 Hairpins @ 150mm
checkpoint | Blockouts: Correct size and position – secure
section | Final Check
checkpoint | Loose tie wire removed
checkpoint | Lifting secure
checkpoint | Cleanliness of mould
checkpoint | Release for pour signed:
checkpoint | Concrete volume/order is correct:
checkpoint | Cover Up Inspection
textbox | Technician:
checkpoint-no-status | Details
textbox | Test Blocks Made:
textbox | Foreman:
textbox | Mix Code:
textbox | Unit IDs scribed in:
textbox | Docket Number:
label | Mix Code: QQ6013HEB9
textbox | Helix straight/position:
textbox | Signed by Foreman:
textbox | Time:
button | am / pm | am,pm
textbox | De Moulding and Strip out (Test Blocks)
textbox | All lifting usable:
textbox | K.P.A
textbox | Covers lashed down:
textbox | Concrete Strength:
date | Date:
holdpoint | Signed:
checklist | QF027A – POST-PRODUCTION/PRE-DELIVERY CHECK SHEET
section | Details
checkpoint | De Moulding and Strip out (Test Blocks)
date | Date:
textbox | Time:
textbox | Cast Number:
label | Concrete Strength
textbox | MPA:
textbox | Beam Weight:
textbox | Pour Item:
textbox | Product ID:
textbox | Inspector Name:
date | Date:
textbox | Cast Number:
date | Cast Date:
section | Products
checkpoint | 1 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 2 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 3 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 4 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 5 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 6 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 7 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint | 8 - Works Completed & Signed Off
textbox | Product ID:
textbox | Comments/Defects:
label | Refer to Defect drawings attached.
checkpoint-no-status | Other Comments:
textbox | Above Works have been allocated to:
section | Final Acceptance for Delivery
checkpoint | SQE Final Sign off for Delivery:
holdpoint | Signature:
checklist | SQE-020-F-070 - NU Girder Inspection
section | Details
checkpoint-no-status | Details
textbox | Pour Item:
textbox | Product ID:
textbox | Drawing References:
date | Date:
textbox | Cast No:
textbox | Foreman:
section | Pre-pour Inspections: Stressing Strands
checkpoint | Number of Strand and Position
checkpoint | Length Bond Breaks, Sealed
section | Pre-pour Inspections: Forms
checkpoint | Width and Sides correct
checkpoint | Cleaned & Oiled
checkpoint | Adequate Bracing
checkpoint | Orientation of stop ends
checkpoint | Length of set out
section | Pre-pour Inspections: RFG
checkpoint | Cage set up correct in jig
checkpoint | 40mm Cover min
checkpoint | Stirrup set up and Number
checkpoint | Crank Bars secure and in position
checkpoint | Skews correct spacing
section | Pre-pour Inspections: Cast Ins
checkpoint | 200mm PVC Duct
section | Final Check
checkpoint | Loose tie wire removed
checkpoint | Tim's correct
checkpoint | End Steel Correct
checkpoint | Release for pour signed
textbox | Foreman:
textbox | Technician:
checkpoint | Concrete volume/order is correct:
textbox | Docket Number:
textbox | Mix Code:
section | Cover Up Inspection
checkpoint | Cover Up Inspection
date | Date:
textbox | Time:
button | am / pm | am,pm
textbox | Unit IDs scribed in:
textbox | All lifting usable:
textbox | Helix bedded in:
textbox | Covers lashed down:
holdpoint | Signed by Foreman:
section | De Moulding and Strip out (Test Blocks)
checkpoint | De Moulding and Strip out (Test Blocks)
textbox | K.P.A
textbox | Time:
button | am / pm | am,pm
textbox | Concrete Strength: |  |  | MPa
textbox | Name:
textbox | HOG |  |  | mm
holdpoint | Signed: