## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-00021 | [5 empty] | ITP-00021
section | INSTALLATION
checkpoint | Temporary hire tank is in correct place and full of fuel
label | Control Documents: Procedures & Documents - SWMS
label | Control Documents: Acceptance Criteria - STH Project Manager
label | Fabricator: Key - P
label | Client: Key - P
date | Sign/date:
checkpoint | Temporary hire tank is connected correctly to generator and hoses are checked for leaks
label | Control Documents: Procedures & Documents - SWMS
label | Control Documents: Acceptance Criteria - STH Project Manager
label | Fabricator: Key - P
label | Client: Key - P
date | Sign/date:
checkpoint | Existing UST is checked and prepared for recovery of diesel
label | Control Documents: Procedures & Documents - SWMS
label | Control Documents: Acceptance Criteria - STH Project Manager
label | Fabricator: Key - P
label | Client: Key - P
date | Sign/date:
checkpoint | Recover diesel from UST and pump into temporary tank
label | Control Documents: Procedures & Documents - SWMS
label | Control Documents: Acceptance Criteria - STH Project Manager
label | Fabricator: Key - P
label | Client: Key - P
date | Sign/date: