## Checklist Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release
18e293cf-bd29-40a8-90e2-1cb0703ebcc4 | checklist | ITP-000 - Client Pre-Construction Checklist Rev1 | itp | ITP-000 - Client Pre-Construction Checklist Rev1
6b0e7808-d610-4a4a-afc0-1f6054ea2e3b | section | Preliminary Works
52f9d05a-773e-4737-a344-62f18dc7d33b | checkpoint | 1.1 Asphalt - submission of asphalt mix design
0742201d-ba92-5425-824e-9effe9ec9f4c | note | FREQUENCY: Prior to commencing asphalt
6bdd916c-20a2-5cc6-8eba-69c2718cc276 | note | ACCEPTANCE CRITERIA: Ensure the mix design/s have been registered and are approved by Superintendent prior to laying mix.
dd28f456-5766-509c-be21-8b3ef860f561 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09.
8a0e9c85-f724-5283-90b9-ade516922991 | note | ○ RAP DoT letter from production plant
90b0ae6e-8257-5202-ad9c-cce72a60f99a | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from the RAP DoT Letter.
48e8afb1-436f-52f1-a03e-2252c055114a | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
dd8713ba-2667-52aa-8f43-c4d24a60dc8f | note | HP
69e6641b-8c31-50eb-8472-115a07a85063 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
96cbccc7-3e27-5886-97ed-753ad22e9ad4 | textbox | Date Completed:
80164786-872b-4097-ad61-1c431b98e2aa | signoff | AUTHORITY HOLDPOINT
62b27195-f01e-45fe-9a9c-b6b0f25f9af0 | checkpoint | 1.2 Concrete - submission & approval of concrete mix design prior to commencement of project
6c7d396a-9ef8-5775-954b-40c5b767071e | note | FREQUENCY: Prior to first concrete pour
5d8d4e7c-7611-5270-95db-27a11ee150d4 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
23a0d244-8d36-5e5d-aae9-bed30112071a | note | ○ Mix shall contain minimum 460 kg/m3 cement content. Special 50 mPa mix is to be VS502B25MET1 with a suitably flowable design slump agreed prior to construction.
82aa2dac-d666-5430-8538-00f8e632ebee | note | REFERENCE DOCUMENTS: CE-019-ST- 0033, VicRoads Spec. Cl. 503.04
9826c28e-03bf-5d10-b789-9ed24371e127 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design from supplier
6bbd7b3f-1c0a-51b7-85df-c47f836be1f6 | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
8ad61330-a375-53d2-8a2b-6019e9e04b9d | note | HP
e910064d-1ea5-53b2-ad46-954ede12d6f4 | note | RESPONSIBILITY: FH Engineer / Superintendent
673a0b3e-e25b-57f5-839d-a4828383027d | textbox | Date Completed:
9c593e71-bc93-47aa-9beb-6ba8a0002b41 | signoff | AUTHORITY HOLDPOINT
19ec6896-16d0-4d0a-9f5f-ace20bd13a49 | checkpoint | 1.3 Welders qualifications, competencies & work methodology
90e54657-4317-5a3e-9383-d8936d08f011 | note | FREQUENCY: Prior to commencing works
d6add6d9-7879-5ce6-99bd-a60373219ccc | note | ACCEPTANCE CRITERIA: Weld methodology to be submitted prior to commencement of works.
c82af4a1-9f5c-5a6e-961d-cdb0ab894a43 | note | ○ Welders shall be trained and compliant in Australian aluminothermic welding competencies as outlined below;
be389775-cbfb-535f-85eb-4706f956ffb4 | note | – TLIW2012 Grind Rails
98504b95-2a84-59ed-935a-08ca48b30861 | note | – TLIW3015 Weld Rails using Aluminothermic welding process
c901e1c2-ba49-544c-af97-429a01fd7744 | note | – TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
78cabea4-f173-5ec0-a7ba-8f57a6898ff9 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033, Appendix C
a4f98bec-9467-58a3-9852-4566d79eb955 | note | INSPECTION/TEST METHOD: Welding methodology
24ad2731-44f1-579c-b1d5-f18b8adc549b | note | RECORD OF CONFORMITY: Superintendent approval via hold point release
02d1e46c-63e0-5d54-97f6-eb62f587eab8 | note | HP
800e04f4-9a74-5c64-b5e6-952637f1a560 | note | RESPONSIBILITY: FH Engineer / Superintendent
e0a3c985-b786-530a-be1b-9d9719a6cae8 | textbox | Date Completed:
b12c0d76-5e50-4bcf-9724-f4ac8b4f3ecf | signoff | AUTHORITY HOLDPOINT
521dfc33-741e-4ddb-862f-59a9fd5722f1 | checkpoint | Final Inspection
d5dd80a1-7df5-575c-9164-2e653373275b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
2421d75c-4726-52ac-8364-4238fcb2afed | textbox | Print Name:
feb6b65d-2d76-53c2-9d14-b3b2abcef871 | textbox | Position:
37a70ebf-70b9-5c95-861b-de33f94eaa67 | textbox | Date:
208d97a6-0f8d-4b85-9684-956cd5608cb9 | checklist | ITP-001 - Subgrade Preparation Rev2 | itp | ITP-001 - Subgrade Preparation Rev2
05d7d8d5-0ad9-48df-a5ec-15611a502a37 | section | Preliminary Works
b0beb003-faec-42fc-979e-b7b4cd11d62c | checkpoint | 1.1 Check for correct documentation
c0bee3b2-5460-5e82-be91-8f2fa53924b1 | note | FREQUENCY: Prior to commencing any activity
71e9b9af-562c-5fb6-bb05-0189a9b80222 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
1cdab396-bb73-5445-a247-7fabaa3d3d15 | note | – using the correct and complete set of drawings
fd8dc810-b22e-5d2a-bc97-960b1ceca899 | note | – all drawings are the latest revision
5744447f-ac98-5680-8ceb-2e652930cd09 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
99df6035-090a-551f-8bc5-3fe92b4865e1 | note | INSPECTION/TEST METHOD: Visual inspection
eb3d7c5d-14b2-54bc-89d7-121028853bd4 | note | RECORD OF CONFORMITY: This ITP signed off
59b3549a-e87c-5a8b-a16f-98de44219729 | note | WP
6b2c0816-64b8-55a3-9fa4-49f664b2ec03 | note | RESPONSIBILITY: Fulton Hogan
604ac252-26cd-5a40-8301-985d9d621589 | textbox | Date Completed:
baae47ec-8565-40aa-b5e3-07f11342b055 | checkpoint | 1.2 Implementation of all measures and controls
ec075302-8254-536b-ab79-d6f1881490ed | note | FREQUENCY: Prior to commencing any activity
fb0d5c2c-3657-5e78-9e5e-841dbb9d2bf0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
5a68f0b2-591c-5102-9ac5-e94399d1660c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
fc5f5908-5265-5308-a81e-41d43799352d | note | INSPECTION/TEST METHOD: Visual Inspection
84e5833c-ec34-5a16-9b3c-d976bf4edfa7 | note | RECORD OF CONFORMITY: This ITP signed off
dd8d35ef-05f7-5ca4-aaa7-dfdf2a4f34d9 | note | WP
a49dec99-7ef0-50d9-968e-358df9c59495 | note | RESPONSIBILITY: Fulton Hogan
fa9c17e1-0ffd-5fea-a28b-6dd3b9b1e139 | textbox | Date Completed:
faef515a-8ba9-4fee-9f59-2ae0a02a2ee4 | checkpoint | 1.3 Selection and approval of Disposal Site
232fc42b-6bba-5545-a1a9-92108bf0c417 | note | FREQUENCY: Prior to commencing any activity
06b74352-134e-59b1-983d-3e4c25bd4df7 | note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
4cf90a8a-a2ad-5a91-a57b-ca79fc15bb99 | note | ○ It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
d4cf62ea-8ba5-5282-925e-5aac16d3067c | note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
c48d174f-8a34-5297-a3eb-f8d6ef2ec3b5 | note | INSPECTION/TEST METHOD: Verify
986d5402-3bde-51d4-981f-51da257afbb8 | note | RECORD OF CONFORMITY: This ITP signed off
f950e8ae-0f73-5e97-b1b1-e25a65b0d5b8 | note | WP
0b7f6466-49a5-58c8-857a-5ad6d9635530 | note | RESPONSIBILITY: Fulton Hogan
4fdb202d-01d9-5504-ad2b-a9daa0738989 | textbox | Date Completed:
68da4b85-3c8b-4f4d-8eb8-56f868f8ea2c | section | Construction Works
6e337f7f-2983-4a20-9235-4f1fc29c3756 | checkpoint | 2.1 Excavation
3c4e26b3-ad90-5618-9b5d-56df6c1cee92 | note | FREQUENCY: Each lot
a7d83d93-f6a0-5f87-8366-ace3dc53cf06 | note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task.
1d9f9d4b-4119-5eb9-a6bf-3a41e0343945 | note | ○ Excavation operations shall not disturb areas outside the limit of works
f75cad31-e0e3-51b2-8762-3fee3103412a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4.
683f5f03-33a3-5f73-8f73-5156a04b2613 | note | ○ Subgrade Preparation Work Procedure
2ba15054-f04a-5898-a804-38c58dc7feef | note | INSPECTION/TEST METHOD: Verify
5280ab79-b700-51de-a0b4-c0be0feace60 | note | RECORD OF CONFORMITY: This ITP Signed Off
8cb0e5eb-c001-5a3b-ab08-1874cc75f42b | note | IP
f9fc4c70-2070-51c0-9e19-a7cc7968df06 | note | RESPONSIBILITY: Fulton Hogan
da90da81-95c2-58c1-ace9-036caf30efcd | textbox | Date Completed:
0fde1964-353f-4b37-a145-233f3687f426 | checkpoint | 2.2 Reinstatement of bonds
2c4aed3c-1e9d-552c-865a-0320e3e3e8ad | note | FREQUENCY:
64a1d4da-1ae1-51cc-944c-f29a7dc04f89 | note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
933a5faf-3c86-5ec3-b162-d9cf6bd1f3dd | note | ○ All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
ba396aba-6a74-541f-ae53-fa9ebd85dfeb | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
d18f3718-b192-5bb7-a20a-2a486626d51a | note | INSPECTION/TEST METHOD: Verify
8a7b0546-2e95-5481-bbef-32fa17fa91ba | note | RECORD OF CONFORMITY: This ITP Signed Off
478b4b15-921b-5c10-b9a5-29f7056b8995 | note | IP
58473d2b-7cc7-5580-810a-da462d022b51 | note | RESPONSIBILITY: Fulton Hogan
97f63a78-92f2-51f1-abc2-5da80aaa00d4 | textbox | Date Completed:
20837c13-2dbb-449a-95ce-60ce49820d84 | checkpoint | 2.3 Inspection of Subgrade Material
a4371af4-78ed-5a9a-8b7b-f3469abb677f | note | FREQUENCY: Each lot
6abf3d98-038c-500d-bbb6-80352a3eca3a | note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
aa6c86da-94a2-5a98-9c9b-f1a54465be94 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
b6982999-830d-5bdf-93d5-ce7bec1774a8 | note | INSPECTION/TEST METHOD: Verify
35f64272-de67-5463-8604-e362eac67590 | note | RECORD OF CONFORMITY: This ITP Signed Off
50a152a1-1afd-5dcf-8fdd-54f9e923d226 | note | HP
828e4d7e-d572-598b-ae3e-ffe543a50041 | note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
1b4c9914-8a64-5354-9966-fbf758ec6a0d | textbox | Date Completed:
bc23e38b-3cf0-4cc5-a25a-32d8dd2f66a0 | signoff | AUTHORITY HOLDPOINT
fbcf6c4a-99a0-410e-977b-95aa5c8cee01 | checkpoint | 2.4 Width and Level conformity
18fa16b5-cd15-5da7-94de-d30fa91240df | note | FREQUENCY: Each Lot
cdb6a644-49ca-5d5d-9fd1-31385ba21386 | note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge.
abeee401-75ba-53c9-ad5e-574e1862d8ed | note | ○ Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
0327cc6f-94eb-5980-a120-0aaeea50da2f | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
2e385f80-63d8-577e-a354-f656f0b3aa35 | note | INSPECTION/TEST METHOD: Survey Report
0ed3a30f-5f37-5bae-8897-10ad7fda8961 | note | RECORD OF CONFORMITY: Survey Record
e6113173-853e-563d-8a36-fb64e1392c19 | note | IP
fd2b06f2-58d9-56fd-bd3b-647918e08724 | note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
c0b1d583-cf0a-5e72-9a44-bfd8200b94c5 | textbox | Date Completed:
8e5b52be-e566-4ed8-967a-ca15fe42027d | checkpoint | Final Inspection
998c01ed-0e51-54c1-b514-7fcdd31d382f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9c2d2a49-8199-55af-b90d-cdd59ddf3489 | textbox | Print Name:
a11fd962-4f46-564d-9f0f-0d0b6d5c4324 | textbox | Position:
5379af28-58c1-5a95-948b-891c212b1cb0 | textbox | Date:
c56f5f03-14c1-43b0-a8b6-d8f07fbc42a3 | checklist | ITP-003 - Electrical and Communication Conduit | itp | ITP-003 - Electrical and Communication Conduit
4ed622bd-5e5c-4b6d-bc3b-cdf6cd83e3dd | section | Preliminary Works
749c96f2-ea46-4664-85d8-4ad7b7c683e5 | checkpoint | 1.1 Check for correct documentation
aa36a642-8ae8-507b-80bd-d1f0cf490095 | note | FREQUENCY: Prior to commencing any activity
e2986e4d-b800-54a9-aa78-46168e866981 | note | ACCEPTANCE CRITERIA: Employees and sub contractors shall be issued with the most current and complete construction drawings
a5cdd2f1-dd46-5c84-813c-c909c031bb24 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c5360b30-7acb-5669-bb40-485268a3c1b4 | note | INSPECTION/TEST METHOD: Visual inspection
3c987975-8636-524b-96c2-b5bb80518388 | note | RECORD OF CONFORMITY: This ITP signed off
9a9a89b0-175e-5980-9be5-dcfbe0ed0416 | note | HP*
fb3c0ed3-e58e-5177-97a7-41fe4449397c | note | RESPONSIBILITY: Fulton Hogan Engineer
11a0be0d-60fa-5ba6-a815-e251d8c79f80 | textbox | Date Completed:
60625d3e-eac9-4669-a83a-8ec6212e6166 | checkpoint | 1.2 Implementation of all measures and controls
30ca7d80-6d61-5d5c-bd53-41f2ae5a1c1f | note | FREQUENCY: Prior to commencing any activity
feea03fb-4207-5a9a-9a7a-73c1cfbf7eea | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
4c32535b-b21a-5017-966f-0b590e752720 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
1a7186e5-37a2-5822-9e47-55bbb5d5e139 | note | INSPECTION/TEST METHOD: Visual Inspection
d7f2f5ae-79d3-52cd-b739-6db345681796 | note | RECORD OF CONFORMITY: This ITP signed off
44e50b85-061e-5e4d-81d3-16124c2ea272 | note | HP*
23e1378f-57a2-525a-a50d-ab74b0d97385 | note | RESPONSIBILITY: Fulton Hogan Engineer
095a69d0-f8c0-53d5-8bbe-1a031197962c | textbox | Date Completed:
d15fef9a-67b8-4de1-bf6c-0a613763979d | checkpoint | 1.3 Materials
bd335d2b-cf13-53ce-be91-5865a55afa0c | note | FREQUENCY: Per Batch
e50879a1-d6aa-5fdb-a0f5-4d837a74dd57 | note | ACCEPTANCE CRITERIA: Electrical supply conduit to be Orange and rigid HD UPVC of sizes as required.
f37ae4a6-cbb4-5177-a275-d29fc6d9bac1 | note | ○ Communications conduit to be White and rigid UPVC of either 32 or 50mm size or larger as required.
bf6487b2-c95a-54df-a19d-22ec891104c2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.1, AS 2053
bcb3cfb5-6659-56b6-8830-5a209c58a1e9 | note | INSPECTION/TEST METHOD: Verify
e221d3e9-a346-5ad1-9d20-30765eda2062 | note | RECORD OF CONFORMITY: This ITP signed
8a6118ba-b473-55ca-b18d-12adf1f511f2 | note | HP*
9be039ff-e1f7-5cef-8add-0805587abb2f | note | RESPONSIBILITY: Fulton Hogan Engineer
a97955a2-eeb6-57cd-8fd7-2fbd492baaec | textbox | Date Completed:
de42c922-dd86-4ca2-afbb-1e6759173a5f | section | Construction Works
3c36be92-dd6b-4163-9c36-aeb15ebe904d | checkpoint | 2.1 Survey set-out
ddb4f53d-5d7f-55eb-a0f0-bd31f1bc7ad9 | note | FREQUENCY: As required
d744990d-2ab1-5b21-aa51-9450e2b2f74e | note | ACCEPTANCE CRITERIA: Work is set out in accordance with drawings.
496e6d4d-9a14-5160-8288-5eb1a22bf29e | note | REFERENCE DOCUMENTS: Work procedure
03aa06ff-53c3-557b-8c58-b483667c1624 | note | INSPECTION/TEST METHOD: Verify
4de29d3d-74fd-51be-8633-a3834a33f49e | note | RECORD OF CONFORMITY: This ITP signed
5fefee12-522e-5903-8d2d-77e9d869379c | note | HP*
a97cc0dd-a9af-50e6-a43a-f1c993911ca3 | note | RESPONSIBILITY: Fulton Hogan Engineer
5321c8c0-9bc6-58eb-8a4b-690cea0defb5 | textbox | Date Completed:
7235eaa9-8658-453b-9adc-689614d14e21 | checkpoint | 2.2 Excavation and Trenching
ddb75c07-a1ab-5fdf-87ea-eec68b22132e | note | FREQUENCY: Prior to Installation
15f767a2-1524-59f3-9ddf-c40e47fe719e | note | ACCEPTANCE CRITERIA: Minimum cover for underground conduits shall be 600mm
5c7dd19a-2ecd-5b7f-9d93-31d72f6f36c1 | note | ○ Open trenching only permitted in unpaved areas, line of trench to be at right angle to the track
650791b7-3645-52b9-a0ae-336f39f6b903 | note | ○ Trench shall maintain a minimum clearance of 300mm from all existing services where possible
a79ce64f-83df-5bde-be1d-40c8155c9181 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5 & 4.2.8
5fac0b12-ea22-58aa-9cc5-b632ca630b12 | note | INSPECTION/TEST METHOD: Verify
32c44a05-e332-5779-9167-69a8232c8ae2 | note | RECORD OF CONFORMITY: This ITP signed
7adcc512-0e3b-5aaf-a6de-28b7be7f1de8 | note | WP
40d2c7f8-62e7-5cd2-88fc-6193058086df | note | RESPONSIBILITY: Fulton Hogan Engineer
4d2d8126-2b60-54d7-be09-563d4bc29863 | textbox | Date Completed:
44a2cda6-b991-4de6-aea3-ae706bffb946 | checkpoint | 2.3 Installation of Conduits and pits
4184a1fd-2784-5fb1-ad42-44891a91ca04 | note | FREQUENCY: Each Lot
366fed38-1c45-5693-ad40-5e1be800c43f | note | ACCEPTANCE CRITERIA: Conduits in the same run shall be spaced 50mm by using clean sand to pack voids
984058c5-5cae-57e9-aed6-d009ab7dcca5 | note | ○ Conduit shall be embedded in not less than 50mm sand and covered by >50mm - 75mm< sand
93920e38-d864-5e88-beb2-afaa4272226d | note | ○ Mechanical protection shall be provided by installation of polymeric cable or cover strip of thickness not less than 3mm, and of a material equivalent of UPVC conduit complying to AS 2053. Protective material shall be placed not less than 100mm above the conduit, and shall not be less than 150mm wide.
1a0dc72e-c3eb-5b2a-8ba0-2b11df47c4ae | note | ○ Conduits shall be joined male to female ends and sealed with approved adhesive immediately prior to joining.
2372717f-c6e4-5146-9a1f-4beb2ecd0560 | note | ○ Conduits shall not be subject to construction loadings
f2617239-c202-5c48-965f-b9f9034a2ce2 | note | ○ Bottom of lowest conduit shall maintain a minimum 100mm above pit floor
b34de121-a443-541a-bb26-975115af8e2c | note | ○ Conduits shall be capped with UPVC electrical caps
c3b41b8f-2220-5915-bcc0-ba01a0e3cdc5 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4
bde94813-9832-562f-9d46-2806dd5d85f2 | note | INSPECTION/TEST METHOD: Visual inspection
e079ca3f-800e-5901-a870-155a14afe737 | note | RECORD OF CONFORMITY: This ITP signed
73f2364b-557f-59a0-9004-c14741f5d5df | note | WP
b9c0b044-9714-545e-871e-24f9815f3807 | note | RESPONSIBILITY: Fulton Hogan Engineer/ YT
6c8a2269-61f4-5fa8-b2ac-29c888c2611c | textbox | Date Completed:
765ecf42-2a75-4911-9eec-3794172e3a40 | checkpoint | 2.4 Inspection of conduit installation
8180d017-48a8-5e6f-b157-83000d18b37f | note | FREQUENCY: Each Lot
5de8c645-90b1-55be-9cb2-a9e90ae1da1c | note | ACCEPTANCE CRITERIA: Laying of conduits and installation of pits shall be inspection by superintendent and conform to design drawings before any backfilling procedure is to commence
2028124e-af93-5049-800f-c2e09911c4cd | note | REFERENCE DOCUMENTS: Work procedure
d12bc488-aea2-5e9f-ac2b-0dd97ba55089 | note | INSPECTION/TEST METHOD: Visual Inspection
fc64fbaf-b13c-560a-8a83-72d43f7f08ef | note | RECORD OF CONFORMITY: This ITP Signed
38d8c041-90bc-5f67-a157-4ff69d95ab08 | note | *HP
684ac279-be94-5da4-8296-39f3b8e79eb3 | note | RESPONSIBILITY: Fulton Hogan Engineer/YT
65225549-5284-56a4-8731-a30f2a9b2007 | textbox | Date Completed:
8a348a4f-cdfc-4d09-a532-7cb05782dec2 | checkpoint | 2.5 Back Fill of Trenches
3387d5d2-9329-5559-9fe4-40cb207eea1b | note | FREQUENCY: Each Lot
1cdc2e3d-ac7a-59e2-8a8e-69b2467e5c06 | note | ACCEPTANCE CRITERIA: Backfilling (for trenching or road crossings)
2c83a0e9-593a-568a-80f0-0c32bd95c1d6 | note | – conduit trench shall be backfilled above marker tape with crushed rock or suitable excavated material and compacted to 90% standard compaction 150mm-200mm below sub base level, the last 150mm-200mm shall be compacted to 100% standard compaction using handheld mechanical plant
3a02f05d-f4ca-5412-8137-98750b13c34a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.5
29f9a8a5-cc37-5892-a047-af4509fce499 | note | INSPECTION/TEST METHOD: Verify
7e01426e-287c-5a0f-8de5-d4052bb8270d | note | RECORD OF CONFORMITY: This ITP signed
7b2fe6c2-9c64-5f89-b8ce-777ada9f87c7 | note | IP
a52b1c43-7c7b-577f-a2e0-5d420dc092b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
251b29f6-d257-5fa8-979a-7eda493957e8 | textbox | Date Completed:
5c376a38-812a-42f0-91f9-49cfa66d5ec2 | checkpoint | 2.6 Installation of Draw Cords
86c46da5-944d-5fce-a5f9-c1574fb7f3b5 | note | FREQUENCY: Each Lot
37ba9354-ac55-5e9b-ba6c-1215e7c5590e | note | ACCEPTANCE CRITERIA: Draw wire shall be provided for each conduit, with extra 3m length at each pit, material to be used shall be 6mm 'telstra rope'
e5db385e-2d8a-5f67-b805-83bd32d4ac1a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.4.6.2
aa0a4d80-d7d3-58be-ae92-49dd71ecad58 | note | INSPECTION/TEST METHOD: Verify
666717db-a4c8-58b6-811c-c06c6fc9e5d3 | note | RECORD OF CONFORMITY: This ITP signed
4837a90f-4262-54e7-acbf-54e343636074 | note | IP
9e185dfd-40fe-5f82-b944-f63fc16e03ce | note | RESPONSIBILITY: Fulton Hogan Engineer
8a96ba13-6269-5ec8-b234-cf2bddbfbabd | textbox | Date Completed:
82c07766-0e3c-459a-bd27-75b9e1d7624b | checkpoint | 2.7 Compaction
ee66425d-fc95-5f5d-845d-51b15f79c058 | note | FREQUENCY: Each Lot
ec7c7087-dfbc-56ba-8d1a-a03aaf446b3e | note | ACCEPTANCE CRITERIA: During compaction optimum moisture content of bedding and select fill is within 85% to 115% as provided by suppliers
706de1f9-6000-5b5f-92c6-c50bebb39ce0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.2.8
98821345-cb21-5f36-a4a6-2e1e2462226b | note | INSPECTION/TEST METHOD: Verify
e6ebfc44-14ad-5c00-805e-721e9603c52c | note | RECORD OF CONFORMITY: This ITP signed
8e5bef8c-3dd9-5941-8a9c-b285f5ba4093 | note | HP*
5b664a82-e6f4-57e2-a049-12bdf3d23e50 | note | RESPONSIBILITY: Fulton Hogan Engineer
aa0c9023-c200-5ae5-9b1a-59931305df8c | textbox | Date Completed:
5bc7aa58-1958-4d5b-963e-103f2bae6cfb | checkpoint | Final Inspection
8ab50fd4-2d2a-597f-8c5f-484b6f876b8f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
62411fcf-f988-59a9-8f6a-2de00eebfff2 | textbox | Print Name:
b824b828-35de-5805-9cbb-7f799a264040 | textbox | Position:
bde662bd-464f-50c2-b213-9923575d4c0b | textbox | Date:
a016c9f2-cabf-42c1-8e74-7e8dcfcf76d3 | checklist | ITP-004a - Class 2 Base Course Placement Rev2 | itp | ITP-004a - Class 2 Base Course Placement Rev2
0a5e806a-f2e6-4e38-86fa-ea6a4e798494 | section | Preliminary Works
c59f878b-044c-44bd-a3fb-3308cd757a62 | checkpoint | 1.1 Check for correct documentation
28c45dce-9cbf-5e62-bc03-f3c65edf7543 | note | FREQUENCY: Prior to commencing any activity
0ea84f1f-19a7-5a89-97a5-1dbded30c91e | note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
3bf0ad18-b71e-5738-ab23-bb8c89280ff6 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
98c85aca-d4cb-5ad6-9a2b-4ceb0deddb64 | note | INSPECTION/TEST METHOD: Visual inspection
9a6bb02b-49cd-56de-bbf8-242dbd560771 | note | RECORD OF CONFORMITY: This ITP signed
d6d4ea1e-11a5-56a4-9a19-32d326e45360 | note | HP*
679620ec-23ab-5227-b778-1f491580f79f | note | RESPONSIBILITY: FH Engineer
ed790359-8695-5d23-8d94-2087be666319 | textbox | Date Completed:
0d0af1a1-13c7-471e-87bb-9880f116f4b7 | checkpoint | 1.2 Implementation of all measures and controls
1e6b5608-f697-5c02-b2c6-bc79615cb637 | note | FREQUENCY: Prior to commencing any activity
aea1ff3a-e235-5cfd-845c-07553d3487e9 | note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
a2bdc6ab-eb44-558f-ad98-9902f8cc9452 | note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
04f4282e-8ea2-59e3-8ba2-bf3a15eb6971 | note | INSPECTION/TEST METHOD: Verify
f352c110-5a1f-52c9-8f0b-d0a66e2e5bc6 | note | RECORD OF CONFORMITY: This ITP signed
bec0d906-20a6-57fe-a2f1-15e56ea2333f | note | HP*
1ab07ec5-f684-51cc-9685-feecb7f3d8ec | note | RESPONSIBILITY: FH Engineer
44f4414d-5663-5584-9d09-78417b6ed1cb | textbox | Date Completed:
4f92ce6c-313b-4791-b699-31b67cd8d707 | checkpoint | 1.3 Material Compliance
55278b14-3af0-5f6d-9c1c-1d18e162ca90 | note | FREQUENCY: Prior to commencing any activity
256a2bd8-eca9-5c11-86e5-a92286625a1f | note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
5bfd8576-2533-57b3-8c93-8356664664fc | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ee5a8e72-42bd-5d1a-ac2c-109365af351a | note | INSPECTION/TEST METHOD: Document Review
580f766d-4150-501f-9a94-b7f53dab14b5 | note | RECORD OF CONFORMITY: Test Reports from supplier
022b7788-4f10-5219-a555-48a0d67b0c47 | note | HP*
cdf28de2-cfac-591d-888e-cb3bff8140e7 | note | RESPONSIBILITY: FH Engineer
f915a2a4-5179-5f93-a0f2-fefe89a08956 | textbox | Date Completed:
63bd3697-c24f-4e7e-877e-f6bf9edab56c | section | Construction Works
0d595c55-257a-49e5-b71f-5913640ee425 | checkpoint | 2.1 Sub Base
17082c0e-0df1-5b29-bf5f-26bf200321c1 | note | FREQUENCY: Each Lot
321df8cc-bb11-5c89-9b3c-0ae31f92f056 | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
0a7143fc-83e8-5067-ac89-0720174a8844 | note | ○ ITP-001 HP for subgrade inspection signed off
ece7231d-942c-5ecd-8904-62a38e8e1c9c | note | REFERENCE DOCUMENTS: VicRoads 173.03
fb2bf03f-6ac6-599d-96c5-eac8d88c8100 | note | INSPECTION/TEST METHOD: Inspection / Test Method
7b492ae4-46e4-5c79-b604-7c525288fadd | note | RECORD OF CONFORMITY: This ITP signed
b47ea351-1f11-52c9-816c-423b117b0ab9 | note | HP*
cc84d4ca-1cd0-5fc6-8144-2d4b8c0b8185 | note | RESPONSIBILITY: Fulton Hogan Engineer
cde55ac2-2548-56b3-8fed-2f6cd8fddd0d | textbox | Date Completed:
899ff0cb-4c3a-49e7-aec5-962a255f75e4 | checkpoint | 2.2 Spreading material
d657b1da-14f9-50b0-9650-88cbdc151318 | note | FREQUENCY: Each lot
650fc7b3-cd32-5ef5-a07c-dbd6bd57abd5 | note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
6a4d0d98-9343-5b14-835c-2128d6fcbf40 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
b8d0cbae-07cb-56e1-8748-f87d137678b2 | note | INSPECTION/TEST METHOD: Visual Inspection
bf9a5b51-68c8-56c0-8fce-92682d1f84c3 | note | RECORD OF CONFORMITY: This ITP signed off
ba4e4dea-f442-5109-8e20-7ec66b336a54 | note | IP
4cbf5078-b0ff-55cb-9902-7b618a1fa9a0 | note | RESPONSIBILITY: FH Engineer
f2760020-550d-5b17-9a19-4091682490ca | textbox | Date Completed:
60dfb811-ab1a-40f3-a400-c4129a82a534 | checkpoint | 2.3 Compaction
bb623d41-ebf1-566d-8705-6fcb5d5ffef2 | note | FREQUENCY: Each lot
bbb030f7-a2f5-5e76-a28d-71af0c93e678 | note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
b3cafb93-e995-525b-9288-0bfed0818f50 | note | ○ Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
5be4f7a9-f25f-5f29-9564-aa45ede39bad | note | ○ Compaction testing shall be carried out once per days production and shall comprise of three samples
5807c4ce-c08f-5ea1-a98f-de656d737b1b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
19415838-8b4c-515f-b5a4-e7ca738cd82e | note | INSPECTION/TEST METHOD: Visual Inspection
75daeecc-b41b-5d92-89fb-dc837f177d02 | note | RECORD OF CONFORMITY: Test Results
2ed873f1-86ae-5e5f-bb4c-ffd4dd11d7bc | note | TP
21f8b87b-743b-55a3-8a0c-88da2a3454ac | note | RESPONSIBILITY: FH Engineer
b08281e5-765a-5623-bbbc-ba061abaac19 | textbox | Date Completed:
b6fa51a7-7f3c-48ff-b8e3-8918db33799d | checkpoint | 2.4 Level Checking and Conformance
90870088-6472-50db-a12b-87b8bb0c7094 | note | FREQUENCY:
637c0cea-151a-561c-8e1c-a48a16795a8d | note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
df50b359-2e5e-5eb2-b2ac-4b5f8a0b9139 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
e94f7514-3a66-5388-9168-7439dd11b1fe | note | INSPECTION/TEST METHOD: Verify
88b03a21-159b-51f3-8c5f-5e82050602cb | note | RECORD OF CONFORMITY: This ITP signed off
37658f6b-14d0-511a-9e55-8209dd4023dd | note | IP
063fc235-0588-5111-86d7-05e92dd50c8d | note | RESPONSIBILITY: FH Engineer
c4ffc17b-e55a-5b89-950b-3f74b58ccf2e | textbox | Date Completed:
1dfe7a9f-326f-46e8-980b-0b0bc9765cbb | checkpoint | 2.5 Finished surface
2d9a4b70-f096-54bd-be92-1a797570fa29 | note | FREQUENCY: Each lot
a8a3980c-e8ca-52c9-b84a-9b3c538e42d0 | note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
703cd3a1-6912-5da0-825d-e4a628beb33b | note | ○ Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
548c6d9e-c2f1-516e-8184-4b34dd4d7b42 | note | REFERENCE DOCUMENTS: CE-019-ST- 0033 CL4.2.2.8
3ad52129-99bb-5d2e-a7a1-a8d09fd96e7f | note | ○ Contract drawings
29cf7e42-7c09-5cee-ae05-dadd221402c9 | note | INSPECTION/TEST METHOD: Visual inspection
5bc87e8c-c7b7-5c0b-9e8e-9e85877be7c5 | note | RECORD OF CONFORMITY: This ITP signed off
f8bfd083-dde1-5d84-8f74-32628d183fd2 | note | SCP
d3695421-b0ed-5d24-9905-304f2ecee289 | note | RESPONSIBILITY: Surveyor/FH Engineer
b2cbc70b-bb90-5b5d-83e6-a9c90a1fe58b | textbox | Date Completed:
67f5fe81-a0bb-4ff0-8996-55e6ee5fd3ab | checkpoint | Final Inspection
f254ecc1-924f-592d-a8c2-31237de64e22 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
775d5990-c389-5eda-b142-68d6cc864354 | textbox | Print Name:
2dcc84b0-f732-567b-88a3-9f916e7d1db4 | textbox | Position:
d8200955-665e-5e81-b881-bae61d2d2b6f | textbox | Date:
b89a591b-8f2e-43c3-8096-328089874651 | checklist | ITP-004b - Cement Treated Crush Rock Sub Base | itp | ITP-004b - Cement Treated Crush Rock Sub Base
db2752a9-ee00-4b10-8046-5e320f96317f | section | Preliminary Works
70d832b5-4ca2-44dd-9c64-7b61dba6df2e | checkpoint | 1.1 Check for correct documentation
cc22332c-baa5-56d3-8067-913a9b9f5293 | note | FREQUENCY: Prior to commencing any activity
0f7c4279-c7da-5965-bb14-88a345fd7f77 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawings
29d9ede7-ea14-5ee8-ad3d-0e7b2975fafa | note | REFERENCE DOCUMENTS: Drawings and drawing registers
5ff14dbf-6d4b-5451-a4e1-2cb2fbd9d967 | note | INSPECTION/TEST METHOD: Visual inspection
9ee8a956-497e-5cf3-9fe5-5a11f853a482 | note | RECORD OF CONFORMITY: This ITP signed
a577daa3-7345-5b6e-a075-e7e760a925f1 | note | HP*
34e58a28-4e57-555f-b122-beb5216f30fb | note | RESPONSIBILITY: Fulton Hogan Engineer
98de9a7e-98d3-56bd-830c-b4d036e33b4a | textbox | Date Completed:
05246063-8fc3-4e91-9876-4e50be7ab07f | checkpoint | 1.2 Implementation of all measures and controls
2dfb599b-b8be-573b-b13e-d17ca8303c18 | note | FREQUENCY: Prior to commencing any activity
bd142861-8be3-558f-aac1-2414b5fe901e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
5007d75a-2006-57c0-9ad4-5ca4da379b4c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
379012c8-68a0-56ff-98b4-b52bd6f55c42 | note | INSPECTION/TEST METHOD: Visual Inspection
95f93fb2-4456-5bb2-84a4-50bd5fc299a8 | note | RECORD OF CONFORMITY: This ITP signed
dd69790c-fef0-52b6-91b0-bd5979b54ba7 | note | HP*
9629fbd0-408f-5543-a359-b24641ff385f | note | RESPONSIBILITY: Fulton Hogan Engineer
58ade49b-e492-51a8-b16b-a0c9f42e13a1 | textbox | Date Completed:
1bce4954-17f1-4f6b-bbc4-44001ad436d9 | checkpoint | 1.3 Confirm CTCR is Appropriate Mix
8a7b0cbf-ed8e-5714-854f-d9447e5c50c3 | note | FREQUENCY: Prior to commencing any activity
d8aad07e-1778-5040-b148-792c72c79d30 | note | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
cbb844b0-25ad-5a7a-aa71-4b8da3cad012 | note | ○ CTCR shall be tested in accordance with 815.141 by supplier
010b6e2d-96af-50df-afbc-19701fb6b933 | note | REFERENCE DOCUMENTS: Design Mix
b47ccce4-11db-513f-9352-21cca4b3ab88 | note | INSPECTION/TEST METHOD: Inspection
7fbb62ee-2515-53cd-b12e-af0c8eff17f0 | note | RECORD OF CONFORMITY: This ITP signed
b31f6aa3-0fcf-555c-b901-4a6e30d6081a | note | HP*
c9aa18fd-7a2f-5d6d-bc23-79dac169f79b | note | RESPONSIBILITY: Fulton Hogan Engineer
d25ba16e-4ce4-5ef6-b15b-d4e98be0f5b4 | textbox | Date Completed:
07f47432-807b-4974-a572-b9c9a9a6bc8b | section | Construction Works
640d8368-c32d-4e40-8213-355dea94e8b4 | checkpoint | 2.1 Sub Base
e82d58f7-c27e-5839-9ea1-c6d26659272b | note | FREQUENCY: Each Lot
c846605d-2ff1-5e01-833d-20b9e6741597 | note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
88d71f65-d512-545b-9fd5-b8307c626a18 | note | ○ ITP-001 HP for subgrade inspection signed off
2fb62c91-7432-517b-8c51-03a68bc570f3 | note | REFERENCE DOCUMENTS: VicRoads 173.03
2ab301ee-2ff9-5d1d-8604-306782796b5b | note | INSPECTION/TEST METHOD: Inspection / Test Method
6207be62-e0bc-5424-a26e-f31da36bd54d | note | RECORD OF CONFORMITY: This ITP signed
5b8a3020-b8b9-5dc6-9c7f-0a2a8cc318bb | note | HP*
104e6fcb-6837-587e-8022-849e2be5955b | note | RESPONSIBILITY: Fulton Hogan Engineer
65d67b0e-6a36-53ca-b078-1df7bf7b3489 | textbox | Date Completed:
eac54264-4bf2-4ec5-8d48-dc8dad18f451 | checkpoint | 2.2 Moisture Content
b57b1e41-1214-59b6-afb0-457dd6f90cd3 | note | FREQUENCY: Each Lot
aa27f847-56dd-516e-bfa3-304ba8dabc2f | note | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
4049de71-a38b-5b99-a98d-079fd5cd201a | note | REFERENCE DOCUMENTS: Vicroads 306.05
b378c189-d0ff-5578-b879-91d7f5cd0c9b | note | INSPECTION/TEST METHOD: Inspection / Test Method
c9af8c9f-1c37-5b8c-a25d-a1730cf7ef8d | note | RECORD OF CONFORMITY: Record of conformity
05b41387-e2e4-56e1-a2d0-78164057281b | note | IP
a307ee60-60ca-5be0-8e10-81d4ff824cb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
7df1e17d-69f5-5f8a-9ca1-db708fcd3870 | textbox | Date Completed:
9470e95f-1897-434e-9676-c000ad9aa7f0 | checkpoint | 2.3 Jointing
874a663c-fa7c-5f9d-b225-3f40011476da | note | FREQUENCY: Each Lot
0ccbb9b7-ef99-5fda-8548-cb9222cc9bd0 | note | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins
c1a0d56c-e53b-5792-955c-8bbcb6510d91 | note | ○ Transverse joints in adjoining paver runs shall be offsset by >2m
42917fa7-5b38-51cc-b5d8-4768829e2130 | note | ○ Longitudinal joints shall be offset from each layer >150mm
b93e57d1-2321-53a6-9e2c-a24f0c3af36a | note | ○ Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
abeacd30-550b-5b5d-90c9-415ec326f391 | note | REFERENCE DOCUMENTS: VicRoads 306.08
e6352930-8102-564b-9321-76f1c8b277d1 | note | INSPECTION/TEST METHOD: Visual inspection
88150acc-d757-5356-acd1-e3e0653c7df5 | note | RECORD OF CONFORMITY: This ITP signed
11266457-375c-587d-a214-79f725624be0 | note | HP*
af515aa2-08a1-5e44-ac46-d8b0aaf804b0 | note | RESPONSIBILITY: Fulton Hogan Engineer
04f50cc1-153b-5d17-821e-72be88c276ba | textbox | Date Completed:
8e9f2de3-1f09-4bce-8b6e-b4b68c242317 | checkpoint | 2.4 Conformity with Drawings
80daab32-3597-558c-a4dc-60860419a8c5 | note | FREQUENCY: Each Lot
a4b336c1-cf4f-59b6-9762-1ae2ff5470c2 | note | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
b0bbad1e-4f42-52b3-b1ad-48184cd5fbe5 | note | ○ Surface of sub grade shall not lie more than 12mm below a 3m straightedge
7f115949-0da2-50b0-b73c-53b19f488a31 | note | ○ Subgrade height shall lie within +15 to -25mm
a0218b2c-8ccf-5592-91fb-a62c02ca5b8e | note | ○ Sub base height shall lie within +10 to -25mm
b338f101-73ed-5294-b3a9-364d95015c6e | note | REFERENCE DOCUMENTS: VicRoads 306.03, 306.11
f1da4813-4bb9-59fe-98bb-8ca904f91a6e | note | INSPECTION/TEST METHOD: Visual inspection
26d1e872-7bc5-5922-aada-9cb15b623775 | note | RECORD OF CONFORMITY: This ITP signed
b96052be-acc8-54d0-aee9-23323ed14bbe | note | WP
a25737ba-9e01-5c75-b761-e7880e07bb2d | note | RESPONSIBILITY: Fulton Hogan Engineer
9f710c31-904c-5c29-a1f8-8467c12ff35a | textbox | Date Completed:
8ddd8d2f-a239-444b-b5a3-5f038d232a36 | checkpoint | 2.5 Curing
a5247669-43b5-554d-9bb4-92cdc1e42ee8 | note | FREQUENCY: Each lot
7e83417c-8512-5278-85a3-94d2f8d8d13d | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
18d2882f-aa4d-5aa5-a447-72001f9f278f | note | ○ As per VicRoads, 4000m2 shall be maximum lot size
8d4283e0-a9f0-5212-8b42-4397e056cec2 | note | ○ No trafficing before 24hrs unless approved by superintendent
1b8e35f6-d650-5da7-be95-1d0aff042e1e | note | REFERENCE DOCUMENTS: VicRoads 306.11
addabe3d-3166-5e98-8fc6-f6571f76e4b6 | note | INSPECTION/TEST METHOD: Visual inspection
ddd3984a-7ba6-5be4-92f7-47793e373e95 | note | RECORD OF CONFORMITY: This ITP signed
057b8f2f-b3f6-59a3-ab9b-0f0124598947 | note | IP
1b58c74b-9910-5238-962e-858abd3d47c4 | note | RESPONSIBILITY: Fulton Hogan Engineer
b269a873-b66c-56fe-b67f-a2589f3e99c1 | textbox | Date Completed:
8b5ae371-7a6c-4e5c-9deb-e914d13fdbcb | checkpoint | 2.6 Compaction Testing
a345262b-03a7-5683-bb3a-eae5b4cf1ee4 | note | FREQUENCY: Each Lot
d725f0a8-8782-5e2f-9b03-0e9ccb0a5b8c | note | ACCEPTANCE CRITERIA: CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
5722d32b-0a64-568d-8604-ce28616f5b59 | note | ○ At completion of compaction, any segregation shall be rectified
208cd2ce-a349-5407-b6aa-8fbefc793126 | note | ○ >500m2 96% modified compaction 6tests
e5660897-0f0a-5671-b845-fda77e2e3620 | note | ○ <500m2 98% modified compaction 3 tests
bb78b016-418d-560f-883e-7e8449aa2f28 | note | REFERENCE DOCUMENTS: VicRoads 306.09, 306.11
67a32351-d7a5-522e-8e59-71946cf0903a | note | INSPECTION/TEST METHOD: Visual inspection
c490addb-54dd-5208-9644-098b0012dbd1 | note | RECORD OF CONFORMITY: This ITP signed
64bb1548-4d09-5c37-8cb7-80de581f3766 | note | WP
42116288-47a2-531e-9257-442553131971 | note | RESPONSIBILITY: Fulton Hogan Engineer
a30529e5-3e04-50d0-8a7a-6b142d7bb7f9 | textbox | Date Completed:
85d27e93-3036-4d55-b37a-a7e7eb972755 | checkpoint | Final Inspection
412d506b-05d6-50b5-b4ec-77bee5cacfb4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4c39d46e-414f-5dba-8c63-c0bbdecf287b | textbox | Print Name:
d0ea1474-71b0-5ef9-ad31-786927965cd3 | textbox | Position:
b49b0664-eae8-57a4-9287-a1b4895516f8 | textbox | Date:
ca46ba52-3bd3-48f1-9453-3fe69020a2cb | checklist | ITP-005 - Track Drains | itp | ITP-005 - Track Drains
89f983f1-4fbd-497a-8867-21f4b608be2f | section | Preliminary Works
c8ddbddd-d3b6-4809-bc40-5720f1f70805 | checkpoint | 1.1 Check for correct documentation
d49a8eb6-4dbc-514d-8830-2e1b76172a76 | note | FREQUENCY: Prior to commencing any activity
e9b66f2c-9982-5f1f-9704-5be4ce0c55cb | note | ACCEPTANCE CRITERIA: Drainage design satisfies requirements of all relevant catchment and drainage authorities, a copy of all drainage work approvals are to be forwarded to the superintendent
5612782b-724f-533a-8f6b-b7863955be77 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e305b5e5-ac35-5a9a-88b2-49a3936f73f3 | note | INSPECTION/TEST METHOD: Visual inspection
f86a57a1-cc4d-566e-ab15-2d69ba6bf9f9 | note | RECORD OF CONFORMITY: This ITP signed off
bbebade8-8f86-5369-afbe-02d02f6cbc53 | note | HP*
991c9df4-4496-506c-b115-0cad88679f8f | note | RESPONSIBILITY: Fulton Hogan Engineer
488bd13d-c8d9-535f-8753-f06f3e9c98ef | textbox | Date Completed:
dd65a3b9-5cdc-4ebc-8af1-477bd9bd39c0 | checkpoint | 1.3 Materials Check
6ca737fb-9753-504d-851f-9b60949c2903 | note | FREQUENCY: Prior to commencing any activity
aeec9292-34e8-5108-8d76-35234f97a8e4 | note | ACCEPTANCE CRITERIA: Ensure drainage pipes are of correct classification and are without damage
f3c924e6-77d9-5973-b842-cd4e0ccb3365 | note | ○ Check triangle drains are of adequate quality, and are design according Ri57A rail profile
ca13ecac-1324-56d6-a424-9f8842141ccb | note | ○ Ensure lid and j-bolts being used are in accordance with STD T9022
a0e94149-8c9e-53f2-8b07-087336e66bb5 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.1
18dc7794-ae87-556a-b3c6-c72aa2d41fb0 | note | ○ STD T9021A STD T9020 STD T9022
108c1c22-8d73-5972-a8a9-b3cd67ae86c1 | note | INSPECTION/TEST METHOD: Visual inspection Inspection Checklist
1b58ff2d-bef2-5712-857d-36fbfa7401f2 | note | RECORD OF CONFORMITY: This ITP signed off Recievable Inspection Checklist
e7437370-8596-5bf8-b84c-9d11e8632422 | note | HP*
c9cd920e-b26e-5b2b-a647-a49daada4f49 | note | RESPONSIBILITY: Fulton Hogan Engineer
732de61b-66a4-599d-b59a-5750f62b1a9b | textbox | Date Completed:
0bcb06d4-93ab-4e8e-a787-d5633daf242c | checkpoint | 1.4 Bedding Sand
aa0d0903-12b1-54fc-88be-59710fcd97ef | note | FREQUENCY: Prior to commencing any activity
9dc13b82-60dc-5e92-a809-3a529cb65a1e | note | ACCEPTANCE CRITERIA: The bedding of all pipes shall be in accordance with AS.3500.3-2003 using sand complying to the following: Max. particle size of 5 mm, Not more than 5% by weight passing a 75 micron AS 1152 sieve, Free from organic impurities,Consisting of hard durable particles, and well graded.
0df59e22-e65e-5a21-8589-4ee1daaf04dd | note | REFERENCE DOCUMENTS: CE-021-ST-0044, cl 4.3
90e0ddc5-3019-5785-90ac-9d03dec4bfec | note | INSPECTION/TEST METHOD: Visual inspection
45d7d2bc-9366-5409-9183-f17c129ad3f9 | note | RECORD OF CONFORMITY: This ITP signed off
deda2446-2136-52ac-bd1b-7e04fa13cfa5 | note | HP*
33dfe638-2faf-5cf9-bee6-6a15e896456b | note | RESPONSIBILITY: Fulton Hogan Engineer
1f7ea730-6e65-51a4-8d15-7129e5ced4df | textbox | Date Completed:
cc7f7bcf-18a8-4aa2-a7a6-e377209fb47b | section | Construction Works
ca89ffa1-42e8-4ca8-864b-b1bddb34cece | checkpoint | 2.1 Set out drainage
0ac34a87-171e-5d53-ad43-66c375b73d9e | note | FREQUENCY: Prior to commencing any activity
584a2744-81d4-5559-9433-a267e4d82d0d | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
cf4909fa-91e0-5cae-b8ce-04d262343ccc | note | ○ Track drain locations are to be identified and based off IFC drawings and sections.
3adcc5f7-d46f-53ec-896c-202c76dcacf0 | note | REFERENCE DOCUMENTS: Design Drawings and Register
68267249-62a7-576f-a937-e26d039fe086 | note | INSPECTION/TEST METHOD: Visual inspection
6d3de3b0-9e93-5dad-a8ec-a3a0fbb7f6bc | note | RECORD OF CONFORMITY: This ITP signed off
0a3ef7e1-4e80-5565-b6d3-71954673f2de | note | HP*
fae07ec4-c54a-58b1-a040-cd17987c0845 | note | RESPONSIBILITY: Fulton Hogan Engineer
576a4438-0fe0-5afb-9f05-22886d735c50 | textbox | Date Completed:
56b3f9aa-d70d-48f2-aea5-fc249d227a30 | checkpoint | 2.2 Excavation (pipes)
4dd90337-5b27-5fae-80df-33277e297464 | note | FREQUENCY: Each Trench
e7f5298b-bc81-59ff-8083-91172ce3db34 | note | ACCEPTANCE CRITERIA: Trenching to allow for minimum clearance depth of 100mm below UPVC pipe, and 15mm from bottom of rail to surface of pipe
8b99b1c3-42b2-53ee-9cf5-edd65aa76a8c | note | ○ Track drains usually have invert for pipes at 400mm depth, with floor of pit 10mm deeper.
9bd25a70-156c-53b2-9302-0689c32819d4 | note | REFERENCE DOCUMENTS: STD T9021 CE-021-ST-0044, cl 4.3
0c157f53-a8e0-5a36-bfa5-89238cad77b7 | note | INSPECTION/TEST METHOD: Visual Inspection
1065a862-7750-5060-bb41-0aabd3c1b184 | note | RECORD OF CONFORMITY: This ITP signed off
bb68823c-a7fa-5550-8b15-876902cf2341 | note | IP
899ce428-34ae-51c9-8cb7-153fd07fc61d | note | RESPONSIBILITY: Fulton Hogan Engineer
e4c5604e-566c-5d3e-8751-46591f8afde9 | textbox | Date Completed:
c5637aa4-31ed-481e-82e8-ecf82ef558bf | checkpoint | 2.3 Bedding
e2c654e2-ac67-5078-ac81-4d883442c366 | note | FREQUENCY: Each lot
e33b0010-d55a-51be-b487-07aefce99a91 | note | ACCEPTANCE CRITERIA: Class 2 crush rock shall be compacted to refusal of 100mm minimum thickness
1a6dd16e-cd1a-5745-a401-60b99d4243be | note | REFERENCE DOCUMENTS: STD T9021A
4961d735-afaf-570f-b9c1-05a5ce2487c9 | note | INSPECTION/TEST METHOD: Visual inspection
15a51d6e-6eea-5956-857a-613bc925589f | note | RECORD OF CONFORMITY: This ITP signed off
1e2df91f-c747-52b8-9193-9d46fadda558 | note | IP
2f907968-928c-5876-aded-95770fe0a055 | note | RESPONSIBILITY: Fulton Hogan Engineer
7cbfd8cf-035c-5b8b-bbae-59df6b066e22 | textbox | Date Completed:
c67b962a-415b-4e1d-aee3-49faf68067bd | checkpoint | 2.4 Joining
dd368b3d-d5ce-5bc0-939a-6b13b8fef4dd | note | FREQUENCY: Eaach lot
4978cdd9-0444-5501-9fa3-be3553b8568a | note | ACCEPTANCE CRITERIA: All UPVC pipes shall be joined utilising 'male' to 'female' ends.UPVC pipes shall be joined using appropriate plumbing adhesive immediately prior to connection.
b9ad08ad-9649-5104-9aa3-5403053275af | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
fb2b1539-de2c-5e2b-bfd5-6c0b156a055c | note | INSPECTION/TEST METHOD: Verify
e6c8c830-a67b-5658-9fcb-619ff96e6f13 | note | RECORD OF CONFORMITY: This ITP signed off
9bc799ee-c474-59d0-b381-1b330b80b66b | note | IP
bb44f59e-3c2f-5182-96f1-12421c0d61f5 | note | RESPONSIBILITY: Fulton Hogan Engineer
0065b688-f4a1-57a3-8344-aad2bbcc6545 | textbox | Date Completed:
c2e147ba-ad82-4ebf-99f1-089e917461e6 | checkpoint | 2.5 Track Drain Installation
40a69a85-8929-57b0-8c85-fc982f9598a6 | note | FREQUENCY: Each Lot
7d5934a9-032a-5cf7-aec3-d9d4d8cb52a4 | note | ACCEPTANCE CRITERIA: Track drains shall be welded to designated positions, and cleaned of all weld splatter.
bcdb7804-87dd-5662-a5ba-b5ef96ecc126 | note | ○ Weld shall be sealed after installation
184ac1a8-1b9b-5b16-ab8d-645be81dde1c | note | ○ Rectangular 300 x 450mm junction pit CHAR(AMP) lid shall be used with 4 x j-bolts secured as per STD T9022
ca8de3eb-8d7c-5148-9d24-ceb1f226b19b | note | REFERENCE DOCUMENTS: STD T9021A STD T9022
e23e719a-d82e-52dc-b427-70c5c3f319d7 | note | INSPECTION/TEST METHOD: Visual inspection
f57f034c-2d7c-5ef3-b179-933457d48eec | note | RECORD OF CONFORMITY: This ITP signed off
644d30f9-beec-51c3-878e-fff64f8cc4df | note | IP
f46f4a4b-da91-592d-8d2f-e50fb0b7b8b6 | note | RESPONSIBILITY: Fulton Hogan Engineer
81250bb1-5407-5ea4-bcec-92f586a1975e | textbox | Date Completed:
7c48c4d1-e282-4307-abee-35841ad0b35a | checkpoint | 2.6 Points Drainage
e1d26a48-ab5b-57b9-a1bf-45d5a7c314bc | note | FREQUENCY: Where required
1b6f26cb-81e4-5eaa-9a07-5ab71e01b058 | note | ACCEPTANCE CRITERIA: The road motor box pit for automatic points shall be drained separately to the normal switch drain and care shall be taken to ensure that water cannot flow into the road motor box pit. Points drainage shall be constructed as shown on Standard Drawing STD_T0304, with 100mm dia UPVC pipe.
ee0b432b-88d2-5b74-ae77-d4309b5562bb | note | REFERENCE DOCUMENTS: CE-021-ST-0044, cl 4.3 STD T0304 STD T0305
d7612de0-233d-542f-b11e-9e55cea5f18b | note | INSPECTION/TEST METHOD: Visual inspection
de0e7a9e-b888-5890-8cd6-7a7502f57e75 | note | RECORD OF CONFORMITY: This ITP signed off
4450dfdb-8d1a-58df-a1e8-ecc3c237663e | note | IP
9c187daf-05c9-55f7-9f22-b5a989c58ab1 | note | RESPONSIBILITY: Fulton Hogan Engineer
03ce7ce9-e983-57cc-9a1f-bfbb4e5e923c | textbox | Date Completed:
2975532c-be94-4298-827e-24a1e66f5327 | checkpoint | 2.7 Concrete Pour
1317c653-fdc9-5446-ac5b-c33d291c60d0 | note | FREQUENCY: Each Lot
c56c9b60-5ab6-5d1c-bacf-db52f2475cc2 | note | ACCEPTANCE CRITERIA: Ensure correct heights of sub grade, as to allow for minimum thickness 150mm concrete, to be poured in same period as track slab
9cde4886-807d-514c-bacc-a832b812013d | note | REFERENCE DOCUMENTS: STD T9021A
62151ad1-c808-5b7f-b13f-64c3abc2d2bc | note | INSPECTION/TEST METHOD: Visual inspection
6b21f1c8-f381-5bc1-bdcf-4b7120e6b2aa | note | RECORD OF CONFORMITY: This ITP Signed off
92976b31-3af9-5d49-9b12-1239ec77cc12 | note | IP
72d36f7d-8cdb-516b-bfc5-ce9f006c2766 | note | RESPONSIBILITY: Fulton Hogan Engineer
7c63da2c-522b-5bb5-9ea5-b54dc4d3c986 | textbox | Date Completed:
3a47941f-c80e-440e-ac1b-2ba912605a12 | checkpoint | 2.8 Connection to local drainage
2b0e956d-0624-5ccc-ae76-bd2beb007362 | note | FREQUENCY: Each Lot
33bdd1c3-3a74-5b67-9e07-8b6d385ed5c6 | note | ACCEPTANCE CRITERIA: Drainage shall be connected to existing Principal’s, VicRoads or the Local Authority's storm water drainage system using either UPVC pipe or reinforced concrete pipes, or an alternative approved by the relevant authority. The minimum pipe size shall be 150 mm.
a327c7b1-ee1c-58c3-bd90-f6171806f7b6 | note | REFERENCE DOCUMENTS: CE-021-ST-0044 cl 4.3.2
3289e638-5b27-59a5-a85e-207c71c6a1b5 | note | INSPECTION/TEST METHOD: Visual inspection
57672851-b662-56f8-9a76-a9a6402ecd2b | note | RECORD OF CONFORMITY: This ITP Signed off
a254933b-b4b3-5735-918b-374c886eea09 | note | IP
036b2f21-e45d-52ca-9642-33da64184b7c | note | RESPONSIBILITY: Fulton Hogan Engineer
128e927c-95cf-5bd7-bac3-6ed30a1aefb2 | textbox | Date Completed:
704fadee-0f91-4b0d-8711-813cb86bdd73 | checkpoint | Final Inspection
cc69d148-1fcf-5730-8030-d5e0a2915325 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d21de05c-6f35-573f-a8b7-671d149e18fa | textbox | Print Name:
c4605bef-bd59-5787-b4e6-958029cf104f | textbox | Position:
cf5c75ff-2da3-5c1a-9efd-df39fa39ab9d | textbox | Date:
b0e147c1-2e4b-4b5e-bec6-fc14235b86c9 | checklist | ITP-006 - Track Placement Rev3 | itp | ITP-006 - Track Placement Rev3
67a1ac29-92e0-43d1-bee0-26ad83436fe2 | section | Preliminary Works
50c3f732-303e-4f59-a182-8a52684254f4 | checkpoint | 1.1 Check for Correct Documentation
308c78d0-7093-5d50-a4f6-19842fe9e42f | note | FREQUENCY: Prior to Commencing Works
755dc791-eeed-5475-8ae4-b6fcfaa5f04c | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
36ed7aa2-6e0b-52b4-992d-1e6044590ff6 | note | REFERENCE DOCUMENTS: Design Drawings and Register
1f3eb82f-4315-5299-87f6-51d3b76b9ed8 | note | INSPECTION/TEST METHOD: Visual Inspection
10d2eb57-2ecb-5994-8d2c-57995457472d | note | RECORD OF CONFORMITY: This ITP Signed Off
de00ddfb-e117-58e8-b01f-004a05556024 | note | HP*
61452e6c-5b91-54c4-9524-1e99756a0d80 | note | RESPONSIBILITY: Fulton Hogan Engineer
3f937581-24d8-5104-a8e3-91f90b03f59e | textbox | Date Completed:
44399980-6f2f-4c20-a1df-f509e80aa0da | checkpoint | 1.2 Check Materials
dfbde2b5-7bb2-5944-b967-f877bc56349c | note | FREQUENCY: Prior to Commencing Works
3bc7dc2c-5154-596e-9c9e-6c7048772b7e | note | ACCEPTANCE CRITERIA: Check rail surface is free from any profile deformation and is straight, no crippled or deformed rail is to be used
cc238b36-1e8c-5711-8c40-a1b96b08c2b5 | note | ○ Check condition of rail sleepers
97fb988b-7ad7-52a4-91f3-9a7f6bc72d04 | note | ○ Ensure rail jewellery is of sound condition
b1e55584-453c-592d-8692-be71c0d4d535 | note | REFERENCE DOCUMENTS: AS 1085
69f22820-fbe4-5ea5-a7ad-cedd5bc131ed | note | INSPECTION/TEST METHOD: Visual Inspection
2caa72e2-818f-55a4-bafb-9bd368895696 | note | RECORD OF CONFORMITY: This ITP Signed Off
f482e743-5ed7-590d-9e04-da8844e02fae | note | HP*
9c5803e8-fcfe-567a-82e5-a4d267bd3129 | note | RESPONSIBILITY: Client, Fulton Hogan Engineer
3af72b62-8f92-55f5-9987-8c0e3a8b4a2d | textbox | Date Completed:
652bd977-740e-44cc-9b6d-b4d5756a1851 | checkpoint | 1.3 Check Special Works Components
596e7d45-6cca-5fec-a02f-a9a328b30cc4 | note | FREQUENCY: Prior to Commencing Works
45285944-93bb-5c69-91a9-694857439492 | note | ACCEPTANCE CRITERIA: Special Works is any trackwork which must be pre-fabricated (ie bent or assembled) before it can be installed on site. This includes all switches, crossings and any trackwork which needs pre-bending.
fdf52748-954e-5337-9da1-48c16de533d7 | note | ○ Ensure that all rails for crossing work is head hardened, and the appropriate weld kits and welding methods are adopted for welding modules and seperate rails. Superintendent to visit yard from intial inspection of the rail and fabrication plans.
1564fcc9-0ec3-504e-9a88-7dd2888eb250 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.2
90d203fc-e0af-59d4-b34f-1202503d42e6 | note | INSPECTION/TEST METHOD: Verify
dca50915-6a2a-5d1d-bdeb-b72e3bcf23ae | note | RECORD OF CONFORMITY: This ITP Signed Off
4fbcdfcd-425a-5bf2-8ab2-d611f8d34405 | note | IP
a4257caa-e762-5d04-82d3-86bcce78657c | note | RESPONSIBILITY: Fulton Hogan Engineer
eeaa586a-1c69-5e91-9abc-044e63d3ab40 | textbox | Date Completed:
fadfa59d-b020-4b8e-8b7b-5d387b71bb77 | checkpoint | 1.4 Check Curved rail
19890402-7e38-5e2d-9cf9-955706ef824c | note | FREQUENCY: Prior to Commencing Works
edf5a367-6f3e-5620-8278-1c83c433cce9 | note | ACCEPTANCE CRITERIA: Rails for curved trackwork, i.e. radius less than 150 m, shall be head hardened and pre-bent. Additional 25 mm diameter tie bar holes may need to be drilled or cut into the web of the rails. This is to allow installation of additional tie bars between the rails to ensure correct gauge can be maintained during concreting.
f9f1181f-73b0-51df-83c8-b0e0ef1e595b | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.3
eca5ccd4-0c35-53d4-b38b-6c0cdaaba262 | note | INSPECTION/TEST METHOD: Verify
40f6936d-f5f2-5e2c-a526-746765b891c5 | note | RECORD OF CONFORMITY: This ITP Signed Off
8346a5bf-d1f6-5bc0-abc5-8c2149e3799c | note | HP*
b20e9245-b10a-5890-97e5-6efc851d0125 | note | RESPONSIBILITY: Fulton Hogan Engineer
82bf0c87-c341-59b4-a0cb-ac200324fb43 | textbox | Date Completed:
8ca52a7e-08a3-431e-b1cd-0ef0b0b8add4 | checkpoint | 1.5 Welders Qualifications
df0c2c3f-c2c3-59c0-b92c-037fedce49a4 | note | FREQUENCY: Prior to Commencing Works
daef17c3-b447-5085-bc11-4cd769291b53 | note | ACCEPTANCE CRITERIA: Welders shall be trained and compliant in Aluminothermic Welding Requirements;
27c2ec27-a4ce-5cdb-8947-f3a8a0db48f0 | note | ○ TLIW2012 Grind Rails
88977cf0-d939-5cc4-8e72-cf74369d9a53 | note | ○ TLIW3015 Weld Rails using Aluminothermic welding process
d7dee22a-f351-5938-b963-7c5eb5fd97cc | note | ○ TLIW3035 Heat & cut materials using oxy-LPG equipment for the rail industry
73f6f175-c6e3-5e14-8cb4-5ca65a59da54 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, Appendix C
6e40a473-5e8a-53aa-adc3-fc7e45cd9264 | note | INSPECTION/TEST METHOD: Verify
3ac7cfea-00a2-5b81-b747-2a68bcaf30bd | note | RECORD OF CONFORMITY: This ITP Signed Off
09153c53-2908-5ffe-85ad-657815c4d2d9 | note | HP*
05769ce2-b27b-51c8-a205-338d28dee1e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9645adf-8c13-5bf1-860f-a2dbccbac017 | textbox | Date Completed:
732e220c-8243-4114-850b-95112194fa06 | checkpoint | 1.6 Ultrasonic Testers Qualifications
778a34e8-8e1c-556e-a129-7ff5037eaf5c | note | FREQUENCY: Prior to Commencing Works
981644b5-172e-54ab-9c02-70fbc9ceb4de | note | ACCEPTANCE CRITERIA: Ultrasonic testers shall be trained and qualified to AINDT Technician level and shall be experienced in rail weld testing. Certification shall be provided to and approved by the Superintendent prior to commencement of testing.
9e576a47-32b1-53e1-9dce-4f314ccb45f1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, Appendix C
cb788e6f-4a68-5790-9011-0f370a48bbf9 | note | INSPECTION/TEST METHOD: Verify
8cd12057-e356-5a06-8291-4e8163812571 | note | RECORD OF CONFORMITY: This ITP Signed Off
e0fc5a05-fa03-5051-85bc-f2ab0b1e6fe5 | note | HP*
148fdca4-9a9a-57f6-8dc7-cb239936ffcc | note | RESPONSIBILITY: Fulton Hogan Engineer
2bff7f29-3041-5cc5-85ac-8ab8b11b5d52 | textbox | Date Completed:
37906a9d-8e1c-461a-80c3-109b842bc0e7 | section | Construction Works
b13549e6-2717-480f-97ce-f55cd81a214d | checkpoint | 2.1 Installation of Sleeper
507b25fe-66a3-506e-b61d-fad95673993a | note | FREQUENCY: Each Lot
f26980b3-95e5-50ec-a7e3-22fdac0432a2 | note | ACCEPTANCE CRITERIA: Dual block sleepers shall be installed at 700mm intervals, toelrance of +/- 50mm in placement
9a65f8f8-a0b2-54d8-bdc5-fb5cb66ffb38 | note | ○ Dual block sleepers shall also comply with the design offsets at each chainage
547688c6-d1a1-54d6-a391-6fc41f472f4a | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.7.1
783b256a-2b99-5a0c-a54d-9e6fb5ccae1a | note | INSPECTION/TEST METHOD: Visual Inspection
74e2d5b2-27e7-5638-90de-fbc4d6ca2f6b | note | RECORD OF CONFORMITY: This ITP Signed Off
87d359e7-64c8-5417-9717-5c26a28a0bfc | note | IP
2ffccbfe-5fff-51ad-be18-3f06ddc29c4f | note | RESPONSIBILITY: Fulton Hogan Engineer
5d9f1c8e-1ae1-5d7e-84d5-aff0b53c97ec | textbox | Date Completed:
4f4b39be-7694-4df0-bc06-48200201921b | checkpoint | 2.2 Placement of Rail
b9b596ff-c391-5695-b207-678b195704b1 | note | FREQUENCY: Each Lot
fdfbdc0a-d302-5491-a363-58ea741865f5 | note | ACCEPTANCE CRITERIA: Ensure rail strings conform to rail plan
e0e46237-9998-5d55-bd84-0763b6a1fd06 | note | ○ All track work, including points and crossings shall confrom to alignment, offset, level and cant as per design drawings and track charts
70bdb1d1-2a12-5b83-9c33-14d582c27292 | note | ○ Bottom of rail and bearing surface shall be clean of foreign materials before laying
b509357f-1041-5d05-8199-14010dcfdef1 | note | ○ Track Gauge shall be calibrated to 1435mm with a tolerance of +3mm , using an approved measuring device
10f59512-cb2b-5488-8834-4e74fd2bdc18 | note | ○ Geometry tolerances as follows:
addd7904-888e-5fa8-b21b-876815cb4841 | note | – Centreline location: +/- 3mm
53889c98-0132-5891-a9bc-3512547e7527 | note | – Level: +/- 3mm
a7b56a1d-7e3a-5fed-a141-85012b925aee | note | – Line measured (>10m chord): +/- 3mm
9ac85de2-c22b-5354-95cd-d380b50ba323 | note | – Twist (3.5m chord): +/- 2mm
d4459fe7-6f93-5119-8840-2b84b7af1b99 | note | – Cant: +/- 3mm
0ce2d49b-4637-5219-81ff-64139b468f8a | note | – Gauge (open track): +3mm, -0mm
bb804e48-4dac-5836-b619-94222b41bcc7 | note | – Gauge,Turnouts (opposite crossings):+2, -0mm
26f25560-4cd3-58c7-a4ac-c4c8f387846e | note | – Gauge, Diamonds and ‘H’ Crossings:+2, -0mm Note: Cant shall be applied uniformly over transitions
3e39782d-3244-5697-ace8-d2972f3d247d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.6.10
ee298267-0a25-5293-9847-98496a7f3ca1 | note | INSPECTION/TEST METHOD: Visual Inspection
b1623b25-17de-5819-8d20-4de4ba287d31 | note | RECORD OF CONFORMITY: Completion of track charts
878579ce-2cf3-557a-a068-fab17e5f5aef | note | HP*
073bac6e-cfd7-519b-93a9-fa44baf4afb2 | note | RESPONSIBILITY: Fulton Hogan Engineer
682616e3-f6ce-5010-ac73-7fe04ea1db26 | textbox | Date Completed:
91dffbb4-6c72-4bdc-8d40-f84aa29ce54e | checkpoint | 2.3 Placement of Jewellery
8414dbf0-de5f-525b-95dc-076cd3d8aa2f | note | FREQUENCY: Each Lot
88891a77-f2c6-59f9-b886-b9014ed4eebb | note | ACCEPTANCE CRITERIA: Each sleeper shall be fastened to track with approved jewellery and rail clips
425dee49-8eb1-591f-8b2f-e4940e626a5f | note | ○ Clips shall be installed with panpuller or equivalent
06bc3777-e210-5dc8-8d88-428c058137a4 | note | ○ All fasteners shall be sealed as per agreed method with Yarra Trams
12f24c9b-7c61-5f4c-9053-4bfd327cad16 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, cl 4.8
22e8bdf9-1d6d-58ae-b862-299ec6a4cc7e | note | INSPECTION/TEST METHOD: Visual Inspection
dc3e9603-eb39-5db3-b4cc-e99471174428 | note | RECORD OF CONFORMITY: This ITP Signed Off
a5e9c06e-8b83-5723-8f25-180c9543c93c | note | WP
c4509835-6c33-5a32-9107-e544ff8f0b20 | note | RESPONSIBILITY: Fulton Hogan Engineer
516a6af3-766c-57b1-88e8-a53ab2760f8a | textbox | Date Completed:
80f71684-0fef-4e2a-80a8-67398cd31b27 | checkpoint | 2.4 Rail End Preparation
a5d50ea5-7cf8-5395-9847-b0c00a1480d3 | note | FREQUENCY: Each Lot
c0abf8b8-e6e4-5270-95d4-439666023e02 | note | ACCEPTANCE CRITERIA: Rails shall be saw cut or flame cut
c23cb34e-4a58-5685-8397-2a96121f265f | note | ○ Minimum closure length from proximity of welds shall be 2m
505a5eb6-1fbf-58dd-b4a7-866655f11d18 | note | ○ Rail end conditions shall match (i.e flame cut - flame cut)
643b5ca7-a870-5285-958c-754b6e629650 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, cl 4.9 & Appendix C Code of Practise SkV Elite Welding Proc.
b04e4ee6-938b-572d-86d6-a81d36913f70 | note | INSPECTION/TEST METHOD: Visual Inspection
165f6db2-dc28-5bd2-a25e-45a86ec0630b | note | RECORD OF CONFORMITY: This ITP Signed Off
ceb4105d-2770-5b0f-a792-a230d72f3a7b | note | WP
0e4db205-c9e9-533b-a864-abd45dbc3298 | note | RESPONSIBILITY: Fulton Hogan Engineer
93e3ceb0-0efd-5af1-9e63-fc1757ea55d8 | textbox | Date Completed:
9ce79a88-c13a-4ba6-8452-b9c3c72b14f9 | checkpoint | 2.5 Welding of Rail
6bfc3311-bbe2-5adb-bec9-4edc76bfcf2a | note | FREQUENCY: Each Weld
9224c4fb-f241-5d21-ad75-002b3254415f | note | ACCEPTANCE CRITERIA: Joints shall be square across the track
d97162b3-0164-597f-b01a-0831ff26c3d3 | note | ○ Maximum skew at square joints shall be 65mm
58ea9de7-e3b6-5ca5-b9ee-7c05a47c379e | note | ○ Portions shall match rail type (i.e HHR, Ordinary)
8dedc24c-2717-541e-8272-213f690b99d3 | note | ○ Welds shall not be within:
6d831010-678f-569a-9714-b903fcbeb039 | note | – 3m of another weld
7c9aed08-720b-55e0-951a-0c6c6167d958 | note | – 3m of a rail end
d61faa71-ae2c-5f1b-b1c6-3ccc6a4a4d6b | note | – 1.5m of a glued insulation joint assembly
98fd3a14-2877-5047-a2fc-c230f10e0925 | note | ○ Field welds shall be +/- 50mm from centre of bay between sleepers
3e54a764-6904-58b9-8b1f-af2d7ade8188 | note | ○ Weld Return forms shall be completed by qualified welder
cae21dda-506b-5540-b7c4-55433e1f6bec | note | ○ Welds shall be grinded after 1 hour
48235f8b-1e1b-5f6f-840b-9fc0e42f1674 | note | ○ Welds shall be free of water
89282895-7ed9-5445-8c27-f5bbf68daa60 | note | ○ Post grinding, welds shall be cleaned for visual inspection
15e9a309-057b-53b6-be3e-c1893e1d918f | note | REFERENCE DOCUMENTS: CE-019-ST-0033, cl 4.9. & Appendix C AS1085
e343dd16-5c6a-5e37-8f1b-b3ee0bdcfd00 | note | ○ Code of Practise SkV Elite Welding Proc.
776452cf-2ba4-53fc-aa50-754fbcb07861 | note | INSPECTION/TEST METHOD: Visual Inspection
4f616356-a9ae-57d4-8e4a-6d3533a1d6a2 | note | RECORD OF CONFORMITY: This ITP Signed Off
9c26c8b5-c47c-51b9-bbf7-16bd9979c269 | note | TP
97d5e800-1e02-5a10-a3ed-e5d49606fb86 | note | RESPONSIBILITY: Fulton Hogan Engineer
f044164d-1b9d-5002-ab4f-52ee0763dc26 | textbox | Date Completed:
93daeecd-dbfe-4c26-a7c9-16c26aa4ef92 | checkpoint | 2.6 Grinding & Cleaning Welds
9d2e188e-a876-526d-8f28-90e56b882f71 | note | FREQUENCY: Each Weld
13b191ca-1103-5d00-902b-ad2d7664de60 | note | ACCEPTANCE CRITERIA: The weld shall be ground smooth to the exact rail head profile after it has sufficiently cooled (not earlier than one hour after pouring). The grinding stroke should not exceed 500 mm to each side of the weld.
ddec4b66-828c-5f33-b7a3-ad214ef76ebd | note | ○ Welds shall be cleaned of sand and cast metal residues to permit a thorough visual inspection.
85577212-fef1-53c1-a1fc-b52e28c8d80d | note | ○ The vertical tolerance of the weld (of a 1m straight edge) shall be 0mm for dip and between 0mm and 0.5mm for peak.
6dfa474c-c74a-597b-89f4-8b23d78354c0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, Appendix C
e92fb8f7-a602-58d2-ae6d-f6cc234e483f | note | INSPECTION/TEST METHOD: Visual Inspection
4327e253-7169-5d1c-9c9b-bd38ea172f6c | note | RECORD OF CONFORMITY: This ITP Signed Off
bac5937c-22fd-53a1-9fea-c231f9bc8444 | note | IP
a4515207-80d5-51eb-a5ef-9687bb10c20d | note | RESPONSIBILITY: Fulton Hogan Engineer
27c4c89d-8d84-55db-a24b-895157c3c044 | textbox | Date Completed:
69acf1d4-de78-4b65-b846-e9979aad77fe | checkpoint | 2.7 Track Adjustment
41ad58a6-6633-553f-9780-442fc6ee7817 | note | FREQUENCY: When required
a6f79e6d-013b-51b1-a16b-569524eb97ac | note | ACCEPTANCE CRITERIA: Allowance must be made for expansion and contraction of rail to control stress. The required adjustment depends on rail temperature at time of laying and/or adjusting the rail lengths,which shall be measured with an approved type of thermometer.
98eaa24e-d51a-569c-b182-fb861f72e8f9 | note | ○ In hot weather, it may be necessary to anchor the track temporarily to avoid expansion while the next section is laid or adjusted to avoid creep.
030c0068-d5b2-5fe7-8665-ea39ec5a8d56 | note | ○ Each rail length shall be adjusted in accordance with the rail adjustment table and shall be anchored to standard pattern in accordance with Standard Drawing STD_T9008.
e6de5bb6-e766-5ffe-83eb-6e39a51b2a56 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, Appendix C STD T9008
35b0a9f0-b36f-5c64-9648-062331f04df1 | note | INSPECTION/TEST METHOD: Visual Inspection
dfec4f4c-dbce-5d11-a994-0c393ec9998d | note | RECORD OF CONFORMITY: This ITP Signed Off
2fc0579c-b6aa-521e-a91a-2789fb5f29d2 | note | IP
28e9a09c-02c1-5ded-b274-716ff5210a85 | note | RESPONSIBILITY: Fulton Hogan Engineer
1f188926-f022-5b6f-b015-c0e153e6e542 | textbox | Date Completed:
a3b8c9e7-3ae6-4c82-a387-10966f35c375 | checkpoint | 2.8 Track Bonds
0949c644-ee6c-5eff-a3ae-1f0dc0aa8c4d | note | FREQUENCY: Each Lot
2376c5bf-337d-5d06-b49a-4f2b22e1401a | note | ACCEPTANCE CRITERIA: Positions and configurations shall conform to design drawings and Yarra Trams Standards and Specifications
83462e7c-f282-5078-894c-f01534c43b40 | note | ○ Ensure bonds are sealed as per agreed method with Yarra Trams
a6ce4125-2e0c-5aa8-81bc-69f591bddf6c | note | REFERENCE DOCUMENTS: CE-019-ST-0033 cl 4.5.4, Appendix C Design Drawings
58108b35-fcca-5cf0-9a6d-0d0b90966586 | note | INSPECTION/TEST METHOD: Inspection / Test Method
73eb096a-d15c-542d-8174-0c9eeaf76b3d | note | RECORD OF CONFORMITY: This ITP Signed Off
1601bf59-61b9-5197-90a1-2f0977d57855 | note | IP
24909328-1ace-50f1-a98a-2eaba235f391 | note | RESPONSIBILITY: Fulton Hogan Engineer
7bde166a-3f0c-500d-96b6-40feede2cda1 | textbox | Date Completed:
b22c6f62-d467-4a90-8a5f-5c2c8c03135a | section | Testing
fa19f968-50f0-4feb-9dc6-793e11b1e66d | checkpoint | 3.1 Track Testing
668580b0-d831-5080-9005-bc9a604bb77c | note | FREQUENCY: Each Weld
ec849e9e-50c1-563a-a015-c0154224be0a | note | ACCEPTANCE CRITERIA: All welds shall be tested by qualified NDT operator
35271e11-47cd-5cb5-8cdc-0029fd4f30c0 | note | ○ Failed welds shall be cut out and replaced
e1c65a6d-7c7c-5e0e-8408-995b5c94fc17 | note | ○ Testing documentation shall be recorded and supplied to the superintendent
d174ee42-5276-5b3e-9ac3-af65542cf745 | note | REFERENCE DOCUMENTS: CE-019-ST-0033, Appendix C
57067952-2d24-596b-ae44-c3692335dc47 | note | INSPECTION/TEST METHOD: Inspection / Test Method
13abcb1c-a7e4-5f8c-8af8-cb1a9944b4bc | note | RECORD OF CONFORMITY: This ITP Signed Off
b7af22f9-a5be-593f-87e1-ceeeeeea1719 | note | TP
399931b5-de88-5a1e-b925-b6ffa66abc95 | note | RESPONSIBILITY: Fulton Hogan Engineer/NDT
61bb44b8-0cf0-5c4b-87ee-89662aaa1eea | textbox | Date Completed:
6b5fe322-de99-43ee-87a0-c4a6a82f25c5 | checkpoint | Final Inspection
db88684f-b235-5edc-bd9c-da69f6b6fece | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d1cc68b2-8ef3-50ad-b673-4bf11c24d8f3 | textbox | Print Name:
229deb91-e62a-5d5f-9758-f8a7fb3ce3d6 | textbox | Position:
aae08cce-db78-52c5-87a5-e7c179d640eb | textbox | Date:
df80d8b2-f844-4363-b52f-90a7c502c126 | checklist | ITP-007 - Concrete Track Slab Pour Rev2 | itp | ITP-007 - Concrete Track Slab Pour Rev2
d9eaa481-a561-4d9b-b944-eeaef847c448 | section | Preliminary Works
bb865ec8-9987-4e33-af3c-8c7da5d4f715 | checkpoint | 1.1 Check for correct documentation
da9a8275-50f9-50d8-bc32-5cda1c8e061f | note | FREQUENCY: Prior to commencing any activity
ddfa1d9b-94d6-567a-b768-f7f115d6676b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
0ad6f719-2209-56d1-96f5-901c143944fd | note | – using the correct and complete set of drawings
e40e60aa-f34f-5df0-acdd-0054c84b9bd7 | note | – all drawings are the latest revision
ee6f378e-0156-54da-b735-031df9eb0155 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2ed51135-6222-583c-b7c3-6ea02fea6fff | note | INSPECTION/TEST METHOD: Visual inspection
c74a80e9-c7c2-5cb5-a328-a9ee981a29a7 | note | RECORD OF CONFORMITY: This ITP signed off
73ee0eca-7e2f-5535-a0e8-562cb3d869b7 | note | HP*
208d7864-7520-5c51-b512-81d82d102c5d | note | RESPONSIBILITY: Fulton Hogan Engineer
19da982a-6a99-598f-9d26-ce100fc53683 | textbox | Date Completed:
b781668b-492e-4e4b-b5a3-8692647da0d8 | checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
0799629a-19cd-5e94-b790-c23f78cd0401 | note | FREQUENCY: Prior to first concrete pour
4734e30e-db3d-54b0-bf74-7057c62b8c40 | note | ACCEPTANCE CRITERIA: Concrete mix design submitted and approved at least 2 weeks prior to first pour.
79007035-4c63-5680-9988-feaea0442d4d | note | ○ Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
39ad5909-714c-5b5e-b7d7-2a494491e758 | note | ○ Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
54402684-e2c9-57da-b510-3da762cede7b | note | REFERENCE DOCUMENTS: CE-019-ST-0033
03de2417-5bc0-56ac-a1f8-ead9bc66adf7 | note | INSPECTION/TEST METHOD: Verify
0dc44347-c365-5e12-b555-6e68f1d1c812 | note | RECORD OF CONFORMITY: Mix Design ITP
37e3b792-b508-5836-a5fd-dfe5fafec170 | note | HP*
116d2f51-a846-5e64-9163-8c16741a6dcd | note | RESPONSIBILITY: FH Engineer / Superintendent
6de91600-7d48-5bd3-be3c-481a0b183734 | textbox | Date Completed:
ee3da262-1680-42c4-b168-ba5a59117555 | section | Construction Works
c9fe49f0-2975-43c0-b568-bf1c379187bd | checkpoint | 2.1 Weather Monitoring
2b128c46-3792-5552-b23e-39f7ad6ce22b | note | FREQUENCY: Prior to start
e619cda9-f346-5645-879c-8b4d9367d06c | note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
65149286-ffe4-5f14-8920-92f2906e0b84 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
76c3dc95-9e8c-566f-a2d1-e73133864318 | note | INSPECTION/TEST METHOD: Verify
7a6fb563-4718-50e7-952e-95d3249f246c | note | RECORD OF CONFORMITY: This ITP signed off
b5792614-9e7d-51c7-abba-2b847e497e11 | note | HP
1c2025a6-6d53-58a3-9d7e-50149eeaf096 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
a4f6e0ea-354a-5594-9f6f-22819242f973 | textbox | Date Completed:
b54e4cbc-0a38-4fb0-ab90-e3ca532dd431 | signoff | AUTHORITY HOLDPOINT
5eaa1007-d1cb-447a-97f0-84a6cd7f21ff | checkpoint | 2.2 Surface Preperation
1079735b-5b1f-51af-812b-573ce4da7416 | note | FREQUENCY: Prior to start
1225de51-1214-5dc0-aeba-ef07d73cbaac | note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
e68a7c33-2960-5511-bcff-5eec9e015e80 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
20703678-21ca-55ec-b7d4-ffa23f9bb425 | note | INSPECTION/TEST METHOD: Verify
79a432aa-34cb-54ce-80ed-588639bf225f | note | RECORD OF CONFORMITY: This ITP signed off
c984a619-dfaa-561a-87c8-a629a1dcd766 | note | IP
cb1f040d-5aad-5003-9ec7-64b1914f5584 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
faed079c-7e77-5729-81f2-1c6db4d6c092 | textbox | Date Completed:
6612dc9f-3017-4655-aa37-dd0dac378360 | checkpoint | 2.3 Setting Out
55558cc8-2db8-5403-8f83-266b01046f58 | note | FREQUENCY: Prior to start
1df0e672-5477-564f-8c48-b8cadaf29a28 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications. No survey/level pegs to be removed by any persons until completion of works.
293c0ef0-90b9-5778-83b7-1289fe56102b | note | ○ Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
aaf22484-dfe0-52d6-b510-380f244b00da | note | REFERENCE DOCUMENTS: CE-019-ST-0033
ccb5f936-c9bb-5194-8459-16da1d2c5fea | note | INSPECTION/TEST METHOD: Verify
be49d8ff-d7e8-5e83-8b70-1f0b615ce1d0 | note | RECORD OF CONFORMITY: This ITP signed off
9440184d-1316-5c7e-b86e-398cd43f4b7f | note | IP
f34606c2-7d9c-51a8-bcec-23f092eab023 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
7e955210-7dc1-54f5-9a66-4f9e4ec35f43 | textbox | Date Completed:
d64105c5-7bf2-4747-a573-7bf4fd9ed56c | checkpoint | 2.4 Formwork
3ff81fb7-80db-5896-a1e7-eeb9a32d3cab | note | FREQUENCY: Prior to start
67f18e2a-e30e-5c66-bc23-0cbff5ccf69c | note | ACCEPTANCE CRITERIA: Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
5cad3234-b23e-5185-bb8a-dc836e46d2c2 | note | ○ The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
39a6b7b9-7327-5d82-bfed-b5ae0d810a01 | note | ○ Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent.
20fd02f3-bfdb-594c-ad64-daf217c598f0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
8991a758-94ea-539a-8a8d-052b1e960449 | note | INSPECTION/TEST METHOD: Verify
4b955c5f-5cac-5581-83e9-2d21043ad30f | note | RECORD OF CONFORMITY: This ITP signed off
2230fe30-9845-5a37-9153-1b047c820448 | note | WP
b9cc20bf-7036-515c-9304-b61a154ac425 | note | RESPONSIBILITY: Fulton Hogan Engineer
a958fe27-5f2d-5829-a8de-f3b3f5b9144d | textbox | Date Completed:
637d0cc7-061e-4c3d-bac9-0f4dd88ea1d3 | checkpoint | 2.5 Reinforcement
a7f2ed84-de42-5abe-9787-a431be8ac437 | note | FREQUENCY: Where Required
fc2f2d03-7773-5c26-8994-1a2b006d591b | note | ACCEPTANCE CRITERIA: Ensure that all reinforcement is placed as specified by construction drawings.
10736376-5da5-534c-a54e-d3bd67000ef0 | note | ○ All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
09344135-ea68-5e24-8e06-0e2822df096e | note | ○ Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
ecdc7c1e-9ffc-57db-b967-69dd9b331273 | note | ○ Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
ff1eede5-8af3-5aed-94f1-6e44f6b58eba | note | ○ Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
5c3c8e17-6edd-5d50-aec5-4a9119542498 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
4784eebc-6b6c-5184-ad98-34e1be3731f7 | note | INSPECTION/TEST METHOD: Verify
8a302360-bfcf-5d3c-8a9e-78a7c945f297 | note | RECORD OF CONFORMITY: This ITP signed off
2a3dc0c8-536d-55a8-b1aa-578486f81618 | note | IP
a1958b98-c45e-5c25-8fd2-ab4ab2da6304 | note | RESPONSIBILITY: Fulton Hogan Engineer
a2178ce4-de10-5549-8e97-0e94b2e47a88 | textbox | Date Completed:
02e114ef-ee33-48a1-82bd-6a8b38e042de | checkpoint | 2.6 Dowels
a4417776-eca1-5deb-8c42-2f3138f0c503 | note | FREQUENCY: Where Required
f917d17e-f8b8-529e-aaee-64785acd05ea | note | ACCEPTANCE CRITERIA: Ensure that all dowels are placed as specified in the construction drawings
d855d025-338a-58a9-8742-2cf4bc9e0399 | note | ○ All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
a15dd173-c058-5ea4-a6c5-a37de711a36d | note | ○ Dowels shall be clean and free from mill scale, loose rust or oil.
432a90ed-f93c-5079-8344-aeb5a592542f | note | ○ Ensure that all dowels are securely held in their correct position until the concrete has set.
a56a2a09-efc1-5023-9710-a013fd10e705 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
674aba32-cc3c-53e2-b083-a72af901a118 | note | INSPECTION/TEST METHOD: Verify
3843b0cb-aa5d-5aec-8b3d-4a9c7a645a1d | note | RECORD OF CONFORMITY: This ITP signed off
aa044a72-2829-5d83-a86b-e73d23b75924 | note | IP
355c72fd-1625-5b65-b539-bc976aab2db9 | note | RESPONSIBILITY: Fulton Hogan Engineer
8fbc673f-189b-5fb9-8d6f-94d477e943a3 | textbox | Date Completed:
d31a38e4-1e7e-4428-8b82-2129fab21b91 | checkpoint | 2.7 Pre Pour Inspection
08bb3b86-5efd-53de-9076-c9296432fadd | note | FREQUENCY: Prior to start
2a6b8885-1766-57a8-9243-1113f1bd3197 | note | ACCEPTANCE CRITERIA: Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
c97aaf50-49c2-52ed-a68e-7b2dbba1bc75 | note | ○ Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
54d22a65-86b2-55b3-b3f8-bda860e91ebe | note | ○ Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
22a63fe8-0e7f-59a0-aadd-2a1738a814f2 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
9fe8593b-aa0e-55e3-a996-db5668a9ccb2 | note | INSPECTION/TEST METHOD: Inspection / Test Method
04a3c494-465c-5e63-a7b6-5913fa0111b2 | note | RECORD OF CONFORMITY: FH Track Inspection
36dd5b28-63eb-503c-ac7c-ee5a0c52bb6a | note | HP
7badbd7b-5cf2-53cd-9115-812a24afff35 | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
75f9f031-ff3e-54ef-9fb0-c9d989499fe3 | textbox | Date Completed:
7f4b32b7-51ae-4122-8901-2ad4a6374927 | signoff | AUTHORITY HOLDPOINT
7aa07e93-b4ec-4b7a-a481-17ab1ffb2d56 | checkpoint | 2.8 Carry out sampling of concrete
159cdc7e-f92a-5ee6-b761-338f62707a41 | note | FREQUENCY: Each concrete pour
c1b97d89-8f04-56fd-b6e9-b7c237743e6a | note | ACCEPTANCE CRITERIA: Slump: Concrete Slump shall be 100mm +/-20
35529f9e-6c73-5dda-8501-56cf0078f0aa | note | Compressive Strength: Shall be measured in accordance with CE-019-ST-0033
e4252931-260f-52ca-8e1d-484b6006e2fc | note | ○ Testing frquency =
f7192292-eb90-5c6c-9f75-b4f22b6a4f16 | note | – 0-50m3, 1 sample
a16daab5-7348-5212-8954-49fa5015d25f | note | – 50-100m3, 2 samples
0d4ac532-a345-5887-9a1a-08cbc682df0a | note | – 100m3+, 3 samples
e3cd2893-57a2-5797-8e85-5ffc02d2e1b1 | note | ○ Each sample shall consist of 4 cylinders
5a80fb3e-fde8-5c36-998a-5b165f0f3c6b | note | ○ Test Results will be provided to the Superintendent
9e0d12fd-9542-5459-a2d4-d12504c06017 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
ce4def23-9ddc-51fa-bb25-a3d47b18c3ff | note | INSPECTION/TEST METHOD: Verify
8f25d747-eec8-5e51-951e-dea2c998549c | note | RECORD OF CONFORMITY: Concrete supplier test sheet
f4ef77f1-7149-5649-9a37-064269f9de4d | note | TP
5fd6387c-b5eb-5576-b6fa-1703551267ee | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendent
ec170bcd-74de-51a4-81ea-37cff0cfd4c9 | textbox | Date Completed:
8056a69a-795d-44a8-9d00-70527a6138a1 | checkpoint | 2.9 Concrete Placement
4d3cf93d-b988-58a9-9de9-8c6821d633e6 | note | FREQUENCY: Each Lot
21998ec3-f153-54a1-98af-102ebfdd9c66 | note | ACCEPTANCE CRITERIA: Ensure formwork is clean
23d10cd4-449b-5a2d-86f7-c448a6752f11 | note | ○ Concrete shall be entirely discharged 60 minutes after batching,
423ec5cb-8b16-591d-927d-5293ff91dd2f | note | ○ Ensure that pouring does not occur from a height greater than 1200mm
07edc218-0b42-58ba-9fb1-aaf3d7f01d8d | note | ○ Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
a1615b4e-9a57-5dee-b4e0-ac3b39a87a56 | note | ○ The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
767006ce-960f-5056-8d65-964c46343613 | note | ○ There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
b518f422-4fa5-53e1-8fb5-83fef60c91e0 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
6e106f48-4644-5b2f-b301-9725bd7871a7 | note | INSPECTION/TEST METHOD: Visual Inspection
192b8586-cc3d-5763-afd0-a599a7db1574 | note | RECORD OF CONFORMITY: This ITP signed off
335c4a4a-9684-58b0-9a10-1761ad2108d8 | note | WP
ad7b1e13-0957-52c7-90c9-05ec8638cea2 | note | RESPONSIBILITY: Fulton Hogan Engineer
840fafc3-60f5-5d9a-bb25-e2d31f54b783 | textbox | Date Completed:
7403e39a-34d1-4215-96a6-a30d062cfe1f | checkpoint | 2.10 Compaction
04008198-9d92-5000-9570-4af1db043d61 | note | FREQUENCY: Each Lot
8b6f91d3-ee98-571a-a5b8-b31e8e62d441 | note | ACCEPTANCE CRITERIA: Immediately after concrete placement, compaction shall take place with an approved vibrator
2dc15ef2-f2f5-52c4-9c60-730cc690c7cc | note | ○ Vibration shall take place until exposed concrete surface is free from air voids
64477f3a-a1f7-5635-9880-28cde40adfc1 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
9f0b52de-518b-5e86-b339-c5bfb39a9b84 | note | INSPECTION/TEST METHOD: Visual inspection
03b47b76-e26e-5536-9857-edc5cc478181 | note | RECORD OF CONFORMITY: This ITP signed off
7923aaa0-b657-5c26-bba5-8f4eaa3283a4 | note | IP
9274db15-fb62-5f89-abaa-c37f35bd75d4 | note | RESPONSIBILITY: Fulton Hogan Engineer
1a65bf06-a8c4-581d-a6ef-49d2a3ccc0b0 | textbox | Date Completed:
40b1ff0b-56f7-4996-a3a9-bfff073fa1fb | checkpoint | 2.11 Record location of each batch
e8b02cec-9eb6-5c11-96b6-25cb8413a6ef | note | FREQUENCY: Each concrete pour
f1a50c24-3558-5714-8664-b2701cecffd4 | note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
56061c26-cdd8-5e21-be1b-0747cc68374e | note | REFERENCE DOCUMENTS: CE-019-ST-0033
38ce572d-d66e-5fb1-9346-38fe29086507 | note | INSPECTION/TEST METHOD: Checklist
24d83310-ea47-5a5e-899c-59aee322f26a | note | RECORD OF CONFORMITY: This ITP signed off
aa71958f-e23f-5cbe-906a-a1f44e9b086f | note | IP
c8c50878-8768-5811-af8c-a4410fc4a6a3 | note | RESPONSIBILITY: Fulton Hogan Engineer
04d635bd-52b0-5dc1-8473-bb28236e46b2 | textbox | Date Completed:
a05478cb-1861-4c54-a6a7-fb0b997da5db | checkpoint | 2.12 Curing
2921c988-04ac-5b38-89cd-85dbb50c68f4 | note | FREQUENCY: Each concrete pour
3a720eb9-cb18-55c1-a796-4f1ecdc7175c | note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
05bb35a6-bd60-515b-a6ee-685a6d103819 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
d6fbbdff-ee97-53ef-aa2e-26a5e91af7f7 | note | INSPECTION/TEST METHOD: Checklist
011e8834-5cc3-5dee-90df-8e0ec97ac06e | note | RECORD OF CONFORMITY: This ITP signed off
03925ecb-764c-53df-8603-9b66b2ef9345 | note | IP
3754e5d2-5c23-5c37-90a0-535a90f537bb | note | RESPONSIBILITY: Fulton Hogan Engineer
30855506-716d-5453-b107-79e40b180459 | textbox | Date Completed:
1fe75e6f-2908-4d42-b7dd-8921ebe17f67 | checkpoint | 2.13 Tolerances
31b55436-7c42-5d5d-87ac-10c18f2e0a0f | note | FREQUENCY: Each concrete pour
77e2b882-db3a-5917-99c8-b6154b6aacfe | note | ACCEPTANCE CRITERIA: All concrete shall finish true to the dimensions, the following tolerances apply:
33da88de-1b5f-5f78-8664-2209a8f1e921 | note | ○ Plan dimension of slab +10,-10mm
aa18b75a-9ae6-5dca-9b54-a0555a0547ba | note | ○ Thickness of slab +10,-10mm
8fcc844d-3685-5357-bdb8-e7e361162706 | note | ○ Cover to reinforcement +5,-3mm
1710c542-d3e4-5873-bf65-9ba96b5b52a2 | note | ○ Finished level of slab +3,-3mm
1cbb1ca5-99ff-53c8-8280-73afd99e832b | note | ○ Foundation level of slab +0,-20mm
60cb65aa-e98e-54ec-ab50-77b106492a21 | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
888cd3a7-6d82-5dad-85ff-9771da59edd0 | note | INSPECTION/TEST METHOD: Checklist
f7c06dd0-e63e-5fdb-b6f3-9793cbdbce56 | note | RECORD OF CONFORMITY: This ITP signed off
ac6a16f0-b3f0-5ff9-89d5-98f74373125f | note | IP
62ceab1d-c8ff-504d-8708-4d1d2f873d97 | note | RESPONSIBILITY: Fulton Hogan Engineer
a3f5d94e-1d58-514c-9628-eaae9544abf4 | textbox | Date Completed:
6b3876d7-b771-4bea-91f5-3c6b4261e615 | checkpoint | 2.14 Slab finish
c188220a-015d-57c7-b160-38e8b7f8bc01 | note | FREQUENCY: Where applicable - if track is Type 1 structure
8c88fea3-f6a3-5ebc-9aa5-b854791484c0 | note | ACCEPTANCE CRITERIA: Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities. All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections. A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C - This is only applicable for T-rail/Vignole rail profiles. The slab surfaces shall be broomed to provide a non-slip finish.
46040cc9-e985-574d-88ec-c011dd33de0d | note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
bce2287d-0c87-56ad-9f97-cb5a4978b076 | note | INSPECTION/TEST METHOD: Checklist
7b3763fe-8127-5f01-b23b-60a8653356f1 | note | RECORD OF CONFORMITY: This ITP signed off
fb7e1f42-1e9b-5e51-ab25-94b98e537ca6 | note | IP
eb946e07-fa9e-579a-8970-3736644a6be6 | note | RESPONSIBILITY: Fulton Hogan Engineer
b116e81b-5b1f-5193-988c-e7f111912b26 | textbox | Date Completed:
46820734-a4df-4363-806a-f65c740dc9c0 | checkpoint | 2.15 Post Pour Inspection
aa3b0bec-1289-56a1-b7e3-e2e25c60d0df | note | FREQUENCY: Each Lot
17f33891-2581-5b20-bc7d-c01afe3b0e3d | note | ACCEPTANCE CRITERIA: Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
483e44b6-65cc-5c92-9ee2-8d9b77d67e2e | note | ○ Ensure no defects are present in slab
9c7f1d48-41d6-59c1-83c5-349bf852b61e | note | ○ Complete Fulton Hogan Post Pour Checklist
236a63e5-e6ed-5e12-b360-c8d8dcf85693 | note | REFERENCE DOCUMENTS: CE-019-ST-0033
96754e11-7984-5d19-9499-4074a104eaa4 | note | INSPECTION/TEST METHOD: Visual Inspection
58301253-4d8b-541a-8e29-87cf6cc00717 | note | RECORD OF CONFORMITY: Post pour checklist
11c0e0a5-749b-566e-a112-62929f030184 | note | IP
55805319-2aa7-5640-9871-61aafe6ffdc5 | note | RESPONSIBILITY: Fulton Hogan Engineer
4791f9e1-cea7-5a1d-be16-2e0023451c23 | textbox | Date Completed:
757899ff-173f-457b-8166-4a772dca586b | checkpoint | Final Inspection
e3a3162c-4cd9-5e9d-8bdc-248d7256de98 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
008950f8-18a2-5331-9eeb-0bdc81cdccee | textbox | Print Name:
39812f43-d829-5ff6-8308-ce968981f8ec | textbox | Position:
e4d4a407-1abf-596f-ae9c-c963e4ce5f32 | textbox | Date:
236d0ca9-1dbe-43bc-9e3d-e443583cced6 | checklist | ITP-008 - Hot Mix Asphalt Rev2 | itp | ITP-008 - Hot Mix Asphalt Rev2
ab8b454a-269d-447f-9792-de02429896e1 | section | Preliminary Works
b78187e2-0052-4c2d-96d7-d0ae7726f3fa | checkpoint | 1.1 Submission of Mix Design
2b395655-ec33-5750-a26f-0372907cdd47 | note | FREQUENCY: Prior to commencing paving
cddd991d-4654-5ddb-8055-e1edb5963212 | note | ACCEPTANCE CRITERIA: Ensure the correct mix design has been registered and is approved by Superintendent prior to laying mix according to standard track structure drawings
eb86cf35-c7e8-5bf6-8120-2c695eee38f5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
db2f0c9f-041f-562b-ad20-8910593b26eb | note | INSPECTION/TEST METHOD: Correspondance of receival of mix design
7d848311-8133-5319-9e63-e0914326da15 | note | RECORD OF CONFORMITY: Superintendent approval Completed ITP
1fd079a3-de88-5ca3-b250-48903f61b78b | note | HP
ac5e1ceb-ff55-5f8d-811f-d9fc73167882 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
139cfe48-18cf-5db2-95c1-3555501471cc | textbox | Date Completed:
7e567d7d-1367-49b4-b5e5-09a6e617bc78 | signoff | AUTHORITY HOLDPOINT
afbfd9c9-52af-4b48-bc2a-a80bc4e01c8d | checkpoint | 1.2 Site Inspection and Base Condition
0d69bc9c-cb96-5e33-90ff-a5e8fb34a2d1 | note | FREQUENCY: Prior to commencing paving
21dc2138-bd6d-5e27-9c3a-6f1f2a8d1a6b | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
8b4563ef-1b77-5135-b8a4-6514a32d308d | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
c1ac4093-0c45-5eb4-a5f4-b31a85eb9646 | note | INSPECTION/TEST METHOD: Visual Inspection
54d3f567-dde4-59be-9cec-44e9317a2594 | note | RECORD OF CONFORMITY: ITP Signed
51bde9ef-137c-5aa1-8bb8-267c151d3a74 | note | WP
bb699df8-9fde-5fd5-b56a-e5c3dcb7c603 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f1212cae-09d5-5c02-828c-d9c1f95470ff | textbox | Date Completed:
6e5caaac-a465-42b5-9040-c15b7c0f409b | checkpoint | 1.3 Ambient Conditions for Placing
e6da0040-7f0d-504f-9f1a-e876e8f3031d | note | FREQUENCY: Prior to commencing paving
a5d39f8d-d2d7-56a4-a70e-304a13d4d50f | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
0f94b8aa-5293-5faf-990e-8acea3f962fb | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
31903b01-8e8d-5f7f-a30f-2b75cb4bdf55 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
df543455-e4e8-54ed-9e8e-75361f32a5a5 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.17
dabb1482-3d36-5370-a772-1319852df0e4 | note | INSPECTION/TEST METHOD: Verify
0db9d59c-977f-53c4-8b25-95f538809c44 | note | RECORD OF CONFORMITY: Thermometer
0b1b208a-94a6-5f0c-84dc-950f3b781c73 | note | IP
70c2064f-0e7c-54fc-a89c-cdf3bedb10fa | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
fc0f0022-6073-5beb-8d55-66f8e6a07d07 | textbox | Date Completed:
a5590c18-b2db-4d31-8fe5-c3bd94dd66cb | checkpoint | 1.4 Planning of Joints
56b51028-80ad-51b3-883a-3eead987bb9a | note | FREQUENCY: Prior to commencing paving
6f475090-dbe8-5015-9053-3cdd1fcbbbbc | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
0fa52da1-0d88-5ba3-bcff-cdbc5e800166 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
48d02b08-27b7-5595-908b-a624843e63d4 | note | ○ Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
7cf3ac58-74a9-530b-ad2d-c61949c69292 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (b) & (c) Pavement Drawings
6deb95a3-3f04-5c7f-995a-542d61761328 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
7d646610-e5b7-52d2-bf1f-c1e139194dab | note | RECORD OF CONFORMITY: Paving Plan
127631fd-4843-5d66-9f03-99422ca18dd7 | note | WP
8acfffca-9836-539c-af42-4d1ff99a97f6 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
de3b50de-0f0f-5598-9799-0673ca967a3a | textbox | Date Completed:
94aaf358-ea9e-4fff-bef5-01d9f17c6708 | checkpoint | 1.5 Longitudinal Joints with existing Pavement
8d5919b6-95b3-5873-8fdf-f89f6f964f0a | note | FREQUENCY: Prior to commencing paving
9b4bb763-a609-5f8d-80a4-a5fb6e09cc6d | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
f5d84aef-70e5-5656-9e55-e155d95c6b58 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
de757b77-9dc0-59a1-90da-1832c57af20c | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.21 (c), Project Specs. Section 3040.06 (d)(vii)
e75f94ea-5e45-50a2-bb94-bc1067001b36 | note | INSPECTION/TEST METHOD: Visual Inspection
17726831-2077-53c1-9988-a72b9d2d4519 | note | RECORD OF CONFORMITY: ITP Signed
d1f2c18d-1ad2-5e0f-b3fc-49b62572358c | note | WP
55185c2d-172e-5094-8555-e50667e1df18 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3c2a57d3-830a-5dcf-ba0b-daae049ebe4c | textbox | Date Completed:
e8974e24-3c9e-466c-beed-61e696fcb1cd | section | Asphalt Placement works
4452477b-8103-4b94-86fe-e88676c759d5 | checkpoint | 2.1 Tack Coat (CRS 60 emulsion)
584ab8d6-a5c3-54d8-88bd-1803c2e4827e | note | FREQUENCY: Prior to commencing paving
00eec974-3db0-50a6-8036-eee09208a775 | note | ACCEPTANCE CRITERIA: Tack coat (CRS 60 emulsion) to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
adc4f2d7-012a-5ea6-95e5-7668bf5bea9a | note | REFERENCE DOCUMENTS: Vicroads Spec 407.19, AS2150 11
159f23c5-2d20-5bf9-8b74-f084cb0972ab | note | INSPECTION/TEST METHOD: Visual Inspection
5f23745b-03f0-5769-abf3-69dd25cfa5c5 | note | RECORD OF CONFORMITY: Spray area
4778cf80-0d8f-580e-965d-6d3108b39b5e | note | WP
35925c5e-579e-5e9b-bc67-352d78cc6983 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
83fcea8e-78bf-598f-8866-7445a31fd0d7 | textbox | Date Completed:
18a22299-20a9-41c1-9801-2ae186325702 | checkpoint | 2.2 Commencement of Placing
4812370d-383f-5e74-af8e-d2480ad9ee5b | note | FREQUENCY: Prior to commencing Paving
c522ade1-3968-5c29-a792-bfbb91bbc998 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
d44af5b3-234b-5785-831b-31758b8e961f | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.23
34c204b4-26e7-57df-96c1-315f893f7d5d | note | INSPECTION/TEST METHOD: Visual Inspection
47d91424-703e-5891-9556-112c7c900f2e | note | RECORD OF CONFORMITY: ITP Signed
07ddad04-b24e-5272-a358-9e90341492ea | note | HP
0caf5ba8-d081-59f6-9d50-a74676e449c6 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
5f631bb8-2932-5c80-95f1-b04a7325cfba | textbox | Date Completed:
7eb1655b-39a7-4980-975d-fc5f15a1b6ea | signoff | AUTHORITY HOLDPOINT
ae072953-9568-4384-99f7-1a5c904ee8bc | checkpoint | 2.3 Mix Design Confirmation
b81d76ce-6340-59e3-b0f2-a8265a6cea86 | note | FREQUENCY: Each lot
e3fd5e3f-1d03-5287-9110-1feec79b4121 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. Asphalt wearing and base layer mixes must abide to IFC drawings and be as specified in standard tram track drawings.
1cf5690d-8036-5eb9-b290-fabe5f2d41ca | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 STD_T9010
ff427e73-2e41-5ec0-9799-03ee63277362 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
168bf149-a4e5-5ea2-8400-7459db8a944f | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
a45f3830-f5d3-5d49-bc0c-d46bb080ded7 | note | HP*
dde0d3cd-3ee4-55e1-93d9-717e7facd4fd | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1a8f3542-4ece-5892-844a-bc7221f94c7e | textbox | Date Completed:
e279b6be-371e-4374-a1f4-ab5a5ad00259 | checkpoint | 2.4 Delivery of Mix
d39f2d89-c874-5dcc-8281-5c3f561c7f6a | note | FREQUENCY: Each load
77f23f6f-3196-5912-ab11-289161d58242 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
625c330d-5613-585e-a3ec-4bd6766123c6 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.20, Table 407.111
0643621c-5c56-516e-b694-b3d11cdcd634 | note | INSPECTION/TEST METHOD: Visual Inspection
c3248451-608d-5bbe-87e9-95f0dffeebe4 | note | RECORD OF CONFORMITY: Delivery Docket
0f689bd3-987a-57a9-8745-eee0f8484671 | note | WP
6aa11af9-e051-58bc-b33f-d9c1b482ab59 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
96c0e2a0-7b67-5420-bad8-06a683c17e53 | textbox | Date Completed:
1faeda92-00bb-4897-ae86-928340a309b0 | checkpoint | 2.5 Traceability
93d45484-7bef-5b2a-993f-ae26c2b7b2ac | note | FREQUENCY: Each lot
4c52c24b-0115-5a3d-9f6f-ba56396975aa | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
541a67d0-d622-5e94-800b-5be20edf8b71 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
8d11682c-49f3-5ad8-ab72-2c44da1ccca7 | note | INSPECTION/TEST METHOD: Verify
50a494cc-2d53-5813-bb70-2732a9d1c81e | note | RECORD OF CONFORMITY: Daily Lot Record
b0a14ee4-79d1-5b9c-a102-cdd84350a4ed | note | IP
c841ecb5-d6e7-561f-8bec-bc4b92adbb2f | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2e0f1741-f8de-5960-967d-2d8e9be41069 | textbox | Date Completed:
7fad8159-04c4-4788-808b-7171cc75fd2a | checkpoint | 2.6 Layer Thickness and Level Control
c8b6f338-080e-56f6-acfe-10b44de68c77 | note | FREQUENCY: Regularly during paving
eca5afc4-c3e6-5c4a-8509-684367394d0b | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
7e94ea90-23e4-5c48-aaec-730c98aad4bd | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.27 (a) & (b) Drawings
3821b1d1-09ee-5baf-b33c-e8f10a5a3610 | note | INSPECTION/TEST METHOD: Verify
95d3577e-d48d-5515-94d9-c31823095801 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
de3dadcf-be84-5fd0-8f73-3eedd1fba56b | note | WP
a7a757aa-c472-535e-a8d5-40b7d3e672c0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
034aa081-c84f-543f-8f89-633ef14b15fb | textbox | Date Completed:
08f82a3f-7e5e-426f-82d4-11e7a587b008 | checkpoint | 2.7 Surface Finish of Wearing Course
921a18c2-1a1c-5226-a2ce-7de31328b7c5 | note | FREQUENCY: During paving and after final roll
c6597de9-81a5-5339-b26e-61c19a117bb8 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
96e8c2d2-53fa-5b72-b383-455ed44e38eb | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(i)
d995c670-0622-5762-9a99-0d779e1e8905 | note | INSPECTION/TEST METHOD: Visual Inspection
c5f3f5a8-1d9b-594e-a5ec-a7da888ec36a | note | RECORD OF CONFORMITY: ITP Signed
84b16d92-c6fa-511a-8e45-6df82f69e003 | note | WP
511e13b3-bf50-570d-8448-168480b28403 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
00ea95eb-f056-5135-8534-5f559a3c7ace | textbox | Date Completed:
8030687c-ed56-463a-ba72-8a90a9a5080d | checkpoint | 2.8 Alignment of layers not placed against concrete edge
a55eebc9-87ac-58be-be13-ab210cc502f0 | note | FREQUENCY: During paving and at completion of work
f677301a-ec42-56dd-82ec-beb4e1811230 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
6ca994af-d5a1-5ad2-a8de-00e461a7babc | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
d07de97d-5c5b-51f3-8317-9592a288a6ad | note | REFERENCE DOCUMENTS: VicRoads Spec Cl.407.29 (a)(iv), Drawings
888e95de-885e-52c4-91f3-efbe7445a7ed | note | INSPECTION/TEST METHOD: Visual Inspection
87496c6e-8386-598a-8352-b7354ceb6f9e | note | RECORD OF CONFORMITY: ITP Signed
f08407eb-b5a9-5726-81c9-11f7cc1c3e0e | note | IP
ea999281-582d-5865-845c-8f903d06c541 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1bc72544-cc4c-502f-9095-1fadd51f0085 | textbox | Date Completed:
b33a7384-20dd-46b1-be8e-9cefdc231824 | section | Testing
a331add4-2abf-416e-bf2d-34c46a2d2fa5 | checkpoint | 3.1 Compaction
42e7bc7b-b48b-5a57-a9d0-4e177cbce0c7 | note | FREQUENCY: Per Lot
fdc2609d-a5e9-576c-8fdd-d9c607a7b5b1 | note | ACCEPTANCE CRITERIA: For wearing course layers <50mm, if characteristic density ratio is:
029a2289-e098-5108-953a-d7b0eb1980db | note | ○ 94.0% or greater Accept lot
abe18538-a444-51e2-88e9-91b99ad5ac75 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
7788dcc9-07e4-56af-8a7c-1481f9c392f2 | note | ○ Wearing course shall be tested at a frequency of 6 per lot, where the lot is either of 4000m2 or one days production
04155448-2709-5f8d-a866-7c4b6bf27a12 | note | REFERENCE DOCUMENTS: VicRoads Spec Table 407.271
192fbe81-eafb-59f7-b191-892d230ef4d3 | note | INSPECTION/TEST METHOD: Verify
f8d0e71c-2b97-545a-a9fa-fa3abcec4d1f | note | RECORD OF CONFORMITY: Test Report
1efe2fce-e37e-535c-95e8-89c1a63bb758 | note | TP
10cef8a9-772b-57e7-a5e7-f70fed8931be | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
54e7070a-a96d-55e7-b5ce-57414454c459 | textbox | Date Completed:
c31d345a-a686-4e66-bc34-6e2dd6edf763 | checkpoint | Final Inspection
51f6dde7-277d-5238-8eee-8980844b3c3b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
23823741-c5d7-5062-b252-aa655912203c | textbox | Print Name:
9b0c4a74-1cdc-55ec-a99c-d18a09da47f9 | textbox | Position:
7d9a69b7-1b6f-58f2-ab1b-0e0ed93345c1 | textbox | Date:
1dc3849a-2217-49c6-9571-96ad1d5887e6 | checklist | ITP-014 - Bluestone Kerb Installation (MCC) | itp | ITP-014 - Bluestone Kerb Installation (MCC)
d2c817ab-65c1-4b18-a75d-499b5bb7fe8e | section | Preliminary Works
c3887d29-3eeb-4988-8b09-bfb5b893e39e | checkpoint | 1.1 Check for Correct Documentation
c7b2c8f9-4a2d-5f25-967e-0ef6cf53be8e | note | FREQUENCY: Prior to Commencing Activity
8f5044aa-aeeb-5941-bba3-ada1db697b35 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
7570c808-d396-592f-800d-13dc95889ab5 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
e679e4b5-fa03-5b93-9ddd-0042b2cd484c | note | INSPECTION/TEST METHOD: Visual Inspection
40a8f19b-083e-5e55-bd59-7e871f5046fa | note | RECORD OF CONFORMITY: This ITP Signed off
bd388b3e-ffd8-5f0d-a682-8a0c6159691b | note | HP*
0325a676-f475-5f0d-953c-104cf270186f | note | RESPONSIBILITY: Fulton Hogan Engineer
3517870c-4935-5c36-9831-453b9915d8f9 | textbox | Date Completed:
ac361ec7-cb6a-47b2-88dc-211791e56fef | checkpoint | 1.2 Implementation of all measures and controls
5038b01b-f611-5696-94bc-67357a078130 | note | FREQUENCY: Prior to Commencing Activity
570f4a5a-0f2e-5b00-b599-ed9dacf7067c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
a06a4101-be33-5cef-b2c4-fc62ae1103e4 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
14c7a067-5188-5c78-abde-d2900fe55701 | note | INSPECTION/TEST METHOD: Inspection
042f4859-ccec-5a3a-8eff-d2a40759bbdb | note | RECORD OF CONFORMITY: This ITP Signed off
a9d95449-72ba-5932-8b73-41d4bc577453 | note | HP*
4b391f71-f347-5e63-8c94-17b7ad1c09e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
5f11b731-0915-5035-b745-78ce79b852dc | textbox | Date Completed:
28a55df2-b448-491d-a574-d7cec16e847f | checkpoint | 1.3 Existing Bluestone Kerb Demolition
d4dddd5b-728d-5054-9c39-6616b1f6c20a | note | FREQUENCY: Each Lot
05fd51d9-f142-574a-aa5d-5e3225139101 | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
858f4af3-99a1-5b7e-bb5a-c8ce2063e1c3 | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
c3b70666-9365-5427-b983-f34153f584b5 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment
fcf160b7-273c-5f75-9990-d987689354ec | note | REFERENCE DOCUMENTS: Work Procedure
4aa6d46c-4a4c-524b-893d-682173d5d82a | note | INSPECTION/TEST METHOD: Inspection
d0f48767-cb10-5fce-a39a-352f4bfd6d44 | note | RECORD OF CONFORMITY: This ITP Signed off
497f6b03-5601-5486-988e-43a82c9b6d6b | note | IP
ef9fdf7c-8905-5d78-9b39-4f6468ae992a | note | RESPONSIBILITY: Fulton Hogan Engineer
e785525a-78d3-5d00-a1a2-877927f22811 | textbox | Date Completed:
771031e9-3ba8-464e-9ab6-5d57c0d6b946 | checkpoint | 1.4 Setting out
abdeaf7d-fb1a-55ab-b7c0-9e3cc8d80fc1 | note | FREQUENCY: Each Lot
aa85e4cf-36f6-52ee-9772-26bc73eb5b61 | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
037f9136-e019-5cd8-8879-e1fe5534dec8 | note | ○ Alignment of new kerb shall be marked out using string line
827942ac-4e54-5b46-be66-adfa6d5e25f8 | note | REFERENCE DOCUMENTS: Work Procedure
20015643-9d91-51d2-a367-2ff6aef472f2 | note | INSPECTION/TEST METHOD: Inspection
50dd4e51-6be3-5055-b4d2-4deff56b133f | note | RECORD OF CONFORMITY: This ITP Signed off
936f04ee-3ce7-56c7-9b5f-10471708e2d6 | note | HP*
24812f62-585d-53f8-a58e-341407cd1ebf | note | RESPONSIBILITY: Fulton Hogan Engineer
e5df97ce-b592-5664-bd63-720f4674d796 | textbox | Date Completed:
5a152b0f-86eb-4430-9100-a764f3f96885 | section | Construction Works
bf8a1ac3-fe79-49a7-a511-5e179e0e73fe | checkpoint | 2.1 Saw cut (if required)
6d35e1d9-79db-5809-8d18-271482875f30 | note | FREQUENCY: Each Lot
146b2034-435e-54a4-abeb-f2d4b21da390 | note | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements:
09bbdea0-2594-5c1c-a6fc-65a7429567b0 | note | – Footpath: Minimum 75mm
ddabbda7-e9d7-53b0-842c-d7a72cae459b | note | – Roadway: Minimum 125mm
cfe3ca11-708d-5375-b92c-6ca45131c2ca | note | ○ Excavate to allow for design heights
8cd9c598-cc3f-51f4-aac1-e69e37c69ca7 | note | REFERENCE DOCUMENTS: CoM TS, Sawn Bluestone cl 2.0
3f6fd8e2-e2d0-56f5-9d4a-e5599f6fb5e6 | note | INSPECTION/TEST METHOD: Visual Inspection
2bc3c57d-66d7-558d-8152-a66f9080e3c9 | note | RECORD OF CONFORMITY: This ITP Signed off
e08bc18f-65b9-5788-a21c-230b446a3b59 | note | IP
0df90d41-e444-5b96-bbfe-2d0f971a9ceb | note | RESPONSIBILITY: Fulton Hogan Engineer
0a32d26f-0fd8-5d74-9fd3-db5d411381ad | textbox | Date Completed:
e16c6d7c-a197-476f-af83-b5a9786118fd | checkpoint | 2.2 Concrete Placement and Setting
00f46def-088e-53ba-a817-3eb3f41cd62d | note | FREQUENCY: Each Lot
cb30384f-e816-509a-a32f-199fa114d8a8 | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
78d8f883-eed7-5c02-b760-2186253e4f8b | note | ○ Gaps of >10-30mm< shall be provided and filled with mortar
8b3908e6-06af-5aed-b1ed-bec6c3db1b26 | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
498ec3b7-015d-50c9-87f4-109a58ead9cb | note | INSPECTION/TEST METHOD: Visual Inspection
404f6567-342f-5e65-9543-28285b0b8522 | note | RECORD OF CONFORMITY: This ITP Signed off
63a0bc6a-98c6-5a9d-ade7-9899ac1bb02c | note | IP
6dfe3648-cecc-5851-99f4-04b3af4d9df5 | note | RESPONSIBILITY: Fulton Hogan Engineer
cd6cd128-5ae6-5c82-9330-3d178dd37e08 | textbox | Date Completed:
98ddef9d-184b-4aed-8ebc-6980dc8808b0 | checkpoint | 2.3 Mortar Mix
5e96af49-ba3a-5bdb-ade6-354bbc44e6f9 | note | FREQUENCY: Each Lot
3b0d617a-9863-55b7-9ac0-32c675384f43 | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
efd9e545-c0d3-57d5-8318-76f533806696 | note | ○ 16% cement
b7ebeae1-400c-5fab-9d18-5f206629ac7c | note | ○ 16% stonedust
8a173603-5ac1-5ac2-aa71-39e5b52c8674 | note | ○ 67% blended wash sand
26caaed8-c534-514f-a579-7e3bc19f0311 | note | ○ 1% lime ready mix grout
79d210e9-f9c4-53f9-a9ac-509254dd0a8b | note | REFERENCE DOCUMENTS: CoM TS, Sawn Bluestone cl 4, AS 3972 CoM SD 1P 50406
91c4f283-f455-5864-956e-b77ef581268d | note | INSPECTION/TEST METHOD: Verify
ed07ca2a-ae53-599c-9ceb-1eb9910b0bef | note | RECORD OF CONFORMITY: This ITP Signed off
bc0b6c9c-5f41-5188-aabe-65796d45e650 | note | IP
ee2f4eae-62fe-5e22-ae98-389e89e058cc | note | RESPONSIBILITY: Fulton Hogan Engineer
9a7cf0f9-756a-580f-b9fd-6d7298df1149 | textbox | Date Completed:
0e6f4645-3e7c-401a-a7d9-036113cc3eeb | checkpoint | Final Inspection
27c9f7d4-2bd2-516d-8eea-924fe06b51b7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6c35f8ff-e627-56e5-91ef-a6a970c94a08 | textbox | Print Name:
da683e6d-6cfa-5fe9-ae40-d18b27a22e90 | textbox | Position:
3a721201-90f6-5035-818f-542df3f4463a | textbox | Date:
7dfa0461-cfa2-42ca-b218-6063deb8d49f | checklist | ITP-019 - Line Marking Rev3 | itp | ITP-019 - Line Marking Rev3
e8b8890b-72a9-439a-af4d-2cbe6890d27f | section | Preliminary Works
b61ec822-03c7-4997-a9eb-b1f4639c952f | checkpoint | 1.1 Check for correct documentation
980dc879-48eb-5de7-aec9-9d9214754acd | note | FREQUENCY: Prior to commencing any activity
636068ee-b45a-5f96-8cc5-b6a47f149eb6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
15d36303-1a7d-5f31-94ed-1bcc7fc8027e | note | – using the correct and complete set of drawings
111609c7-4237-5d9d-8ccd-c17c43b347c5 | note | – all drawings are the latest revision
f5872759-1b9b-5630-8c21-4eab6b962a97 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c7185f7c-5dd3-5b02-986c-1e8709a67db6 | note | INSPECTION/TEST METHOD: Visual inspection
4bca6641-7814-50ec-871e-cf92ba7793d5 | note | RECORD OF CONFORMITY: This ITP signed off
bd6d53a7-ff1c-5e75-ae5a-492eb4156bcb | note | WP
42815dfe-6e52-5179-9975-1f9afbbeec91 | note | RESPONSIBILITY: Fulton Hogan Engineer
6b45f401-8b68-5fc9-aacb-20da75ccee88 | textbox | Date Completed:
7973f941-6477-4006-b40b-979b2024ddab | checkpoint | 1.2 Implementation of all measures and controls
47b93fa5-09f9-580f-9617-13545cbeda7f | note | FREQUENCY: Prior to commencing any activity
63dc848b-feee-5c03-8745-315de03750c7 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
89c765c9-18fc-555d-9f43-d27a899621d2 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
29ad6ad1-b054-5ec5-a909-aaf5e2766df3 | note | INSPECTION/TEST METHOD: Visual Inspection
d5ee4e91-9076-5af6-bbfd-c0d276089d28 | note | RECORD OF CONFORMITY: This ITP signed off
4d97e51a-c3e0-5661-8419-416abbf399f6 | note | WP
5dd749c1-77a9-5f0f-a6b7-643cf68ecc32 | note | RESPONSIBILITY: Fulton Hogan Engineer
abecf0cd-01b3-556e-b969-70f50e6dd600 | textbox | Date Completed:
b1a56df4-8594-42c4-8e0c-0a1858688d28 | section | Construction Works
bd2e832b-bff3-4af2-bfb4-e39af4272dcb | checkpoint | 2.1 Setting Out
d0df2840-953f-5054-88e5-880f0305aa03 | note | FREQUENCY: Prior to start
f4612f75-9b77-57ca-8cf0-7f44067d99e7 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
c07f2cae-4639-5a64-8968-b9c1a46b7285 | note | REFERENCE DOCUMENTS: Drawings
589f5597-ed7d-5ad7-a222-7c56b848b33f | note | INSPECTION/TEST METHOD: Visual Inspection
66fb25e4-0767-54b7-9a6f-f06463d7748e | note | RECORD OF CONFORMITY: This ITP signed off
3cf7adb5-a148-5ba5-a35f-a9996f50b5cd | note | IP
faa86385-90da-5664-910f-796a6d231834 | note | RESPONSIBILITY: Fulton Hogan Engineer
daba2e4d-1064-5271-b66e-2a1ba90cf95f | textbox | Date Completed:
0e0b7369-a662-44d1-8e08-733918827ba0 | checkpoint | 2.2 Position of Markings
5f2ffd22-f314-5cf6-a333-48da21fe0900 | note | FREQUENCY: Prior to application
c3f310e9-a6d1-59c3-880a-e7b539f7883e | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
3a4f4822-51af-5b2a-8806-a1303fb2d525 | note | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2.
cf74e626-8c71-5601-a196-3b299b8c3836 | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2, Yarra Trams Drawing STD_T9010,
64f695c8-a183-53b7-bb17-441104aac070 | note | INSPECTION/TEST METHOD: Visual inspection
6bc75e89-e8cd-5f18-8b7c-9d4f71147f63 | note | RECORD OF CONFORMITY: This ITP signed off
5b9469ee-65b7-5cb9-ba4e-20a68370911a | note | HP
eb369424-e5fa-55a5-93ad-84c9e4fcb31f | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
a4058946-983e-5c3e-9257-388ffb1b39c0 | textbox | Date Completed:
dcdbbcc4-53f2-481c-8de7-a9ec7af9f187 | signoff | AUTHORITY HOLDPOINT
933303f9-6323-4b1a-a866-5c6fe1f3312a | checkpoint | 2.3 Tolerance of Pavement Markings
9d3b48ae-0914-5a3c-90f4-cc69766a9889 | note | FREQUENCY: Each lot
2598711f-719f-540a-ba3e-8f12aa36cbd7 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with tolerances outlined whereby the outer edge of the tram track clearance line marking shall be offset 0.9m from the running edge of the rail with a tolerance of +50 mm to -25 mm as per IFC drawings. The distance between the centreline of the marking and the centreline of the set out mark shall be <30 mm.
0c81b5fc-6106-5eb3-b814-d6c1367fc386 | note | REFERENCE DOCUMENTS: IFC Drawings VicRoads Sect 721 Table 721.A101(A)
4fd769ac-ff90-5974-bdea-d57e8550df09 | note | INSPECTION/TEST METHOD: Visual inspection
4ac36ec8-bf56-56d0-b5c3-aed8b375571e | note | RECORD OF CONFORMITY: This ITP signed off
e49ee534-9b73-5865-85f7-028f979a9622 | note | IP
db44a852-525d-5e8a-a948-73f69d1cc162 | note | RESPONSIBILITY: Fulton Hogan Engineer
f85f57b6-9458-5407-bf41-bdb7e62847ad | textbox | Date Completed:
7fe2c553-8702-40ec-953e-ee1560da8b6a | checkpoint | 2.4 Raised Pavement Markings
46a6c6a1-b0ff-5ed6-b804-ef6f38825f14 | note | FREQUENCY: Each lot
f5edff0e-bb50-5c2f-b881-4af872e8c965 | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances and positionings as outlined in Table 721.A101(B) when installing raised pavement markings.
d77a6422-aa7d-5192-b1c7-d1cbc3fa0cb6 | note | REFERENCE DOCUMENTS: VicRoads Sect 721 Table 721.A101(B)
00229e95-6d55-5f44-87f9-3bea24ccdd4d | note | INSPECTION/TEST METHOD: Visual inspection
ff92e870-cf96-5e16-afcd-5ae286489dbf | note | RECORD OF CONFORMITY: This ITP signed off
2e9b1f59-ce83-56ad-b66b-7f8b2edf3f26 | note | IP
8276dab8-8598-51a3-a533-9fa5a7fbf17c | note | RESPONSIBILITY: Fulton Hogan Engineer
9138b059-9e49-5019-8205-66bec723fc3a | textbox | Date Completed:
b8fac63d-dac9-41a0-bb22-8ca329a80d85 | checkpoint | Final Inspection
3152e8cf-199c-534f-b687-275247b0457b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ba585c6c-0aaa-5619-9515-08bf5030acfd | textbox | Print Name:
e543df12-f0a1-51fa-bfee-58d66d3e3f86 | textbox | Position:
e3b575ca-b31f-58d3-8689-6eed07502c41 | textbox | Date:
652d4fb3-ae64-4b35-8b07-8b3a57b4814f | checklist | ITP-020 - Exothermic Welding | itp | ITP-020 - Exothermic Welding
172f8f3b-24ae-4cec-90d4-638266e4c0af | section | Preliminary Works
903c4a71-6b8c-40f0-b2ab-8bf8fd29e277 | checkpoint | 1.1 Check for correct documentation
48a46ace-63d7-59a0-870b-58d1d25773d0 | note | FREQUENCY: Prior to commencing any activity
6ef25c91-ffaf-5543-b35a-9510b508d2eb | note | ACCEPTANCE CRITERIA: Ensure that all employees and contractors are using the most current and complete set of drawings
993a521f-edee-5982-8dc5-c8a49b366831 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8a5be968-836a-5e42-aa96-bfcbc9b8e015 | note | INSPECTION/TEST METHOD: Visual inspection
9bc08308-421c-5b68-bd48-cee98e02c2ca | note | RECORD OF CONFORMITY: This ITP signed off
fcad5060-93a3-5423-a8fd-a9a6b735e308 | note | HP*
230e6c22-5b55-57ad-a3b3-b4c284dfae9f | note | RESPONSIBILITY: Fulton Hogan Engineer
67fa5725-932a-5bdb-9b45-71a3d0122632 | textbox | Date Completed:
ac576aa6-3f35-4899-95fd-3c2754f02e10 | checkpoint | 1.2 Implementation of all measures and controls
374724a9-005d-56b7-a62a-ac6915e03e14 | note | FREQUENCY: Prior to commencing any activity
a71a9056-a147-5dfe-8caf-8862e3e28246 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
07586753-cf09-5f06-ada3-bf676ec43294 | note | ○ Ensure that all employees and contractors involved in the welding process have been inducted onto the relevant Hotworks permit
decf7e6b-8149-575f-ab6b-e014c0c1f8b2 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
60a3ea2a-3281-5d9c-9b3b-291a9be33362 | note | INSPECTION/TEST METHOD: Visual Inspection
60852c22-f1de-5f64-835a-8eb39ac86435 | note | RECORD OF CONFORMITY: This ITP signed off
e3b2b0cb-502a-5b29-9e2c-b4dffc7cee92 | note | IP
3f531290-0530-53a6-b173-787903b8aae7 | note | RESPONSIBILITY: Fulton Hogan Engineer
592d8017-0a78-56fa-83e7-e8ef35d1a9b1 | textbox | Date Completed:
0087034c-8656-405c-9d21-72c804c9f7c8 | checkpoint | 1.5 Materials Check
81fc62dd-36c9-59c7-94ce-683217650733 | note | FREQUENCY: Prior to commencing any activity
3dcdccf6-24ac-583b-9805-a31132892e4d | note | ACCEPTANCE CRITERIA: Ensure the materials and equipment gathered are for the correct type of connection being made.
b69ee220-eb8d-5a91-80e0-5a834088504b | note | ○ Inspect the mould ID tag to ensure that it corresponds to the application, indicated by the following parameters:
33ba6cae-fae8-5b08-8007-822f1f05b3f2 | note | 1. Mould part number:
94d0834d-19a9-52dc-a19e-4bddb68c5994 | note | 2. Conductor size:
acc2466b-8497-576e-81c2-0f14990a690e | note | 3. Welding material required
9430a535-5643-5653-98ec-21b152499946 | note | ○ Check to ensure the graphite mould is not worn or broken, which could cause leakage of molten weld metal during the reaction.
805f2bd6-864f-5f0d-b762-cd6b911b1a02 | note | ○ Ensure a working fire extinguisher is available within 10 metres of the working area.
c1b5c03d-3fd8-50ae-a661-cc37620cb046 | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
85490e80-3786-5fe5-9d18-ab8cd208bbed | note | INSPECTION/TEST METHOD: Visual inspection
11f22de8-5aff-5a2a-8de4-99fc6cab9dde | note | RECORD OF CONFORMITY: This ITP signed off
d10732fd-26a8-5bca-965e-9787a3165954 | note | HP*
206aa14c-93b9-5cdd-b1b5-5f9d2a17f66d | note | RESPONSIBILITY: Fulton Hogan Engineer
65c393ba-996f-5f68-b2f4-737ae2b08dc1 | textbox | Date Completed:
d14a4de9-99e9-4d18-9712-d54a7c4aadd4 | section | Construction Works
954a145c-8198-4654-ada4-4de7d3a3337e | checkpoint | 2.1 Preparation
97772caf-04ad-5427-843d-3ba0692aa26a | note | FREQUENCY: Each Weld
d7d18cef-465e-5c4a-9157-407169bcc338 | note | ACCEPTANCE CRITERIA: Ensure the position of the conductors being welded is correct.
3e3a95e6-b596-5a42-9f15-5e0155a115f4 | note | ○ Heat mould to ensure it is dry.
bcf6e42a-134a-53f0-ad9c-85b40ea84754 | note | ○ Strip & clean conductors, ensure they are dry & clean.
a8ffec53-f4a0-5be0-9d57-774790694633 | note | REFERENCE DOCUMENTS: Design Drawings and Register
32f562a3-6cdb-5054-934d-b8c06decfc1d | note | INSPECTION/TEST METHOD: Visual inspection
781b5e6b-cb66-5148-abfe-ab38559a6643 | note | RECORD OF CONFORMITY: This ITP signed off
0bb2aea5-a27b-527e-b4d0-57f93b73e037 | note | IP
20dd1fcf-ec7d-52e1-8af7-6a269efd870e | note | RESPONSIBILITY: Fulton Hogan Engineer
48a92069-6b6c-5f92-b17e-84bfd299d621 | textbox | Date Completed:
8845d900-3e58-43e5-b9f5-864510309dbb | checkpoint | 2.2 Welding
f6388f94-be4c-55fc-8948-44235976f774 | note | FREQUENCY: Each Weld
2a763167-c79b-58df-8041-5c82f5efd4ed | note | ACCEPTANCE CRITERIA: Ensure conductors are correctly positioned in the mould, allowing the mould to close tightly.
1852c0f1-dbbc-5d8a-8c80-dadebbcc6dff | note | ○ Ensure welding material has been insected and is intact.
623651b3-8874-55f9-8d70-68c8b3231149 | note | ○ Ensure reaction is completed and molten material has solidified (allow 30 seconds post ignition)
77babafa-e78f-5006-9fe1-4c49aaf822ee | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
1c9b76bc-0150-5495-adbe-e5c95d4b84f0 | note | INSPECTION/TEST METHOD: Verify
a1421fe3-ac4c-5816-a6ec-46938cc7a1c6 | note | RECORD OF CONFORMITY: This ITP signed off
4099dfdc-1ccf-5bf3-b16b-c8f1e30f6a69 | note | IP
1562b777-e466-51dc-98ff-c1c6fede548f | note | RESPONSIBILITY: Fulton Hogan Engineer
9f695211-ff58-5f2d-82ee-61d1948b2c7d | textbox | Date Completed:
48724ca5-3f87-4640-917f-c048635908f2 | section | Testing
c0c87b7e-b815-4675-b439-5b7f174504da | checkpoint | 3.1 Weld Review
0baa4621-0059-5c70-aa7d-f15988e19a40 | note | FREQUENCY: Each lot
72c72b98-c0c3-5fb2-a3f1-b9a67faef9f1 | note | ACCEPTANCE CRITERIA: Ensure weld is inspected and that a quality connection has been made.All welds shall be inspected a Fulton Hogan engineer.
726c157b-4360-53ce-99fb-76d8f6905b7e | note | REFERENCE DOCUMENTS: Eritech CADWELD Exothermic Welding Manual Fig. 2, 3, 4
8b949a4f-fa60-5b17-a888-a39e2d22e047 | note | INSPECTION/TEST METHOD: Verify
20e77ed4-7d2d-598c-b2b0-05734418e302 | note | RECORD OF CONFORMITY: This ITP signed off
1a972cf0-321b-5f66-b86f-244ae74d8516 | note | TP
54b08cf7-71bd-5ede-88e2-3b736ce8a145 | note | RESPONSIBILITY: Fulton Hogan Engineer
b8915a78-f7fd-5bc6-8fe5-3e350c21e911 | textbox | Date Completed:
dc6ee1b6-bad8-47f3-a2de-aad0a324ad5b | checkpoint | Final Inspection
70f0794f-dd4a-520c-a93c-9bbf4b8db3b8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5a683724-e181-5a15-8389-b742dc4ff05d | textbox | Print Name:
72bf7fbb-5514-572c-92fc-d37ce33b654b | textbox | Position:
0f3b8ed1-d0d9-500f-95c5-178a3318690f | textbox | Date: