## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP-001 - Clearing & Grubbing | itp | ITP-001 - Clearing & Grubbing | 50a72da4-e22b-4596-b5d2-cfdd64193ec6
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check current drawings are used on site for works
ad5b8343-9e16-5a68-84c8-9f125f74fd5a | note | FREQUENCY: Prior to commencing any activity
81fcf058-ede8-5c19-8117-73e011715817 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
fe7b2c6b-6bb1-5ec8-a4e4-dc80061c5cb5 | note | – using the correct and complete set of drawings
4d5b1d63-b4e6-527b-9abd-1adb1b1eb147 | note | – all drawings are the latest revision
f6429b5d-dc66-5d03-aa97-a5f66497c0f0 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
a0eb38db-2438-5312-8ed4-f9fe17331376 | note | INSPECTION/TEST METHOD: Visual inspection
c4758d1c-82a6-53a0-b52f-7c4667a34815 | note | RECORD OF CONFORMITY: This ITP signed
1bd0119b-1d41-593a-a941-e0726a3c85d9 | note | HP*
d5bce240-59e6-540e-985f-3e1dcab45650 | note | RESPONSIBILITY: Site Engineer / Site Foreman
06ccbf4d-35b8-523e-a44d-832989da42db | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
15bf8e0f-fd7f-517f-bca0-a17eed77356a | note | FREQUENCY: Prior to commencing any activity
ceee0667-34f8-5da8-81df-31427e6d7351 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
8ff2d5c1-7839-5724-afbc-0ba5516bba1e | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
7d215039-b041-5ce1-ba50-54634c51a9e8 | note | INSPECTION/TEST METHOD: Visual Inspection
4877ad6e-208f-5c18-b84f-1239f49ec38d | note | RECORD OF CONFORMITY: This ITP signed
5e12d792-1ad0-5941-b9aa-534caf62cdee | note | HP*
b679d5a7-7e80-5128-9e9a-63f856852c08 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8048d4b5-5076-5bc9-8426-1b57ee56112a | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit issued
d5bddd23-f40b-5d78-812d-2ff9e22e72a5 | note | FREQUENCY: Prior to Commencing
df7feb52-634d-5d0e-88cc-08ce4ad27171 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
d2298f1a-daf3-57cf-9358-1186d4b9ea2b | note | REFERENCE DOCUMENTS: Excavation Permit
b05146dc-0dfb-519b-8ac7-27453fe5fa68 | note | INSPECTION/TEST METHOD: Document review
7738fe75-542b-5fb6-9cec-73739ea908e1 | note | RECORD OF CONFORMITY: Excavation Permit #
5e0b340e-b972-557a-b5d6-f61601046d83 | note | IP
0a5f2d05-cd6d-5505-a301-d007269551a9 | note | RESPONSIBILITY: Site Engineer
38196b76-273b-5cdc-8e86-941d67e53096 | date | Date Completed:
| checkpoint | 1.4 - Flora & Fauna
04dce6e2-9310-5be0-a600-5aaee9532782 | note | FREQUENCY: Prior to commencing clearing
2bed3460-71d3-5b7c-97b0-c593a7b30cbb | note | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
b66876ce-2d5f-534a-9ff5-8dbf530fcfb9 | note | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
b7211a29-e363-5df1-aebc-f9b5fed4f71d | note | INSPECTION/TEST METHOD: Visual Inspection
a53bfd46-6dc2-5c04-aa6b-f6acbb192e34 | note | RECORD OF CONFORMITY: This ITP Signed off
630d2bdf-97ff-5e4e-ba68-9ae4bfe831c3 | note | IP
44e72f47-4d96-5e7c-8f51-ea23cd2762f0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e08beb30-626d-516f-877a-0ce7cd9de0c7 | date | Date Completed:
| checkpoint | 1.5 - Permit to distrurb flora & fauna
c485f92b-af25-5570-8b76-dc879b4ca589 | note | FREQUENCY: Prior to commencing clearing
56a49ad5-2972-501b-8ba0-58b6c3feb195 | note | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
1ff3a9c0-688d-5da5-ab52-1fd337d7eaae | note | REFERENCE DOCUMENTS: Condition Plans endorsement
5c29bb88-b074-5e4e-abd1-391f5efa88d3 | note | INSPECTION/TEST METHOD: Visual Inspection
d13c8e4c-eb3a-5f48-b420-b37b46f77167 | note | RECORD OF CONFORMITY: This ITP Signed off
01b92c2e-220f-583b-82ee-6eb30cfbe83e | note | IP
be541503-324e-5201-babd-5ad2cddd80a0 | note | RESPONSIBILITY: Project Engineer
a4cf9dec-9fe6-5765-9c2a-bc8d15cb6a41 | date | Date Completed:
| section | 2 - Clear & Grub
| checkpoint | 2.1 - Define work area
7fc010db-4c79-5399-aadb-069aaa66baea | note | FREQUENCY: Prior to commencing clearing
7cedf6ef-78b5-56f3-909b-a77becdd13af | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
4503fdb2-533b-538c-8358-5268f2ced4d9 | note | REFERENCE DOCUMENTS: 201.1
b3da1e15-f23f-5caa-972b-13707765f5e8 | note | INSPECTION/TEST METHOD: Inspect
6ac61f65-d512-5c7b-8e4c-b5020dde2fdc | note | RECORD OF CONFORMITY: This ITP Signed off
aa3855d7-af71-5341-b06c-9f58c43b41e6 | note | HP
455d5db0-ceaa-5303-a7a2-a51e41d92446 | note | RESPONSIBILITY: Project Engineer/ Superintendent
d58a7900-6549-54c2-960f-ee0b9423e4a9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Cultural Heritage and Areas of Significance
59decaba-86c2-5c2b-a420-29bfc14a8db7 | note | FREQUENCY: Prior to commencing clearing
7dbdce7a-e4ee-5065-9860-d2c74d4dc978 | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
c4f5d607-c9d7-5374-af19-2075de2f46a2 | note | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
2ea500b3-b4b0-5b67-ac14-eb627a1fc446 | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
80cf4543-0c0c-5209-85cc-b6d2d98334aa | note | REFERENCE DOCUMENTS: CHMP
f1615fa2-1478-504e-a9ca-733cdfd7758c | note | INSPECTION/TEST METHOD: Inspect
592773ad-32fe-53e0-a112-adf78ede5dbe | note | RECORD OF CONFORMITY: This ITP Signed off
c882301c-5ea2-5c98-a854-fb0a49acbc16 | note | HP
a8a13b0c-221a-5c31-b536-538fc089128a | note | RESPONSIBILITY: Project Engineer/ Superintendent
494d3c23-29d6-5800-a1fc-1019f81d8aa7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
f5801112-a707-5715-8023-b168538ba1b6 | note | FREQUENCY: Prior to commencing clearing
d2624cc8-fc97-5000-9ac3-9033167112a7 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
8e4f18a1-f17c-55b7-9a0f-353c08f9d748 | note | REFERENCE DOCUMENTS: Drawings CEMP Tree Management Plan 176.I1
ab151b42-04cb-5807-979a-1879bdbf16cf | note | INSPECTION/TEST METHOD: Visual Inspection
49db5463-8623-5dd3-aa8b-bd6e5134680d | note | RECORD OF CONFORMITY: This ITP Signed off
3319bc7c-93cb-54ac-93e4-1333f24b7f53 | note | HP
5945e508-e329-5cd6-af5d-9e50c243828c | note | RESPONSIBILITY: Project Engineer/ Superintendent
00804005-f35b-5e57-bf41-6a6fe4673fd7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Felling of Trees
5d338939-f03f-5fac-8e71-9e5fcd254d97 | note | FREQUENCY: Prior to commencing clearing
1b0b8ac9-f8fe-524d-8bc4-6bfd5d48d95e | note | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
38c4cd6f-5e70-5969-8175-ccefc377075d | note | REFERENCE DOCUMENTS: 201.04
6f306da5-5bba-5218-acd0-2e02e0d3da7e | note | INSPECTION/TEST METHOD: Visual Inspection
ef4e5b98-2f12-515c-a19f-ee7b26d64733 | note | RECORD OF CONFORMITY: This ITP Signed off
d5288505-a2ff-592d-9a47-d38b6f3ce0ee | note | IP
41205a2f-1bb5-5833-9218-5502aed5f70b | note | RESPONSIBILITY: Site Engineer / Site Foreman
cc86bd8a-929a-5866-8fe3-e3945284f628 | date | Date Completed:
| checkpoint | 2.5 - Backfill holes
27f7f819-db5f-5ca3-a33d-f1c038442c7f | note | FREQUENCY: After clearing
49754606-e464-5db5-9c3f-571d49b2f3ef | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
ea246136-14b7-51ed-a3e6-eb07c622096a | note | REFERENCE DOCUMENTS: 201.05
9affe64f-e80f-5065-aa8a-b3050f51b8c1 | note | INSPECTION/TEST METHOD: Visual Inspection
ed3cba95-1d1c-59db-bc65-b39fe6b52ab9 | note | RECORD OF CONFORMITY: This ITP Signed off
9d2703cc-9a90-53e3-8791-4fff13731e82 | note | IP
ea416db7-6dc0-5a53-80e0-a421ac2f62af | note | RESPONSIBILITY: Site Engineer / Site Foreman
d9e773f1-7807-5ad1-965f-bac7c9e49248 | date | Date Completed:
| checkpoint | 2.6 - Dispose of Trees and vegetation
96bf4398-35e5-5459-82a7-14ca1baae91f | note | FREQUENCY: After clearing
2c343525-c5e6-5cde-8b1c-bd1e02c97282 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
d2abab7f-5d1b-520c-a470-c2dcfcd76ab8 | note | ○ Noxious weeds shall not be mulched.
62191d20-8934-5040-9566-6b88f52c9da9 | note | REFERENCE DOCUMENTS: 201.07
2d2ed5db-9206-5865-ba81-90997b758365 | note | INSPECTION/TEST METHOD: Visual Inspection
c477c96e-c5fc-56b7-9282-4c67f4ef83c3 | note | RECORD OF CONFORMITY: This ITP Signed off
018684d8-d587-557d-b5c8-fee21e5b1b9b | note | IP
02c2fd33-5e85-5edc-8898-45eeca31bd81 | note | RESPONSIBILITY: Site Engineer / Site Foreman
36658157-4956-5f08-8538-0b6e0bfb1c14 | date | Date Completed:
| checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
66fcfdaa-29da-582a-b540-2d0e608245c3 | note | FREQUENCY: After clearing
651d55ff-35d1-5e80-ae1f-dd0c234cf3fc | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
9158173e-7e38-585d-859a-6ef95866806b | note | REFERENCE DOCUMENTS: 201.07
d4ac5ec6-62a2-54d3-874c-397bc7ece9d4 | note | INSPECTION/TEST METHOD: Visual Inspection
4ee07411-768e-5a8d-99a0-c0cddbe9abc0 | note | RECORD OF CONFORMITY: This ITP Signed off
2a6d3e4f-1bc3-5cb3-86d0-ad155285acb8 | note | IP
87f3fb9f-e0dd-57ff-9b82-488450a5d5a3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ab047e79-3dbb-5944-af30-33af7a3cf130 | date | Date Completed:
| checkpoint | 2.8 - Stripping of topsoil
f1cc1ff8-8314-59f4-9c96-c13a130f8c36 | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
d88fea38-01e7-5262-b977-678ec2028dce | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
e166492e-8567-56bd-b4bb-508df3eaaf0c | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
d6717ec5-4fca-5cdc-bf91-5017034cdd0a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
e59cf263-53a7-557a-b251-2ce1335aaa5c | note | INSPECTION/TEST METHOD: Visual Inspection
a41d957e-0061-5e7e-923d-c10826adcbf4 | note | RECORD OF CONFORMITY: This ITP Signed off
46ec7219-2851-5480-a243-e7132e10a9d1 | note | IP
f781a0c3-93b5-5886-8303-2f1831dab2c2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
18eae6e9-c033-5e03-8565-62378fd5a7ab | date | Date Completed:
| checkpoint | 2.9 - Removal of abandoned services
f3ec4b13-48a4-5ffb-badc-3be38361d56b | note | FREQUENCY: Prior to commencing works
8071b4c3-0328-57ce-8ad4-019dc415e43c | note | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
4f1541ec-391b-5745-a9a0-769166b22e2c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
652c38d7-be37-5880-8064-706a91e689bc | note | INSPECTION/TEST METHOD: Visual Inspection
872c08b7-f22f-5f33-9556-b38d0caa3f09 | note | RECORD OF CONFORMITY: This ITP Signed off
04c5a841-d140-5cf6-b4fe-4a7aa1dab89e | note | IP
893f54ed-f513-59f7-8b39-276b12b63b92 | note | RESPONSIBILITY: Site Engineer / Site Foreman
aa1dbc81-8c04-5aeb-a3b6-321f4d14d76d | date | Date Completed:
| checkpoint | 2.10 - Clearing of Trees and Vegetation
7e3da080-8e0e-5294-b097-d2eac970b573 | note | FREQUENCY: During clearin works
c25c53c9-11d8-5927-aea0-a8dd83938d1c | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
c6957fee-0afd-598f-89e4-d04050687383 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
95e1d2ae-d36f-5fe7-9b45-df54e986420f | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
470d2592-fb8f-54b0-9dbb-6672c37ffa76 | note | INSPECTION/TEST METHOD: Visual Inspection
d741ed3d-5aec-5220-a1f5-f1cde61b5e66 | note | RECORD OF CONFORMITY: This ITP Signed off
c5425e4a-9682-5257-8fc6-6dca0186b970 | note | IP
0d618964-26ba-59fd-bfce-5ad76d27144d | note | RESPONSIBILITY: Site Engineer / Site Foreman
d3fe011b-6232-5a04-a309-ac52b8d89d59 | date | Date Completed:
| checkpoint | 2.11 - Grubbing of vegetation
9a654f84-d7ae-5238-8ec7-5493cc68c253 | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
1a219312-2dc8-5bda-a73f-0cf701f97c06 | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
0619c26a-c016-590f-875b-1737aaa41a2f | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
ee2f963f-84b9-5a10-aaba-230f9a93ec6f | note | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
488416ee-a196-5e56-b585-c51423053f66 | note | INSPECTION/TEST METHOD: Visual Inspection
dfa33425-8d5e-5636-829a-784ee0ebbb68 | note | RECORD OF CONFORMITY: This ITP Signed off
76ff37cc-94a8-53dd-8ba3-b7b1b35e04a7 | note | IP
70746ce6-2c34-59b8-a68a-73ca14233c33 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f7e53827-b2b2-5606-b37b-38dc4cac9faa | date | Date Completed:
| checkpoint | Final Inspection
8d9c4df1-1624-557b-9d32-481c7882eaf3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0d2db574-e86b-541c-b1c1-dfe69c346430 | textbox | Print Name:
87d8fe3c-d4d5-5507-88d1-44b0ce7268f7 | textbox | Position:
2e2f0bae-55f4-5c86-9b3a-912eb571041b | date | Date:
| checklist | ITP-003 - Earthworks Foundation | itp | ITP-003 - Earthworks Foundation | e4483370-1153-4b98-9ee5-99c0918a0199
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
3fb99a86-fbd7-52c7-8801-a64a10bb1861 | note | FREQUENCY: Prior to Commencing Work
6c5cb398-71c3-50f6-b044-217e92fc58a2 | note | ACCEPTANCE CRITERIA: All personnel on site have completed site specific induction
89afa029-6192-5faf-b383-84bb24a16a90 | note | REFERENCE DOCUMENTS: Induction Register
dd795dbb-75e6-521d-bf71-5a4464ae3b53 | note | INSPECTION/TEST METHOD: Document Review
415dd669-17b0-5788-acdd-bf468469695c | note | RECORD OF CONFORMITY: This ITP signed
d1012dbc-3181-5d57-bcf5-02ed0dc8e2e6 | note | HP*
53fc8cad-0c3a-5c44-9425-900778fe433d | note | RESPONSIBILITY: Site Engineer / Site Foreman
a043764e-1387-5745-a3b9-41969ed76609 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
c2db07ba-f583-5e37-97e6-b15c6470709d | note | FREQUENCY: Prior to commencing any activity
5e4d17d8-7ce6-5250-a0b0-ee3b4750e845 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
160365ac-8e32-5829-885e-0766b43911ed | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
6d4032d9-ca92-52ea-8c27-60cc3bb09d63 | note | INSPECTION/TEST METHOD: Document Review
c53aa2d9-562b-52fd-81f6-8bce5725dcfa | note | RECORD OF CONFORMITY: This ITP signed
e896fb12-3387-5c4f-8baf-7075937389cc | note | HP*
6a24d8a0-f740-58a2-a829-72d155157f54 | note | RESPONSIBILITY: Site Engineer / Site Foreman
83d0bd8c-bdb0-50d1-9ac5-042faed094ae | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit issued
1889c5f9-29b1-570d-9a3a-519cd028158b | note | FREQUENCY: Prior to commencing
3eea5dc1-6091-50d0-8962-ab20d39e0f80 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
ed620c63-3095-5bdb-adbe-3386444511e4 | note | REFERENCE DOCUMENTS: Excavation Permit
2ef53f40-2272-5842-bbe5-239a69834c69 | note | INSPECTION/TEST METHOD: Document Review
e717425e-bca0-5197-933e-2ef12a7f5c7c | note | RECORD OF CONFORMITY: Excavation Permit No.
2e4930cb-0487-5e5c-add4-81ea063d52b3 | note | IP
4ca34445-4e07-5904-9180-d91f0caa11b8 | note | RESPONSIBILITY: Site Engineer & Superintendent
00044e38-f61b-51c3-8c8a-bf7ea59c4fa4 | date | Date Completed:
| checkpoint | 1.4 - Check that current revision drawings are being used
92faf4ec-fa88-5b39-99d5-007eb677d5ad | note | FREQUENCY: Prior to Commencing Work
e3260284-eb85-57cb-a220-2621ee33ce1d | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
92f0f07b-f02f-5838-a467-f2efda0f1828 | note | REFERENCE DOCUMENTS: IFC Drawings
425f776b-3821-557a-bfad-b0cc03fa77cb | note | INSPECTION/TEST METHOD: Document Review
142a65b1-6283-5421-b8d7-dd488edbf6d3 | note | RECORD OF CONFORMITY: This ITP Signed off
e1314bee-4f34-531b-83d9-efff6bfd55bf | note | IP
c11291a2-72bf-5499-a4bb-88aac9749ff2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ca6c49f1-e96e-5c10-a7d7-d68ae57083ec | date | Date Completed:
| checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
2d778f80-530e-58e7-b613-231e74420ed6 | note | FREQUENCY: Prior to Commencing Work
9207a917-8a69-59a5-95c0-5433891eb7b0 | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
107f2e8f-d90a-53a9-9448-2cceefc65137 | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
b0cf0aea-8235-54c3-8c83-d722572eb452 | note | INSPECTION/TEST METHOD: Document Review
efcf01b7-6c8e-5771-b21e-bef5f58ae233 | note | RECORD OF CONFORMITY: This ITP Signed off
107e2a8d-687a-5e12-b057-f1ab8dcc5718 | note | IP
141244d7-53e3-549c-bb58-63266eea1d94 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cdd6acb0-1f5a-5bd6-ba6d-03ba7e09ccef | date | Date Completed:
| checkpoint | 1.6 - Verification of Site Clearing
78c6a20f-2412-5533-afcf-d097426e1b87 | note | FREQUENCY: Prior to Commencing
74a284f0-7617-5155-8bb3-7ff6c5bd9fee | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
c1d4d09b-f1ce-56ea-a236-e44a4bea154e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05, ITP-001
40d8f3c9-a0e7-5725-8ec6-b77ad28ecbbc | note | INSPECTION/TEST METHOD: Visual Inspection
fbbd8c5f-4735-5ba4-8cf8-cd758ae017b8 | note | RECORD OF CONFORMITY: This ITP Signed off
2e2adb0e-4b10-5f46-a6c7-c6fc2d15bc2b | note | IP
448088f3-ee07-59c5-983a-669cdcbc07a2 | note | RESPONSIBILITY: Project Engineer
9849a66c-da5e-5d55-bf6f-a774bf2c309d | date | Date Completed:
| checkpoint | 1.7 - Placing Fill
270cab58-64fd-5208-a9db-81ad0be5fc10 | note | FREQUENCY: Prior to Commencing Fill
75283a9d-2187-5274-82ca-7039ac3cf2f8 | note | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
9160e04c-bba4-526e-8a49-ae9a0357497a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
3e717d00-459b-5257-b571-a88356dedd6d | note | INSPECTION/TEST METHOD: Visual Inspection
c8f85131-76a6-54d4-9a64-de30cf845034 | note | RECORD OF CONFORMITY: This ITP Signed off
f1164e64-b0ec-557c-b7ec-92cf03d9fd1e | note | IP
d0af182e-b505-5d73-90cd-c981ece48df7 | note | RESPONSIBILITY: Project Engineer
17c8dd0c-ea4a-550b-aece-2256134744cb | date | Date Completed:
| checkpoint | 1.8 - Rock Subgrade
f4edda98-63b4-5346-9058-c793c57a4a26 | note | FREQUENCY: During Excavation
6b6edef0-790a-5eb2-8862-25f03cf01411 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
ea103654-c6d1-5ca6-99bb-35db7f403702 | note | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
262403f5-3d5f-50f1-af5f-ff078c98ccc6 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
bddea529-5e48-535e-a59d-ab03b0745db4 | note | INSPECTION/TEST METHOD: Visual Inspection
9b4179ca-2911-5f96-8736-b560ac32c9e6 | note | RECORD OF CONFORMITY: This ITP Signed off
11c24a59-686f-5ff4-abec-5a8a627ce37d | note | IP
fced53bb-a2ac-599e-a670-cc3c2869f366 | note | RESPONSIBILITY: Project Engineer
0b1206f1-c068-52d2-9aee-309f7a9f8aa6 | date | Date Completed:
| checkpoint | 1.9 - Ground Water
a0c644fc-4f23-511a-9c0c-5c065335d9b2 | note | FREQUENCY: During Excavation
240e0275-eeca-55c6-8c3e-3b97113147e0 | note | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
9af2f2e2-30db-5f23-a0fd-cb52b6e0c432 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
06cb1024-a8ce-5860-8168-27d24e547c9e | note | INSPECTION/TEST METHOD: Visual Inspection
2fcb2824-a272-51e1-8c3b-468030958821 | note | RECORD OF CONFORMITY: This ITP Signed off
300f67d9-b33e-50df-8ffa-d02e00b080ba | note | IP
67627b66-6fa6-5751-b1b0-2e66ed5e5c89 | note | RESPONSIBILITY: Project Engineer
7d29e66f-e7dd-5bdb-89de-8cf78eacea05 | date | Date Completed:
| checkpoint | 1.10 - Unsuitable Material
4c579bcf-cd4d-583d-baae-e2c249cac6d1 | note | FREQUENCY: During Excavation
3c3c0cba-ab86-539a-bf0a-89e03add16e0 | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
ec5e93ef-0bd6-5f1b-a509-c703408c3cd1 | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
a36f8b36-3a8f-5403-bb69-ed00090c96ea | note | REFERENCE DOCUMENTS: IFC Drawings
03acbf92-1557-5703-8f56-1564368b10a9 | note | INSPECTION/TEST METHOD: Visual Inspection
b89e8b67-f414-5aba-965c-41b88efd00a2 | note | RECORD OF CONFORMITY: This ITP Signed off
0b056266-dbbe-5cc2-83bd-d5913dc4f194 | note | IP
d647335f-7d7b-5664-aed8-73ec0e2cf6bd | note | RESPONSIBILITY: Project Engineer
05fe6fe9-e948-5de0-9259-3b457bda1d80 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey set-out
21deb9f4-983f-5242-a773-527941d2fa2b | note | FREQUENCY: Prior to Commencing
66aa7e45-40aa-5026-8a1d-b115c46a8379 | note | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
fecc909d-eae7-578c-8d4f-bd60f471e661 | note | REFERENCE DOCUMENTS: IFC Drawings
63cc7ab9-44b4-5734-b663-c715364d5f0d | note | INSPECTION/TEST METHOD: Site Inspection
43fbc386-45b7-553a-b13d-1eb2b45d3ec6 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
fc7db8f9-fe17-5a5a-b9c7-7b1e0751f9b0 | note | SCP
e5eba14d-5160-5a56-8ce5-8a2f82853320 | note | RESPONSIBILITY: Project Engineer/ Superintendent
e6fa650c-1a38-5060-a4fb-bf82db9420d2 | date | Date Completed:
| checkpoint | 2.2 - Placement of Geotextiles
36041529-8e15-5a0a-af48-156bdd13ebd8 | note | FREQUENCY: On cut surfaces
9badbc6c-e56c-54ff-a2dc-73d727b1ab57 | note | ACCEPTANCE CRITERIA: Geotextiles / fabrics placed as per manufacturers specification
9bfc970f-933e-5d31-acc1-46f9b47f0b37 | note | REFERENCE DOCUMENTS: Drawings, Manufactuer specification
58224a35-5dba-5d43-96b2-a12af9302e0c | note | INSPECTION/TEST METHOD: Verify
a55733a6-d602-58bc-843e-82db4be2af5e | note | RECORD OF CONFORMITY: This ITP Signed off
63fa0ee1-9a5a-5b02-91c4-4e65dc446cf4 | note | IP
e0b74641-c198-5030-9acc-8ea90e862e0f | note | RESPONSIBILITY: This ITP Signed off
c170cd5f-0403-5fc1-aa32-52038e00607c | date | Date Completed:
| checkpoint | Final Inspection
1c50673a-5aeb-580c-8437-b31c3fc2f2b7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e84f19b2-2036-5d74-a103-ca9c68f8a947 | textbox | Print Name:
b7195b89-40be-55a8-8804-0282f37f7821 | textbox | Position:
f8cf62a4-4b86-538e-bbc3-0aa79eb12ca8 | date | Date:
| checklist | ITP-011 - Bored Piling | itp | ITP-011 - Bored Piling | c40aa3c7-86d7-420c-9945-98aa1bd0c1e2
| section | 1.0 - Design and Submissions
| checkpoint | 1.1 - Check for correct documetation
0a0fc9e5-fc9b-56e2-a126-8a006d4d8dd2 | note | FREQUENCY: Before commencement of activity
bed9a8e1-115c-5254-958a-f400050698eb | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
b0161631-dde6-5ade-85af-185332db474d | note | REFERENCE DOCUMENTS: Drawings
6ac6dc69-a295-5a96-8fd3-030fe2daaa0f | note | INSPECTION/TEST METHOD: Current revision of drawing
3c9162d9-d3c6-56a4-a788-6cf91a3b1d96 | note | RECORD OF CONFORMITY: Current revision of drawing
58ef6524-7739-5c90-8bd1-48b56633be27 | note | HP*
cb825fdf-2f7e-57ae-8d47-5cf491baa5e6 | note | RESPONSIBILITY: Project Engineer, Site Engineer
7406721e-6435-5e68-a0e8-430c22e31e37 | date | Date Completed:
| checkpoint | 1.2 - Approval of Mix Design
c2f3714c-5933-5061-a220-a9974da86820 | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
1fa58066-1c34-5517-b3a2-a12021621e14 | note | ACCEPTANCE CRITERIA: Mix design reviewed and approved by superintendent.
c7df30a2-46a0-509e-8375-e9bad97860bc | note | REFERENCE DOCUMENTS: Cl 610.07(b
b2749795-4fe2-538d-9728-5cde42ffe49e | note | INSPECTION/TEST METHOD: Approval
a2256876-1b8a-5f0d-81ab-8810a02b45ca | note | RECORD OF CONFORMITY: VicRoads letter of approval
b4ab1abc-6e6f-5c48-a775-e94467c346ea | note | AP
33d86392-865a-5930-9bc0-998ca64afcd4 | note | RESPONSIBILITY: Superintendent
fa0ad4c6-ab4d-5ff9-adcf-9631e311d8df | date | Date Completed:
| checkpoint | 1.3 - Approval of Quality Procedure
f18066d8-f918-56a4-91df-f460799c4311 | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
2cc518a7-9e0b-55f7-aaa2-8da1e7a4df5a | note | ACCEPTANCE CRITERIA: Proposed materials and pile construction procedures reviewed by the superintendent
7578984c-98e2-5857-9373-885a090a5fe9 | note | REFERENCE DOCUMENTS: Cl 606.03(a)
b6fbd509-d9a8-5fbd-ab75-8414e8a214e6 | note | INSPECTION/TEST METHOD: Approval
1a50aba8-5866-571e-9a05-624335ff4baf | note | RECORD OF CONFORMITY: VicRoads letter of approval
20d7b043-d08f-597f-b911-25d71d35e70e | note | HP
5b92b87e-07f9-5d8a-b60f-ce9b0cfb60d0 | note | RESPONSIBILITY: Superintendent
280daca8-fc94-5363-bd2b-1781c5c67f7e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Ensure Traffic, Safety, Quality and Environmental management measures are in place
346bd1c6-e784-593f-9040-240a1e78a1c2 | note | FREQUENCY: Prior to commencement of activity. EMP at least 2 weeks prior
847178b0-547c-59a8-88c7-dac584a8cbe7 | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
5b0976b3-c478-580f-ab33-276f66f65683 | note | REFERENCE DOCUMENTS: PSP, TMP & EMP
fa72768d-f025-54d6-9fcd-3046d8d992ec | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
c7ea1d8e-09ef-56be-9309-562a9cfe33f8 | note | RECORD OF CONFORMITY: Inspection
efe92ac9-bd31-55ff-98e1-38f1320c8c5f | note | HP
09da5824-16b7-56c2-b21a-fe2201b3b6a0 | note | RESPONSIBILITY: Site Engineer, Superintendent
aea014b2-4e0a-5c90-b3ae-201dbe4c432c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Certification of approved Hot Dip Galvanising
4a304e77-2ce4-5a58-b0bd-f969de884d8f | note | FREQUENCY: Prior to Epoxy coating
c9e79f6f-50b3-5ee5-b0dc-895310d02997 | note | ACCEPTANCE CRITERIA: Galvanising treatment in accordance with appropriate Standard documents and Design specification 200 microns
a9f6c07e-4715-5796-ba2d-3dca73ebd226 | note | REFERENCE DOCUMENTS: Drawings AS/NZ4680
79653223-8c34-5d2b-af84-0de49aa9183a | note | INSPECTION/TEST METHOD: Verify
fb387304-a566-5542-8581-b28bc58adf2e | note | RECORD OF CONFORMITY: Manufacturers certificate
beba2636-e732-5b4a-889e-9f60f03c168d | note | HP*
c8fedabb-ee97-5d60-a1d2-7eb2041ed255 | note | RESPONSIBILITY: Project Manager, Site Engineer
922d6867-42a1-5235-a6b9-0b82f6f6f16d | date | Date Completed:
| checkpoint | 1.6 - Certification of approved Epoxy coating
0efcffca-db41-5b37-bb23-021638ea8121 | note | FREQUENCY: Prior to arrival on site
0faff230-40d3-586d-aeb6-752d5d30b14b | note | ACCEPTANCE CRITERIA: Epoxy treatment in accordance with appropriate Standard documents and Design specification
49ffb144-70ff-5038-8ff8-7b951f16a8fd | note | ○ 2 x Base Coat GFX @ 250 microns
dcb2de77-b393-56ed-948b-be76d3823645 | note | ○ 1 x Top Coat Polyurethane, 100 microns
b9ab6396-693d-51f8-ba02-63eeeac1f994 | note | REFERENCE DOCUMENTS: Drawings AS2312
ed4b8d91-c649-54b5-8094-665c126f2b70 | note | INSPECTION/TEST METHOD: Verify
5533b71d-010d-583c-8f4b-293fb7c3132b | note | RECORD OF CONFORMITY: Manufacturers certificate
af2ff604-8d3a-593f-9405-ba0b863e92c6 | note | HP*
911ea4c6-31e1-512e-ab04-e707bf36b056 | note | RESPONSIBILITY: Project Manager, Site Engineer
8c97bf25-d659-56f4-a627-aeae0d4bebc7 | date | Date Completed:
| section | 2.0 - Bored Piling
| checkpoint | 2.1 - Survey and setout
b67b82eb-ffb6-575c-9945-8e4b64a0ac35 | note | FREQUENCY: Each Pile
468f3f84-3f47-5cc6-b26d-b6ba7bcfcfe9 | note | ACCEPTANCE CRITERIA: Survey and confirm position and depth as per drawing
b5294bbc-fcb7-5ce7-af35-3ef7807a2fcc | note | REFERENCE DOCUMENTS: Drawings
31cdf0aa-de64-5119-b8f0-666f206a34e9 | note | INSPECTION/TEST METHOD: Survey
ef1bc9d1-5e87-5978-bcfb-87b099595924 | note | RECORD OF CONFORMITY: This ITP Signed off
5f9bf3fb-3515-5502-b9f7-22a2fcd37ea1 | note | IP
da0645e5-53e8-5101-8485-d8e068f839ab | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
6b25bc54-b989-5f5c-891b-38d5768fc9d0 | date | Date Completed:
| checkpoint | 2.2 - Excavation Levels
816689b9-e177-5a5c-aaf6-0e6ce199d5fa | note | FREQUENCY: Each Pile
cd2f449b-63b8-58f6-814f-2fb587ca2699 | note | ACCEPTANCE CRITERIA: Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works.
712567c4-194a-56f9-ae22-d24e263ab226 | note | REFERENCE DOCUMENTS: Drawings
595d943b-2d5e-5b02-b98c-50669b522714 | note | INSPECTION/TEST METHOD: Verify
352e9896-85f3-5312-9122-76280a95ee12 | note | RECORD OF CONFORMITY: Drilling check sheet
07e50c0c-5393-5359-98ff-e810fb35edd3 | note | HP
8307e9d3-9583-5005-8f58-7d35ae564601 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
cadc69f5-14d6-557d-9800-92604a8f948c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Inspection of Pile Excavation
9b0903a7-0912-50a3-8195-947124c30c65 | note | FREQUENCY: Each Pile
fef5c456-6eb1-5e23-a4c7-d7e95bcae565 | note | ACCEPTANCE CRITERIA: First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level. Material encountered consistent with design.
3b6153c1-2a2f-5be9-9069-a20ac0c8a6a7 | note | REFERENCE DOCUMENTS: Drawings Cl 606.06
a8af4a7e-0e6c-5078-992d-addae9fba350 | note | INSPECTION/TEST METHOD: Inspection / Test Method
6530f28a-ee52-5798-a237-2a15f875abfe | note | RECORD OF CONFORMITY: This ITP Signed off
e6933629-7949-5af8-b179-b75f84906130 | note | HP
f2389683-93bb-5880-a3c8-d893258efca2 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
bbb7c424-8324-5d31-9783-825ee2ec23ec | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Bore Logs
65a6947a-2c25-5a44-b100-81ec69e94d88 | note | FREQUENCY: Each Pile
8d9ff2df-022f-5326-9685-255a39191230 | note | ACCEPTANCE CRITERIA: All bore logs and pile installation records to be sent to and reviewed by designer
9f338457-9093-5c10-9b8f-4e65c375616e | note | REFERENCE DOCUMENTS: Bore logs
b98a703d-fb71-5624-a7fd-559c22605dd2 | note | INSPECTION/TEST METHOD: Verify
e47e7681-f6b9-59f2-ae0e-57ed02bde9b0 | note | RECORD OF CONFORMITY: Drilling check sheet
b13fb6a3-0d8d-5b09-bc77-eb3657c8f16a | note | HP
64fa5f9d-7793-525f-9d27-c3bb7cdfc102 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
31a0840a-6c24-59cd-a62a-66aa5d235e5f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Spacers installed on Reinforcement Cage
c09d6fbc-d411-58a8-95bd-3f55ba501655 | note | FREQUENCY: Each Pile
31e5cc23-e160-5b7e-b9eb-e6cd1fca1f82 | note | ACCEPTANCE CRITERIA: Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals
84de2fe1-d522-5da3-9ab4-4f26e7f0f02d | note | REFERENCE DOCUMENTS: Cl 611.10
ea370d8f-def2-5408-874f-8849c290a500 | note | INSPECTION/TEST METHOD: Inspection
15e7bce9-9f91-5f98-9537-a346745445a5 | note | RECORD OF CONFORMITY: This ITP Signed off
cb122976-0544-52b7-b87c-7ddfcb731949 | note | HP*
dfb76689-24af-5676-b26b-4c6a7aa0a73a | note | RESPONSIBILITY: Site Engineer, Superintendent
225504e0-81ce-5f2e-85cc-b64422e6d493 | date | Date Completed:
| checkpoint | 2.6 - Inspection of column and cage height and centre
bd8d9578-73ce-5522-96bf-4bf735f43a59 | note | FREQUENCY: Each Pile
e81ef8d1-bd64-508e-ade4-82c66e6ed47b | note | ACCEPTANCE CRITERIA: Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance
5244e8c4-ea06-5803-b4a2-282380bfb4f5 | note | REFERENCE DOCUMENTS: Drawings Cl 606.08
822f09b2-10b3-5832-9f41-14550edcfcd6 | note | INSPECTION/TEST METHOD: Inspection
ad904b47-1946-52f3-86c9-afb241e71c3b | note | RECORD OF CONFORMITY: This ITP Signed off
f7bb2175-8189-56b2-bf18-70a766034fa3 | note | IP
bca24bb6-28ca-55ac-b8ea-747f70190823 | note | RESPONSIBILITY: Site Engineer, Superintendent
20e3dc5f-46f9-595c-8363-275743762e15 | date | Date Completed:
| section | 3.0 - Placing and Finishing Concrete
| checkpoint | 3.1 - Quality Checks
df5122b0-2e92-5888-8ab8-be004e2a6ec1 | note | FREQUENCY: Prior to each concrete pour
205ff605-aabb-5237-b0a7-e03eb59921d2 | note | ACCEPTANCE CRITERIA: Relevant ITPs and Quality Control checklists completed and reviewed
be427712-096e-5c45-9c53-1237e52b408b | note | REFERENCE DOCUMENTS: Cl 610.18
215e2520-aaec-59e6-9126-d814db7fffb6 | note | INSPECTION/TEST METHOD: Inspection
fb4e5acf-db41-5d3e-883a-2b446820f5c6 | note | RECORD OF CONFORMITY: This ITP Signed off
eb3cf7cc-9328-53f0-8048-7f229d527edb | note | HP
2f862885-c8b9-5359-b017-ea7b3ee0a8b6 | note | RESPONSIBILITY: Site Engineer, Superintendent
f724cfc3-1d8f-556e-b3a6-a4666198f246 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Carry out sampling of concrete
fbb8cb1f-7c30-5b45-ad2a-cffc6372c487 | note | FREQUENCY: Each concrete pour
b2d2cd79-1114-50c4-9930-719738f1d422 | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm), (550mm - 800mm)
317ae1cb-6d27-52d8-8702-421f5e1de3ea | note | REFERENCE DOCUMENTS: Cl 610.16 Table 610.161
3a766838-e2d6-59fa-af3d-705b205e2b06 | note | INSPECTION/TEST METHOD: Verify
172e4950-5875-50bd-9d80-79c4c06d14ca | note | RECORD OF CONFORMITY: Checklist
4d98b5ab-f967-5dc9-9b03-8794eca664bb | note | IP
a131c317-dac1-51e9-9a8e-bfbc458ed884 | note | RESPONSIBILITY: Site Engineer
45773f58-e1fc-58bf-9f2c-fff103790c27 | date | Date Completed:
| checkpoint | 3.3 - Record location of each batch
687bd76b-9774-55fe-a738-7b878df6829a | note | FREQUENCY: Each concrete pour
c6fee042-90f8-513e-aff3-cca97b368a14 | note | ACCEPTANCE CRITERIA: Batch location recorded
486cbe58-63ef-5ee9-bca8-47008e727a1d | note | REFERENCE DOCUMENTS: Cl 610.15
a8d0e02f-0a59-5667-81ca-570273247b33 | note | INSPECTION/TEST METHOD: Verify
cd8a9077-2703-5851-9fb5-89bf77bf4045 | note | RECORD OF CONFORMITY: Checklist
0f9a1f5e-520f-50e5-88a1-de3255b3e8cb | note | IP
e92b971b-c9da-56cd-96d6-08b6b7458ea4 | note | RESPONSIBILITY: Tester
37d7d2f4-8b32-5229-be68-ede9d1037e07 | date | Date Completed:
| checkpoint | 3.4 - 7 Day concrete test result
324c6bbe-3df7-527e-87e5-ea3b1303a24c | note | FREQUENCY: Each sample
b3df15d9-39c5-5ac1-9af6-09334cf2d2dd | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa
e7cdb4f0-ac79-528f-a653-aa00e6f3ac25 | note | REFERENCE DOCUMENTS: Cl 610.05
0f2ffd11-a96d-53a1-adc4-bc9e5699c998 | note | INSPECTION/TEST METHOD: Test Report
95381417-acf8-5eed-96b7-7f7ab80958a5 | note | RECORD OF CONFORMITY: This ITP Signed off
b9d3a692-ea7a-56d7-b96a-dd14fc4be9ca | note | TP
ff138138-1df3-52e3-bb3a-2b2e490abb2c | note | RESPONSIBILITY: Site Engineer
3577db4c-23bc-5231-9641-3a392bdaf17f | date | Date Completed:
| checkpoint | 3.5 - 28 Day concrete test result
1a1e9797-66f7-55a6-9f6c-e259dc0285e4 | note | FREQUENCY: Each sample
503999f4-3e2c-52d2-b7fb-22cd4ed91388 | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa
9e2f17a5-f68a-5b9d-afa2-af711ae871bb | note | REFERENCE DOCUMENTS: Cl 610.05
2ab9b83b-8254-5e1a-b922-bdff4b772e78 | note | INSPECTION/TEST METHOD: Test Report
4619b176-ec6f-5ab0-ad4c-6283b84dd9f5 | note | RECORD OF CONFORMITY: This ITP Signed off
59e69a89-5207-5c46-9be9-11fc902f92cd | note | TP
4dedb29d-7790-570c-a534-c4381d6d8597 | note | RESPONSIBILITY: Site Engineer
43f9792a-fc6a-5d31-a4bd-2bf8d38140b0 | date | Date Completed:
| checkpoint | 3.6 - Tolerance Check and As Built Survey
374766f3-9136-5acd-9c9c-b7657bb7c4a5 | note | FREQUENCY: Each Pile
6f6b3e84-8909-5b24-a936-bb02ce8f14cf | note | ACCEPTANCE CRITERIA: Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality
dc47e33f-fd22-5541-a088-b3589614b450 | note | REFERENCE DOCUMENTS: Cl 605
671f9cd6-77ce-5c6f-bb6e-cd70fedbd07a | note | INSPECTION/TEST METHOD: Survey
4f402bdb-929d-559c-bfd7-954344ec9f30 | note | RECORD OF CONFORMITY: Survey report
63b75292-84d1-531f-9829-c783919ac214 | note | WP
f8ec4799-3f40-5249-b8b8-7c29497f8a77 | note | RESPONSIBILITY: Site Engineer
d6d2b54a-cde3-5b13-a35f-b345f2e4cb3c | date | Date Completed:
| checkpoint | Final Inspection
eaae6d36-e462-58ee-b5de-e639fc54f8d3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d786f1ed-a94b-5164-909b-1eca9ef2915e | textbox | Print Name:
b2bc3fcf-3295-500a-9510-201cdefabd30 | textbox | Position:
46044c52-3adb-5a26-a943-a20ec0b722dd | date | Date:
| checklist | ITP-012 - Ground Anchors | itp | ITP-012 - Ground Anchors | 7c37e4e0-b778-458f-ac67-662671702d5b
| section | 1.0 - Design and Submissions
| checkpoint | 1.1 - Hot Dip Galvanised certification of DYWIDAG threadbar
b5906014-7af7-5f8f-af4a-a7915209d5fe | note | FREQUENCY: Prior to commencement
695d6c2e-5826-5843-9006-71dc6782312d | note | ACCEPTANCE CRITERIA: Galvanising achieved as per drawings
9bb7fb41-186b-54de-a406-efa13c0e30dc | note | REFERENCE DOCUMENTS: Drawings
e41b673e-2bcb-5435-bbc0-a67ad0198589 | note | INSPECTION/TEST METHOD: Current revision of Drawings
37db3d64-ff1f-53cf-ba4b-5e083499b460 | note | RECORD OF CONFORMITY: Certificate
f2574923-218d-5f6f-add2-5bb4b28c989d | note | Verify
4114ea72-32af-527c-8be1-cecce09dfa12 | note | RESPONSIBILITY: Site Engineer
06e6a7a0-6a96-59e8-9d57-6c6b1b762100 | date | Date Completed:
| checkpoint | 1.2 - Approved grout product
f8e0a69b-1990-5195-b044-6d8d8f3fa935 | note | FREQUENCY: Prior to commencement
96422251-c601-575a-a514-11f6494eb3cd | note | ACCEPTANCE CRITERIA: Proposed grout product approved prior to commencement of works
8a084688-151a-560d-b149-f526088064a7 | note | REFERENCE DOCUMENTS: Drawings
7d8b0c65-cb3a-5fe6-a7ed-46d64d5be919 | note | INSPECTION/TEST METHOD: Approval
ecea2d00-c387-516d-8703-035c0f3f3cf8 | note | RECORD OF CONFORMITY: This ITP Signed
b3f9564f-196d-589a-8536-2581b8f65688 | note | AP
f8b8cca8-146d-5bbf-86cc-2523066e3274 | note | RESPONSIBILITY: Geotechnical Engineer, Site Engineer
ef26300c-61e4-5ba4-bd7d-f68f9e226508 | date | Date Completed:
| checkpoint | 1.3 - Acceptable individual bar length
5ad9ed92-be79-5c80-bb8d-d6346f276709 | note | FREQUENCY: Prior to commencement
27529f8e-9151-5554-ae77-aae05a22dd0e | note | ACCEPTANCE CRITERIA: Bar Lengths conform with minimal length of 3000mm as per drawings
eb3a4a76-5dbc-56cf-9145-367556cf8dd4 | note | REFERENCE DOCUMENTS: Drawings
dfd4603f-7683-5f33-b7c5-1b8a84542fb7 | note | INSPECTION/TEST METHOD: Verify
d250126d-fb1a-556c-b2c9-cc1514d86ce0 | note | RECORD OF CONFORMITY: This ITP Signed
2d8e6994-99cd-5664-9a61-ee16949f8732 | note | RESPONSIBILITY: Site Engineer
afaded78-a41a-57e6-b761-3cbb3f1d8512 | date | Date Completed:
| checkpoint | 1.4 - Acceptable internal duct diameter
b4329e00-abbf-5bab-b1c9-34a946e1dbc6 | note | FREQUENCY: Prior to commencement
2aa5664b-dd32-5263-bb52-75c24a6d733a | note | ACCEPTANCE CRITERIA: Internal duct diameter to allow 5mm grout annulus around bar circumference
70181c42-8b1d-5e66-bcfd-fd987453748a | note | REFERENCE DOCUMENTS: Drawings
82d54f4d-3bd7-5df0-b1c4-3891e7123f71 | note | INSPECTION/TEST METHOD: Verify
2d9d9cc6-c143-52d2-9b70-34ea269d336f | note | RECORD OF CONFORMITY: This ITP Signed
43c47298-7f27-533a-ad46-750c8977af06 | note | RESPONSIBILITY: Site Engineer
e64f064a-7f11-5568-b45a-efde1630f835 | date | Date Completed:
| checkpoint | 1.5 - Supplier of materials to supply product certification
bd1a26c2-2a61-55ef-959c-9d2f716f63b1 | note | FREQUENCY: Prior to commencement
960e80fe-a675-529a-af1a-0ffadcaba341 | note | ACCEPTANCE CRITERIA: Certification of threadbar and all other ground anchor material to be certified
0f6e4aeb-634e-5889-bde7-f00713cf55de | note | REFERENCE DOCUMENTS: Drawings
e75217d6-3f76-5526-bc40-d828ccd06b8c | note | INSPECTION/TEST METHOD: Verify
b1fb5124-593e-54f3-b505-5ec385755c3b | note | RECORD OF CONFORMITY: Manufacturers Certificate
03d4bed0-30aa-5b1d-9f68-1c1a367f66de | note | HP*
44d75ce1-48a7-5e6c-ab34-ae25aada64e1 | note | RESPONSIBILITY: Site Engineer
c3886a72-9d42-51f1-a7df-2614772cb820 | date | Date Completed:
| checkpoint | 1.6 - Acceptance of Test Results from Preproduction Anchors
399f9e94-29f1-5ad1-9df9-23f4ab7d037e | note | FREQUENCY: Prior to ordering materials
2a5b4f48-edfa-5f6a-836e-9af1ad879e5c | note | ACCEPTANCE CRITERIA: Test Results reviewed and approved from Preproduction Anchors
b50a5cbc-ab12-5edf-8059-e620cdb3934e | note | REFERENCE DOCUMENTS: Drawings
4105ed8e-b7c5-50cc-bcd0-bd8793c5e6c3 | note | INSPECTION/TEST METHOD: Verify
3a71a75c-f2f5-5169-9795-e44c8b934fff | note | RECORD OF CONFORMITY: This ITP Signed
dc3dc7e0-7f7f-5d82-9e56-c3fb332d9d32 | note | HP
f43598ff-7456-5a24-87df-4aadb5cc5da5 | note | RESPONSIBILITY: Geotechnical Engineer, Superintendent
ef6933c3-258b-57b4-bb33-6478db2d0796 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 - Ground Anchors - Installation
| checkpoint | 2.1 - Records of ground anchor drilling and grouting taken for each hole
b21afb3f-fc17-5b96-80c1-2da5972e66d0 | note | FREQUENCY: Each Anchor
c144afae-9206-590e-8607-662d3c4b40c8 | note | ACCEPTANCE CRITERIA: Logs to be taken during drilling
37c8595b-2ecf-5a74-9cc5-0251aa91e320 | note | REFERENCE DOCUMENTS: Borelogs
9ccb939d-71c5-5589-952b-bc327c293f3d | note | INSPECTION/TEST METHOD: Verify
78e2e84f-2bfd-512a-b014-b924618267ac | note | RECORD OF CONFORMITY: Checklist / Form
8caa01b8-49cb-57de-944b-02c3cdf60805 | note | IP
6c1dbec4-7fbc-5ddb-b55a-c96922d98823 | note | RESPONSIBILITY: Site Engineer
d6b09be4-cc30-5f66-bab9-08a7ec55a7a9 | date | Date Completed:
| checkpoint | 2.2 - Appropriate placement of spacers along anchor
0b05e81e-042c-56b0-abae-3066c738e839 | note | FREQUENCY: Each Anchor
2c73b9bd-f24e-5f89-b7df-0e7a0cd4e3c3 | note | ACCEPTANCE CRITERIA: Spacers placed at a maximum of 1000mm
9c075ba0-5bfe-53a4-a033-86b115309605 | note | REFERENCE DOCUMENTS: Drawings
05ef8308-5b11-53ec-b8d1-881525186ea6 | note | INSPECTION/TEST METHOD: Verify
417ce9db-41dd-53ea-b8a2-f52dd4bb443f | note | RECORD OF CONFORMITY: This ITP Signed
65644416-019f-59de-87ec-737ff87104d2 | note | WP
0e0fd3c9-1cde-591c-ba9f-82fe5af26358 | note | RESPONSIBILITY: Site Engineer
ca78e018-fd58-5172-a93e-c3f34ae06b3f | date | Date Completed:
| checkpoint | 2.3 - Inspection of Ground Anchor Drilling
975edf90-e4b4-5bcf-aff0-df0692d1bb55 | note | FREQUENCY: First 4 Anchors
afb941cd-2774-5c2a-b5d2-849dd5f64a35 | note | ACCEPTANCE CRITERIA: First 4 x Ground Anchors to be witnessed by, and borelogs taken by Geotechnical Engineer,
8e43e796-ab5b-5adf-be17-d93ee6a0f29b | note | REFERENCE DOCUMENTS: Borelogs
cbcb2666-4078-5cdf-9145-1468754fa926 | note | INSPECTION/TEST METHOD: Verify
fc7ea8a4-c7d4-504c-a957-89bed1ba4f6e | note | RECORD OF CONFORMITY: Checklist / Form
d07a3dac-3475-5b0a-8da1-2f221b237960 | note | IP
6845f17b-8f7a-5c8f-b193-59ce96f432df | note | RESPONSIBILITY: Geotechnical Engineer
3bed8b13-bd39-5ae3-93b9-400c889f6256 | date | Date Completed:
| checkpoint | 2.4 - External grout tubes to reach distal end of anchor hole and not withdrawn until completion of grouting
85ba58df-143c-5d3f-9e8d-89687971b5e9 | note | FREQUENCY: Each Anchor
709d41f3-570d-536e-9df5-0b839687db4a | note | ACCEPTANCE CRITERIA: Grout inserted at the end of the anchor hole to ensure desired grouting location
7a716df1-43f9-5a80-857e-00333d4a315f | note | REFERENCE DOCUMENTS: Drawings
de22fb80-ec97-5bc4-ac30-a136e61e73a3 | note | INSPECTION/TEST METHOD: Verify
a93ce91b-4485-5564-b3bc-a3b6e97f95e3 | note | RECORD OF CONFORMITY: This ITP Signed
fb6b95ae-1f08-5871-a6fd-e97032ea21cf | note | WP
91e7f94d-90cb-5b95-9740-c92a86bd153b | note | RESPONSIBILITY: Site Engineer
f5d54f62-fdb9-541e-964a-4b261d9c761e | date | Date Completed:
| checkpoint | 2.5 - Anchor location
15341037-83bc-584a-ab9d-956baef8cd67 | note | FREQUENCY: Each Anchor
10fdb2ca-48f6-57db-a3ca-a3fbb8e0fd36 | note | ACCEPTANCE CRITERIA: All anchors drilled at the location and to the minimum diameter specified
86850364-735a-52c3-a3bd-448b50ad118a | note | REFERENCE DOCUMENTS: Drawings, Survey setout
ba114edc-d4d4-559a-b37f-0149490b4dc0 | note | INSPECTION/TEST METHOD: Survey
15d9260c-b32e-5b22-88e7-79839f2e5dd2 | note | RECORD OF CONFORMITY: Survey Report
6db694dd-2ac4-5e90-9b83-9d8e1c163e7b | note | HP
a7d9b28e-689e-589c-bcb8-f855743393be | note | RESPONSIBILITY: Site Engineer, Superintendent
619b5466-6da1-5084-8aa4-f6d330edf53f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Acceptable hole
5bd9f404-08de-50c7-bc10-221b1aaef632 | note | FREQUENCY: Each Anchor
1246ec0b-24a8-5940-b622-6153bcbf46d0 | note | ACCEPTANCE CRITERIA: Acceptance that the hole is clean with minimal smearing
9e125759-53f3-5ccc-a6a2-bc588f30266b | note | REFERENCE DOCUMENTS: Drawings
f7711fa7-c6a4-5fbf-84d0-6e23864b6a3c | note | INSPECTION/TEST METHOD: Verify
7ad043a4-d8f1-52ed-a8a2-065bf7dee40c | note | RECORD OF CONFORMITY: This ITP Signed
b146998e-2518-5cb0-9d9a-f373d3f2fcc4 | note | HP
e5ef97ec-d099-5826-b5cb-31d4c6aa3883 | note | RESPONSIBILITY: Site Engineer, Superintendent
d55f4d8f-7b71-574f-97ca-f01e3b37bbe1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Anchor assembly supports
bf93a698-8b7d-57d7-b19a-effa12b451a3 | note | FREQUENCY: Each Anchor
f0da651e-bbeb-5c72-9f67-adf9ba67501f | note | ACCEPTANCE CRITERIA: Ensure adequate supports are in place to minimise likelihood of damage / bending to anchor assembly
297dce7e-cb6b-5e42-a825-7c2ce9cdf47b | note | REFERENCE DOCUMENTS: Drawings
31873d91-38b3-50ea-b267-ab2181aec58e | note | INSPECTION/TEST METHOD: Verify
3695b76f-881b-5e7f-8f09-9172cf794a4b | note | RECORD OF CONFORMITY: This ITP Signed
2e4ba234-a488-585f-9cb5-50e99039810d | note | WP
2a660f87-238b-5a92-b986-e935fb6d0f64 | note | RESPONSIBILITY: Site Engineer
a2436512-bb59-530e-bb02-f077e3eb0e9d | date | Date Completed:
| checkpoint | 2.8 - Corrosion Inhibiting Compound
15c9086f-ec0c-5d2c-9639-3fa7ac65c214 | note | FREQUENCY: Each Anchor
9a8c798e-b1c3-5c17-bf18-bcbf0820810b | note | ACCEPTANCE CRITERIA: CIC has filled the entire trumpet and protective cap
c90c0462-fed2-5034-bd3e-95a947fd6f9e | note | REFERENCE DOCUMENTS: Drawings
a300415a-559c-5781-9828-d9d7d57670c9 | note | INSPECTION/TEST METHOD: Verify
802bb2c2-469e-5fe4-a7bf-39ce2f689621 | note | RECORD OF CONFORMITY: This ITP Signed
2eb2b9bf-ef0a-57e6-a2c7-eddc9dbb391a | note | WP
a349d48d-cba5-5a3e-9067-0ebd4bb9f232 | note | RESPONSIBILITY: Site Engineer
2e1c3ae0-aa79-5929-b8b0-a4a45b986689 | date | Date Completed:
| checkpoint | 2.9 - Protective Caps
e3a1f240-662b-5c71-a556-6b003c7652af | note | FREQUENCY: Each Anchor
1c4c309b-ce66-5568-a3bb-abe632f329a6 | note | ACCEPTANCE CRITERIA: Protective Caps are watertight, allow for inspection and refilling of CIC
0939041b-952e-5dbd-9576-407b494c6230 | note | REFERENCE DOCUMENTS: Drawings
7fcf2d1b-b847-5c8a-8e77-0518bf248a7b | note | INSPECTION/TEST METHOD: Verify
09c9713d-2b70-527c-b030-a375b7a871cd | note | RECORD OF CONFORMITY: This ITP Signed
2aaf36f7-dc0c-5f3c-ad41-e0dfeb5f6546 | note | WP
5945fb44-350c-55d7-ba27-c69defea29db | note | RESPONSIBILITY: Site Engineer
01842d1c-6822-56b2-b6df-1fdbff5cd20f | date | Date Completed:
| checkpoint | 2.10 - Fluidity Testing
cfe0b329-9383-5c01-998b-180094e345d5 | note | FREQUENCY: Each Anchor
264f24bf-a99e-5d2b-892d-a35ca5d5c317 | note | ACCEPTANCE CRITERIA: Fluidity of emerging grout to be within 20% of inserted grout to ensure all low quality ground is displaced
5b8e2dc2-7b4a-564c-b874-3e9a357b208b | note | REFERENCE DOCUMENTS: Drawings
3e40bd76-c75d-5cb5-a6cd-ede80c6fae60 | note | INSPECTION/TEST METHOD: Verify
b409d9e8-f831-5463-8b44-5471a93b595c | note | RECORD OF CONFORMITY: Test
48a6bc91-7fe7-502d-a653-ce3417686d15 | note | TP
f456cad6-0849-5130-8197-93750450af7a | note | RESPONSIBILITY: Site Engineer
435950ec-c001-519a-b6df-1bb2e64b9e7d | date | Date Completed:
| checkpoint | 2.11 - Threadbar - post stress
620909a0-6649-5f9a-815d-b83392a3e3ed | note | FREQUENCY: Each Anchor
46ed1097-a663-5ac2-b087-f617200304e0 | note | ACCEPTANCE CRITERIA: Following stressing, all bars to be cut to allow for a minimum of 150mm to stick out from the bearing plate
dada4a29-c2ee-591c-9208-2ef38ecac03c | note | REFERENCE DOCUMENTS: Drawings
f43a2e56-31a1-5b64-a0e5-c837820962ad | note | INSPECTION/TEST METHOD: Verify
642a9447-e3f7-5d99-bf23-834ad5888dc6 | note | RECORD OF CONFORMITY: This ITP Signed
5224ff4e-7b28-50ec-a0a6-285ac8dca0da | note | WP
5a7ffb96-f1b5-589a-bb66-9daa3faa9df4 | note | RESPONSIBILITY: Site Engineer
60ed267d-cfb2-5275-b177-1288ee46507f | date | Date Completed:
| section | 3.0 - Ground Anchors - Testing
| checkpoint | 3.1 - 7 Day Grout Strength
e82ad5eb-238e-5ec4-a186-24d3b8b72ebd | note | FREQUENCY: 3 x 75mm cubes per anchor or batch (lesser) tested
56c0d875-5cd4-5e3a-bf98-ef8e4c400531 | note | ACCEPTANCE CRITERIA: 32MPa achieved
28c50ac7-c3e9-551b-be75-ffdcebb8b4e1 | note | REFERENCE DOCUMENTS: TfNSW
6c0ae861-820d-5da9-ad30-33a9be1f944b | note | INSPECTION/TEST METHOD: Test
18963b61-4619-5fed-8659-db21890114d6 | note | RECORD OF CONFORMITY: Strength result
6c1d8946-95ea-5e6b-8675-af80686cc7ad | note | TP
eb89113c-2f82-5cba-bdec-84fc379f47ce | note | RESPONSIBILITY: Site Engineer
47cbb069-9dea-5c75-864d-a6c3f571a229 | date | Date Completed:
| checkpoint | 3.2 - 28 Day Grout Strength
1c3030d6-1fb3-50f9-837c-e98b603328b5 | note | FREQUENCY: 3 x 75mm cubes per anchor or batch (lesser) tested
5bd6a3f6-15ef-5e5a-9009-2a094ebac70b | note | ACCEPTANCE CRITERIA: 40MPa achieved
455e966c-a35d-5188-971e-f609c464e98f | note | REFERENCE DOCUMENTS: TfNSW
e0320ba7-bb34-56c4-87f3-b28a74095904 | note | INSPECTION/TEST METHOD: Test
e73e4673-a8fb-5234-a199-5b33abe4fe67 | note | RECORD OF CONFORMITY: Strength result
cc2b56c0-3e08-5e68-aba3-db0b682469a1 | note | TP
17b872bb-b519-5f9a-a742-8626586d455b | note | RESPONSIBILITY: Site Engineer
d5c9284c-9167-5c0c-8349-42f12ba0a711 | date | Date Completed:
| checkpoint | 3.3 - Bleed Test
1df5adec-0a10-5904-be88-3de32957cc68 | note | FREQUENCY: One Test / Once per 4 hours
1ad1b698-2f10-5ae5-bf33-3a7c3df885c8 | note | ACCEPTANCE CRITERIA: Final bleeding < 0.5%
3ca2daa4-c5ba-5586-b6b4-bc16f20782f0 | note | REFERENCE DOCUMENTS: ASTM C940
a7939e67-dc05-5268-aa0d-a5b7904a0b3e | note | INSPECTION/TEST METHOD: Test
60366563-d21b-5b52-bc78-1e24543bdec4 | note | RECORD OF CONFORMITY: Bleed test result
abef15fe-18e6-5c0f-ab58-ebef5b18f6ca | note | TP
c1fd73da-67f0-5cc5-8508-5991aa701a5e | note | RESPONSIBILITY: Site Engineer
76c86637-b148-5a1e-a7ae-34e7fba1c8e3 | date | Date Completed:
| checkpoint | 3.4 - Fluidity Test - <20s after mixing
f51cb6c9-230b-557c-bb42-6adba920ef92 | note | FREQUENCY: Once per batch
945a13f3-59e9-5b7b-8709-89b7ef1349f0 | note | ACCEPTANCE CRITERIA: Grout to pass through cone test in <20s
ac0f66b5-91d9-5f1e-a257-e4245f28f151 | note | REFERENCE DOCUMENTS: ASTM C939
3b4594e0-8026-5596-994d-abb36eeee37a | note | INSPECTION/TEST METHOD: Test
9bf4da27-0ba3-5c16-a540-9a1f9accd0a4 | note | RECORD OF CONFORMITY: Fluidity Test Result
f4b3d03f-bbfa-5311-b958-871850ee8053 | note | TP
bd9ba7da-ebd5-5d80-a050-8d5c948608d6 | note | RESPONSIBILITY: Site Engineer
e0cd64fb-2bfe-5bb5-b25f-2fec9383b297 | date | Date Completed:
| checkpoint | 3.5 - Fluidity Test - 45m after mixing
701c8824-6e3a-562e-a129-d5d1d6656096 | note | FREQUENCY: Once per batch
0dc20905-ca42-57a6-b05b-7aff233ef674 | note | ACCEPTANCE CRITERIA: Grount to pass through cone test within 3s of first test
44d96b2e-ac8a-5ac4-bcaa-5499f789efbb | note | REFERENCE DOCUMENTS: ASTM C939
cb391575-2ea1-5815-95e3-5e11e7fc7615 | note | INSPECTION/TEST METHOD: Test
56f34506-d113-543f-b185-c5c192b2c922 | note | RECORD OF CONFORMITY: Fluidity Test Result
d5cb9a20-63c8-5ce4-bfa6-3ac1ce947530 | note | TP
777f8ed8-b18c-5fdc-8be2-3222365419c9 | note | RESPONSIBILITY: Site Engineer
50e9a413-bf92-5178-b8c6-e7a9a5e24d54 | date | Date Completed:
| checkpoint | 3.6 - Proof Testing
85a41d23-e7ad-502d-ac47-a27a80ded3e5 | note | FREQUENCY: 3 x Anchors, Prior to Production Anchors
0d0efaf4-fc03-578a-b458-29d4705bdd59 | note | ACCEPTANCE CRITERIA: Proof Testing undertaken in accordance with drawings to determine characteristics of ultimate resistance
6fdf5b81-7f5e-5e4c-99e8-46c17a71cdcc | note | REFERENCE DOCUMENTS: Drawings
7493a84f-97be-5f22-a586-328a4f775d2b | note | INSPECTION/TEST METHOD: Verify
5c965eae-7cc7-50ec-a550-50939f854069 | note | RECORD OF CONFORMITY: This ITP Signed
7ad7a375-30fa-5303-961e-f63d20e13551 | note | HP
8df4faa5-bfdc-5331-aa86-0868ceb7ae2e | note | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
a694a9c6-6a39-566c-b89d-97f57ebf094e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Suitability Testing
5c993666-e32c-5aa1-a454-a283de1c9097 | note | FREQUENCY: 3 x Anchors, Prior to Production Anchors
85d3d4e8-0de8-523b-9dd4-4749b1878035 | note | ACCEPTANCE CRITERIA: Suitability Testing undertaken in accordance with drawings to confirm anchor design, drilling method and installation will be adequate in existing ground conditions
c0c0203a-7772-50c1-8a0d-1ad609db5577 | note | REFERENCE DOCUMENTS: Drawings
13a57aad-b770-5e72-a7a9-af8385649d84 | note | INSPECTION/TEST METHOD: Verify
10c1ce97-fdcb-5020-9750-6c69ceb51df9 | note | RECORD OF CONFORMITY: This ITP Signed
7e91087a-2b3f-5bf8-8f8d-42a28e014df2 | note | HP
eca272ce-a76a-5163-a63f-1347ba0b5a75 | note | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
7e9b1f41-110c-57ec-a1f9-26f712bce6e4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Acceptance Testing
38d06cec-0958-5286-ae6b-6eb25605951f | note | FREQUENCY: Each Anchor
07afb663-df0c-5370-8760-25e0acb6c8c5 | note | ACCEPTANCE CRITERIA: Acceptance testing undertaken in accordance with drawings to confirm adequate bond strength and conform with acceptance criteria
c862757b-3a73-56ab-ac8d-a8e71d47db53 | note | REFERENCE DOCUMENTS: Drawings
9086351b-2f7d-52df-bf45-d4587a329a37 | note | INSPECTION/TEST METHOD: Verify
fc22ef40-42b6-5a93-a586-029c286a9f2e | note | RECORD OF CONFORMITY: This ITP Signed
78bcae35-bf37-53ec-ae01-0d57bd3fbb64 | note | HP
f2db878a-0283-5767-8bc2-5077c0a9d058 | note | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
5f350e61-bf31-5709-a3cc-7177c762555d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
cc8cda58-8b3d-5fd5-acb3-b891dc9cec22 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
84ae09c4-b647-525f-9856-0eb51b68692e | textbox | Print Name:
191d536b-0eaf-519e-8f97-bea46cf2e486 | textbox | Position:
cf7d64a2-6a0c-5f90-8be6-bb4c2c42ac7d | date | Date: