## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Drainage |  |  |  |  | Yes | Add Drainage checks | 0379271e-6998-4be0-aff1-d968a861619e
checkpoint-group |  |  | section | Storm Water
checkpoint-status |  |  | checkpoint | Plans correct issue and construction set
checkpoint-status |  |  | checkpoint | Check set out from builders
checkpoint-status |  |  | checkpoint | Check Plans for correct sizing and pipe material
checkpoint-status |  |  | checkpoint | All Falls achieved as per plans
checkpoint-status |  |  | checkpoint | All Manholes hauched as per code
checkpoint-status |  |  | checkpoint | All Cesspits, Manholes installed to correct heights
checkpoint-status |  |  | checkpoint | All Trenches compacted with compactor
checkpoint-status |  |  | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | Pipes tested for inspection
checkpoint-status |  |  | checkpoint | Rainwater Tank installed as per engineers report
checkpoint-status |  |  | checkpoint | Photos Taken
checkpoint-status |  |  | checkpoint | Inspection passed
checkpoint-status |  |  | checkpoint | Engineer Inspected
checkpoint-status |  |  | checkpoint | Mark up drawings Done
checkpoint-group |  |  | section | Sewer
checkpoint-status |  |  | checkpoint | Plans correct issue and construction set
checkpoint-status |  |  | checkpoint | Check Plans for correct sizing and pipe material
checkpoint-status |  |  | checkpoint | All Falls achieved as per plans
checkpoint-status |  |  | checkpoint | All Manholes hauched as per code
checkpoint-status |  |  | checkpoint | All Manholes installed to correct heights
checkpoint-status |  |  | checkpoint | All Trenches compacted with compactor
checkpoint-status |  |  | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | All ORG and RE installed as per plan
checkpoint-status |  |  | checkpoint | Pipes tested for inspection
checkpoint-status |  |  | checkpoint | Inspection passed
checkpoint-status |  |  | checkpoint | Mark up drawings Done
checkpoint-status |  |  | checkpoint | Photos Taken
checkpoint-group |  |  | section | Water Mains and Infrastructure
checkpoint-status |  |  | checkpoint | Plans correct issue and construction set
checkpoint-status |  |  | checkpoint | Check Plans for correct sizing and pipe material
checkpoint-status |  |  | checkpoint | EF welding completed by a certified welder
checkpoint-status |  |  | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
checkpoint-status |  |  | checkpoint | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
checkpoint-status |  |  | checkpoint | Pipes tested for inspection
checkpoint-status |  |  | checkpoint | Chlorination of Pipe work completed as per TCC IDC Code
checkpoint-status |  |  | checkpoint | E Coli Test done and Passed
checkpoint-status |  |  | checkpoint | Warning tape installed
checkpoint-status |  |  | checkpoint | All Trenches compacted with compactor
checkpoint-status |  |  | checkpoint | Inspection passed
checkpoint-status |  |  | checkpoint | Mark up drawings Done
checkpoint-status |  |  | checkpoint | Photos Taken
checkpoint-group |  |  | section | Dewatering
checkpoint-status |  |  | checkpoint | Pumps supplied able to do flow rates required
checkpoint-status |  |  | checkpoint | Wells installed to heights slightly lower than cut
checkpoint-status |  |  | checkpoint | Storage tanks install and linked dup to prevent overflow to street
checkpoint-status |  |  | checkpoint | Valves installed on tanks for Sludge removal
checkpoint-status |  |  | checkpoint | Water Quanilty Monitored and checked daily
checkpoint-status |  |  | checkpoint | Balance pipes installed between tanks
checkpoint-status |  |  | checkpoint | Water Flow rate checked daily
checkpoint-status |  |  | checkpoint | Power supply checked for reliability
checklist-sectioned |  |  | checklist | First Fix |  |  |  |  | Yes | Add First Fix checks | e3d0b476-9849-4560-96b2-86e0569535c6
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Area accessible and ok to begin work
checkpoint-status |  |  | checkpoint | Plans correct issue and construction set
checkpoint-status |  |  | checkpoint | Check Plans for correct sizing and pipe material
checkpoint-group |  |  | section | First fix checks
checkpoint-status |  |  | checkpoint | Sanitary fixtures and fittings specifications received for set out
checkpoint-status |  |  | checkpoint | All Pipes silicone though noggs
checkpoint-status |  |  | checkpoint | Vents install though roof
checkpoint-status |  |  | checkpoint | All stud stiffeners installed
checkpoint-status |  |  | checkpoint | Marshall flashings installed
checkpoint-status |  |  | checkpoint | All pipes pressure tested to 1500KPA (fusiotherm refer to test procedures)
checkpoint-status |  |  | checkpoint | Gas sized and install as per NZS 5061
checkpoint-status |  |  | checkpoint | Gas tested to 7KPA or Greater
checkpoint-status |  |  | checkpoint | Gas piping material correct for installation
checkpoint-status |  |  | checkpoint | Noggs installed for fixing of sanitary fixtures and fittings
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Photos Taken & attached
checkpoint-status |  |  | checkpoint | Inspection passed
checkpoint-status |  |  | checkpoint | Work completed as per spec and tidied up
checklist-sectioned |  |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S Toolbox Talks | aee625fb-2770-4156-8739-d577c2cec47f
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 09020810-29af-59cb-8738-ed3c206406fa |  | textbox | Office location:
text | 22438a23-102d-5a40-9f75-a5112c4f34c4 |  | textbox | Who is running this meeting:
text | 84e17b0b-b543-51f0-a6ff-0ddf7666f6f3 |  | textbox | Company
text | a4e2c638-2e08-5854-93c5-fa6f6d3da816 |  | textbox | Agenda items:
text | 4a37a44d-e7dc-53e7-af99-a075e4607111 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | 1
text | 159ba9d8-dafe-561e-91a5-2fb4a6f40812 |  | textbox | Issues raised from site safety inspection:
text | 14c27c0b-2226-5434-9e78-f75e190ba8f6 |  | textbox | Actions:
text | 8f3a5c2e-e3f5-503d-ab85-9c42870f768f |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 2
text | 3bb0df4d-5496-5a54-9242-25d4989edd43 |  | textbox | Issues outstanding from previous briefings:
text | eacd8cef-901d-5ac0-9da6-f4e2cdbe9b07 |  | textbox | Actions:
text | 11ff0792-1f5a-5290-ba6c-61eddc0a518a |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3
text | 6b604528-3642-5d95-8405-0bd6a4296afc |  | textbox | Employee-raised issues:
text | 39861733-b210-585c-bb9a-2230d5f813a7 |  | textbox | Actions:
text | a74b34ec-f244-59df-8f9a-a687c130c680 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4
text | 2c490cd2-0a6f-5c5b-aac8-54a874720dbf |  | textbox | Positive safe-action observations:
text | ccd2a70e-350d-5092-a54d-b2d401e73f89 |  | textbox | Actions:
text | 8ec86626-e486-5bc2-b22f-aca37c7d7b49 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5
text | f86da1f9-2286-5b05-ab4c-9edea3cfcdcc |  | textbox | Incidents or injuries:
text | 98cac4be-9db4-5c20-9648-0af36717e94b |  | textbox | Actions:
text | 34abfd1a-e08b-5c05-8747-f34e53c99b6e |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task & Action/Outcome
text | 4a91354d-f959-5d7d-b0dd-96a83061d23c |  | textbox | 1
text | 1a014b15-25c7-571d-b186-e1ae30bb1438 |  | textbox | 2
text | 4256dbdb-804a-563c-8e45-281d580fc06d |  | textbox | 3
text | 76775c53-3903-5e27-9d33-11c9897b44a4 |  | textbox | 4
text | 0f815e2c-ddba-5f14-94c0-d163ebb0b4cf |  | textbox | 5
text | 0738b909-5034-52d9-acbf-e110260384c9 |  | textbox | 6
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Issue & Action
text | e8a4616c-147b-560c-87e6-28e19c37c713 |  | textbox | 1
text | e108f108-e763-58c1-af6a-939e1104e89f |  | textbox | 2
text | af8f69ab-3326-548f-9084-201b968e9b0a |  | textbox | 3
text | e5c29fb7-501b-5efb-8885-69a4bdedea67 |  | textbox | 4
text | 3e654e50-dfd1-5746-832a-11bf8f8838e9 |  | textbox | 5
text | 74ccec0f-4832-5df4-a4f8-8c95739b8863 |  | textbox | 6
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Item & Action
text | 6c0f4fe2-f9e8-5c25-ab0c-381203cf5f3b |  | textbox | 1
text | 51dbd5bc-d440-58dc-84ec-581fd1ae8935 |  | textbox | 2
text | 44f584c0-17ff-522a-a902-77cb68a7d7d7 |  | textbox | 3
text | 129f0ed8-fae2-5475-ba5d-daf5fa086a90 |  | textbox | 4
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Reviewed and signed off
text | ed8044f2-9314-58e9-9593-c47d5c920671 |  | textbox | 1
text | 8fc8a6ca-10ec-5144-86da-4b9c74916fa9 |  | textbox | 2
checklist-sectioned |  |  | checklist | Underfloor |  |  |  |  | Yes | Add Underfloor checks | c187c1db-176c-4a8e-9718-c1c7e445d26b
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Area accessible and ok to begin work
checkpoint-status |  |  | checkpoint | Plans correct issue and construction set
checkpoint-status |  |  | checkpoint | Check set out from builders
checkpoint-status |  |  | checkpoint | Subgrade and bedding detail as per Plans - Gap 20/ Sand
checkpoint-status |  |  | checkpoint | Testing of subgrade required
checkpoint-status |  |  | checkpoint | Wrapped all pipe work with a min of 25mm though concrete areas
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Hot Water System (relief drain)
checkpoint-status |  |  | checkpoint | Drains laid to correct falls
checkpoint-status |  |  | checkpoint | Pipes wrapped though floor
checkpoint-status |  |  | checkpoint | Pipes tested for inspection
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Photos Taken & attached
checkpoint-status |  |  | checkpoint | Inspection passed
checkpoint-status |  |  | checkpoint | Water needed in floor for 1st fix
checkpoint-status |  |  | checkpoint | Work completed as per spec and tidied up
checklist-flat |  |  | checklist | Fire Penetration |  |  |  |  | Yes | Add Penetrations | 7de5d2ca-f5dd-4b93-8c0f-9b48d51b8b6d
checkpoint-status |  |  | checkpoint | Wraps/ Collars/ Cast in installed
checkpoint-status |  |  | checkpoint | Seal approved for the wall / floor type
checkpoint-status |  |  | checkpoint | Seal approved for the penetration & its application
checkpoint-status |  |  | checkpoint | Are pipes supported as specified by the manufacturer
checkpoint-status |  |  | checkpoint | Sealed is installed as per specification
checkpoint-status |  |  | checkpoint | Penetration Label includes
checklist-sectioned |  |  | checklist | Second Fix |  |  |  |  | Yes | Add Second Fix checks | 8938b6cf-d712-4fe2-b8d4-11d21fa86842
checkpoint-group |  |  | section | Preinstall QA
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-status |  |  | checkpoint | Area accessible and ok to begin work
checkpoint-group |  |  | section | Second fix checks
checkpoint-status |  |  | checkpoint | Fixtures and fittings checked for damage
checkpoint-status |  |  | checkpoint | Flanges installed on all penetrations
checkpoint-status |  |  | checkpoint | All fixtures sealed with silicone as required
checkpoint-status |  |  | checkpoint | All fittings checked for leaks
checkpoint-status |  |  | checkpoint | Hot Water system commissioned
checkpoint-status |  |  | checkpoint | System commissioned
checkpoint-group |  |  | section | Handover checks
checkpoint-status |  |  | checkpoint | Photos Taken & attached
checkpoint-status |  |  | checkpoint | Work completed as per spec and tidied up
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 39c5b4b4-bcb3-4750-93f0-4c72083cfceb
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 1d219079-d951-5e85-8d55-3db63943c050 |  | textbox | Reference/Drawing/Instruction Number
text | dd08d29f-e2d7-502d-b954-98262563c270 |  | textbox | Variation Area
text | 35251c75-59d5-5066-bc14-5e905bb08899 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff