## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | e81af7a3-c77b-4bf5-8d04-700f4266b5f1 |  | checklist | Drainage - Stormfilter Install Checklist |  |  |  |  | Yes | Drainage - Stormfilter Install Checklist | 026cb59e-f68c-4b3b-8d4d-295b2d994fd4
checkpoint-group | 75afb62b-967b-40c3-a4dd-b1f378c016d4 |  | section | Stormfilter Install
checkpoint-status | da279c0f-90c3-4262-8858-de6c40c2129a |  | checkpoint | Latest consented drawings
text | 778a99e7-55bb-557d-8462-8b94ecb30ed0 |  | textbox | Drawing Ref No.
checkpoint-status | 34324387-87fd-4a05-93bc-4d46e955b342 |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | 72e61127-c7f4-4e57-9949-19b5a7c94680 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | c52a870a-ffc9-4176-8be7-920717d18a17 |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | 965f32bc-3aff-459f-a2bb-a10fe85c62a5 |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | dc4c2f29-9df9-450d-99a2-40554aec4fde |  | checkpoint | Correct manhole installed to specified height and sitting level
checkpoint-status | da8d0d80-3e08-4a7b-9b64-de97ff2c665e |  | checkpoint | Manhole Risers Installed (if applicable)
checkpoint-status | 1f6c8fb4-396b-4b98-97a6-9ce289c0bd40 |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | 022db12f-2cf8-49e0-a76e-ad02c79c6562 |  | checkpoint | Manhole benching completed and acceptable
checkpoint-status | e7ce2067-8bf3-44c3-ae14-d8c05b25536f |  | checkpoint | Concrete Lid Installed and sitting appropriately
checkpoint-status | 2ef097ec-84ec-4612-918a-723c2035aaa0 |  | checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint-status | 75cccce6-d7ef-4dec-b63a-4def5b11d239 |  | checkpoint | Signoff on Completed Work (Council etc)
checkpoint-group | 789669c1-01a8-478c-82bd-3d665fcf058e |  | section | Backfill
checkpoint-status | afcca20e-bdcf-495e-ba3b-20b8d4e32827 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | cabb433e-0a1c-44ea-8277-985b5f82c676 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | bae757e0-e212-4f83-a343-3c461fcd0b7e |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 010908d6-b450-46dd-bfb6-a95442d6e731 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 51026825-e71d-441f-b27e-0fbc7b02ca7f |  | checkpoint | General photos and observations during backfill
checkpoint-status | 25840aa8-5d6a-4910-a918-3ee817574cc1 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 54e5dc69-75fc-434c-91c5-77b3b061d968 |  | checklist | Sewer- Pipeline Installation Checklist |  |  |  |  | Yes | Sewer- Pipeline Installation Checklist | 11bd74d4-09a1-43a9-ab54-cb63f842e7a9
checkpoint-group | 2ea9b22a-7cd1-4a33-8081-fc50d6e68f49 |  | section | Pipe Laying
checkpoint-status | 1c1bee75-d978-43b2-bc11-dd0829bf1dc3 |  | checkpoint | Latest consented drawings
text | 8c179bf3-b76b-5c8d-b591-ceba9958c6d5 |  | textbox | Drawing Ref No.
checkpoint-status | 0d9fa3cb-4a17-4a77-be3b-074e9274e764 |  | checkpoint | Setout completed checked and accurate
checkpoint-status | d1c77947-bc97-4dc8-89f5-a79ca8b33c63 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 98ae6e1b-6cdf-4d0d-98e9-cc052615b4b8 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | f530ed9a-6b08-4d9f-a1c6-c2adbdf7195e |  | checkpoint | Bedding depth and material correct
checkpoint-status | 7cd7cd8e-000e-42f3-8475-dd85047f8a96 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 241195c3-40af-5bf7-a5dd-c03b1a77fc50 |  | textbox | Start Invert
text | afe51843-ad30-5951-b409-e1b1783cf675 |  | textbox | Finish Invert
text | c8ade721-dd0c-510f-a0da-1d43f906666c |  | textbox | Grade of Pre-Line %
text | d689c05f-6165-5ab1-89e1-760e564de18b |  | textbox | Product Type
checkpoint-status | f9939f12-8642-4ce8-9243-8d849931ad23 |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | c0ef5894-8168-4f12-8061-8f740bf88cb2 |  | checkpoint | Local Authority Inspection Passed
text | f95ee5b8-5824-5e16-a80f-40cc331b0fca |  | textbox | Name of inspector
date | e7dc8d34-89ce-55fb-94ec-254531610fa5 |  | date | Date
checkpoint-status | e8318124-db91-409a-bfab-ab14bbbf28f1 |  | checkpoint | Pipe Laying Completed
text | c2099ccf-e610-516d-b8fb-d184ef7d7c64 |  | textbox | Laid by
checkpoint-status | a836a212-01cd-478b-9967-43be6511b9f8 |  | checkpoint | Bedding Sound
checkpoint-status | c235b591-145a-48c5-855b-fa92336ef6c8 |  | checkpoint | Soil Removed
checkpoint-status | d8b2546a-a491-48d3-ad12-cf452b367c86 |  | checkpoint | Trench Compacted
checkpoint-status | 26b04220-fb70-475b-9829-005dbccbc9f1 |  | checkpoint | Hard Filled
checkpoint-status | 36d4d569-e8ec-43dd-bd14-e6a3cb6c114a |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 3645f26a-8341-41f4-85c9-5dd2131d9666 |  | checkpoint | Air Test Complete
checkpoint-status | d1ec2f6e-493c-48c2-bc54-a436e6440195 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | c9a039ef-9ef7-516f-adc1-c7147b766485 |  | textbox | Sign Off By
text | 599a8b31-1a72-55fb-ac27-0ad050ceba29 |  | textbox | Acknowledgement of checklist by
text | f9d71c67-9215-54b7-9c8d-2a963439065f |  | textbox | Foreman
checkpoint-group | ce80a85a-ed83-4753-877e-843263014abe |  | section | Backfill
checkpoint-status | c86fce5d-49a9-4d8a-ae0a-0d3c1d0586ed |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 0cf23ec8-62be-4f3d-8d8d-ff7a69422c87 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | c3d7c48c-8b17-4ae3-8e80-fe43bd1fb7f0 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | b2c74591-c3ca-44ec-88b4-9cb4152ad16a |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 24b55fcc-5fce-4c3d-a377-03d9f7b0785f |  | checkpoint | General photos and observations during backfill
checkpoint-status | 7a6c6576-da1e-4929-b044-5d5465f13dbc |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | acc85a82-46ef-4b06-b223-d7afdd0f82b1 |  | checklist | Civil Install Checklist |  |  |  |  | Yes | Civil Install Checklist | 1a22266b-3815-4b77-a02c-26610b40f113
checkpoint-status | f096ea47-d308-4de2-9e00-bae482cfc640 |  | checkpoint | Foundation Set out
checkpoint-status | c18e1a90-0aee-4444-b6d0-ccaaaf7e89b5 |  | checkpoint | Confirm Levels Correct
checklist-sectioned | 39bb1284-5123-4047-b421-e26f66365868 |  | checklist | Drainage - Tank Install Checklist |  |  |  |  | Yes | Drainage - Tank Install Checklist | 1cf70f67-941e-42ec-9003-48f725f1b032
checkpoint-group | fb5ee3a3-0248-49b8-81af-4b7d9bbb0538 |  | section | Tank Install
checkpoint-status | cc92c27e-8a50-48d4-a550-ffb12aa76894 |  | checkpoint | Latest consented drawings
text | d9f81119-c5aa-58e1-b0a7-acacadf6dbfb |  | textbox | Drawing Ref No.
checkpoint-status | db1f4d8b-6542-401c-9ba5-e6f728427945 |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | b152d7d9-0bf7-4ce2-af27-febe0231f093 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 602fbb9a-a397-46bd-b5a4-643d536cc186 |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | b4f1e482-c1c7-4978-969a-a1e1659dcc61 |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | a12d62a5-5aab-4ba6-89ce-4c916f80c3fa |  | checkpoint | Correct tank installed to specified height and sitting level
checkpoint-status | cd260724-ba60-4e90-bf02-1ff20b2fc1aa |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | 204d214d-c7e8-4cf9-bbf9-c0d1cd866fba |  | checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint-status | bc77ad00-6e73-4577-978b-43d226a0f020 |  | checkpoint | Signoff on Completed Work (Council etc)
checkpoint-group | adaf7a4c-35fc-4414-a3ce-c43d1136dc43 |  | section | Backfill
checkpoint-status | cc8826d5-30d2-4391-b159-d7bbdb26d779 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | fb251cfd-3710-43ec-87bf-3df8790883ce |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | f15e86d1-1a79-419a-80f6-86b2ec6932f7 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 5c68aa46-6b7d-4358-b4ec-67a2afc3d840 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 41b04b0e-84cf-4679-b826-180256b0474f |  | checkpoint | General photos and observations during backfill
checkpoint-status | e1c93ed5-4b18-475c-ab65-88509855d831 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | 73d633af-5410-4378-beab-b92d29a119e2 |  | checklist | Drainage Installation |  |  |  |  | Yes | Drainage Installation | 20ba4ef8-7a73-49c2-a3c4-ed4322f9e767
checkpoint-status | 2591a61b-7708-4aa6-a44f-9db2b6409385 |  | checkpoint | Setout and position checked and confirmed
checkpoint-status | b04e76fa-05b6-4c86-8924-7ab46347bcda |  | checkpoint | Trench width and lid level (attach photos)
checkpoint-status | 785a4341-db08-414f-abea-723fac4c3e25 |  | checkpoint | Gap 10 & 65 measured and ordered
checkpoint-status | 6d6cd474-f3e8-4a25-becb-12585c338931 |  | checkpoint | Stockpiles & cart out confirmed
checkpoint-status | 52d8089e-7135-4e4f-8b7e-7d765da2790d |  | checkpoint | Pipework installed as per specification
checkpoint-status | 05906801-57e3-4a0c-8117-a6aab9f5b7f7 |  | checkpoint | Pipe test booked and test ready
checkpoint-status | 11dbbe4c-25f1-411b-b2bb-adcf2b65ed9f |  | checkpoint | CCTV complete
checkpoint-status | 37f19a1a-571a-4289-8054-a2da4bb38126 |  | checkpoint | As built plans complete
checkpoint-status | ea4618b2-0fad-418f-a7cd-3fa791609923 |  | checkpoint | Clegg test on hardfill (results recorded)
checkpoint-status | 9a255d63-d900-4f50-a694-0c9c167cec0b |  | checkpoint | RON & CAR signed off
checkpoint-status | eabd0924-08a4-4202-83d7-3310bab03ca6 |  | checkpoint | Pipework complete & ready for sign off
checklist-sectioned | 132c3e7f-4260-4394-9fb2-900683a6a59c |  | checklist | Below Ground Services Checklist |  |  |  |  | Yes | Below Ground Services Checklist | 2869ff8c-f21e-4cc2-a7fc-c314a610c440
checkpoint-group | bc910152-6d1f-4359-806b-2a8b1122e42c |  | section | Pre-Installation
checkpoint-status | f523af06-e001-4e3c-81ce-b003ccf52bd0 |  | checkpoint | Pre-Installation checks complete
text | d14abfb7-8442-5a8c-b601-415bc9ceb9db |  | textbox | Drawing Red No:
text | 42e53e28-9763-5774-90d8-5593dd416a7d |  | textbox | Starting Point:
checkpoint-status | d008d8a6-4b18-4e04-916f-b6800b4c10e4 |  | checkpoint | Finishing Point Established
text | 98c0ad19-17b3-5445-b08b-43d0730ea1df |  | textbox | Grade of Pre-Line%
text | 34591b0f-7902-5cbe-a665-b3123792010f |  | textbox | Level Obtained
checkpoint-group | a75245a7-eaa4-4794-940d-cc9997bfedc6 |  | section | Installation
checkpoint-status | e49bc9df-11c2-415f-bc7b-8a67d99fd824 |  | checkpoint | Pipe Work Tested
checkpoint-status | 06fc58d8-2605-49b3-af70-ab07faa39d78 |  | checkpoint | Air
checkpoint-status | 80135cb2-e942-4528-a2e2-0c89b5c17eb1 |  | checkpoint | Water
checkpoint-status | b6441f91-31a2-4344-80ab-f150acef8b22 |  | checkpoint | Visual
checkpoint-status | 301e909b-7be3-48fa-96a9-2c82d2d3900c |  | checkpoint | Backfill Material
checkpoint-status | 2b201df8-aed9-454b-b465-4b1af58c97b4 |  | checkpoint | Local Authority Inspection Passed
text | b4288d23-f7a9-5742-b242-148c34a5d821 |  | textbox | Name of Inspector:
checklist-flat | 9581fdb1-5e61-4fa8-8d05-f2487377de9f |  | checklist | As Built |  |  |  |  | Yes | As Built | 342ff5a0-9c62-4d26-843b-8f4b71c814d5
checkpoint-status | 1aaec3df-3309-4067-afc4-5238cb1c6838 |  | checkpoint | As built Pipework complete and ready for sign off
checklist-flat | 88ac5466-ed63-4a0a-997f-71443e5ea713 |  | checklist | Cesspit Installation |  |  |  |  | Yes | Cesspit Installation | 5218077e-98a5-4ed9-816c-8b7f8903d4b3
checkpoint-status | d73c2ce4-128f-4992-924c-a0a0238009a4 |  | checkpoint | Setout & position checked and confirmed
checkpoint-status | 195f701e-2691-4cc9-8f5c-8dc05f8e03b0 |  | checkpoint | Cesspit installed as per standards
checkpoint-status | c30d625c-311f-4e29-8873-a7f1db5e33f4 |  | checkpoint | Setout & position checked and confirmed
checkpoint-status | 22381c22-dd1a-4e61-bd50-63bf2d639ade |  | checkpoint | All cut pipes epoxied
checkpoint-status | 7ef0f2ab-def2-4daf-9054-953764f196a5 |  | checkpoint | Confirm Levels Correct
checkpoint-status | 2c74ef9d-221e-41f3-9714-39222e5ce1f5 |  | checkpoint | Cesspit cleaned of all Debris
checkpoint-status | 3cde5380-62b9-48e1-83a0-132b94b70f53 |  | checkpoint | Concrete Apron installed (if required)
checkpoint-status | 66a7aa5c-29e4-4839-85a9-6fbead1374d1 |  | checkpoint | Frame & Grate alignment checked
checkpoint-status | 527a27ad-8dfa-4f4c-8b45-82f9f82ab72f |  | checkpoint | Minimum sump depth checked
checkpoint-status | 88778cc2-035f-4c47-96d3-1b89896cf99a |  | checkpoint | Captive Grates installed (if required)
checkpoint-status | 9422dc07-0fb6-4a4b-9bcf-5b5dd4ceb0ec |  | checkpoint | Cesspit complete & ready for sign off
checklist-sectioned | 20fcec2f-a7d6-4ac8-835f-bd1a32aece88 |  | checklist | Watermain- Pipeline Installation Checklist |  |  |  |  | Yes | Watermain- Pipeline Installation Checklist | 898171b8-de79-45c1-ab3f-a7f2221e4adc
checkpoint-group | 01332502-e7db-42a9-938a-9e2e44d26b8b |  | section | Pipe Laying
checkpoint-status | 2a56b5f4-bf09-4a45-b2cb-f0b72d292380 |  | checkpoint | Latest consented drawings
text | cd4dcfe6-09d6-5ca1-8e76-83a236d3a34c |  | textbox | Drawing Ref No.
checkpoint-status | 809f752e-9e83-4885-8932-babda717a73a |  | checkpoint | Setout completed checked and accurate
checkpoint-status | f3b98ce2-0f55-4598-a4ff-24547372f1f8 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | e7839c36-93c6-41b3-b07f-4ead760e12fd |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 00802352-383f-4512-b015-6b0839ec5d7a |  | checkpoint | Bedding depth and material correct
checkpoint-status | 6bba13c1-1508-47be-95e7-5f20fbca7425 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | e5e86452-e5ce-53d4-9322-b8aa37bfd4b4 |  | textbox | Start Invert
text | 85078244-25b2-5a7c-9a5a-c1fcacfb2374 |  | textbox | Finish Invert
text | e8c1d4fb-bc4f-5724-9029-742b3544ef6a |  | textbox | Grade of Pre-Line %
text | 3a4e76bd-b984-506e-ae93-69d205555dfa |  | textbox | Product Type
checkpoint-status | 8c454595-8b8a-4847-8987-223219909e93 |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 4382815c-39ba-45df-9321-78daed8f218e |  | checkpoint | Local Authority Inspection Passed
text | 4ba9cea2-b91e-52f8-9303-168a65fd354c |  | textbox | Name of inspector
date | 77bb158c-76f5-5161-b3d9-a5e9b54edb4d |  | date | Date
checkpoint-status | a91a6524-131c-4a99-9062-b0916c14defb |  | checkpoint | Pipe Laying Completed
text | b13d32e4-7204-5101-8f84-e40e0062082d |  | textbox | Laid by
checkpoint-status | 334b880f-c585-4be3-8cdf-9add569dd7bd |  | checkpoint | Bedding Sound
checkpoint-status | 385bb3b1-7e19-4dd6-99d8-9498b34873f8 |  | checkpoint | Soil Removed
checkpoint-status | c4dce0b1-8e7d-4cbc-87f4-8b2cb92d5f01 |  | checkpoint | Trench Compacted
checkpoint-status | dcbe25f5-61fb-4f85-969f-a6ef0d69ab97 |  | checkpoint | Hard Filled
checkpoint-status | a3974588-ce96-446e-99b0-429659690408 |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 86011f9d-4960-45ef-a8c0-5f51e99e6e8f |  | checkpoint | Air Test Complete
checkpoint-status | 511b251a-8e3b-46ec-baa4-0d7a5937eee1 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 4cf2ce70-e7c3-538a-8d3e-31fdb99ed116 |  | textbox | Sign Off By
text | 8edea8a5-3860-57e9-aeef-1958fec31c5e |  | textbox | Acknowledgement of checklist by
text | b74350e0-4688-515c-b22e-50e977ced494 |  | textbox | Foreman
checkpoint-group | c9bbd766-6e7f-4768-8e50-de9dc077bdc2 |  | section | Backfill
checkpoint-status | 50a6ad60-f903-456e-a27d-674c14184215 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 4abd9cbc-8561-4dbf-9e6b-cdd41eaab587 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 77582235-c24b-4162-b1d5-6f8cf42b3715 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 662214c0-8227-4b03-ac76-bebbb49381ab |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 743a5579-ed2d-46d8-870a-3fac638a27a3 |  | checkpoint | General photos and observations during backfill
checkpoint-status | eda854bb-4bea-40fc-9999-50055c1eb5e6 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | dc54bafd-d777-467d-923c-75092122d6ac |  | checklist | Stormwater- Pipeline Installation Checklist |  |  |  |  | Yes | Stormwater- Pipeline Installation Checklist | 8d41cd1e-7a65-4551-a1d3-ebeeca2b1660
checkpoint-group | 3afc0d28-4a74-4381-aba1-ab6bbc1bc7ca |  | section | Pipe Laying
checkpoint-status | 0e7aaaa3-b759-4859-b836-2d8db0e93825 |  | checkpoint | Latest consented drawings
text | 02170c69-7fa0-536e-a2e2-049dcb12f80b |  | textbox | Drawing Ref No.
checkpoint-status | 48b9b4e0-5649-4bc9-87a0-b179262693cc |  | checkpoint | Setout completed checked and accurate
checkpoint-status | e3b4f544-f151-4f36-8301-84ac59ec0f67 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 3b5b1990-1547-45ca-a0fc-7c2dada5ce89 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | f4c14850-749f-415e-ad60-4ac5d54034f9 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 49164952-313a-4b22-92ab-3b847456b693 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 25de5498-1c5e-52ba-b09c-2738e735c5f7 |  | textbox | Start Invert
text | d2fde892-861c-532f-ad0b-01df67f4f512 |  | textbox | Finish Invert
text | 67584bf2-e34d-51f6-9954-de7485551d17 |  | textbox | Grade of Pre-Line %
text | b53d4005-5ea6-56ff-be49-e446b381097c |  | textbox | Product Type
checkpoint-status | d27c0140-2652-49c4-b093-b61ea6421f8a |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 9f1341e4-974b-446c-82c5-1c365476fdba |  | checkpoint | All Downpipes have been checked, installed and approved
text | 9c1ead20-6067-5fa1-8b04-f66181d26542 |  | textbox | How many installed?
checkpoint-status | 66273d08-a3ff-40b9-bb80-476c78573c3f |  | checkpoint | Location confirmed
checkpoint-status | c8e8b675-41b0-4bd4-ba43-7d4ad4ea7bdc |  | checkpoint | Heights are correct
checkpoint-status | 2d7339b5-9c3c-472e-88be-1274d95fae9d |  | checkpoint | Caps are secure
checkpoint-status | 0961e97c-8ada-404c-ad74-2904d17d1402 |  | checkpoint | All Cess Pitts have been checked, installed and approved
text | dfd00599-f92d-5e9f-9c18-457ee8a3e3dd |  | textbox | How many installed?
checkpoint-status | 3a50c613-e53a-450c-80ee-79d3b5fdbf55 |  | checkpoint | Location confirmed
checkpoint-status | a7af3f46-3793-48a3-8c2e-e30ac62b04b5 |  | checkpoint | Heights are correct
checkpoint-status | cb9aae7e-d22c-4433-b2f9-441e783eb6c8 |  | checkpoint | Caps are secure
checkpoint-status | 5c517e65-621c-49c1-ac0f-1487bcf6d65c |  | checkpoint | Pipe Laying Completed
text | 5680ef68-3106-5432-92f8-73e61515c5bf |  | textbox | Laid by
checkpoint-status | bd0edfc9-e6fb-42a4-bf63-bddc0ae5358b |  | checkpoint | Bedding Sound
checkpoint-status | 7a3633d0-cb1d-4456-aa88-e669f9ab1678 |  | checkpoint | Soil Removed
checkpoint-status | e2eee042-ea5b-4720-bd88-396227607c17 |  | checkpoint | Trench Compacted
checkpoint-status | 972937fa-1913-4765-a4d9-fca9bf01efc1 |  | checkpoint | Hard Filled
checkpoint-status | ea1108a1-ab36-44be-b4b0-f8ba8a655b54 |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 8d403cc0-6693-4a14-896c-fcbfa116a6d9 |  | checkpoint | Local Authority Inspection Passed
text | de4ba539-ce9d-55ed-9dd5-d3ffbccb5ce6 |  | textbox | Name of inspector
date | ba426d23-de86-512a-8c92-7d7771a49d82 |  | date | Date
checkpoint-status | 71b6e6bc-2d00-4ab8-a1fc-379a04914c72 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 24c70fb6-d069-53e8-b29b-b9586de30606 |  | textbox | Sign Off By
text | 16ed6e6b-2ad2-56a0-bc7a-8e8a550f3eef |  | textbox | Acknowledgement of checklist by
text | 731f0452-32e7-5eb7-b2ad-5b6fafbb29a1 |  | textbox | Foreman
checkpoint-group | 6b9d2086-f639-4c65-83ae-0f003272baa9 |  | section | Backfill
checkpoint-status | 5189e464-7ecd-4c78-8d87-06a10c81f1e8 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | e8233221-50c5-4e57-80da-b6247bc47cdb |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 88e16a35-9b12-408f-abe1-0d72356f8ac5 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 2be963c6-9cac-4fda-b7ed-5911896e1d34 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | e3fbc0b4-b1ef-444d-bf09-7fc7dca2dfe3 |  | checkpoint | General photos and observations during backfill
checkpoint-status | e63cdfb5-e127-4e8a-922a-c3874991123d |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | f27e3b52-eeb0-4f2f-9c90-1ad5bf2cc4b2 |  | checklist | Firemain- Pipeline Installation Checklist |  |  |  |  | Yes | Firemain- Pipeline Installation Checklist | 983b2a65-cfa0-40e8-a6b6-25e336c91891
checkpoint-group | bbfb0eee-bd75-47db-8bbc-b635cc35e285 |  | section | Pipe Laying
checkpoint-status | 4286b162-fc54-450b-8801-0909077a8f69 |  | checkpoint | Latest consented drawings
text | f0b765d7-2793-596f-9491-77eb67879be8 |  | textbox | Drawing Ref No.
checkpoint-status | f8973d61-a738-4e82-bc00-839825bae2af |  | checkpoint | Setout completed checked and accurate
checkpoint-status | e0862b8a-e7a5-43fa-8110-153fe94cc721 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | ede27b8d-82ce-4d21-b80f-dd7e8a6f953f |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 77a9a8ec-faed-4244-8944-bad133149ebe |  | checkpoint | Bedding depth and material correct
checkpoint-status | 02a1878d-1fe3-4bf6-b6a4-04c1c4d15e55 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | f05119cc-3a62-51a4-8b8d-0015d9353d01 |  | textbox | Start Invert
text | d97c3522-c450-505f-ad25-4a5e055da0ae |  | textbox | Finish Invert
text | 077f27b4-9625-5c7a-bb3d-ae7828c5dd2e |  | textbox | Grade of Pre-Line %
text | c7ca93f9-a64e-5652-8976-4d9fb3089359 |  | textbox | Product Type
checkpoint-status | 602516e7-d3b5-45a2-95bb-4fc1e78aed9c |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 69feab6e-8517-4a3b-99c2-090e43023732 |  | checkpoint | Local Authority Inspection Passed
text | e1ee7710-8dee-5491-bf02-352c7111dac7 |  | textbox | Name of inspector
date | a499e05f-f797-566e-87be-e9491178ff69 |  | date | Date
checkpoint-status | 24153485-7a0e-4cfd-8051-517bcdd78909 |  | checkpoint | Pipe Laying Completed
text | 7b62a4eb-085b-505d-a4e4-e079e27e9925 |  | textbox | Laid by
checkpoint-status | 967a3d2f-b0f6-4c5a-b6bf-94c8bb7b846d |  | checkpoint | Bedding Sound
checkpoint-status | c805ac38-7acf-4a81-a099-63d3c23a4294 |  | checkpoint | Soil Removed
checkpoint-status | 9397ee79-fb4c-4111-8358-6ffeca66257b |  | checkpoint | Trench Compacted
checkpoint-status | 1676e1ad-6712-4f83-a97d-e0cd6a96c386 |  | checkpoint | Hard Filled
checkpoint-status | f9e63b00-e7b4-46e1-a8ee-c682e7c522ba |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 8ddf82f0-3d7f-46fa-b8e8-7807e2fa1881 |  | checkpoint | Air Test Complete
checkpoint-status | 8170e8a5-1110-46cf-a1c8-db7f6ebd0ff5 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 2233e778-8d82-5fdb-abfb-27c918edd383 |  | textbox | Sign Off By
text | 93dada49-451e-5892-9cd8-78b830f3335c |  | textbox | Acknowledgement of checklist by
text | bf7828af-8345-5c7c-9ec1-76c931e29ee2 |  | textbox | Foreman
checkpoint-group | 8ad7dcdd-6270-4689-9ed2-604e28edfb4e |  | section | Backfill
checkpoint-status | 8aca9bb0-eaed-4090-ba8c-27e522f6e5ac |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 3215a356-3a35-4285-8ed6-7420dceaad24 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | d01b3396-5589-45b9-8b3d-c2e9f74a9f6f |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | dd0f0689-357d-4939-86fb-7b8af3c7f13b |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | d280f589-f6e7-4b1d-b2f2-c90e3f1ffb4a |  | checkpoint | General photos and observations during backfill
checkpoint-status | d6621041-d5be-44f6-a259-332d3972d6b6 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 3530c67a-9fc2-4d8a-bc3e-8fe2c390319b |  | checklist | Wingwall Install Checklist |  |  |  |  | Yes | Wingwall Install Checklist | a67a7b06-47db-4373-b332-41cabbe2eb8d
checkpoint-group | eacfe42a-3ab4-49a1-a67d-7cb6c9955830 |  | section | Wingwall Install
checkpoint-status | 4b9efc9d-aec7-4f83-8a26-cda0e64bd1fb |  | checkpoint | Latest consented drawings
text | 76838bed-2985-5eaa-b321-232485e5081d |  | textbox | Drawing Ref No.
checkpoint-status | 89511ef8-1552-43d2-b1b3-f816e6a3a478 |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | 3bcf0990-7915-4a7f-abe0-b96f76deb4b7 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 9b3fe2ba-68fb-43b8-9a17-d80ee2f290bc |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | a98265c9-1a7f-439d-8976-1c015c61955b |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | 4903aa52-14ea-4e23-9ba4-d321a4087504 |  | checkpoint | Correct wingwall installed to specified height and sitting level
checkpoint-status | c2a3409e-6877-42a4-bd55-85a7f183526a |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | c2ecbec3-8072-41b7-bf24-bb6bcde961c4 |  | checkpoint | Signoff on Completed Work (Council etc)
checkpoint-group | 2661cb15-e8ad-4578-8a67-59b35b09997b |  | section | Backfill
checkpoint-status | 27e351f3-4657-4e7e-8b48-cfe4cfe328cd |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 453989d5-eb2b-4077-83b9-a6fc076d24ca |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 945d94ff-9bc6-437a-b3f5-79bc1f0d4154 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | b6eeef11-2f8e-4392-96f4-adc823a94396 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | add773af-6502-4663-8b2a-d8182d8aecaf |  | checkpoint | General photos and observations during backfill
checkpoint-status | 46b76b36-8670-4adf-a802-1184abf8053d |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | c6c3a6cd-5414-4342-81d9-21425aa88d1c |  | checklist | Connection Checklist |  |  |  |  | Yes | Connection Checklist | a6e3d320-c2a7-4def-8c52-026d285c39f4
checkpoint-status | 3a735062-e378-4dab-b1db-76fb4f26fbe2 |  | checkpoint | Approval given to connect
checkpoint-status | 7d1e9ea6-e679-4db8-b4ce-ed563fa94059 |  | checkpoint | Heights confirmed - Invert level
checkpoint-status | 87549972-bacf-4d9e-8d41-d02dc44153da |  | checkpoint | General comments & photos during installation
checkpoint-status | 22ebf94b-735e-450f-9ce8-a08376ed0e61 |  | checkpoint | Connection completed
checklist-sectioned | ee0eccc1-3682-49d1-a91c-a45cd881d58a |  | checklist | Drainage - Manhole Install Checklist |  |  |  |  | Yes | Drainage - Manhole Install Checklist | b05ed972-f577-43d6-99a3-c07d3051056b
checkpoint-group | 9bbbd937-3bff-4987-a059-e46771201eb6 |  | section | Manhole Install
checkpoint-status | 44a298da-4abb-4c89-8178-a9e960282aa7 |  | checkpoint | Latest consented drawings
text | 9bfacaac-159b-5c7b-9c3c-e2b9e609a461 |  | textbox | Drawing Ref No.
checkpoint-status | 4236fff5-002a-424a-ae20-d4a0714baed9 |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | c6045e39-f612-4d98-933b-1534c30f3414 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 0f3197de-4f94-4c82-9302-69811ab1ba5e |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | 0eb57012-15bc-4c99-9576-1472069e9003 |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | 2ae50fbf-a337-4153-9035-6282806d15ea |  | checkpoint | Correct manhole installed to specified height and sitting level
checkpoint-status | c4301127-3a68-4e59-b4b1-3c5c62250794 |  | checkpoint | Manhole Risers Installed (if applicable)
checkpoint-status | 8901772f-7bd9-4d38-b1ba-aff796f912e0 |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | c477021f-207d-4000-9d0b-316204e7458b |  | checkpoint | Manhole benching completed and acceptable
checkpoint-status | f23d64b0-2035-4f11-9960-ba757028aa13 |  | checkpoint | Concrete Lid Installed and sitting appropriately
checkpoint-status | 6e22d966-7a1a-4e4b-9d1a-6b96f361a602 |  | checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint-status | b3fe4c64-c37b-4c01-80fe-855c8d542189 |  | checkpoint | Signoff on Completed Work (Council etc)
checkpoint-group | 2ecf3b8b-1082-403d-8c30-8f2689627d74 |  | section | Backfill
checkpoint-status | 705a0e3a-18a5-4cd4-a8a0-bfa1350d11eb |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | c1d0f486-ac3e-4ac6-a8f8-8cab8a57a447 |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | d700229a-4b57-4da9-89d7-e33dc795b7cf |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 2f802669-e9c1-428f-a951-e7a46ffca1a8 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 0381f862-7766-442f-b0b2-6538220302b8 |  | checkpoint | General photos and observations during backfill
checkpoint-status | c82ae04c-376d-4240-a29d-9b3090759f46 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | e0b18577-2c37-4216-8394-d1f208c21c66 |  | checklist | Drainage As Built Details |  |  |  |  | Yes | Drainage As Built Details | b6902cce-c4bf-423b-ac3c-0e5cad7d6ccf
checkpoint-status | 5af24c86-cc41-407f-a705-7db9a362aeaa |  | checkpoint | As built Pipework complete and ready for sign off
text | e496ecd3-ecf3-5c16-9182-eeece672d23c |  | textbox | Pipe Diam (mm)
text | 0d5954e5-9c18-5516-bbd2-97e3b2c62990 |  | textbox | Pipe Length from MH Centres(mm)
text | 3b9d8481-b674-57a4-b28d-af92b0d8dd44 |  | textbox | Pipe Type
text | 0d97fd30-91ea-5ecc-b0f6-b28d9ca5eafb |  | textbox | Pipe Supplier
checklist-sectioned | 6d975853-70b1-465f-8555-1ce0730d33ab |  | checklist | Services Trench Checklist |  |  |  |  | Yes | Services Trench Checklist | b7883d7d-4bcd-46a9-96fc-4abe49121098
checkpoint-group | c5a52b7b-d20d-402f-a0e4-5ed285cbbc1d |  | section | Trench Excavation
checkpoint-status | 7bb9c7c8-3987-4538-84b3-20fb869bd896 |  | checkpoint | Latest consented drawings
text | 70e01a90-e1b5-540e-a2c9-07e3170d4a56 |  | textbox | Drawing Ref No.
text | aa86c349-6ce6-5b3d-8ced-9d048d2efbb9 |  | textbox | Trench type
checkpoint-status | 912699bb-0fc2-40e9-a560-ebc4eb76cb6f |  | checkpoint | Setout completed checked and accurate
checkpoint-status | 9ff9327b-3b75-4366-8579-c28388f8d341 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 8c95f45b-ef48-4088-92bb-05ad5099cc2d |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | a18ab204-b9e3-4b56-96e4-2cad847418bd |  | checkpoint | Bedding depth and material correct
checkpoint-status | 771d31dd-c655-4eeb-9e5a-88d56d1eee97 |  | checkpoint | Services laid as per detaill - attach relevant cross section
checkpoint-status | 07f9de2b-adea-4df9-8bf5-a24269eb7bcf |  | checkpoint | Bedding Sound
checkpoint-status | 8b08df7d-a5ad-4439-9023-ca87d85ac326 |  | checkpoint | Soil Removed
checkpoint-status | 317f09ce-86f1-4489-a052-60eded1c9a62 |  | checkpoint | Trench Compacted
checkpoint-status | b4ede2e5-620e-41b6-a792-d1f6e8b6f064 |  | checkpoint | Hard Filled
checkpoint-status | 2bde1dc6-24c9-4fce-8efa-cde96bd223b4 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | f24a07a3-ba03-5f10-9305-a04c88da2215 |  | textbox | Sign Off By
text | e6eaf715-52d6-5cdf-857f-94fbbc764730 |  | textbox | Acknowledgement of checklist by
text | 1f15827b-89d5-5d0b-a44c-0ec46c8cf27a |  | textbox | Foreman
checkpoint-group | 381060cf-398d-4c59-b4bb-6768d2821f2b |  | section | Backfill
checkpoint-status | 237c9146-7d5c-4bf5-a06b-c22de83ed376 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 9503d545-98e9-4f2a-a6e9-188bd9f2f93e |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 2330f11c-b2f7-47a0-87f2-fbd15bb73daa |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 55f7dd16-a116-4239-a263-a9c8ca2935a9 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | b0cb2064-65ff-4c4f-bf4f-2ccdf501427b |  | checkpoint | General photos and observations during backfill
checkpoint-status | 71e5d4e5-49d2-43dc-b13a-cea0eafe8438 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | 27ce3610-9ac2-41a2-8a18-3a8ec7efde7b |  | checklist | Gasmain- Pipeline Installation Checklist |  |  |  |  | Yes | Gasmain- Pipeline Installation Checklist | c083fdb1-334d-4d30-b26e-cd08428fe6fd
checkpoint-group | 7eea14a2-4b3c-4686-9de7-a78e0c62ed2a |  | section | Pipe Laying
checkpoint-status | 7ebc1cea-ea0e-4595-9749-b188ff9ed7b2 |  | checkpoint | Latest consented drawings
text | 8a2d6f4b-f07f-50cd-a8a7-ef023cf567e7 |  | textbox | Drawing Ref No.
checkpoint-status | f28bc2e9-a898-4237-a1aa-9362fedbe55c |  | checkpoint | Setout completed checked and accurate
checkpoint-status | 5fab6a53-d4ce-4730-a58e-d6531bb0001c |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 0cf80fb1-fa80-49ca-9d5f-7dc8fee7b3b1 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | d046ade8-f3e6-4cd3-8be4-c21e48ec3120 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 5f98a1d2-0e8f-4386-88e7-216f421b6560 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 9b619e58-5258-5809-991a-b2cc88af40f8 |  | textbox | Start Invert
text | b6023286-575d-569a-b225-18b0e5f1bc54 |  | textbox | Finish Invert
text | 50066fef-e45f-5be3-b401-ea807d75f3a7 |  | textbox | Grade of Pre-Line %
text | fcc12539-2c97-53be-8498-af2d411d56fa |  | textbox | Product Type
checkpoint-status | 388c5ba5-2d13-46d5-877f-038a241a13bf |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 6186c30f-e120-4ab2-b682-f81f895082cf |  | checkpoint | Local Authority Inspection Passed
text | 4d5609e7-71b2-54c4-8714-fce14bb4d4d5 |  | textbox | Name of inspector
date | a8a1c114-26c1-57fe-a0c5-7bdc60176d28 |  | date | Date
checkpoint-status | a87c9218-b5b1-4402-b872-3991e10048b1 |  | checkpoint | Pipe Laying Completed
text | 39b92083-7abc-5ee8-b289-c5d7b3d2f79a |  | textbox | Laid by
checkpoint-status | 25bc7536-c492-4934-a1d5-7522a137079b |  | checkpoint | Bedding Sound
checkpoint-status | 8877dad5-ff74-44bd-abdb-bedb63a96cd1 |  | checkpoint | Soil Removed
checkpoint-status | 8e091fc6-665a-4b8f-893a-6000f908159e |  | checkpoint | Trench Compacted
checkpoint-status | 18e8a863-e0e2-452e-b800-2f635654196f |  | checkpoint | Hard Filled
checkpoint-status | 889f8f6f-182a-47e6-8316-c9aa281c014d |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | a6defe7e-a778-4d21-9c68-16dd167def90 |  | checkpoint | Air Test Complete
checkpoint-status | 8687f440-d7c9-4d55-8168-5d14f39a2afe |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 33184110-1475-5300-9bda-f2bd1b200f15 |  | textbox | Sign Off By
text | 32f75367-c1c9-5e79-b509-6ac01aa44edc |  | textbox | Acknowledgement of checklist by
text | 65214274-cc04-55cd-81d1-e8b1f0c49821 |  | textbox | Foreman
checkpoint-group | 626d73bc-add1-48e9-9052-4099381e27ad |  | section | Backfill
checkpoint-status | d1140acc-60ce-4bee-a72a-68393fc4c62b |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | b1ea7132-7695-4a55-9755-fe5961f5008e |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | a84361d7-8c06-4b6f-8af0-8b3dd710d7ca |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | 2b71dd65-8f58-4303-80a7-b234236f0f90 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | dd788878-8ea8-4f1e-a8a5-6198e3af3015 |  | checkpoint | General photos and observations during backfill
checkpoint-status | d2430978-1c15-458f-9fe5-c71dfc5ac479 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | b758e679-66d1-4692-9805-c0c7327ea00c |  | checklist | Pressure Test |  |  |  |  | Yes | Pressure Test | d8307d67-82f1-4a6c-9104-bfa29dd22d2c
checkpoint-status | fe5eb717-1a1d-4607-8094-809324904983 |  | checkpoint | Test Media(Water/Gas/Fire)
text | 885dd6fd-2b8c-5420-8618-b968c92fc644 |  | textbox | Working Pressure
checkpoint-status | 2b381c8c-90c5-4b5c-bc6d-375da9dc4c4a |  | checkpoint | Test Pressure(PSI/Kpa)
text | 492a4322-875c-53c3-bdea-5a4b5903e4e3 |  | textbox | Duration of Test (mins)
checkpoint-status | d5ad2d47-e193-450f-b9e9-519a95affdc3 |  | checkpoint | The above systems have been installed and pressure tested
text | 886bcf17-d094-5274-8a34-9e2e87e915f6 |  | textbox | Witness Name & Company
text | 750acc2b-f703-5a5f-86e6-2ba07b92bdb7 |  | textbox | Bassett Representative
checklist-sectioned | 63a20584-8780-479f-ac03-c21cd83d1761 |  | checklist | Drainage - Soakpit Install Checklist |  |  |  |  | Yes | Drainage - Soakpit Install Checklist | e3b13ccb-06f0-44c8-bb91-9ed7bcb3c92e
checkpoint-group | ffba0fce-1e87-443e-84de-36a15035f9fb |  | section | Soakpit Install
checkpoint-status | db727cb6-74fd-4982-a20e-4a9d49b90451 |  | checkpoint | Latest consented drawings
text | c3317e51-5340-5629-b532-4b929fd683d9 |  | textbox | Drawing Ref No.
checkpoint-status | c7c1e6ca-0aa9-45ca-ae44-f52b11615248 |  | checkpoint | Setout Completed checked and accurate
checkpoint-status | e66fcc7b-ce75-403b-b734-0f1e981914ae |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 941a9c44-6260-4135-a79a-171a7c3a076f |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status | e5d7856d-e723-40b9-9c7c-4dd60efda0de |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status | aa4ffd2b-9cce-45c7-a007-9d9d3a889795 |  | checkpoint | Correct Soakpit installed to specified height and sitting level
checkpoint-status | 34ed79c2-51f2-41b0-8c7d-707a4472065a |  | checkpoint | Risers Installed (if applicable)
checkpoint-status | d4813821-e51d-4537-8278-8bef6a8bfbc3 |  | checkpoint | Joints & connections correctly sealed as specified
checkpoint-status | 908437b8-5111-43ba-b1a0-dea6f1ec3041 |  | checkpoint | Soakpit benching completed and acceptable
checkpoint-status | 7dff9e22-46aa-4598-98cf-87ff89670be5 |  | checkpoint | Concrete Lid Installed and sitting appropriately
checkpoint-status | 920f1501-075f-4ec2-a2ad-5151fc19e2f7 |  | checkpoint | Cast Iron Lid Installed and sitting flush
checkpoint-status | 3511c752-109c-4ca5-8b09-26c6cb7650ba |  | checkpoint | Signoff on Completed Work (Council etc)
checkpoint-group | bd6fe07b-992c-4349-8435-d8cd2766531c |  | section | Backfill
checkpoint-status | 703d9d9a-9a4d-408f-a6c0-f9ae40b5e08c |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 946595d8-eb21-415f-99db-5ce5a55f5b2b |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 3bece902-9f31-4dbe-a81f-cbea05ba5048 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | f507f3b8-62f1-4eb4-ada2-dba0e99a480b |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
checkpoint-status | 4e402f1b-2f42-497f-9500-bb027bd2a73f |  | checkpoint | General photos and observations during backfill
checkpoint-status | d2246ea0-1593-4b63-9313-877bf5a83229 |  | checkpoint | Backfill completed correctly and heights checked/ correct