## Structure
Project Name | National Storage Mt Wellington(#77027) | Checklists
Drainage Installation
Stormwater | Standard Double Cesspit 1A(SWDCP 1A) to Stormwater Soakpit 1 (SWSP1) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
| Stormwater Soakpit 1(SWSP1) to Stormwater private connection2(SWPC2) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
| Stormwater private connection2(SWPC2) to Stormwater private connection1(SWPC1) | Stormwater- Pipeline Installation Checklist
| Stormwater private connection1(SWPC1) to Proposed Field Catchpit (SWFCP 1B) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
| Stormwater private connection1(SWPC1) to Stormwater Soakpit 2(SWSP2) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 2(SWSP2) to Catchpit standard single 2A (SWCP 2A) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
Cesspit Installation
| Stormwater Soakpit 3(SWSP3) to Proposed Field Catchpit3A (SWFCP 3A) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 3(SWSP3) to Stormwater Soakpit 4(SWSP4) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
| Stormwater Soakpit5 (SWSP5) to Stormwater Soakpit 6 (SWSP6) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 6 (SWSP6) to Proposed Field Catchpit6A (SWDFCP 6A) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 6 (SWSP6) to Proposed Field Catchpit6B (SWDFCP 6B) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 6 (SWSP6) to Stormwater Soakpit 7(SWSP7) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 7(SWSP7) to Proposed Field Catchpit7A (SWDFCP 7A) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
Drainage - Soakpit Install Checklist
| Proposed Field Catchpit8A(SWFCP 8A) to Stormwater Soakpit 8(SWSP 8) | Stormwater- Pipeline Installation Checklist
Cesspit Installation
Drainage - Soakpit Install Checklist
| Stormwater Soakpit 8(SWSP 8) to Stormwater Soakpit 9 (SWSP9) | Stormwater- Pipeline Installation Checklist
Drainage - Soakpit Install Checklist
Wastewater | WWMH to SS Connection | Wastewater- Pipeline Installation Checklist
Drainage - Manhole Install Checklist

## Checklist
name | value
Cesspit Installation
Setout & position checked and confirmed
Cesspit installed as per standards
Setout & position checked and confirmed
All cut pipes epoxied
Confirm Levels Correct
Cesspit cleaned of all Debris
Concrete Apron installed (if required)
Frame & Grate alignment checked
Minimum sump depth checked
Captive Grates installed (if required)
Cesspit complete & ready for sign off
name | value
Drainage Installation
Setout and position checked and confirmed
Trench width and lid level (attach photos)
Gap 10 & 65 measured and ordered
Stockpiles & cart out confirmed
Pipework installed as per specification
Pipe test booked and test ready
CCTV complete
As built plans complete
Clegg test on hardfill (results recorded)
RON & CAR signed off
Pipework complete & ready for sign off
name | value
Pressure Test
Test Media(Water/Gas/Fire)
Working Pressure
Test Pressure(PSI/Kpa)
Duration of Test (mins)
The above systems have been installed and pressure tested
Witness Name & Company
Bassett Representative
name | value
Drainage As Built Details
As built Pipework complete and ready for sign off
Pipe Diam (mm)
Pipe Length from MH Centres(mm)
Pipe Type
Pipe Supplier
name | value
Below Ground Services Checklist
Pre-Installation
Pre-Installation checks complete
Drawing Red No:
Starting Point:
Finishing Point Established
Grade of Pre-Line%
Level Obtained
Installation
Pipe Work Tested
Air
Water
Visual
Backfill Material
Local Authority Inspection Passed
Name of Inspector:
Stormwater- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Connections to manholes complete and approved
All Downpipes have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
All Cess Pitts have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Sewer- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Manhole Install Checklist
Manhole Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct manhole installed to specified height and sitting level
Manhole Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Manhole benching completed and acceptable
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Stormfilter Install Checklist
Stormfilter Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct manhole installed to specified height and sitting level
Manhole Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Manhole benching completed and acceptable
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Tank Install Checklist
Tank Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct tank installed to specified height and sitting level
Joints & connections correctly sealed as specified
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Wingwall Install Checklist
Wingwall Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct wingwall installed to specified height and sitting level
Joints & connections correctly sealed as specified
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Services Trench Checklist
Trench Excavation
Latest consented drawings
Drawing Ref No.
Trench type
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Services laid as per detaill - attach relevant cross section
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Connection Checklist
Approval given to connect
Heights confirmed - Invert level
General comments & photos during installation
Connection completed
Watermain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Gasmain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Firemain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Civil Install Checklist
Foundation Set out
Confirm Levels Correct
As Built
As built Pipework complete and ready for sign off
Drainage - Soakpit Install Checklist
Soakpit Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct Soakpit installed to specified height and sitting level
Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Soakpit benching completed and acceptable
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Soakpit Install Checklist
Soakpit Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct manhole installed to specified height and sitting level
Manhole Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Manhole benching completed and acceptable
Soakpit steel cage installation
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct

## Weekly Checklist
name | value
Cesspit Installation
Setout & position checked and confirmed
Cesspit installed as per standards
All inlets & outlets sealed & epoxied
All cut pipes epoxied
Grate & Lentil set to Kerb line
Cesspit cleaned of all Debris
Concrete Apron installed (if required)
Frame & Grate alignment checked
Minimum sump depth checked
Captive Grates installed (if required)
Cesspit complete & ready for sign off
name | value
Drainage Installation
Setout and position checked and confirmed
Trench width and lid level (attach photos)
Gap 10 & 65 measured and ordered
Stockpiles & cart out confirmed
Pipework installed as per specification
Pipe test booked and test ready
CCTV complete
As built plans complete
Clegg test on hardfill (results recorded)
RON & CAR signed off
Pipework complete & ready for sign off
name | value
Pressure Test
Test Media(Water/Gas)
Working Pressure
Test Pressure(PSI/Kpa)
Duration of Test (mins)
The above systems have been installed and pressure tested
Witness Name & Company
Bassett Representative
name | value
Drainage As Built Details
As built Pipework complete and ready for sign off
Pipe Diam (mm)
Pipe Length from MH Centres(mm)
Pipe Type
Pipe Supplier
name | value
Below Ground Services Checklist
Pre-Installation
Pre-Installation checks complete
Drawing Red No:
Starting Point:
Finishing Point Established
Grade of Pre-Line%
Level Obtained
Installation
Pipe Work Tested
Air
Water
Visual
Backfill Material
Local Authority Inspection Passed
Name of Inspector:
Stormwater- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Connections to manholes complete and approved
All Downpipes have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
All Cess Pitts have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Sewer- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Manhole Install Checklist
Manhole Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct manhole installed to specified height and sitting level
Manhole Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Manhole benching completed and acceptable
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Services Trench Checklist
Trench Excavation
Latest consented drawings
Drawing Ref No.
Trench type
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Services laid as per detaill - attach relevant cross section
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Connection Checklist
Approval given to connect
Heights confirmed - Invert level
General comments & photos during installation
Connection completed