## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | MSR checklist |  |  |  |  | Yes | MSR checklist | 000bb50c-bb11-484e-a92c-cbbd95eaf7e7
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Purlins installed and QA / handover received from main contractor
checkpoint-status |  |  | checkpoint | visual inspection by SWP
checkpoint-group |  |  | section | Liner deck
checkpoint-status |  |  | checkpoint | Liner deck fixed down in every purlin and every pan
checkpoint-status |  |  | checkpoint | Correct fixing installed
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | VCL installed and covered all surface
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-group |  |  | section | Acoustic board install
checkpoint-status |  |  | checkpoint | VCL clean, no ponding water, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been cheeked for damages
checkpoint-status |  |  | checkpoint | All holes/penetrations patched
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Boards tightly butted all areas covered
checkpoint-status |  |  | checkpoint | Correct insulation installed as per spec
checkpoint-group |  |  | section | Underlay installed
checkpoint-status |  |  | checkpoint | Correct underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
checkpoint-status |  |  | checkpoint | All areas covered
checkpoint-status |  |  | checkpoint | Underlay installed as per specifications
checkpoint-status |  |  | checkpoint | Joints taped together as per drawings and specifications
checkpoint-group |  |  | section | Metal roof installation
checkpoint-status |  |  | checkpoint | Drip edge installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Laid straight and perpendicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang as per drawings and specifications
checkpoint-status |  |  | checkpoint | Top end turned up
checkpoint-status |  |  | checkpoint | Bottom ends turned down
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/specs/fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Sealant installed with 2 continues beads
checkpoint-status |  |  | checkpoint | Clean excess sealant
checkpoint-status |  |  | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
checkpoint-status |  |  | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
checkpoint-status |  |  | checkpoint | Fixings installed as per drawings and specifications
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
holdpoint |  |  | signoff | Client/main contractor sign off
checklist-flat |  |  | checklist | Defect - |  |  |  |  | Yes | Add Defect Checklist | 10d1bd2c-6b20-47b4-9690-10844fd6b998
checkpoint-status |  |  | checkpoint | Defect details recorded
text | 0322025b-f507-52b9-85c7-77e2184ef552 |  | textbox | Explanation of defect:
text | 511dbd3c-65ee-5fab-a9f0-c215a9516c04 |  | textbox | Area:
text | 50a37124-f973-544b-8bd5-895ca17ba3ea |  | textbox | Party responsible for damages:
text | a1c7baa7-df64-5969-9ddb-0c9813bace3a |  | textbox | Efforts required for repair:
text | 94b4c812-e0b9-58ca-80ee-6ea973aff9fc |  | textbox | Man hours required for repair:
holdpoint |  |  | signoff | Request Approval from Main Contractor
checkpoint-status |  |  | checkpoint | Defect Fixed
holdpoint |  |  | signoff | Request Defect signoff
checklist-sectioned |  |  | checklist | MSR Cladding Checklist |  |  |  |  | Yes | QA - MSR Cladding Checklist | 125d69c1-7474-4ccb-a338-a10f7d323730
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean and ready
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes / penetrations patched and watertight
checkpoint-group |  |  | section | Brackets and Rails
checkpoint-status |  |  | checkpoint | Z brackets installed to fixing plan
checkpoint-status |  |  | checkpoint | Rhom rail installed to fixing plan
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL no damage
checkpoint-status |  |  | checkpoint | Insulation installed with no gaps
checkpoint-group |  |  | section | Cladding
checkpoint-status |  |  | checkpoint | Covertek installed with 150mm laps
checkpoint-status |  |  | checkpoint | Starter flashings installed
checkpoint-status |  |  | checkpoint | Soaker flashings installed
checkpoint-status |  |  | checkpoint | Sheets laid straight
checkpoint-status |  |  | checkpoint | Closure foam installed
checkpoint-status |  |  | checkpoint | Correct screw pattern / fixings used
checkpoint-group |  |  | section | Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to spec and drawings
checkpoint-status |  |  | checkpoint | Fixings according to spec and details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite to Plywood Checklist |  |  |  |  | Yes | QA - Fibertite to Plywood Checklist | 1839a21b-cbdd-47cd-963b-fec56441cdfa
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Fibertite Membrane
checkpoint-status |  |  | checkpoint | Correct Glue used per spec
checkpoint-status |  |  | checkpoint | Fibertite fully glued to plywood
checkpoint-status |  |  | checkpoint | Broom / roll fibertite into glue
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully closed & QA'd with hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to details
checkpoint-status |  |  | checkpoint | Welding of Fibertite to flashings fully finished and QA'd with hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | MSR Checklist |  |  |  |  | Yes | QA - MSR Checklist | 1aa7500e-7369-4158-8f67-6542d09a786d
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down and secure
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Acoustic Board
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed with no gaps
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Topdeck Install
checkpoint-status |  |  | checkpoint | Covertek Installed with 150mm overlap
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Lay sheet with minimum 75mm gutter overhang
checkpoint-status |  |  | checkpoint | Top end of sheet turned up
checkpoint-status |  |  | checkpoint | Fixing back into purlin
checkpoint-status |  |  | checkpoint | Closure foam to gutter end
checkpoint-status |  |  | checkpoint | Profile Washers over 12m
checkpoint-status |  |  | checkpoint | Sheets straight & perpendicular to gutter
checkpoint-status |  |  | checkpoint | Screw pattern as per fixing plan
checkpoint-group |  |  | section | Roof flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specification & drawings
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch On Warmroof to Concrete Checklist |  |  |  |  | Yes | QA - Torch On Warmroof to Concrete Checklist | 30afbf82-3a8a-43d4-b86c-d23ac172a095
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground down/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ELD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Metal Flashing Install Checklist |  |  |  |  | Yes | QA - Metal Flashing Install Checklist | 37f716fa-2b32-4655-8656-220ae4bccdd5
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Flashing Install
checkpoint-status |  |  | checkpoint | Installed with a minimum upstand of 150mm or according to drawings
checkpoint-status |  |  | checkpoint | Expansion joint installed if needed (i.e. with runs longer than 12m for coloursteel or 8m for Ali.)
checkpoint-status |  |  | checkpoint | Fixings according to Code as a minimum (or plans if more are required) in a straight line
checkpoint-status |  |  | checkpoint | Laid in a straight and tidy manner
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly and facing away from waterflow
checkpoint-status |  |  | checkpoint | All visible ends & junctions cut and folded straight and tidy
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch On to Concrete Checklist |  |  |  |  | Yes | QA - Torch On to Concrete Checklist | 391f49e0-48f8-4438-8ad8-02902f3f5b11
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertherm Checklist |  |  |  |  | Yes | QA - Fibertherm Checklist | 39311d8d-eb7e-41d0-9cc9-a3cbd54449aa
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation
checkpoint-status |  |  | checkpoint | End openings to have closure foam installed
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | VCL tape to be installed to all sheet laps
checkpoint-status |  |  | checkpoint | VCL tape to all upstands
checkpoint-group |  |  | section | Post and Rail install
checkpoint-status |  |  | checkpoint | Post installed at correct fixing centers
checkpoint-status |  |  | checkpoint | Thermal break pad under post foot
checkpoint-status |  |  | checkpoint | Rail installed to posts
checkpoint-status |  |  | checkpoint | Gutter line colsure/drip edge flashing installed
checkpoint-group |  |  | section | Insulation install
checkpoint-status |  |  | checkpoint | Specified Insulation installed
checkpoint-status |  |  | checkpoint | No Gaps
checkpoint-group |  |  | section | Top Deck install
checkpoint-status |  |  | checkpoint | Lay sheets straight
checkpoint-status |  |  | checkpoint | Hang over into gutter min 75mm
checkpoint-status |  |  | checkpoint | Top end of sheets turned up
checkpoint-status |  |  | checkpoint | Bottom end of sheets turned down
checkpoint-status |  |  | checkpoint | Fixing back to rail
checkpoint-status |  |  | checkpoint | Profile washers
checkpoint-status |  |  | checkpoint | Screwed off as per fixing plan
checkpoint-group |  |  | section | Flashing install
checkpoint-status |  |  | checkpoint | Installed correctly, accoriding to spec's & drawings
checkpoint-status |  |  | checkpoint | Fixings according to specs & details
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Soffit Checklist |  |  |  |  | Yes | QA - Soffit Checklist | 39ae95a7-3d81-4c02-b533-0d2a8fc90acf
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Substrate ready (check plans) with proper purlin spacing
checkpoint-status |  |  | checkpoint | Design/Spec/Approvals complete
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Flashings installed according to plans
checkpoint-status |  |  | checkpoint | All sealant work complete
checkpoint-status |  |  | checkpoint | Install soffit lining according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Screw pattern according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Finish flashings complete
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Cladding Install Complete
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Plywood Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Plywood Checklist | 41186768-0696-478f-b1cb-d73e6b87c7a1
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings poping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Vapor Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, and free of debris
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | Insulation boards installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer if no Securock
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Torch On to Plywood Checklist |  |  |  |  | Yes | QA - Torch On to Plywood Checklist | 41c60514-0782-4bb4-aa53-c0bcd44fe26d
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | No Screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Joints flush and even
checkpoint-group |  |  | section | Prime of Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and free from debris
checkpoint-status |  |  | checkpoint | Primer installed
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Install clamps/rings/baskets
checkpoint-status |  |  | checkpoint | Flood/ILD test
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Carpark MMA Checklist |  |  |  |  | Yes | QA - Carpark MMA Checklist | 4b72691e-0aea-4238-9490-814a55f35e3e
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | SSSP onsite
checkpoint-status |  |  | checkpoint | Photos of any existing linemarkings installed
checkpoint-status |  |  | checkpoint | Fencing demarcation installed
checkpoint-status |  |  | checkpoint | Site signage installed
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Removal of coatings
checkpoint-status |  |  | checkpoint | Grind of substrate
checkpoint-status |  |  | checkpoint | Shotblast of substrate to achieve suitable profile
checkpoint-group |  |  | section | Pre-start of membrane install
checkpoint-status |  |  | checkpoint | Substrate dry
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Prime of substrate
checkpoint-status |  |  | checkpoint | Stripe out cracks
checkpoint-status |  |  | checkpoint | Map out areas based on coverage rates for install
checkpoint-status |  |  | checkpoint | Membrane layer installed
checkpoint-status |  |  | checkpoint | Wear layer installed and broadcast
checkpoint-status |  |  | checkpoint | Excess broadcast swept and removed
checkpoint-status |  |  | checkpoint | 1st Top coat
checkpoint-status |  |  | checkpoint | 2nd top coat
checkpoint-status |  |  | checkpoint | Linemarking installed
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checkpoint-status |  |  | checkpoint | Site cleared and broken down
checklist-flat |  |  | checklist | Dayworks - |  |  |  |  | Yes | Add Dayworks Checklist | 4e156efc-1b13-4ae9-a3b4-d1e36399cb81
checkpoint-status |  |  | checkpoint | Day Work Details
text | e21a1316-3644-56c3-8154-0db7ce6ae395 |  | textbox | NTSC / SI #:
text | 3c88379a-f04f-5e87-a3d7-32fb2e4a2edc |  | textbox | Labours (HR)
text | 8dc8739e-b613-5e80-8fe4-94c5c8ac41f2 |  | textbox | Work Description:
text | 96153263-b692-5bdc-803a-e436e395ee3d |  | textbox | Materials:
text | f2ff5bdc-ed1b-59b3-abb4-6da6359e2a7c |  | textbox | SWP Representative. Prepared By:
text | af6919e0-c28a-59ee-86d6-7d98d270badc |  | textbox | Client Representative. Confirmed By:
holdpoint |  |  | signoff | Request Signature Signoff
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | SYS - PT - Job Details | 5bf53c62-de71-42c6-8b7b-c97860632083
checkpoint-status |  |  | checkpoint | Site Info
text | 9bb707b8-cf60-58cf-9f1e-ed72a6bc59ad |  | textbox | Site Address
text | 47e33888-a733-543c-84dc-4b6c0d9d6527 |  | textbox | Main Contractor Details
text | 62969f3d-7ca7-5b24-93fc-6cd27bb33193 |  | textbox | Project Managers Details
text | e6cc1352-b2ec-53a1-8b7f-fed211ecaa72 |  | textbox | Site Manager Details
checkpoint-status |  |  | checkpoint | Latest Drawings
checkpoint-status |  |  | checkpoint | Scope of Works Attached
checkpoint-status |  |  | checkpoint | Additional Pre Start Docs
checkpoint-status |  |  | checkpoint | Fixing Plan Attached
checklist-sectioned |  |  | checklist | QA - Fibertite Warm Roof Over Concrete Fully Adhered Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Concrete Fully Adhered Checklist | 66e1c2d4-b984-4dbf-bdfc-18b94b3ce9a9
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Installation of SA primer
checkpoint-status |  |  | checkpoint | Install VCL over primer sheets lapped minimum 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and watertight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | Install SA primer to top surface of VCL
checkpoint-status |  |  | checkpoint | Install Board bond 600u in specified pattern
checkpoint-status |  |  | checkpoint | Insulation boards installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-group |  |  | section | ILD install
checkpoint-status |  |  | checkpoint | SS mesh laid flat over all surfaces
checkpoint-status |  |  | checkpoint | Testing wire installed
checkpoint-group |  |  | section | Roofboard
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Install board bond 600u in specified pattern
checkpoint-status |  |  | checkpoint | Roof board installed in brick pattern where possible
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite warm roof fully adhered over CLT |  |  |  |  | Yes | Fibertite warm roof fully adhered over CLT | 77c2d777-3ca4-404f-ba3a-a664bd826b73
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge Protection installed
checkpoint-status |  |  | checkpoint | Substrate completed and handed over by others &/or QA from proceeding trades supplied by Main contractor
checkpoint-group |  |  | section | CLT
checkpoint-status |  |  | checkpoint | Handed over by Main contractor
checkpoint-group |  |  | section | Vapor Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, and free of debris
checkpoint-status |  |  | checkpoint | SA Primer installed over CLT
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 100mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Tapered EPS Installed
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | SA Primer installed over VCL
checkpoint-status |  |  | checkpoint | 600U Board bond adhesive installed as per suppliers recommendations
checkpoint-status |  |  | checkpoint | Tapered EPS boards installed into 600U Adhesive
checkpoint-group |  |  | section | PIR board installed
checkpoint-status |  |  | checkpoint | EPS Surface is dry prior to install
checkpoint-status |  |  | checkpoint | 600U Board bond adhesive installed as per suppliers recommendations
checkpoint-status |  |  | checkpoint | PIR Board installed into 600U Adhesive
checkpoint-group |  |  | section | HDP Board
checkpoint-status |  |  | checkpoint | PIR Board dry prior to install
checkpoint-status |  |  | checkpoint | 600U Board bond adhesive installed as per suppliers recommendations
checkpoint-status |  |  | checkpoint | HDP Board installed into 600U Adhesive
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | HDP board clean and dry prior to install
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Sign off
checkpoint-status |  |  | checkpoint | Area left Clean and Tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per spec
holdpoint |  |  | signoff | Client / Main contractor sign off
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Plywood Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Plywood Checklist | 792309aa-538c-47a2-905d-147b88f9dbc2
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Plywood
checkpoint-status |  |  | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
checkpoint-status |  |  | checkpoint | No screws/nails/fixings popping up
checkpoint-status |  |  | checkpoint | Plywood joints flush and even
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD checked
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Weather Monitoring |  |  |  |  | Yes | Weather Monitoring | 7c183c88-25be-465f-ba0f-cd756bbfa3db
checkpoint-group |  |  | section | Current Weather
checkpoint-status |  |  | checkpoint | Todays date & Time
checkpoint-status |  |  | checkpoint | Wind / weather conditions
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checkpoint-group |  |  | section | Weather Forecast
checkpoint-status |  |  | checkpoint | What is the weather forecast this week
checkpoint-status |  |  | checkpoint | Record any delays
checkpoint-status |  |  | checkpoint | area / gridlines
checkpoint-status |  |  | checkpoint | Comments / issues / observations
checklist-sectioned |  |  | checklist | Torch on Warmroof Over Metal Deck Checklist |  |  |  |  | Yes | QA - Torch on Warmroof Over Metal Deck Checklist | 7e4faebc-c426-4bb7-a4c8-ca0c2177cccd
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stitched together at 300mm centres
checkpoint-status |  |  | checkpoint | No sharp edges protruding
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with recessed flat plates
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Prime of Securrock
checkpoint-group |  |  | section | Base Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Bleed of bitumen on overlap should be up to 10mm
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Check of all welds at the end of the day
checkpoint-group |  |  | section | Cap Sheet
checkpoint-status |  |  | checkpoint | Install from low to high
checkpoint-status |  |  | checkpoint | Side laps a minimum of 80mm and end laps 150mm
checkpoint-status |  |  | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
checkpoint-status |  |  | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
checkpoint-status |  |  | checkpoint | Flood test / ILD tested
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Site Visit date: |  |  |  |  | Yes | Supplier Site Visit | 83ac6e66-ffcf-4a92-aa5d-991678a13c39
checkpoint-status |  |  | checkpoint | Site Details
text | 3664f5fe-074c-5f35-8774-8e631184d977 |  | textbox | Job Name
text | 393757b5-5afc-5284-bd4d-ad71ee6e48f0 |  | textbox | Who is in attendance
text | 05ccfbd2-c751-5822-b036-1ecba2ae6eb2 |  | textbox | Area/Gridlines/Detail
checkpoint-status |  |  | checkpoint | Photos
text | 2c1a0c7b-805d-5c6e-9f5b-413c23cd9b12 |  | textbox | Inspection Notes
holdpoint |  |  | signoff | Signoff Required
checklist-flat |  |  | checklist | Flood Test Area: |  |  |  |  | Yes | Add Flood Testing Checklist | 8623022f-da90-4483-b18b-ba6bc016ee15
checkpoint-status |  |  | checkpoint | Is area fully finished, QA’d and ready to be tested
checkpoint-status |  |  | checkpoint | Flood test details
text | 95a74f2e-1fb6-530e-80cd-eb8c764f19a4 |  | textbox | Date:
text | 3f47d458-27fd-5bc3-9ac2-e51774eeaa7d |  | textbox | Area tested:
text | 8816e5bd-b79c-5efc-8782-366bb8704c1e |  | textbox | Duration:
button | b497ecb4-87c1-53cd-b77e-3553aed37ff9 |  | button | Have you checked regularly for leaks | Yes, No, N/A
button | 170dbd09-45ec-5ba0-99dc-d0aba011af11 |  | button | Is there rain in the forecast | Yes, No, N/A
button | f7d8d101-6769-5385-97c2-df59fe4c7590 |  | button | Have you eft some outlets/scuppers so that the building doesn't flood | Yes, No, N/A
button | b7208d67-3bc9-59e4-babc-e8eb916b9f9c |  | button | Have all leaks been repaired | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Flood test complete
button | c95a6585-f5a3-50ca-afd2-d36a2d6233a6 |  | button | Have the plugs been removed from the drains | Yes, No, N/A
button | 9a761b5f-6317-5bec-b918-f7910124fd80 |  | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
holdpoint |  |  | signoff | Sign Off
checklist-sectioned |  |  | checklist | Fibertite Overlay Install Checklist |  |  |  |  | Yes | QA - Fibertite Overlay Install Checklist | 89a0576e-4abb-4daa-9cb1-36e9f21775f0
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
checkpoint-status |  |  | checkpoint | Cut back existing roof edge at gutter
checkpoint-status |  |  | checkpoint | Remove ridge as we go
checkpoint-group |  |  | section | VCL-Vapour Control Layer
checkpoint-status |  |  | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
checkpoint-status |  |  | checkpoint | All areas covered and lapped a minimum of 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and made watertight
checkpoint-group |  |  | section | Roof Pan Infills
checkpoint-status |  |  | checkpoint | Surface is dry before installing Poly
checkpoint-status |  |  | checkpoint | Infills to be a minimum 5mm above ridges on roof
checkpoint-status |  |  | checkpoint | Every pan has been infilled
checkpoint-group |  |  | section | Roofboard
checkpoint-status |  |  | checkpoint | Substrate/surface dry & clean prior to being installed
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct screws with load washer
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-status |  |  | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Correct Glue being used for substrate
checkpoint-status |  |  | checkpoint | Fibertite fully glued to substrate
checkpoint-status |  |  | checkpoint | Broom/rolling of fibertite
checkpoint-status |  |  | checkpoint | Wipe/clean laps with acetone prior to welding
checkpoint-status |  |  | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly
checkpoint-status |  |  | checkpoint | Fixed down according to specification
checkpoint-status |  |  | checkpoint | Cleaned down with acetone prior to welding
checkpoint-status |  |  | checkpoint | Fibertite fully welded to flashing and QA'd with hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | New Files Folder: |  |  |  |  | Yes | Add Files Folder | 8b97e5cc-59b6-4be7-a1de-2e8259d1079c
checklist-sectioned |  |  | checklist | Metal Roof Installation Checklist |  |  |  |  | Yes | QA - Metal Roof Installation Checklist | 9c52dcca-db2f-41c8-8d09-97abe1a6cbf8
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Safety Mesh Installation
checkpoint-status |  |  | checkpoint | Laid perpindicular to the purlins.
checkpoint-status |  |  | checkpoint | Fully secured to Purlins/Timber.
checkpoint-status |  |  | checkpoint | No protruding bits or loose ends.
checkpoint-group |  |  | section | Covertek Roofing Paper Installation
checkpoint-status |  |  | checkpoint | Laid either perpindicular or parallel with purlins.
checkpoint-status |  |  | checkpoint | Overlapped a minimum 150mm
checkpoint-status |  |  | checkpoint | All areas completely covered.
checkpoint-status |  |  | checkpoint | Laid tight to timeber/purlins.
checkpoint-status |  |  | checkpoint | Secured so it will not blow away if roof not being installed immediately.
checkpoint-group |  |  | section | Metal Roof Installation
checkpoint-status |  |  | checkpoint | Drip edge installed
checkpoint-status |  |  | checkpoint | Laid straight & perpindicular to gutter/purlins
checkpoint-status |  |  | checkpoint | Gutter overhang 75mm minimum
checkpoint-status |  |  | checkpoint | Top ends of sheets turned up.
checkpoint-status |  |  | checkpoint | Fixings back into purlins and laid in a straight line as per Code of Practice.
checkpoint-status |  |  | checkpoint | Closure foam to gutter ends.
checkpoint-group |  |  | section | Roof Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to drawings and to the Code of Practice.
checkpoint-status |  |  | checkpoint | All fixings in place and done according to code of practice.
checkpoint-status |  |  | checkpoint | All laps and junctions sealed properly.
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Daily Cassette Log - |  |  |  |  | Yes | Add Daily Cassette Log | a84b6c3b-a348-4bec-9d5f-6a1a65f37018
checkpoint-status |  |  | checkpoint | Date:
text | 9d2638ad-0bd1-52a6-afe6-4499e48241f7 |  | textbox
checkpoint-status |  |  | checkpoint | Cassette Number:
text | 5a3ce756-611c-5d45-825d-801573ad4ec0 |  | textbox
checkpoint-status |  |  | checkpoint | Record any delays:
text | 158cfb28-d029-5fb0-9561-46c08d5ff7fa |  | textbox
checkpoint-status |  |  | checkpoint | Wind/Weather Conditions:
text | 41a2780e-715b-50dd-a2a9-4f9d96939346 |  | textbox
checkpoint-status |  |  | checkpoint | Comments/Issues/Observations:
text | 510468be-b9e5-56f1-ba11-711d05cafa81 |  | textbox
checklist-flat |  |  | checklist | Delay Checklist |  |  |  |  | Yes | Add Delay Checklist | ae2f3b1b-388f-4fb7-99f0-18ae00f8f7f6
checkpoint-status |  |  | checkpoint | Delay details.
text | 00707f1b-bb0e-5836-92e8-85d72dca9b30 |  | textbox | Date:
text | 087bf237-5239-533c-862c-5755715c3df6 |  | textbox | Description:
text | 2434eef9-d4a2-5600-86b4-3a2bcbd02c0b |  | textbox | Area/Grids:
text | 69ca477f-4d1a-50ac-91c2-75315490c530 |  | textbox | Wind/Weather Conditions:
checklist-sectioned |  |  | checklist | Fibertite to Concrete Checklist |  |  |  |  | Yes | QA - Fibertite to Concrete Checklist | b2d72e50-5d2f-401e-932e-9b92b8c58e03
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  |  |  |  | Yes | FiberTite warm roof to CLT mechanically fixed and adhered checklist | b7f4e3f2-27dc-4ee0-be04-b383fbe4bc51
checkpoint-group |  |  | section | Pre start
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Visual inspection of substrate ready for SWP
checkpoint-status |  |  | checkpoint | QA document received from previous trade from main contractor
checkpoint-group |  |  | section | CLT Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
checkpoint-status |  |  | checkpoint | Installation of SA primer
checkpoint-group |  |  | section | Vapor control layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, free of debris
checkpoint-status |  |  | checkpoint | Z flashing installed
checkpoint-status |  |  | checkpoint | Install VCL over primer
checkpoint-status |  |  | checkpoint | VCL lapped with a minimum of 100mm side and end laps
checkpoint-status |  |  | checkpoint | Installation of SA primer
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | VCL clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | VCL has been checked for damages and repaired
checkpoint-status |  |  | checkpoint | Closure flashings installed correctly
checkpoint-status |  |  | checkpoint | Install board adhesive in specified pattern
checkpoint-status |  |  | checkpoint | Specified insualtion board installed
checkpoint-status |  |  | checkpoint | Insulation board mechanically fixed with specified ficing patter
checkpoint-status |  |  | checkpoint | Boards tightly butted
checkpoint-group |  |  | section | Tapered EPS
checkpoint-status |  |  | checkpoint | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
checkpoint-status |  |  | checkpoint | Install board adhesive in specified pattern
checkpoint-status |  |  | checkpoint | EPS board installed into adhesive
checkpoint-group |  |  | section | ILD system installed
checkpoint-status |  |  | checkpoint | ILD System installed as per specs
checkpoint-status |  |  | checkpoint | ILD test plate installed
checkpoint-group |  |  | section | HDP board
checkpoint-status |  |  | checkpoint | PIR clean, dry, free of debris prior to install
checkpoint-status |  |  | checkpoint | Install board adhesive in specified pattern
checkpoint-status |  |  | checkpoint | HDP board installed in brick pattern where possible
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Prime substrate where required
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Sumps
checkpoint-status |  |  | checkpoint | Sealant installed to dropper flange under membrane
checkpoint-status |  |  | checkpoint | Membrane dressed in to outlets
checkpoint-status |  |  | checkpoint | Clamp/rings/basket installed
checkpoint-status |  |  | checkpoint | Flood test
checkpoint-group |  |  | section | ILD report
checkpoint-status |  |  | checkpoint | ILD report
checkpoint-group |  |  | section | Fiberclad flashing
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixing and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-group |  |  | section | Pressure bar installed
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications ( right way around )
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Prime of Substrate where required
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Over flashings
checkpoint-status |  |  | checkpoint | Over flashings has a separation barrier
checkpoint-status |  |  | checkpoint | Fixings done according to specifications and details
checkpoint-status |  |  | checkpoint | Primer of Substrate
checkpoint-status |  |  | checkpoint | Sealant installed
checkpoint-group |  |  | section | Review and sign off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work completed, checked and reviewed as per specifications
checkpoint-status |  |  | checkpoint | Client/main contractor sign off
checklist-sectioned |  |  | checklist | Fiberglass System Checklist |  |  |  |  | Yes | QA - Fiberglass System Checklist | b92d6039-d15c-4552-a856-c3bf35c206c0
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Surface Prep
checkpoint-status |  |  | checkpoint | Concrete free of contaminants
checkpoint-status |  |  | checkpoint | Concrete flat and smooth
checkpoint-status |  |  | checkpoint | Bug holes in plinths filled and smooth
checkpoint-status |  |  | checkpoint | All 90deg corners chamfered
checkpoint-group |  |  | section | Membrane install
checkpoint-status |  |  | checkpoint | Install sealant angle fillets to all wall floor junctions
checkpoint-status |  |  | checkpoint | Prime surfaces with Epistixx
checkpoint-status |  |  | checkpoint | 1st body coat with 300gram fiberglass installed
checkpoint-status |  |  | checkpoint | 2nd body coat
checkpoint-status |  |  | checkpoint | 3rd body coat
checkpoint-status |  |  | checkpoint | Traxx 2000 wear coat.
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Concrete Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Concrete Checklist | be50d940-0573-4f64-918f-db7c18c69d73
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Concrete Substrate
checkpoint-status |  |  | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
checkpoint-status |  |  | checkpoint | All lumps and sharp concrete bits ground/hammered down
checkpoint-status |  |  | checkpoint | Large holes filled with grout
checkpoint-group |  |  | section | Vapor Control Layer
checkpoint-status |  |  | checkpoint | Substrate clean, dry, and free of debris
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapor control layer has been checked and no damage
checkpoint-status |  |  | checkpoint | Insulation boards installed
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards)
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer if no Securock
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length of fixing with load washer
checkpoint-group |  |  | section | Fibertite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with the welding machines
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Claps/rings/baskets installed
checkpoint-status |  |  | checkpoint | Flood/ILD tested
checkpoint-group |  |  | section | Fiberclad Flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Metal Gutter Install Checklist |  |  |  |  | Yes | QA - Metal Gutter Install Checklist | c2bddb9c-3a52-4076-a60a-4ef3b0ab721e
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Brackets installed according to plans/spec/best practice
checkpoint-status |  |  | checkpoint | Gutter lapped and sealed correctly according to best practice
checkpoint-status |  |  | checkpoint | All terminations and ends folded/sealed properly
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation Checklist | c472263b-3b85-4f61-a5c1-a33452ae6ad5
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | c660775b-1f8e-59fe-aa87-9487b676ba60 |  | textbox | Reference/Drawing/Instruction Number
text | a425f38e-e922-5f64-8bea-54bc9fb41ab1 |  | textbox | Variation Area
text | c43010e2-b9ce-5d0c-b6b3-95b950f90f84 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-sectioned |  |  | checklist | Sheet Tanking System Checklist |  |  |  |  | Yes | QA - Sheet Tanking System Checklist | ca40238a-1dfc-4a78-bd44-57dc25a960f7
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Primer
checkpoint-status |  |  | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Temperature must be over 4 degrees for membrane install
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear
checkpoint-status |  |  | checkpoint | Membrane applied with min 50mm overlap
checkpoint-status |  |  | checkpoint | Overlap is to pressure applied or rolled for seal
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Works to be protected by main contractor
checklist-flat |  |  | checklist | Final inspection |  |  |  |  | Yes | Add Final Inspection Checklist | e3ef2f53-a6d1-49be-91a2-bf68310253af
checkpoint-status |  |  | checkpoint | Final inspection
text | 410107a2-943a-552b-aaa2-e81aa6649488 |  | textbox | Date
text | a351a905-8cb2-5279-8cf0-6ff70b0e43ad |  | textbox | Area/elevation/grids
text | a475ce2b-e456-5265-b02c-8a4944ed39b7 |  | textbox | Description
label | 34635029-703b-548c-a694-3b58803e695b |  | note | Attach Photos
holdpoint |  |  | signoff | Request Signature Signoff
checklist-sectioned |  |  | checklist | Metal Cladding Install Checklist |  |  |  |  | Yes | QA - Metal Cladding Install Checklist | ef890509-62a0-4d3f-bb21-f7d42743af0b
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Install
checkpoint-status |  |  | checkpoint | Bottom flashing installed straight/level all the way around
checkpoint-status |  |  | checkpoint | Building wrap installed
checkpoint-status |  |  | checkpoint | Flashing tape installed (check plans)
checkpoint-status |  |  | checkpoint | Soaker flashings installed
checkpoint-status |  |  | checkpoint | Cladding installed plumb and straight
checkpoint-status |  |  | checkpoint | Screw pattern according to plan/spec/best practice
checkpoint-status |  |  | checkpoint | Flashings installed as per specification
checkpoint-status |  |  | checkpoint | Closure foams installed
checkpoint-status |  |  | checkpoint | Fixings installed correctly
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off
checklist-sectioned |  |  | checklist | Fibertite Warm Roof Over Metal Deck Checklist |  |  |  |  | Yes | QA - Fibertite Warm Roof Over Metal Deck Checklist | f8db6aec-e9e9-40f1-9b40-4d6abdb333f1
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Substrate complete and ready for SWP
checkpoint-group |  |  | section | Metal Deck
checkpoint-status |  |  | checkpoint | Timber to have separation barrier
checkpoint-status |  |  | checkpoint | Base deck screwed down in every pan
checkpoint-status |  |  | checkpoint | Sheet edges stiched together at 300mm centres
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Is the substrate clean, dry and clear of swarf
checkpoint-status |  |  | checkpoint | All areas covered and sheets lapped 50mm
checkpoint-status |  |  | checkpoint | All holes/penetrations patched and water tight
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Surface is dry prior to install
checkpoint-status |  |  | checkpoint | Vapour control layer has been checked for no damage
checkpoint-status |  |  | checkpoint | Insulation board installed in a brick pattern
checkpoint-status |  |  | checkpoint | Joints flush (no gaps between boards on ends)
checkpoint-status |  |  | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
checkpoint-group |  |  | section | Securock
checkpoint-status |  |  | checkpoint | Is the surface dry
checkpoint-status |  |  | checkpoint | Installed in brick pattern
checkpoint-status |  |  | checkpoint | Correct length screw with load washer
checkpoint-status |  |  | checkpoint | Installed as per wind uplift fixing plan
checkpoint-group |  |  | section | FiberTite
checkpoint-status |  |  | checkpoint | Adhesive installed to substrate
checkpoint-status |  |  | checkpoint | Laying of membrane into the adhesive
checkpoint-status |  |  | checkpoint | Broom/rolling of membrane
checkpoint-status |  |  | checkpoint | Wipe and clean of laps prior to welding
checkpoint-status |  |  | checkpoint | Test weld with welding machine
checkpoint-status |  |  | checkpoint | Probe of seam with QA hook
checkpoint-status |  |  | checkpoint | Membrane dressed into drains/outlets
checkpoint-status |  |  | checkpoint | Clamps / rings / baskets installed
checkpoint-status |  |  | checkpoint | Flooded / ILD checked
checkpoint-group |  |  | section | Fiberclad flashings
checkpoint-status |  |  | checkpoint | Installed correctly according to specifications (Right way around)
checkpoint-status |  |  | checkpoint | Fixings and welding done according to specifications and details
checkpoint-status |  |  | checkpoint | Probe of weld with QA hook
checkpoint-group |  |  | section | Review and Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | All installation work complete, checked and reviewed as per specification
checkpoint-status |  |  | checkpoint | Client / Main Contractor sign off