## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 2fbadff5-3e88-44c3-82fe-45a4385df5b1 |  | checklist | AES Fit Off |  |  |  |  | Yes | AES Fit Off | 57661fcc-617c-49c7-834c-17237ab657a4
checkpoint-status | ab9befa1-48dc-4e4a-8a6c-d6a2a60bc066 |  | checkpoint | Equipment fitted off and tested
checkpoint-status | 5c6f2580-c9ef-492f-aa43-0277abeddd97 |  | checkpoint | Wall Controller installed
checklist-flat | bb5ee51f-5619-49ef-b1b9-ab7330b970a8 |  | checklist | Statewide Fit Off |  |  |  |  | Yes | Statewide Fit Off | 605b991e-c5e7-45c7-a161-ba502d54e8b9
checkpoint-status | 66020886-19e2-42fe-ba47-dcc982f9b0ea |  | checkpoint | Grilles cut out completed
checkpoint-status | 2f97866b-bf92-43d2-87bb-a8b76a923ce5 |  | checkpoint | Grilles fit off and installed correctly
checkpoint-status | 7125c2b7-ba3b-4b9f-ade5-9574083b1ce9 |  | checkpoint | Fans fit off, powered and set to medium speed
checkpoint-status | e1a4aac5-3a45-44ad-befb-8bf519c3ae1b |  | checkpoint | Access panels installed at Fan
checkpoint-status | 5dc10968-fa45-4aad-9039-5bc34cf1e498 |  | checkpoint | Rangehood installed / flex connected to Rangehood
checklist-flat | cba34eda-5b50-4faf-9480-66c1b81a1037 |  | checklist | Statewide Rough In |  |  |  |  | Yes | Statewide Rough In | 619ed7b2-6a1c-4611-900f-17a85e1b8379
checkpoint-status | 6b9cb63d-b80f-461d-8db5-d36c54f0ac39 |  | checkpoint | PVC, flex duct & In-line Fan installed and correctly fixed
checkpoint-status | 9ba32893-7a3e-4e8a-821c-7fd9c1d97ba2 |  | checkpoint | Cushion box installed to external louvers and duct connected & correctly sealed
checkpoint-status | 3c22745b-2274-41d3-afec-bc868fc9bd91 |  | checkpoint | Rangehood droppers installed
checkpoint-status | 3e31a927-53ec-4e77-b58c-03621d1e7e6b |  | checkpoint | Access panels marked on floor
checklist-flat | c17802dc-fcda-4127-b6f6-124a1ce5c369 |  | checklist | Auscool Commissioning |  |  |  |  | Yes | Auscool Commissioning | 9cf29486-0e5d-4fd8-8098-9cb7e8082b1c
checkpoint-status | 3d564fbd-be26-4b7b-8c9a-c77c2aa332d9 |  | checkpoint | Test and record air flows and ensure correct operation
checkpoint-status | 128a445a-b0bb-496f-8feb-8fe5620631bd |  | checkpoint | Check and test for any noise, vibrations etc and rectify
checkpoint-status | d1a0d18f-76fb-4930-8276-e1447c014ddb |  | checkpoint | A/C units pressure tested to 3500Kpa
checkpoint-status | 8558664e-2f94-4bc6-9efe-3b97136bb359 |  | checkpoint | A/C refrigeration valves opened and A/C tested
checkpoint-status | 4980cb9c-cc2e-4360-9e8a-92cdac929a9a |  | checkpoint | Clashes with other services
checkpoint-status | 07407234-20f9-4197-8edf-b8a39aca4564 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | d1738640-a560-4524-8edc-2908ba18ace9 |  | checklist | Auscool Fit Off |  |  |  |  | Yes | Auscool Fit Off | bd56a094-866c-4093-9578-c7a79dcbdbc9
checkpoint-status | dc881d87-d7e0-479f-a077-c990058f08b4 |  | checkpoint | Indoor unit fit off and installed correctly
checkpoint-status | 09b7b0a9-8a7c-451e-b46a-e3e7a2624637 |  | checkpoint | Grilles cut out completed
checkpoint-status | 87a372d4-f2a9-438e-8d17-f22625ee3ac5 |  | checkpoint | Grilles fit off and installed correctly & B/fly dampers left open
checkpoint-status | 7db7c1f6-494e-47b0-9caf-3c285c288645 |  | checkpoint | Access panels installed
checkpoint-status | cb229631-39b0-4815-9c99-2621f24dedb3 |  | checkpoint | All drains fit off and tested
checkpoint-status | c4c80a8c-ccc0-4ec4-a53b-442a3d4f7890 |  | checkpoint | Condenser unit fit off, pipes and wires sealed and capped where required
checkpoint-status | 64e99cd1-5a79-4804-9158-db9f54897fd6 |  | checkpoint | Condenser labels Installed
checkpoint-status | 1f210a5d-aebc-4417-a8e8-06bfccf59e07 |  | checkpoint | Builders works complete
checkpoint-status | 9b7b607d-d2c8-454f-9f34-58f90b11f5d2 |  | checkpoint | Clashes with other services
checkpoint-status | 6b9f66fa-c241-4d4b-919c-7e808a7f97cf |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 1b30f145-9a79-4e9c-9708-19a1db227a41 |  | checklist | AES Rough In |  |  |  |  | Yes | AES Rough In | dc6650b1-bd62-4a6f-97e3-533538cc8fea
checkpoint-status | 8b3575df-5c6e-499d-b5c0-74946c57bc95 |  | checkpoint | Electrical cables roughed in and correctly clipped
checkpoint-status | 4e375bb3-4560-4e45-ac38-e4b6999d2285 |  | checkpoint | Wall Controller cable roughed in
checkpoint-status | 4c6756da-4dca-4635-8536-2521d09dd7dc |  | checkpoint | Wall penetration Fire caulking completed and fire penetration labelled / documented.
checklist-flat | d9e7dacc-72bc-4faa-b14e-85b01c10240d |  | checklist | Auscool Rough In |  |  |  |  | Yes | Auscool Rough In | fb8008ad-a13b-496f-9f4c-c87405ef1a12
checkpoint-status | 8104ac74-0e8c-4c12-8a01-57f39c15a837 |  | checkpoint | Ducted AC unit installed c/w isolation mounts & filters
checkpoint-status | 695a43f3-0e41-48d2-aacc-7140ae51cc10 |  | checkpoint | Living & Bedroom cushion boxes & flex duct installed
checkpoint-status | 3eab44ce-e0cc-4d22-bcf3-9b80419cdf0c |  | checkpoint | Access panels marked on floor
checkpoint-status | e60fb31e-4441-467e-8774-8c170f5a2eea |  | checkpoint | Refrigeration pipes roughed in and installed to common riser
checkpoint-status | eb23b21b-eae0-4e25-a335-f00179a41217 |  | checkpoint | Drain pipes roughed in and Terminated internal tundish
checkpoint-status | bc2e62cc-90a6-46e7-bdda-609af80aba37 |  | checkpoint | Wall penetration Fire caulking completed and fire penetration labelled / documented.
checkpoint-status | 303255e2-94f2-4832-b1a6-9477e864c636 |  | checkpoint | Pressure testing of Refrigeration pipework complete